Annual Review - Summary Sheet

Title: Promoting Inclusive Markets in Somalia (PIMS)
Programme Value: £15M (DFID contribution - £13M and DANIDA - £2M)		Review Date: July 2017
Programme Code: 204157	Start Date: June 2014	End Date: April 2018

Summary of Programme Performance
Year	2015	2016	2017
Programme Score	B	A	A+
Risk Rating	Medium	Major	Major

Summary of progress and lessons learnt since last review
The Promoting Inclusive Markets in Somalia (PIMS) programme contributes to private sector development and job creation in key sectors/value chains important to the economic lives of the poor and marginal communities in selected regions of Somalia. PIMS supports the establishment and/or strengthening of input and product markets for small producers, entrepreneurs, and consumers and rehabilitating critical market infrastructure in identified value chains – livestock (including dairy), fisheries and food crops (including sesame).

Overall Assessment
As summarised below, PIMS has performed well in terms of reaching small holder farmers, including in hard-to-reach regions, and businesses involved in improving the input and product markets, industry knowledge and practices, and catalysing private sector investment. This performance has been achieved especially in the context of a prolonged drought situation in Somalia over the past six months. This Annual Review has awarded an output score of “A+” which means the programme outputs have moderately exceeded expectations. Planning and delivery of the programme’s activities in the livestock, dairy and sesame sectors have faced a slowdown following the extensive drought. This slowdown in activities will delay results and absorption of the allocated budget in the final year.

These results, therefore, should be taken with caution. Firstly, the programme has very ambitious targets, with most outputs and outcome targets expected to increase manifold, in the final year (2018). Secondly, the prolonged drought means missed cropping season(s) and consequently a backlog of outcome level results, especially those related to income, investment and jobs from the rain-dependent value-chains e.g. sesame and diary industries. Finally, the programme is expected to absorb more than half of the allocated budget in the final year which now looks challenging because of the drought.

Summary of progress
PIMS has performed well during this review period. Highlights include:

The programme has provided better inputs, expert knowledge and market information to over ten thousand small-holder farmers and micro businesses that are considered critical building blocks for private sector development (PSD) in Somalia. It has helped enhance industry knowledge and practice, by providing information and technical knowledge relating to use and availability of better inputs (e.g. high-yielding seeds, fertilisers suited to the soil quality, and animal feeds, medicines and vaccination).

PIMS has partnered with 19 lead agri-business firms, exceeding the target by over three times. These firms are supported by the programme to work with identified farmers to pilot test new production techniques and inputs. Results from the pilot tests are then communicated to other small-holder farmers to encourage them to adopt new production techniques and inputs. The entire process from organising pilot tests to scaling-up is time intensive.

PIMS has leveraged additional investment of £1.7m, more than two times the target, from the partner lead firms who have made this investment in acquisition of new farm equipment and machineries, purchase of cultivatable land, and construction of warehouses and stores etc.

The programme has done well in using Cash for Work (CfW) in creating durable assets yielding long-term economic benefits. For example, the programme rehabilitated 57KM of canal irrigation, thus opening up nearly 2,300 Hectares of new farmland for sesame, maize and other crops. The programme has also rehabilitated 2,700 Ha of grazing land areas which is expected to provide fodder to at least 7,000 camels during the 90 day dry spell. Likewise, spots repairs and construction of Irish crossings (low water level crossing bridge) under the programme, has helped small milk producers to have uninterrupted access to milk markets, thus saving income lost by the farmers to milk spillage and spoilage.

Whilst the programme has done well in reaching the farmers with better knowledge, inputs and access to markets, and catalysing investments from the partner lead firms, the programme’s impact on generating additional income for the farmers and businesses has been less than commensurate because of the extensive drought. The programme has therefore missed the income target by far.

Main issues or challenges faced
The on-going drought remains the single most important challenge facing the programme. A majority of the target value-chains and sub-sectors rely on a stable climate. The Food Security and Nutrition Analysis Unit - Somalia (FSNAU) and Famine Early Warning Systems Network (FEWS-Net) assessment of elevated risk of famine remain unchanged over March - June 2017. Food and Agriculture Organisation (FAO) Somalia has reported heavy rainfall and flooding along the middle and lower reaches of the Shabelle River. In the worst case scenario this could mean one more missed or bad cropping season because of weak or heavy rains, and consequently a backlog of results, especially those related to income and jobs from the farm related value-chains e.g. sesame and diary.

Key lessons learnt
Don’t rush in, and allow sufficient time for demonstration effects to materialise: Market development programmes are time intensive. This is because: firstly, design of market development interventions requires a detailed diagnostic for granular understanding of how the key actors and markets operate and what are the main binding constraints on market development. Preparing such a diagnostic is time and resource intensive, especially in difficult environment where market systems are weak and complex. Secondly, mobilising the strategic skills and expertise needed takes time and can be challenging, especially in a weak supplier market. Thirdly, systemic change takes time. For example, farmers and producers need hard evidence before they can be persuaded to adopt change. Therefore pilot-testing of new technologies and practices is essential for effective uptake. Thirdly, the real economic benefits of job creation and investment happen through demonstration effects and increased adoption of change. Market development programmes, therefore, need additional time, after the interventions have been made, to better capture the impact and results.

Don’t throw out the middlemen: The middlemen (e.g. intermediaries/traders/brokers) can usurp a disproportionately larger share of the profits, especially when they have a monopoly. This notwithstanding, middlemen can also serve as worthwhile financial and technical facilitators in the overall production process. They are an integral part of the production and distribution chain and are key to driving adoption of change. Engaging with relatively large businesses operating in the target value chains is critical and can yield better value propositions for all actors across the value chain, including small producers. For instance, by engaging with the lead firms, PIMS is able to leverage on their technical, financial and managerial expertise and experience. The lead firms are already engaged in the value-chains, have a better understanding of the incentives of the various actors. They are in a better position to drive change. Cost sharing has been important in ensuring greater ownership and hence sustainability of the programme outputs. Direct engagement with the programme, has also enabled the lead firms to understand the programmes value propositions better which has encouraged them to make more investment. Engaging local firms has also helped manage the conflict dynamics.

Make smart use of subsidy to stimulate markets: Well targeted subsidy can stimulate markets with sustainable economic benefits to consumers as well as producers. For example, limited support provided through training of Community Animal Health workers (CAHWs) and Agro Vet Dealers (AVDs) engaged by Alla Aamin and VetCare (PIMS’ lead firms in the veterinary drug intervention) has helped expand the market of veterinary drugs and vaccination by an estimated 25%. Equally, too much of a subsidy can undermine market developments. For example, the prolonged drought in Somalia has necessitated humanitarian assistance, including free distribution of drugs, seeds, vaccinations etc. The impact of the humanitarian response on markets needs to be analysed further. The implementing partner, DAI, believes that this may have discouraged some market actors to make their own investments in PIMS supported interventions.

Key recommendations:

A one year no-cost time extension:
DFID should seek an extension of the programme duration to ensure that the output indicators are compensated for the time lost to the drought to realise targets and ample time to measure impact. The drought has severely affected PIMS’s key production sectors i.e. sesame, dairy and livestock necessitating DAI to scale down interventions in those value chains. The FEWS-NET’s assessment of elevated risk of famine remained unchanged over March-June 2017. Therefore, there is a genuine risk that the programme’s planned interventions will be unable to run full course. And even if they do, their impact on jobs, income and investment will not be fully felt and/or captured by the time of the scheduled end of the programme in April 2018. A time extension will help (a) the programme scale up interventions if the rain situation improves or reorient its interventions if the drought persists, and (b) allow additional time for lesson-learning and evaluations to better capture the impact of the programme interventions. Following approval of this AR, DFID team will prepare the documentations for necessary approval for the time extension consultation with DAI. (Action: DFID team in consultation with DAI by August 2017).

Based on DFID team’s initial discussions with the DAI on potential time extension, it is expected that the increase in DAI’s management cost due to the proposed extension will be minimal. This is because (a) a good portion of the extended time will be used in capturing results and therefore can be done with reduced staffing and (b) the cost saved in scaling down of activities during the drought can be reallocated to meet the cost of extended time. (Action DFID and timing by August 2017).

Summary of progress made in addressing the last annual review report’s (2016/17) recommendations:

Below is a summary of progress made in addressing recommendations from the last annual review. A full list is attached as Annex 1:

R1: The implementing partner (DAI) should continue to undertake rigorous and regular political economy analysis (PEA) at the market level.
PIMS has embraced continuous Political Economy Analysis (PEA) in the choice and sequencing of interventions. For example, PEA is used in the PIMS Fisheries Strategy paper and the Dairy Subsector Strategy and Beneficiary and Partner Selection Criteria. PEA also informed the selection of infrastructure assets and demonstration plots in the sesame sector to avoid conflict.
R2: Re-assess timescale for PIMS results.
The PIMS log frame was revised in December 2016 with adjustments made to the milestone targets; new targets were discussed and agreed with DFID, DAI and Danida.
R3: PIMS should undertake end user market testing
PIMS has pilot-tested improved technologies and practices among its target beneficiaries to obtain buy-in. In promoting the usage of improved sesame seed varieties and adoption of better agronomic practices to improve yields, PIMS conducted varietal trials with its lead firms setting up 50 demonstration plots to show-case better agronomic practices to smallholder sesame farmers.

A. Introduction and Context

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204157/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204157/documents

Outline of the PIMS Programme
PIMS was set up in June 2014 to address critical market constraints in Somalia largely through direct support to firms, market actors and service providers and create jobs.
The purpose of this project is to contribute to private sector development by driving productivity, livelihood and job creation in value chains important to the economic lives of the poor and marginal communities in selected regions of Somalia.
PIMS aims to do this by supporting establishment and/or enhancement of input and product markets for small producers, entrepreneurs, and consumers in identified value-chains – livestock (including dairy), fisheries and food crops (sesame). PIMS provides expert information to help better integration of the market actors and systems within and across the targeted value chains. It complements this by providing knowledge and training to producers in adopting high-yielding inputs and more efficient production techniques. PIMS supports the improvement of existing/restoration of irrigation systems (e.g. removing deposit of mud to allow better flow of water ) to provide access to small farmers to more reliable supply of water at relatively lower rates than hitherto. PIMS also supports rehabilitation and improvement of defunct market infrastructure e.g. roads and market centres to link producers to consumers.
PIMS is implemented through a private sector implementing partner, DAI (Development Alternative Initiative). PIMS largely sits outside government systems, whilst constraints relating to policy and regulations afflicting the markets are addressed by other complementing programmes in DFID Somalia’s Economic Development Portfolio.
PIMS is co-funded by DANIDA who have contributed £2m (19 million Danish Krone equivalent) through DFID.
PIMS had a delayed start because of the challenges surrounding mobilisation of the programme management and implementation team in the difficult operating environment of Somalia and the need for a cautious and adaptive approach for better risk management, including reputational and financial risks.

## B: PERFORMANCE AND CONCLUSIONS

The outcome statement for PIMS is that “Improved industry practices and market systems in the targeted value chains, catalysing private sector investment and sustainable jobs”. This is measured by the following indicators:

Outcome Indicator	Baseline	Milestone Target 2017	Achieved by May 2017	Comment on milestone indicator
% of surveyed firms reporting income increases per year and cumulatively	0%	20%	21%[1]	Target met. Progress could have been better but for the impact of drought e.g. none of the milk producers recorded an increase in income thus dragging down this indicator.
Net additional income (NAI) for the small scale producers and entrepreneurs	0	£ 3,000,000	£218,462[2]	Target missed. The prolonged drought has severely affected production in PIMS supported sectors and this has resulted to limited increment in NAI. / Nearly half of the increase in NAI has come from expansion of markets of animal drugs and vaccinations.
Net additional full time equivalent (FTE) jobs created and/or sustained for low income Somali individuals in the target value chains	0	500	582[3] of which 40% are women (934)	Target met. Additional FTE jobs expected from the on-going implementation work.
Value of follow on private sector investment in the target value chains	0	£ 800,000	£1,702,869 [4]	Target exceeded. An additional £ 4M+ investment expected to be leveraged from the on-going negotiations following the B2B event.
[1] 107 out of 516 sampled beneficiaries (including the lead firms) supported by PIMS reported to have had increased incomes. 27% of the sesame producers, 43% AVDS/CAHWs and 0% milk producers (91% of the milk producers reported to have lost their animals due to drought)
[2] The supported 11 AVDS increased their sales of Vet drugs from an average of $ 180 per month to $ 466 per month. Most of the sales were from animal feed supplements. 38 of the supported CAHWs increased their revenue from $ 1.5 per day to $ 4 per day. The CAHWs work on average of 25 days/month. (Conversion rate 1 USD=0.81 GBP). PIMS is also finalising its multiplier methodology based on ILO conventions, so this will be factored for 2018.
[3] These are total full time and part time jobs converted to FTEs based on our methodology including jobs created by the construction companies engaged in the CfW (machine operators, site supervisors, security guards etc.-all converted to FTEs based on the # days worked)
[4] These are actual investments made by the industry players (these include acquisition of new farm equipment/machineries, purchase of cultivatable land, construction of warehouses/stores etc.)

PIMS has performed strongly despite the ongoing drought situation in Somalia. PIMS exceeded expectations in achieving targets for two of three outcome indicators for the year in review. However, Outcome 2 (Net additional income (NAI) for the small scale producers and entrepreneurs) missed it achieving 7% of the set milestone target. With PIMS’s interventions being largely production (livestock and agriculture) based, the prolonged drought did have adverse effects on the anticipated results/milestone targets as evident with Outcome 2. The drought situation stifled both profits and growth for businesses and therefore undermined the ability to create jobs.

This year’s relatively good performance should be interpreted with caution. As the full impact of the drought gets realised over time, the programme’s ambitious targets for the final year will become even more challenging to achieve.

 Overall output score and description: A+ - Outputs moderately exceeded expectation
The programme moderately exceeded its milestone targets for all four Outputs thus, scoring an “A+” . The following table shows the scores for each Output.

Output	Impact Weighting	Performance		Risk
1. Improved market information flow and industry practices paving the way for private sector investments in the target value chains.	25%	A+	Outputs moderately exceeded expectation	Major
2. Improved access of producers, traders and consumers to market opportunities in target value chains	25%	A+	Outputs moderately exceeded expectation	Major
3. Community and market infrastructure assets rehabilitated to link small producers, input suppliers, traders and consumers to markets in the target value chain	15%	A+	Outputs moderately exceeded expectation	Major
4. Improved technical capacity of small scale producers and entrepreneurs for enhanced productivity and value chain development	35%	A	Outputs met expectation	Major

Has the log frame been updated since the last review?
Yes, the log frame was last updated in December 2016. This was done through a process involving the DFID, Danida, DAI and results experts from DFID’s cross-office Accountability and Results Team (ART in Nairobi and the third party independent monitoring agency (LAMPS). In the revision, the output and outcome statements were refined and sequenced for more clarity to reflect PIMS’ overall Theory of Change.

The programme’s outcome and output indicators for 2018 were revised upwards to address the increase in programme delivery funds by £3m (refer to Annex 1). Given the persistent drought, it is advisable to re-visit the log frame post annual review to review the outcome and output indicators for 2018.

## C: DETAILED OUTPUT SCORING

Output Title	Improved market information flow and industry practices paving the way for private sector investments in the target value chains.
Output number per LF		1	Output Score	A+
Risk:		Major	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Y (previously 30%)

Indicator(s)	Milestones	Progress	Indicator score
1.1 Number of investment promotion events and/or negotiations initiated between business and private sector investors or financial service providers as a result of PIMS profiled investment opportunities and improved business practices	6	6	A
1.2 Number of regulations specific to PIMS value chains reviewed/revised and/or drafted against the principles of good regulations	3	3	A
1.3 Number of lead firms, businesses and business associations assisted to improve their business management practices	6	19	A++

Key Points
- The lead firms play an important role in pilot-testing and propagating new inputs and production techniques. The programme’s success in partnering with a significantly greater number of lead firms than anticipated has helped in expanding the programme’s outreach to a large number of small farmers including in difficult to reach regions. The programme has assisted 19 lead firms with training and small financial support in expanding their outreach to small-holder prodicers. These lead firms in turn have worked with small producers e.g. in pilot-testing new varieties of seed, animal drugs and vaccinations etc. The programme also supports the lead firms in disseminating results of the pilot tests and scaling up adoption of better production practices by larger number of small producers. PIMS partnered with the USAID’s GEEL programme to run business management training, during the PIMS-organized out grower Management training workshop (March 31 – April 8, 2017) in Kenya.
- PIMS organised 6 investment promotion events, including Business to Business investment promotion forum in Hargeisa in February 2017. This attracted 19 international companies and 243 local and regional companies. A number of business opportunities were identified from the event and negotiations are on-going.
- PIMS implementing partner, Somalia Agricultural Technical Group (SATG) has, together with the Somalia Ministry of Agriculture, reviewed the Seed Policy Document in Somalia. Once approved and enforced, the policy will enable farmers, seed growers, and inputs/seed suppliers to produce and sell certified seeds.
- PIMS, in partnership with the Heritage Institute for Policy Studies (HIPS) has engaged policy experts to review the livestock and fisheries policies, legal and regulatory environment and identified gaps that exist. These experts will identify entry points for the PIMS programme to support with the regulatory environment.

Summary of responses to issues raised in previous annual reviews (where relevant)
In the last annual review, it was recommended that the PIMS’s team engage more actively with similar programmes in comparable contexts to learn from best practice elsewhere, and to inform PIMS’s implementation. PIMS has engaged with similar market development programmes especially the Kenya Markets Trust programme. Lessons learnt will help improve the business professionalism of the lead firms and producer associations. PIMS is equally working very closely with the Somali Business Catalytic Fund (SBCF) and Small-Medium Enterprise Facility (SMEF) projects which are part of the World Bank’s Somali Core Economic Institutions and Opportunities Program (SCORE) seeking to build on complementary approaches.

Recommendations
- PIMS should focus on a sustainability approach ensuring the lead firms, businesses and business associations supported under PIMS are able to increase their commercial sustainability.
- Lead firms require more support to improve their strategic skills and expertise. PIMS has engaged the “market leaders” as lead firms with incentives to broaden market access and inclusivity. The lead firms require more support to deliver the required inputs.

Output Title	Improved access of producers, traders and consumers to market opportunities in target value chains
Output number per LF		2	Output Score	A+
Risk:		Major	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Y (previously 30%)

Indicator(s)	Milestones	Progress	Indicators score
2.1 Number of business linkages facilitated between small scale producers/entrepreneurs and input suppliers and/or buyers	20	26	A+
2.2 Number of processors/exporters assisted to meet requirements of end market buyers	10	18	A++
2.3 Percentage of small scale producers/entrepreneurs and processors/exporters who perceive PIMS support to be appropriate and effective	75%	78[5]%	A
[5] Results of the perception survey conducted by Forcier, 78% of sesame producers perceive PIMS interventions to be appropriate; 76% of milk producers perceive the interventions to be appropriate and suitable to their needs

Key Points
PIMS is providing technical support, training and market linkage support thus moderately exceeding the respective target milestones for all the three output indicators.
- Following the PIMS’s business to business event held in February 2017 in Hargeisa, PIMS facilitated 26 business linkages between buyers and sellers of produce/inputs and businesses operating at the different segments of the value chain. Four (4) sesame exporting companies (Danwadaag, Al Mizan, HornAfric and Asma Trading) were linked to new suppliers, agro-input dealers and extension workers. Seven (7) business linkages were facilitated between fish exporting companies and fish suppliers including linking Yustan, a fish exporter to Ethiopia, to small local Somalia companies (Shewa, Barfisco and Al Naciim) from whom they are currently buying seafood to meet the growing market demand of fish in Ethiopia.
- PIMS organised a fertiliser market development workshop and through the event, PIMS implementing partner SATG was linked to ETG Group, Africa’s largest fertilizer importer and distributing company based in South Africa. SATG has been able to import two containers valued at £31,200 of fertilizer from ETG to be sold to farmers in Somalia.
- PIMS has provided a comprehensive training package to 10 trainees on milk hygiene, improved milk containers and milk preservation in order to meet domestic end-market requirements. This was conducted by the PIMS Lead Firm, MCC, a women-owned milk hygiene and marketing company in Somaliland.
- PIMS is training 9 fishing companies; Suudi, Sundus, Cafco, Red Sea, Sanaag, Bille, Raasi Axmar, Danwadaag fishing company and Fanax fishing companies in Puntland on fish end-market requirements – giving both practical and theoretical technical support – to meet both local and international end market fishing standards and practices.

Summary of responses to issues raised in previous annual reviews (where relevant)
The last annual review recommended that the log frame be revised to better demonstrate the link and sequencing of this output with other outputs while ensuring the milestone targets are realistic.

PIMS has structured the deal agreements with its lead firms in such a way that the lead firms engage the service providers to provide technical assistance to smallholders to improve productivity (rather than the project engaging the service providers). This strengthens the ties between the lead firms and the process of capacity building. These changes have been captured in the log frame which was revised in December 2016. The PIMS methodology note has also been revised to ensure the programme monitors additional results emanating from the crowding-in effect including conducting annual farm/enterprise surveys.

Recommendations
- DFID should seek an extension of the programme duration and revise its log frame accordingly to ensure that the output indicators are accorded more time to realise targets and ample time to measure impact.
- PIMS needs to evaluate the sustainability and effectiveness of the support provided to the supported enterprises.

Output Title	Community and market infrastructure assets rehabilitated to link small producers, input suppliers, traders and consumers to markets in the target value chains.
Output number per LF		3	Output Score	A+
Risk:		Major	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Y (previously 25%)

Indicator(s)	Milestones	Progress	Indicator score
3.1 Number of critical community market and value chain infrastructure rehabilitated and functional	See below	See below	A+
	3 Km road	4.5 Km completed	A+
	2 Irish crossings (low-water crossing or bridge).	2 Irish crossing done	A
	Prioritization of irrigation canals completed	18 irrigation canals prioritized; 30Km of the identified canals rehabilitated
	500 Ha grazing land areas rehabilitated e.g. by planting of grass and fencing.	900 Ha grazing land areas rehabilitated.	A++
3.2 Number of new infrastructure Cash For Work (CfW) days for low income Somalis	90,000 (70% youth; 30% women)	98,702 (59% youth; 35% women); 143,000 CfW days expected by end of May.	A+
3.3 Number of existing and new local management committees/user associations with improved organisational capacity to manage sustainable asset maintenance.	6	Capacity needs of over 18 asset user groups assessed. Of these, 10 asset user groups have already been trained in maintenance of community assests. The programme needs to design a methodology for assessing the organisational capacity of the groups trained.	A+

Key Points
- The Cash for Work (CfW) sub-projects are on track. The CfW activities have been ramped up partially in response to the impact of the drought situation in Somalia. PIMS has rehabilitated 4.5KM of the identified milk feeder roads in Habale and one Irish crossing located in Dhobolog has been completed.
- Over 98,700 employment days (59% youth; 35% women) have been generated with the rehabilitation of the 4.5KM milk feeder roads in Habale and the Irish Crossing located in Dhobolog. The prolonged drought had an impact on the anticipated success of the projects lower results realised with most of the youths migrating with their livestock in search of pasture.
- PIMS has contracted three companies to rehabilitate 18 irrigation canals that could potentially open up more than 2,400 Ha of new farmland. To date, 30 Km of the identified canals have been rehabilitated generating more than 60,000 CfW days for 3,500 low income Somalis.
- 300 Ha of grazing land areas in Puntland have been rehabilitated through planting of grass and fencing and an additional 600 Ha is expected to be completed by end of May 2017.

Summary of responses to issues raised in previous annual reviews (where relevant)
The previous annual review recommended that the infrastructure interventions be reviewed to ensure they are appropriately targeted and relevant for the end user markets. It also advised that the key terminologies around infrastructure assets and the financial/social impact of the infrastructure interventions be clearly defined.

The programme has done an in-depth community led selection and prioritisation of the CfW sub-projects to ensure they resonate with the community needs. For instance, the milk routes and Irish Crossings for rehabilitation were selected based on the volumes of milk lost as a result of delays in milk delivery as reported by the milk transporters, traders and milk producers.

PIMS has defined the infrastructure assets to be rehabilitated and the potential impact on market development. The assets to be rehabilitated include: (a) spot improvement of milk feeder roads (3km) which will reduce milk delivery time from 2 hours to about 1 hour (this will reduce milk spoilage during transportation by about 10% and reduce the maintenance costs on the vehicles, reducing transactions costs) (b) irrigation canals - 30km which will open up new farm lands of up to 2,400 Ha. This will create over 3,000 FTE jobs and (c) grazing land areas -1,600 Ha which will enable livestock keepers’ access fodder during the dry spell. This will maintain and possibly increase milk productivity resulting in increased income.
Recommendations
- DAI to improve its monitoring processes and reports to collect inclusivity data on different categories of beneficiaries.
- DAI should continue to undertake rigorous and regular political economy analysis (PEA) at the market level to inform the selection of infrastructure assets to be rehabilitated.

Output Title	Improved technical capacity of small scale producers and entrepreneurs for enhanced productivity and value chain development
Output number per LF		4	Output Score	A
Risk:		Major	Impact weighting (%):	35%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Y (previously 15%)

Indicator(s)	Milestones	Progress	Indicators score
4.1 Number of lead firms investing and providing technical assistance to small scale producers/entrepreneurs in target sectors via demonstration plots and/or extension services	12	13	A
4.2 Number of Service Providers engaged by lead firms to deliver technical capacity building to small scale producers/entrepreneurs	125	143	A+
4.3 Number of small scale producers, input suppliers and entrepreneurs who receive PIMS capacity building support to improve productivity, skills and technologies and/or business practices.	8,000 (50% women)	10,083 (36% women)	A+
4.4 Percentage of target producers and entrepreneurs who perceive PIMS supported interventions to be accessible, affordable and suitable.	60%	64%	A

Key Points
- PIMS has moderately exceeded the milestone targets of Output 4 indicators. PIMS has reached 10,083 smallholder producers and entrepreneurs with improved production practices and technologies with 5,112 of the beneficiaries in the sesame sector, 4,849 in the dairy sector and 122 in the fisheries sector. It is worth noting that the firms offering crop production support services were severely challenged in their efforts by the prolonged drought situation.
- Across the three value chains, PIMS engaged with market leading companies to pilot and test new approaches through signing of deal notes. The adoption of new approaches by providers leads to growth, with the expectation that interventions will be copied by other firms and replicated throughout the sector. This overarching pattern will exhibit how the wider systemic change can occur and continue to develop.
- 13 lead firms supported by PIMS have jointly invested to offer technical assistance to smallholders to improve productivity and competitiveness. The lead firms, selected through a rigorous due diligence process are fairly distributed across the three sectors and regions (i.e. 4 in dairy sector, 4 sesame sector and 5 in the fisheries sector). These lead firms have the potential to create the greatest impact to the smallholder producers who remain PIMS’s main target group. The lead firms have committed to cost share in PIMS’s interventions to a tune of £1.1m against PIMS investment of £1.1m (cost share ratio of 1:1)
- The 13 lead firms have engaged 143 service providers to deliver durable solutions to smallholders including training and technical assistance in production techniques. The service providers engaged comprise of 38 Community Animal Health Workers, 11 Agro Vet Dealers, 34 extension workers, 50 lead /champion farmers in the sesame sector and 10 master trainers on milk hygiene in the dairy sector. The service providers have so far provided technical assistance (training, field demonstrations to animal disease diagnosis) to 10,083 smallholder producers.
- Perception survey conducted by Forcier Consulting (independent research company based in Somaliland) reported that 64% of PIMS beneficiaries perceive the on-going PIMS’s interventions to be accessible and appropriate to their needs. 66% of the sesame producers perceive PIMS technologies and practices to be accessible, 49% of milk producers perceive access to vet drugs and services to be more accessible and affordable from the local agrovet dealers, drug importers and community animal health workers; the direct actors PIMS is engaging with.

Summary of responses to issues raised in previous annual reviews (where relevant)
The last annual review recommended that PIMS builds closer links with other DFID-supported capacity building initiatives to ensure public sector capacity is also built to deliver PIMS objectives.
Engagement between PIMS and the World Bank funded Small-Medium Enterprise Facility (SMEF) is ongoing linking PIMS’s lead firms to business service providers, enabling them to get additional capacity building support.

Recommendations
PIMS needs to ensure that investments and partnerships are assessed with a sustainability focus. This is particularly the case as the programme moves to its final year. It needs to have clear exit plans leaving behind sustainable market systems before its planned closure by April 2018.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The key cost drivers are personnel fees and grants. This reflects the programme’s model of providing technical assistance to market leaders, small-holder farmers and micro businesses.

VfM performance compared to the original VfM proposition in the business case
The PIMS Business Case proposed that VfM analysis would be based on indicators measuring the programme’s economy, efficiency and effectiveness: A detailed analysis and methodology used for calculation is attached in Annex 5.

Economy:
The management cost has decreased from 17% to 14% since the beginning of the programme, following the scaling up of the programme in January 2017 due to additional funding from Danida, thus benefiting from economies of scale.

Average fee rates paid to the consultants working on the programme has seen a gradual decline with increasing use of local consultants where available and feasible.

Efficiency:
The programme is well on track to deliver its outputs, with nearly 75% of all its output targets for this annual review period moderately exceeding expectations. This performance is an indication that the programme is able to deliver outputs at lower cost than originally anticipated.

The programme’s unit cost is also lower than some comparable programme. For example, in the market development component, so far, PIMS has dispensed over £ 238,000 to its lead firms and this has resulted to 10,083 direct beneficiaries being reached with improved inputs, practices and technologies which translate to £23.61 per beneficiary reached, compared to a cost of £32 per beneficiary for the Kenya Markets Trust Programme (KMT) in 2016. In general, PIMS has managed to keep transaction cost down by selecting lead firms which are in close vicinity of the target beneficiaries. PIMS has also focussed on piloting new ideas e.g. new seeds with larger number of farmers (compared to KMT) which has helped in reducing the unit cost. Given the short timeframe for the programme, piloting new ideas with large number of small farmers was felt necessary for introducing systemic change.

The cost of rehabilitating 1Ha of irrigated land is about £107 in 2016 and this is expected to reduce to £93 in March 2018. The EU’s total irrigation expenditure since 2002 amounted to €10.3 million resulting in irrigating 50,000Ha, or a cost of €207 per Ha (£178.53) which is significantly higher than the costs under the PIMS programme. The PIMS CfW activities delivered irrigation through rehabilitation of canals by using a community based model which delivered low overhead costs. Because of the community based approach, PIMS is able to negotiate more realistic wage rates which were below other programmes and this has helped reduce the unit cost.

Effectiveness:
Rehabilitation of grazing lands under the programme is estimated to result in an additional income to pastoralists of £897,000 which would otherwise be lost due to migration of the herders. This compares to a programme cost of £150,000 which gives a cost benefit ratio of 6:1. This is estimated to increase further to 9:1 by the end of this year.

The rehabilitation of canals will open up 2,280 Ha of new farmland for sesame, maize and other crops. Cultivation of new farm land areas is expected to increase smallholder incomes by £528,000 against the programme spend of £213,000. This gives a cost benefit ratio of 2.5 in Dec. 2017 and 5.7 in Mar 2018.

Assessment of whether the programme continues to represent value for money
As demonstrated in the above section, the review judges that the programme continues to offer strong value for money.

Recommendations:
The VFM metrics developed by the programme are a good start. However, these should be more target-driven and informed by an assessment of current market conditions.

Quality of financial management
Funding is conditional on tight financial management procedures and periodic audits. . The contract is based on results-based payments to ensure that payments will be strictly in accordance with satisfactory delivery of the agreed milestones. Payments are only billed on achievement of milestones in line with reporting requirements and after approval of supporting documents. DAI uses a high quality financial and administrative system using TAMIS (the DAI financial and project management module) for day-to-day financial management, which DAI will give DFID access to increase transparency. The implementing partner follows similar arrangement for making payments to the downstream partners. PIMS programme activities and results are being monitored and validated through a cross-office third party monitoring arrangement.

As of 31st March 2017, the programme has spent £5.15m, thus leaving a sum of £7.85m in the remaining life of the programme up to April 2018. At the time of the cost extension of the programme approved in January this year, pro-longed drought was identified as a significant risk to delivery of the pipeline of activities and absorption capacity. The delay in some of the planned activities now raises a genuine risk that the programme may not able of fully absorb the remaining funds. It is expected that the programme’s spending rates may slowdown following a scaling down of activities in some target value chains in response to the drought. The summary recommendations section sets out actions for dealing with this issue.

The last financial report was submitted in the quarterly report sent on the 21st April 2017. An external financial audit review was conducted in June 2016 and report submitted to DFID on the 27th October 2016. The external audit reported that all financial records and statements were well and appropriately represented. On implementation and reporting to DFID, the report flagged the need for DAI to fast-track programme activities to ensure pre-agreed timelines for delivery of milestones are achieved. DAI has strengthened its team’s capacity and rolled out the use of Technical and Administrative Management System (TAMIS) to ensure activities are on track and reporting is timely despite activities slowing down as a result of the prolonged drought. DAI has also designated the M&E Manager and the Operational and Finance manager as the focal persons for ensuring up-to-date programme documentation and correspondence.

Separately, DAI carried out an internal audit of the PIMS programme and the report will shortly be shared with DFID.

Date of last narrative financial report	21st April 2017
Date of last audited annual statement	Financial Audit submitted to DFID on the 27th October 2016

E: RISK

Overall risk rating: Major
The programme’s overall residual risk is Major, under the DFID five-point risk management framework.

Overview of programme risk
DAI maintains a risk register that is updated quarterly and shared with DFID and capturing all evolving key risks. DFID’s Risk Register has been updated to include the following risks. DFID’s team will continue to closely monitor the identified risks in consultation with DAI:-

Drought conditions: A majority of the target value-chains and sub-sectors in Somalia are affected by the prolonged drought. Continuing drought conditions could mean a missed season and consequently a backlog of results, especially those related to income and jobs from the crop production value-chains. PIMS aims to mitigate this risk by focussing on less weather-dependent value chains like fisheries and areas with access to irrigation. PIMS could also consider mitigate the impact by supporting improved resilience e.g. by promoting drought-resilient seeds. In the event of the worst case scenario, PIMS will expand cash-for-work programme in rainfall dependent regions such as Puntland and Somaliland to help small farmers and farm labourers tide-over the impact of any drought.

Weak capacity of small organizations: Additional vetting procedures on potential and current grantees and lead firms have been introduced, in light of the current climate to ensure a greater focus on more stringent due diligence, with multiple layers of vetting. DAI will also assess their needs and provide capacity building support to strengthen delivery. DFID and DAI are exploring ways of partnering with Shurako and possibly use its due diligence methodology in the identification and verification of cash for work projects’ beneficiaries.

Turn-over and recruitment of staff: PIMS has had difficulties in recruiting and retaining suitably qualified local and international staff. This has contributed to delays in programme delivery in the past and could continue to do so. DAI will mitigate this risk by engaging short term consultants and providing surge support from its London office. In addition, most critical positions are currently filled-up and risk of inadequate staffing causing serious delays is considered low as long as DAI is able to retain the staff already on-board.

Increase in humanitarian response by multiple agencies has resulted in increased injection of feed, water supply and other inputs to mitigate the impact on food supply. With these inputs primarily directed to agriculture, PIMS interventions may be compromised by the effect on markets and value chains of this direct large scale supply. PIMS will continue to monitor and report.

Outstanding actions from risk assessment
There are no outstanding actions on due diligence and fiduciary risk assessments. Increased vetting procedures have been introduced as referenced above to ensure extra scrutiny of grantees and lead firms.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
PIMS is on track to exceed the majority of its output indicators particularly indicators 1.1 (Number of investment promotion events and/or negotiations initiated between business and private sector investors or financial service providers as a result of PIMS profiled investment opportunities and improved business practices), indicator 2.1 (Number of business linkages facilitated between small scale producers/entrepreneurs and input suppliers and/or buyers) and indicator 4.2 (Number of Service Providers engaged by lead firms to deliver technical capacity building to small scale producers/entrepreneurs). As mentioned in Page 1 of this report, these results, should be taken with caution given the prevailing drought situation and ambitious targets with most outputs and outcome targets expected to increase manifold, in the final year 2018.

At outcome level, the drought has had a serious impact on PIMS. Anticipated net additional income (NAI) gains and income increases from participating firms have been dramatically eroded following the prolonged drought. This has affected sesame and dairy production. The drought situation will continue to stifle both profits and growth and therefore undermine the ability to create jobs.

In a market systems programme, attribution is greatest after the end of the intervention. The realisation of outcomes will be felt to a greater extent in the future with attribution referring to the direct link between activities and outcomes and the total change taking place. Given the drought situation and accompanying time lag in transmission of outputs to outcomes, there is a genuine need for additional time to better capture the programme’s results. A critical component of PIMS M4P programming is building sustainability into market interventions, so that the exit strategy is appropriately designed at the start for partners to adopt and for wider change to become systemic and create momentum within a market system. However, in line with DCED assessment standards, this will lead to greater impact in 2 years from the end of the programme, through the process of attributable change.

Potential options for remedying the likely shortfall in outcome indicator achievement include extending the programme’s life cycle as well as revising the log frame in light of the drought’s impact.

Performance of partnership (s)
DFID has continued to review DAI’s performance as part of the Key Supplier Management (KSM) reviews. The last review was concluded in July 2016. This exercise enabled DFID and DAI to have constructive discussions on performance and agree areas of improvement. There had been some major issues with DAI including the quality of deliverables, timeliness of milestone delivery, responsiveness and staffing. Following the 2016 review, a number of action points were agreed between DFID and DAI to improve delivery and performance including the scheduling of monthly meetings to monitor progress. Significant progress has been realised including DAI’s UK office providing additional technical assistance to the local office and more qualified personnel being recruited by DAI.

Monthly meetings between DAI and DFID have helped keep track of performance in additional to DAI’s production of weekly situation reports and quarterly reports on programme implementation progress. Quarterly programme management committee meetings in Hargeisa and Mogadishu have been consistently held. DAI’s UK programme management team is frequently in the Nairobi with regular travel to Somali field offices and the latter’s technical input is more evident in their reports. As a result, there has been improvement in delivery and performance.

Asset monitoring and control
The PIMS’ quarterly reports provides full community and partner assets. Assets comprise of the community (e.g. feeder roads, low level water crossing bridge), private sector (modern equipment and machines supported with small matching grants) and implementing partner’s assets. DAI shared a full inventory of the PIMS assets in the Nairobi office in March 2017. The register is up to date. The Economic Development team, DFID Somalia, in liaison with the DFID Finance team, intends to undertake a spot check of the assets at the DAI’s offices in Nairobi later in 2017.

G: CONDITIONALITY

Update on partnership principles (if relevant)
PIMS is largely focused on stimulating the private sector outside the remit of Government. As such, the Partnership Principles do not apply in the detailed management and monitoring of this programme.

H: MONITORING & EVALUATION

Evidence and evaluation
DAI in liaison with DFID, DANIDA and LAMPS (DFID’s third party monitoring team) concluded a second revision of the log frame in December 2016. The log frame indicators have been re-arranged to fit into the PIMS’s overall theory of change targeting: (a) improvement of access to market opportunities in target sectors, (b) facilitation of private sector investment and (c) improvement of infrastructure assets through cash for work in the target sectors. All the outcome and output milestone targets have been adjusted based on the re-calculated projections and to cater for the additional funding from DANIDA (£2M). Given the operating context (prolonged drought), it is advisable to re-visit the log frame post annual review to revise the outcome and output indicators for 2018.

All the baseline indicators have also been gathered for all indicators against which PIMS will be able to measure progress.

Though no evaluation has been undertaken to date, DFID will consider involving its third party monitoring team (LAMPS) and/or seek support from centrally funded programmes like Business Environment Reform Facility (BERF) to undertake an analysis of the links between PIMS’s project outputs, and achievement of outcome indicators, as well as longer term impact to inform wider DFID programming. This will is scheduled for February/March 2018.

DAI has updated and shared its M&E framework and methodological note (attached as Annexes 2 and 3 respectively) with DFID. The M&E framework has been revised in line with the last PIMS’s Annual Review’s recommendations (FY2016/17) and is now aligned to the monitoring methods.

Monitoring progress throughout the review period
Monitoring of PIMS’s implementation is regular and continuous ensuring overall progress is tracked and programme resources are utilised effectively. Monitoring activities include:
- Participation in both quarterly strategic (programme steering committee) and operational (programme implementation committees) level programme management committees’ meetings. During these meetings, programme progress is discussed by representatives from the donors, implementing partners and participating government ministries. Programme is reviewed against the DFID log frame milestones, risk management, programme work plan and budget are also discussed.
- Monitoring of PIMS’s on-going field activities has remained a participatory and a continuous process where PIMS intervention officers, M&E team, implementing partners and government are involved. The lead firms have milestone based payment contracts with PIMS, hence they hold greater responsibility to capture the relevant data to measure progress (the lead firms use the data to as well measure their business performance and this remains a strong value proposition for them to keep records). PIMS intervention officers and area coordinators work with the lead firms to ensure the interventions are delivered as planned and the necessary data is captured. In most cases where field demonstrations are conducted, government officials are included for independent observations and reporting to the programme steering committee (PSC) and the programme implementation committees (PIC).
- DAI has contracted a local Somali research firm/partner, Forcier Consulting to undertake wide scale research including baseline, perception and enterprise performance surveys. This has enabled the programme to obtain independent views from its beneficiaries (direct beneficiary feedback) and concentrate on the weaker points for continuous improvement.
- DFID Somalia and Danida have both contracted independent third party verification providers, LAMPS and Axiom respectively, to verify partner results, build implementing partner’s capacity for effective monitoring and analyse and share results and findings with both development and implementing partners. LAMPS and Axiom have consulted severally to avoid duplication of efforts
DAI has established a quality assurance process to check implementing partners’ self-assessment reports, to verify data and to support and complement partners’ monitoring and progress reports. This is outlined in the M&E framework attached as Annex 2.

Monitoring progress throughout the review period
PIMS has had continuous interaction with its beneficiaries to obtain timely feedback on what is working, not working and their general views about PIMS interventions. Below are some snapshots of the beneficiary feedback;

Direct CfW beneficiaries	Sectors
“…. I lost 70 of my animals to the drought…..almost entire herd. It has been really tough on us but the on-going road repairs has helped me work and earn money to support my family, they have never gone hungry despite the biting drought……... on the other hand, the repairs done on this section of the road will help us transport milk to the market and also receive food and other stuff from town, it will improve a lot……..” Mohamed Osman Abdillahi aged 50 in Hakise	“…..I have been growing sesame for the last 13 years and for all that time, we have all been broadcasting seeds which has often resulted to very low yields….SATG has trained us how to grow sesame……the problem has not been the seed but on our crop management ……now that I understand what to do, I have prepared 120 Ha for the next growing season in Middle Shabelle…..” Mukhtar, Managing Director, Horn Afric sesame growing and export company in Mogadishu
“….the drought has killed most of the livestock and the remaining ones have become very unproductive...... the CfW has provided me with something to provide daily meals for my children and also buy feeds for the remaining animals……….the road at Dhoboloq is really bad during the rainy season….. floods even block people from accessing the whole village and people have to spend on the other side until the flood stops, with these repairs and fixing of the bridge, all those problems will be solved……” Huda Mohamed Isse, aged 42 in Dhoboloq	“ …..I didn’t know sesame seeds can be planted in rows like vegetables….we have been simply broadcasting our seeds. From the demonstrations we just concluded, we were able to get almost 800kgs/ha against 300 kgs/ha that we have been getting….we will be able to sell more sesame from next season now that we know how to produce better and we are connected to 1,500 experienced farmers from whom to buy from….” Hassan, Field Manager, Moumin Group Mogadishu
“……the CfW activities gave me the opportunity to provide for my children and also sometimes buy feeds for my animals…….floods here even carry away vehicles or trucks, these vehicles bring us sugar, flour and other food stuff and also transport our milk to the market…when it rains, and the road floods, trucks cannot come to our village, we hope these repairs and bridge will change that….” Amina Ali Haybe, 35, Dhoboloq	“….We have been selling veterinary drugs around Burao area where there are only few milk producers. We know thousands of the pastoralists live in the villages and working with the community animal health workers, we’ll be able to reach many more customers and increase our sales…we are as well using the field demonstrations to sell feed supplements to the pastoralists and from the few trials we have done, the results are promising…..” Mubarak, Manager, Alla Aamin Pharmaceuticals, Somaliland
“……I have never known sesame needs to be fertilized but now I know it can be fertilized with urea and DAP…..before I used to prepare the land by disk plow but now I can do harrowing, furrowing, ridging… I used to broadcast the seeds during planting and this took almost 35-40kgs/ha. The new planting techniques we learnt only takes 5kgs/ha…this is a big saving for the farmers…..” Ahmed Isse, Sesame farmer in Middle Shabelle

Process of Review
This AR was done in-house, led by the SRO and programme management team. The AR also reflects inputs from DANIDA who co-fund this programme. The review is based on the implementing partner, DAI’s most recent six-monthly progress report and other relevant technical notes attached at the end of this report. The AR also reflects information gathered through field visits to a couple of projects in Somaliland, interviews with beneficiaries in Mogadishu and Hargeisa, and detailed discussions with the DAI officials in Hargeisa, Mogadishu and Nairobi. The cross-office third party monitoring arrangement for Somalia, Learning and Monitoring Programme for Somalia’s (LAMPS) verification reports have been referenced. The AR has been quality assured by and includes comments from the Nairobi cross-office Accountability and Results Team (ART).

Annexes (to be attached)

1. ANNEX 1: REVIEW OF RECOMMENDATIONS FROM LAST ANNUAL REVIEW
2. ANNEX 2: M&E FRAMEWORK
3. ANNEX 3: METHODOLOGICAL NOTE
4. ANNEX 4: PIMS PROJECT SCORE CALCULATOR
5. ANNEX 5: PIMS VFM ANALYSIS