Business Case

Summary Sheet

Title: Development Impact Bonds Pilot
Programme Summary: The programme seeks to pilot Development Impact Bonds, a new tool for financing programmes on a Payment by Results basis, and build evidence on their suitability in improving the efficiency and effectiveness of DFID programming.
Programme Value: £4.8m	Country/ Region: Multiple
Programme Code: 204722	Start Date: / Planned: 10 April 2017 / (Actual start date 30 June 2017)	End Date: / 31 March 2023
Overall programme risk rating:	Moderate Choose a risk rating
Quest Number: / Vault Number:	5784438 / 13157755

Note: The Financial Case has been redacted until the programme evaluation tender has been completed.

## Intervention Summary (2 pages max)

Narrative summary of why UK support needed, what the funds will be spent on, where, over what period of time, via whom and what they will deliver.
DFID is looking to drive improvement in the effectiveness and efficiency of international aid: in the Single Departmental Plan we commit to “ensure that aid is spent effectively and efficiently” and “build on what we have already done to cut waste, introduce even greater transparency and ensure robust independent scrutiny and effective lesson-learning”. Delivering programmes on a Payment by Results (PbR) basis can enable us to do this. By only paying for outcomes achieved, we can set performance expectations at the very outset of projects and give providers flexibility in achieving them. DFID’s 2014 PbR Strategy commits us to expand the evidence base on what works best for PbR, and build capacity for doing PbR in the right ways.

This business case seeks £4.8m in funding to pilot Development Impact Bonds (DIBs), a new tool for pre-financing PbR contracts, and build evidence on their commissioning, management, and effectiveness in delivering programmes on a PbR basis. DIBs will be piloted by supporting a small number of projects designed by other donors or delivery partners where a PbR and DIB financing structure is desirable and feasible. Evidence generated through the pilot will help us understand when DIBs may be an appropriate commissioning tool and the costs and benefits of using them.

The policy areas, locations, and duration of pilot DIB projects will be determined during the project inception phase following robust due diligence of project proposals. An initial scan of DIBs available suggests that the potential pilot projects would generate results in employment/income generation, health and education, with project lengths of 3-5 years.

Does the programme fit with DFID’s strategic architecture: the UK Aid Strategy, Single Departmental Plan, International Development Act and the department’s Business Plan?
In addition to the above alignment with the SDP, a DIBs Pilot will also deliver on DFID’s Economic Development Strategy (2017) where we commit to “assess the scope for financing programmes through development impact bonds”.

What percentage of DFID’s Single Departmental Plan results target does this programme represent? Could the programme be adjusted in scope or scale to deliver SDP results?
Projects that will form the DIBs pilot are yet to be commissioned – it is therefore not possible to estimate what percentage of DFID’s SDP the pilot will represent. The programme will select DIB projects that align with DFID’s strategic objectives, and that deliver SDP results. It is likely that pilot projects could be adjusted in scope and scale to deliver more SDP results.

Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy?
- A number of other donors have expressed interest in or initiated the commissioning of DIBs. DFID has coordinated closely with such partner donors including the Belgian Ministry of Foreign Affairs, the Dutch Ministry of Foreign Affairs, and Grand Challenges Canada.
- The projects selected for the DIBs pilot will be assessed on the basis of the sustainability of their exit strategy before any funding is committed. For the pilot programme on the whole, an evaluation will be conducted throughout the duration of projects, informing future use of DIBs by DFID.

Has the programme considered working with HMG Departments and accessing cross-HMG funds?
The programme has drawn on the experiences of other HMG Departments in using Social Impact Bonds (SIBs, the domestic equivalent of DIBs) and will continue to share relevant experiences with HMG Departments through staff meetings and workshops. The programme has not identified any cross-HMG funds appropriate for funding pilot DIBs at this stage.

How does the programme relate to other UK aid within the specific sector, including multilateral, bilateral and centrally managed programmes?
Pilot DIBs are likely to be targeting results across multiple areas (e.g. health, employment, education), and project due diligence criteria include alignment with other UK aid.

Is there sufficient flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments?
DIBs link payment to the delivery of a pre-defined outcome. This approach enables DFID to give the provider greater flexibility to decide what activities are needed – adapting to changes in the local context or individual needs, and applying learning on what is/ isn’t working to achieve the outcome. This should empower and incentivise the provider to proactively course correct to find the best routes to achieving the desired outcome.

Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio?
Yes: Moderate Risk Level

Is there a clear communications strategy to reinforce our objectives? Will the programme be branded with the UK aid logo and recognise UK Government funding – and, if not, why not?
The DFID DIBs team will refine a communications strategy in conjunction with the Communications Division once DIBs Pilot projects have been selected. Any branding will be in line with current guidelines.

Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme?
- As the Business Case is valued under £40 million, it has not been submitted to Quality Assurance Unit.
- The DIBs team has the skills and resources to deliver this programme, and is collaborating with relevant country offices and sector experts, and has budgeted for additional technical assistance to refine the payment model if needed.

Do the SRO and team have the capability and resources to deliver this programme?
Yes, a Development Impact Bonds Adviser will be SRO for the programme, with support from a Programme Manager. The team will be able to draw on DFID’s strong technical expertise and experience of delivering Payment by Results programming.

Strategic Case

Why we should intervene – Strategic fit

DFID is looking to drive improvement in the effectiveness and efficiency of international aid: in the Single Departmental Plan we commit to “ensure that aid is spent effectively and efficiently, and reflects Britain’s strong interest in a more stable and prosperous world” and “build on what we have already done to cut waste, introduce even greater transparency and ensure robust independent scrutiny and effective lesson-learning”[1].
[1] DFID Single Departmental Plan 2015-2020 available here: https://www.gov.uk/government/publications/dfid-single-departmental-plan-2015-to-2020/single-departmental-plan-2015-to-2020#value-for-money-and-delivering-efficiently

Commissioning on a Payment by Results (PbR) basis can enable us to do this. By only paying for outcomes achieved, we can set performance expectations at the very outset of projects and give providers flexibility in achieving them. We can therefore incentivise delivery partners to focus on performance, measure impact and disseminate learning. DFID’s 2014 PbR Strategy[2] commits us to:
[2] Sharpening Incentives to Perform: DFID’s Strategy for Payment by Results (2014) available here: https://www.gov.uk/government/publications/dfids-strategy-for-payment-by-results-sharpening-incentives-to-perform

  1. expand the evidence base on what works best in PbR;
  2. build capacity for doing PbR in the right ways.

However, PbR commissioning is challenging. Firstly, it is risky for providers who do not get paid if they do not meet our expectations. Where complex solutions are needed with little evidence available, providers may not be able to take on delivery risk or access appropriate financing to deliver the project. Ability to take on risk partially depends on supplier size and the impact that not being paid will have e.g. risk of redundancies, insolvency, halting of other development projects to cover loss. Large organisations with larger balance sheets may be able to hold more risk than smaller organisations that may require significant upfront payments and be unable to bid for contracts with larger PbR proportions[3].
[3] Outcome-based payment schemes: government’s use of payment by results (2015), p24-26; available here: https://www.nao.org.uk/report/outcome-based-payment-schemes-governments-use-of-payment-by-results/

Secondly, PbR is technically challenging. Limited internal ability to help delivery partners assess, measure, and build capacity to deliver may result in programmes not progressing beyond the design stage. NAO’s review of government use of outcomes-based payment schemes recommended that commissioners should focus on setting outcomes and performance expectations, and ensuring payments create positive incentives in designing effective PbR schemes[4]
[4] ## Outcome-based payment schemes: government’s use of payment by results (2015) available here: https://www.nao.org.uk/report/outcome-based-payment-schemes-governments-use-of-payment-by-results/

In the UK and worldwide, a ‘Social Impact Bond’ (SIB) mechanism has been devised to address some of the challenges associated with PbR. To date, more than 60 SIBs have been commissioned world-wide, of which 32 have been launched in the UK. Two ‘Development Impact Bonds’ (DIBs) have also been launched, which translation the SIB mechanism to a development concept.

This business case sets out a proposal to pilot Development Impact Bonds (DIBs) and build evidence on their effectiveness in delivering programmes on a PbR basis and overcoming challenges associated with PbR. Evidence generated through the pilot will help us understand when DIBs may be an appropriate tool and the costs and benefits of using them.

How can DIBs make a difference?

DIBs are a new tool for pre-financing PbR projects that can help us to fund more programmes on a PbR basis. Specifically, they have the potential to address the dual challenge of provider risk and capacity to deliver on a PbR basis.

In a DIB, impact investors provide the upfront finance to deliver interventions. They take delivery risk away from providers, and are only paid back if programmes deliver. But investors do not only provide finance – they can also bring expertise in performance management and impact measurement, building provider capability to deliver.

The following illustrates a possible DIB structure:

Box 1: How DIBs work

The commissioner/donor enters into a Payment by Results arrangement with a provider for the delivery of an intervention to achieve specific outcomes.

Investors provide up-front finance to the provider to fund the provision of services, along with input into project design, and performance management.

The provider delivers the intervention to service users and outcomes are measured.

Improved development outcomes are verified by the donor, e.g. by appointing an independent verifier.

The donor pays if and when agreed outcomes specified in the PbR agreement are achieved.

Outcome payments from the donor then provide a return to investors. If results are not delivered, investors are not paid. If more/better results are delivered the investor receives a return.

Investor
Donor
Provider
Service
users
1.
2
6
3
4
5

Investors bear the delivery risk of the project - if results are not delivered, investors are not paid. This means that even providers who would not otherwise have the financial capacity to take on a project on a PbR basis may now have the scope to get involved as they face a lower level of delivery risk.

The risk transfer in the investor-provider relationship incentivises investors to ensure providers have the capacity to deliver, to measure and manage performance, and address any emerging issues quickly. It is this relationship between the investor and service provider (within the framework set by a PbR contract with a donor) that drives efficiency and effectiveness improvements in projects.

Context and conditions for success – When can DIBs offer best value?

For a DIB to drive efficient and effective delivery, certain conditions are considered necessary. These are outlined below:

  1. Project aim: projects should explicitly aim to transition payments to being tied to outcomes in order to incentivise provider focus on efficient, effective outcome delivery.

  1. Project type: Projects should be suitable for PbR. This means projects should have measurable outcomes, a clearly identifiable target cohort or population, attribution should be possible, the outcome timeframe should be reasonable, and independent outcome verification feasible. Most suitable projects will present a simple outcome metric but require a complex or innovative set of activities in order to achieve outcomes (e.g. tailoring activities to meet the individual needs of people living in complex situations).

  1. Donors should aim to transfer the financial risk to providers but be able to tolerate failure from a policy side. Donors should also have internal capacity to help design or assess the quality of PbR-type projects, and engage in a dialogue with suppliers and investors on setting outcomes, incentives, performance expectations, payment triggers, rates of return, and ensuing contract terms include effective safeguards and prohibit unethical behaviours.

  1. Providers should recognise the need to improve their performance (efficiency, effectiveness) and measure the impact of their work. Often, such suppliers will be organisations innovating in the products or services they deliver, but also in the delivery process or business model.

  1. Investors should be individuals or organisations looking for their finances to generate a social impact alongside a financial return. Investors in DIBs should be able to dedicate non-financial resources, such as their time and experience, to projects and work in partnership with suppliers and donors to design and deliver PbR projects.

  1. Funding Arrangement: The payment structure in a DIB should be designed to deliver better value for money than current alternatives for achieving the desired outcome. There should be a clear rationale for why social investment is needed for the project and outcome to be achieved.

To maximise the benefits generated through good DIBs, a DIBs pilot should target results areas where performance gains (and efficiency savings) can be replicated more broadly. It should also focus on incentivising transparency and shared learning during programme delivery, so that the knowledge and good practice generated can be replicated.

Context – How strong is the evidence on DIBs?

DIBs are a new tool for delivering development projects - only two DIBs have been implemented so far, both very small. Existing evidence on DIBs is therefore limited.

However, DIBs are part of a wider impact bond family – originating from social impact bonds (SIBs) used domestically by governments to commission public services. To-date, over 60 social impact bonds have been commissioned. The UK is a world leader in the SIB market, with 32 SIBs. Government in US, Netherlands, Belgium, Germany or South Africa have also made use of the instrument.

A qualitative review of thirty-eight existing impact bonds by the Brookings Institute (2015) found the following:

  1. Existing impact bonds have focused on specific sectors: areas where government is already contracting third parties to deliver services and where service inputs are complex, but outcome are simple to measure.

  1. Impact bonds can improve service delivery but deals so far have been complex: the design phase of impact bonds includes determining outcomes, metrics, budgeting, and cost-benefit analysis (common to all PbR interventions) and also forming the arrangements between the SIB parties.

  1. Deals have been varied in terms of their structure, mechanics and stakeholder roles: this means that impact bonds are not always directly comparable, but demonstrates flexibility in deal structuring.

  1. Rigorous experimental or quasi-experimental evaluation was not always necessary for measuring impact and triggering payment: many SIB commissioners relied on administrative datasets, or historical baselines.

  1. Impact bonds lead to a shift in focus to outcomes: the study found that existing SIBs encouraged transparency and accountability in commissioning public services. Instead of paying for services, government pays for outcomes. At the same time, SIBs push providers to deliver on these outcomes.

  1. Impact bonds drive performance management: Bringing private sector mentality into the provision of services can lead to more efficient and effective delivery of social services. This has been mainly seen through the push toward outcome achievement and fidelity to the intervention delivery model and less in terms of adaptation of service provision along the way.

  1. The impact bond mechanism stimulates collaboration: this applies to all parties involved in impact bonds.

  1. Impact bonds have enabled the development of strong monitoring and evaluation systems: the impact bond mechanism incentivises evidence collection and can therefore lead to improving outcomes for service users through identifying interventions that work.

  1. Impact bonds can shift the focus of government toward preventive services: this could have economic implications for government and society

While implementing impact bonds in a development context brings specific challenges, emerging evidence on SIBs shows that the impact bond mechanism has the potential to improve effectiveness and efficiency of outcome delivery, and generate valuable impact evidence.

Objectives

Given the emerging evidence on impact bonds outlined above, but limited experience with DIBs specifically, the main aim of the DIBs pilot is to test whether DIBs are a tool that DFID is able to use, and start to generate understanding of how and when DIBs can add value in DFID programming.

The DIB pilot programme has the following objectives:

  1. Objective 1: Understand the process of agreeing and managing a project on a Development Impact Bond basis, including implications for DFID’s funding arrangements, assurance and financial management.

  1. Objective 2: Build understanding of whether Development Impact Bonds enable efficient and effective delivery of programmes in DFID priority results areas, and how they can support innovation.

  1. Objective 3: Build understanding of the conditions for DIBs to be an appropriate commissioning tool and the costs and benefits of using them.

Annex D includes a list of research questions the proposed pilot will explore. An evaluation plan is presented in the Management Case.

Gender Equality

We have considered how a DIBs pilot could contribute to DFID’s strategic vision for girls and women. The DIB instrument itself is a financing arrangement between donors, development providers and investors, and any impact on gender equality will depend on the interventions selected for trialling DIBs, as well as the detail of PbR arrangements used, such as results areas targeted, result metrics, or payment triggers. In order to promote gender equality, the DIBs pilot will carry out gender equality assessments of interventions considered, and ensure that results metrics used demand equity of benefit for men, women, and disadvantaged groups. Payment values and triggers will be chosen based on their ability to incentivise equity of benefit. The pilot will prohibit activities that increase or entrench existing inequalities.

Terrorism and financing

It is expected that the risks of UK aid funds being diverted to terrorist organisations is low. This is because providers of services under the DIBs pilot programme will only be paid once results have been delivered and verified. The DFID DIBs team will complete a robust due diligence on any partners we work with as part of a DIBs pilot and ensure partners are aware of their responsibilities in relation to counter-terrorism legislation.

Appraisal Case

Options for piloting Development Impact Bonds

We propose to launch a DIB pilot, focusing on learning about DIB commissioning and establishing a rigorous monitoring and evaluation framework. Options considered for piloting DIBs are outlined below:

Option 1: Do nothing: This would involve continuing only with current and planned PbR programmes, without testing the use of development impact bonds. Instead, we could work with other donors to encourage them to develop DIBs independently and share knowledge, and take up the approach once more evidence is available. It is likely that some evidence on DIBs would be generated through current or planned PbR research work in DFID.

Delivery: Under the do nothing option, the internal DIBs team would work solely through building relationships and influencing other donors.

Option 2: DIBs as a commissioning option: An option to submit bids designed as DIBs structures could also be included in commissioning planned PbR projects and programmes. To ensure take-up across the department and by suppliers, the DIBs team could provide support to commissioning teams and providers in design and during implementation and monitoring.

Delivery: The DIBs team would provide support to commissioning teams, including advice on the DIB instrument. However, specific project design and implementation support on DIBs would likely need to be procured from a supplier.

Option 3: DIB pilot (internal design): Under this option, the DIBs team would carry out an internal appraisal of policy areas or programmes where PbR/DIBs are desirable and suitable to select an appropriate project (or several projects) to be run as a DIB pilot, design a project outline (desired geography, outcomes, cohort, intervention length, etc.) and commission.

Delivery: Following internal project area identification or shortlisting, the option could include a range of delivery routes, e.g. commissioning detailed project scoping and design externally.

Option 4: DIB pilot (external design): A number of external projects that are structured as DIBs are nearing design completion with the aim of launching activities in 2017. A number of these providers have approached DFID as a potential outcome funder. DFID could consider supporting one or more of these externally designed DIBs. The team would complete due diligence on projects (fit with DFID results priorities and project quality and value for money assessment) to decide whether to support one or several projects on a DIB/pay-for-outcomes basis.

Delivery: Following the shortlisting of available DIB projects, selected DIBs could involve DFID becoming the sole funder of a DIB project, but also co-funding with another donor or national government, or funding through a multilateral organisation. The final delivery route would depend on the type of projects available and interest from other parties.

Option 5: DIB fund: Another option for commissioning DIBs is to open a DIBs fund which would invite DIB designers to come forward with DIB project proposals in several wide areas (e.g. health, education, WASH). The fund could also commission other PbR instruments to compare the relative efficiency/effectiveness of DIBs and provide support for project design to ensure a quality pipeline of applications.

Delivery: Due to resource requirements, it is likely that a DIB outcomes fund would be managed through a third-party manager, with strategic input from the DIBs team which would also communicate evidence generated to DFID.

Options 2 – 5 would all require an additional evaluation component dedicated to generating learning on the impact of the DIB structure on results achieved as well as the process involved in designing and managing a DIB to achieve impact.

Option assessment and preferred option

Options were assessed against the following criteria:

  1. Resource requirements v. existing capability and capacity – amount of resource (staff, finance) required compared to existing capability and capacity within DFID and in likely implementing partners to deliver the outcome and manage risks.

  1. Developing future DFID capability – as the identified need for the DIBs pilot relates to lack of knowledge and experience in DFID in relation to the DIB instrument, options were also assed with regard to potential to build DFID’s DIB capability.

  1. Timing - speed of launch and delivery – given the potential benefits of DIBs to PbR commissioning outlined in the Strategic Case, a rapid launch of a DIB pilot is preferred. This would enable us to start generating and disseminating evidence on DIB commissioning and realize any DIB benefits earlier. Pace of delivery is also considered, as this also determined when sufficient evidence can be generated to inform future DIB commissioning.

  1. Control over pilot content – DIBs offer best value under a specific set of conditions (see para 12 in the Strategic Case). The DIBs team should therefore be able to assess whether any projects proposed for inclusion in a pilot meet these conditions, or if they can be shaped to do so.

  1. Evidence generated – given the variation in the impact bond market, and lack of a fixed model for delivering impact bonds, a pilot project should look at generating comparative evidence, e.g. through testing DIB delivery in different contexts, with different characteristics to enable comparison and generate evidence on where they might offer best value.

  1. Driving value for money – generating solutions to complex problems while ensuring value for money is one of DFID’s objectives. DIBs piloting options are therefore also assessed on their potential to drive competition and select proposals delivering best value for money.

All criteria were weighted equally in scoring options. Options were scored on a scale from 1 (high) to 5 (low) and the option with the smallest score selected. Assessment outcomes are presented in Annex A. Option 4, piloting DIBs though funding one or more of externally-designed projects, was identified as the preferred option.

The DIBs team has carried out a mapping exercise to find DIBs currently under development. We have identified 33 DIB projects initiated by other donors, service providers or intermediaries, at varying stages of the design process. The team shortlisted projects aiming to launch in 2017/18 that also align with DFID’s policy objectives and priority countries. Shortlisted projects are summarised in Annex C.

Most shortlisted DIBs are of a relatively small total ticket size (<£5m), with larger ones having secured or aiming to secure commitment from multiple donors and mostly seeking <£5m additional outcome funding. Option 4 was therefore evaluated as having relatively low resource cost compared to available resource and faster speed of launch and delivery compared to option 5 (establishing a DIB fund) and option 3 (internal design) as it will not require DFID to carry out project scoping and design.

On developing future capability, option 4 allows us to generate first insights into the process of agreeing and managing DIBs as DFID will participate in the finalisation of the payment terms with DIB service providers, and other donors. This approach also ensures that a range of DIB projects with different characteristics will launch. This means better scores than options 1 and 2 on ‘evidence generated’ as it reflects the evidence need and learning objectives identified in the strategic case. Supporting a small number of DIBs is unlikely to produce robust quantitative evidence on the relative efficiency/effectiveness of the instrument compared to an internally designed pilot (option 3) or outcomes fund (option 5). However, these DIBs can serve as case studies for future projects.

While option 4 would not allow us to have complete control over the content of pilots (especially where other donors initiated and funded DIB design), independent contracting allows the DIBs team to target outcome areas aligning with DFID’s strategic priorities. This therefore still means stronger performance on this criterion than ‘do nothing’ where DFID is not directly contracting DIBs. This is similar for the ‘driving value for money’ criterion whereby option 4 would mean some reliance on the VfM criteria employed by other donors when initiating DIB design. Due to the small number of DIBs available, it is unlikely DFID will be able to compare projects on a like-for-like basis in terms of VfM. However, some of this is, again, offset by our ability to work with DIB providers independently, and not participate in projects where we have concerns regarding value for money.

Commercial Case

What is the opportunity for DFID to get involved in a DIB?

We engaged extensively with providers, investors, and PbR/DIB advisory services to understand the level of interest and volume of projects that are planning to use a DIB structure. We found that the use of DIBs is at a very early stage, with only two small impact bonds actually implemented in low and middle income countries.[5] Engagement with investors has so far demonstrated their willingness to provide the pre-financing for projects – particularly among banks, family foundations, and investment funds that have already invested in UK SIBs. However, investors report that action has been held back by the lack of projects that have secured outcome funder interest.
[5] A Sustainable Cocoa and Coffee Production DIB in Peru ($110,000); and Educate Girls Development Impact Bond in Rajasthan India ($270,176)

In the course of our scoping we identified a total of 33 projects that are planning to use DIBs, each of which is targeting a different outcome. Eleven of these DIBs are at a very early design stage and would not be ready to launch until at least 2018. Of the 12 that are at a later stage of design, only 6 are targeting DFID countries and results priorities and could be in a position to launch in 2017. All 6 of these projects have submitted unsolicited funding proposals to DFID.

Assessment of commercial options for selecting and supporting DIB projects

As the appraisal case highlights, the key advantages of supporting externally designed DIBs is that the expensive design phase has already completed, these projects would launch this year if awarded DFID funding, which would enable prompt learning. We considered what commercial approaches were most suitable to delivering the objectives of this business case, while ensuring a fair process that does not limit competition and drives value for money.[6]
[6] See Commercial Options assessment: https://ec.vault.dfid.gov.uk/otcs/cs.exe?func=ll&objaction=overview&objid=6112358

Our analysis concluded that if the projects meet our policy criteria, our best delivery route would be to award funds through an Accountable Grant (AG) or Memorandum of Understanding (MoU). These instruments are suitable because the project proposals have been submitted to DFID by not-for-profit and multilateral organisations that are seeking donor support for their mission, and are interested in the intervention freedom and flexibility that tying donor contributions to results can offer.

After business case approval we will fully appraise each of the 6 DIB project proposals against a common set of technical, commercial and due diligence criteria to ensure we take a robust and fair approach that supports good projects. The key questions are:
      1. Are the results ones DFID wants to support (i.e. is the organisation aligned to DFID’s objectives?)
      2. Is the partner organisation the most suitable provider for delivering these results or would a procured / competed approach be better route to delivering results?
      3. Is the project ready to launch without significant adjustments
      4. Is there an identifiable benefit, e.g. through risk transfer, in using the PbR/DIBs approach, and
      5. Is the proposed outcome price reasonable and acceptable

The AG and MoU templates allow for payment by results arrangements to be included and the Department for Communities and Local Government (DCLG) found that grant awards were effective in raising social investment for outcomes-tied homelessness programmes delivered by third sector providers under the DCLG’s Fair Chance Fund. The AG and MoU finalisation process also leaves flexibility for DFID to drive down outcome pricing and set strong performance incentives, based on past performance and comparable programmes.

Due diligence will be conducted before grant arrangements are signed. We will take a risk based approach based on DFID’s standard due diligence guidance. In addition we will review the terms of the financing arrangements agreed between the providers and their social investors to ensure parties are commonly aligned toward the achievement of desired social outcomes. We will also undertake a Risk Assessment on the social investors that are providing pre-financing to ensure that DFID is not exposed to any additional reputational risks as a result of the investor’s involvement in the project.

Flexibility to adjust delivery route for first DIBs if providers face insurmountable barriers

We will pursue the Accountable Grant approach in the first instance. However, we propose to maintain some flexibility to change our delivery route in the event that we run into unexpected and insurmountable barriers that prevent this from being a feasible approach. Such barriers may exist because DIBs are a new instrument which pushes existing DFID experience.

An alternative delivery route, should the grant arrangement outlined above not be feasible, is for DFID to support a small number of DIBs through a third party organisation. Relevant organisations, such as the Global Innovation Fund and other donors, were considered in the commercial options appraisal. If a change to the delivery route were needed we would seek a Business Case Variation from the Head of Department. The case for variation would be informed by the nature of the barrier and its broader implications for DIBs, as well as a cost-effectiveness assessment of the alternative delivery route.

Performance Management of each DIB project

During project delivery, the provider will be required to provide regular updates on how the project is performing, whether the theory of change is performing as expected, and provide advance forecasting of results to be achieved. DFID will require providers to record and share the real costs of delivery. This cost data should show spend against the original costed work plan as well as new activities. This data reduces the knowledge asymmetry between DFID and the provider on what it actually costs to deliver outcomes.

The DFID Programme Manager will be responsible for managing each DIB grant arrangement. In a DIB, the day to day delivery management of the project sits with the provider and investors as they hold the financial risk associated with non-delivery. The Programme Manager’s focus should shift away from reviewing inputs and activities and towards focusing on the results being achieved, whether the verification process is sufficiently robust, and monitoring for unintended impacts including through beneficiary feedback. The Programme Manager will review annual statements of expenditure to compare real project costs to original costed work plans as a check on the reasonableness of outcome pricing – importantly this review is not a check on whether the inputs are “right”, i.e. whether the chosen input mix will lead to specified outputs and outcomes, which is the responsibility of the providers and/or social investors.

Commissioning of Independent Results Verification

Each DIB pilot is required to have a robust and independent process for verifying that the results claimed have been achieved before the supplier is paid. This is to prevent and detect fraudulent results claiming, and ensure quality as well as quantity of results.

The independent verification process will be specific to each DIB. It could consist of data that is automatically collected through an independent provider/ government monitoring the DIB (at no or very low cost), but we anticipate that some projects will need to commission an independent service provider to verify or audit results.

Given the presence of other donors, we will assess on a case by case basis whether DFID or another donor commissions the results verification process. There is a large market of suppliers (both international and national) who can provide this service. Where DFID is to commission the service, the commissioning route will be defined to meet the specific requirement of that project and with advice from Procurement and Commercial Department.

Procurement of the Independent Evaluation of the DIBs Portfolio

1. The evaluation is an integral component of this pilot programme and will be designed to meet the learning objectives of this business case by gathering emerging evidence[7] on:
  [7] Note that evidence and insights related to objective 1 in this business case - understanding the process of commissioning, finalising and managing a project on a Development Impact Bond basis, including implications for DFID’s funding arrangements, assurance and financial management – will be gathered and communicated by the DFID DIBs team directly.
  1. Whether Development Impact Bonds enable more efficient, effective and innovative programming;
  2. What conditions (context, characteristics, stakeholders) enable DIBs to be a useful tool and the costs and benefits of using them;

To gather this evidence the evaluation requirement will need to assess the process and impact of each DIB project, and also look across the portfolio to compare and contrast how the DIBs performed across a range of conditions. A single Terms of Reference document covering both project and portfolio level evaluations will be most cost-effective.

The most suitable procurement route is the DFID Global Evaluation Framework Agreement (GEFA). The GEFA includes a large number of pre-qualified suppliers that offer both process and impact evaluations, across the full range of thematic areas that the DIB pilots could focus on. The suppliers were pre-qualified to the GEFA based on their record of delivering results and value for money.

The DIBs evaluation requirement will be tendered using a mini-competition among the GEFA suppliers, to drive further competition. Bids will be assessed against pre-defined criteria designed to identify the most economically advantageous tender. The tender process should take 3-4 months to complete. We will launch the evaluation tender once we know what the first DIB pilot projects are, so that we can be specific about the pilot project results priorities and locations.

The evaluation terms of reference, design, and evaluation outputs will all be subject to DFID’s independent evaluation quality assurance process (EQUALS).

Financial Case

FINANCIAL CASE HAS BEEN REDACTED UNTIL PROGRAMME EVALUATION TENDER HAS BEEN COMPLETED.

Management Case

What are the Management Arrangements for implementing the intervention?

The DFID DIBs team will be responsible for the overall management and day-to-day oversight of the DIBs pilot programme, as well as implementing a central monitoring and evaluation (M&E) framework. This is necessary as the aim of each pilot project is to contribute to DFID’s understanding of the DIB mechanism (finalising, agreeing, managing, efficiency and effectiveness) and the conditions for it to deliver best value.

DFID Programme Team Structure:

DIB Project C
DIB Project A
DIB Project B
M&E provider
SRO of the DIBs pilot programme, responsible for design and implementation, and feeding learning from DIBs pilots into broader DIBs strategy
A2 DIBs Adviser
Responsible for design of programme management structure and day-to-day programme management including communications, financial management, due diligence and procurement, smart rule compliance
A2 DIBs Programme Manager
Head of PSD

A1 BEH Team Leader

1. Responsibilities of the DIBs team in managing the DIB pilot programme include:
  1. Establish Pilots: Robust review, selection, due diligence of projects and finalisation of DIB grants / MoUs with effective PbR arrangements.
  2. Participate in governance structure of each DIB, at least quarterly for management purposes, and more frequently to gather learning on DIB.
  3. Programme cycle management: on-going risk management, annual programme review process, continuous financial management and reporting at appropriate levels, and proper close-down of projects.
  4. Monitoring and Evaluation: Design and implement M&E plan for DIBs pilot, including commissioning and managing an external evaluation provider, and establishing an evaluation steering group and quality assurance process.
  5. Translating learning from DIB programme (gathered through M&E and work with other donors) into longer-term DIBs strategy and broader DFID learning.

Monitoring and evaluation framework

1. Monitoring and evaluation is critical to the success of the programme to:
  1. ensure the individual projects supported meet their milestones and targets;
  2. ensure that the aggregated results of the DIB pilot match expectations and the programme delivers evidence outlined in its objectives;
  3. assess the effectiveness of innovative interventions and new partners;
  4. disseminate this information to improve the performance of future DIBs and to influence wider DFID and other programmes in using the DIB mechanism.

Each pilot project will have separate detailed management and M&E arrangements in order to reflect differences in project size, policy area, country context, and funding arrangements. Project-specific M&E will be agreed on a project basis with input from partner donors and funded through DIB grants. To evaluate the pilot programme, the DFID DIBs team will appoint an external provider who will draw together learning from project evaluations and carry out further primary research with parties involved in each DIB.

The DFID Programme Manager will be responsible for ensuring an effective and coherent programme of monitoring and evaluation activities is established during the first 9 months of the project, the key activities are included as milestones in the DIBs Pilot Programme Delivery Plan. Key objectives include finalising the Evaluation Framework, including monitoring and evaluation requirements in grants, and the procurement, management and quality assurance of an independent Evaluation.

Evaluation Plan

The DIB pilot will be structured around generating answers to questions that test our assumptions about DIBs and enable us to establish the value and potential use of DIBs in DFID programming. This evidence is of interest to other donors, broader UK government use of PbR and impact bonds, partner governments, and DFID service providers – particularly third sector organisations considering delivering on a PbR basis. It is important that stakeholders are confident in the validity and impartiality of the findings generated. As DFID will play a role in the design and oversight of the DIB projects, the evidence generation work stream should be completed by an independent party, and include evaluation of DFID’s contributions to the DIB projects.

We therefore concluded that a robust, independent evaluation that adheres to the OECD DAC criteria, and is subject to independent quality assurance processes was essential.

The evaluation questions have been structured around an Evaluation Framework (Annex D) that is based on DFID’s strategic theory of change for how DIBs can enable more effective and efficient delivery of PbR programmes.

1. The evaluation framework seeks to generate evidence on:
  1. Whether DIBs enable effective and efficient delivery of PbR programmes. The validity of the theory of change for DIBs. The conditions (context, characteristics) for DIBs to be an appropriate commissioning tool.
  2. To what extent were the DIB projects effective/ efficient? What were the factors influencing their achievement/ non-achievement of objectives, including the role of the DIB structure?
  3. The overall costs and benefits of using DIBs
2. We anticipate that there will be two layers of evaluation. In some of the DIB pilot projects there will be an independent project level evaluation that is focused on evaluating the effectiveness of the programme in achieving its intended outcomes – this forms part of the independent payment verification process. Wherever possible we will require the project level evaluations to consider not just the effectiveness of the programme, but also to look for broader positive or negative impacts of the programme. DFID will sit on the steering group of these evaluations, and require that the evaluation design and outputs are quality assured by EQUALS.

In addition there will be an overarching programme level evaluation that will be commissioned and managed by DFID. The programme level evaluation will look across the portfolio of DIB projects supported by DFID (and at the wider literature) to answer the following core evaluation questions:

Q1: Does the DIB mechanism facilitate the use of PbR where this was previously difficult or not possible?

To what extent does DIB model overcome the challenges that prevent some providers from delivering on a PbR basis? To what extent do DIBs help build supplier capacity in delivering on PbR contracts?

Q2: Does the DIB model lead to improvements in the effectiveness and / or efficiency of programmes?

- Who were the main stakeholders in the DIB? What incentives were they under? What role did they play? To what extent did this role make maximum use of their comparative advantage? How did this effect how the design and delivery of the project and its results?
- What value do investors add beyond providing finance? (E.g. Do they provide better performance management, and incentivise providers to focus on outcome measurement and delivery?)
- To what extent did the focus on outcomes create more flexibility, autonomy and innovation within the interventions? What factors enabled (or prevented) flexibility and innovation within the interventions?
- To what extent can delivery and innovation risk be transferred from government and providers to investors through the DIB structure?
- To what extent were programmes implemented through DIBs effective and/or efficient? (and if possible how does this compare to other contract models)
- Did the DIB structure have any negative impacts?
- What were the overall costs and benefits of using the DIB model

Q3: Under what conditions do DIBs work best?
Under what conditions (context, characteristics, stakeholders) do DIBs work best? And why?

The evaluation questions included in the Evaluation Framework will also form part of the terms of reference for the programme level evaluator as indicated in Annex D.

DFID will establish a Steering Group for the Programme level evaluation to ensure the evaluation is relevant and useful to target stakeholders. All evaluation outputs (including the initial terms of reference, evaluation design, approach papers, and evaluation reports) will be quality assured by EQUALS and published.

The programme level evaluation will be commissioned within the first 9 months of the start of the DIBs pilot programme. The programme level evaluation will supplement but not duplicate the project level evaluations.

Risk Management Plan

The overall residual risk of not achieving the outcome is assessed as Moderate. Fiduciary risk is assessed as minor, while reputational risk is moderate due to the novel way that DIBs engage socially motivated investors. We will ensure that the strong value for money rationale for the DIBs model is communicated effectively alongside the UK government’s existing use of social impact bonds.

Our risk assessment identified 18 potential risks. We have designed mitigating actions to be taken to reduce the probability and/or impact of each risk, as set out in the DIBs Programme Delivery Plan. Mitigating actions will be implemented as part of the selection and grant award stage of the programme. The Residual Risks (which assumes mitigating actions can be successfully put in place) are summarised below. The two major risks require particularly close handling as set out in the Delivery Plan.

We will escalate to the Head of Private Sector Department if any mitigation actions cannot be implemented; the likelihood or impact of a risk increases; or any new major risks occur. Programme Risks will be reviewed quarterly as part of programme cycle management.

Exit strategy

Each DIB project funded will devise its own exit strategy as appropriate to the wider policy and country context. The DFID DIBs team will ensure that the quality of the planned exit strategy is assessed prior to making funding decisions for pilot DIBs.

The DIBs pilot programme as a whole will complete when individual component DIBs have delivered results under their grants, service providers and investors have been repaid, and when learning from pilot DIBs has been consolidated and fed into DFID’s DIB strategy. The DIBs team will be responsible for taking this work forward. A timeline for the DIBs pilot programme will be specified once projects selected for funding are confirmed.

---------------------------------------------------- End of Business Case -----------------------------------------------------
## Annex A – Options appraisal
Option	Resource requirements v. existing capability and capacity	Developing future DFID capability	Timing - speed of launch and delivery	Control over pilot content	Evidence generated	Driving value for money
Option 1: Do nothing / Score: 24	1 – Minimal resource is required for this option. As DFID would not be financing any DIBs, only staff resource would be needed in working with other donors. The existing DIBs team would be able to take on any work with other donors.	5 – It is unlikely that any significant future DFID capability would be developed on DIB commissioning. Only second-hand experience with DIBs would be gathered through other donors, and only if other donors decided to commission DIBs.	3 – Under this option, DFID would have no control over the timing and speed of launch of DIBs supported by other donors. While a number of DIBs are being designed currently, many are still in search for outcomes funder and therefore uncertain on launch timing.	5 – DFID would not have any direct influence over the content of any possible DIB pilots.	5 – Evidence generation under this option would depend on likelihood of other donors supporting DIBs and providing DFID with appropriate data and insights. This is highly uncertain.	5 – DFID would not have any direct influence over the procurement of any possible DIB pilots, or competition in contracting, and would therefore be unable to drive value for money delivered through projects.
Option 3: DIB as commissioning option / Score: 16	3 – Staff resource would need to be provided by the DIBs team as well as commissioning teams across DFID in scoping out programmes suitable for DIBs. Where programmes and funds are managed externally, management contract amendments would be needed to reflect the change in the DIBs offer. DIB projects would be delivered within the financial envelopes of existing projects. DIBs team is able to support internal policy teams, but capability and capacity of external fund/programme managers in contracting and supporting DIBs is unknown and likely to be limited as this is a new contract type.	1 – Future capability would be developed as a number of commissioning teams would be exposed to DIB contracting and management.	4 – This would depend on the timing of programmes that may be adapted for DIBs commissioning, and availability of programme partners (e.g. fund managers) to take on a new commissioning tool.	3 – DFID would have some control over pilot content as this would only work across DFID priority areas/programmes. However, there is no guarantee that DIBs would be taken up by bidders for programme funding.	3 – The amount and relevance of evidence generated would be highly dependent on evaluation frameworks in existing programmes and how amenable these are to accommodating suitable evaluation methods.	2 – DIBs would be designed and delivered within existing DFID programmes and direct comparison of bids to other tools would enable us to ensure that DIBs are used only where they offer better performance. However, ability to assess value for money would depend on parameters set in current programmes.
Option 4: DIB Pilot, internal design / Score: 14	4 – Significant resources required in scoping out a project area, and designing a new programme. Cost of DIB designs to date has been up to £1m-£1.5m. Financial resource need would depend on the size of the DIB(s) designed. Some capacity and capability is available in the DIBs team, but we would likely need to buy in consultancy support for DIB structuring and research, especially if multiple DIB pilots are commissioned.	2 – An internally designed pilot would help us develop future capability in chosen project area(s), although there may not be scope to run pilots across DFID’s portfolio.	4 – Internal scoping and design is likely to require a significant amount of time to evaluate project areas and teams with capacity to support this. A first project would be likely to launch in late 2018 or 2019.	1 – Under this option, we would have complete control over pilot content. The DIBs team would be responsible for selecting appropriate project area(s) and launching projects with relevant policy teams.	2 – As the pilots would be designed internally, this presents an opportunity to generate evidence relevant to DFID policy (impact) as well as DIBs contracting (process), but only in policy areas selected for the pilot.	1 – Outcome areas for internally designed DIBs could be selected based on the possibility to compare VfM to other existing projects. DIB pilot projects could then be selected through a competitive process to ensure VfM.
Option 5: DIB pilot, external design / Score: 12	2 – Staff resource under this option would be provided by the DIBs team, with input from relevant policy/country leads to assess the quality of externally designed projects, fit with DFID priorities, and potential in generating useful evidence. Financial resource need would depend on the size of the DIB(s) designed. The current DFID DIBs team has the capacity and capability to deliver this and has been engaging actively with DIB designers.	2– A pilot funding externally designed DIBs would help us develop future capability in selected project area(s), although there may not be scope to run pilots across DFID’s portfolio. Since DFID would be joining projects at a later stage, this approach would not provide experience in designing effective DIB tenders.	2 – Timing would depend on project availability as DFID would not initiate project design. Initial scoping has identified a good selection of relevant projects already in development or ready to launch in 2017.	2 – DFID would contribute to pilot content as an outcomes funder, but other funders may also influence this and some projects may not be amenable to change at later stages in their design process. However, any available projects can be screened to ensure best possible fit with DFID priorities.	2 –A number of DIBs are ready but require additional funders to launch. This is an opportunity to spread DFID funds across several projects, in varying contexts and outcome areas. This would provide scope to learn how conditions affect DIB design and performance.	2 – We would rely on VfM considerations being incorporated by other donors and/or Dib designers. However, DIBs can be screened to ensure they deliver comparable results/value to other DFID projects, provided that we can identify appropriate comparators (e.g. price paid per outcome).
Option 6: Outcomes fund / Score: 14	5 – Significant staff and financial resource would be required to develop and manage fund with a number of outcome tied commissions (e.g. research/ baseline assessments prior to tendering). This is likely to require market building activities to ensure sufficient responses to tender. Some capacity and capability is available in the DIBs team. However, due to the size of the task, it is likely that we would need to bid for additional staff resource or outsource fund design and management to an external body.	1 – An outcomes fund would initiate DIB design across a number of outcome areas, and present an opportunity to learn about and build capability in DIBs commissioning, contracting, management and evaluation.	5 – An effective fund would likely commission a range of instruments outside DIBs (e.g. traditional PbR) to compare to, and involve a significant market-building and fund design stage. It could therefore only expect to launch first DIBs in late 2018 or 2019.	1 – Under this option, we would have complete control over pilot content. The DIBs team, together with an outcomes fund manager would be responsible for selecting appropriate outcomes areas and supporting bidders in generating projects in these areas.	1 – The outcomes fund would present an opportunity to generate a robust evidence base on the DIB instrument, including on how this performs (impact, process) compared with ‘traditional’ PbR, and on process of designing effective PbR competitions.	1 – An outcomes fund could drive VfM through tender design, with competition among suppliers for best outcome prices.

## Annex B – DIBs Pilot Programme Theory of Change

Impact
Value for money, better results for more poor people, money spent where it makes the most difference
Outcomes
Evidence: improved understanding of the impact and value of DIBs, understanding on how the tool is commissioned and managed and of relative costs and benefits compared to other tools
P.7 Dissemination of evidence and insights on the use and relative value of DIBs
More inputs
DFID able to make informed choices on how to use DIBs and compare the instrument to other PbR and non-PbR tools in commissioning and management, and emerging evidence on impact and value
Outcomes

A1: Other outcome funders, investors, service providers and intermediaries have designed quality DIB projects without DFID input, but require additional outcome funding.
A3: A pipeline of DIB projects can be identified that fit with DFID strategic priorities and represent good value for money
A5: Once funding is committed, DFID is able to adapt procurement practices to commission DIBs.
A6: DIBs projects are established, and operate for a sufficient time to generate data on management, effectiveness/ efficiency, risk transfer, delivery.
A2: Outcome funders, investors providers and intermediaries have characteristics/incentives/ behaviours outlined in the ‘DIB Approach’
A7: Valuable evidence/insight can be generated from a small number of pilot projects
A8: The type and quality of evidence generated on DIBs enables comparison to PbR and non-PbR tools and influence decision-making

DIBs contracted and start delivering to users
Outputs – programme-level

Greater flexibility & innovation in service delivery

Evidence on conditions for DIBs to work effectively
Results delivered for targeted service users
DFID (and other outcome funders) transfer delivery risk to investors
Evidence on effectiveness and efficiency of DIBs
Evidence on DIB arrangements (including payment models)
Evidence on DIB management arrangements
Evidence on commissioning process (e.g. resource and time needed)
Evidence on design process – gathered from projects assessed
Outputs – project-level

P3: Due diligence of project feasibility led by investor or outcome funder
P2: Robust DIB project design focused on specified results
P1: Robust identification of problem, cohort, and what good results and good design look like.
P.6 Contracting – DFID evaluates delivery structure, selects suitable projects and contracts
Processes/Activities
Investor
Service provider
Intermediary
DFID inputs
Design costs
Investor behaviour/skills
- Financial skills
- Performance management
- Planning skills
- Adaptability – ability to respond to change requests quickly
- Entrepreneurship
- Delivery
- Measurement

Investor finance

Provider attitude
- Experience with development work
- Recognition efficiency gains possible and needed
- Appetite for change
- Need for pre-financing

Provider project design

Outcome funder attitude
1. Recognition efficiency gains possible and needed
2. Appetite for change
3. Data-driven decisions
4. Ability to delegate project decision-making
Outcome funder finance

Intermediary
- Can help connect investors and providers, put deal together
- Can bring skills if providers or investors lack these (e.g. project design, or performance management)

DIB Approach
Outcomes funder
P.5 DFID identifies DIB projects seeking funding through consultation with DIB designers and outcome funders
P4: Results measurement and verification process identified
Comparable projects delivered through non-DIB structure
Monitoring and Evaluation framework
Inputs by other funders, service providers, intermediaries, investors
Problem
DFID is looking to drive improvement in the effectiveness and efficiency of international aid, including through the use of Payment by Results. However, PbR contracting transfers delivery risk to suppliers who may not be able to take this on, and requires advanced technical competency. This may limit the pool of suppliers bidding for PbR contracts, restricting innovation and driving up prices. Development Impact Bonds are an instrument designed to overcome PbR hurdles but DFID has no experience in commissioning these.
## Annex C – DIB projects identified for pilot

1. Kangaroo Mother Care DIB https://ec.vault.dfid.gov.uk/otcs/cs.exe?func=ll&objaction=overview&objid=5521130
2. Syrian Refugee Employment DIB
https://ec.vault.dfid.gov.uk/otcs/cs.exe?func=ll&objaction=overview&objid=5518803
Poverty Graduation DIB
https://ec.vault.dfid.gov.uk/otcs/cs.exe?func=ll&objaction=overview&objid=5517895
Physical Rehabilitation DIB
https://ec.vault.dfid.gov.uk/otcs/cs.exe?func=ll&objaction=overview&objid=5519610
1. Type II Diabetes Mellitus Prevention DIB https://ec.vault.dfid.gov.uk/otcs/cs.exe?func=ll&objaction=overview&objid=5518804
2. Girls’ Education DIB https://ec.vault.dfid.gov.uk/otcs/cs.exe?func=ll&objaction=overview&objid=5517896
## Annex D – DIBs Team Theory of Change for Development Impact Bonds and aligned DIBs Evaluation Framework (March 2017)

The table below shows how the evaluation questions have been developed against our Theory of Change for how DIBs can help enable more effective PbR programme. The priority evaluation questions for the DIBs pilot are shown in Bold, though we will be attempting to answer as many questions as is possible with our evaluation budget.

Theory of Change Element	Draft Evaluation Questions	Programme Level Evaluation	DIB Project Level Evaluations
A1: Challenges and barriers to designing and establishing DIBs can be overcome	What are the challenges? How were these overcome? / What conditions (context, characteristic, stakeholders) prevent DIBs from being implemented?	 / 
A2: Market allows DIBs to be developed and implemented, investors willing to pre-finance	What types of investors are supporting DIBs?	 - Partial
P1: Outcome Funders focus on results (i.e. outcomes) and not inputs	To what extent did the outcome funders shift their focus to outcome results and away from inputs? If so, why? If not, why?	
	How was risk allocated within the DIB, and how did this affect the behaviour of the outcome funders? To what extent can delivery and innovation risk be transferred from government and providers to investors through DIB structure?	
P2: DIBs enable more service providers to deliver on a payment by results basis	To what extent does the DIB model overcome the challenges that prevent some providers from delivering on a PbR basis? To what extent do DIBs help build supplier capacity in delivering on PbR contracts?	
	Does this result in better competition to deliver results that are important to donors? To what extent is the DIB model enabling more providers to deliver on a PbR basis?	No – not purpose of pilot
P3: DIBs create incentives for service providers to focus on producing results (i.e. outcomes)	What were the incentives and how did they influence service providers? To what extent did the DIB create incentives for service providers to focus on outcome level results? If so what was the effect?	
P4: There is greater innovation and flexibility to delivering services	To what extent did the focus on outcomes create more flexibility, autonomy and innovation within the interventions? What factors enabled (or prevented) flexibility and innovation within the interventions?	
P5: Programme implementation improves and is more effective and/ or more efficient	To what extent were programmes implemented through DIBs effective?	 Aggregate from project level data or generate	 (required)
	What were the programme’s outputs? To what extent were these produced as planned? / To what extent were programmes implemented through DIBs efficient? To what extent did the DIB model (or other factors) cause this to happen?		 (ideally)
A4: Different actors and stakeholders (service providers, investors, donors) have the time, capacity and resources to act and cooperate in ways which make the DIB work and maximise their particular comparative advantage	Who were the main stakeholders in the DIB? What incentives were they under? What role did they play? To what extent did this role make maximum use of their comparative advantage? How did this effect how the design and delivery of the project and its results?	
	How have capabilities and skills of the DIB participants (providers, investors, outcome funders) changed (positively or negatively) as a result of the project? Do DIBs help build supplier capacity in delivering on PbR contracts?	
	What value do investors add beyond providing finance? (E.g. Do they provide better performance management, and incentivise providers to focus on outcome measurement and delivery?)	
A5: Data required is available and evaluations are resourced and conducted as needed	What was the effect of the DIB on data availability and quality?	
IMP1: Expected outcomes were produced	To what extent and for whom did intervention achieve its intended outcomes?		(required)
IMP2: Expected outcomes were produced more effectively than with other approaches	To what extent was the DIB more effective in delivering the outcome than more conventional aid instruments (e.g. PbR, pay for service, grants)	If possible
IMP3: Expected outcomes were produced more efficiently than with other approaches	To what extent was the DIB more efficient in delivering the outcome than more conventional aid instruments? / Did programme result in a lower cost/outcome compared to alternative approaches?	If possible
	How does the cost per outcome paid compare to the actual costs incurred by the partner to deliver the outcome?	(Project monitoring)
IMP4: With additional unexpected positive outcomes	Did the DIB produce any unintended positive outcomes?	 Aggregate from project level data or generate	 Required where evaluation is happening
IMP5: And without unexpected negative outcomes	Did the DIB produce any unintended negative outcomes? E.g. for marginalised or harder to reach beneficiaries or because of focus on narrowly defined result?
IMP6: And in ways that generate learning for use of DIBs and PbR in other contexts	What lessons were learned that could be relevant for DIBs or PbR in other contexts? Which aspects of DIBs make them a more effective tool? Under what conditions (context, characteristics, stakeholders) do DIBs work best? And why? / Are there negative impacts of using a DIB?	
A6: Outcomes produced are at least as sustainable as outcomes produced using other approaches	To what extent are the outcomes produced by the DIB likely to be sustainable? / How does this compare with the sustainability of outcomes produced by other aid instruments?		 (ideally part of project level evaluation)
Value for Money	Did benefits of the DIB project justify its cost? What were the costs and benefits of using the DIB structure?	
	How do the whole life costs: benefits of the DIB compare to other mechanisms?	Unlikely to be possible
	How does the cost of investor finance in a DIB compare to commercial lending or organisations self-financing PbR contracts?	 or via monitoring

Key	A:	Assumption
P:	Process
IMP:	Impact