Global SME Finance Initiative: Annual Review 2017

Date Programme started: February 2012
Dates review undertaken: 28 March – 30 June 2017

Node Ref: 8895017

Annual Review - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Global SME Finance Initiative
Programme Value: £75 million		Review Date: June 2017
Programme Code: 202935	Start Date:28/02/2012	End Date: 31/03/2021

Summary of Programme Performance
Year	2013	2014	2015	2016	2017	2018	2019	2020
Programme Score	B	A	A	A	A
Risk Rating	Medium	Medium	Medium	Medium	Moderate

Summary of progress, lessons learnt and headline actions

Description of the Initiative
The DFID-IFC Global SME Finance Initiative aims to bridge the gap in financing to small and medium-sized enterprises (SMEs), especially in more challenging environments and market segments, including fragile and conflict-affected states (FCAS) and women-headed businesses. The Initiative does this by providing direct funding lines, risk-sharing facilities and performance-based incentives (investment services or ‘IS’) with a view to changing behaviour of bank and non-bank financial institutions (partner financial institutions, or ‘PFIs’) in lending to SMEs in the target geographies and segments. The Initiative also provides advisory services (AS) - expert knowledge in building capacity of the PFIs to better understand and price the risks of lending to SMEs, including supporting specific focus on SME sub-sectors where there is a need (e.g. women-owned SMEs). In addition, the Initiative supports innovation, and establishment and strengthening of financial market infrastructure (credit reporting bureaux and development of secured transactions and collateral registries) to address more systemic constraints on SME financing in the target countries. The Initiative also incorporated a technical assistance pool to fund three of 14 G-20 SME Finance Challenge Winners for scaling up technology-based solutions. DFID is looking for additionality of the Initiative in mainly two areas: (i) catalysing development finance institutions (DFIs) and private sector lending in support of SMEs in FCAS and (ii) women-headed businesses, to drive job creation and female economic empowerment. This component of the Initiative was completed last year.

This is a programme run by the International Finance Corporation (IFC), part of the World Bank group, in which DFID is an anchor investor. The Initiative does not involve any new legal entity and is managed through a trust funds structure. IFC sees the Initiative as a “blended finance” initiative. Concessional funding from DFID and the Netherlands Ministry of Foreign Affairs has helped mobilise investment from IFC and the European Investment Bank (EIB).

Process of Review
This Annual Review includes the findings from the field visits conducted by DFID private sector advisors in four country offices (Burma/Myanmar, Côte d’Ivoire, Tanzania and Zambia), the most recent semi-annual progress reports from IFC and interviews with the IFC Headquarters and regional staff, discussions with DFID country office representatives, the Female Economic Empowerment lead in the Growth and Resilience Department, PSD’s Results and Evaluation Adviser, the Statistics Adviser of the Economic Development Cabinet and the PSD Adviser in the International Financial Institutions Department responsible for DFID’s institutional relationship with IFC and the World Bank Group.

Summary of progress

Performing extremely well in reaching SMEs in IDA and FCAS countries: As of March 2017, the Initiative supported a total of 104 projects (96 of which are funded by DFID) in 28 countries by providing investment and/or technical assistance. The 96 projects funded by DFID include 33 investment projects and 63 advisory projects. Overall, 13 projects have been completed and another 65 are in implementation, with the balance moving into implementation once negotiations are complete and approvals obtained. About 75% of the projects funded by DFID are in “IDA” countries – the world’s poorest developing countries eligible for funding from the International Development Association (IDA). The rest of the projects funded by DFID are in IDA-blend countries, which also include large segments of underserved SMEs. Of the 96 projects funded by DFID, 46 (or 48%) are in FCAS (10 advisory projects and 36 investment projects versus a logframe target of 25%.

Good performance in mobilising investments in the PFIs in FCAS: Out of the total of 58 partner financial institutions (PFIs) supported by the Initiative, DFID supported 55 PFIs of which 23 are in FCAS countries that represent some of the hardest-to-reach markets like Afghanistan, Bangladesh, DRC, Liberia, Malawi, and Sierra Leone. In total, the Initiative is working with PFIs in 9 FCAS countries, and is working on building financial infrastructure in 13 markets, including in 7 FCAS countries. The Initiative’s investment and technical assistance supported PFIs in providing £4.39 billion of commercial loans to 97,607 SMEs in FCAS.

Gender focus is improving. Implementation of the Gender Action Plan has focused IFC’s efforts on gender. Approximately one-third of the Initiative’s projects (32 out of 104 projects – including 14 investment projects and 18 advisory projects) now have a dedicated gender component. This includes 30% of the projects in Africa, 38% of the projects in South Asia and 22% of the projects in MENA. This is beginning to be reflected in results.

Since 2015, the number of loans to women SMEs has increased by 62% and the volume of loans by 72%. As of December 2016, the Initiative met 98% of its milestone for the number of loans to women-owned SMEs set for this period, and 24% of its overall target for this indicator. At the same time, the Initiative has significantly surpassed its milestone for the volume of loans to women-owned SMEs, and it has met 75% of its overall target for the volume of loans facilitated. This indicates that the average loan size for women-owned SMEs is higher than anticipated when targets were set. An increased average loan size for women-owned SMEs is a positive change that may indicate a diminishing gender gap in loan sizes among the Initiative clients. More analysis is needed to evaluate the growth in the average loan size for women-owned SMEs. It should be noted that while the Initiative’s work on financial infrastructure (such as collateral registries) does not have specific gender components, it disproportionately helps women borrowers who have fewer fixed assets available to provide as collateral for loans. The financial infrastructure projects take a longer time period to report results due to the necessary legal/regulatory work that precedes the establishment of credit bureaux and collateral registries, and the time needed for PFIs to develop the appropriate products using these registries. Currently only 4 out of 18 financial infrastructure projects report results, and as more projects become mature enough to report results, it is expected that these projects will show a solid impact on increasing access to finance to women-owned SMEs.

Exceeding target for volume of loans and good progress on number of loans. The Initiative has exceeded its 2016 logframe volume target and is working towards meeting the targets for the number of loans. The Initiative is well on track to meet the longer term targets. The Initiative facilitated 141,626 SME loans (79% of milestone target) totalling US$10.52bn (147% of milestone target). Of these loans, loans to women SMEs were 11,779 (98% of final target) totalling US$619.31m (313% of the milestone target).

The number of SMEs reached: The PFIs supported by the Initiative are estimated to have reached nearly 141,626 SMEs at December 2016. While these results fell short of the logframe target of 179,463 for March 2016, it should be noted that the milestone for the number of SME loans set for 2016 represents 90% of the Initiative’s total target for this indicator. Despite not meeting the 2016 milestone, the Initiative has met 71% of its overall targets for this indicator. It is also notable that the number of loans to SMEs reported as of December 2016 more than doubled compared to the results reported as of December 2015 since more clients have projects in advanced implementation stage that are able to report results. Therefore, despite not meetings the 2016 milestones, the Initiative seems well on track to meet the end term target of 200,000 SMEs by 2019.

Jobs target: Loans to SMEs facilitated under the Initiative are estimated to have sustained and created an estimated 442,000 to 666,190 additional direct jobs compared to the milestone target of 700,000. This is mainly due to longer gestation in loans leading to jobs than was originally anticipated in the Theory of Change. See ‘Main issues or challenges’ for a discussion of job data estimation.

Financial absorption has been on forecast: All of DFID’s contribution to the Initiative has been disbursed on schedule and fully committed as of 30 June 2016. Going forward, DFID will work closely with IFC to monitor the disbursements to the activities identified. We have received statements showing disbursements to activities identified as at 31 March 2017. (EDRM 5741917 AS and EDRM 5706933 IS).

Efficiency in use of DFID funding: The total number of PFIs and financial market infrastructure projects supported under the Initiative has exceeded the logframe targets by over 3 times. This is largely attributable to minimisation in use of DFID-funded subsidy and to the relatively smaller size of projects in FCAS (and IDA countries) than was anticipated in the programme design.

Strong mobilisation of funding from DFIs and the Initiative’s PFIs: Every £1 of DFID concessional funds has helped mobilised £13.5 of commercial funding from IFC and other investors. DFID’s concessional funding for the investment component of the Initiative (£40m, or US$59.48m) has mobilised approximately £501m (US$802m) of DFI investment.

Funding Mobilised in line with Logframe - 2017(*)
	Millions
	US$	£
IFC	596	372
Other commercial funds managed by IFC	90	56
European Investment Bank	100	63
The Netherlands	16	10
Japan	0.3	0
TOTAL	802	501

* Based on an exchange rate of US$1.60 = £1.00 (the exchange rate used at start of the Initiative).

Since the last annual review, the Initiative committed one new project and two new projects have moved into implementation. Additional funding was provided to two advisory projects in Bangladesh. Over the last year, one advisory project was completed, and one was terminated due to challenging country conditions. At the time of this review, 23 investment and advisory projects are in the programme pipeline in 16 countries.

In Africa, IFC are working to embed learning on SME finance and to enable systemic application of these learnings across the continent. IFC is also working on a country-by-country basis to develop or strengthen credit bureaus and collateral registries with the overall goal to improve financial infrastructure that will ease the conditions for banks to lend to SMEs. The Initiative is supporting 22 financial infrastructure projects, 18 of which are funded by DFID. While the implementation of such programs takes long time given the need to coordinate with multiple private and government stakeholders, the financial infrastructure projects in Nigeria, Liberia, Malawi and Afghanistan are starting to report results.

In East Africa, the Initiative is moving to focus on digital banking which provides an inexpensive delivery channel to reach smaller SMEs and more women SMEs in particular, on thinking around the banks’ value chains and further capacity building to contribute to innovation and increase competitiveness in SME banking.

In West and Central Africa, the Initiative has played a major role in supporting banks especially in FCAS and has paved the way to creating markets and opportunities, despite starting from a low level in terms of capacity of PFIs to assess SME risks and increasing macroeconomic headwinds such as inflation, government debt and deficits, and government payment arrears which impacts down the supply chain.

In South Asia, the Initiative continues especially in the advisory component to work with banks such as in Burma (Myanmar) on lending, risk management, treasury operations, digital and core banking systems. In Bangladesh and Pakistan, the Initiative has worked with banks that are increasing their women SME businesses and is working with the management on rolling out their women SME banking businesses.

Main issues or challenges faced

Ambitious milestone targets: As mentioned in previous annual reports and following the mid-term review performed by Dalberg Global Development Advisors and Beecher Analysis Group, the milestone targets in the Initiative were ‘front-loaded’, meaning that progress was assumed to be linear and targets would be achieved in a consistent linear progression. Experience under the Initiative has shown that much ground work was needed in the initial years to enable progress on some of the targets such as the gender targets. The gender action plan being implemented (see Section F: ‘Gender Considerations’, below), the use of the projected reflows under the programme (see ‘Treatment of potential reflows’, below) and improving data collection (see Section I: ‘Monitoring and Evaluation’, below) will work towards keeping the Initiative on track toward meeting these targets.

Ongoing challenge of achieving scaled impact on gender: As outlined in the summary of the progress of the Initiative, The Initiative is continuing to focus on implementing the gender action plan, which includes not only increased focus on women SMEs in the Initiative’s investment projects, but also on financial infrastructure projects that can have a disproportionate positive impact on women SMEs (e.g. collateral registries) and capturing and providing better quality gender disaggregated data. The gender action plan, improvement on tracking women SME data by PFIs and the expected results seen from the activities under the Initiative in prior years should allow the improvement in gender results which the Initiative is already beginning to experience.

Jobs-created figures are very hard to obtain: Over the last two years, IFC have worked extensively trying to estimate the number of jobs created and supported through their loan portfolio using econometric modelling. The Initiative has developed two models to extrapolate jobs growth results (outlined in Section B and detailed in EDRM No. 5486044). IFC believes these models give a more reliable indication of jobs created as a result of the Initiative. IFC updated last year’s model to include more data and to measure jobs supported in addition to jobs created. The current estimates are based on a database of more than 50,000 observations, which is the largest possible database for such indicators. This has made the estimates much more robust. Furthermore, the extrapolation model will be refined throughout the life of the Initiative as more data become available. IFC are working to improve the estimations, including preparation of a peer-reviewed methodology note for jobs extrapolation to be published in an industry journal.

Lessons learnt from the Initiative

Concessional funding can be catalytic in mobilising DFI investment in challenging environment: Since its inception, the Initiative has helped structure 33 SME finance investment deals using £40m (US$59.48m) of DFID concessional funds. The funds were invested alongside US$523.3m from IFC and about UDS$27.5m from other donors to risk sharing facilities. DFID funding is supporting investment projects with 32 partner financial institutions (PFIs) in 17 countries.

Financial institutions generally need risk-sharing and technical assistance more than credit lines in lending to SMEs in FCAS: Lending to SMEs in FCAS is generally constrained more by high perceived risks and transaction costs and low technical know-how than lack of funds. Risk-sharing help stimulate the initial appetite of financial institutions to get in to SME lending and over time develop a better understanding of the risks involved and price their products to reflect the actual involved. The technical ability of the financial institutions in FCAS is generally very weak and needs technical assistance in developing systems, processes and products for lending to SMEs.

Women entrepreneurs need more than capital to start and grow business: Women headed businesses are generally smaller than male-headed business, and have less access to professional support in running the business. Therefore, they need non-financial services like training and mentoring support in different areas of business, including accountancy, business development, and product design. Non-financial services are presently outside the remit and constrain the Initiative’s ability to support women-headed businesses in a more meaningful way.

IFC representation on governing bodies of banks has a big positive impact: PFIs have expressed how helpful it has been having IFC on the governing body. It increases international actor’s trust of the banks, and IFC helps facilitate connections with international financers. IFC are also valuable in contributing towards discussions on experiences and difficulties, such as issues with tax which can be communicated via the IFC to governments and central banks.

Loans to under-served SMEs have greater impact on job creation than loans to SMEs that are relatively better served by formal financial institutions: Early indications suggest that loans to first time borrowers and under-served SMEs are more effective. For example, it is estimated that loans to SMEs in FCAS and low-income countries (LICs) that were relatively more credit-constrained (e.g. first time borrowers) created twice as many jobs as loans to SMEs that previously had access to formal commercial loans. The largest amount of growth in jobs within SMEs has been within the smallest firms of between 5 and 15 employees. The larger firms are more likely to have acquired loans in the past and are therefore not reflected in the data being collected.

IFC role is more effective when accompanied by strong engagement through the tenor of the loan than just at the point of disbursement of the loan: Providing lending capital is not enough and the PFIs need continuous technical support in adjusting their risk models to realities of the market. Continued careful attention is required to ensure that capital support is effective in bringing about sustainable behavioural changes. A key aspect of ensuring additionality of IFC support is to promote strong engagement from the IFC contact point designated for partner banks.

Headline future actions

Continue focus on gender: IFC is building a strong awareness of working with women SMEs with their PFIs. IFC is seeing results of earlier work with PFIs including work on risk scoring, credit assessment and underwriting. As noted in the mid-year report, some of the results under the Initiative are not linear and we expect to see the benefits of earlier groundwork with respect to reaching women SMEs, particularly following the Gender Action Plan adopted by IFC. Although DFID’s initial funding commitments to the Initiative have been fully disbursed, DFID will work to support IFC’s existing efforts with PFIs on gender and to strengthen the gender focus under the Initiative, through ongoing dialogue between the SRO and IFC including, for example, agreeing the use of reflows to support women SMEs.

Increase demand side work on gender: Women entrepreneurs are constrained by a myriad of factors including access to finance. IFC have raised concerns that the Initiative’s inability to provide more direct advisory support to SMEs is a significant limiting factor in IFC’s ability to provide well-rounded (financial as well non-financial) support that women entrepreneurs need. As an ongoing effort, DFID will encourage IFC to consider partnerships with programmes that work with smaller or informal women SMEs that are working to scale them up – almost like identifying “pre-pipeline” partners in the target countries.

Agree use of expected reflows: As of April 2017, IFC estimated that up to US$69m (£53m) could be potentially returnable to DFID from 2017 to the end of the Initiative. To date, IFC have been recycling funds arising as a result of DFID’s concessional financing, but this is expected to become increasingly difficult as the Initiative gets closer to the scheduled end date, particularly beyond 2019 as the tenor of the investments becomes an issue hindering re-investment. Discussions with IFC have identified and assessed four possible options for treatment of funds when the tenor becomes a constraining issue:

  1. Extend the end date of the Initiative to March 2024 to allow the Initiative to support new loans and risk-sharing facilities.
  2. Re-purpose the reflows for rebates, advisory services and monitoring and evaluation (M&E), with advisory services expanded to include research and development activities to support specific priority areas (e.g. Women SMEs) and enabling a more flexible pricing for advisory services to increase client up take of these services.
  3. Roll over funds from reflows into a separate dedicated trust fund for supporting SME investment (deployed into other IFC-managed programmes).
  4. Return the reflows to DFID in several tranches over a specified time period.

Following evaluation of the impact of each option on SME financing and consideration of obtaining the greatest value for money, DFID believes that the second option, combined with an extension of the Initiative to March 2024, would provide the best use of the reflows. The SRO and the programme manager will work with IFC to agree details needed to implement this option and to submit to ministers for approval an addendum and no-cost extension to the Business Case by the end of 2017.

Align the annual review reporting cycle under the Initiative with IFC’s results collection timeline: Data used in the annual review is preliminary data reported by IFC at the end of May of each year. In this annual review, for example, project portfolio and funding mobilised data is as of March 2017, while results are as of December 2016. This preliminary data may not reflect reports from all the PFIs under the Initiative. The final audited data are not available until late August/early September of each year. IFC and DFID’s SRO and programme manager will discuss how to better align DFID’s annual report cycle with IFC’s results collection and reporting timeline, which may include a future reports being issued later in 2017 or early 2018 to capture audited data and reviews after that occurring on an annual basis from the last report.

Review and amendment of logframe. Because the Initiative has already reached some of the milestone targets for several output indicators, DFID will work with IFC to see whether targets for the remaining years of the Initiative should be revised in light of the performance of the Initiative against the original assumptions, with the aim of using any revised targets for the next annual review. The targets should also take into account the intended use of reflows expected under the Initiative.

Promote linkages and share lessons learnt with others. As an ongoing effort, DFID will work to increase the linkages between the Initiative and its other programmes, particularly in terms of gender, job impact and mobilisation of funding, including for example, CDC, Financial Sector Deepening Africa (FSDA), the ‘billions-to-trillions’ agenda and the Financial Sector Reform and Strengthening (FIRST) programme. This was also mentioned in some of the reports from the DFID client visits. The SRO will work on sharing learnings from the Initiative more widely. This can include, for example, learnings from the G20 Challenge Winners component of the Initiative, working with other organisations such as the Global Banking Alliance for Women to organise roundtables and other events.

Explore lending and support options in local currencies. Most developing countries face volatility in the exchange rates. Given the lack of appropriate hedging mechanisms in those countries, this volatility poses significant risks to PFIs and SMEs in borrowing in foreign currency. IFC has reported that often the banking sector is not able to provide local currency loans in the target countries. IFC will explore local currency loans and currency risk management support to PFIs in the markets where currency risk is a critical binding factor on SME financing. Challenges in providing local currency options include the pricing gap between local currency and hard currency funding, the availability of currency swaps to enable hedging of currency exposure. The new private sector window will allow new local currency instruments and enable greater lending and support options for SMEs in local currency going forward.

A. Introduction and Context (1 page)
DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3716779.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5351599.xlsx

Summary of Programme

How it works – what it does
The Initiative was created in March 2012 with the objective of increasing access to finance for SMEs, and as a result creating and supporting new employment opportunities. The Initiative supports scaling up of lending to SMEs through partnership with mainstream commercial banks, leasing companies and other non-banking finance companies in developing countries. The Initiative provides banks with risk sharing mechanisms, credit enhancement and technical assistance as well as improved credit history information and referencing in support of scaling up their financing to SMEs.

The Initiative is made up of three components:

1. Risk sharing and investment component (£40m): Combining returnable grants and investments to help scale up lending to SMEs. This is done through (a) the risk sharing, which guarantees to cover up to 50% of the loss suffered by the PFIs in the SME lending portfolio, (b) performance based incentives to achieve targets, e.g. women headed SMEs and (c) direct funding lines.
2. Advisory Services (£32m): IFC provides capacity building support to the PFIs on a 50% cost-sharing basis and support for changes in the broader financial support infrastructure such as collateral registries or credit bureaux.
3. Financing for G20 SME Finance Challenge Winners (£3m) DFID provided funding to three of the 14 G-20 SME Finance Challenge Winners for scaling up technologies which may help SME finance. Part of DFID’s funding contributed to the establishment of the SME Finance Forum. This component is completed. All grants made under this component of the Initiative have been utilised. The final results were shown in last years’ annual review and are also shown in Section C of this annual review, below for ease of reference.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
Results data relating to loans provided, SMEs reached and volume of investments mobilised from DFIs reported in this Annual Review relate to the year ending December 2016. The Initiative has measured these results based on outstanding loans as opposed to disbursed loans starting in 2015. IFC results measurement system also switched to using the Annual Reach Survey to collect data from the PFIs which is based on year-end information. IFC highlighted that the new method of measuring results based on outstanding loans would lead to a drop in results compared to those reported in the past years and the logframe milestone targets which are set based on the basis of disbursed loans, but that this would more accurately reflect the impact of the Initiative. Back-dating this approach to prior years would be complex and disproportionally resource intensive.

The performance of the Initiative against the milestone outcome indicators is listed below:-

Outcome Indicator 1: Number of SMEs reached with loans, of which (a) 25% to women headed or owned businesses, and (b) 25% in the fragile countries and frontier markets

Results presently short of overall milestone target following change in reporting methodology: Following the change in results reporting methodology, 141,626 SMEs were reached as of December 2016 compared to the logframe target of 179,454 set for March 2017. The IFC expect the Initiative to gather momentum once all projects reach maturity over the next two years and are confident that the target of 200,000 SMEs can be reached in 2019. It is notable that as of December 2016, only 4 of the 18 financial infrastructure projects were at an advanced enough implementation stage to report results. As these projects mature, the Initiative expects its reported SME reach to increase significantly.

Almost 70% the SME loans made were in FCAS markets, which is significantly greater than the targeted 25%. The result of one credit bureau project in Nigeria contributed 17% of this overall result. This project is working with 20 PFIs and reported approximately 24,000 loans. The Initiative has reached 11,779 women owned SMEs vs the revised target of 12,000, i.e. 98% of the target.

Outcome Indicator 2: Monetary value of additional principal amount of SME loans made by PFIs through the investment and advisory components of the Initiative and through the development of financial infrastructure, of which (a) volume of loans outstanding to women headed or owned businesses, and (b) 25% in the fragile countries and frontier markets

The Initiative has exceeded its milestone targets for the volume of loans facilitated to SMEs, including for women and in FCAS: The Initiative has already met and exceeded its overall target for the volume of SME lending (exceeded by 47%) Including the target for FCAS (exceeded by 31%). The Initiative is on track to meeting its overall target for volume of lending to women-owned SMEs.

The results for women SMEs and for SMEs in FCAS significantly surpassed the respective milestone targets, and the overall targets. The monetary value of additional loans to SMEs headed by women at £387.07m was almost 3 times the set target of £123.75m. The monetary value of additional loans to SMEs in FCAS was almost 4 times the set target of £1,121,646,391. Overall, 67% of the Initiative’s results for the monetary value of loans made have been in FCAS markets, almost treble the targeted 25%.

Outcome Indicator 3: Number of new jobs created and supported by SMEs benefiting from the Initiative

Underperforming: There are limited data on jobs created since PFIs typically do not collect such data from SMEs, and even those that track such data do not use a consistent methodology. To address this issue, IFC developed a jobs extrapolation econometric model to estimate the number of jobs created and supported as a results of the Initiative’s activities. IFC extrapolations indicate that 442,005 – 666,190 jobs have been created as a result of the Initiative’s activities. In addition, 1,023,256 jobs were supported as a result of the financing in 2016. These results are based on a dataset comprising of more than 50,000 observations, and the multipliers from the econometric model are robust to various regression methodologies and specifications (e.g. Heckman selection model, fixed effects). As a result, the model now is better able to estimate the actual number of jobs which have been created as well as the jobs supported. Furthermore, modelling for jobs growth to predict the number of jobs created by 2019 shows that the Initiative should be able to comfortably meet its 2019 target of creating one million jobs.

Aggregate Output Score and Description:
The overall composite score across the three programme outputs is estimated at A.

Two of the headline outcomes (outcome indicators 1 and 3) fell short of their targets due to the change in reporting methodology imposed which was not accompanied by any change to the logframe targets. Two of the Initiative’s priorities are to have a significant impact on gender and in FCAS and frontier markets. The Initiative has been significantly outperforming its targets in these areas. Furthermore, the Initiative remains likely to achieve its long term milestones for 2021 due to the non-linear and exponentially increasing results. There still remains reason to believe that the projected output results will not only be reached but exceeded, due to the lower than expected average size of DFID funds allocated to more projects enabling higher outreach.

Notwithstanding the relatively better performance on the Initiative’s main deliverables i.e. FCAS and gender, there remains substantive challenges to overcome under the new reporting methodology, particularly on employment, and evaluation challenges surrounding overall impact measurement.

Lessons: Provided in the Summary Sheet
Actions: Provided in the Summary Sheet
Has the logframe been updated since the last review? Following the MTR, the Initiative has redefined its gender targets for the volume of loans, and it has extended the timeline for meeting its overall targets from 2019 to 2020.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Risk sharing mechanism (s) to catalyse investments from DFIs in the selected PFIs for scaling up SME financing on commercially sustainable basis in the 15 target countries, including in the high risk environments of fragile/conflict-affected countries.
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	50
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Year 6 / (March 2017) / Target	Progress (December 2016)	Score
1.1: Cumulative number of Partner Financial Institutions (PFIs) supported with risk sharing and funding mechanisms.	15 PFIs	55 PFIs	A++
1.2a: Volume of additional funding mobilized for SMEs through PFIs under the investment facility component (concessional funding).	£1,436bn	£1,987bn	A
1.2b: Investment leveraged from DFIs and PFIs as a multiple of the size of the risk sharing funding from DFID.	£323m	£501m	A
1.2c: Share of fragile countries and frontier markets in (a) –see note below	£359m	£267m	A-

Note: The indicator in 1.2(c) includes investment services only. The share of fragile countries and frontier markets supported by advisory services and financial infrastructure projects is much higher – 57% (36/63) of advisory projects are in FCAS vs 29% (10/33) of investment projects.

Key Points
- More than treble the number of PFIs/banks and non-banks financial institutions supported. The initiative has more than exceeded not only the set milestone for indicator 1.1 but also trebled the overall target of the programme. These investments were supported by DFID’s concessional funding of £40m with approximately half on loans and half on RSFs.
- The Initiative is meeting its target for IS portfolios in overall volume of SME loans generated. The IS portfolio is exceeding targets by 66%.
- The Initiative has considerably exceeded its target to mobilise investment from DFIs. The facility has mobilised £501m of DFI investment, exceeding the target of £323m by £178m. This investment came from the IFC managed funds (£372m, a 198% increase from the original commitment of $200m. An additional £56m of other commercial funding managed by IFC was invested in the Initiative’s projects. EIB made a £63m envelope commitment, primarily for RSFs in Africa, and a first investment in ETF RSF was committed in April 2016. The Netherlands committed £10m for investment services and the Initiative received the first disbursement in December 2015.
- The Initiative is working in the most difficult geographies where investment is most needed. The Initiative has significantly exceeded the targets for work in fragile countries and frontier markets, more than trebling the targeted PFIs in FCAS.

Output Title	Capacity of partner banks and Non-Banking Financial Institutions (NBFIs) strengthened through well-targeted technical assistance to partner financial institutions in risk management, product development, and improvement in of business processes, and support for development of financial market infrastructure such as credit bureau and collateral registry in the identified.
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	45%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Year 6 / (March 2017) / Target	Progress (December 2016)	Score
2.1a: Cumulative number of PFIs and financial infrastructure projects covered with advisory services and activities.	34	63	A++
2.1b: Cumulative number of PFIs and financial infrastructure projects supported with advisory services in the fragile countries and frontier markets	9	32	A++
2.2a: Volume of SME loans generated by PFIs / financial infrastructure covered by advisory services plus IFC's non-concessional financing.	£3.1bn	£4.6bn	A++
2.3a Percentage of PFIs reporting that the growth of their SME loan portfolio is greater than the growth of the bank's commercial loan portfolio. / 2.3b Percentage of PFIs with the NPL rates over 10% at baseline that report a lowered NPL ratio (at the SME portfolio level).	(a) 65%-75% / (b) 65%-75%	(a) 73% / (b) 86%	A+
2.4a: Number of Credit Bureaux (CBs) and Collateral Registries (CRs) created or significantly strengthened. / 2.4b: Credit Bureaux: / (b1) Total number of firm inquiries / (b2) Total number of loans to firms / (b3) Total value of loans granted to firms / 2.4c: Collateral Registries: / (c1) Number of SME loans by CRs / (c2) Value of SME loans by CRs	(a) 14 / (b1) 0 / (b2) 0 / (b3) £0 / (c1) 40,000 / (c2) £4,792m	a) 16 / (b1) 0 / (b2) 24,078 / (b3) £1.3bn / c1) 5,197 / c2) £231.2m	B
2.5: Number of PFIs provided with technical support for strengthening capacity to identify, screen and support SMEs that either contribute to low carbon and climate resilient outcomes or have neutral impact.	7	7	A

Key Points

- The Initiative has exceeded the milestone target for the number of PFIs and financial infrastructure projects supported. The initiative has significantly exceeded the target for number of PFIs supported with advisory services.
- Advisory services are needed to increase lending to women SMEs. Of the overall volume of loans to women SMEs, 55% come from projects supported by advisory services (£212m vs total women SME loans of £387m).
- Risk sharing activities need the support of advisory services. IFC have stressed that it is very important to provide advisory services to go along with their risk sharing activities. IFC have worked a lot to improve their on boarding and to improve their partners understanding of the facility in order to maximise take up and the benefits to the clients.
- Pricing incentives have proved effective at increasing uptake of advisory services. IFC offer performance step downs where clients get pricing incentives contingent upon them meeting certain targets. This has been effective in driving partners in thinking about their use of funds and the expansion of their programmes. This has also assisted in the creation of very clear commitments which pave the way for the requirement of advisory services.

Output Title	Development of technology based approaches and solutions to drive SME financing and development in the identified developing countries.
Output number per LF		3	Output Score	A+
Risk:		Minor	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

G-20 Finance Challenge Winners
This component of the Initiative has finished as all of the challenge winners have completed their projects. The results of this component were set forth in last year’s annual review (EDRM 5488068).

Key Points
- Although, this was a relatively small component of the Initiative in terms of share in funds allocated, it is very strategic given the focus on harnessing of innovation and technology in SME lending.
- Good take up of the psychometric tool. One of the challenge winners developed a psychometric tool for use in the credit assessment process. The tool has been adopted by over five times the targeted number of banks and non-bank financial institutions, and over twice the milestone number of SME loan applications have been processed and approved using the tool. This is encouraging given the promise of the psychometric tool, especially in poor countries with weak credit history information sharing mechanism (e.g. credit bureaux).
- Many SMEs in fragile countries have successfully won large procurement contracts.
- Many SMEs have been reached through credit counselling and/or facilitation. The Initiative was able to reach over 15 the targeted number of SMEs through credit counselling and/or facilitation.

## D: VALUE FOR MONEY AND FINANCIAL PERFORMANCE (1 page)

Performance of key cost drivers:

The key cost drivers for both investment and advisory services relate to:

1. Overall program management,
2. Implementation of individual projects and transactions, and
3. Monitoring and evaluation activities.

The Initiative’s delivery model emphasizes partnerships between global and regional teams of the IFC. This model ensures the global team leverages and work closely with the regional managers and staff to select, approve projects, as well as deploy DFID funding. Assigned regional staff are responsible for driving the programme at the regional and country levels, while the global team leads the overall coordination supporting regional teams as needed to ensure sufficient delivery capacity and cost effectiveness.

The Initiative reduces the cost for DFID by utilising IFC’s existing investment apparatus. All investment projects are managed by IFC Investment and Portfolio Officers, with the support from the SME Initiative global team for portfolio-level supervision, oversight and reporting to DFID. The vast majority of the investment costs are funded by IFC or by project fees thus reducing the cost of deal origination and execution for DFID.

The operating expenses for the Initiative’s investment and advisory services components are leveraged by contributions from PFIs, and in the case of investments, other IFIs and investors. These are expected to be further leveraged as the Initiative scales up and the average administrative costs decline relative to the volumes invested.

Overall management fee paid to IFC has remained unchanged and competitive at 4.6% of the overall programme cost, including a 3% centrally mandated Trust Fund Management Fee paid to the World Bank for providing back-stop and trust fund account management support.

Performance against Value for Money (VfM) metrics
The Business Case considered Value for Money under the specified components listed in the table below. The volume of investment leveraged from DFIs for every £ of funding from DFID substantially exceeded the set target (13.5 vs a target of 8.5). The volume of lending to SMEs by DFIs for every £ of concessional funding from DFID also exceeded the set target of £20, at £52. IFC management fees are fixed and have remained unchanged relative to the size of the Trust Fund, Costs are on target even as the number of projects supported by the Initiative exceeds the anticipated number when it was designed. See EDRM No. 5486149.

VfM Indicator	Milestone target (March 2017)	Progress (December 2016)
1) Volume of investment leveraged (£) from DFIs for every £ of funding from DFID.	8.5	13.5
2) Volume of lending to SMEs by PFIs (£) for every £ of concessional funding from DFID.	£20	£52
3) Management costs.	Below 6.4% (£4.8m) of the overall programme size (£75m)	On target.

Does the project continue to represent value for money?
The Initiative has used less DFID funding per project than was originally anticipated, reaching the PFIs with 33 investment projects and 63 advisory assistance projects. The targets of number of PFIs supported with investment projects (55) and advisory projects (63) have exceeded the respective targets of 15 and 34 respectively. As a result, every £1 of DFID concessional funds has helped mobilise £13.5 of commercial funding from IFC and other investors. In terms of jobs, as has been previously explained, the time lag between loans to SMEs to jobs is much longer than was originally anticipated in the Initiative Cost Benefit Analysis and, as a result, the job impacts of the Initiative are expected to materialise in later years.

The Initiative continues to represent good value for money based on the criteria set in the Business Case. Outcome indicators currently exceed the targets or are just short of the targets set. The Initiative is on track to meet the overall outcome targets by 2019.

E: RISK

Overall risk rating: Moderate
The SME Finance Initiative has a Risk Matrix with a mitigation strategy in place. DFID conducts a detailed risk review with IFC as a part of the AR process which last year identified three additional risks related to programme delivery. The risk review undertaken as part of this year’s review included a categorisation of risks by category (fiduciary, external context, delivery, safeguarding, reputational) and a rating of the likelihood (rare to probable) and impact (minor to severe) of gross risk and the net risk after accounting for mitigating factors in the Initiative. The risks embedded in the programme are reviewed and updated as necessary between annual reviews to ensure that DFID and IFC discuss and agree any changes, potential new risks or risks which are no longer relevant.

Details of the mitigation action against risks can be found in the Risk Register (EDRM No. 5474826).

The risks under the Initiative remain stable, with some risks declining with the increasing years of operation of the Initiative. There are three broad primary risks associated with the programme:

Delivery risk: A Central Assurance Assessment (CAA) was carried by DFID’s International Financial Institutions Department over November-December 2015 and IFC has shown to be a low risk delivery partner. IFC is focusing on applying its performance standards more consistently and evenly across its portfolio.

Gender take-up: As a result of previous recommendations, IFC has introduced the Gender Action Plan (outlined in the gender section), following which there was been an improvement in gender results. Moreover, the potential use of reflows to support the gender performance of the Initiative is meant to address this risk.

Results measurement: Throughout the life of the Initiative, results measurement has proved to be challenging due to data availability and data collection issues. This is compounded by the very long lag times for projects to feed through to job creation, and has meant many results are extrapolated estimates. A key recommendation from the MTR relating to data collection has been implemented with significant progress being made. There have been improvements in PFIs tracking results by gender, and IFC has offered instruments to improve tracking, including an extrapolations model to help estimate numbers of loans to women-headed businesses. IFC have recruited more staff to ramp up work on M&E and are focused on it, as a key recommendation from the mid-term review.

F: GENDER CONSIDERATIONS

Context
This Initiative is a flagship economic development programme of the Private Sector Department with strong focus on gender. Despite the challenges faced by the Initiative in delivering on the gender related goals and targets, the partnership with IFC has strategic significance and is part of other female economic empowerment initiatives of IFC, for example the Goldman Sachs Foundation-IFC Women Entrepreneurs Opportunity Facility (WEOF) supporting women entrepreneurs in emerging markets.

IFC adopted a gender action plan in October 2015 (EDRM No. 5172563) to improve the gender focus and performance of the Initiative. Approximately 1/3 of projects have a gender component. The current focus of the Initiative is on building a strong business case for financial institutions to focus on women-owned SMEs and developing a pipeline of projects with a gender component. IFC are committed to working with PFIs to improve tracking, data collection and reporting to enable the Initiative to capture, among other things, the gender-specific performance of the Initiative.

The main actions under the gender action plan include:-

Stronger Pipeline: The Initiative is working with IFC’s regional teams to implement its gender business development strategies. All new investment pipeline projects have a gender component. IFC have appointed three Gender Champions in Africa and have engaged a Senior Gender Specialist to raise the profile. Of the funds disbursed since November 2015, 60-70% been deployed to support projects with strong gender component.

New financial products: IFC successfully worked with supply chain-based financing to target small women SMEs in the distribution chain in Nigeria. IFC are exploring if and how this approach can be replicated in reaching small women entrepreneurs involved in agribusinesses and other manufacturing activities such as ready-made garments in countries like Bangladesh, Pakistan, Nigeria, DRC and Sierra Leone. IFC’s advisory services also focus on developing and providing non-financial services (NFS) to SMEs through its partner banks. NFS is particularly beneficial to PFIs targeting women SMEs as financial services coupled with NFS is a proven approach to increase the ability of PFIs to acquire and retain women customers. In addition, IFC are looking at if and how technology can be harnessed to better target women entrepreneurs. For example, IFC are currently looking at ways that banks can help women to carry out transactions more easily through via mobile technology. They are exploring how payments and cash flow data can be used in designing lending products for women entrepreneurs who often lack collateral. They are also looking at how the PFIs can better address other financial services needs e.g. savings and insurance of the women entrepreneurs.

More diversified workforce and Board: IFC are also working with the PFIs to help them and their SME clients become better employers of women with a more diversified workforce and management board.

Addressing missing data on women SMEs: Starting with the 2015 results, the Initiative has made targeted efforts at collecting gender disaggregated results for all projects. Data on gender is integrated into IFC’s Annual Reach Survey process and all projects are asked to report on number of loans and value of loans to women headed or owned businesses. When clients are not able to report gender disaggregated data, IFC applies extrapolation techniques tailored to the type of project or client to enable estimation of the number and volume of loans to women-owned SMEs.

Research and making the business case for lending to women entrepreneurs: There is ongoing wider research that examines the performance of women portfolios of projects compared with those of men which should benefit the SME Initiative. IFC is revising the SME finance gap analysis based on a more sophisticated methodology. The new gap analysis will estimate the total SME finance gap as well as the finance gap faced by women-owned enterprises.

In order to advance the know-how in financing of women entrepreneurs in particular and female economic empowerment in general, the Initiative will have to continue intensive engagements with wider efforts within the World Bank Group and other DFIs to progress knowledge and actions in this area.

Sponsorship of gender-focused activities: IFC has an active partnership with the Global Banking Alliance for Women (GBA) through which it supports knowledge and business development activities to promote increasing access to finance for women. GBA is organising learning events, including the GBA All-Star Academy, a 3½-day skill-building immersion programme for banks that are interested in targeting women, including women owned SMEs. Enrolment is open to senior bank executives with responsibility for new business development, marketing or new customer segments. The All-star academy focuses on developing holistic value propositions for women, outlining market strategies and best practices for implementation.

IFC organises roundtable meetings with selected groups of CEOs to discuss strategies for targeting the women SME segment in a profitable and sustainable manner. The roundtables include discussions on market opportunities presented by women-owned SMEs, approaches for efficient implementation of a women-focused customer value proposition, as well as examples of successful and bank offerings targeting women-owned SMEs.

G: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
DFID’s contribution of £75m has been fully disbursed to IFC in December 2015 and fully committed to activities identified. DFID agreed with IFC in May 2015 to provide a no-cost extension to the Initiative from March 2019 to March 2021 in order to allow IFC to deploy remaining allocations on deals with tenors of five years or more. If reflows are used as currently envisaged, DFID would seek to extend the Initiative to March 2024 to maximise the impact of using reflows to support women-owned SME related projects.

Performance of partnership(s)
DFID relies upon IFC’s investment apparatus and operational systems and procedures in implementation of the Initiative. Strategic direction and management oversight is provided by a Donor Steering Committee composed of the donors to the Initiative that meets semi-annually. There is more frequent engagement between the relevant PSD and IFC staff at the operational level. Overall, the relationship between DFID and IFC is positive, although in-country coordination between IFC and DFID country offices can be improved. IFC have taken some action to address this – for example, they have made it routine procedure to meet DFID advisers when on mission to countries with DFID offices. From the viewpoint of DFID’s project teams, we now share progress reports with DFID country offices and involve them in AR and field visits.

Asset monitoring and control
DFID receives semi-annual operational/progress reports. It also receives financial statements and high level information about pipeline of activities along with IFC’s call of funds which provide assurance over the use of programme assets and the implementation of projects.

H: CONDITIONALITY

Not applicable – as the Initiative is delivered through IFC. DFID does not provide any funding directly to financial institutions or the governments of the countries in which the Initiative operates.

I: MONITORING AND EVALUATION (½ page)

Monitoring progress throughout the review period
All projects under the Initiative are subject to IFC’s governance and monitoring and evaluation (M&E) standards. Projects under the Initiative are subject to the same SME results framework and reporting requirements as applicable to all other IFC advisory and investments services projects. Results data for projects funded through this Initiative are collected and reported through the IFC’s Results Measurement Network (RMN). Data for this Initiative go through three stages of IFC’s internal data control and assurance by:-

1. IFC’s in-country staff leading on the project who provides quality assurance for the data collected and reported by a PFI;
2. RMN staff for the relevant region; and
3. A senior staff of IFC’s Development Impact Department based in the HQ.

The data are finally reviewed by IFC’s external quality assurer of impacts and results, Ernst & Young.

IFC undertakes supervision missions to projects and continues to do so over the life of the Initiative so that IFC’s M&E team can verify their results and can engage their clients to get a better understanding of how PFIs’ clients have been impacted by this Initiative. Going forward, IFC has agreed to the following actions:

- including M&E/data reporting clauses in the legal agreements with PFIs, as it is essential for IFC staff to have a legal basis for requesting data
- integrating M&E into project cycles so that questions are being asked at appropriate times in the project cycle, not too early or too late
- maintaining an M&E specialist for the programme to work with regional staff and clients on ongoing M&E, which will also support an ongoing learning agenda
- continuing to communicate with staff and management about the critical nature of the M&E programme and specific demands on staff and clients going forward.

M&E Studies
The Facility is currently working on the following M&E studies:

DRC Advans Bank Congo (Advans DRC). Study to evaluate how business loans from Advans DRC affected the employment and sales growth of the bank’s SME clients. (Study is complete).

Bangladesh Eastern Bank Limited (EBL) SME Profiling & Impact Survey. This study focuses on analysing the impact of EBL loans had on SME’s sales and employment. An initial survey of EBL customers was implemented in 2013 and the same customers were asked to participate in a repeat survey in 2016.

Kenya Co-Op Bank baseline SME study. Study to gain an understanding of the needs of Co-Op Bank’s SME clients, their experience banking with the Co-Op vs. its competitors, and to assess any gaps in customers’ expectations and satisfaction. A repeat survey will be implemented in 3 years to assess the impact of loans on SME’s growth and to determine any changes in customers’ satisfaction with the Co-Op bank’s services to SMEs. (Survey of SMEs in progress).

Additional evaluations are being planned in Côte d’Ivoire, Myanmar (Burma) and Tanzania.

Review Process
DFID staff engages regularly with IFC with progress reports submitted every six months to monitor the effectiveness of the Initiative. There are more frequent engagements at the operational, almost on a weekly basis between IFC and DFID.

List of Documents
- Business Case as approved by the Secretary of State for International Development in January 2012. EDRM 3716779
- Facility Operational Report March 2017 EDRM 5780310.
- Audited results at December 2016 reported by IFC against revised logframe indicators. EDRM 5682896.
- DFID Annual Review Report June 2016 EDRM 5488068
- Final Mid-Term Performance Review 08 June 2015 EDRM 5178032
- Delivery Plan (revised March 2017) EDRM 5382472
- Risk Register (revised June 2017) EDRM 5474826
- Quarterly financial statement of receipts, disbursements and fund balance as of 31 March 2017 EDRM 5741917 AS and EDRM 5706933 IS.
- Gender Action Plan EDRM 5172563
- M&E Plan EDRM 5172580
- IFC Note on Blended Finance in the Initiative EDRM 5477339
- IFC Note on Attribution of Results EDRM 5477502 and 5477491
- Country visit reports EDRM Vault No.11876131
- Note on Reflows EDRM 5470317
- Evaluation of G20 SME Finance Challenge, Report by Enclude, September 2015 EDRM: 5283334