Business Case

Summary Sheet

Title: UK Partnership Programme for the Modernisation of Official Statistics
Programme Summary: UK Partnership Programme with the Office for National Statistics for the modernisation of official statistics.
Programme Value: Up to £4.5 million		Country/ Region: Global
Programme Code: 300443	Start Date: 21 August 2017	End Date: 31 March 2020
Overall programme risk rating:	Low
Vault Number:

Intervention Summary
This programme will build a strategic partnership between DFID and the UK statistical system, as led by the Office for National Statistics (ONS). It builds on ONS’s current small scale international development work and will help them to build their own capacity so they can scale up the technical assistance they provide to developing countries prior to the next spending review when they will bid for their own additional ODA funding.
Through capitalising on the UK’s comparative advantage in the modernisation of official statistics, it aims to improve the quality and availability of data to support the Global Goals and to ensure no one is left behind.
This programme will work closely with the GREAT for Partnership initiative which aims to boost partnerships between UK institutions and their counterparts in the developing world.
The funding will meet the cost of deploying UK staff to HMG priority countries and associated programme costs, and the costs of partner country staff coming to the UK. It will also meet the cost of UK experts working with DFID in the UK in policy or country teams and the associated management costs.
Does the programme fit with DFID’s strategic architecture: the UK Aid Strategy, Single Departmental Plan, International Development Act and the department’s Business Plan?
Yes. This programme supports the 2015 UK Aid Strategy[1], the Leave No One Behind Promise[2], agreed by the Prime Minister and other world leaders in 2015, and the Single Departmental Plan[3], by ensuring there is data to measure the Global Goals.
[1] UK aid: tackling global challenges in the national interest, November 2015.
[2] Leaving No One Behind: Our Promise, 10 January 2017.
[3] DFID Single Departmental Plan, 2015-2020, September 2016.
What percentage of DFID’s Single Departmental Plan (SDP) results target does this programme represent? Could the programme be adjusted in scope or scale to deliver SDP results?
This programme will not directly deliver SDP results, however, it will help to ensure there are data to measure the Global Goals. The programme will also “boost partnerships between UK institutions and their counterparts in the developing world.”
Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy?
Yes. This programme is designed to contribute to wider international needs for better data to support the Global Goals and includes meeting the needs of partner governments as well as international organisations. The ONS will bid for its own Official Development Assistance (ODA) in the next Comprehensive Spending Review.
Has the programme considered working with HMG Departments and accessing cross-HMG funds?
Yes. This intervention works with the UK Government Statistical Service, through the Office for National Statistics (ONS).
Accessing cross-HMG funds is not appropriate in this case.
How does the programme relate to other UK aid within the specific sector, including multilateral, bilateral and centrally managed programmes?
This programme complements work by country offices and centrally managed programmes to support statistics capacity building.
Is there sufficient flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments?
Yes. There are significant changes in the world of data access and use and ONS recognise this. Their operating model will be flexible so they can adapt to the changing context. This flexibility will be built into the Memorandum of Understanding to enable them to change programming.
Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio?
Yes. This is a low risk programme and within our appetite for this type of intervention.
Is there a clear communications strategy to reinforce our objectives? Will the programme be branded with the UK aid logo and recognise UK Government funding – and, if not, why not?
Yes. ONS have a well-developed communications strategy including through twitter and blogs. DFID will work with them on a communications strategy for this programme which will reinforce our objectives. The programme will be branded with the UK aid logo.
Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme?
Yes. The proposal has been quality assured by DFID’s Chief Statistician.
We are very confident that ONS has the technical skills, capability, and political will to deliver the programme. ONS will also use staff from other areas of the UK Government Statistical Service and the wider community of statistical expertise. The programme is being scaled up gradually so that ONS are able to build their partnership working capability and staff resources allocated to this work over the period of the programme.
Does the SRO and team have the capability and resources to deliver this programme?
Yes. A Senior Statistician in DFID’s Data for Development Team will play the SRO role and has extensive experience of managing programmes of this kind.
The SRO will work closely with DFID Statistical Advisers in country and in the UK to monitor programme performance.

Strategic Case
Context
The 2015 UK aid strategy, tackling global challenges in the national interest[4], confirms the UK’s commitment to promoting global prosperity as well as tackling extreme poverty and helping the world’s most vulnerable. The government will lead the work in implementing the “Leave No One Behind Promise”, agreed by the Prime Minister and other world leaders in 2015, when the UN General Assembly passed a resolution adopting the Global Goals. “Quality, accessible, timely and reliable disaggregated data will be needed to help with the measurement of progress and to ensure that no one is left behind. Such data is key to decision-making.[5]”
[4] https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/478834/ODA_strategy_final_web_0905.pdf
[5] UN General Assembly Resolution A/RES/70/1, “Transforming our world: the 2030 Agenda for Sustainable Development”. Para 48. http://www.un.org/sustainabledevelopment/summit/
To have the greatest effect on poverty, it is vital that Global Goal indicators are available to the widest possible audience, and disseminated in an accurate and timely manner. The DFID-funded 2016 report “A World that Counts: Mobilising the Data Revolution for Sustainable Development[6]” highlights the urgent need to mobilise the data revolution for all people and the whole planet in order to monitor progress, hold governments accountable and foster sustainable development.
[6] http://www.undatarevolution.org/wp-content/uploads/2014/12/A-World-That-Counts2.pdf
There is an acknowledgement that to meet the challenges of the Global Goals we will need to work with a much wider range of partners including private sector, civil society, government and international organisations. At the launch of the Global Partnership for Sustainable Development Data (GPSDD) in September 2015 DFID’s previous Secretary of State said that “A data revolution is as fundamental as anything to achieving the Global Goals. There are still too many data gaps that will prevent us from measuring our progress against the Global Goals.[7]” A new partnership with the UK Office for National Statistics (ONS) will provide one way to address the data challenge.
[7] Speech by International Development Secretary Justine Greening at the launch of the Global Partnership for Sustainable Development Data. https://www.gov.uk/government/speeches/data-matters-the-global-partnership-for-sustainable-development-data
In the UN resolution, endorsing the Global Goals, the international community committed to do more on data: “We will support developing countries … in strengthening the capacity of national statistical offices and data systems to ensure access to high quality, timely, reliable and disaggregated data.[8]” The Global Action Plan for Sustainable Development Data[9] sets out what is needed at the international, regional, national and sub-national levels to monitor the Global Goals, see Figure 1.
[8] UN General Assembly Resolution A/RES/70/1, “Transforming our world: the 2030 Agenda for Sustainable Development”. Para 76. http://www.un.org/sustainabledevelopment/summit/
[9] Global Action Plan for Sustainable Development Data, Draft as at 21 October 2016.

Figure 1: Global Action Plan Strategic Areas
Quality and timely data are vital for enabling governments, international organisations, civil society, private sector and the general public to make informed decisions and to ensure the accountability of representative bodies. But support to statistics remains low comprising a mere 0.25% of Official Development Assistance[10] and leaving a huge funding gap estimated to be $350 -$400 million a year. Without this data, countries will not be able to monitor or address the Global Goals or to ensure no one is left behind.
[10] Partner Report on Support to Statistics 2016, page 7.
A strategic collaboration with the UK Statistical System, led by the Office for National Statistics (ONS) will support the Global Action Plan for statistics as set out in Figure 1.
Need for DFID Intervention
The 2015 UK Aid Strategy[11] notes that to achieve the four strategic objectives the government will need to use a whole of government approach leveraging wider UK expertise to tackle global problems. The ONS has a strong international reputation as one of the best statistical offices in the world. The ONS is frequently asked to provide support to improve the policies, approaches, methods and practices in other countries. This new collaboration will expand existing partnerships and create new partnerships with institutions in developing countries. It will help to build ONS’s own capacity to deliver technical assistance in developing countries prior to the next spending review when they will bid for their own development funding.
[11] UK aid: tackling global challenges in the national interest, November 2015, para. 2.5.
This programme will build on evidence from existing UK partnership experience, as well as partnerships between other developed country national statistical offices and developing country counterparts, to harness ONS expertise for the benefit of developing countries. Specifically it will create:
Bigger partnerships: Building on positive evidence from existing UK partnerships, the programme will expand the scale and ambition of existing partnerships and launch new ones, under a single programme. Key activities may include short and long-term deployments of staff (in both directions), peer-to-peer networking, workshops, conferences, remote mentoring and study visits, with a view to a sustainable transfer of knowledge, attitudes and behaviours which will have genuine development impact.
Bolder partnerships: The partnership will provide for a broader range of activities than is currently the case. At the moment ONS are only able to respond to ad-hoc funded requests for short term technical assistance. The new proposed strategic partnership will help ONS to establish a larger international development unit to lead high quality partnerships between the UK statistical system, especially the ONS, and institutions in a smaller set of specifically targeted partner countries. This unit will have a strategic and coordination function and will help to make ONS support more coherent, ambitious and effective.
Better partnerships: This programme will work closely with other UK partnership programmes (for example the GREAT for Partnership programme, HMRC, BEIS, ROLE UK) to learn lessons (for example on how to prepare technical staff for working overseas, how to manage programmes effectively) and to streamline processes where possible (for example security and logistical challenges which all partnerships share). This programme will provide support to ONS until the next Spending Review, planned for 2020. By 2020 it is envisaged that the ONS will have significantly scaled up its ODA work and will bid for its own additional ODA resources from HM Treasury.
The programme aims to achieve the following impact and outcomes:

The UK statistics system has a strong reputation in the essential building blocks of an official statistical system as well as in the modernisation of statistical systems. The proposed collaboration will leverage the reputation and this expertise and support the development of new, specific strategic UK partnerships on the modernisation of official statistics, as well as providing a flexible facility to enable technical contributions to other relevant programmes, with well thought out visions, which complement UK aid efforts in areas where the UK has a comparative advantage.
New Partnerships
Initially the programme will be focussed on developing new medium to long term partnerships with three African countries and with the UN Economic Commission for Africa (UNECA). The support will focus on the modernisation of the work of statistical offices, recognising that their role is changing as the data ecosystem expands to cover a wide range of non-official data and the systems and methods related to the quality assurance of these new data sources.
The following criteria were used to select three partner countries where ONS will work in more depth:
- The UK has a comparative advantage (there is a clear gap in support in areas where the UK is strong, and the UK has the right skills and logistical support in place);
- There is a positive environment that supports/promotes/ incentives the National Statistical Institute to take on new ideas, and to grow the capacity of their staff through partnership – not substitution;
- There is a drive to modernise the National Statistical Institute, the partner has a strong vision for change;
- There is a medium to long term strategy (SDG data roadmap or equivalent) which is supported by leaders accountable for improving official statistics;
- There is a strong government commitment to open data. The National Statistical Institute has sufficient funding and support for their work; and
- The collaboration will support broader UK Aid objectives and DFID is supportive of the partnership as an effective model for supporting change.
Based on these criteria, Rwanda, Ghana and Kenya, have been selected, all of which are DFID priority countries, as well as being countries which are making good progress and demonstrating commitment to their respective SDG Data Roadmap processes. Through supporting them there will be a demonstrative effect for other countries in the region. To ensure long term sustainability, support will also be offered to UNECA to help them to reposition themselves as a resource for national statistics offices as they modernise. There will be a strong element of lesson learning between the three countries and through ECA with other countries in the region.
These partnerships will focus on the following areas:
- Strategic leadership for statistics offices – Providing leadership training and mentoring support to senior leaders to help them modernise their offices and to take a leading role in the data revolution.
- Data Interoperability – Integrating new data sources with existing sources and develop data platforms to make more data available to users. This will link to existing work on SDG data collection and reporting. In addition, the partnerships will help countries develop statistical regulations to deal with new data sources and work with UNECA to learn lessons and look at ways to roll these out to other countries.
- Quality Frameworks – Helping statistical offices to devise quality assurance frameworks for data sets which they do not collect. Test these and work with ECA on agreeing a regional standard.
- Data Research and Capability – Provide technical support as countries set up new data science campuses/labs. This could include support for training to define and prepare curricula and module contents; support setting up apprenticeship schemes and support setting up data warehouses to support the data campuses. A key focus of this work is the link to policy makers as well as to academics. The support will also extend to ECA and consider their role in supporting linkages between data science campuses in the region, to help with training, to learn lessons and consider holding an annual regional data science conference.
- Innovation - Identify innovations in the area of statistics which have the potential to improve the efficiency and effectiveness of data collection, analysis or use. This is likely to focus initially on innovations in Civil Registrations and Vital Statistics (CRVS) and will then look at other areas including population censuses.
The support provided in each country will be tailored to their needs, so the focus will be different in each country. In Kenya it is likely the support will cover strategic leadership, data interoperability and quality frameworks whereas in Rwanda it will focus on supporting their new data science campus and on quality frameworks. In Ghana there is likely to be more focus on CRVS alongside data interoperability and quality assurance frameworks.
A scoping phase will be undertaken as soon as the project is approved, during which ONS will assess the local needs, including the wider knowledge management systems, and how ONS skills can best contribute to meeting the partners’ goals. The scoping phase will also identify the resources required for such a partnership, the specific objectives and impacts as well as setting out how the programme will fit with DFID’s country objectives. The design of each partnership will need to be approved at the programme steering groups, comprising of both ONS and DFID senior staff (see management case).
If, through the scoping phase, it is assessed that ONS are not well fitted to meeting the challenges of any of the suggested partners, DFID and ONS will discuss through the steering group and identify if the resources should be allocated to a different country.
 Flexible Facility
Alongside these new partnerships, the programme will also include a short term flexible support component. This will provide short-term support within the context of other strategic frameworks or as part of a broader statistical capacity building strategy. This facility will complement UK aid efforts in areas where the UK has a comparative advantage. We will use the following criteria to identify specific components to take forwards:
- A medium to long term strategy for change is already in place within the host national statistical office, to which UK technical assistance will contribute;
- The collaboration will support broader UK Aid objectives;
- The country / countries / region that the component will support are at a minimum ODA eligible, and ideally among UK Aid priorities;
- There is a positive environment in counterpart institutions and there is evidence that the learning is demanded and will translate to new routines and behaviours;
- The technical area is one where the UK statistical system has a comparative advantage;
- The scale of the work is manageable by ONS - and staff are available and willing to support; and
- The likelihood of impact from the intervention is high.
Some specific examples which could be supported through this facility include:
- Measuring jobs - ONS have been supporting DFID’s Economic Development Directorate to develop a roadmap to improve the quality, consistency and dissemination of data on employment quality and productivity. There is demand for further inputs over the next six months to develop an enhanced network of labour statistics expertise. ONS labour market statisticians have the necessary expertise and contacts to deliver this ambition and provide good value for money.
- Data Management - Support to DFID to produce guidance and set up systems to manage results data including working with DFID’s two Data Trailblazer countries (Kenya and Syria).
- Improving economic statistics - Through the DFID Economic Statistics Programme (GB-1-204933) DFID is investing in the UN Economic and Social Commission for Asia and the Pacific (UNESCAP) Regional Programme for Economic Statistics which supports nine countries in South Asia to implement action plans for economic statistics, focusing on improving national accounts and business registers and developing training materials on economic statistics. UNESCAP have approached ONS to provide technical inputs for this programme, and this partnership arrangement can enable this to be taken forwards in a cost effective way.
- Improving quality and coverage of data in Middle East and North Africa through Eurostat - Since 1996, Eurostat have implemented a regional programme known as MEDSTAT, providing expertise and technical assistance to 10 countries in the Middle East and North Africa Region, including several DFID partner countries. Eurostat are seeking technical inputs in topics including labour statistics, business statistics, environmental statistics, and the SDGs. Support to these activities would draw on ONS key strengths and help to support UK objectives in the region.
- Age and aging - DFID, ONS and key partners have worked on the establishment of a UN City Group on ageing and age disaggregated data to ensure that issues of age and aging are reflected in the SDGs, as part of their commitment to Leave No 0ne Behind. The ONS will host this Titchfield City Group from 2017. Funding from this partnership can be used to ensure that the group effectively reflects the needs and concerns of developing countries, and to bolster the collection, analysis and use of good quality data on ageing and age in developing countries. This will in turn help to evidence the equitable delivery of the SDGs and help them to meet the leave no one behind pledge.
- SDG data dissemination platform - ONS is developing an iteration of the US’ National Reporting Platform, to report on SDG indicator progress. There is demand from developing countries on setting up their own national reporting platforms and the ONS has already learned many lessons which will enable developing countries to develop the US platform for their needs. All code developed will available to others as it uses an open source approach (GitHub), and all lessons documented.
- Research and training
- Horizon scanning: conducting research into new tools and technologies;
- Robust data standards: developing guidance materials to support developing countries; and
- Training: data quality training and quality assurance for analysis.
This collaboration with ONS is designed to be very flexible to respond to the changing needs of DFID and developing countries. Throughout the programme ONS will actively explore how innovation can help to modernise statistical offices as well as learning and sharing lessons from the different work areas.
Gender Equality
In accordance with the 2014 International Development (Gender Equality) Act all work with the ONS will consider the impact on gender equality, including, as appropriate and feasible, the disaggregation of data. The disaggregation of data is critical to inform policy and programme decisions, and for effective monitoring and analyses of vulnerable groups, including women and girls. Disaggregated data can help to:
- Make the invisible visible;
- Better understand the lived realities of people’s lives;
- Program more effectively; and
- Improve program impact.
ONS will work throughout the data life-cycle to ensure women and girls are visible, including in the following areas:
Methodological standards: ONS will work with partners to ensure data tools include what women do e.g. work defined as paid labour;
- Data production: ONS will work with partners to ensure data collection methods are not biased against women e.g. male enumerators used to speak to women;
- Data analysis: ONS will work with partners to ensure data is disaggregated on the basis of sex, age, disability status and geography;
- Data access and dissemination: ONS will work with partners to improve access to data. They recognise the risk of increasing the digital divide, that is the risk of increasing inequality, in terms of access and use of information. They will seek to address this by building this into the design of their programme;
- Data use/ application: ONS will work with partners to address gaps in gender data to improve understanding of the impact on women and girls in policy, research and programmes;
Terrorism Financing
Overall the terrorist financing risks associated with this programme are low. There may be occasional cases where DFID funds work in fragile states which could bring ONS into contact with radical and extremist groups, representing a higher level of risk. DFID will manage these risks through our relationships with ONS ensuring their policies on terrorist financing are sound through a proportionate due diligence process, and exploring these policies more thoroughly for areas of work where we judge any risks to be more substantial.

Appraisal Case
Assessment of Feasible Options
1. Do Nothing: rely on existing funding mechanisms.
2. Direct support to ONS.
3. Support through range of other organisations.

Description	Assessment	Evidence
1: Do Nothing	Doing nothing will mean there is unlikely to be any improvement in official statistics in the focus countries or in UNECA. The 2015 UK Aid Strategy[12] notes that to achieve the four strategic objectives the government will need to use a whole of government approach leveraging wider UK expertise to tackle global problems. By doing nothing we will not be able to contribute to this whole of government approach.	The UK is committed to modernising its statistical system and is well-regarded internationally for its approach to innovation. Without DFID support ONS would continue to provide some support to developing countries but this would be small scale and ad-hoc until they could bid directly to the Treasury for additional resources. However, without the opportunity to scale up and demonstrate that they can work at scale then it would be difficult for them to bid for additional funding. The opportunity to harness ONS’ potential to strengthen statistical systems in developing countries would be lost.
2: Direct support to ONS	Better statistics will help to inform policy making. Open data will help businesses to grow and will help citizens to hold governments to account. Direct support would be provided for ONS to set up long term partnerships with three African countries and ECA alongside a short term flexible facility to provide technical assistance to support other statistical strategies eg. through World Bank or IMF.	A lessons learnt study on Partnerships and Financing for Statistics highlighted the importance of country ownership and alignment of donors support with country strategies. It also showed that aid for statistics delivered through more comprehensive programs providing coordinated and predictable support was thought much more likely to be successful.[13] / This model would allow greater focus on DFID and country priorities. It would help to address the current risk of fragmentation
3: Support through range of other organisations	Use a range of private sector companies and other organisations to provide short and long term technical assistance.	This programme will work primarily with national statistics offices and as such the UK ONS is well placed to support this as they understand the specific issues and challenges. There is no other one organisation which could match this support although in some areas some firms may have specific expertise. Providing support through a range of different organisations would substantially increase the management costs. Additionally, under this option this would not build ONS’s own technical capacity and would not help them to be well placed to bid for their own resources in the next Comprehensive Spending Review.
[12] UK aid: tackling global challenges in the national interest, November 2015, para. 2.5.
[13] Partnerships and Financing for Statistics: Lessons Learned from Recent Evaluations, Open Data Watch, June 24, 2015

Based on the analysis above, we conclude that Option 2 represents the best model to meet the need set out in the Strategic Case.
Theory of change
There is some evidence of the impact of statistical capacity building in the work conducted by Open Data13. Their work built on earlier efforts to support capacity building, which was summarized in the synthesis report for DFID prepared in 2008[14]. These lessons remain as pertinent now as they were then. Key elements, set out in eight dimensions or pillars[15], are identified as:
[14] Department for International Development, Evaluation of the Implementation of the Paris Declaration: Thematic Study of Support to Statistical Capacity Building: Synthesis Report, (2009), Accessed: May 11, 2015, https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/67730/thematic-study-statcapacity. pdf.
[15] Mary Strode and Ian MacAuslan. Support to Statistical Capacity Building Development of an Evaluation Framework. (2008). Email to Open Data Watch, May 19, 2015.
Key Lessons Learned in Statistics Capacity Building13	How these lessons have been applied
Strengthening the focus on results and the demand for statistics at the top of government.	This programme will include a focus on results and on building demand for statistics
Strengthening the accountability of statistical agencies and the statistical system as a whole to government and to users more generally.	This is a core part of the modernisation programme
Ensuring an effective legal and institutional framework for the national statistical system that promotes coordination and ensures accountability.	This is a core part of the modernisation programme
Having in place an agreed, nationally owned, feasible, medium-term strategy for the development of the national statistical system and effective mechanisms for work planning and budget management.	All countries have an NSDS as well as an SDG data roadmap which is being implemented.
Providing predictable financial resources for the operations of the statistical system over the medium-term.	This is not a focus of this programme but DFID will work with the Global Partnership for Sustainable Development Data (GPSDD) and others to build predictable long term financing.
Ensuring good management and leadership of statistical agencies and the statistical system as a whole.	This is a core part of the modernisation programme through senior level leadership and mentoring.
Providing enough staff with the right qualifications and skills and ensuring that these continue to be updated.	Staff training will be part of this programme with an emphasis on new skills to respond to the data revolution.
Ensuring that the statistical system has access to the tools, technology resources and infrastructure it needs to operate effectively and making sure these are maintained and updated.	This programme and our work with GPSDD includes a focus on innovation and on building new tools to meet the needs of statistics offices.

In terms of partnerships more generally, the GREAT for Partnership programme[16] was designed to improve global learning on partnership practice. There are examples of strong and weak partnerships. Weaker partnerships are characterised by supply-driven, short-term interventions which are often not sustainable. In contrast, stronger partnerships have been seen where interventions are requested as part of a wider, comprehensive reform strategy, championed by effective leadership, targeted on a specific issue which may be a binding constraint, and delivered in the context of a longer term, flexible relationship, that has helped improved the functioning of institutions.
[16] GREAT for Partnerships Business Case, https://devtracker.dfid.gov.uk/projects/GB-1-205191
The GREAT for Partnerships business case notes several key factors that affect the likelihood of impact. These include:
1. High level leadership and commitment on both sides to the partnership;
2. A link to both organisations’ mission, strategy and values;
3. Clarity and realism on what the partnership is designed to achieve;
4. Clear roles and responsibilities, whilst retaining an adaptive approach and flexibility;
5. Led by the developing country-partner and appropriate for the context; and
6. Openness to learning and change on both sides.
This programme with the ONS incorporates these lessons which are similar to the earlier ones.
In the area of data there are a range of international standards and classifications including for the recently adopted Sustainable Development Goals (SDGs). This means that all countries often face very similar issues in the area of statistics which means partnerships, such as those with the ONS, can be particularly valuable.
The theory of change is summarised in Figure 2. There is moderate evidence on the link between the outputs, outcome and the impact. There is less evidence on ONS’s ability to carry out this work as they have not been operating at this scale. This risk is being mitigated by ensuring there is strong support from the National Statistician as well as scaling up the work gradually over three years and ensuring a close working relationship with DFID statisticians, other parts of Whitehall engaged in partnership working and with other international partners working on statistics capacity building. ONS International Development Team will also undertake further risk mitigation activities as outlined in their risk register, see Figure 5.

Figure 2: Theory of Change

What measures can be used to assess Value for Money?
The key costs drivers of option 2 are the cost of staff and associated travel costs.
ONS will ensure efficiency of its activities and will ensure each piece of work contracted through this programme will be scrutinised and will use a deliverable based contract.
VfM measures will be agreed with ONS and will be reported to DFID, and other partners, on a six monthly basis as part of progress reports. The table below summarises the mechanisms driving VfM and the potential VfM indicators.
VfM Mechanisms	Potential VfM Indicators
Economy
Individual pieces of work will be contracted through open, fair and limited competition where appropriate. Overall economies are achieved in the reduction in transaction costs saved by eliminating the requirement to produce a separate business case for each piece of work.	All work undertaken will have a concept note and a budget which will be approved by the ONS International Development Team / Average daily rate for staff / Average daily rate of short term expert
Efficiency
The largest financial proportion of this programme is staffing costs. All staff will be selected competitively, based on their capability and capacity to deliver the agreed work programme.	Average time to disburse funds from time of receiving proposals
Effectiveness
Better statistics will help to inform policy making. Open data will help businesses to grow and will help citizens to hold governments to account.	Improvement in Open Data Readiness Assessment (number of dimensions which have shown an improvement) / Skills and knowledge produced through the programme are being further used by others eg. ECA or other stakeholders in the wider data ecosystem / The holistic nature of the project and the leadership of the project by the statistical offices enable these offices to build their capacity to manage a strengthened statistical system meeting national needs.

Summary Value for Money Statement for the preferred option
Our assessment is that providing direct support to ONS represents the best value for money for DFID.

Commercial Case
DFID’s funding, up to a maximum of £4.5 million over three years, will be used to support ONS International Development Team as set out in the Strategic Case. The Business Case is seeking approval for up to £4.5 million to allow for a flexible programme that is able to respond to change. The ONS International Development Team will undertake statistical capacity building activities in DFID partner countries which will use the UK’s strengths as an official statistical system. Activities can be proposed by DFID country offices or National Statistical Institutes (NSIs) in DFID priority countries.
ONS International Development Team will be responsible for the programme leadership, partnerships management including preparation of all UK staff deployed to partner countries, monitoring evaluation and learning, responding to demand and raising awareness.
ONS International Development Team will develop correct evaluation criteria to be used in the process of ensuring that a contractor with appropriate track record/skills/expertise can be identified, and value for money.
Key Cost Drivers
Cost drivers will fall into two principal categories:
- Management and administrative costs including salaries, anticipated expenses, communications and reporting activities; and
- Assignment costs of partnerships themselves, including design, implementation, deployment, monitoring, review and all associated programme costs.

Financial Case
Overview of costs
The programme has a ceiling allocation of £4.5m over three years (2017/18 – 2019/20). These funds will be used to fund the challenge of measuring the Global Goals and the commitment to “leave no one behind”.
Cost profiling and planning
All funds used in this programme will be ODA-eligible and are expected to be disbursed according to the table below:
Financial Year		Estimated Salary Costs	Overheads	Non Salary Costs (T&S, accom, etc.)	Total
2017 - 2018					700,000
Partnerships	Overseas based staff	56,000	16,000	150,000
	UK based staff	85,000	59,000	50,000
Flexible Facility	UK based staff	150,000	104,000	30,000
2018 - 2019					1,800,000
Partnerships	Overseas based staff	225,000	65,000	480,000
	UK based staff	174,000	120,000	65,000
Flexible Facility	UK based staff	335,000	231,000	105,000
2019 - 2020					2,000,000
Partnerships	Overseas based staff	225,000	65,000	480,000
	UK based staff	218,000	150,000	100,000
Flexible Facility	UK based staff	380,000	262,000	120,000
TOTAL		1,848,000	1,072,000	1,580,000	4,500,000

Financial and fraud risk assessment
The programme is low risk as ONS is another Government Department and uses the same financial management standards as DFID. ONS International Development Team will maintain oversight of all the proposed, approved and underway assignments, tracking the actual number of days delivered, the costs associated with these days, as well as the objectives and deliverables of the assignments. ONS will report to DFID quarterly on the activities undertaken and request reimbursement for staff time and costs for the previous quarter. ONS International Development Team will ensure the programme will deliver value for money.
Expenditure will be validated against the work plan, progress reports and financial reports. At the start of each year, detailed annual budgets will be agreed.
Travel and subsistence
ONS staff undertaking overseas travel as part of their official business, will use the official rates for expense payments as published by HMRC on .gov.uk[17]
[17] https://www.gov.uk/government/publications/scale-rate-expenses-payments-employee-travelling-outside-the-uk
Fixed Assets
We do not expect this programme to generate any assets which would need to be managed by DFID. Nor do we anticipate any form of funding which would involve the return of capital to DFID, or which would create liabilities for the UK government.
Management Case
What are the governance arrangements for implementing the intervention?
The ONS-DFID collaboration’s governance structure is shown in Error! Reference source not found.. It is organised around a Steering Group which: sets the overall strategy and vision for the programme, approves the partnerships and activities under the flexible facility, reviews progress and makes recommendations. The Steering Group will comprise of senior staff from ONS and DFID, with responsibility for the programme, and with relevant expertise. The Steering Group will be chaired jointly by the DFID Chief Statistician and the ONS Director responsible for this work (currently the Chief Economist and Director of National Accounts and Economic Statistics). It is expected to meet every six months and its TORs and membership will be agreed at the first meeting.

Figure 3: ONS-DFID Collaboration Governance Structure

The Steering Group will be supported at the Operational Level by the ONS International Development Team (ONS Team). The ONS Team are responsible for the management and operation of the programme.
At the Operational Level the ONS Team will be responsible for delivering the programme, through activities including:
- Managing and prioritising requests for expertise from partner governments, DFID staff and other bodies and ensuring they meet eligibility criteria;
- Liaising across the ONS, the GSS and beyond to identify specialists and establish a pool of technical experts;
- Supporting and facilitating short and long-term deployments of experts to partner countries to provide technical assistance (logistical support, pre mission training etc);
- Disseminating information and actively promoting the existence of the programme, lessons learnt and best practice; and
- Reporting to DFID quarterly using the agreed logframe.
At the Working Level the Senior Responsible Owner (SRO) will manage this programme keeping in close touch with the statistics cadre to ensure they are aware of the work and can link in where appropriate. The SRO will also ensure policy division teams are aware of any work which may relate to their areas, for example Inclusive Societies Department will be part of the new working group on “Leave No One Behind”. For specific projects there will be a named DFID link person who will work directly with the ONS Team.
The SRO of the programme will be accountable to the Head of the Data for Development Team for programme performance, financial management, and regular reviews of the programme.
The Programme Manager will work with the SRO to ensure financial management responsibilities are fully discharged, including funding agreements with partners, regular review of forecasts and budgets, and processing of payments in line with contracts and grants.
What are the risks and how will these be managed?
Based on the analysis below, we judge the overall net “at approval” risk level for this programme to be minor.
 The ONS-DFID collaboration is low risk with a high potential benefit. We will always be open and honest about risks, working closely to ensure we have a shared understanding. ONS has different levels of tolerance for different types of risk as outlined below and in their risk register.
ONS risk appetite underpins the risk management approach to program implementation. For example, the low appetite for fiduciary risk is mitigated by the financial and compliance policies and their close scrutiny of all program expenses. Underpinning their risk management is a culture of openness where staff and partners are encouraged to be completely open about risks. ONS’ risk guidance document sets out clear roles and responsibilities as well as setting out their own risk appetite, see Figure 4.

Figure 4: Risk Appetite
ONS have a risk register which includes risk owners and risk ratings and mitigating actions for each risk and is updated quarterly. The ONS Team will manage risks and will have regular conversations about risk, considering the continued relevance of existing risks; noting emerging risks; reviewing the success of mitigating actions; and recording changing levels of risk. This initial analysis forms the basis for the risk register, which will serve as a tool within the delivery plan for the active management of project risks throughout the life of the project.
A summary of the risk register is shown in Figure 5. The ONS Team will keep and update a risk register every quarter. If any risk or risks detailed below increase beyond their risk appetite, they will act quickly to escalate these and take controlling actions. Moderate risks will be escalated to the DFID SRO and major and severe risks will be escalated to the Steering Group.

Figure 5: Summary Risk Register
Partnership principles and other conditions
Funds under this programme are not expected to be provided directly to partner governments. Should this change for any unforeseen reason, the DFID SRO should ensure compliance with the partnership principles has been fully addressed and agreed with the Steering Committee.
How will progress and results be monitored, measured, and evaluated?
Monitoring
The ONS Team will be responsible for regular project and programme monitoring and impact measurement, using the log frame indicators. A nested log frame approach will be taken. For each of the four major partnerships, ONS will work with partner countries and institutions to define a clear theory of change, and outputs, outcomes, indicators, milestones and targets. For each of the activities under the flexible facilities, appropriate objectives and indicators will also be set. A menu of indicators and a monitoring guide will be established by the ONS Team within the first six months of the start of the programme, which will assist in the development of each set of indicators, and the overall logframe, which will then be developed to reflect the mix of different activities. The ONS team will consider the use of digital tools for aggregation of results across the series of nested log frames.
It is likely the indicators in the menu will include all or some of the following:
OUTCOME: Increased availability and frequency of high quality disaggregated data (by country)
- Average number of visits to websites per day
- Number of SDG indicators with at least one data point in the last five years
- World Bank Statistics Capacity Building Score

OUTPUTS
- Statistical Legislation: Extent to which the legal framework for the National Statistics Office has clear roles, responsibilities, reporting lines and functions which reflect the needs of the wider data ecosystem.
- Quality Assessment Frameworks: Extent to which the country has adopted Quality Assessment Frameworks.
- Data development and Dissemination: Number of new data sets uploaded to SDG national reporting platform.
- Stories of change: documented examples of changes in quality, frequency, coverage of national data sets due to ONS assistance.
An interim logframe will be agreed by the Steering Group within six months of the start of the programme. This will be used to monitor progress at the first annual review. There will be some degree of flexibility in the log frame, so that milestones and targets can be adjusted to changes in demand, or shifting contexts or political priorities in the UK or partner countries. Changes will be approved at the Steering Group.
The ONS Team will submit quarterly reports to DFID on progress of specific projects, and the overall programme, including an updated risk register. Six monthly programme results reporting against the overall log frame will be submitted to the Steering Group. At the Steering Group, the ONS Team will also report progress on agreed aggregate input and activity level indicators, including the number of days of assistance delivered, and the budget spent, in order that they can monitor value for money.
The ONS Team will capture information to assess performance in a timely, effective and efficient way. The log frame will be used to monitor whether the programme is on track, measure results achieved against targets at regular milestones, and to assess possible requirements for action. Results indicators will be used to report to the Steering Group, demonstrating successes and lessons learnt. The assessments will be linked to the key milestones and targets at output, outcome and impact level.
Annual reviews will be conducted in line with DFID’s Smart Rules, assessing progress against the programme logframe. These will be the responsibility of the SRO, and will be quality assured by another member of DFID staff.
Evaluation
Evidence from monitoring the impact of both the individual projects and the overall programme will be used to set priorities for evaluation. A final programme evaluation will be undertaken and will include an impact assessment, performance assessment and recommendations for any future programmes. The evaluation will follow the evaluation framework for support to statistics developed for DFID[18] which covers these areas:
[18] Department for International Development, Evaluation of the Implementation of the Paris Declaration: Thematic Study of Support to Statistical Capacity Building: Synthesis Report, (2009), Accessed: May 11, 2015, https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/67730/thematic-study-statcapacity. pdf.
- Focus on results based management at the highest level of government;
- Accountability of the statistical system to government;
- Appropriate institutional context;
- Strategy for statistics;
- Resources for statistics;
- Management in the statistical system;
- Qualified staff; and
- Appropriate methods and tooIs.
Scoping studies will be carried out in each country and for each institution. These studies will use the Framework above to provide baseline information which can be used in the evaluation. The full details of the evaluation will be finalised at the end of 2017.