Business Case

Summary Sheet

Title: Yemen: Access, Logistics, Liaison, and Accountability (YALLA)
Programme Summary: To provide technical expertise and logistics to enable better access, a more effective and better coordinated humanitarian response and to facilitate the flow of essential goods to help alleviate the humanitarian crisis in Yemen.
Programme Value: £18.3 million		Country/ Region: Yemen, Saudi Arabia, Djibouti, Jordan
Programme Code: 300417	Start Date: 1 August 2017	End Date: 31 July 2020
Overall programme risk rating:	Major
Vault Number:

Intervention Summary (2 pages max)

Narrative summary of why UK support is needed, what the funds will be spent on, where, over what period of time, via whom and what they will deliver
This Business Case is for a contribution of £18.3 million between 2017 and 2020 to be delivered through UN agencies, and potentially other partners. The programme will enable the delivery of the DFID Yemen humanitarian portfolio as a whole, and the wider international response, by helping to address humanitarian access constraints into and within Yemen; restrictions on shipping imports; and the need for a coordinated, effective and accountable humanitarian system.

Yemen is one of the most challenging operating environments for the international humanitarian community. In addition to the wider impacts of the conflict, famine currently threatens 6.8 million people and cholera has killed over 2,000 people between April and October 2017. Humanitarian actors face severe and unpredictable access constraints both to enter into and to travel within Yemen. The absence and unreliability of commercial transport companies to reach Yemen by air, sea or land obliges the UN and their partners to rely on alternative solutions. Yemen is reliant on imports for 90% of its food, fuel and medicine. The UK’s financial and political support for a mechanism to maintain and increase import flows helps to avert famine. In such a complex emergency, support to the UN to establish a strategic and accountable humanitarian architecture is vital to coordinate an effective response at the scale required. The dynamics of the conflict means the programme will need to adapt as circumstances change. There are six components to the programme under two main pillars:

1. Improve the technical and coordination capacity of the UN-led humanitarian response.
  1. Support the core costs of the United Nations Office for the Coordination of Humanitarian Affairs (OCHA) to enable it to fulfil its role, including negotiating access in country. This includes paying for nine full time access negotiators and key leadership positions outside Sana’a to enable an effective response across the country (£1.5m in 2017/18)
  2. Provide additional short-term humanitarian advisory support to DFID Yemen in London and Amman to deliver DFID’s humanitarian portfolio (£350,000 in 2017/18)
  3. Strengthen UN performance through secondment of specialist staff to UN agencies. For example, specialist cholera supplies expert into the World Health Organisation (£200,000 in 2017/18)
  4. Establish a feedback mechanism for beneficiaries to provide feedback to help guide and improve the humanitarian response (£1m in 2018/19).

1. Improve commercial and humanitarian access into and within Yemen.
  1. Fund the UN Logistics Cluster including the UN Humanitarian Air Service (UNHAS) to enable the transport of UN and NGO personnel into and out of Yemen, in order to deliver the response (£1.5m in 2017/18)
  2. Fund the UN Verification and Inspections Mechanism (UNVIM) to improve shipping access and essential imports including food, fuel and medical supplies (£1.3m in 2017/18).

Does the programme fit with DFID’s strategic architecture: the UK Aid Strategy, Single Departmental Plan, International Development Act and the Business Plan?
This programme is directly linked to the UK Aid Strategy and the Single Departmental Plan which commits the UK to strengthening resilience and responses to humanitarian emergencies (Objective 2). The programme supports DFID’s commitment in the Strategic Defence and Security Review (2015) to focus efforts on fragile and conflict affected states. It complies with the International Development Act (Gender Equality) 2014 and is aligned with both the Yemen and Gulf National Security Strategies.
What percentage of DFID’s Single Departmental Plan results target does this represent?
This programme does not directly contribute to DFID’s SDP results.
Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy?
Funding decisions for this programme were informed primarily by the UN-led 2017 Yemen Humanitarian Response Plan (YHRP) and will continue to be guided by the YHRP over the next three years. The interventions respond to the needs outlined by the UN Logistics and Coordination Clusters. Given the continued access constraints and the humanitarian need, no exit strategy has been set out. However, the UK will continue to engage with parties to the conflict for improved commercial and humanitarian access to reduce the need for these interventions. DFID will also engage with other donors, both those which already jointly fund the interventions in this Business Case (such as the US, ECHO and Germany) and others to ensure there is a wide support base. In the Annual Review, DFID Yemen will assess the context and progresses made, and consider how the programme will adapt to new conflict, political or humanitarian developments, and whether the UK remains best placed to respond to these needs.

Has the programme considered working with HMG Departments and accessing cross-HMG funds?
Cross-HMG funds are not appropriate for a humanitarian programme of this type.
How does the programme relate to other UK aid within the specific sector, including multilateral, bilateral and centrally managed programmes?
The programme underpins DFID Yemen’s broader programme portfolio and policy priorities. For example without UNVIM, the shipments that all UN and NGO partners rely on would experience severe delays and restrictions. Without UNHAS, given the limited availability of private transport and logistics services in Yemen, the large scale UN-led response would be paralysed. By funding the UN Humanitarian Coordinator and OCHA, we are supporting more effective humanitarian coordination, which will improve the overall delivery quality of the humanitarian response in Yemen.

Is there sufficient flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments?
DFID will monitor the context jointly with partners to reprioritise should the needs and the nature of the conflict change. Currently no funds have been committed beyond 2017/18 and therefore there is flexibility to shift future commitments. In addition, this Business Case builds in a mechanism to allow DFID to respond flexibly to escalating access or coordination needs through the use of an Emergency Response Mechanism (ERM). This would entail a competitive process to seek proposals from existing DFID Yemen partners to meet an identified need within the scope of this Business Case, and which could be rapidly implemented once funding is confirmed. Any new proposal would be robustly assessed to ensure its appropriateness and that it delivers value for money, and would require approval from the Senior Responsible Owner (SRO).

Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio?
The programme risk is assessed as major and is within DFID’s risk appetite. This programme reduces DFID Yemen’s overall portfolio delivery risk by facilitating and improving the overall humanitarian response, and is assessed against the high return of enabling the provision of life-saving humanitarian aid. The UK’s engagement with relevant parties to the conflict helps offset some of the risks of the interventions, for example helping to overcome some of the barriers to imports and access. All partners have undergone due diligence assessments, which also includes assessing their assurance mechanisms for implementing partners and sub-contractors. We will monitor risk with partners in monthly and quarterly meetings and site visits (e.g. UNVIM operates from Djibouti) where possible to ensure risks are managed.

Is there a clear communications strategy to reinforce our objectives?
Partners will use UK branding on written material and supplies, with exemptions granted if this is deemed an additional security threat to operating in country.

Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme?
This Business Case is not required to be reviewed by the Quality Assurance Unit; however, it has been quality assured by DFID Yemen’s Humanitarian Advisors, as well as specialists in Social Development, Conflict, Statistics, Finance, Commercial and an Economist. The proposed partners have implemented previous DFID Yemen programmes. Their proven performance and due diligence assessments have demonstrated their delivery capacity.
Does the SRO and team have the capability and resources to deliver this programme?
The SRO for this programme is the Yemen Humanitarian Team Leader. The Humanitarian Programme Manager will be responsible for day to day operations alongside three technical advisors, and drawing on cross-cutting advisers as required.

Strategic Case

Context
Yemen has had a long history of conflict, instability and pervasive poverty. The country faces a range of deep-seated development challenges including state fragmentation, endemic corruption, rapid population growth, deep-rooted gender inequality, poor provision of basic services, and a weak economy. As a result, even before the current conflict, the UN assessed that 16 million Yemenis needed some form of humanitarian assistance.
The current conflict has its roots in the Arab Spring protests in 2011 when the former President Saleh resigned, handing over power to President Hadi’s Transitional Government. In September 2014, the Houthis staged a de-facto takeover of the capital, Sana’a. Following a failed peace deal and with support from forces loyal to Saleh, the Houthis consolidated control over northern Yemen in early 2015. In response, at the request of President Hadi, a Saudi Arabia-led Coalition of mainly Gulf Cooperation Council (GCC) countries began military action in Yemen in March 2015. Building upon existing tensions in the South of Yemen (predominantly involving southern separatist and religious extremist movements), this war has now directly affected all but one of Yemen’s 22 governorates. It has led to a complicated political and military picture, with fragmented alliances that heighten humanitarian and commercial access challenges and unpredictability, and which will take a long time to resolve.
The conflict has led to a humanitarian crisis, with a reported 47,000 civilian casualties, including over 8,000 killed since March 2015. Over 2 million people are internally displaced.[1] The conflict has resulted in 20.7 million people in need of humanitarian and protection assistance, with the latest Integrated Phase Classification (IPC) estimating that over 6.8 million people are severely food insecure and urgently in need of life-saving assistance. In addition, Yemen is experiencing the largest cholera outbreak recorded in a single year.[2] Social protection payments to the poorest 1.5 million households were not made between January 2015 and August 2017.[3] As the conflict continues to worsen, political alliances are fragmenting, institutions and systems such as health care are collapsing, and the humanitarian and protection needs continue to increase.
[1] WHO: Health Facility Based Death and Injuries in the Yemen Crisis 2015-16 (as of 15 July 2017)
[2] According to WHO, as of August 14th, there have been 508,680 suspected cases of cholera, and 1,977 deaths. Daily case increase rate is around 5,000. The disease is showing early signs of plateauing in some governorates, but is still on the increase in others especially those more recently impacted.
[3] The first payment was made in September 2017.
The economic situation in Yemen severely affects the humanitarian situation.  Since the onset of the conflict, official oil and gas exports producing vital revenue have halted. Yemen’s foreign exchange reserves are nearly exhausted, resulting in importers struggling to access foreign exchange for commercial imports of basic necessities. This has contributed to a reduction in food imports, on which Yemen is heavily reliant. It has also led to currency depreciation, which pushes up food prices, diminishes households’ purchasing power and fuels black market activity. Public sector salaries are unpaid for almost a year affecting over a million civil servants, further eroding the population’s purchasing power and adding new beneficiaries to the humanitarian caseload. Pre-conflict, 25% of households relied on government salaries, of which 31% were food insecure.  In this context, with governance systems and institutions disintegrating, public services collapsing, investment in a robust UN humanitarian system is crucial.
Access into Yemen
Sea Access
The Government of Yemen controls and runs Aden port while the Red Sea ports (Hodeidah, Salif and Ras Isa) are located in areas controlled by Houthi/Saleh de-facto authorities. The UN Security Council Resolution (UNSCR) 2216 (2015) ruled that Member States should take necessary measures to prevent arms, weapons and ammunitions entering Yemeni territory.[4] Subsequently, the Saudi-led Coalition assumed primary responsibility, under UNSCR 2216, to put measures in place to prevent the flow of arms into Yemen. Coalition navies began regulating access to Yemen’s ports, requiring commercial operators to seek clearance from the Saudi Evacuation and Humanitarian Operations Centre (EHOC) before being allowed to dock. Commercial importers reported that they faced a set of opaque, inconsistent and bureaucratic clearance processes meaning significant delays and increased costs for ships seeking to offload in Yemen’s ports.
[4] Full text of the United Nations Security Council Resolution 2216 (2015) is available at::http://www.securitycouncilreport.org/atf/cf/%7B65BFCF9B-6D27-4E9C-8CD3-CF6E4FF96FF9%7D/s_res_2216.pdf
Yemenis are reliant on imports of fuel, food and medical supplies to meet 90% of basic needs through two major sea access points, Red Sea and Aden ports.[5] Of this, 80% of imports come in through Hodeidah and neighbouring Salif – demonstrating the criticality of these ports to Yemen’s economy. Maintaining and increasing commercial shipping flows through Red Sea ports is therefore essential to lower prices for wheat and fuel, which have increased by 28% (wheat) and 53% (gas) and 45% (diesel) on average since January 2015.[6]
[5] UN OCHA Yemen Humanitarian Bulleting Issue 4 http://reliefweb.int/sites/reliefweb.int/files/resources/OCHA_Yemen_Hum_Bulletin_Jan_2016.pdf
[6] WFP Market Watch July 2017 https://www.wfp.org/content/yemen-monthly-market-watch-2017
The ongoing conflict resulted in severely restricting the flow of imports into Yemen, with devastating impact. In order to improve the flow of commercial imports into Yemen, the UN Regional Humanitarian Coordinator proposed the UN Verification Inspection Mechanism (UNVIM) in June 2015, as an independent process to verify and inspect commercial cargo ships. UNVIM was formally launched in December 2015 to help the Coalition tackle illicit flows into Yemen by sea, whilst also facilitating the flow of essential goods. UNVIM aims to verify commercial cargo within 48 hours, thereby reducing disruption and building commercial confidence in the import sector.

As a result of UNVIM the flow of commercial imports improved, with around 1,500 ships entering the Red Sea and Aden ports between January 2016 and March 2017. This is compared to a handful of ships in the second quarter of 2015.[7] However, while UNVIM operates effectively within its remit, imports to the Red Sea ports do fluctuate due to other factors including delays in clearance from EHOC and importers struggling to access finance. The UN reported that while commercial food imports to Hodeidah were at 70% pre-crisis levels in July 2017, there are large monthly fluctuations. For example, Yemen received only 20% of its fuel needs in January 2017 and 43% in March 2017.
[7] Prior to UNVIM’s introduction, Yemeni ports were operating at a fraction of the pre-conflict capacity. In June 2015, Yemen imported 11% of its fuel requirements. https://reliefweb.int/sites/reliefweb.int/files/resources/OCHA%20Yemen%20Situation%20Report%20No%2013%20issued%20on%2030%20June%202015.pdf and https://reliefweb.int/sites/reliefweb.int/files/resources/final_january_2016_shipment_snapshot_11022016_v.3.pdf

Air Access
In August 2016, the Government of Yemen banned all commercial flights to Sana’a. A priority of the international community since then has been increased access to Sana’a Airport for lifesaving humanitarian supplies and for emergency medical evacuations.[8] Indeed, UN Security Council Presidential Statements in June and August 2017 have called on all parties to allow the safe, timely and unhindered access for humanitarian assistance, including increased access to Sana’a airport for lifesaving humanitarian supplies and movement of urgent humanitarian cases.[9] Since August 2016, the humanitarian response has therefore been fully reliant for air transport on the WFP Humanitarian Air Service (UNHAS) linking Sana’a and Aden airports to Djibouti and Amman. This is in addition to ICRC and MSF operating their own humanitarian flights. WFP Logistics also operates a regular sea shuttle between Djibouti and Aden ports.
[8] UN Security Council Presidential Statement, June 2017 https://www.un.org/press/en/2017/sc12873.doc.htm
[9] UN Security Council Presidential Statement, August 2017 https://www.un.org/press/en/2017/sc12946.doc.htm

Land routes
Given the challenges accessing Yemen through the Red Sea ports, alternative land routes for humanitarian and commercial cargo have been trialled by commercial importers and humanitarian agencies. Entry from Oman to Yemen, through Shahen land port is used by private companies, with an average transit time to Sana’a of three days. The second option is from Saudi Arabia to Yemen through Alwadiah land port, with an average transit time of two days. This entry point is relatively small, and experiences heavy congestion.[10] Coalition presence at the border, and the situation in the northern governorates, make the use of this corridor hardly feasible as an alternative to Hodeidah. Neither substitute for the scale of the Red Sea ports.
[10] http://www.logcluster.org/sites/default/files/logistics_cluster_yemen_hodeidahcontingencyplan_170322_0.pdf

Access within Yemen
Humanitarian agencies face complex and unpredictable constraints delivering assistance within Yemen. Impediments to humanitarian access reported by partners generally fall into three broad categories: bureaucratic restrictions, interference in the delivery of relief, and the security constraints as a result of active fighting and military operations.[11] Roughly 69% of the 333 districts in the country are either fully accessible or have relatively few access constraints. Of the 31% remaining, access to 43 districts are categorised as hard to reach or inaccessible. The districts (located in Marib, Sa’ada and Taiz governorates) which are most difficult to access have a population of 2.1 million, with 1.3 million estimated to be in acute need of assistance.[12]
[11] https://docs.unocha.org/sites/dms/Documents/OOM_HumAccess_English.pdf
[12] http://reliefweb.int/sites/reliefweb.int/files/resources/humanitarian_bulletin_issue_23_-_09_may_2017.pdf
Delivering assistance to these difficult-to-access governorates is challenging. The Houthi-Saleh controlled de-facto authorities at the national, governorate and local levels impose ad-hoc restrictions on the movement and activities of humanitarian organisations, and seek to interfere in delivery, for example by trying to influence the targeting of beneficiaries, contesting the choice of implementing partners, refusing entry of humanitarian supplies and, obstructing the conduct of assessments.[13] The progressive fragmentation of authority across the country, including in (nominally) Government of Yemen-controlled areas has led to a proliferation of check-points and militia rivalries, hampering access across southern Yemen too. While bureaucratic procedures are less stringent in the South, there are still security issues and frequent diversion attempts.
[13] In August 2017, the UN Humanitarian Coordinator issued a statement on the “shrinking humanitarian space in Yemen” condemning the continued obstruction to the timely provision of humanitarian assistance and urging all parties to the conflict to uphold their obligations under international humanitarian law to facilitate the safe and unhindered delivery of humanitarian assistance in areas under their control.
As basic social services in Yemen are near collapse, there is pressure on humanitarian organisations to expand the response. Ensuring unhindered access is essential to enable humanitarian actors to save the lives of those who depend on assistance, particularly as Yemen is facing an unprecedented cholera crisis and almost seven million people are at risk of famine. Full and unimpeded access to carry out the operations for the affected populations will not solve such a large scale crisis, but is crucial to responding to the vast need in Yemen.
Why should DFID provide additional humanitarian aid?
The rationale for this investment is three-fold:

Strengthen the quality of the overall international humanitarian response for Yemen.
Conflict analysis reveals increasing state and institutional fragmentation, and unpredictable political dynamics that heavily constrain access. Meanwhile, the international humanitarian system has faced challenges in meeting leadership, coordination and capacity requirements of a Level 3 emergency. This points to the necessity of supporting the humanitarian system in Yemen through the Office for the Coordination of Humanitarian Affairs (OCHA), to provide:
- Leadership. To ensure that the response is led by empowered and experienced professionals.
- Situational Awareness. To ensure that decision making is based on situational awareness, through the provision of quality contextual analysis.
- Assessment, Planning and Monitoring. To ensure humanitarian action is guided by joint planning based on prioritised needs (e.g. the production of the Humanitarian Needs Overview, the Humanitarian Response Plan and Monitoring Reports).
- Coordination Mechanisms. To ensure that coordination mechanisms are adapted to the context and support the effective and coherent delivery of humanitarian assistance.
- Humanitarian Financing. To ensure that financing in predictable, timely and allocated based on priority needs.
- Access to Assistance. To ensure an access strategy is rolled out across the response, and that coordination structures are able to respond to access needs and requirements.

Support to OCHA in Yemen helps ensure that their approach is in line with the UK’s humanitarian priorities: to expand field presence[14]; to negotiate better humanitarian access; to use a stronger evidence base to inform the UN response plan; to more effectively manage the risk of aid fuelling the conflict; to improve interagency accountability mechanisms; and to effectively communicate the severity of the humanitarian crisis. DFID will also fund new strategic posts into OCHA to strengthen their ability to negotiate and facilitate access into Yemen. [15] DFID will work with OCHA to consider whether additional personnel with expertise in conflict sensitivity, gender, social inclusion and other cross-cutting areas are required to strengthen the overall international response in Yemen in these critical areas. Integrating these positions within OCHA will help them be applied at a strategic level to the Yemen response.
[14] DFID funding to OCHA will also contribute to the strengthening the OCHA field hubs outside of Sana’a in Aden, Hodeidah, Sa’ada and Ibb. These hubs are vital for humanitarian access negotiations, engagement and advocacy with local authorities on behalf of humanitarian actors, and wider planning for unpredictability.
[15] This plan brings new strategic posts into OCHA Yemen, including the deployment of a senior P5 Head of Aden hub, a P4 Civil-Military Coordinator in Riyadh, a P4 Head of Access in Sana’a and other Hub level access negotiators. It also strengthens the capacity of Hodeidah, Ibb/Taiz and Sa’ada OCHA hubs with the deployment of additional Humanitarian Aid Officers and the deployment of an Information Management Officer to the Humanitarian Access Working Group (HAWG) in Sana’a.

Accountability
An OCHA assessment in July 2017 found that at present individual agency implementation of beneficiary feedback and community engagement work is uneven or absent. There is no coordinated mechanism across the response. Introducing a common Accountability to Affected Populations (AAP) system across the response in a fragile, active conflict environment has not been tried before. This pilot project will support the humanitarian system to: (1) ensure beneficiaries are informed about the humanitarian response, and can provide feedback, and (2) ensure that the humanitarian response is informed by the views of these beneficiaries, and that programming is designed, delivered and adapted based on the aggregation of these views, which will help strengthen the overall response. While this mechanism is still in development for Yemen, it would consist of micro-surveys, radio broadcasts and a feedback service to gather the views of affected people. This information would then be analysed and shared among UN agencies and NGOs to support improvements.
Support humanitarian and commercial access into and within Yemen.
Common service platforms provided by the WFP Logistics Cluster are vital in enabling humanitarian goods and personnel to reach people in need in Yemen. The Logistics Cluster provides a range of services free of charge to all humanitarian organisations involved in the cluster system, including those listed below.[16]
[16] See 2017 YHRP for full list of common services provided by the Logistics Cluster.
- The UN Humanitarian Air Service (UNHAS). With the absence of commercial options, UNHAS enable the movement of personnel and equipment to Sana’a and Aden. UNHAS’ services also offer an evacuation route for agencies, without which many of DFID’s partners would not be able to maintain international staff presence in Yemen.
- A weekly sea shuttle linking Djibouti to Aden port for humanitarian workers and supplies. The boat also offers accommodation to UN staff while the ship is anchored given the limited UN guesthouse capacity in Aden.[17]
  [17] Currently capacity for 16 international staff
- Contingency planning capability. For example, additional logistics support to respond to the spiralling cholera outbreak in Yemen from April 2017.[18]
  [18] In April 2017, with the spiralling cholera outbreak, WFP Logistics scaled up their activities with the provision of a dedicated cargo plane in Djibouti airport, controlled temperature transport and storage facilities. Those additional services increased WFP logistics and staff requirements and are essential to the implementation of the $254m Cholera Response Plan.
- Fuel provisions, enabling agencies to operate in times of shortages. Agencies pay for this.

DFID has previously funded both UNHAS and the Djibouti sea shuttle. Support under this business case will include continued support for these services. If there is a demonstrated need and strong case for DFID to support other elements of Logistics Cluster services, a case for this will be presented to the DFID Yemen Head of Office for approval.

The ongoing conflict has also severely restricted both commercial and humanitarian imports. As outlined above, UNVIM operates to help the international community prevent the flow of arms ito Yemen in line with UNSCR 2216. Meanwhile it provides importers with confidence that they will not be unduly delayed with when accessing Yemen Red Sea ports, and is crucial for the continuation of Yemen’s commercial import sector.

Delivering broader UK objectives and realising international commitments and UN reform.

The UK Aid Strategy commits the UK to lead the response to humanitarian emergencies. Such crises as Yemen, if unaddressed, often have a direct impact on the UK, for example by contributing to irregular migration, transnational crime and terrorism, and directly threaten the UK’s national security. UK support will make a clear and unequivocal statement that the UK recognises the severity of people’s humanitarian and protection needs in Yemen and is committed to working with others to tackle some of the barriers to an effective humanitarian response. This programme will also provide additional sources of information for further analysis of the conflict and humanitarian context in Yemen.

DFID Yemen will also work with partners on the broader UN reform agenda to ensure the World Humanitarian Summit and Grand Bargain commitments are implemented in Yemen. For example, the Accountability to Affected Population (AAP) pilot is an interagency accountability mechanism, which will also provide valuable insights into any unintentional worsening of (especially local) conflict dynamics, enabling adjustments for conflict sensitive programming – another priority UK ask of the international humanitarian system. DFID Yemen’s support for OCHA will also prioritise the UK’s key priorities for UN reform. This includes more effective leadership and collaboration across the system to ensure funds can make the greatest impact; ensuring the cluster system is being coordinated behind a single assessment plan, with authority behind the Humanitarian Coordinator; and improved joint needs assessments responding to the protracted crises.

Impact and Outcome expected

The expected impact of the programme is that “vulnerabilities of people affected by the conflict in Yemen are identified and reduced, prioritising the most vulnerable”.

The overall aim of this humanitarian intervention will be to reduce the vulnerabilities of people affected by conflict in Yemen. This programme will contribute to improving the cost-effectiveness and efficiency of other DFID Yemen programmes and of the international response as a whole through a better informed, better coordinated, better targeted, more principled and accountable response. This includes improving access into and within Yemen for humanitarian aid. This contributes to the overarching Theory of Change for the Yemen Humanitarian programme.
The expected outcome is that the capacity of the international humanitarian system to respond in Yemen is strengthened, with agencies able to maintain accountable humanitarian operations and scale up delivery where possible. This will be measured by: key humanitarian programme cycle deliverables (e.g. YHRPs, HNOs and Periodic Monitoring Reviews (PMRs)) endorsed by the Humanitarian Country Team in a timely manner; humanitarian cargo are allowed to berth into Yemeni Red Sea ports in line with regulations as set out in UNSCR-2216 and; percentage of humanitarian agencies in the Humanitarian Country Team (HCR) benefitting from the Logistics Cluster services; and the percentage of UN agency and NGO humanitarian plans that include joint communication and feedback and accountability mechanisms.
Gender and Equality

The conflict in Yemen has a disproportionate effect on women and girls, in a country which is already ranked lowest in the World Economic Forum’s Global Gender Gap Index. In developing this Business Case, we have taken into account the gender related differences in the needs of those affected by the situation. This programme supports cross-cutting technical expertise to strengthen the capacity of the humanitarian system to respond to emerging vulnerabilities and needs in Yemen – including those of girls, women and the disabled. For example, the information generated by surveys of affected populations under the accountability element will be analysed to reflect the specific views of women and girls regarding the response, data which DFID will use in advocacy work and programme design. DFID Yemen will work to influence and support the UN’s staffing and commitment to technical expertise in gender, inclusion and conflict sensitivity. Our support to OCHA also helps to facilitate strengthened needs assessment, taking into consideration the distinct needs of the vulnerable. For example, the selection process for projects to be included in the Humanitarian Response Plans includes a set of markers ensuring all proposals have integrated gender considerations.
Conflict Sensitivity and Terrorism Financing
This programme is informed by and reflects the conflict context. We consider the impact of our programme on the conflict, and the local and regional dynamics and relationships through monthly Programme Boards and dedicated conflict advisor support. We will work with partners to ensure steps are taken to address conflict sensitivity, as detailed further in the appraisal case (page 18).
Terrorist groups including Al-Qaeda in the Arab Peninsula (AQAP) and Daesh-Yemen are active in Yemen. It is the policy of DFID to ensure that no UK taxpayer funds are used to support individuals or entities associated with terrorism. All DFID partners sign MoUs which agreeing to comply with this and with the relevant counter terrorist financing legislation. Due diligence and delivery chain mapping is undertaken on all partners to reduce risk and provide further assurance over the use of UK funds.

Appraisal Case

Assessment of feasible options: Part 1

There are three components of this business case for which no credible alternative option exists, apart from a ‘Do Nothing’ option: OCHA core costs, support to the Logistics Cluster and UNVIM. In addition, an ‘Emergency Response Mechanism’ (ERM) is a way to build flexibility into the programme to respond rapidly to changing needs using existing DFID Yemen partners. It will allow partners to scale up interventions which fall within the scope of this Business Case. The ERM will not be assessed in the Appraisal Case given that it is a mechanism for flexibly allocating funding, rather than a standalone component of the programme. Any activity funded through the ERM would need approved by the the Senior Responsile Owner (SRO) – as it is within their delegated authority.

OCHA is the only organisation with a globally-recognised mandate to facilitate effective leadership and coordination in humanitarian responses, and has established itself across Yemen since 2015. Supporting OCHA will provide common services, build the humanitarian system’s capacity and strengthen coordination in Yemen. Attempting to establish an alternative, parallel system would contravene the UK’s Grand Bargain commitments to improve the efficiency and effectiveness of humanitarian funding. Supporting OCHA’s core costs increases the UK’s ability to influence OCHA’s strategic direction and operations. For example, influencing OCHA to recruit new access negotiators to improve their ability to negotiate access barriers, which are hampering the response as a whole.

The international humanitarian community depends on the WFP Logistics Cluster services, including UNHAS, to maintain international staff presence in country and agencies would likely withdraw staff should this service not continue. No commercial flights have been allowed into Sana’a airport since August 2016, meaning that UNHAS is one of the only options (along with MSF and ICRC flights) for humanitarian personnel to get into and out of the north of the country. Aden airport was recently opened to humanitarian and limited commercial flights, including UNHAS, but this option remains uncertain because of the security situation. In addition, overland travel from Aden to the north of the country is difficult and risky. No alternative options to the WFP Logistics Cluster are currently viable given (a) that the private sector currently do not have the capacity to provide reliable logistical services to the humanitarian community; (b) the risk of duplicating the work of the Logistics Cluster; and (c) the absence of political buy-in from the international community and parties to the conflict to invest in meaningful alternatives to improve humanitarian access into and within Yemen.

Restoring commercial cargo flows is essential to alleviating the humanitarian situation in Yemen. UNVIM, which the UK was instrumental in establishing, is the only organisation that has international support and mandate as an independent verification and inspection mechanism for commercial supplies into Yemen. UNOPS is an established UN agency and the mechanism provides increased transparency on imports processes and any blockages. This increases commercial confidence, maintaining and potentially increasing the number of ships berthing and associated volumes of cargo, which in turn reduces prices of food and fuel. The establishment of UNVIM required considerable diplomatic support and the backing from all parties to the conflict. Since its operational inception in December 2015 it has been operating effectively within its remit. Withdrawing support or seeking to establish an alternative to UNVIM would not be supported by other stakeholders and would undermine UNVIM, with potentially severe consequences on the levels of imports into Yemen.

Emergency Response Mechanism (ERM)

A mechanism proposed in this Business Case for allowing flexibility to respond to changing needs and challenges is a new Emergency Response Mechanism (ERM). This would support innovative programme responses in times of escalating or changing need, especially in relation to facilitating humanitarian access. DFID Yemen would seek options and proposals from existing partners that falls within the scope of this business case as part of a rapid competitive call. All proposals would be evaluated by the programme team and cross-cutting advisors for their appropriateness, value for money, and for conflict sensitivity, and other key risk considerations. All partners would need to have the capacity to rapidly implement once funding is confirmed. All proposals funded under the ERM would be approved the Senior Responsible Owner (SRO). Once funding is agreed, DFID will amend their existing MoU or Accountable Grant with the chosen organisation.[19]
[19] If DFID Yemen did fund a new partner, a due diligence assessment would first have to take place.

There is a ‘Do Nothing’ option for the above support.

Given that OCHA, WFP Logistic Cluster and UNVIM are all multi-donor funds, needs could potentially be met by other donors and UK funds used elsewhere. However, all three are key foundation stones of the humanitarian response, and it is not currently clear which other donor would step in to fill the gap. Insufficient funding to any intervention risks paralysing the international humanitarian system. In addition, UK political support, backed up and evidenced by our financial contibutions, has been key to the success of these interventions; withdrawing funding risks undermining these elements of the response. Withdrawing UK support to OCHA would also reduce our ability to influence OCHA’s strategic direction and coordinstion of the response as a whole. Not supporting an Emergency Response Mechansim would limit DFID’s ability to respond to new priorities or constraints, especially in relation to humanitarian access.

Assessment of feasible options: Part 2

There are three components where an alternative option for delivery exists: an alternative supplier to CHASE OT for the provision of technical personnel to DFID Yemen and to facilitate the Standby Partnerships arrangement; and an alternative delivery partner for the Accountability to Affected Populations pilot.

Humanitarian advisory support to DFID Yemen and to the UN system

Option One: Do nothing.

Cost: This option would not have any direct costs implications. However, without contracted support, staffing levels in both DFID Yemen and the UN would risk being insufficiently flexible to respond to changing or escalating needs.

Benefits: The savings made from doing nothing could be used to fund more projects or reduce the overall size of the programme. However, this option would also risk DFID and the UN’s ability to scale up quickly with high quality staff, and maintain flexibility to reduce resources later as needed.

Option Two: Procure trained personnel through CHASE OT contract: Draw on DFID’s existing contract with CHASE OT to source expert humanitarian advice to DFID Yemen in a flexible manner. Also use CHASE OT to facilitate the Standby Partnership mechanism to deploy surge staff into the UN system for strategically important posts.

Cost: £550,000 in 2017/18 (£200,000 Standby Partnerships, £350,000 CHASE OT support to DFID Yemen). This option requires the CHASE OT logistics teams (who manage the deployment of both CHASE contractors and Standby Partnership personnel) and some DFID Yemen staff time and oversight. DFID recently undertook a competitive tender exercise to replace the existing CHASE OT capability. The new contract will commence from November 2017 and follows extensive commercial and technical evaluation. The new contract includes capped rates and rate reductions based on the length of assignments.

Benefits: There remain critical staffing gaps in key UN agencies, which limit the effectiveness of the international response. Using DFID’s existing Standby Partnership (SBPP) arrangement through CHASE OT, DFID can provide additional staff quickly to the UN to support critical and strategic positions.[20] Previous DFID supported SBPP positions have been effective.[21] Contracting expert humanitarian advice through CHASE OT allows DFID Yemen access to expertise that is not readily available internally at the scale and speed required for such a large and urgent response, for example to source expertise to respond to the cholera outbreak.[22] The CHASE OT contract ensures a rigorous assessment of personnel to ensure those on the database are of high quality, with DFID Yemen further assessing candidates to ensure they have the skills and experience needed to fulfil the job requirements. The CHASE OT framework agreement is the only current capability enabling DFID Yemen to expand and contract in response to peaks in the crisis.
[20] Previous Standby Partnership positions DFID have funded includes a Protection Advisor in OCHA and a cash expert in the Cash and Markets Working Group
[21] Further detail provided on page 16
[22] The CHASE OT model operates in two ways: providing salaried core staff which are contracted for long periods, and more flexible higher cost day rate staff, from the experts database, that are able to provide surge capacity and specialist expertise for specific tasks.

Option Three: Tender for external support for expert humanitarian advice: Prepare terms of reference and issue an open and competitive tender for a dedicated Yemen Humanitarian response contract to provide flexible and responsive expert humanitarian advice for both DFID Yemen and the UN.

Cost: More expensive than Option 1. Tendering for a new contract would require considerable design input from the DFID Yemen team and a prolonged tendering process. A Yemen specific call down facility would have high administrative costs. For example, DFID Yemen would need to fund a small team to manage the contracting (including pre-deployment briefings, logistics, HEAT training, medical, duty of care considerations and so on). Currently these functions are performed by the CHASE OT team, with their existing deployment surge capacity in DFID. This option risks directly competing with another core DFID programme, duplicating the costs, and would result in a disjointed approach with the rest of DFID and the UN.

Benefits: There is a possibility that a DFID Yemen specific contract may be able to source from a wider market of expertise than available on the CHASE OT roster. However, DFID recently concluded a competitive tender exercise for the new CHASE OT requirement, meaning the market has been recently tested. DFID already has the capability to draw on a wider range of expertise as outlined in Option 2.

Accountability to Affected Population (AAP) Pilot programme

Option One: Do nothing

Cost: None. However, without the capacity to communicate life-saving information to, and to hear feedback from the affected population, DFID and other donors have more limited capacity to assess the effectiveness of the overall response,and to adapt the response based on that information. DFID has pushed hard for better accountability as part of UN reform efforts, and to ensure partners take this up in the field. Not promoting good practice in Yemen misses an important opportunity to strengthen the overall response and take forward Grand Bargain commitments.

Benefits: DFID funding could be directed elsewhere. Attention can be focused on countries where AAP delivery is easier and cheaper and without the risks associated with this project.

Option Two: UNICEF as implementing agency

Cost: DFID would fund UNICEF to manage the Accountability to Affected Population (AAP) pilot up to £1 million in 2018/19. Funding will be released only after achievement of milestones.

Benefits: An AAP pilot will strengthen the humanitarian response in Yemen through providing a feedback mechanism for beneficiaries, and working with UN agencies and NGOs to act on and adapt their activities based on that feedback. This element of the Business Case is still being developed, and the final proposal will be approved by the SRO, with robust indicators included in the logframe.[23] However, in wide consultation with partners – including the Humanitarian Coordinator, OCHA and the Community Engagement Working Group (CEWG), all have been clear that UNICEF is best placed to manage AAP in Yemen. UNICEF would be the conduit for delivering funding to implementing partners to deliver the different activities (for example, to specialist organisations to undertake regular surveys and to link with telecommunication systems). The key role of UNICEF is to champion the findings and ensure senior response figures are aware of and use findings to inform programming. Learning from elsewhere (e.g. Nepal) has shown that this is a crucial role and one which plays to the strengths of a UN agency rather than an NGO or the private sector because of the need for established relationships within the humanitarian system to effectively influence other agencies to use the mechanism. UNICEF Yemen will be supported from UNICEF Head Quarters by senior staff members specialised in AAP, something unavailable to other agencies. UNICEF is a tried and trusted partner in Yemen, and has already been subject to due diligence assessments.
[23] The final project will be funded through payment by results to help reduce the risk of funding this pilot.

Option Three: Implementation through the private sector or other recognised UN agencies

Cost: The availability of recognised partners with AAP experience and access to affected areas of Yemen is limited. Consultation conducted to date across partners in Yemen has not identified an alternative provider. There would be substantial transactional costs in undertaking further work to source alternative bodies, undertaking due diligence and oversight of new partners - if any such exist.

Benefits: There is a limited pool of alternative partners with the experience, capacity and existing presence in Yemen to host the AAP pilot. However, private companies (including local telecommunication providers) will be contracted as the implementing partners. The buy-in of all major UN agencies will also be needed for the success of the system-wide accountability and feedback mechanism.

Conclusion of Appraisal Case:

DFID will fund OCHA core costs to improve the leadership, coordination and technical capacity of the UN response. DFID will also fund UNVIM and services provided by the WFP Logistics Cluster to improve humanitarian and commercial access into and within Yemen. DFID will use the existing CHASE OT framework to contract technical expertise to ensure that DFID and the UN has appropriate technical expertise to respond to a complex and fluid response. DFID will support UNICEF to manage a pilot accountability and community engagement project. The pilot will provide all partners with the tools and resources to incorporate beneficiary views and perspectives into their planning and strategy, and to meet their commitments under the Grand Bargain and Transformative Agenda. Finally, DFID will use a new Emergency Response Mechanism to support innovative programme responses in times of escalating or changing need.

Theory of Change for the preferred options
The overall theory of change underpinning this and other humanitarian interventions for DFID’s humanitarian response to the crisis in Yemen is shown below. The inputs, processes and outputs relevant to this particular programme are highlighted in yellow. This programme specifically provides technical expertise, funding and staff time at the input level, all of which enable the delivery of the outputs, outcome and impact.
Outline of the intervention
This intervention will provide £18.3 million to fund a range of partners in Yemen. Our first 2017/18 allocation will fund six major activities:

Support to the Office for Coordination for Humanitarian Affairs (OCHA) (£1.5m in 2017/18). Funding directed to the running of OCHA office is crucial to support it to fulfil its function to provide overall leadership and strategic direction for the UN response. Our support will allow OCHA to expand field presence and ensure all national clusters have full time coordinators; to negotiate better humanitarian access[24]; to use a stronger evidence base to inform the UN response plan and ensure response planning is based on prioritised needs; to ensure that the response is well funded; to more effectively manage the risk of aid fuelling the conflict; to improve interagency accountability mechanisms; and to effectively communicate the severity of the humanitarian crisis.
[24] DFID will also fund nine positions within Yemen, in Saudi Arabia and the United Arab Emirates to improve coordination and access into Yemen.

Support to Standby Partnerships (£200,000 in 2017/18). Funding the rapid deployments of staff to UN agencies to fill short-term strategic priority positions.[25] The exact results delivered will depend on which roles are filled, but could include cluster and/or sub-clusters co-ordinators or senior advisers depending on the prioritised staffing needs of UN agencies.
[25] Standby Partnership positions (SBPP) are crucial to enable staff to be rapidly recruited in times of need. For example, DFID support a supply Chain expert seconded into the World Health Organisation (WHO) to support the cholera response. SBPP is a gap filler that should only be used for unforeseeable HR requirements. In other words, agencies should only use SBPP for positions that are not included in their annual staffing plan and annual budget. It cannot be used for more than 6 months for a same position.

Expert, short-term humanitarian advisory support in DFID (£350,000 in 2017/18). Staff will be located in multiple locations including London and Amman to support DFID Yemen’s policy and programme priorities. CHASE OT support will be reduced in later years as we replace them with permanent civil service positions where possible.

Support to the WFP Logistics Cluster including UNHAS (£1.77m in 2017/18). Funding UNHAS will ensure the international humanitarian community has access to a safe, reliable and predictable air transport service to and from Yemen by pre-agreed routes. Our support will fund around 30 flights to and from Yemen per month. After 2017/18, DFID will also fund other services provided by the Logistics Cluster, if there a demonstrated need and strong case for DFID support. A case for this will be presented to the DFID Yemen Head of Office.[26]
[26] WFP Logistics Cluster services are outlined on Page 7

Support to UNOPS (UNVIM) (£1.3m in 2017/18). Funding to facilitate the flow of commercial goods to Yemen, including food, fuel, and medical supplies while maintaining compliance with UNSCR 2216 to put measures in place to prevent the flow of arms into Yemen. Specifically, we would expect that, on average, UNVIM will enable shipments to berth at Hodeidah, Al Saleef and Ras Isa ports, with applicant ships verified or referred for inspection within 48 hours of receipt of documentation.

Establish a common Accountability to Affected Population (AAP) platform. (£1m in 2018/19). Funding a pilot mechanism to both enable the views of beneficiaries better inform strategy and programming of the overall humanitarian response as well as to improve communications, information about the response as a whole.

Strength of the Evidence Base
Evidence from other crisis contexts demonstrates the importance of supporting critical enablers that facilitate better operational delivery of the humanitarian response.[27]
[27] Evidence from other humanitarian contexts, most notably Somalia and the Haiti earthquake response demonstrate the importance of supporting all aspects of the humanitarian response and ensuring that critical enablers that facilitate better operational delivery are adequately supported.

UN OCHA core costs: The Annual Review for our past support to OCHA highlights the importance of supporting the architecture that will enable a humanitarian response in a crisis situation. It demonstrates that for relatively small inputs, in terms of costs and staff time, it is possible to provide vital core support that enables wider humanitarian response mechanisms. Since July 2015, OCHA has coordinated the expansion of the UN footprint to five Hubs outside Sana’a and has been crucial in providing the leadership, advocacy and operational support to agencies and INGOs (e.g. negotiating on access). The Multilateral Development Review (MDR) highlighted that OCHA provides a unique focal role for leading the international humanitarian system, responding, coordinating preparedness and response, including information management and advocating on behalf of the wider humanitarian community.[28] Directing funds to OCHA who have demonstrated their expertise and value in Yemen, proves an efficient and effective use of resources, without which the effectiveness of the whole response would be undermined.
[28] United Nations Office for the Coordination of Humanitarian Affairs (OCHA) Agency Assessment 2016

Standby Partnership (SBPP): The SBPP is an established mechanism for emergencies that provides quality staff quickly by drawing on large databases. The time taken for the UN or DFID to contract someone directly would exceed these, so this is the preferred mechanism for short-term deployments which are necessary to respond flexibly to a fast moving humanitarian context. DFID has taken the approach of only deploying ‘transformational’ posts, which the UK has shaped or identified in the UN system. Funding more senior and strategic posts (P4 and above) better contributes to improved coordination and functioning of OCHA in particular. Previous deployments in Yemen through Standby Partnership have included a Cash and Protection Advisor, both of whom received positive performance evaluations. Evidence does show that DFID needs to be increasingly proactive in identifying the relevant posts (e.g. Gender, Conflict or Social Development advisors) and lobbying OCHA to fill these posts. Also the short length of SBPP deployments are, on occasion, insufficient to have a long-term impact. In the cases where the SBPP has demonstrated potential for impact, DFID will encourage those agencies or INGOs to budget for permanent positions in their costs plans - as SBPP are for a maximum duration of six months.

CHASE OT technical advice: DFID’s approach to staffing chronic emergencies should reflect crisis response principles, scaling up quickly with high quality staff and maintaining the flexibility to reduce resources later as needed. CHASE OT can provide expertise not available in the Civil Service and have given DFID flexibility in how, and for how long, a post is deployed. The performance of CHASE OT contractors has been strong in previous iterations of this programme, though no formal reporting mechanism has been in place. However, CHASE OT contractors are more expensive than Home Civil Servants (HCS). DFID Yemen will begin phasing out our reliance on CHASE OT and has put in place and is implementing a plan to recruit HCS.

Accountability to Affected Populations (AAP): Evaluation of humanitarian work consistently demonstrates that aid which involves beneficiaries in the design and delivery is more effective, more efficient and much preferred by those affected by crises.[29] Yet evaluations identify the marginalisation of affected people as a key failing of the current humanitarian system. The need to be accountable to affected people is enshrined as a key principle of humanitarian reform. Feedback mechanisms from affected populations also provide valuable insights into any inadvertent worsening of (especially local) conflict dynamics, enabling adjustments for conflict sensitive programming. The model proposed in this programme draws heavily on experiences in other crises, notably Nepal, Iraq and the Philippines, where a similar approach was piloted and delivered positive results.[30] There is limited evidence on the implementation of an AAP initiative in a complex, protracted crisis as Yemen, and an evaluation element is built into the design to gather evidence on the successes and challenges.
[29] The Listening Project 2011
[30] The common service model is designed to coordinating and consolidating feedback via responding agencies and providing non-agency specific research into the experiences of affected people, informing the design and delivery of the overall response and providing a reliable information service for affected people.

WFP Logistics: Even the most optimistic scenarios for Yemen foresee a long period of recovery and stabilisation until local Ministries and administrations can fulfil their roles and resume services to the entire Yemeni population. In this context, it is essential that reliable logistics services remain available to the humanitarian community which otherwise would have to rely on the local private sector with the risk of being seen as taking sides or of fuelling the war economy. The ongoing humanitarian operation in Yemen would not be possible without support from the WFP Logistics cluster. Since 2015, they have allowed humanitarian operations to continue while fuel shortages affected most of the country. WFP Logistics have also responded to new challenges such as the ongoing cholera outbreak.[31] Access negotiations are demanding and NGOs have reported to DFID that WFP Logistics services had been “massively helpful”, saving them negotiations with numerous local counterparts to access parts of the country and offering free transportation and storage of goods. In other cases, international NGOs have highlighted WFP’s support to scale up their footprint in southern governorates. UNHAS (operated by WFP Logistics) is the only means for international staff to enter Yemen.[32] It currently operates eight flights a week connecting Sana’a and Aden to Djibouti and Amman, which transported 900 passengers in July 2017.
[31] WFP Logistics have provided free transport by sea, by air and by road across Yemen to all humanitarian agencies and NGOs as well as increased storage capacity and most importantly a cold chain ensuring safe transport and storage of sensitive medicines and other medical supplies.
[32] With the exception of MSF and ICRC who operate their own flight service.

UNVIM: There is plentiful evidence of the success of UNVIM. After the port of Hodeidah was closed in 2015, fuel and wheat prices sky-rocketed, by 55% and 61% respectively compared to pre-crisis levels. UNVIM was crucial in improving commercial confidence in Yemen’s Red Sea ports, a key priority for the UK government. Fuel prices have decreased to 285 YER per litre from 579 YER per litre since the reopening of the Red Sea ports, and decreased a further 36% since UNVIM’s inception in May 2016. Correspondingly, wheat availability has improved significantly, resulting in prices falling by 27% since the ports reopened and a further 5% since UNVIM inception. Evidence also shows that UNVIM is solving one piece of a much bigger problem; it does not verify goods further downstream in-country, nor does it address any of the broader problems facing the import sector such as access to finance. Due to the political context, there are limits to UNVIM’s scope. However, without UNVIM commercial ships would not be able to berth in Red Sea ports at the current rate, with associated impacts on costs and confidence of importers. It therefore offers value for money for a relatively small investment.

Emergency Response Mechanism: Based on DFID’s Rapid Response Facility (RRF), and building on the experience of DFID Syria, DFID Yemen will introduce a new process to facilitate a quick and effective response to escalating need. The ERM will allow existing DFID Yemen partners to bid for new funding to meet these emerging needs. The emergency response uplift will be added on to the existing grant under a new component of this programme, and will be approved by the Senior Responsible Owner (SRO), as it is within their delegated authority. The RRF has been operating effectively to enable DFID to respond to rapid onset emergencies since 2013. DFID Syria has triggered three ERMs, with activities approved by DFID for implementation within 72 hours of receiving proposals.

Vulnerability and Gender
As humanitarian needs escalate, women and girls face disproportionate threats to their safety and ability to access assistance. This programme supports cross-cutting technical expertise to strengthen the capacity of the international humanitarian community to respond to emerging vulnerabilities - including those of girls, women and the disabled. All technical advisers appointed through the CHASE OT contract will ensure that gender and vulnerability dynamics are integrated fully into the planning, implementation, monitoring and evaluation stages of all DFID programmes. DFID Yemen will work to influence and support the UN’s staffing and commitment to technical expertise in gender, inclusion and conflict sensitivity. Fortnightly meetings with the OCHA Head of Office will be used to take forward this agenda. Our support to OCHA also helps to facilitate strengthened needs assessment, taking into consideration the distinct needs of the vulnerable.

The information generated through Accountability to Affected Population (AAP) component will ensure that the voices of women, girls and other vulnerable groups are captured and amplified across humanitarian interventions in Yemen. In addition to designing specific ‘gender appropriate’ ways to involve women, the AAP mechanism will develop and maintain a feedback and complaints mechanisms that are safe, confidential and accessible to all. Specifically, the project has a specific element addressing sexual exploitation and abuse (SEA), providing safe channels for any abuses to be reported by those affected. The data collected will be used by DFID Yemen in our advocacy work and programme design.

Finally, the programme will take into account the complex dynamics and unpredictability of the conflict, by being flexible to reallocate funds to respond to escalating need, allowing DFID Yemen to expand or contract our programming as the needs of the most vulnerable dictate.

Conflict Sensitivity and Sustainability

As the trajectory of the conflict in Yemen remains uncertain, DFID Yemen encourages all partners to scenario plan – demonstrating how they would adapt their activities if there were certain ‘trigger points’ causing a major change in need and approach. For example, WFP as Chair of Logistics Cluster published a contingency plan for responding to needs should the port of Hodeidah become inoperable due to the conflict. DFID have also encouraged OCHA to invest in regular conflict analysis and to invest in their technical capacity to monitor the impacts of the interventions at different levels (local/activity, regional/national and strategic level). DFID will remain flexible to re-programme activities as a result of major changes to the conflict dynamics.

Accountability to Affected Populations: Research from past emergencies shows that lack of access to information increases the stress experienced by affected communities, reduces empowerment and increases vulnerability among the marginalised. Providing communities with the necessary channels to express their needs and priorities increases the capacity of responders to design interventions that are conflict and context-sensitive, appropriate, transparent, less likely to do harm or be appropriated, and thus deliver maximum benefit. The feedback mechanism can help identify problems (e.g. misunderstandings about aid allocation) at an early stage and support agencies in responding. This component supports the rest of the DFID Yemen portfolio in their approach to conflict sensitivity through creating a feedback loop that can reveal inadvertently negative impacts on conflict dynamics or vulnerability through the way assistance is being delivered that need adjusting.

UNVIM: UNVIM is designed flexibly to meet the changing dynamics of the conflict; it was developed and is implemented with a clear understanding of the conflict actors and dynamics. It seeks to minimise the ability of armed groups to import weapons that fuel the conflict in Yemen, whilst also facilitating the flow of essential commercial goods to alleviate the humanitarian need. Whilst it facilitates the flow of commercial goods, it is based on the humanitarian principle of impartiality in terms of allowing all those in need to access items to alleviate humanitarian suffering. UNVIM only handles imports by sea and does not seek to address the risk of illicit goods entering by land routes or by other means. It also does not currently inspect smaller vessels below 100 metric tonnes. In this sense it is, by definition, limited in its impact on the conflict.

CHASE OT, WFP Logistics Cluster: Other elements of this intervention should be neutral in their impact on the conflict as they all seek to enable the humanitarian response that responds to needs generated in part by the conflict. All UN personnel working for OCHA, UNOPS/UNVIM and WFP are sensitised to the Do No Harm and Conflict Sensitivity concepts before deployment through a number of compulsory trainings such as the UNDSS basic and advanced security online trainings. Recruitment and procurement processes consider the identity and affiliations of the staffing they contract vis-à-vis the populations being served.

F.	Likely impact on climate change and environments
This programme has been designed to support multiple interventions that strengthen the capacity of the international humanitarian community. There are few opportunities for supporting environmental management or addressing climate change. Supporting flights into Yemen has an environmental impact. On the other hand, WFP Logistics provide quality-controlled petrol and diesel to humanitarian agencies which otherwise would need to buy fuel from the local, uncontrolled market. UNHAS also uses high quality Jet A1 fuel to operate its flights. Overall, DFID does not judge the programme to pose a significant risk to the environment.

G.	Value for Money assessment for intervention
A qualitative assessment of economy, efficiency, effectiveness and equity are used to assess the programme’s approach to Value for Money (VfM):

Economy

OCHA Core Costs: Supporting core costs including staffing and hub management for the OCHA country team promotes value for money across the wider humanitarian response. For example, OCHA will negotiate access and advocate on behalf of other agencies and INGOs, which in turn promotes economy by allowing them to save on these costs. We will also work with the central DFID team managing the core OCHA relationship to ensure value for money considerations are pushed for at country level.

Logistics Cluster: WFP manage the Logistics Cluster, a good performer in the recent Multilateral Development Review and Central Assurance Assessment which asserted that while WFP lacks the mechanisms to have a systemised approach to VfM, there is a strong emphasis across the whole programme team on driving costs down in delivery. DFID will undertake a separate cost-benefit analysis of all individual interventions funded under the Logistics Cluster to ensure the budget is appropriate.

While air transportation is expensive, WFP’s buying power means that it has considerable ability to drive down costs. UNHAS operates eight flights a week to Yemen, and in July 2017 transported 900 passengers. [33] The total cost of operating the flights is in the region of £900,000 per month, meaning a fully booked flight makes the cost per beneficiary £1,000 per flight. Before the UNHAS service in Yemen began, there was no direct and reliable services allowing humanitarian workers to reach Sana’a directly. Instead, several flights at higher costs had to be taken to reach Sana’a.[34] A decision was taken by the UN Humanitarian Coordinator and Logistics Cluster that a direct Amman-Sana’a flight represented comparative savings for the international community. UNHAS also introduced penalties for missing flights, to recover some of the costs and to discourage agencies with a high record of “no shows”.[35]
[33] There are two flights per week between Djibouti-Aden, three flights per week between Djibouti-Sana’a and three flights per week between Amman-Sana’a.
[34] Before UNHAS, humanitarian workers had to take several flights via Cairo/Addis Ababa/Europe and then Djibouti before reaching Sana’a. The journey was so long that UN personnel were allowed to fly business class and had to stay at least one night in a 5 star hotel in Djibouti (at the average cost $500 per night). Average Yemenia flight from Cairo or Amman was $1200.
[35] WFP Logistics are assessing whether to apply a similar regime to the sea shuttle to Aden.

UNVIM: Support to UNVIM enables a robust, independent mechanism to bring transparency and speed up the clearance process for commercial ships entering Yemen. For a relatively small financial outlay - at approximately £450,000 per month - UNVIM contributes to increasing confidence of commercial shipping companies and helps reduce their costs (whose vessels can incur daily costs of up to $15,000 waiting to enter ports). UNVIM also indirectly supports the opening of the Red Sea ports for business. The key cost drivers of UNVIM are personnel costs of the office which processes clearances and the expertise to carry out inspections. UNVIM have made savings through: recruiting staff using the CTG Global Agreement[36] rather than procuring a maritime service company; procuring soft skin vehicles instead of armoured vehicles as the security situation in Djibouti is not as severe as Yemen; using the UNDP compound and therefore saving on security and rental costs. Indirect costs to UNOPS are 7%, which is a similar fixed rate to other UN agencies.
[36] CTG Global, who provide manpower (ie. 4 full time Inspectors). CTG Global is a UAE-based organisation operating since 2004 that specialises in the mobilisation and management of skilled and unskilled personnel for the humanitarian and development community in fragile and conflict-affected states. The Global Agreement has lower costs than other providers.

Technical Advisory support: The CHASE business case covers the resourcing of expert humanitarian support. DFID has assessed the most economical way to resource flexible expert humanitarian advice was through this competitively awarded CHASE OT contract. Drawing on this existing contract avoids the transaction costs associated with a specific Yemen tender. DFID Yemen will also review our use of CHASE OT within our staffing model annually, with the objective to transition off using contracted CHASE OT staff for longer term roles within eighteen months. For each Standby Partnership, the budget is carefully scrutinised and negotiated, where possible.[37]
[37] SBPP budgets use standard UN rates for Yemen.

Efficiency

Logistics Cluster: Logistics Cluster fills all humanitarian planes with light, fragile or sensitive humanitarian cargo whenever seat occupancy rate is low.[38] UNHAS also maintains flexible flights, adding an extra flight to the Amman-Sana’a route to respond to demand. Other efficiencies offered by the Logistics Cluster is the dual use of the Aden sea shuttle, which not only provides a safe and reliable way for humanitarian workers to reach Aden port, it also offers cargo capacity (used for medical supplies in the current cholera response) and accommodation for humanitarian workers (given that the UN guesthouse capacity in Aden is still limited).
[38] For example, in May 2017, UNHAS transported 876 passengers along with 445 kg of “light weight cargo” to Aden and Sana’a

UNVIM: The efficiency of UNVIM can be demonstrated by the time taken for ships to be verified or referred for inspection once UNVIM have received all documentation. Since its inception, this time has remained under 48 hours. UNVIM’s Steering Committee consists of the Government of Yemen and the Coalition, and UNVIM’s donor base includes the UK, US and New Zealand. This range of stakeholders and the high level of donor engagement ensure that delays that risk UNVIM’s efficiency can be rapidly escalated.

Technical Advisory Support: The flexibility provided by CHASE OT offers efficiencies to DFID by allowing the volume of humanitarian expertise within the department to expand and contract at short notice. For example, DFID Yemen was able to contract a specialised humanitarian adviser with health expertise to support the response to the cholera outbreak. Funding strategic surge positions through Standby Partnerships supports a more efficient and effective UN response.

Effectiveness
OCHA Core Costs: Supporting OCHA in Yemen is crucial to enable them to fulfil their coordination role in country and support their leadership in a Level 3 crisis. An effective OCHA underpins the effectiveness of the entire architecture of the humanitarian response.

Logistics Cluster: Funding WFP Logistics allows a more cost-effective and timely implementation of the humanitarian response orchestrated by all agencies coordinated through the cluster system. It also offers a demonstrated capacity to scale up activities when needed (e.g. ongoing cholera response) and to anticipate such needs (e.g. Logistics Cluster Hodeidah port contingency plan). Funding UNHAS to provide a common service helps the humanitarian community achieve on-time humanitarian interventions as well as efficient, reliable and sustainable access to those in need. UNHAS capacity is also crucial for medical and/or security evacuations from remote areas.

UNVIM: An approximate monthly operational cost of £450,000 per month, UNVIM plays a vital role in facilitating the flow of commercial goods into Yemen. Between May and August 2017, 2.23MT of cargo including food and fuel was discharged at Red Sea ports port having undergone UNVIM clearance. This includes 1.26 million metric tonnes of food, roughly equivalent to two and a half months of Yemen’s food needs. It is clear that UNVIM outputs do not necessarily lead to desired outcomes, and there continues to be issues both in terms of the Coalition handling of ships, the capacity of Red Sea ports and importers’ access to finance, which impact on the overall volumes of imports to Yemen.. However, UNVIM has influence in other ways – for example, providing data to understand the maritime situation and engaging with the Coalition to improve management processes. DFID continue to play a lobbying and strategic role to improve the effectiveness of UNVIM.

Technical Advisory Support: In terms of provision of expert advice, CHASE OT has scored ‘A’ or an ‘A+’ in the last three Annual Reviews confirming they are effective at providing flexible expert humanitarian advisers at short notice. Standby Partnership positions are also a proven means to allow the rapid recruitment of technical expertise to support the wider humanitarian response.

Equity
Ensuring that the benefits of humanitarian assistance are distributed fairly is at the core of this programme. Facilitating humanitarian access routes in Yemen, supporting commercial imports, investing in a common accountability mechanism and improving the humanitarian coordination architecture, including through strengthened conflict and gender-sensitivity and social inclusion capacity in Yemen all support a more inclusive and equitable response.

Funded agencies performance will be monitored through the following VfM indicators using the methodology of Economy, Efficiency and Effectiveness. This will inform real-time, strategic, decision making on the performance of the programme overall.

VFM Principle	Measure	VFM If…	Rationale
Economy	CHASE OT staff costs as % of total costs	Reduced or kept low	Lower input unit costs are a sign of ensuring the better value in our procurement arrangements
Efficiency	% of DFID Yemen staff posts filled	Increased or kept high	A fully resourced team will be better able to deliver the range and volume of outputs we are seeking; to ensure the programme is effective.
	% UNHAS seat occupancy rate.	Kept high	A measure of how efficiently the service is running - i.e. how well utilised the flights are
	% of applicant ships verified or referred for inspection within 48 hours of receipt of documentation	Kept high	A measure of efficiency of the UNVIM mechanism
Effectiveness	Proportion of output indicators meeting or exceeding expectation	Higher than 50%	A measure of performance - if individual areas of work are performing well, it points to the overall programme being effective.
	# quality OCHA inter-agency sitreps, monthly bulletins, quarterly dashboards based on cluster and HCT working groups’ inputs.	Kept high	A measure of the effectiveness of OCHA management and coordination
Cost Effectiveness	% in-kind shipments that arrive and are handed over to recipient agency within agreed delivery time	Kept high	Ensures goods are not delayed, ensuring good use of funds for rapid delivery
	Disbursement rate of UNVIM/WFP Logistics and OCHA core costs.	Kept high	Given the humanitarian imperative, a disbursement rate is a good indicator of the speed of delivery and the risk of the programme not disbursing fully

Commercial Case

What is the proposed funding mechanism/form of arrangement?
DFID Yemen will sign a Memorandum of Understanding (MoU) with OCHA, WFP, UNOPS and UNICEF which are agreed between DFID and the UN agency at HQ level. The MoUs will outline the value and timing of the planned payments, the timeline for reporting and include clauses on anti-terrorist financing and DFID’s zero tolerance for fraud and corruption. DFID Yemen will use the CHASE OT contract for technical expertise and SBPP deployments.

What assurances have been obtained on capacity and capability of the organisation/s to deliver the programme/intervention?
The above UN Agencies have an established response in place, and were selected based on proven experience and existing presence in Yemen, details of which are outlined below. All have provided their annual audited statements. All have successfully delivered with DFID funds in the previous iteration of the programme, which scored an ‘A’ in its last Annual Review.

OCHA: The Due Diligence of OCHA’s activities showed that they have the experience, capacity and capability to deliver in Yemen. Since 2015, DFID’s support to OCHA technical capacity, field presence and overall leadership has resulted in:
- Mobilising the Humanitarian Country Team (HCT) and the cluster system for the production of interagency countrywide Humanitarian Needs Assessments, providing high-quality information for the UN appeals (Humanitarian Response Plan) over the past two years. Though under-funded, Yemen HRPs are some of the best funded in the world.
- A number of guidance papers through the setup of various working groups, including the Community Engagement Working Group, the Cash and Market Monitoring Working Group, the Humanitarian Access Working Group, the Partnership Working Group) which have been rolled out through the cluster system.
- Regular reporting in the form of flash updates, monthly bulletins, HRP and implementation status snapshots. It has also facilitated missions to Yemen for donors and journalists.

CHASE OT technical expertise and Standby Partnership: The CHASE OT contract, which also manages Standby Partnership, was awarded through competitive tendering and has scored consistently highly at the annual review point, scoring either A or A+ for the last 3 years. This capability has been recently re-procured and the new contractual arrangement will commence following transition in November 2017. As part of the tendering process, the procurement due diligence and full technical/commercial (value for money) evaluation was undertaken. CHASE OT contractors appointed to key posts within DFID Yemen are competitively selected.

Accountability to Affected Populations (AAP): The AAP intervention is expected to be delivered through UNICEF. UNICEF is an existing DFID Yemen partner. DFID Yemen currently funds UNICEF for a £38 million programme focusing on nutrition, health and WASH. UNICEF have a strong track record delivering in Yemen, with the last Annual Review (March 2017) scoring an ‘A’. DFID Yemen is currently undertaking analysis of their capacity to manage the APP pilot, as well as the commercial and management arrangements that will be in place.

WFP Logistics: The Logistics Cluster, which is coordinated by WFP, is responsible for UNHAS services. Within WFP, it is WFP Aviation that coordinates the provision of safe, reliable, cost-efficient and effective common air services to the humanitarian community. Since April 2015, DFID has funded both UNHAS and the Aden sea shuttle in Yemen, without which the ability of UN agencies and humanitarian NGOs to respond to the crisis in Yemen would be severely, if not completely, restricted.

The Due Diligence on UNHAS demonstrated that it has the proven operational capacity to deliver in Yemen, with adequate organisational, procurement and financial management processes. WFP Aviation manages its partners, who are primarily aircraft operators, and ensure they meet international safety requirements and UN Aviation Standards.[39] All air operators undergo an evaluation process conducted by WFP's Aviation Safety Unit before are accredited as WFP service providers. Crucially, UNHAS has developed their engagement with government and non-government actors at local, national and regional levels as well as with the Humanitarian Country Team (HCT) giving it the political leverage to continually operate in the political context. DFID’s position on the Steering Committee, and regular briefings with the Logistics Cluster gives us assurances on both the need for logistics support and on UNHAS’ ability to continue to deliver this essential service in Yemen until safe and reliable commercial flights are resumed in Yemen.
[39] International Civil Aviation Organization's Standard Aviation Recommended Practices (SARP).

UNVIM (managed by UNOPS): The UN Office for Project Services (UNOPS) manage UNVIM. DFID have funded UNVIM since its establishment in Yemen in 2015 along with the US and New Zealand.

DFID’s experience funding UNVIM since 2015 has provided assurances to DFID on its flexibility to deliver in changing political contexts. The Due Diligence Assessment summarised that UNOPS is a well-established organisation with strong policies, procedures and accountability mechanisms, with no findings which pose an unacceptable negative fiduciary or reputational risk to DFID. External and internal audits are periodically carried out and are publicly available. Specific governance arrangements have been established that include the UN, the Government of Yemen and the Coalition, which enable its delivery in a complex political environment. The challenges that UNVIM face are less around its own processes and procedures, and more around the political and conflict context within which it operates. DFID have and expect to continue to have to provide political support and lobbying to ensure its effective operations.

How will contract and supplier performance be managed?
DFID will hold the UN agencies to account for the management and delivery of outputs through quarterly reviews of the logframe, expenditure reports and by conducting annual reviews. Regular meetings will ensure DFID are alerted to delivery risks such as access constraints early on and can work together with partners on alternative arrangements. Future payments will only be made after satisfactory reporting of the previous period, demonstration of delivery against outputs, evidence of future plans and accurate forecasting. In addition to these arrangements, DFID will:
OCHA: Engage with the OCHA Yemen and the UN Humanitarian Coordinator (UNHC) through separate fortnightly phone calls on the programme delivery as well as broader context updates. Attend the monthly Humanitarian Country Team (HCT) donor meeting chaired by the UNHC as a way to be kept informed and challenge the HCT on the implementation of the OCHA-led Humanitarian Programme Cycle (including HNOs, HRPs and Periodic Monitoring Reports).
CHASE OT: DFID Yemen will identify technical expertise required to assist in policy and programme development for the Yemen response. DFID Yemen will then contact CHASE OT with terms of reference. CHASE OT will identify potential candidates, providing CVs for DFID Yemen to choose the most appropriate candidate. DFID Yemen will then pay CHASE OT for the fees and expenses of the contracted staff as identified in the tasking order. CHASE OT inputs for staffing include appraisals of performance against deliverables set out in each Terms of Reference, and DFID Yemen will use these to feed back to CHASE on the performance of staff. These will be used by both CHASE OT and DFID Yemen to inform choices for future recruitment of staff, to ensure candidates have the skill set required to deliver and that equipment is delivered in an efficient manner. This will be used to check that the staffing expertise adds value compared to recruitment of Home Civil Servants.
Standby Partnerships: UN Agencies will submit requests to CHASE OT with terms of reference for staff to fill critical gaps. DFID Yemen will review the request and agree whether it is an essential post and inform CHASE OT of their decision. CHASE OT will then go their Standby Partners (CANADEM, RedR, Norwegian Refugee Council and the Danish Refugee Council) to identify candidates with the relevant skills who can be deployed at short notice. The UN agencies will then select their candidate with DFID Yemen covering their costs. In addition, where DFID Yemen identifies a critical gap in the response, they will approach UN agencies offering support in this area and developing a terms of reference jointly with the UN agency.

Accountability to Affected Populations: UNICEF are the expected partner to manage the AAP pilot. Management arrangements are still being finalised. DFID Yemen already meets with UNICEF on a monthly basis, so it is likely that management will take place through this forum.
Logistics Cluster: Have a seat on the WFP/UNHAS Steering Committee and engage in regular briefings with the Chair of the Logistics Cluster. Use DFID and WFP’s bi-weekly meetings to raise logistical issues.
UNOPS: Attend the UNVIM monthly donor meetings, and engage on an ad hoc basis with UNVIM representative in Riyadh and Djibouti. Conduct site visit to UNVIM activities in Djibouti.
What are the key cost elements that affect overall price? How is value added and how will we measure and improve this?

OCHA, UNOPS and UNICEF: Primary cost driver are national and international staff salaries which are driven in part but the country of deployment, with fees factoring in the hardship of the post. The UNOPS budget has been scrutinised. The UNICEF budget is not yet agreed, but key costs are expected to be personnel.

CHASE OT and Standby Partnerships: Costs for expert humanitarian advice from CHASE OT are set as part of the CHASE contractual agreement. Positions through Standby Partnership are in line with standard UN rates. Within this, key cost drivers include daily rates which are determined by the level of expertise, duration and location. The CHASE OT Contract has set maximum rates for staff. There are costs reductions for deployments with a cumulative duration of over 3 months.

Logistics Cluster: Key cost driver for UNHAS flights is the rent and insurance of chartering planes, fuel, airport fees and personnel. The number of seats used and related cost per passenger on UNHAS flights will be monitored.

Value for Money (VfM) through procurement

There is no direct procurement of goods for this programme.

All three UN agencies funded through this programme have been assessed as part of the Multilateral Development Review and have been subject to Central Assurance Assessments to assess their ability to deliver value for money. Additionally the budget for UNVIM was negotiated between donors and UNOPS to drive downs costs. WFP undertake all procurement for UNHAS following UN procurement rules. The policies have been shared with DFID as part of the due diligence and are satisfactory.

The competitive nature of CHASE OT’s pre-arranged contracting with suppliers means that quality is tested and assured, maximum prices have been competitively tendered and the response is quick. CHASE pre-existing response frameworks have already considered VfM and allow us to maximise speed against quality standards and corporate social responsibility considerations. The Standby Partnership mechanism brings VfM through speed, efficiency and quality for the coordination (and delivery) of humanitarian assistance. Directly providing secondments allows DFID to ensure that key roles are deployed quickly and that experts are of a high quality.

All components will be assessed using the log frame and the value for money indicators for the project. If components deliver against the milestones and targets set at the prices negotiated they can broadly be considered to have offered value for money.

Flexibility and Scenario Planning

As the trajectory of the conflict in Yemen remains uncertain, DFID Yemen encourages all partners to scenario plan – and demonstrate how they would adapt their activities if there were certain ‘trigger points’ causing a major change in need and approach. DFID will remain flexible to re-programme activities as a result of major changes to the conflict dynamics. This includes funding through the Emergency Response Mechanism (ERM), a funding mechanism which can be activated in times of escalating need, whereby existing DFID Yemen partners are asked to propose an intervention which they have the capacity to rapidly implement, once funding is confirmed.

Financial Case

What are the costs, how are they profiled and how will you ensure accurate forecasting?

The programme will be funded from DFID Yemen’s RDEL budget allocation. The total budget is for £18.3 million over three years, it is ODA eligible, and is 100% humanitarian expenditure. Anticipated budget profile and sector codes are shown below:

Sector code: Relief Coordination, Protection and Support Services (72050)
Benefitting country: Yemen
Component	Funding Type	2017/18	2018/19	2019/2020
Support to OCHA core costs	Multilateral Organisation (109)	1,500,000	1,500,000	1,500,000
Humanitarian advisory support through CHASE OT	Humanitarian Assistance (105)	£350,000	£250,000	£100,000
Standby Partnerships (SBPP)	Humanitarian Assistance (105)	£200,000	£100,000	£100,000
UNOPS - Support to United Nations Verification Mechanism (UNVIM)	Multilateral Organisation (109)	£1,300,000	£1,300,000	£1,300,000
WFP - Logistics support including to UN Humanitarian Air Service (UNHAS)	Multilateral Organisation (109)	1,770,000	1,500,000	1,500,000
Accountability to Affected Populations proposal	Multilateral Organisation (109)		1,000,000	1,000,000
Contingencies through Emergency Response Mechanism	TBC		1,000,000	1,000,000
Sub-Total		£5,120,000	£6,650,000	£6,500,000
Total				£18,270,000

- The first payment of £1.77 million to WFP (to fund UNHAS) will be made in December 2017 to fund UNHAS services in November and December 2017.
- The first payment of £1.3 million to UNOPS (to fund UNVIM) will be made in October 2017 to fund UNVIM activities from August until December 2017.
- The first payment to OCHA of £500,000 will be made in October 2017 to fund OCHA activities until the end of the financial year.
- The first payment for Accountability to Populations is expected to go to UNICEF and commence from 2018/19.
- Payments to CHASE OT personnel will be made on a monthly basis and in arrears.
- Payments to any Standby Partnerships are made every six months and in arrears.

Subsequent payments and funding allocations for outer years will be contingent on our assessment of the need, and of the continued effectiveness of these interventions in facilitating the broader response. We will also continually assess DFID share vis a vis other donors as part of ongoing work to engage other donors to maintain and increase support for the interventions in this business case. While the preference is for all payments to be in arrears, the payment schedule will depend on the organisation’s pipeline and the immediate need. Forecasts and regular updates are of particular importance given the access challenges. Explained variances are anticipated. Should there be any significant change to the conflict, DFID reserve the right to change the planned contribution. Should issues occur that significantly impair delivery of the project, DFID and partners will discuss these changes, attempt to resolve them and, in the last resort, DFID will modify or terminate its financial contributions to projects.

In 2017/18, the funds have been allocated from DFID Yemen’s resource allocations. The DFID Yemen Head of Office will agree all future allocations, including ensuring resources are available before approving use of the contingency balance. All payments will be based on our assessment of the needs, and performance of various agencies. The outer year budgets (2018/19 and onwards) have not been formally committed to partners to allow us flexibility to respond if circumstances and needs change, including considering shifting implementing partners. This includes using a Emergency Response Mechanism for new funding proposals related to this programme should there be a major de/escalation in the conflict.

Direct Programme and Non-programme attributable costs (NPAC): DFID Management costs are 40% of a Programme Manager, 40% of Humanitarian Advisor/s and 10% of SRO. This is within DFID Yemen’s current head count. The indirect costs of WFP, UNHAS and OCHA are all fixed at 7%.

Payment of Funds
The UK has a Global Framework Agreement with WFP (who manage UNHAS) that forms the basis for the funding agreement. DFID will transfer the funds under the terms set out in the Contribution Arrangement. The UK will sign MoUs with UNOPS (who manage UNVIM) and with OCHA. DFID will transfer the funds under the terms set out in the MoU.

We will pay in arrears unless partners demonstrate the immediate need for funds. We will maintain regular contact with WFP, UNOPS and CHASE OT to ensure that data input as part of DFID’s monthly finance cycle is accurate and that DFID is able to identify and monitor the financial impact of any changing circumstances and emerging risks. In line with the Resource accounting principles, where DFID funds can be separately tracked we will forecast monthly on DFID’s financial systems to reflect the timing of the activities being funded. DFID will receive quarterly updates from all partners. Funds will be committed to all partners in sterling. WFP, UNOPS and OCHA will carry the risk of currency fluctuations, including any fall in the value of sterling as well as retaining the benefits when there is an increase in the value of the pound relative to local currency.

Financial Management
OCHA, WFP and UNOPS have strong financial systems in place and DFID have used our central and country relationships to build on and improve their financial reporting. UNHAS submits quarterly financial reports and WFP submit annual audited statements which separately identify DFID funds. These will be reviewed for financial anomalies or red flags by the Programme Manager, with support from the Yemen or MENAD Finance Manager as required. The WFP Due Diligence Assessment also reviewed the financial systems in place showing that financial processes and procedures were in place, with adequate Standard Operating Procedures (SOPs). However, the Due diligence Assessment advised DFID to assess how far these procedures are followed in country (for example through spot checks and the annual review). Recommendations will be followed up. Procedures for carrying out financial and procurement activities are included in UNOPS’ overarching policies and these are implemented on behalf of UNVIM by the UNOPS Regional Hub in Amman.

Assessment of financial risk and fraud
Operating in this conflict, where institutions are weak, there is inevitably a high risk of aid diversion, corruption and fraud. DFID’s policy in Yemen is to work with well-established organisations who demonstrate strong systems and controls to both detect and prevent fraud. This was a key consideration in the selection of OCHA, WFP and UNOPS as delivery partners. All have in place robust policies and procedures to prevent fraud, bribery, corruption, terrorism and money laundering. The Management Case incorporates a more detailed assessment of their controls. Due Diligence Assessment also reviewed their systems specifically around robustness of fraud prevention and provided DFID with evidence that controls are robust to detect endemic or significant fraud.
While these precautions will not remove all risk, in the past programme there were no reported cases of aid diversion from any of OCHA, UNHAS or UNOPS. DFID Yemen regularly communicates to partners their responsibility to report aid diversion, corruption and fraud to DFID. When any partner becomes aware of an incident they will report the incident to the DFID Programme Manager or directly to DFID’s Counter Fraud Service within 48 hours. They will fully investigate the incident until the matter is resolved, keeping DFID up to date.

Management Case
Management arrangements for implementing the intervention

  1. DFID Management
The DFID Senior Responsible Owner is the DFID Yemen Humanitarian Team Leader. The programme will be managed by the Programme Manager. Technical expertise will be provided by a Humanitarian Advisor and cross-cutting advisers. They will scrutinise the delivery, risks and finances through reporting and the project’s delivery plan.

Within DFID, the Conflict Humanitarian and Security Department (CHASE) are responsible for the UK’s institutional relationships with WFP and OCHA. The UK is a member of the WFP Executive Board which provides an oversight function. DFID will work closely with CHASE to ensure consistency with the wider objectives of UK core funding, sharing good practice and lessons – specifically through DFID’s core funding arrangement with OCHA.

The key DFID oversight arrangements are:
- DFID has a seat on the UNHAS Steering Committee, which meets bi-monthly. DFID also engages with the Logistics Cluster on an ad hoc basis through the DFID advisor in Amman.
- Quarterly face-to-face meetings between the DFID Team and the WFP will be used to discuss Logistics Cluster and UNHAS performance, finances and risks.
- DFID engages with UNVIM through monthly donor calls, and through DFID representatives in Riyadh and Amman. DFID also receive daily and monthly updates from UNVIM on performance.
- The DFID team have bi-weekly meetings with the Head of OCHA Yemen to engage on specific issues as they arise.
- DFID expect to engage with UNICEF on a monthly basis on progress and key challenges. DFID will expect UNICEF to report quarterly.
- All UN partners provide lists of their downstream partners and some will be selected for stakeholder interviews as part of the DFID Annual Review process.
- Annual Reviews during the programme life and Project Completion Report at the end of the programme.

  1. Partner Management

The Logistics Cluster, chaired by WFP, manage the services from their offices in Sana’a, Aden, Djibouti and Amman. These are staffed by international and national staff with in-depth knowledge of the Yemen context. They are supported by both the Regional Bureau in Cairo and Headquarters in Rome. UNOPS manage UNVIM primarily from Djibouti port, with staff also in Saudi Arabian ports. OCHA operations are managed from Amman and Sana’a. Deployment of CHASE OT staff is managed from London.

Risks of the intervention and how will these be managed
Given the high return of providing life-saving humanitarian and development assistance, DFID Yemen has a high risk appetite at the context, delivery and operational level but a low risk appetite at the fiduciary, reputational and safeguarding level. We mitigate risks by: working with established agencies with a strong track record in delivering in Yemen; up to date due diligence assessments on all partners; monitoring delivery regularly including conducting site visits if possible (outside of Yemen); cyclical independent monitoring and verification of the programme (in Yemen); and reviewing the risks and our tolerance thresholds regularly at the programme and portfolio level.
The Logistics Cluster, UNOPS and OCHA have their own risk management system, including a live risk register, and will report regularly to DFID. The main risks (net – after mitigation) identified in this programme are detailed in the delivery plan and outlined below. These will be monitored and discussed on a quarterly basis with all Partners and updated accordingly. They will be managed or escalated in line with DFID Yemen’s Risk Management Strategy.

The main risks identified by DFID Yemen in collaboration with our partners are shown below in our risk table. These will be monitored and updated throughout the lifetime of the project.
Component	Risk Description / (Net risk colour)	Mitigating Actions
All	Conflict restricts access by humanitarian partners to Yemen / Probability: Likely / Impact: Major	All Partners: De-conflict field missions, convoys and fixed assets with the EHOC (Saudi-led Coalition) notification system. / All Partners: The security situation is regularly monitored with updated security plans and contingency measures in place. / All Partners and DFID: Conflict analysis and its implications reflected in updated management strategies and activity plans. / All Partners: Hold regular meetings with district authorities, local council members and religious leaders to improve access and acceptance at the local level. / All Partners: Work through national organisations whenever possible, employing local staff. / DFID: Ensure UNOPS, WFP and OCHA have strong contingency plans,
All	Threats to staff safety from state or non-state actors / Probability: Likely / Impact: Major	All Partners: Staff evacuation plans in place and regularly updated. / All Partners:Safety and security protocols to protect staff and assets are in place and followed. / All Partners:Access information locally about movements/activities of various groups; Listen to the local population. / All Partners:Work closely with local groups who can work as deterrent for such situations. / All Partners and DFID: Regular updated security analysis. Continued close monitoring of situation jointly with other actors. Hold regular consultative meetings with the district authorities, local council members and religious leaders to maintain acceptance. Where deemed necessary restrictions on movements in cities. / All Partners: In extreme situations, evacuate staff as per the organisational policy. / All Partners: Coordinates for offices and accommodation provided to UN/ KSA for de-confliction.
All	Financial intermediaries lose international and local access to funds. / Probability: Possible / Impact: Major	DFID: Encourage OCHA and WFP to hold bank accounts with multiple banks in Yemen and to use more than one financial intermediary inside of Yemen to deliver payment. / DFID: Monitor the banking sector challenges, and work with stakeholders to have sufficient plans in place. / DFID: Continue lobbying the central bank to implement all measures needed to keep Yemen from being black listed by Financial Action Task Force - Middle East and North Africa (FATF MENA).
Logistics Cluster (UNHAS)	Restrictions in flight clearances. Heightened conflict – airspace and airports no longer safe enough to fully operate / no adequate ground services. / Probability: Possible / Impact::Major	WFP: Regular liaison with Coalition. / WFP and OCHA: Identify alternative solutions for the evacuation of humanitarian staff and families. / DFID: HMG engagement for the reopening of Sana’a airport to commercial flights
Logistics Cluster (UNHAS)	Increasingly stringent policies by the Coalition or the Government of Yemen restricts humanitarian access to Yemen (e.g. double visa requirement, restrictions on journalists) / Probability: Likely / Impact::Major	WFP, OCHA: Regular liaison with logistics offices and hubs on procedures, regular communication with agencies on changes in procedures; / WFP, OCHA: Regular liaison with Coalition and GoY / WFP, OCHA:Engagement with all partners to gauge experience on UNHAS / DFID: HMG political engagement
UNVIM	Ships and/or Member States unaware of procedure GoY or Coalition restrict entry of ships verified and cleared by UNVIM, bypass UNVIM altogether or instruct UNVIM to divert vessels away from Hodeidah without justifiable reasons / Probability: Possible / Impact: Major	UNOPS: Regional Humanitarian Coordinator to send ToR, SOP & letters to all stakeholders; Embassies to confirm Member States’ understanding that UNVIM does not override Sovereign right of Government / UNOPS: Process communicated to GoY and Coalition in advance through UN Secretary General’s letters. / UNOPS: GoY and Coalition on Steering Committee to resolve such occurrences. If necessary, reported to UN Sanctions Committee and raised with Member States. / DFID: HMG political engagement
UNVIM	Ships do not comply with requests for physical inspections and/or Restrictions in entry or clearance of cargo due to heightened conflict affecting border countries; increased port traffic. / Probability: Possible / Impact::Major	UNOPS: Communication of process in advance through UN Secretary General’s letters. / UNOPS: contact ship’s company to explain GoY within rights to block ships. / UNOPS: Regular liaison with logistics offices and hubs on clearance procedures, regular communication with agencies on changes in procedures
UNVIM	UN lacks capacity to verify all ships within 48 hours meaning physical inspection takes longer than expected. / Probability: Possible / Impact::Major	DFID: Check UNOPS fully staffed / DFID: UK Maritime Advisor visit to Djibouti to check operational capacity / UNOPS: Steering Committee to discuss case and explain to donors. / DFID: If chronic problem, consider additional staff.
All	Multi-donor projects struggle to diversify their donor base and DFID funds more than their fair share. / Likelihood: Medium / Impact: Moderate	DFID: Monitor DFID share of projects and continue to engage with other donors to fund vital enabling services.
OCHA	Weak coordination between humanitarian actors, resulting in lower quality response / Likelihood: Medium / Impact: Moderate	DFID: Monitor leadership and management carefully and, where necessary, Ministers and the UN missions in New York and Geneva to push for improved planning and high quality gap filling if staffing is an issue. / OCHA: Ensure advocacy and lobbying strategy is in place and strategic deployments into the UN system through the standby partnership to bolster human resources and ensure that critical coordination and information management roles are in place.
All	Lack of national and local authority cooperation with UN creates delays / Likelihood: Possible / Impact: Moderate	DFID: Increased number/strength of OCHA access negotiation capacity a direct mitigation / OCHA: Conflict monitoring/analysis will also reveal fractures in chains of command/collaboration within and between conflict sides that affect this, helping the agencies to prepare/calibrate a response / All Partners: Maintain close working relationships with government ministries and local authorities. / All Partners: Work together in order to jointly pass the message to the authorities in order to facilitate the access to the beneficiaries and movement to the field; / DFID: UK support to UN action to engage with local level structures and set up regional hubs. / All Partners: Support OCHA Access Advocacy work by sharing information on their Access Constraints with the Humanitarian Access Working Group chaired by OCHA Sana’a, in order to populate the Access Monitoring and Response Framework (AMRF) as a safe and effective joint access advocacy tool.

Fraud/Corruption/Aid diversion Risk Matrix
Risk Description / (net risk colour)	Mitigating Actions
Mismanagement of funds (fraud and corruption) by partner or downstream partners / Probability: Possible / Impact: Major	DFID assessed all partners fraud and corruption risk through Due Diligence Assessments. / All Partners: Receive regular communications and fraud awareness sessions from DFID. / All Partners: Conduct downstream partner appraisals, maintain strict financial procedures, and include code of conduct policies in all FLAs. All partners only pay their partners in arrears and after reconciling all costs. / All Partners: Undergo annual financial audits and reports shared with DFID / All Partners: Whistle blower policies and mechanisms for beneficiaries and others to notify of any fraud and corruption. / All Partners: Required (and reminded) to report any cases or suspicions of misappropriation or fraud of DFID funds.
Damage and diversion of supplies during storage or transportation, additional reputational risk if aid is diverted to terrorist organisation. / Probability: Likely / Impact: Major	All Partners: Keep up to date with security updates and sit reps to make early decisions on relocating people and assets. / All Partners: Have appropriate precautions and controls such as security guards, bars, CCTV, stock logs etc are in place / All Partners: always investigate opportunities for asset recovery of losses and assess any lessons learnt on controls. / All Partners: required to report any cases or suspicions of aid diversion of DFID funds. / UNHAS and UNVIM have put in place beneficiary/client feedback mechanisms. / All partners have confirmed their compliance with UK counter-terrorism legislation. / All Partners: Draw on conflict analysis, specifically CSSF-commissioned ‘political economy’ and ‘war economy’ analysis to inform partnership and procurement choices
Cash going to terrorist organisations / Probability: Possible / Impact: Major	DFID: Delivery chain mapping undertaken identifying all stakeholders before reaching the beneficiary. / DFID Yemen policy followed on working alongside (de facto) government institutions. / DFID: Ensure all partners conduct robust risk assessment on their partners and suppliers and transactions are made through legitimate financial institutions/intermediaries. / DFID: Annual audited statements provide assurance funds are all accounted for.

How will progress and results be monitored and measured?

The programme will be managed through a single logical framework (logframe). The logframe will track progress against measurable indicators, determined in the development of this Business Case and monitored quarterly. The completed logframe will provide the results against which the Annual Review and Project Completion Review will score the programme. If progress is off track both with regards to the logframe indicators and more generally in terms of risk mitigation and associated performance, DFID Yemen will work with partners to put in place a Performance Improvement Plan, which would include an action plan and monthly progress meetings.

- CHASE OT will provide final reports from SBPP and humanitarian advisory support staff.
- UNHAS will provide standard reporting against its proposal, as per DFID’s global agreement with UNHAS.
- OCHA will provide standard reporting against its proposal, on an annual basis and upon completion.
- UNOPS will report to donors on a monthly basis against agreed indicators. This common reporting to donors will minimise the administrative burden on UNOPS and ensure consistent reporting to all donors.

DFID monitoring:
Due to the constrained operating environment field visits are not possible at this time, with the exception of Djibouti. Therefore monitoring of results will primarily be through a desk review examination of progress reports, including through DFID monthly programme board meetings, and final reports, as well as regular meetings with the partners in country.

Annual Review
In compliance with DFID Smart Rules the first annual review will be carried out 12 months after the beginning of the programme. It will track progress made on recommendations in the project completion review of the preceding programme. It will also reflect on key cross-cutting issues, including gender sensitivity and social inclusion, conflict sensitivity, value for money and environmental impact. A project completion review will be completed within 3 months of the project end date (October 2020). We will coordinate closely with CHASE so that information is exchanged between this and the review of WFP and OCHA core funding. The predecessor programme is currently undergoing a project completion review – relevant findings and recommendations will be implemented under this successor programme.

Evaluation
The Accountability pilot has ring fenced evaluations funds for an evaluation after its first year. Funds in outer years of this programme are provisionally earmarked for evaluation of certain components – subject to an evaluability assessment. The programme will also collaborate with and support where appropriate any independent evaluations, learning reviews or analyses being carried out that cover aspects of the response in which this programme is involved.