Addendum No. 2 to the
Standard Administrative Arrangement
between
the United Kingdom’s Department for International Development and
The United Nations Development Programme (UNDP)

The United Kingdom’s Department for International Development (hereafter referred to as the “Donor”), and the United Nations Development Programme (hereinafter referred to as “UNDP”) acting as Administrative Agent of the UN Community Resilience and Recovery Support to FATAs Returning Internally Displaced Persons Programme in Pakistan on behalf of itself and all the Participating UN Organizations, (hereinafter referred to as the “Administrative Agent”) have agreed as follows:

WHEREAS, Participating United Nations Organizations that have signed a Memorandum of Understanding (hereinafter referred to collectively as the “Participating UN Organizations”) have developed a UN Community Resilience and Recovery Support to FATAs Returning Internally Displaced Persons Programme in Pakistan (hereinafter referred as the “Joint Programme”) starting on September 2015 and ending on June 2017, as may be amended from time to time, as part of their respective development cooperation with the Government of Pakistan as more fully described in the Joint Programme Document (hereinafter referred to as the “Joint Programme Document”), a copy of which is attached hereto as ANNEX A, and have agreed to establish a coordination mechanism (hereinafter referred to as the “Steering Committee”) to facilitate the effective and efficient collaboration between the Participating UN Organizations and the host Government of Pakistan for the implementation of the Joint Programme;

WHEREAS, in Addendum 1 signed between the Donor and the Parties on 27 October 2016, extended the Joint Programme to 31 October 2017 and modified the schedule of payments.

The Standard Administrative Arrangement between the Parties is therefore modified to reflect the extension of the Joint Programme to 31 October 2018 and an additional contribution of Five Million Pound Sterling (GBP 5,000,000), which brings the total contribution to Thirteen Million Pound Sterling (GBP 13,000,000).

Preamble:
WHEREAS, Participating United Nations Organizations that have signed a Memorandum of Understanding (hereinafter referred to collectively as the “Participating UN Organizations”) have developed a UN Community Resilience and Recovery Support to FATAs Returning Internally Displaced Persons Programme in Pakistan (hereinafter referred as the “Joint Programme”) starting on September 2015 and ending on 31 October 2018, as may be amended from time to time, as part of their respective development cooperation with the Government of Pakistan as more fully described in the Joint Programme Document (hereinafter referred to as the “Joint Programme Document”), a copy of which is attached hereto as ANNEX A, and have agreed to establish a coordination mechanism (hereinafter referred to as the “Steering Committee”) to facilitate the effective and efficient collaboration between the Participating UN Organizations and the host Government of Pakistan for the implementation of the Joint Programme;

WHEREAS, the Donor has agreed to make an additional contribution of Five Million Pound Sterling (GBP 5,000,000), bringing the total contribution to Thirteen Million Pound Sterling (GBP 13,000,000).

Schedule of Payments (Annex B)

Date	Amount
October, 2015	£4,000,000
October, 2016	£2,000,000
April, 2017	£2,000,000
November/December, 2017	£2,500,000
April, 2018	£2,500,000

All other terms and conditions of the Standard Administrative Arrangement remain unchanged. This addendum shall enter into force on the date of signature by the Participants.
IN WITNESS WHEREOF, the undersigned, being duly authorized representative of the respective Participants, have signed the present Amendment to the Standard Administrative Arrangement in English in three copies.

For the Donor	For the Administrative Agent
Signature: ____________________	Signature:
Name:	____________________	Name:
Title:	____________________	Title:
Place:	____________________	Place:
Date:	____________________	Date: