## NE Confl Mgmnt & Stab Logframe
Logframe
Programme: | UK Conflict Stability and Security Fund Nigeria
Project Start Date: | 2016-08-01
Implementing organisations: | Mercy Corps, CIVIC, HD and Okapi
Project title: | North East Nigeria Conflict Management and Stabilisation Initiative
Project duration: | 8 months
Project cost: | £1.7m
IMPACT | Impact Indicator 1 |  | Control (Mar 2017) | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
Strengthened community resilience to violent extremism and increased social cohesion between conflicting communities | Percentage of people who report satisfactory government services at the local level | Planned | 60.68% | n/a | BV + 5% | n/a | BV + 10%
|  | Achieved | Significant (p<.01) | n/a |  |  | BV +11.86%
Source
End-line surveys from a representative sample of program participants and control communities.
| Impact Indicator 2 |  | Control (Mar 2017) | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Percent of people who believe the use of violence in support of a social or political cause is not justified | Planned | 88.85% | n/a |  |  | BV + 10%
|  | Achieved | Significant (p<.01) | n/a |  |  | BV + 5.76%
Source
End-line surveys from a representative sample of program participants and control communities.
| Impact Indicator 3 |  | Control (Mar 2017) | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Percent of youth confident in their future | Planned | 77.4% | n/a |  |  | BV + 10%
|  | Achieved | Not significant (p>.1) | n/a |  |  | BV +3.43%
Source
End-line surveys from a representative sample of program participants and control communities.
OUTCOME 1 | Outcome Indicator 1.0. |  | Control (Mar 2017) | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017) | Assumptions
Strengthened capacity of government, civil society organizations, security services and youth to prevent violence and resist the influence of Boko Haram. | Percent of community members who believe that the local government is able to effectively prevent violent extremism in their area. | Planned | 51.7% | n/a | BV + 5% | n/a | BV + 10% | 1. Increased capacity for social and civic engagement makes youth less susceptible to extremist and nationalist narratives. 2. Increased capacity of government and civil society institutions will translate into impact on target youth in a short-enough timeframe to be measured through this program. 3. Security conditions will remain stable enough to allow program activities to take place.
|  | Achieved |  | n/a |  |  | BV +7.2%
Source
Weighted average end-line surveys from a representative sample of program participants and control communities.
| Outcome Indicator 1.1. |  | Control (Mar 2017) | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Percent of community members who believe that the state government is able to effectively prevent violent extremism in their area. | Planned | 57.12% | n/a |  |  | BV + 10%
|  | Achieved |  | n/a |  |  | BV +5.99%
Source
Weighted average end-line surveys from a representative sample of program participants and control communities.
| Outcome Indicator 1.2. |  | Control (Mar 2017) | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Percent of community members who believe that religious leaders are able to effectively prevent violent extremism in their area. | Planned | 76.32% | n/a |  |  | BV + 10%
|  | Achieved |  | n/a |  |  | BV +4.05%
Source
Weighted average end-line surveys from a representative sample of program participants and control communities.
INPUTS (£) | CSSF (£) |  | Govt (£) | Other (£) | Total (£) |  | CSSF SHARE (%)
| 1692220 | [5 empty] | 100%
OUTPUT 1 | Output Indicator 1.0. |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017) | Assumptions
Strengthened civil society's capacity to collect, analyse, and disseminate data to track and promote public discourse on drivers of instability and potential threats to stability. | Number of reports developed on drivers of violence that include recommendations to shape public discourse on instability and violence | Planned | 0 | n/a | BV + 10% | n/a | 3 | 1. Community members are willing to conduct dialogues across lines of division, including former members of Boko Haram and the CJTF. 2. Government leaders at state and local level are willing to accept input from civil society into developing CVE plans.
|  | Achieved |  | n/a |  |  | 3
Source
Program files
| Output Indicator 1.1. |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Number of assessments conducted by CSOs and contributing practical solutions to resolving conflict issues | Planned | 0 | n/a | 1200 | 2000 | 2
|  | Achieved |  | n/a |  |  | 2
Source
Program files
| Output Indicator 1.2. |  | Control (Mar 2017) | Milestone 1 |  |  | Target (Mar 2017)
| Percent of community members who are willing to accept community members formerly associated with a violent extremist group. | Planned | 17.34% | n/a | 295 | 445 | BV +6%
|  | Achieved | Not significant (p>.1) | n/a |  |  | BV +0.48%
Source
End-line surveys from a representative sample of program participants and control communities.
INPUTS (£) | CSSF (£) |  | Govt (£) | Other (£) | Total (£) |  | CSSF SHARE (%)
| 266926.7 | [5 empty] | 100%
OUTPUT 2 | Output Indicator 2.0. |  | Control (Mar 2017) | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017) | Assumptions
Strengthened government and community initiatives that work together to reduce youth participation in violence. | Percent of people who report satisfaction with the Borno State government's efforts to prevent violence | Planned | 71.83% | n/a | BV + 10% | n/a | BV + 10% | 1. Governments will be willing and able to cooperate with communities, and will be able to do so in a short timeframe. 2. Small projects will have the ability to shift deeply held attitudes about government competency.
|  | Achieved | Significant (p<.01) | n/a |  |  | BV +9%
Source
End-line surveys from a representative sample of program participants and control communities.
| Output Indicator 2.1. |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Number of community-led CVE plans developed | Planned | 0 | n/a | 1410 | 1940 | 9
|  | Achieved |  | n/a |  |  | 9
Source
Program files
| Output Indicator 2.2. |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Number of joint community- and government-led projects implemented | Planned | 0 | n/a | 2980 | 5000 | 9
|  | Achieved |  | n/a |  |  | 6
Source
Program files
INPUTS (£) | CSSF (£) |  | Govt (£) | Other (£) | Total (£) |  | CSSF SHARE (%)
| 220985.03 | [5 empty] | 100%
OUTPUT 3 | Output Indicator 3.0 |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017) | Assumptions
Strengthened government efforts to support youth to engage in meaningful economic and social opportunities and reduce their vulnerability to Boko Haram's financial inducements. | Number of initiatives led by the government to support youth to engage in meaningful social and economic opportunities | Planned | n/a | n/a | BV + 5% | n/a | 5 | 1. If young people are active members of the community then they will be more respected by each other and community members 2. Market conditions will be favorable enough to accommodate new small businesses or employment (formal or informal)
|  | Achieved |  | n/a |  |  | 2
Source
Program files
| Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Number of participating youth who have access to economic opportunities, including self-employment. | Planned | 0 | n/a | 1400 | 2200 | 250
|  | Achieved |  | n/a |  |  | 288
Source
Program files
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Number of participating youth engaged in social activities | Planned | 0 | n/a | 1400 | 2200 | 2000
|  | Achieved |  | n/a |  |  | 2160
Source
Program files
INPUTS (£) | CSSF (£) |  | Govt (£) | Other (£) | Total (£) |  | CSSF SHARE (%)
| 181514.05 | [5 empty] | 100%
OUTPUT 4 | Output Indicator 4.0 |  | Control (Mar 2017) | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017) | Assumptions
Strengthened local alternative narratives to prevent participation and recruitment into extremist groups. | Percent of program participants who report that CVE messages they heard through media have reduced their support for violent activities | Planned | 77.09% | n/a | BV + 5% | n/a | BV +10% | 1. Local religious, community, and peer youth leaders feel safe enough to actively disseminate counter-narratives and positive messaging
|  | Achieved | Significant (p<.05) | n/a |  |  | BV +5.4%
Source
End-line surveys from a representative sample of program participants and control communities.
| Output Indicator 4.1 |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Number of media programs implemented to counter narratives towards preventing youth participation in extremist groups | Planned | 0 | n/a | 2980 | 5000 | 20
|  | Achieved |  | n/a |  |  | 115
Source
Program files
| Output Indicator 4.2 |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Number of parents who report an ability to identify signs of radicalization and protect youth from extremist recruitment | Planned | 0 | n/a | 2980 | 5000 | 150
|  | Achieved |  | n/a |  |  | 2172
Source
Program files
INPUTS (£) | CSSF (£) |  | Govt (£) | Other (£) | Total (£) |  | CSSF SHARE (%)
| 312795.55 | [5 empty] | 100%
OUTPUT 5 | Output Indicator 5.0. |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017) | Assumptions
Structured dialogue among key local stakeholders on violent extremism, and an alternative narrative, grounded in mainstream interpretations of Islam, and collectively developed by religious leaders from Borno State. | Number of formal dialogue sessions and informal consultations on violent extremism. | Planned | 0 | n/a |  |  | 50 | There is sufficient security in Maiduguri for stakeholders to engage in this dialogue, without facing undue risk.
|  |  |  | n/a |  |  | 288
Source
|  | Achieved |  | n/a |  |  | 50
Source
Program records (minutes and meeting attendance records)
| Output Indicator 5.1. |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Number of local religious leaders and other stakeholders who engage in discussing, drafting and validating an alternative narrative. | Planned | 0 | n/a | BV + 5% | n/a | 100
|  | Achieved |  | n/a |  |  | 128
Source
Program records (minutes and meeting attendance records)
| Output Indicator 5.2. |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| A first draft of an alternative narrative that encourages moderation and dialogue is produced by the Ulamas. | Planned | 0 | n/a | BV + 5% | n/a | 1
|  | Achieved |  | n/a |  |  | 1
Source
Program records and delieverables
INPUTS (£) | CSSF (£) |  | Govt (£) | Other (£) | Total (£) |  | CSSF SHARE (%)
116882.71
OUTPUT 6 | Output Indicator 6.0. |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017) | Assumptions
Enhanced societal participation in tension and conflict management in Southern Borno. | Number of community leaders from targeted LGA in Southern Borno involved in tension and dispute management. | Planned | 0 | n/a |  |  | 80 | 1. Leaders of communities from the targeted LGA in Southern Borno are willing to dialogue, to develop a shared understanding of grievances on either side, and to resolve them collaboratively. 2. Communities are able to mobilise and local stakeholders are not reluctant to engagement of women and youth in tension and dispute management.
|  | Achieved |  | n/a |  |  | 70
Source
Program records (meeting attendance records); conflict analysis from HD and other organisations/researchers; informal interviews with local stakeholders; feedback from communities.
| Output Indicator 6.1. |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Number of informal consultative sessions with key stakeholders from the targeted LGA. | Planned | 0 | n/a | BV + 5% | n/a | 20
|  | Achieved |  | n/a |  |  | 20
Source
Program records (minutes and meeting attendance records)
| Output Indicator 6.2. |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Number of preliminary intra-faith dialogue sessions facilitated by HD with leaders of communities from the targeted LGA. | Planned | 0 | n/a | BV + 5% | n/a | 10
|  | Achieved |  | n/a |  |  | 10
Source
Program records (minutes and meeting attendance records)
INPUTS (£) | CSSF (£) |  | Govt (£) | Other (£) | Total (£) |  | CSSF SHARE (%)
128117.06
OUTPUT 7 | Output Indicator 7.0. |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017) | Assumptions
Nigerian security stakeholders in Borno state have increased understanding and commitment to gender sensitive civilian protection and harm mitigation principles, practices, and tools to improve ongoing counter-insurgency and stabilization operations. | Number of security personnel participating in assessments, training and dialogue on security and physical protection challenges, disaggregated by gender. | Planned | 0 | n/a | BV + 5% | n/a | 15 women, 85 men | 1. CIVIC will have the entry points and relationships to enable military personnel to talk freely with the assessment team. 2. Security agencies see the importance of trying to strengthen their work on civilian protection and are open to engagement. 3. CIVIC gets the engagement and buy-in of field commanders to release security personnel for training
|  | Achieved |  | n/a |  |  | 23 women, 129 men
Source
Lists of participants and interviewees engaged with during the project
| Output Indicator 7.1. |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Number of security personnel in three different locations who have strengthened understanding of civilian protection and harm mitigation. | Planned | 0 | n/a | BV + 5% | n/a | 15 women, 85 men
|  | Achieved |  | n/a |  |  | 6 women, 210 men
Source
Participant lists
| Output Indicator 7.2. |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Number of roundtables held with members of non-military security agencies to increase their knowledge of civilian protection | Planned | 0 | n/a | BV + 5% | n/a | 2
|  | Achieved |  | n/a |  |  | 2
Source
Program records (minutes and meeting attendance records)
INPUTS (£) | CSSF (£) |  | Govt (£) | Other (£) | Total (£) |  | CSSF SHARE (%)
| 121655 | [5 empty] | 100%
OUTPUT 8 | Output Indicator 8.0. |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017) | Assumptions
Affected communities and civil society groups in Borno, including women’s organizations, have increased knowledge of community protection strategies and roles and responsibilities for security force personnel and trust and confidence between communities and security forces is built . | Number of members of communities, civil society groups and security force personnel that engage in dialogue | Planned | 0 | n/a | BV + 5% | n/a | 100 women, 75 men | 1. Security forces are open and non defensive in discussions. 2. Community members are able to share their concerns open and honestly without fear of backlash. 3. There is sufficient security in Maiduguri for stakeholders to engage in this dialogue, without facing undue risk.
|  | Achieved |  | n/a |  |  | 77 women, 111 men
Source
Lists of participants and interviewees engaged with during the project
| Output Indicator 8.1. |  | Baseline | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Number of civilian-military dialogues to discuss security concerns and security force behaviour | Planned | 0 | n/a | BV + 5% | n/a | 3
|  | Achieved |  | n/a |  |  | 3
Source
Participant lists
INPUTS (£) | CSSF (£) |  | Govt (£) | Other (£) | Total (£) |  | CSSF SHARE (%)
| 78344.63 | [5 empty] | 100%
OUTPUT 9 | Output Indicator 9.0. |  | Baseline (Sept 2016) | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017) | Assumptions
Kanuri-speaking communities are better informed, more empowered and have a platform for expression. | Majority of target population have access to Kanuri language radio programming designed to give them better news and information about the region. | Planned |  | n/a | BV + 5% | n/a | 80% | 1. DKRI has the resources to remain on air and to support CVE activities. 2. The AU, LCBC and national government are committed to fighting Boko Haram 3. National governments are committed to stabilizing the LCB region.
|  | Achieved |  |  |  |  | 80%
Source
Listener surveys & broadcast footprint
| Output Indicator 9.1. |  | Baseline (Sept 2016) | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Majority of target population have access to Kanuri language CVE programming. | Planned |  | n/a | BV + 5% | n/a | 80%
|  | Achieved |  |  |  |  | 80%
Source
Listener surveys & broadcast footprint
| Output Indicator 9.2. |  | Baseline (Sept 2016) | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017)
| Majority of community members have access to Kanuri language programming designed to encourage a sense of belonging to the Kanuri community. | Planned |  | n/a | BV + 5% | n/a | 80%
|  | Achieved |  |  |  |  | 80%
Source
Listener surveys & broadcast footprint
INPUTS (£) | CSSF (£) |  | Govt (£) | Other (£) | Total (£) |  | CSSF SHARE (%)
| 26000 | [5 empty] | 100%
OUTPUT 10 | Output Indicator 10.0. |  | Baseline (Dec 2016) | Milestone 1 | Milestone 2 (March 2018) | Milestone 3 (March 2017 | Target (Mar 2017) | Assumptions
Full service SW and FM radio constructed. | Construction of FM mast, and installation of FM dipoles & transmitter. Number of reports and stories sent to the newsroom for broadcasting | Planned |  | n/a | BV + 5% | n/a | 23 news items &reports a day
|  | Achieved |  | n/a |  |  | 23 news items & reports a day
Source
|  |  | Program records (minutes; progress and interim reports, deliverables) |  |  |  |  | RISK RATING
INPUTS (£) | CSSF (£) |  | Govt (£) | Other (£) | Total (£) |  | CSSF SHARE (%)
| 239000 | [5 empty] | 100%

## Definitions for LogFrame
Impact Indicator 1
"extremist violence"
"capacity"
"quality report" | reports from each dialgoue, must include policy recommends.
"to accept" (Output 1.3)

## Smart Guide
Smart Guide
Teams should use the guide below to complete the results framework template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined e.g. DRF, OP, ICF KPIs, MDG indicators
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the results framework are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.

## Calculations
Linked to RF sheet
Event | Date | Linked
Baseline | August 2016 | Baseline (August 2016)
Milestone 1 | March 2017 | Milestone 1 (March 2017)
Milestone 2 | March 2018 | Milestone 2 (March 2018)
Milestone 3 | March 2019 | Milestone 3 (March 2019)
Target | June 2020 | Target (June 2020)