DFID NIGERIA
CONFLICT MANAGEMENT IN NORTHEAST NIGERIA

Organization name
Mercy Corps Nigeria as lead consortium member with Centre for Civilians in Conflict (CIVIC), Centre for Humanitarian Dialogue (HD) and Okapi Consulting.
Organization primary contacts
Liza Baran – Director of Conflict Management Programmes lbaran@mercycorps.org / Lisa Seymour-Doughty – Senior Programmes Officer / ldoughty@mercycorps.org
Project title
North East Conflict Management and Stabilisation Programme
Project summary
This programme is an expansion from a pilot phase implemented from August 2016 to March 2017. The programme will result in increased peace within and between communities, and increased confidence in government and security institutions to address the root causes of conflict and violent extremism in Borno State. The consortium will strengthen protection of civilians, support social cohesion, address the root causes of violent extremism and contribute to conflict management in Northeast Nigeria by: a) strengthening government and civil-society efforts to address key grievances; b) increasing economic and social engagement opportunities for youth; c) promoting reconciliation and transitional justice at a community level; d) supporting civilian protection and improving civil-military relations; e) laying the groundwork for successful reintegration of former members of violent groups, their victims and IDPs; and f) promoting positive alternative narratives through radio.
Project start / end date
1st June 2017 – 31st March 2019
Total budget
£5,4 million
Geographic area of implementation
The programme will work in thirty communities in Borno State. The consortium will continue to work with the nine communities identified in the NE CMS pilot programme (Aburi, Budum, Bulabulin Ngainaw, Damboa Central, Gwozari, Mala Kyariri, State Low Cost, Wulari and Zannari), and will add a further eleven communities in year one and ten communities in year two. In the NE CMS pilot, the consortium worked in the following LGAs: Biu, Damboa, Dikwa, Maiduguri, Mubi. New communities will be selected by consortium partners based on a set of criteria determined at the beginning of the project that considers the dynamic environment of the North East. Dandal Kura radio will reach a wide population across the entire Northeast of Nigeria via radio broadcast.
Context
1. What is your assessment of the situation in the Northeast and how it is likely to develop over the funding period?
Background and Context Boko Haram, which splintered into two distinct groups in August 2016, Jama’atu Ahlis Sunnah Lida’awati wal Jihad (JAS) and Islamic State West Africa (ISWA), grew increasingly active and deadly in its attacks against state and civilian targets in recent years, drawing on a narrative of victimisation and vengeance for state abuses to elicit recruits and sympathizers. Operations by regional forces, most notably those from Chad and Nigeria, reversed the territorial advances that Boko Haram made from mid-2014 into early 2015, when it took nominal control of large swathes of territory in Northeast Nigeria under a self-described Islamic caliphate. The group has since reverted to asymmetric attacks, largely against soft targets in Northeast Nigeria and northern Cameroon. Today, Northeast Nigeria remains a conflict-affected, fragile area, where the civilian population is vulnerable to continued security, economic, political, societal and environmental risks. The violence has caused a humanitarian emergency, displacing more than 2.2 million people and cutting off humanitarian access to roughly three million others. Boko Haram attacks have damaged health centres, markets, roads, homes, and schools, deterring the return of the displaced. Civilians continue to face grave human rights violations and abuses primarily by these groups, but also by Nigerian security forces and vigilantes. These include death, injuries, sexual and gender-based violence, arbitrary detention, disappearances, forced displacement, attacks on civilian sites and forced recruitment.[1] The fighting and abuses of Boko Haram have traumatized significant portions of the population. / Security forces have caused direct and indirect harm during operations against Boko Haram and by a failure to protect civilians from Boko Haram’s attacks. The government is not able to meet the needs of the population and is largely seen as absent from the community life. This can fuel frustrations and mistrust in the ability of the government to improve the situation and provide protection to the communities. CIVIC research found that although most civilians felt Boko Haram had perpetrated the majority of harm to them and their families, the military had also caused harm through failure to protect communities from violence and prevent collateral damage during operations. Meanwhile, in some areas of Borno State, particularly in communities of mixed faiths, the insurgency has damaged social cohesion. Mistrust, tensions and competition over resources, including the delivery of aid and the reconstruction of places of worship, are likely to complicate reintegration and reconciliation efforts. These challenges will compound as communities undergo repeated displacement or are confronted with the prospect of voluntary, and involuntary returns of IDPs to their home areas. / Ensuring peace and security in the Northeast of Nigeria will be very difficult without a clear vision for post-Boko Haram life and a concerted effort to build peace and tackle grievances. President Muhammadu Buhari announced that Boko Haram had been “technically defeated” on December 24, 2015, and in support of this military success, the Nigerian government has developed a rehabilitation and reintegration programme for Boko Haram defectors. However, attacks continue and the current operations and success of the programme is uncertain. Governance Grievances The baseline survey conducted by Mercy Corps within the North East Conflict Management and Stabilisation Programme pilot suggests that a majority of the population is dissatisfied with the ability of the local government to provide basic services. Mercy Corps Nigeria’s (MCN) research on Boko Haram’s recruitment tactics revealed that frustration over poor governance, high corruption and failure to provide security created space for Boko Haram’s message to take root in communities.[2] Boko Haram successfully recruited youth and exploited grievances and frustrations over inequality by providing opportunities for youth to achieve their economic ambitions. The Centre for Humanitarian Dialogue’s preliminary dialogue sessions with Gwoza LGA leaders from the Muslim and Christian faiths further revealed that entrenched practices of resource allocation have complicated relationships and perceptions at the community level. Local stakeholders have cited religious intolerance and domination, politicisation and radicalisation of religion, tribal ‘protectionism’, political exclusion, impunity and lack of access to land and economic opportunities as some of the major sources of tension and potential conflict. There is deep dissatisfaction among those who feel under-represented politically and marginalised economically. / Community members in Northeast Nigeria reported during dialogue sessions with CIVIC that they have low trust in the ability of the local government to prevent further violence. They also don’t trust the ability of the Nigerian security forces to provide protection. At the same time, most communities trust the ability of the vigilante group Civilian Joint Task Force (CJTF) to provide security but see their actions as promoting further violence. Meanwhile, community systems of leadership have also lost legitimacy and are increasingly perceived to be corrupt, with community leaders seen as benefitting economically from the conflict and diverting resources in many locations. / Preliminary findings of Civilians In Conflits’ gendered analysis of civil-military relations suggest low levels of trust between civilians and security forces. In many cases, interviewees informed them of the military not acting to protect communities from attacks even when asked to do so or leaving communities when attacks seemed imminent: “They were running away even ahead of us,” said one respondent to a Civilians In Conflict (CIVIC) study. High levels of sexual exploitation and abuse in International Displaced People (IDP) camps and Local Government Administrations (LGAs) and the diversion of food and non-food items in IDP camps by soldiers has further damaged trust. / To address these and broader challenges fuelling grievances that have the potential to radicalise various segments of the society, the Office of National Security Adviser is currently working on a Countering Violent Extremism (CVE) strategy and a national plan which are part of a broader National Counter-Terrorism Strategy. The CVE strategy will inform policies to be developed at the state and community levels to prevent violent extremism. The State government of Borno, one of the most affected states, has prioritised this task. However, state government officials who participated in a CVE planning workshop facilitated by Mercy Corps confessed that even though they understand the necessity of a CVE framework and a supporting implementation plan, they lack skills in developing policies. “We know this is an important assignment, but we don’t know where to start,” said one of the participants of the workshop. / There is political will at all levels of political and military leadership to prioritise civilian protection in security force operations. In November 2016, at an event co-organized by CIVIC, the Chief of Defence Staff promised to develop and implement a policy on civilian protection and harm mitigation. Defence Headquarters asked CIVIC for assistance in developing a draft (currently pending final approval) and to integrate civilian protection into trainings targeted at soldiers and officers. / Lack of Economic and Social Opportunities for Youth / Mercy Corps’ study Motivations and Empty Promises: Voices of Former Boko Haram Combatants and Nigerian Youth found that many youth see Boko Haram as an opportunity to get ahead, hanging their futures on the promise of business support. A follow-on research study, Gifts and Graft: How Boko Haram Uses Financial Services for Recruitment and Support, revealed that many respondents who accepted financial support and cooperated with Boko Haram’s demands did so under a protection scheme. Many recruited youth saw Boko Haram’s financial services as more accessible than existing alternatives.[3] / Borno State is among the worst performing states in the nation on a variety of education indicators that reflect a broader political, economic, and social crisis. For youth across the State, economic opportunity is scarce. A labour market assessment conducted by Mercy Corps in January and February 2017 found that most businesses hire workers based on familial, religious, or ethnic affiliations and gender rather than merit indicators including education and previous relevant work experience. Many youth see informal business as the only way to achieve their ambitions. In the midst of conflict, the few opportunities that youth had have dwindled further. Boko Haram specifically targets schools for destruction and utilizes youth in their operations, and the insurgency severely damaged the Borno economy, destroying or driving away the scant services the state provided and forcing many traders to flee. / Further research conducted by Mercy Corps suggested that strong family influence, particularly that of parents, prevented youth who had an opportunity to join Boko Haram from doing so.[4] The same research provided evidence that peer influence plays a role when youth make decisions whether to join violent groups. Youth cited external connections – perhaps through trading with outside communities, by having close friends or relatives outside of their immediate communities, or through school or religious groups – as a common thread in their stories of resistance. In addition to providing them an additional source of protection, these outside connections are a channel through which youth can broaden their perspectives and potentially resist tacit or explicit messages reverberating in their communities. / Finally, youth often feel disengaged from the decisions made in their communities. This limits their ability to make purposeful contributions in communal life and practice critical leadership and interpersonal skills with a wider range of community members. / Preparing for the Re-integration of Former Fighters, Their Victims and Displaced Populations One of the main pre-conditions for stabilizing the Northeast is a clear strategy to reintegrate former fighters. The government has reportedly sought to address this issue by establishing the “Safe Corridor” programme focusing on the rehabilitation and reintegration of repentant and surrendering Boko Haram members into society. Repentant former members are reputedly sent to a camp where they undergo a de-radicalisation process. However, a number of surveys, including Mercy Corps’ NE CMS pilot baseline, confirm that the vast majority of community members are not prepared to accept former fighters back into their communities. The main reason cited is mistrust in the ability of the government to change the views of former extremists. It is hard for communities to distinguish those who chose to join Boko Haram from those forcibly recruited; therefore, communities often reject acceptance of any person associated with Boko Haram (whether voluntary or involuntary) to ensure their safety. This particularly affects women and children linked with Boko Haram, who are stigmatized and rejected by communities based on the prejudice that they were brainwashed and can never change.[5] Furthermore, in consultations with Centre for Humanitarian Dialogue (HD) and CIVIC, youth and CJTF leaders from Maiduguri have voiced strong opposition to the rehabilitation and reintegration of former Boko Haram combatants. In their view, resources should be directed towards those who have borne the brunt of the conflict, as opposed to those who perpetrated violence. / The NE CMS pilot programme revealed another issue – that of a growing number of abuses by the CJTF, an organization of primarily young men, but also which recruits and uses children. The CJTF leadership has expressed concerns to CIVIC that leaders are struggling to keep control of members who engage in abuses and violations of international human rights and humanitarian law, and that they do not know how to act in a way that prioritizes civilian protection. The CJTF is one of a number of vigilante groups and the extent of human rights abuses committed by others is unknown. There is a high likelihood of members of the CJTF and other vigilante groups being involved in or setting up groups that are oppositional to the state and/or perpetrate violence in communities. Communities, including members of civil society, are also concerned about the future of the CJTF and other vigilante groups. A common foreseen conflict scenario is that, even if the government manages to defeat the insurgency, lack of foresight, planning and action could lead to vigilante groups (including the CJTF) splintering and forming opposing factions, some of which include Boko Haram members, that are armed, know how to fight and are linked to different political interests in the State. / In the near future, some Internally Displaced People (IDP) will return to their home LGAs, whether voluntarily or forced to do so by the government, or as a result of sending people back from Cameroon. Furthermore, hundreds of people continue to come into LGA headquarters from surrounding villages – for example, in a five-day period in late April, almost 1,000 people came into Dikwa from rural areas for safety. The Governor of Borno had stated publicly that all IDP camps in Maiduguri would be closed by May 2017 before reversing this policy. Many IDPs are concerned about their physical safety and security upon return and worry about further attacks, especially given the previous inability of the Nigerian state to protect them. There are perceptions held by IDPs that those who stayed behind are sympathizers of Boko Haram, another issue that threatens tension around the reintegration of IDPs as they return home. When the displaced do re-settle and restart their lives, these new disputes are likely to compound old tensions over access to land, political appointments and chieftaincy titles, the dispensation of justice, the restoration of property, places of worship, and markets and demands for compensation.
2. Problem statement. What is the problem that you will address? What will be your strategy to address this problem?
Problem: Grievances against government authorities and unequal economic opportunities leave members of communities, and youth in particular, vulnerable to recruitment and radicalisation by violent extremist groups. Research shows that in fragile conflict and post-conflict contexts, international assistance tends to focus on ‘fighting fires’ rather than investing in conflict prevention and addressing the underlying drivers of instability. In addition to emergency assistance to meet life-saving needs, the response mounted by local, national and international actors must also invest in building long-term stability. Aid should help re-establish and strengthen dispute and conflict management structures where they have been eroded, build trust in governance and security institutions by strengthening relationships as well as increasing institutional will and capacity to ensure protection and services, support processes of trust-building and reconciliation to heal social cleavages which may otherwise perpetuate conflict, enable communities to collectively agree on how best to rebuild their lives, and provide support that counters the appeals of extremist groups. / Goal: The programme will support divided communities to come together, strengthen protection of civilians, support social cohesion, start to address some of the root causes of violent extremism and contribute to conflict management in Northeast Nigeria by: a) strengthening government and civil-society efforts to address key grievances; b) increasing economic and social engagement opportunities for youth; c) promoting reconciliation and transitional justice at a community level; d) supporting civilian protection and improving civil-military relations; and e) laying the groundwork for successful reintegration of former members of violent groups, their victims and IDPs; and f) promoting positive alternative narratives through radio. / As is illustrated in the below diagram (and see as Annex 1.), the NE CMS’s Theory of Change posits that if communities and local institutions collaborate to address their basic needs (including protection), youth have increased civic and economic opportunities, and communities develop the tools, skills and support they need to peacefully resolve disputes and address underlying drivers of conflict, then communal grievances and violence will be reduced, and intra- and inter-communal cohesion will increase. / Theory of Change for North East Conflict Management and Stabilisation Programme / Strategy: The programme will be implemented by four consortium members: Mercy Corps, as the lead, in partnership with the Centre for Civilians in Conflict (CIVIC), the Centre for Humanitarian Dialogue (HD) and Okapi Consulting. The consortium members will work with a broad range of actors and institutions in Borno State on a range of multi-tiered interventions that correspond to the mandates and expertize of each consortium member, and to the added value that each member brings to the project. / In the mid to long-term, the security and prosperity of Borno State depends on the ability of communities and authorities to manage tensions over resources and religious dominance. The consortium’s proposed activities in the Northeast of Nigeria are consistent with the increased focus on conflict prevention articulated in the UK government’s Building Stability Overseas Strategy (BSOS). The activities outlined below are an investment in: a) early warning (improving the ability of local stakeholders to anticipate potential triggers of violence); b) crisis prevention and response (improving the ability of local stakeholders to take appropriate and effective action to prevent a crisis or stop it from spreading or escalating); and c) upstream prevention (helping to establish platforms and mechanisms that are capable of managing tensions and shocks in fragile societies). / This consortium’s competitive advantage lies in the breadth of its programming and strong relationships with a variety of actors due to its history of working in the State to address the underlying factors that have contributed to instability in the Northeast while laying the groundwork for a more peaceful future. The programme will build upon the strengths of individual consortium partners to promote dialogue between civilian, military and state actors to address key grievances and improve civil-military relations, support youth populations most susceptible to messaging by extremist groups, and promoting reconciliation and transitional justice at the community-level that supports the reintegration of former members of violent groups, their victims and IDPs. / While different consortium members will lead different activities within the programme’s three objectives, the programme has been structured to take advantage of synergies between activities to strengthen and scale interventions. The consortium is the only grouping of actors that focuses on communication, dialogue and reconciliation between civilians and the military, civilians and government, and different actors involved in the conflict in the Northeast at all levels, from the community to State government. Consortium partners have already established strong relationships with stakeholders in the Northeast, and will build upon established trust to begin implementation of activities immediately. Additionally, the programme contains strong community and youth mobilisation mechanisms to address the underlying causes of the conflict. / The consortium consists of learning organizations with experience in Northeast Nigeria and similar contexts, allowing each organization and the consortium to leverage lessons learned and best practices from past experiences. There is an existing practice of sharing information and analysis, and offering advice and support, between the consortium members. Consortium partners will continue to place a strong emphasis on evidence generation and programme learning, including gathering real-time evidence on effectiveness that can generate recommendations on how to strategically scale-up interventions. The consortium will take the lead in coordinating local CSOs, INGOs, and donors in the Northeast working on conflict management and peacebuilding in line with the Peace and Security Working Group mandate, a national network of organizations engaged in peacebuilding across Nigeria. Currently, the sub-group operating in the Northeast is dormant and, when operational, was Abuja-based. By re-engaging CSOs, INGOs, and donors in the Northeast and bringing together actors in Maiduguri itself, the consortium will ensure greater coordination of interventions, programming and funding based on better conflict analysis conducted at the LGA level and promote closer interaction between international and civil society organizations. This will include promoting two-way capacity-strengthening with local CSOs, CBOs, and INGOs, improving the capacity of each to expand the range of potential partnerships. / Finally, this consortium of organizations is able to cover all of the areas that CSSF supports, preventing further conflict and instability and supporting post-conflict stabilisation. The consortium partners each come with the following, complementary, areas of strength and expertise: / Mercy Corps: Mercy Corps’ interventions within the consortium are built upon strong evidence collected in Phase 1. It is able to leverage its humanitarian programming in Borno State to build trust in communities and has a strong community mobilisation methodology for youth, traditional leadership, local officials, and other stakeholders. Mercy Corps’ strengths rest in its different areas of technical expertise, including governance, youth, and livelihoods. Mercy Corps will address some of the “push” and “pull” factors that drive participation in violence, including governance grievances, unequal economic opportunity, and vulnerability to extremist messaging. / HD: The Centre for Humanitarian Dialogue focuses on dialogue, mediation and reconciliation and is one of the few organisations with this mandate and expertise in the Northeast. HD has built robust relationships with local and regional, traditional, and religious leadership, from the Shehu of Borno, to the Emir of Gwoza, and the Chief Imam, promoting tension-management, reconciliation and peaceful reintegration. / CIVIC: The Centre for Civilians in Conflict focuses on concrete ways to ensure civilian protection is prioritised in all stages of security force operations and steps are taken to mitigate civilian harm through training, workshops, and policy work. CIVIC builds the resilience of communities to physical threats and the communities’ confidence to engage with security forces. Finally, it brings together security forces and communities in dialogue to share concerns and challenges (including issues with security force behaviour), engage in joint problem solving, build trust, and promote civilian protection. / Okapi Consulting: Okapi Consulting supports Dandal Kura Radio International (DKRI), the only Kanuri-language radio station in the Lake Chad basin. DKRI has the opportunity to reach the entire population of Borno state and the Lake Chad basin region with alternative narratives to extremist groups and promote transparency between government, the security forces, and communities.
3. What is the proposed form of assistance?
The programme will help reduce violence in Northeast Nigeria by helping government and communities to address some of the root causes of violent extremism. The programme will produce three primary outputs considered to be critical for prevention of participation in violence in northeast Nigeria. These outputs were identified through research, stakeholder and partner analysis and partners’ results conducted under the NE CMS initiative: / Strengthened capacity for communities to engage government and security forces leading to increased trust in the ability of Borno State and local governments to address community needs (including provision of basic services and security). / Reducing youth participation in violence due to active engagement in communal and economic activities. / Increased capacity of communities to collaborate across lines of division to prevent violence and promote peaceful integration.
4. What is your current presence in the country and in the area of intervention? What relevant activities are you currently implementing? What is your current staffing set-up ad how will this change to implement this project?
As some of the first INGOs on the ground in Borno working on conflict management and peacebuilding, Mercy Corps Nigeria, CIVIC, HD, and Okapi Consulting are uniquely positioned to implement the activities outlined in this proposal. All consortium partners worked together through the NE CMS pilot, conducting activities in various LGAs in Borno State (including Dikwa, Gwoza, MMC, and Mubi) and broadcasting across the Northeast. / Building on the government and community relationships established through Mercy Corps Nigeria’s humanitarian programmes in Borno and furthered during the NE CMS pilot programme, MCN is well connected to the key stakeholders outlined in this proposal. Since 2012, MCN has been working across the country to prevent conflict, provide humanitarian relief, improve educational and economic opportunities for adolescent girls and youth, and increase access to finance for the most vulnerable. With an annual budget of £22,000,000, MCN works in 13 states and receives funding from DfID, USAID, OFDA, the European Union, the European Commission, and the MacArthur, Coca-Cola Africa, GHR, and MasterCard Foundations. MCN recently published research studies on the recruitment practices of Boko Haram and drivers of youth participation in extremist groups. Lastly, MCN has researched the role of religious and traditional leaders in conflict and peacebuilding. MCN utilizes this research in the implementation of its programming. The NE CMS pilot programme was implemented by a team of six national staff and an expatriate Programme Manager, all based in Maiduguri. The Director for Conflict Management Programmes, based in Abuja, provided technical oversight and managed donor relationships on behalf of the consortium. To ensure high quality programme delivery, Mercy Corps will expand the staffing structure to engage more local experts to oversee key components of the project, including an M&E manager and a Communications and Reporting officer based in Abuja. MCN also has administrative, operations, and programme teams already based in Borno State. A steering committee comprised of representatives of all consortium partners will be formed to engage in decision-making and coordination throughout the course of the programme. Please consult Appendix A for detailed description of the consortium management structure. / The Centre for Humanitarian Dialogue has been active in Nigeria since the beginning of 2013 and has successfully facilitated inter-communal dialogue processes between communities in Plateau and Kaduna States, enabling them to address longstanding disputes and build capacities for managing emerging tensions. The impact from the dialogue process in Plateau State is demonstrated by improved relationships and a reduction in open hostilities between local communities. The communities have played an important role in intervening during periods of violence and attacks, and tensions have significantly reduced as a result. There has also been a marked improvement in the relationship between the communities and the Plateau State Government, leading to improved government responses to attacks. In the NE of Nigeria, HD has developed a robust network of contacts over the past two years, including religious, traditional and community leaders from Borno State. During the NE CMS pilot, HD relied on a team that consisted of a Senior Programme Manager, a Project Officer, two Senior Facilitators, three Local Advisors, and one Administrative and Logistics Assistant. In its dialogue projects, HD applies a ‘hybrid’ approach which seeks to maximise the combined skills and attributes of ‘insider’ and ‘outsider’ practitioners. Therefore, HD’s team in the Northeast was set up to combine local knowledge, convening power, project management and mediation expertise. HD will use a similar staffing structure for NE NCS 2, boosting capacity for programme delivery with support from a Finance Manager, a Project Assistant and potentially a Gender and Inclusion adviser. Strategic oversight is provided by Senior Management in CIVIC’s Africa regional office based in Nairobi, and additional technical and thematic support is provided upon request by HD’s Mediation Support and Policy team and the M&E team. / CIVIC is the leading global advocate for the protection of civilians in conflict. CIVIC documents harm to civilians and analyzes its causes while providing governments, armed forces, and international institutions practical solutions for tracking, preventing, and responding to civilian harm. CIVIC offers technical assistance by training and networking civil society and local communities to advocate for support for self-protection and to ensure accountability when harm occurs. Through a working partnership with the Nigerian Defence Headquarters, CIVIC is assisting the Government of Nigeria to incorporate protection of civilians in policy, doctrine, and practice for military and security forces throughout the country. With DFID’s support in 2016, CIVIC engaged with the Lafiya Dole operation in Borno State against Boko Haram to improve civilian protection training and empowered local civilians to engage local forces and demand better protection. CIVIC has offices in Abuja and Maiduguri, staffed by experts in military engagement and training, civilian engagement, and civil society advocacy. CIVIC’s Maiduguri staff were funded under the NE CMS pilot and its staffing configuration will not change under NE NCS 2. / Okapi Consulting has been active in Nigeria since 2015 and is one of the most experienced organisations in the establishment and management of large media projects in fragile and conflict environments. Okapi trains journalists and other programme-makers and works with local partners to create broadcast and media projects which feed people’s need for reliable news, information and entertainment. Okapi also provides people an opportunity to voice their hopes, fears, and ideas. Okapi established Dandal Kura Radio International (DKRI) to help counter the Boko Haram narrative with the support of DfID and OTI, first in Kano and then in Maiduguri. By giving people across the region a voice, and encouraging women and men to speak out, Okapi is giving Kanuri-speaking people the opportunity to create a true, uniting Kanuri narrative which counters the divisive and violent narrative of Boko Haram. Okapi is based in South Africa and its Nigeria operations are centred in Maiduguri, where 88 people are employed by DKRI as journalist, producers, presenters, technicians, and management. Different Okapi staff members have worked on media projects in Nigeria since 2012 and similar projects in DR Congo (Radio Okapi), Central African Republic (Radio Ndkea Luka), Somalia (Radio Bar Kulan), and Burundi (Radio Iiambo).
[1] Nigeria Humanitarian Response Plan for January-December 2017, UNOCHA, 2016
[2] “Motivations and Empty Promises;” Voices of Former Boko Haram Combatants and Nigerian Youth, Mercy Corps, 2016
[3] “Gifts and Graft. How Boko Haram Uses Financial Services for Recruitment and Support”, Mercy Corps, September 2016
[4] “Motivations and Empty Promises. Voices of Former Boko Haram Combatants and Nigerian Youth”, Mercy Corps, April 2016
[5] ‘Bad Blood’: Perceptions of Children Born of Conflict-Related Sexual Violence and Women and Girls Associated with Boko Haram in Northeast Nigeria, International Alert/ UNICEF, 2016; Perceptions and Experiences of Children Associated with Armed Groups in North East Nigeria, NSRP/ UNICEF, 2017.

Project outline, approach and implementation
5. What activities will be undertaken? Please refer to the areas under “what are we looking for?” in the call for proposals.
Output 1: Strengthened capacity for communities to engage government and security forces, and increased trust in the ability of Borno State and local governments to address community needs (including provision of basic services and security). / Activity 1.1: Increase Borno State Government capacity to engage communities and develops a CVE framework through a participatory process. Led by Mercy Corps with technical support from CIVIC, HD, Okapi, and DFID Partnership to Engage, Reform and Learn (PERL). To address a lack of formalized CVE strategy in Borno State, Mercy Corps will build the capacity of state government officials to develop CVE policies through a participatory and consultative process, and facilitate the application of acquired skills to develop a CVE framework for Borno State. This work will be done in close coordination with ONSA to ensure alignment with the national CVE framework. Government officials will be trained on policy analysis, stakeholder dialogue, drafting of policies and implementation plans, and budgeting (with support from PERL). To support the sectoral parts of the CVE framework, NE NCS 2 and local partners, in close cooperation with local government officials, will organise dialogue sessions to receive input from the communities that will inform the State CVE framework. Building on the alternative narrative produced by local Ulamas in the the NE CMS pilot programme, HD will provide discreet technical support to Mercy Corps, as the latter engages with government authorities on the Borno State CVE framework. Okapi will support this process through regular coverage in Dandal Kura Radio International (DKRI) news segments and related programmes. / Activity 1.2: Mobilise communities within target LGAs to create and implement CVE action plans and influence local budget processes. Led by Mercy Corps with support from CIVIC and engaging other partners PERL, HERWA and others, to be determined). Mercy Corps will incorporate a representational cross-section of community leaders with influence in the selected communities into CVE committees to develop community CVE action plans. These plans, supported through training in advocacy, will influence the LGAs to address community-identified priorities in the State budget. To ensure the success of this approach, PERL will lead training modules in the budgeting process for select members of each community CVE committee and LGA officials in each LGA, beginning with three LGAs previously engaged in NE CMS. Communities will advocate for the allocation of funds to meet identified needs in the local budgets, and LGA officials will learn how to build participatory budget processes for requests from the State. Recognising that the development of community CVE action plans and subsequent budget support may take time and faces risks (including a potential lack of political will, limited capacity of civil servants, and limited functioning of Borno State LGAs), at the early stage of the programme NE NCS 2 will work with partners, such as GIZ, and the Ministry of Reconstruction, Rehabilitation and Resettlement to provide support to implement jointly-identified projects. This will help meet the immediate needs of the communities, will add to rebuilding trust in the ability of the local government to provide basic services, and will ensure sustainability of the project while building community members’ skills to influence government decisions and hold their government officials accountable. Finally, it will be essential to plan activities around the protection of civilians. CIVIC will provide technical support to Mercy Corps and CVE committees to develop self-protection plans and communication modalities to security forces. / Activity 1.3: Engage local partners and communities in recruiting youth to lead community development projects. Led by Mercy Corps. To connect civic engagement to community CVE action plans and to build social cohesion, CVE committees will mobilize community youth into groups of not more than 30 individuals to implement joint development projects resulting from the CVE action plans. Community youth will discuss reasons for youth participation in violence and ways to improve the lives of communities before designing and implementing projects to address the identified issues. Such projects may include advocating to public officials to fix street lighting for increased safety, renovating schools or market stalls, planting gardens, painting murals with the support of local artists, holding community soccer matches, and/or organizing cultural events that features the diversity of traditions of the participants. Youth leaders will be encouraged to work with peers to identify projects that build social cohesion, mitigate host-community tensions, and pave the way for wider youth participation in community development. Each community will develop a minimum of two projects. Mercy Corps’ experience in other conflict-affected environments, including in Guatemala and Syria, found that youth are more likely to acquire project management and implementation skills after two cycles of project implementation. These community development projects will provide youth the opportunity to practice their leadership skills, actively participate in community dialogue, and mobilize their peers around community service and peaceful coexistence. / Activity 1.4: Increase trust between communities and security forces. Led by CIVIC, building on Activity 1.2., led by Mercy Corps. Military action and inaction has caused significant levels of civilian harm and contributed to mistrust of security forces by communities. CIVIC will conduct workshops and training sessions to build security force capacity to better protect civilians from harm. CIVIC will also coordinate efforts to build communities’ trust and confidence in the government’s capacity to provide security by systematising and institutionalising dialogues and mechanisms of communication and response between civilians and security actors. The purpose of these activities will be to ensure security forces prioritize civilian protection, and are seen to do so, and are accessible and responsive to all (women and men) in communities. / Activity 1.5: Transparently disseminate information around government security and service measures to communities in Borno State. Led by Okapi Consulting. Okapi Consulting will, via Dandal Kura Radio International (DKRI), record, edit and broadcast aspects of the dialogue sessions initiated in Activities 1.2. and 1.3. and encourage feedback from listeners to improve transparency and accountability. In addition, DKRI will address the issue of corruption in wide-ranging discussion programmes that look at community needs and local government budgets. Programming will also ask listeners about their opinions on issues-of-the-day, providing them a chance to express themselves openly and publicly and ask questions directly to decision-makers and local government officials. DKRI will provide a platform for constructive feedback to local and state governments on improving their engagement with communities, and highlighting successful stories of government addressing the needs of communities and implementing joint government-community initiatives. / Output 2. Reduced youth vulnerability to extremist groups through increased access to finance and economic opportunities. / Activity 2.1: Support CSO capacity to support youth on acquisition of financial, business and life skills. Led by Mercy Corps. Mercy Corps will identify a local CSO to build its capacity to form Village Savings and Loan Associations (VSLAs) or Sharia compliant VSLAs as well as to deliver financial capabilities curriculum adapted by Mercy Corps and tailored to the context of Northeast Nigeria. Many youth need practice and tools to build confidence to apply new knowledge and skills to their everyday life decisions and behaviours. Financial capabilities curriculum aims to improve youth overall knowledge, skills, attitude and self-efficacy by blending financial education, business, life/soft skills to improve client/beneficiary ability to manage future economic opportunities. The curriculum will also contain modules on specific business skills areas, such as bookkeeping and asset management prioritized by employers and fundamental for entrepreneurs, that were identified during a labour market assessment conducted under the NE CMS programme in January and February 2016. / Activity 2.2: Youth establish informal savings and credit groups. Led by Mercy Corps. Mercy Corps’ research on Boko Haram’s recruitment tactics revealed that frustration over poor governance, high corruption and failure to provide security created space for Boko Haram’s message to take root in communities.[6] Boko Haram successfully recruited youth and exploited grievances and frustrations over inequality by providing opportunities for youth to achieve their economic ambitions. Mercy Corps’ study Motivations and Empty Promises: Voices of Former Boko Haram Combatants and Nigerian Youth found that many youth see Boko Haram as an opportunity to get ahead, hanging their futures on the promise of business support. Many recruited youth saw Boko Haram’s financial services as more accessible than existing alternatives.[7] Borno State is among the worst performing states in the nation on a variety of education indicators that reflect a broader political, economic and social crisis. For youth across the State, economic opportunity is scarce. / After building social cohesion and trust during the implementation of joint community development projects (Activity 1.3.), each group will be given the opportunity to create an informal savings and credit group. The VSLA model will encourage the youth groups to pool their savings and disburse loans to their members after agreeing to a group constitution. Mercy Corps has diverged from traditional savings group models to accommodate the emergency nature of Nigeria programming and meet the specific needs identified in Borno State.[8] Mercy Corps will work with the local partner engaged under Activity 2.1 to lead creation of sharia-compliant VSLA or standard VSLA groups. Sharia compliant VSLAs are designed specifically to not include payment of interest and instead a onetime loan application fee is charged. Having the option to select between availing sharia compliant financial products and services whether they are informal or formal are often found appealing in Islamic areas. / Mercy Corps will build on the experience of its financial inclusion projects, which have already been tested in other regions of Nigeria. NE CMS’s programme will provide skills training and financial education to promote savings and long-term sustainability and growth of economic interventions. Financial capabilities training will be integrated into the VSLAs to build their knowledge, skills, attitudes and self-efficacy for future economic opportunities. / Activity 2.3.: Youth establish group income-generating enterprises with targeted financial support. For those VSLAs that are interested, training on income-generating enterprises (IGEs) will be integrated into the savings group platform as an initial opportunity for groups to begin to earn an alternative income, bolster their savings fund and build their confidence for future individual IGEs. Building off the financial capabilities training, youth will be able to apply their newly acquired business skills to better run an enterprise, manage cash inputs to start businesses and foster ongoing group learning. To inform the selection of income-generating activities, Mercy Corps’ local partner will leverage the results of the labour market assessment conducted under the NE CSM programme. This will also inform the specific technical training and mentorship needs youth require that the program will provide under Activity 2.1. Mercy Corps will provide group enterprise grants to each group that develops a business plan that supports VSLA contributions and the income-generating potential of all group members. The purpose of the project will be for youth groups to build positive income-generating activities to launch productive livelihoods. / Mercy Corps, with its local partner, will work with groups prior to the disbursement of funds to support business plan development and ensure that proposed group IGEs are viable in the market and provide equitable opportunities for all group members to engage in activities. Mercy Corps, with its local partner, will also provide ongoing mentoring to the group and develop stringent monitoring and evaluation systems to ensure funds provided for group IGEs are used for their intended purposes. / Activity 2.4.: Facilitate linkages to formal financial services. To ensure scale up and sustainability of the programme Mercy Corps will identify state and bank initiatives providing access to capital for youth groups to initiate new businesses or expand existing ones. A mapping of such services will be undertaken and Mercy Corps will work with state government bodies as well as financial institutions to link youth to financial capital to allow them to fulfil their economic ambitions. / Mercy Corps will identify one local partner and build its capacity in business skills training, beneficiary identification, and monitoring and evaluation, to implement Activities 2.1. and 2.3. A strong monitoring and evaluation system will underpin these activities to ensure the funds are used for their intended purposes. Mercy Corps has significant global experience for monitoring funds disbursed to youth for business development in myriad contexts, and will incorporate these systems into NE CMS programming. / Output 3. Increased capacity of communities to collaborate across lines of division to prevent violence and promote peaceful integration. / Activity 3.1: Engage religious leaders in designing alternative narratives. Led by HD. HD will sustain dialogue among local religious leaders and other key stakeholders at the state, regional and federal level to design follow-up activities that use the alternative narrative as a basis for dialogue. This could include dialogue between the moderate Ulamas involved in the NE CMS pilot programme, and more radical Ulamas that disagree with the views expressed in their alternative narrative. In addition, HD will undertake consultations with religious bodies (CAN, JNI, SCIA) to build on the alternative narrative, and promote tolerance and reconciliation across the faiths in Borno State. / Activity 3.2: Bring together members of different faiths to promote peaceful integration. Led by HD. HD will facilitate intra- and inter-faith dialogue at a community level, between Muslim and Christian communities from Gwoza LGA (and potentially other LGAs, based on a continued needs-assessment) to achieve what they collectively identify as: a) short-term trust-building measures; b) mid-term reintegration and reconciliation objectives; and c) long-term peaceful coexistence and resilience goals. The Gwoza dialogue will likely involve delegates representing displaced Gwoza constituencies currently residing in Maiduguri, Adamawa, Plateau, Bauchi, Nassarawa, FCT. As part of this work, HD will support communities to establish early warning/tension management mechanisms. / Activity 3.3: Political, military, and CJTF leaders delineate options for a return to civilian life for vigilante members. Led by CIVIC with support from HD and Mercy Corps. CIVIC, HD, and Mercy Corps will undertake informal consultation and dialogue with CJTF leadership in Borno State to work on mitigating the risk of a new phase of the conflict forming due to the actions of vigilante groups, including the CJTF. The consortium will achieve this through engagement with political and military leadership on the future of vigilante members, and training and engagement with CJTF leadership and membership on civilian protection and the laws of war. These activities will be based on research on similar groups in other comparable contexts which would be applicable in Nigeria. The consortium will work alongside other actors involved in discussions with political, military and CJTF leaders, including the British Council. / Activity 3.4: Community leaders learn negotiation, mediation, and dialogue skills to lead peaceful reintegration processes. Led by Mercy Corps and HD. To prevent potential outburst of violence once IDPs return home, Mercy Corps will work with CSOs that received capacity building support through Mercy Corps’ USAID-funded Engaging Communities for Peace in Nigeria (ECPN) programme to promote social cohesion within and between communities through dispute resolution training, community forums and joint implementation of violence prevention and reconciliation projects. Mercy Corps and partners will build the capacity of community leaders (identified through the CVE committees formed in Activity 1.2.) to master negotiation, mediation and dialogue skills so that they engage in resolving key community disputes. Community leaders will also facilitate conflict prevention forums focused on key conflict drivers that impact the host and IDP communities and developing actions plans and agreements to collaboratively implement violence prevention and reconciliation projects. Such activities will be included in the community CVE action plans developed and implemented under Objective 1. HD will engage traditional institutions, local government authorities, religious leaders, and youth associations in inter-generational dialogue to promote inter-generational understanding and social cohesion and to strengthen formal and informal grievance and conflict resolution mechanisms. / Activity 3.5: Communities create self-protection plans. Led by CIVIC. To support sustainable safety of the communities, CIVIC will support communities to strategize and act to better protect themselves through facilitation of self-protection workshops where those who are representative of the community and have influence in the community will develop a self-protection action plan, followed by consultation and input from other community members, dissemination and implementation. These plans, once completed, will flow into the community CVE plans detailed in Activity 1.2. / Activity 3.6: Provide guidance to young people and parents on identifying signs of radicalisation among youth. Led by Mercy Corps and Okapi. Building on the success of engaging local partners Christian Association of Nigeria (CAN) and Jama’atu Nasril Islam (JNI) in the NE CMS pilot, Mercy Corps will continue to work with these two organizations to disseminate information on the signs of radicalization in youth and methods of protection to community leaders, parents, and young people themselves. At the beginning of NE NCS 2, Mercy Corps will conduct a mapping exercise of INGOs, government agencies, and CSOs providing psycho-social support to young people exhibiting signs of radicalisation, building a referral network that spans all communities engaged through the programme. Furthermore, Okapi will develop different radio programmes, such as programmes that: a) help parents identify signs of radicalisation and receive advice from affected parents on how to approach the problem; b) promote dialogue between youth and elders on challenges of resisting the Boko Haram narrative; and 3) disseminate effective alternative narratives formulated in partnership with HD. / Activity 3.7: Government and civil society learn about approaches to transitional justice. Led by HD. HD will provide guidance, comparative information, and lessons (technical assistance) to government authorities and non-governmental stakeholders in Borno State on approaches to transitional justice and accountability, particularly non-judicial means. Depending on the needs and priorities identified by local stakeholders, HD may facilitate dialogue on victim redress, forgiveness, truth telling, and transitional justice. These recommendations will be taken to the Borno State government for further elaboration in the CVE framework developed through Activity 1.1. / Activity 3.8: Development of a communications strategy (including radio messaging) results in broad support for an understanding of reconciliation. Led by Mercy Corps and Okapi Consulting, with support from HD. Consortium partners will support regional and federal campaigns aimed at disseminating positive messages on reconciliation through radio and cultural events. In partnership with local organizations, including those led by influential local religious leaders, the consortium will organise dialogues to popularize an alternative narrative to Boko Haram and other extremist groups. Dialogue activities will also provide spaces where victims, offenders, and community members will meet to decide how to repair harm caused by violence. To ensure a conflict sensitive and do no harm approach, HD’s recognised experts in restorative justice will advise on the best approaches and will build the capacity of local organizations to facilitate such community dialogues. Results of the community dialogues will be collected and analysed to inform restorative justice processes at the state and federal levels. The popularization of alternative narratives will entail, at minimum, the translation of content in Hausa, Kanuri, and Arabic and will include consultations with CAN, the JNI, the SCIA, and other relevant bodies. Okapi Consulting will support DKRI to broadcast alternative narratives and dialogues around reconciliation and peace through radio. / Activity 3.9: Radio programming widely disseminates faith dialogue, alternative narrative messaging, and other forms of peacebuilding radio to Kanuri-speaking populations. Led by Okapi Consulting. Okapi Consulting will support Dandal Kura Radio International (DKRI), a Kanuri-language radio station that operates from two hubs in Maiduguri and the Chadian capital N’Djamena. DKRI is fed by a growing network of local correspondants. An estimated 10 million Kanuri speakers live in this region. While it is not possible to give precise listenership figures, an evaluation carried out in Borno State in 2016 by London-based research company ORB indicates DKRI is recognised as a positive information source by more than 90% of those surveyed. Infrastructure development throughout the region is weak at best, as is the literacy rate, making radio the only efficient means of reaching most of the population. DKRI is the only predominantly Kanuri language radio station in the region. Radio is accessible to almost the entire population – not everybody owns a radio however virtually all people have access to a person owning a receiver. DKRI serves as a strong medium through which to disseminate alternative narratives to a wide population. Specifically, Okapi will support the production of radio programming which mediatizes inter-faith dialogues and engages with communities in discussions about the issues that affect them most. Other radio programmes could link IDPs and the communities they originally came from, where possible, developing contacts before the IDPs return, and/or transitional justice programming that demonstrates how transitional justice processes work.
6. How is your approach innovative?
NE CMS will contain several innovative approaches. First, Mercy Corps is exploring a relationship with Palantir, a company that helps organizations use data better by integrating multiple sources of information to target communities most at-risk for violent extremism. Mercy Corps has worked with Palantir extensively in Syria to improve access to communities. For CVE programmes, Palantir would help Mercy Corps use both our assessment data as well as external sources, including media, Armed Conflict Location and Event Data (ACLED) reports, et cetera to examine where resources should be invested. This data will also help track changes in community dynamics and programme interventions over time. Secondly, Mercy Corps will partner with PERL to promote policy dialogue at all levels of society, including State Government, LGAs, and communities. PERL will provide two training modules: 1) joint training for communities and LGA officials in each LGA on participatory budget development and government budget processes; and 2) support to a technical working group at the State level to incorporate community needs, identified through LGAs, into State budgets. These activities are innovative because they span governance structures in the Northeast, promoting community identification of needs and creating accountability mechanisms between communities and government. Thirdly, CIVIC will work concurrently on strengthening abilities of security forces to protect civilians, building resilience and confidence among civilian populations, and bringing civilians and security forces together in meaningful dialogue to build trust in the Nigerian state’s ability to protect. This holistic and comprehensive approach was piloted during the NE CMS pilot, with lessons learned informing NE CMS. NE CMS will deepen engagement in pilot LGAs and scale-up to new locations.
7. How will the project be implemented, given the operational and institutional capacity constraints of working in the conflict-affected parts of the north east? What is your approach and capacity in relation to security?
The consortium selected high-population areas to maximize the number of participants. Mercy Corps will implement NE NCS 2 through its existing field office in Maiduguri, and will work through local partners to whom it will provide mentoring and programmatic and organization capacity building support to ensure programme objectives are met, financial standards are maintained, and the sustainability of interventions is prioritized. Mercy Corps Nigeria is currently delivering humanitarian assistance in Borno State and will leverage relationships established in that context to overcome potential operational and security constraints. Mercy Corps Nigeria, CIVIC, HD and Okapi’s security policies are based on the principle of community acceptance, which involves working with community, government, and religious leaders to ensure staff safety and provide services that are welcome, needed, and appropriate in local contexts. The community, instead of security contractors, becomes the guarantor of security. As in other conflict zones where consortium partners work, staff will maintain a low profile by traveling in unmarked vehicles which blend into the local environment. This method allows staff to continue working even during volatile periods. / CIVIC’s activities will build on its existing programming and project team in Nigeria, which engages with government and security agencies in both Abuja and Borno. Given the high-level institutional buy-in needed on the military side, CIVIC will continue to engage through the military chain of command, with whom it has strong relationships built during the development of current civilian protection policy work with the Chief of Defence Staff and Defence Headquarters (funded by the Government of Germany) and trainings. This project will also build on CIVIC’s existing relationship with the Defence Headquarters and National Defence College as well as the Training, Operations, and Planning teams to support field assessment and training activities. / HD’s activities will be implemented by its existing Northeast team, with the potential for one or two additional local advisors. This team will continue to broaden HD’s local network of religious, traditional, community, opinion, women, and youth leaders. HD will set up a “Friends of the Gwoza Process” group of prominent traditional leaders and influential opinion leaders from outside of Borno State and beyond. Members of the auxiliary group will be called upon to engage with the parties in the Gwoza dialogue process at key junctures, to add further leverage, and promote the peaceful settlement of contentious issues. Secondly, HD will mobilize traditional justice experts with extensive comparative experiences to provide technical advice and assist with the reparative needs identified by local stakeholders. / Okapi’s activities will be implemented by the existing DKRI team, supplemented, where necessary, by additional staff who will be trained to a required standard.
8. Will local partners be used or will implementation be direct? If local partners will be used, who are they, what is their role, and is this an existing partnership? Has a due diligence assessment been completed for the implementing partner(s)? How will the partner(s) monitor the project?
Consortium partners will implement using different modalities. CIVIC and HD will implement directly, with their staff and consultants carrying out all activities. In addition to direct implementation, the CIVIC components have a strong element of capacity strengthening and accompaniment. CIVIC staff and consultants will train and mentor military personnel and community members identified as having strong potential to gradually lead trainings (for the military) and workshops and to facilitate dialogues (for the military and communities). Mercy Corps will put partner organizations at the forefront of programme implementation, giving the responsibility for outreach, facilitation, and training. Mercy Corps will continue to work with the three local partners identified under the NE CMS pilot programme, given the time and effort invested in capacity building and alignment of organizational goals. These three partners are the Christian Association of Nigeria (CAN), Jama’atu Nasril Islam (JNI), and HERWA (a Borno-based CSO with experience in peacebuilding). These three local partners went through a due diligence process prior to receiving sub-grants under the NE CMS pilot programme and proved their capability of managing funds and delivering programme activities. Mercy Corps will add additional partners to lead Objective 2 activities (leadership and business skills training, internships, and business grants), providing intensive capacity development support throughout the partnership to ensure quality programme delivery and to prepare the selected CSOs for future partnership with donors and INGOs. Mercy Corps Nigeria will provide technical assistance to partners, mentor them through implementation, and provide oversight, including ensuring impartiality and inclusiveness in the selection of programme participants in all activities. This partnership strategy aims to reinforce local capacities for preventing and resolving conflict, promote the sustainability of interventions and knowledge, lay the groundwork for scale-up and/or Mercy Corps Nigeria’s exit, and ensuring that programme activities are locally appropriate. Partners’ local knowledge and ownership will complement Mercy Corps’ position as a credibly impartial outside and technical expert in integrated peacebuilding, stabilization, and development approaches. Based on the project logical framework, partners, with the support of Mercy Corps’ monitoring team, will typically undertake monitoring activities, outputs, and milestones that are expected to occur throughout the programme. Finally, Okapi Consulting may produce some programmes itself as well as providing technical and financial support to its existing partner, Tauraruwa Broadcasting, which operates Dandal Kura Radio International. / A Due Diligence Assessment has been completed for the implementing partners.
Results
9. What are the expected results of the project? Results should be clear and disaggregated by sex and age where possible, for the number of people that you plan to reach with various activities, per year and over three years.
Please see the attached logical framework for a detailed list of activities, outcomes, impact, and expected results. This programme will result in increased peace within and between communities and increased confidence in governance and security institutions to address the root causes of conflict and violent extremism in Borno State. The consortium will support the Borno State Government to develop a CVE framework and encourage 30 communities across nine LGAs in Borno State to develop CVE action and self-protection plans, strengthening cooperation between communities and government and increasing trust in the ability of the Borno State Government to address community needs. The programme will address some of the structural motivators that push youth towards engagement with extremism by supporting productive youth livelihoods, including linking 1,500 youth to employment opportunities, providing business grants to an additional 1,500 youth to support entrepreneurial ventures, and promoting engagement between young people and their communities by facilitating 100 youth-led community development projects. Finally, NE CMS will result in the increased capacity of communities to collaborate across lines of division to prevent violence and promote the peaceful integration of perpetrators of violence, their victims, and IDPs. Through faith dialogue, enhanced community mediation skills, dissemination of positive alternative narratives to extremist language across a range of media (including radio), and the delineation of options for the reintegration of vigilantes, communities will start to feel more peaceful, safe, and secure and some will come to believe that the use of violence to support political or social causes is not justified.
Evidence and Assessments
10. What is the strength of available evidence underpinning the proposal? What are the gaps in evidence that the project will need to address to improve the effectiveness of the intervention? On the basis of what assessments have you designed your proposal? How have insights from potential beneficiaries shaped the intervention?
Mercy Corps Nigeria, CIVIC, and HD are at the forefront of research and analysis on conflict and violence in Northeast Nigeria. With the study “Motivations and Empty Promises” and “Gifts and Graft,” Mercy Corps conducted research on what leads Nigerian youth to join Boko Haram, while CIVIC has conducted research on perceptions of civilians, security forces and vigilante groups when it comes to civilian harm. HD and UNDP have recently conducted a study “Sahel – Perceptions of Radicalization, Violence and (In)Security Drivers,” to inform non-coercive responses to radicalisation and to ultimately encourage a shift in the way related challenges, such as border management, state-shaping, faith- and community-based dialogues, or economic development are addressed in border regions of the Sahel. The consortium has also drawn on relevant research produced by the National Stability and Reconciliation Program (NSRP), International Alert, Centre for Democracy and Development (CDD), and USAID/OTI. Furthermore, consortium partners bring their experience from the NE CMS pilot, which provides strong insights into how to tailor programme activities to better protect civilians, build peace, and target social and economic drivers, as well as “pull” factors, of youth participation in violent extremist organizations. This knowledge will be complemented through collaboration with CSOs in Borno State. / Mercy Corps will also conduct a study of the youth livelihood components of the NE CMS programme to best understand which activities have the greatest potential for impact and scale, increasing the Value for Money of the programme. Four communities will be selected, each of which will receive a different livelihood activity (e.g., individual business grants, group grants, internships, community development projects). A baseline study focusing on youth livelihood indicators, such as youth perceptions of community engagement, happiness, and ability to succeed in life, will be administered at the start of the program. A midline study will be administered after a period of six to ten months to gauge changes in youth perceptions. This study will inform which livelihood activities will be implemented during the remainder of the programme, and will be shared with other stakeholders working in Northeast Nigeria to
Risk analysis
11. Please provide an analysis of risks and how these risks will be managed.
Risk 1. Instability. Although security in Borno State has improved, Boko Haram continues to conduct attacks through suicide bombings and terrorism. There is a risk that Boko Haram may have a resurgence or continue targeted terrorist attacks to disrupt government- and community-led efforts at reconciliation. Mercy Corps, CIVIC, HD and Okapi mitigate this risk through consistent analysis and close collaboration with government and security actors in the community. All consortium partners have already established a presence in Borno State and close cooperation with local partners and other INGOs allow each organization to quickly adapt to security risks. / Risk 2. Corruption. Corruption is a constant risk in Nigeria. To counter this risk, Mercy Corps, CIVIC, HD and Okapi have strong quality control measures and closely monitor and mentor partners through the lifecycle of its programmes. All consortium partners have been operating in Nigeria for several years and have experience in managing this risk. / Risk 3. Gender expectations. Cultural and religious norms may limit women’s participation and/or negatively impact gender relations. All NE NCS 2 activities promote participation of women by considering their schedules, workloads, and child care duties when planning events and activities. Mercy Corps, CIVIC, HD and Okapi always consult with participants to identify emerging issues and plan appropriate responses. Given security forces are male-dominated, CIVIC ensures women comprise the majority of civilians who take part in its facilitated dialogues and organize activities to ensure their meaningful participation. / Risk 4. Political interference. Dialogue meetings, social and economic empowerment projects, research, and advocacy initiatives may be subject to political interference if not well-planned. The consortium will mitigate this risk by ensuring that government supports research and advocacy before they begin. Risk 5. Keeping stakeholders engaged. In the community dialogues that involve religious minority and majority groups, there is risk that the majority could become complacent or even disinterested in dialogue, especially in the face of daunting reintegration experiences. Those in the majority might be less willing to discuss sensitive issues, especially if the minority group seeks to address entrenched social, political, or economic power dynamics. To mitigate this risk, HD will facilitate story-telling and scenario-building workshops that encourage leaders to visualise the best and worst case scenarios for their communities, and to arrive at a consensus as to what is actually feasible in the near future. Similarly, change in key personnel among the military and political leadership could lead to reduced interest and support for prioritizing civilian protection in operations. CIVIC will mitigate this risk by engaging a wide and diverse number of people at all levels of decision making and proactively building relationships with new appointees. / Risk 6. Security force actions. Despite CIVIC’s engagement with security forces, security force behaviour could reduce trust and willingness of communities to engage in dialogue that could lead to backlash against communities. CIVIC will mitigate this risk by creating an atmosphere during dialogues that is conducive to the sharing of concerns in a constructive manner, engaging with military leadership and supporting communities to build common platforms so no one person is seen as coming forward with a critique. / Risk 7. Cultural and religious sensitivities. Mercy Corps works through local partner organizations, including CAN, JSI, and HERWA. Mercy Corps will empower these local partners to be proactive in guiding programming and raising any issues that they might see in consortium implementation. Mercy Corps and consortium members will also ensure diversity in national program staff, making sure team members reflect different religious and ethnic backgrounds so that sensitivities around culture and religion are considered and incorporated into programming. The consortium will conduct conflict assessments prior to entering communities and all consortium members and their local partners will receive conflict sensitivity and Do No Harm trainings bi-annually. The consortium will also identify specific risks around cultural and religious sensitivities in planning meetings prior to the implementation of any activities. / Risk 8. Poor economic environment inhibits youth livelihood activities. Functioning market systems are a pre-requisite for youth building sustainable livelihoods with support from Mercy Corps. A Youth Vulnerability Assessment conducted in January and February 2017 through NE CMS found that many youth were engaged in employment or self-employment activities prior to the Boko Haram insurrection. Often, the insurrection resulted in the disruption of market activities or the loss of capital. Mercy Corps will build upon its Livelihood and Market Recovery Assessment for North-East Nigeria, researched with funding from USAID, and Labour Market Assessment, researched through the NE CMS programme, to guide youth into activities that are in-demand and have strong potential for growth. / Risk 9. Youth livelihood activities captured by patronage networks. There is a risk that cash programming used for youth business development can be captured by patronage networks. To mitigate this risk, Mercy Corps sets up CVE committees that are representative of the communities in which Mercy Corps works. These committees will help Mercy Corps identify vulnerable and at-risk youth to receive Mercy Corps support. In communities where youth groups are already present, Mercy Corps will explore working with these groups to take advantage of existing, sustainable community structures. Mercy Corps will also form youth groups and spend the first months of group activities focusing on community development and social projects that do not provide individual financial benefit to any group members. Only after several months of community development and social projects will Mercy Corps introduce income-generating activities, with the expectation that only youth that remain engaged during the community development projects will participate in income-generating activities.
Cross-cutting themes
12. Please indicate how the project will address the following cross-cutting themes: / How will the project be “conflict sensitive” and consistent with the principle of “do no harm” throughout the implementation period? / How will the project ensure gender mainstreaming and how will it be compliant with the UK International Development (Gender Equality) Act 2014? The proposal should answer the following specific questions: (I) How will the project contribute to reducing gender inequality? (ii) How will the project take into account gender differences in needs? (iii) How will the project address barriers that could prevent girls and women from accessing assistance? (iv) How will the project affect relations between girls / women and boys / men? / How will the project promote better data collection, management and analysis? / How will you maintain flexibility? For example, what opportunities exist to scale the project up or down? What options are there to move the project towards a more developmental approach if that becomes appropriate? What is the exit / transition strategy?
To successfully implement activities within the three focus areas, the consortium will build the following cross-cutting themes and core principles into all activities: / Conflict Sensitive and Do No Harm Approach: Do No Harm (DNH) is a core principle that all consortium partners apply in their lines of work. Recognizing that giving visible preference to a particular segment of the population risks reinforcing fears of identity-based exclusion, the programme approach emphasizes consensus building and will ensure that benefits of programme participation are equally accessible to all segments of the community. Conflict sensitivity will be incorporated into risk management and M&E practices to ensure it is adequately considered and reported. / Mercy Corps has developed a standardized curriculum and tools for training all staff in the principles of DNH and conflict sensitivity. At the start of the programme, and quarterly thereafter, Mercy Corps will conduct conflict and DNH analyses that include relationship mapping tools to identify influential individuals and organizations from the community to ensure the programme is balancing key stakeholders and understands the dynamics and tensions between groups. Mercy Corps will also utilise a conflict and resource mapping tool, which helps identify key resources and whether they are sources or potential sources for conflict and tensions. / CIVIC amends programming based on conflict analyses to reduce the likelihood of negative impacts on conflict dynamics and increasing positive impact. Aware of the particular risk of dialogues between security forces and communities increasing conflict between them, CIVIC ensures substantial engagement with each group separately beforehand so they are well placed to engage with each other in a way that is constructive rather than defensive. CIVIC also maximises opportunities to build relationships across conflict lines in the communities in which it works. / Gender and Disability Mainstreaming: Conflict is affected and experienced differently by women, men, the young, the elderly, and the diverse array of ethnic and religious communities found in Borno State. The consortium’s participatory, community-led approach is designed to promote inclusion of all members of the community in a context of traditional gender roles, as well as polarized ethnic and religious identity. Gender analysis and gender sensitization will be conducted at programme inception with all staff engaged in the project, as well as key stakeholders, to increase understanding of gender roles in conflict management and the benefits of increased inclusion of women in mitigating conflict. Women’s participation will be promoted by bringing women together separately from men in activities, giving each gender group an opportunity to express themselves openly. All data will be disaggregated by gender in order to evaluate the differential impact of the programme on both women and men. Consortium partners will assess this data to understand the distinct role each gender plays in resolving and preventing community conflicts. Notwithstanding the low numbers of women in the security forces, CIVIC will ensure women meaningfully participate in its activities. The content of CIVIC’s workshops, training, and dialogues integrate gender by looking at the vulnerability and agency of women, men, girls, and boys and covering areas such as sexual exploitation and abuse, outreach to women as part of community engagement, the suspicion that falls upon young men, and encountering children in military operations. / In addition to gender, the consortium will mainstream disability in its work, which is important given the additional harm people with disabilities face and the increased number of people with disabilities due to the conflict. / Promotion of Better Data Collection, Management, and Analysis: Building upon the solid evidence base for programming and policy initiated during the NE CMS pilot, including analysis of approaches that were effective, the consortium will continue to collect missing and additional data to inform programme activities and efficacy. This includes producing additional research that can inform policies and interventions by the government and partners to best address CVE- and peacebuilding-related issues. Mercy Corps will hold regular sessions to receive feedback from partners, stakeholders, and beneficiaries. For workshops and training conducted by CIVIC and HD, pre- and post-training questionnaires as well as impact monitoring will be used to follow-up on progress made as well as to feed into and improve content and facilitation in subsequent sessions. / Flexibility: Consortium partners engage in adaptive management, defined as identifying and adapting to new challenges in a timely and intentional way by better understanding and responding to contextual dynamics. Using data to understand the impact of program activities, and their variable impact on women and men, consortium partners will adapt programmes to have the greatest impact in a dynamic and fast-changing environment. / Strong Coordination with Civil Society and Government: The premise of much of the NE NCS 2 programme is building trust and strengthening coordination between communities, civil society, and government. / Mercy Corps will align its interventions with humanitarian activities, which provides a solid basis for building trust within communities and IDP camps. This also increases the willingness of beneficiaries to participate in sustainability and behavioural change activities, once their basic needs are met. Finally, close coordination with humanitarian activities will increase the cost efficiency of interventions. / The consortium will take the lead in re-engaging the Northeast sub-group of the National Peace and Security Working Group to promote cooperation among agencies and organizations engaged in CVE and peacebuilding work in Borno State to avoid duplication, align approaches, and complement activities. CIVIC will build on and strengthen existing relationships with protection actors in Borno State to ensure joint advocacy with civil society and alignment with government actions.
Accountability, Coordination and Partnership
13. How will you engage with community-based organisations and individuals to enhance accountability? How will you engage with State governments? Will your project bring your organisation into contact with the security sector, such as military and CJTF? If so, how will you work with them?
One of the primary objectives of NE CMS is to increase the capacity of communities to hold government and security forces accountable. Local civil society and faith-based organizations will play a critical role in engaging communities in dialogue and peacebuilding activities. The Consortium will work directly with government at all levels, including the Borno State Government in the development of a Borno State CVE framework and LGAs in the development of participatory budget processes that address community-identified infrastructure needs. The consortium will work directly with security forces, often through direct chains of command, to promote civilian protection and responsiveness to community capabilities and needs. This includes the CJTF, who will be consulted on measures promoting civilian protection and livelihood options for CJTF members who wish to exit the institution.
Consortia (if applicable)
14. Consortia proposals must provide the following: / A full list of partners and their eligibility to operate in Nigeria; / The management structure, systems, technical oversight, identification of a lead partner and explanation of the roles of each of the partners. Please note that the lead partner (not DFID) will have responsibility for due diligence of the other consortium members; / An explanation of why the partners are together (is this simply responding to this call for proposals or do partners have a history of working together?); / An explanation of what are the advantages or gains in working together;
Building on the experience of working as a consortium while implementing the NE CMS pilot programme, this consortium will implement a broad set of activities that address the underlying factors that have contributed to instability in the Northeast and laying the groundwork for a more peaceful future. The programme will build upon the strengths of individual consortium partners to promote dialogue between civilian, military and state actors to address key grievances and improve civil-military relations, support youth populations most susceptible to messaging by extremist groups, and promoting reconciliation and transitional justice at the community-level that supports the reintegration of former members of violent groups, their victims and IDPs. / Consortium partners include the Centre for Civilians in Conflict (CIVIC), which works in a highly technical niche of civilian protection and civilian-military relationship building that is an important element for a peacebuilding programme, Centre for Humanitarian Dialogue (HD), which seeks to prevent, mitigate, and resolve armed conflict through dialogue, and Okapi Consulting, which develops media projects in regions of conflict in order to reduce violence and promote understanding through transparent, democratic narratives. Finally, Mercy Corps, as lead consortium member, will leverage its different areas of technical expertise, including governance, youth, and livelihoods to address the “push” and “pull” factors that drive participation in violence. / A detailed overview of how this consortium will be managed is included as Appendix A.
Value for Money (VfM)
15. How will the proposed intervention be consistent with DFID’s Approach to Value for Money (VfM). What is the multiplying effect of multi-year funding? How do the costs represented in the costed work plan represent good Value for Money? What is your proposed payment schedule and how does this link to measurable progress (outputs) and the log frame?
This consortium’s established structures, policies, and systems in Nigeria (including in the Northeast) have resulted in good Value for Money (VfM) to-date. All consortium members are committed to building upon these methodologies in NE NCS 2, which has been designed to demonstrate good VfM throughout the programme life cycle. Operating in Borno State, a post-conflict environment with continued sporadic violence, can impact access to communities and the availability of goods and services, with an effect on programme costs. With this in mind, the consortium will use DFID’s 4Es framework to guide the most economical sourcing on inputs feasible, an efficient generation of outputs that are effective in driving outcomes that maximises equitable delivery of impact. For the consortium members and downstream partners, the opportunity to reach the maximum number of Nigerians with quality programming will be a constant priority. All consortium members will employ the following practices: / This VfM framework will be embedded in the NE NCS 2 strategy and explained to and endorsed by all consortium member and partner teams on an ongoing basis; / Competitive, open, and transparent procurement processes will be used. This includes effective management of contracts to guarantee that inputs are and remain competitively priced; / Financial standards, procedures, and tools combine the best practices for tight internal controls that ensure compliance with the economy and efficiency aspects of DFID’s 3Es framework; / Programme management standards will ensure that targets are achieved within the time and budget allocated and that systems are efficient and effective; / Regular review of the VfM approach by each consortium member’s management will ensure that implementation conforms to DFID guidance on best practices. / Economy: NE NCS 2 will utilize existing management controls which embed VfM thinking into operational decision-making and reporting. Particular attention will be paid to any potential cost drivers (for example, inflation and exchange rates) to ensure controls anticipate and mitigate any changes to these drivers. / Procurement procedures for each consortium member will meet all major donor requirements and ensure fairness, transparency, and good stewardship of donor resources, achieving competitiveness and best VfM relative to local and international markets. This includes compliance with international and local laws and regulations concerning the ineligibility of vendors, contractors, and suppliers for reasons of fraud, corruption, or terrorist activity. Dedicated procurement personnel at each level of operation (including all consortium members’ lead and field offices) increase market knowledge and ensure receipt of fair market pricing. For large or recurring procurement, consortium members will advertise public tenders to solicit bids from as many eligible suppliers as possible. Procurement processes balance quality with monetary cost and allow for effective tracking of items from request to delivery to use. Where the lowest-cost materials or services were not selected, notes will indicate the justification and the value gained from selecting a higher-cost input. These principles for procurement will also apply to downstream partners that work with Mercy Corps and Okapi. / In many cases, the inputs used in NE NCS 2 are expert staff and consultants. These staff will be able to maximize networks and access at a low cost. / Efficiency: Strict budgetary control is maintained by all consortium members at all levels of the programme. In carrying out this review, any cost savings are tracked and, on a semi-annual basis, recommendations are made to reallocate savings towards areas that are demonstrating the greatest impact. Any reallocation of greater than 10 per cent will be undertaken in consultation with DIFD. / NE NCS 2 will submit a costed work plan to DFID that estimates the per-unit cost of each programme activity (measured through the output indicators included in the attached logical framework) prior to the commencement of the programme. In each quarterly report, consortium partners will review the costed work plan to assess their efficiency in the creation of outputs. / NE NCS 2 will aim to make effective use of high-quality inputs to achieve the highest possible quality results (outputs). / Maximising local resources: Consortium members believe that low cost and high effectiveness can often be achieved simultaneously by maximising local resources and tailoring activities to local needs and context. NE NCS 2 will source inputs and services locally, when possible and appropriate, to provide wider economic benefit in targeted communities. / Multipurpose cash: Consortium members will seek to utilise cash-based assistance whenever appropriate. Cash, compared with in-kind assistance, is often more efficient.[9] Cash will be used primarily in Objective 2 when providing economic assistance to youth to start their businesses and support internships. / Finally, the consortium will lead partnership between CSOs, INGOs, government, and the private sector to prevent gaps and duplication in programme activities. This consortium will leverage the activities of each of its members to add value in their specific areas of expertise to the overall production of outputs. Finally, Mercy Corps and Okapi will partner with local CSOs in Borno State to build capacity and deliver quality services cost-effectively and efficiently. / Effectiveness: NE NCS 2 is designed from available evidence and based on a clear theory of change with objectives and targets based on baseline data. Consortium members will assess their interventions and activities, measured through rigorous monitoring, evaluation, and learning systems, against the Theory of Change to determine which interventions and activities should be scaled, adjusted, or discarded. Consortium members will base their interventions on international best practices and build upon lessons learned from their activities both in the Northeast of Nigeria (through the NE CMS pilot) and in similar contexts. Incorporating these strong learnings and best practices will maximize effectiveness by using proven methodologies, while the breadth of programme delivery and diversity of technical expertise and experience that will be brought to NE NCS 2 by the four consortium members will have a multiplier effect that expands programme impact. / Equity: Equity can be defined in terms of whether the outcomes and outputs will benefit different types of recipients equally. Consortium members will employ tools developed to identify those most vulnerable in a particular community, enabling programme teams to target vulnerable groups or individuals effectively. This will include using a gender lens in programme design and implementation. To ensure inclusiveness and equity, NE NCS 2 will engage with both target communities and government authorities to implement activities that support peace and good governance in a holistic manner. / For diagrams of Mercy Corps’ delivery chains, please see Appendix C.
Monitoring and Evaluation Plan
16. How will you ensure that the project delivers results? Please be as specific as possible. We will expect results data to be provided on a regular (at least quarterly) basis.
Consortium partners will be responsible for leading the monitoring and evaluation of the activities for which they are the lead implementer according to the logical framework attached as Appendix B. Mercy Corps, as lead consortium partner, will provide oversight of data collection and analysis and compile data on indicators included in the logical framework for submission to DFID on a quarterly basis. / The consortium’s monitoring and evaluation systems aim to ensure accountability to both DFID and programme beneficiaries, enhance programme and partner performance, and measure impact. As a consortium of learning organization, each consortium member has invested significant resources in developing indicators, data collection tools, and analytic methods for measuring programme impact, with particular attention to the challenges of collecting data in conflict-affected environments and evaluating peace building programmes in particular. Design and implementation of the monitoring and evaluation strategies will be led by each consortium member’s M&E team member, with support as needed or requested from the Monitoring, Evaluation, & Learning Manager at Mercy Corps Nigeria. Mercy Corps will work closely with partners to select and define indicators and to collect and analyze data in order to build partner capacity and improve the accuracy of results measurement. Mercy Corps will also involve programme participants in monitoring and evaluation activities, including working with communities to develop context-specific impact indicators and to measure programme success against community perceptions and priorities. / The programme team, including partners, will develop a detailed logical framework and indicator plan before developing a monitoring and evaluation strategy. Results measurement for the programme will include both output and outcome indicators. Impact indicators will be directly linked to the programme’s Theories of Change, providing the opportunity to test the validity of the Theory through the programme evaluation. Monitoring and evaluation activities will include a baseline and endline survey, and on-going monitoring of programme processes.
Other
Anti-terrorism and anti-corruption policies.
Anti-terrorism: Consortium partners will prohibit providing material support or entering into transactions with prohibited parties, as is in line with applicable law and donor regulations. As the consortium will implement many of its activities together with local community volunteers, all consortium members will vet said volunteers to ensure they do not have ties to any terrorist organisations. Furthermore, consortium members will train their staff and partners on the concept of Do No Harm and conflict sensitive approaches to development. / In the proposed operating area (Borno State), numerous armed groups operate, as well as the Nigerian Armed Forces. / Boko Haram is a designated terrorist organisation currently engaged in terrorist activities in the Lake Chad Basin area, including Borno State, Nigeria. The organisation is currently engaged in an insurgency against the Government of Nigeria and uses terrorism attacks targeted at the civilian population as part of its operations. Consortium partners will take precautions to ensure assistance is not diverted to Boko Haram and its two splinter groups, Jama’atu Ahlis Sunnah Lida’awati wal Jihad (JAS) and Islamic State West Africa (ISWA). / The Civilian Joint Task Force (CJTF) is a partially state-sponsored, informal security actor. It operates in several areas in Borno State, including Jere and Dikwa LGAs. The CJTF consists of local youth often serving part-time in the CJTF to protect their local areas from Boko Haram and, in some cases, to patrol the location to prevent criminal activities. The level of organisation, skill, training, and whether they are armed with firearms or not, differs from location to location. In areas where the CJTF has a large security role, consortium members will check-in with the CJTF to alert them to consortium presence and sensitize them to intended consortium activities. If members of the CJTF approach a consortium member or partner in that capacity and ask for assistance, the consortium will explain its mission statement and beneficiary criteria, ensuring that they understand that our selection process for beneficiaries is open and transparent. If issues were to emerge vis-à-vis the Nigerian Armed Forces or state-sponsored armed groups, CIVIC will engage the Government of Nigeria in addition to other INGOs in order to find solutions. / Mercy Corps and partners use Community Accountability and Reporting Mechanisms, including a feedback hotline, to receive information from the communities selected to receive interventions. This includes any suspected cases of diversion of project materials to any party other than the intended beneficiaries, as well as any cases of theft, robbery, or threat thereof of materials distributed by Mercy Corps. Mercy Corps investigates all such cases in order to not only prevent diversion of project materials, but also to ensure that our beneficiaries are safe. / Corruption: Corruption is an ever-present risk in Nigeria. To counter this risk, Mercy Corps has a board approved Anti-Corruption and Anti-Bribery policy, which all staff are required to follow and which includes processes and procedures to ensure compliance. The policy is shared upon request with donors and other interested parties. / The consortium will prohibit and take a zero-tolerance stance towards all forms of corruption, including fraud, theft, embezzlement, unapproved conflicts of interest, false claims, and bribery. Employees who engage in or assist with any form of corruption will be subject to discipline, including termination, and may be subject to criminal prosecution. Partners in violation will be in breach of their agreement with Mercy Corps or other consortium member, and may have their agreements terminated, be prohibited from working with the organization in the future and/or be subject to criminal prosecution. / The consortium will require all employees and partners, and encourage all beneficiaries, to immediately report incidents of corruption. Consortium members will report credible evidence of corruption, after a thorough investigation, to the appropriate authorities and to the donor, as required by our donors or by law. Should Mercy Corps engage a local sub-grantee for the implementation of this project, Mercy Corps will train and closely monitor the local sub-grantee in all matters related to financial transactions, ensuring that they adhere to all the standards and requirements of Mercy Corps, the donor, and relevant Nigerian and international legislation.
[6] “Motivations and Empty Promises;” Voices of Former Boko Haram Combatants and Nigerian Youth, Mercy Corps, 2016
[7] “Gifts and Graft. How Boko Haram Uses Financial Services for Recruitment and Support”, Mercy Corps, September 2016
[8] “Tipsheet: Savings Groups in Humanitarian Response: Lessons from Northeast Nigeria with Displaced Populations.” Mercy Corps, 2017. https://www.mercycorps.org/sites/default/files/Mercy-Corps-Tipsheet-Savings-Groups-Nigeria-Response.pdf
[9] Mercy Corps Cash Transfer Programming Toolkit. https://www.mercycorps.org/sites/default/files/CTP1MethodologyGuide.pdf