Annual Review - Summary Sheet

Title: Zambia Sanitation and Hygiene Programme
Programme Value: £23,100,000 (DFID component)		Review Date: Review undertaken in early March 2018 for the period 1st March 2017 to 28th February 2018.
Programme Code: 202345	Start Date: 23 Nov 2012	End Date: 30th September 2018

Summary of Programme Performance
Year	2012	2013	2014	2015	2016	2017	2018
Programme Score	N/A	B	A	A+	A+	A	A
Risk Rating	N/A	High	Medium	Low	Moderate	Moderate	Moderate

Summary of progress and lessons learnt since last review

The Zambia Sanitation and Hygiene Programme (ZSHP) has made impressive achievements and is on track to achieve or exceed the key output targets in the last six months. It has delivered over 3.7 million new users[1] of improved sanitation (including 344,142 new users in the last year), and over 11,000 villages have been declared Open Defecation Free (ODF) across 68 districts of the country. More than 6.2 million people have been reached by hygiene promotion messaging (420,761 during the review period), and 3.4 million people are reported to have access to handwashing facilities. The innovative Real-Time Monitoring (RTM) system developed in the project has helped to track and accelerate progress. Over 500 masons across the country have been trained in the marketing and construction of latrines (139 masons trained during the review period), and their training is being incorporated into the syllabus of national vocational training centres. The status of sanitation facilities has improved in over 1000 schools nationwide (142 schools were reported completed in the last year), and many of these have improved menstrual hygiene arrangements. There appears to be strong anecdotal evidence of improvement in girls’ attendance and performance at school as a result of the interventions. From a low base, it is also apparent that community and rural leaders are now far more aware of the impact of WASH on the health and economic development of their communities.
[1] Data from the DHIS2 reporting system

ZHSP aims to improve the sanitation and hygiene status of 3.6 million people in rural Zambia. The programme directly contributes to the UK Manifesto targets of reaching 60 million people globally with improved sanitation, and overall the funding committed from DFID is £23.1 million. It began in 2012 and is implemented by UNICEF (in partnership with the Government of Zambia, and NGOs) and has used Community Led Total Sanitation (CLTS). It received a cost extensions in 2016, to help increase the programme reach, improve the sustainability prospects of the project, and to support the ongoing cholera response. A six month no-cost extension was agreed in January 2018 to re-programme some unspent funds respond to the cholera outbreak in Lusaka.

There has also been considerable, ongoing ‘upstream’ sector-level support by the ZSHP, including support to the newly created Ministry of Water Development, Sanitation and Environmental Protection (MoWDSEP), supporting the coordination of development partners in the WASH sector, and efforts to support WASH policy and strategy development. ZSHP funds earmarked for a post ODF sustainability study were re-programmed in January 2018 to help UNICEF respond to the cholera epidemic in Lusaka which escalated in December 2017. Whilst the cholera response work will be covered in the Programme Completion Review (PCR) later this year, initially reported activities[2] focus on Lusaka and include: distribution of chlorine for urban water supply treatment and for disinfection purposes at treatment centres and unprotected wells; provision of water quality testing kits; and supporting coordination of response activities within the WASH sector.
[2] Reported in the UNICEF progress report of 21st February 2018

Whilst the programme has made considerable gains in expanding numbers reached since the programme began, the main challenge is to ensure such gains are sustained after the project, and that the momentum for increasing the coverage to additional villages, chiefdoms and districts, is not diminished when the ZSHP phases out.

Lessons Learned:
1. Stakeholder focus and monitoring systems have been more effective as a tool for ‘expanding’ than ‘sustaining’ sanitation and hygiene improvements. CLTS typically aims at households constructing toilets using local materials, which in Zambia can be prone to weakness and gradual collapse. Sustained monitoring and refresher sessions are needed at community level to ensure households continue to build, progressively improve, and continue to use sanitation facilities;
2. Mandates for sanitation and hygiene in Zambia cut across line ministries, which can be barrier to the effectiveness and sustainability of the programme. Considerable efforts are needed to ensure inter-ministerial collaboration, particularly at national level, and would benefit from stronger Ministerial sponsorship;
3. Establishing specific community structures such as Sanitation Action Groups (SAGs), volunteers and a stand-alone monitoring system for achieving ODF can be very effective at rapidly increasing sanitation access. However, after the project, these ‘stand-alone’ structures and systems may be less likely to be sustained than those which are integrated into wider-scope and more permanent structures and systems such as neighbourhood health committees, Community Health Workers/Assistants;
4. In a programme of this size and scale, regular quantitative surveys are needed to check the ongoing effectiveness and impact of the activities, and realign approaches as needed, in real-time.
5. WASH programmes designed for health and nutrition outcomes should ensure adequate measures to break faecal-oral transmission pathways. In this case, ZSHP impacts may be undermined by the lack of inclusion of improvements in domestic water quality (through household water treatment, or source improvements). Although there have been some efforts made by the MoLG/MoWDSEP to ‘reward’ ODF communities with water points from within the wider national rural WASH programme.

Summary of recommendations for the next year (to end of September 2018)
1. Close progress monitoring on remaining activities: With limited time remaining on the programme, UNICEF should ensure no delays are incurred in the implementation of the remaining activities. Where programme targets are not on track to be met within the programme period, UNICEF should inform DFID by the end of June 2018, with a clear plan on how this will be addressed. Particularly at risk are the reconstruction of the school WASH infrastructure, or transition of all 68 districts for real-time monitoring to ‘phase 3’ (where they can manage the RTM system without AKROS support).
2. Ensure adequate VFM tracking: UNICEF should strengthen monitoring and analysis of VfM metrics, to provide DFID with the data ready for the PCR, and to be included in the final UNICEF programme report. UNICEF should provide DFID an update by the end of April as to their intentions for tracking VFM in the ZSHP.
3. Accelerate efforts for post-project sustainability: UNICEF should accelerate efforts to build foundations for post-programme continuity and sustainability, including: convening high-level meetings between MoWDSEP, MoH and MoCTA (not necessarily all together) agreeing institutionalisation of certain project structures and systems (by the end of June); convening stakeholders from district to national level to reflect on learning on the programme, and to develop post-project action plans and budgets (by the end of June); and advocate for inclusion of activities (including RTM) in the annual budgeting cycle for 2018 (and track allocations by the end of September); aim to support the government launch the ODF Strategy[3] (by the end of July[4]) and gain high-level political support.
  [3] Or if a strategy is not possible to launch before the overarching policy, consider revising to a ‘Campaign’ or similar
  [4] Although it is acknowledged that the actual timing will be determined by the Government, UNICEF should actively advocate, push for and support the government to meet these timeframes
4. Analyse sustainability and impact using secondary data: UNICEF to support the relevant ministries to analyse the sustainability and impact/outcomes of the programme, using existing secondary data[5]. The outcomes of this should be presented during the convening of stakeholders (listed above – by end of June), and should inform the finalisation of the upcoming sector strategies and policy[6].
  [5] Including (for example), but not limited to; impact of school WASH on education outcomes; impact of CLTS/BCC activities on health outcomes; ongoing sustainability of sanitation and hygiene service levels in the communities post ODF declaration; and the ongoing performance of the RTM reporting and verification system post-ODF certification. Whilst the analysis of such datasets may have considerable limitations, it should still be possible to obtain relevant and valuable broad trends.
  [6] Specifically the WASH policy, ODF strategy and BCC strategy.
5. Review ZSHP lessons learned and disseminate widely: As the largest rural sanitation Zambia has ever had, and one of the largest in the region, the ZSHP learning should be captured and disseminated at the district, national and global scale by UNICEF in the final quarter of the programme. Lessons should feed into the upcoming sector strategies and policy. This annual review has also identified a series of recommendations for the wider WASH sector and these are presented in a separate document.
6. Meeting to discuss implications of this annual review: A meeting should be held between DFID and UNICEF to discuss the implications of the annual review recommendations and agree actions, by the end of March. The outcomes of this meeting should be documented (to allow reference during the PCR process), particularly noting any modification to the recommendations or timeframes proposed in this review document herein.

A. Introduction and Context

DevTracker Link to Business Case:
DevTracker Link to Log frame:	7690849

At the time of programme design, access to improved sanitation in rural Zambia was just 33% (JMP 2011 data), diarrheal diseases accounted for 18% of under-five child mortality (ZSHP Business Case 2011), and rates of stunting were at 46% (ZSHP baseline survey, 2014). The ZSHP was an ambitiously designed programme, aimed at helping the Government of the Republic of Zambia (GRZ) to achieve their MDG targets on WASH. The five outputs of the ZSHP are:
3,600,000 people have sustained access to improved sanitation facilities
- 1,000 schools have appropriate sanitation facilities including hand-washing facilities, and soap available; with hygiene promotion and management system.
- National, provincial and districts level administrations have capacity to plan, implement and monitor sanitation promotion (including cholera emergency preparedness and emergency response);
- Chiefdoms with difficult soil conditions maintaining active and accredited service providers enabled to respond to public and private demand for sustainable latrines;
- Useful learning is drawn from implementation and M&E on sustainability of rural sanitation programmes and quality of behaviour change interaction.

With an original budget of £19 million from DFID and completion date of March 2016, in 2015 the programme received a cost extension of £4.3 million to run until the end of March 2018. This cost extension period is referred to as ‘Phase 2’ of the ZSHP, and aimed to help complete the ongoing activities of the project, added a further 600,000 people for sanitation and hygiene targets, and put a focus on sustaining gains made. In January 2018 DFID agreed to an additional no-cost extension, allowing time for the completion of remaining activities, and also reprogramming of funds earmarked for the programme Post ODF Sustainability Assessment (POSA)[7] to cholera response activities for the October 2017 Lusaka cholera outbreak.
[7] The POSA was envisaged as a large, 18-month long post implementation monitoring study, to be commenced from March 2018.

Overall, progress in terms of increasing access to sanitation and hygiene facilities has been good. Progress to school sanitation targets has been slower due, in part, to delays in approvals for toilet designs with the Ministry of General Education (MoGE). Sustainability checks and “end-line / impact” surveys were conducted by independent firms in 2016, with reports released in 2017. These highlighted improvements made and also various challenges in the likely effectiveness and sustainability of the programme.

The major areas of work in the programme during this annual review period have included: training additional masons for sanitation marketing activities; scaling-up the Real Time Monitoring (RTM) system; ongoing Behaviour Change Communication (BCC) activities; capacity building of stakeholders at the chiefdom, school, district, province and national levels; and school WASH infrastructure construction. There was also technical assistance provided to the MoWDSEP, and support to the coordination of the Cooperating Partner (CP) coordination platform, and dialogue on joint sector initiatives such as the WASH Policy and Joint Sector Review.

The number of Implementing Partners (IPs) has progressively reduced on the programme. During the reporting period UNICEF had implementation contracts with two local NGOs on school WASH and with AKROS on a wide range of project activities[8]. UNICEF also seconded consultants into the MoWDSEP and MoCTA at the central and regional levels as well as channelling funds to national, district and provincial authorities to undertake specific activities[9].
[8] AKROS’s work included: Real Time Monitoring (RTM) – conduct trainings and equip district staff and traditional leadership in targeted districts to monitor and report on School-Led Total Sanitation (SLTS) (including implementation of Education Management Information System - EMIS pilot), Community-Led Total Sanitation (CLTS) and Hygiene interventions/indicators within respective areas; conduct training of masons in 65 chiefdoms; train district builders on RTM to submit periodic reports on sales, new latrines built; facilitate and or work with provincial and district teams to convene monthly coordination meetings; carry out a mapping exercise in 10,000 transition and expansion villages; implement sanitation and hygiene facilities in targeted schools (included both hard and soft ware).
[9] These activities include monitoring, trainings and administration.

The project is being implemented against a backdrop of ongoing sector reforms, and a shift in responsibilities for WASH from the Ministry of Local Government (MoLG) to the newly formed MoWDSEP. The MWDSEP was established in the last quarter of 2016 and through 2017 was in the process of appointing staff and defining institutional activities, strategy and roadmap. Under MWDSEP, the recently formed Department of Water Supply and Sanitation provides an institutional home for WASH. There have been noticeable delays in the recruitment and placement of key staff (at both national and sub – national levels) in line with the Department’s organogram. Ongoing staff changes at the Ministry of Health’s Department for Health Promotion and Social Determinants have had a negative impact on continuity of planned actions. The department has had three different Directors since the last review.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment: The Impact Survey was released during this review period (July 2017). It notes that whilst there has been limited impact on reduction of diarrheal disease[10], there have been significant reductions in stunting and wasting rates[11].
[10] Diarrhoeal disease impact is often a difficult indicator to measure changes in, giving confounding factors, seasonality, etc
[11] The Impact Survey report mentions that the findings on limited impact on diarrhea, but impact on stunting, is similar to the findings from a CLTS study in Mali

Excerpt from the 2017 Impact Evaluation Report
‘The overall prevalence of severe stunting of 32.4% at baseline (2013) was significantly higher than the level of 18.2% at end-line (2016) (aPR=1.86; 95% CI: 1.59 – 2.18). The overall prevalence of wasting of 14.1% at baseline was also significantly higher than at end-line (7.4%) (aPR=2.07; 95% CI: 1.60 – 2.68)’.

According to the 2017 Impact Survey Report, The Impact Survey was undertaken in 2016, and since then considerable efforts have been made to increase behavioural change activities, particularly targeting handwashing practices, so the outcome indicator may have since improved.

There have been some differences between findings from the impact survey and the datasets reported in the RTM system. This may well be due to different classifications on what is defined as ‘improved’, or indicators for handwashing (the definitions used in the Impact Surveys were relatively ‘strict’, and may have used different classifications for ‘shared’ toilets), which makes the datasets challenging to reconcile. The Phase 2 POSA will not now provide a final independent verification of reported data, and final outcome and impact targets will not be measured at the end of the programme which is a limitation.

Overall output score and description

This review scores progress made by February 2018 against January 2018 milestones.

The overall weighted output score is A – met expectations.

Whilst some key targets were exceeded (such as schools with improved sanitation facilities, and number of new users of sanitation and ODF villages), a number were not met and were not on track to be completed by the expected programme completion date of March 2018. These include, for example, work on sector strategy, the reconstruction of collapsed toilets, and the scaling-up and transition of RTM system in the districts. Most activities are on track to achieve targets by the extended deadline of September 2018 however. There are also a number of recommendations from the previous annual review which are delayed in their implementation.

There have been a number of challenges affecting the programme’s ability to complete activities, many linked to the hiatus created in the creation and establishment of the MoWDSEP, and staff turnover in the MoWDSEP, the MoH and at the local level. Some delays may also be attributable to staff turnover in UNICEF, and the competing priority of the ongoing cholera response. Whilst the no-cost extension was only agreed in January 2018, there was an expectation of some form of time extension of the ZSHP from as early as July 2018[12] which seems to have affected planning on UNICEF’s part.
[12] DFID had formerly discussed the potential of funding for a £12m business case addendum for peri-urban sanitation, which would have allowed the continuity of some of the ZSHP activities. When a decision was made in October 2018 not to proceed with this, the discussions commenced for a no-cost extension.

Table 1: A Summary of Output Scores and Justification.

Output	Score	Weighting	Comments
1	A	50%	According to RTM data, UNICEF has exceeded key targets relating to new users of sanitation, and number of communities declared ODF. However, targets for the number of new users for handwashing, and behaviour change communication targets were not achieved, and certain recommendations from previous annual reviews have been delayed or seen limited progress (such as the engagement of MoH for RTM processes and data analysis, and also the development of the programme transition (exit) plan).
2	A	20%	UNICEF has slightly exceeded the targets for infrastructure of WASH in schools (1021 completed against a target of 1000). Progress on the reconstruction of toilets in 50 schools has been limited.
3	B	10%	There has been limited progress in finalising the ODF Strategy, and in the scaling and ‘handover’ of the RTM system to 68 districts is delayed. Overall, the sustainability of the RTM monitoring system is not yet secured. However UNICEF has continued to provide considerable technical assistance to the recently formed MoWDSEP, and exceeded the target on the number of cholera preparedness plans developed.
4	B	10%	The programme just missed the milestone targets for the number of chiefdoms with masons. However, the main finding is that UNICEF did not take the opportunity to reflect on and modify the approach for Sanitation Marketing, despite sales figures suggesting modifications were needed.
5	A	10%	The reports from the Phase 1 Impact and Endline surveys, and also the 3rd Sustainability Check reports were finalised and disseminated (albeit many months after the field surveys were completed). The POSA has been cancelled, and there has been limited considerations on how to analyse the existing RTM datasets to review and report on sustainability, and how to reflect and disseminate lessons learned on the project with the wider sector.
Overall	A	100%

Key Success Factors:
- Strong enthusiasm and commitment from traditional leaders such as the Chiefs and village headmen in many of the project areas, and also the motivation of district and provincial government staff. The ongoing ‘championing’ of the ODF campaign by the Ministry of Chiefs and Traditional Affairs (MoCTA) has also helped ensure sanitation is ‘on the radar’ of traditional leaders nationwide.
- Good coordination and collaboration of line ministry staff at the district level, albeit with less inter-ministerial coordination at higher levels of Government.
- The RTM system continues to help local and national stakeholders track progress towards targets, and can help address issues arising, in real-time.
- The Community Health Assistant training centre in Mwachisompola: helped with expanding the skills of CLTS to a wider number of people across the country
- The recent creation of a line ministry with explicit mandates for the sector (MoWDSEP), and also strong engagement from the Ministry of General Education (MoGE) on issues such as Menstrual Hygiene Management.

Key Challenges:
- The ongoing institutional reform has led to delays in implementation whilst the new MoWDSEP becomes established, recruits staff and wishes to review strategies that were developed and finalised in the former MoLG. More generally, UNICEF has commented that as each key programme decision needs to be made by or with the endorsement of the MoWDSEP, this has slowed progress. One example that directly affected the programme was the long time period taken for the Ministry to decide on the final set of seven districts which were to be added to the ZSHP, to replace districts in Western Province which have been absorbed by an incoming AfDB funded rural WASH programme.
- There has been considerable staff turnover in UNICEF during the review period. UNICEF had a change of programme officers responsible for the ZSHP, and the incoming officer was also tasked to be the acting Chief of WASH in the transitional period until the current Chief was in post. This turnover may have led to some breaks in institutional memory, and continuity. There were also staff changes within the DFID team. An Infrastructure Adviser will take over the SRO role from 1st April 2018.
- The cholera response, development of a new funding proposal for DFID for peri-urban sanitation, and response to refugee camp WASH interventions, all posed additional demands on the ZSHP team’s time during the review period.
- Staff turnover at the district level and also in the schools has undermined efforts on training/capacity building at the local level, and affected institutional memory.

Has the log-frame been updated since the last review?

Yes. Indicators to remove the Post Open Defecation Free Sustainability Assessment (POSA) and add cholera response activities were updated in January 2018 for the no-cost extension. Some milestones for January 2018 needed finalising. The revised log-frame also re-calibrated milestones according to progress, particularly in light of set-backs with the creation of the MoWDSEP (indicators 1.2, 3.1, 3.2).

Following the AR the log-frame should be clarified to show that data is being collected on cumulative new users which may or may not reflect status at any one time rather than sustained users. The achievement of some outcome/impact indicators will now not be measurable now that the final end-line post-ODF sustainability survey will not be done, although it may be possible to collect such information in future through the upcoming DHS survey.

## C: DETAILED OUTPUT SCORING

Output 1	3,600,000 people with sustained access to improved sanitation facilities
Output number per LF		1.	Output Score	A
Risk:		Minor and unlikely	Impact weighting (%):	50%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress (UNICEF data) as of 28th February 2018
1.1: Number of additional people with sustained access to an improved sanitation facility through DFID support to UNICEF	3,600,000	Exceeded (by 5%) / A total cumulative number of new users reported through the RTM system is 3,776,886 across 68 districts. / This data represents cumulative numbers of new users, rather than representing numbers of people with sustained access, as discussed below.
1.2: National Sanitation and Hygiene Behaviour Change Communication strategy and plans established with MLGH and implemented, with both community level interventions and mass media components	National sanitation and hygiene BCC strategy and plans established and implemented	Not met / The new MoWDSEP wished to revisit all former strategies developed under the former MoLG. The Ministry is also placing a stronger focus on developing the WASH Policy, than sub-strategies but progress has been slow. A Technical Working Group (TWG) has been established in September 2017, and has met twice to date. The TWG has requested a consultant to support the updating and finalisation of the strategy, and the ToR has been developed. Procurement is due to start in March.
1.3: Number of verified Open Defecation Free (ODF) villages achieved through DFID support	11,000	Exceeded (by 5%) / 11,584 villages, 42 chiefdoms and 4 districts have been declared ODF.
1.4 Number of people reached with hygiene promotion activities focusing on the importance of using latrines and hand-washing with soap or ash	7,000,000	Moderately not met (95%) / 6,670,914 people reached (not including those reached by Cholera messaging). This has included mass media (TV, community radio), school and community/market messaging using social marketing approaches, and through activities during global handwashing day.
1.5 Number of people with sustained access to hand-washing facilities	3,600,000	Moderately not met (95%) / 3,411,361 reported through the RTM system[13]. As with indicator 1.1, this data tracks cumulative figures, rather than sustained usage.
1.6 Number of chiefdoms in the 68 districts with an evidence based, feasible Hand Washing action plan that is reviewed once per year	80	Not met (87.5%) / Chiefdom orientation sessions have been done for 115 chiefdoms, of which 70 have developed handwashing plans to date. Handwashing actions are also incorporated into the national ODF Strategy (see 3.1)
[13] Of note the end-line survey found much lower rates of handwashing facilities, so the basis of calculating and defining this indicator needs to be clarified.

Key Points

The field visits of this review identified that the chiefs which were met were very engaged in efforts to achieve ODF, and were keenly engaging their village headmen and community champions to drive forward progress in their chiefdoms.

The RTM system criteria which define ‘improved’, ‘adequate’ sanitation, ‘ODF’ and ‘functioning handwashing facilities’, need to be clarified, to ensure consistency between stakeholders and that these are consistent with sector (and SDG) definitions. This includes what was classified as improved vs shared, etc. The precise means by which output indicator 1.5 is calculated should be clarified and this should be compared with the criteria used in the impact survey. Definitions used between the RTM and the baseline/end-line surveys should be compared, to identify possible causes for discrepancies in findings[14]. It is also noted that the current reporting on indicators 1.1 and 1.5 focusses on cumulative ‘new users’, and may not adequately track whether the users are ‘sustained’.
[14] This could include for example comparing RTM data for the survey enumeration areas, covering the same period as the end-line survey

Summary of responses to issues raised in previous annual reviews (where relevant)

UNICEF should educate leaders such as Council Chairpersons/Secretaries, District Commissioners and Area Members of Parliament on the CLTS programme by December 2017.

Ongoing: UNICEF has ensured sanitation is part of the standard agenda in the House of Chiefs meetings, and has achieved considerable ‘institutional championing’ within MoCTA on achieving ODF chiefdoms. UN Volunteers in five provinces have produced newsletters on sanitation, helping to raise awareness of key stakeholders, and UNICEF has provided a briefing statement on WASH to the National Assembly – an influential forum of politicians at the apex of central government.

UNICEF should engage MoH to enhance cooperation with MoWDSEP, to formalise the EHT role in RTM, and encourage MoH to use the RTM data for cross analysis with their disease surveillance data.
Limited progress: Efforts to bring the Ministries together have been hampered by issues of inter-ministerial fragmentation, the ongoing institutional reform of the MoWDSEP, and the fact that there has been considerable staff turnover at director level in the respective WASH departments of the two Ministries. Further efforts are needed in this area moving forwards (see recommendations).

UNICEF should produce a phase out plans by June 2017 with clear role transfer accompanied with timelines on how the government will take over the running of the programme and transform it into routine service delivery government programme.

Delayed, ongoing: A transition plan was developed for the RTM, which is helping to guide the ongoing work of capacity building and handover at Ministry to district levels. UNICEF has discussed the idea of a ‘Sustainability Compact’ with the MoWDSEP (but not other Ministries) using an example from Liberia, but has not started developing one specific for Zambia to date. Therefore the production of a ‘transition plan’ as per recommendations is delayed, and needs to be accelerated. UNICEF has been actively advocating for the creation of a budget line and budget allocation for rural sanitation (not specific for RTM but sanitation generally), supporting institutional capacity in MoWDSEP to take ZSHP activities forward, and ensuring sanitation plans are embedded in sector policy and strategy (e.g. in the updated RWSSP, in the ODF strategy, etc).

Recommendations

1. Finalise the transition plan: UNICEF to accelerate progress on post-project plans and budgets of the Ministries (not only MoWDSEP), provinces and districts. Annual recurrent costs to sustain activities should be clear to all levels (including costs to sustain the RTM system, and undertake post ODF verification and re-mobilisation), and efforts are needed to ensure these are budgeted for in the next annual budgeting cycle. UNICEF to track and report on budget allocation at the different levels by the end of the project. Stakeholders from each level should be convened by the end of May to discuss and develop a plan for post project continuity, and UNICEF should produce a written update of this to the respective Ministers/PS’s and to DFID by the end of June. At the convening meeting, it would also be a good opportunity to broadly discuss lessons learned from the programme.
2. Engage the MoH: UNICEF to accelerate progress on recommendation 2 above, in convening a minister and PS-level meeting between MoWDSEP and MoH by the end of April (and earlier at Director-level). Issues to discuss would include: options and relevance of institutionalising ZSHP structures and functions into permanent MoH-linked structures[15]; who and how the two Ministries plan and budget for ongoing activities, especially where MoH staff and structures are used at the district and sub-district level; how to effectively utilise and cross-analyse RTM monitoring data with health datasets. UNICEF to support MoH to review and update the ToRs/job descriptions to help the institutionalisation process, and to support the communication to those affected by the change (e.g. provinces and districts).
  [15] Such as integration of SAG activities into neighborhood health committees, integration of community champion activities into CHAs or CHWs, integration of RTM data into MoH monitoring systems, integration of some functions within the Department of Health Promotion, etc.
3. Confirm definitions used in RTM and end-line survey: UNICEF and AKROS should clarify their definition of ‘improved’ / adequate sanitation as per reported RTM data, and confirm how indicator 1.5 is calculated, and ensure these definitions align with the log-frame indicators (and wider sector understanding of ‘improved’ sanitation, JMP monitoring, etc). UNICEF to determine how to also report on ‘sustained access’ as per the log-frame indicators, and contrast definitions used between the RTM data and the end-line survey, to identify possible causes for discrepancies. UNICEF to send an update of the outcomes of this review to DFID by the end of June.
Output 2	1,000 schools have appropriate sanitation facilities including hand-washing facilities and soap available, with hygiene promotion and management system
Output number per LF		2.	Output Score	A
Risk:		Minor / unlikely	Impact weighting (%):	20%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress ( UNICEF Data and text)
2.1 Number of additional schools that have appropriate sanitation facilities including hand-washing facilities, and soap available; together with an appropriate management system and hygiene promotion	1000	Exceeded (102%) / 1021 schools reported completed. A total of 50 schools require toilets to be reconstructed, which is ongoing.
2.2 Number of Provincial Education Offices with a school WASH Action Plan reviewed and reported upon on a yearly basis	10	Met / Plans were developed during the previous reporting period. WASH plans for all ten Provinces have been harmonized in this reporting period, including those developed during the previous reporting period, which now include school water supply, sanitation, hygiene and MHM.
2.3 Number of piloted schools with Education Statistics reported through real-time monitoring system (DHIS2)	50	Met / Completed during the previous reporting period. The schools have continued to report using DHIS2, and some additional support and trainings were provided during the period. Scaling-up has not yet commenced.

Key Points

Whilst school targets have been exceeded, fifty schools still need to have their toilets rebuilt to address collapsed units (linked with earlier design standards)[16]. UNICEF should assess whether there are any health and safety risks for other toilets of the same design and communicate guidance to schools if necessary. This will be discussed in a meeting with UNICEF and DFID shortly after this review. Progress towards this reconstruction has been slow, due in part to the procurement process[17], and there is a risk that UNICEF is may not complete this by the end of September.
[16] Once completed this will bring the total number of completed schools to 1071
[17] Initially UNICEF intended to procure contractors, but this was decided to be too risky for quality assurance, and expensive, so NGOs were instead contracted.

As the project has implemented the school WASH in phases, different schools have different ‘packages’ of infrastructure and training. Anecdotal findings from the fieldwork in this review suggest good quality work has been done, and that teachers, students and the Parent Teacher Associations (PTAs) are committed to sustaining gains. The innovative activity (and facilities) for mass handwashing appeared to be continually conducted in the schools visited, whereby students were integrating handwashing into their daily routine. The EMIS system is also helping to increase efficiencies in school monitoring in Namwala District, and is stimulating improvements in WASH facilities in non-target schools. There has also been replication of certain activities in non-target schools by the district authorities and PTAs, such as school toilet construction, provision of handwashing facilities, and considerations for Menstrual Hygiene Management (MHM). UNICEF should ensure the replication of good practices observed in the ZSHP is reported on as part of its wider lessons learning activities of this programme. UNICEF has supported the development of national MHM guidelines, and has started rolling these out in some provinces/districts, although this may not be rolled out across all project areas by the end of September.
Summary of responses to issues raised in previous annual and mid-year reviews

Extend the timeline for the delivery of the school latrine construction to September 2017.

Delayed, ongoing: Whilst UNICEF has achieved the target of 1000 schools through additionally targeted schools using own funds, as at 10th March, procurement had been done, but they have not started the reconstruction at 50 schools (partially delayed by the late rainy season).

UNICEF to work with the MoGE to officially communicate the endorsed low cost design to all provinces, districts and schools by end of August 2017.

Ongoing: MoGE decided to review the design for government schools and then launch both designs (the low cost design for community schools and the design for government schools) together. The design for the government schools was endorsed in September 2017. They plan to disseminate both designs through the provinces and partners during second quarter of 2018.

UNICEF to ensure UK aid branding in all programme supported schools by end of August 2017.

Ongoing: Signboards have been provided to schools / IP’s for 781 schools, and installation is ongoing. Other signboards have been provided to MoGE/DEBS or held by UNICEF, to be delivered to schools during monitoring visits.

UNICEF to provide Technical Assistance to MoGE for the Education Management Information System based on experience from the Namwala pilot project.

Delayed/ongoing: Work has been done on analysing and documenting experiences in EMIS. This should be fed into discussions on future EMIS requirements which the World Bank is supporting as part of their ZEEP Education programme.

Recommendations
1. Ensure a complete package in all target schools: By the end of the programme, UNICEF should ensure that all target schools have received the ‘complete package’ in terms of toilets, Kalingalinga buckets, mass handwashing facilities, and associated trainings to teachers and DEBS. UNICEF should continue to support the MoGE to access funds for the MHM guidelines and toolkit for mass hand washing facilities to be rolled out across all provinces and target districts. .
2. Report progress on remaining 50 school reconstructions: UNICEF to update DFID every two months on progress to completion. UNICEF to assess any health and safety risks of toilet collapse and issue guidance to schools if required.

Output 3	National, provincial and district level administrations have capacity to plan, implement and monitor sanitation promotion (including cholera preparedness and emergency response).
Output number per LF		3.	Output Score	B
Risk:		Major/possible	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s) / (new for no cost extension)	Milestones	Progress 2016-2017
3.1 The National ODF Action Plan is reviewed, revised and reported upon annually	Technical Working Group formed and procurement process initiated.	Met / Two TWG meetings held on updating the strategy with the SDGs, and ToR for consultant to finalise the strategy developed. Procurement to start in March
3.2 Advocacy and technical support provided to create and sustain WS&S Directorate within MLGH	MoWDSEP Organogram developed and approved by Cabinet Office	Met / The 2017 milestone was extended to January 2018, reflecting the slow progress of establishment of the MoWDSEP, and was met.
3.3 Number of target districts with operational real-time monitoring system to report on rural WASH interventions	68	Not met (90%) / 61 districts submitting monthly reports through RTM. Delays incurred in MoWDSEP/AfDB confirmation of 7 new districts (described below)
3.4 Number of target districts with operational, multi-sectoral planning, prevention, response and coordination mechanisms against Cholera epidemics.	20	Exceeded (135%) / A total of 27 plans were developed together with the Disaster Management & Mitigation Unit of the Office of the Vice President.
3.5 Number of water points where chlorination levels are enhanced to ensure free chlorine residual of 0.5 mg/l	300 by end Sept 2018	Not scored during this annual review - to be measured at end Sept 2018.
3.6 Number of people who benefit from the improvements in the water supply service levels in the target areas	TBD (after the scope of the works/cost estimates are approved by DFID’s infrastructure advisor)
3.7 Number of people reached with messages on safe hygiene practices	100,000 by end Sept 2018
3.8 Number of schools provided with basic emergency WASH package (to be agreed with the Ministries of Health and Education)	50 by end Sept 2018

Key Points

Whilst most log-frame milestone targets have been met, sustainability continues to be a major issue, and there have been delays on issues such as ensuring the transition of RTM activities, and the completion of previous annual review recommendations.

UNICEF has provided considerable and ongoing Technical Assistance (TA) to the new MoWDSEP, such as the secondment of three staff into the Ministry, giving inputs to the strategic and capacity development plans of the Ministry, and collaborating with GIZ (and the wider Co-operating Partner group, which UNICEF also supports), on issues such as the updating of the national WASH policy, and the organizing of a Joint Sector Review. UNICEF also provided TA to MoCTA during the reporting period, but to date in the ZSHP no embedded TA has been provided to the MoH. There were also UN Volunteers stationed in five provinces, helping to raise the profile of sanitation and build capacity of provincial authorities.

The achievement of indicator 3.3 has been delayed due to the incoming of an African Development Bank (AfDB) funded programme in Western Province, which led to the MoWDSEP requiring the ZSHP to shift from Western Districts to seven new districts. AKROS has reported that less than half of the 68 districts are at a stage where they can operate and maintain the RTM system without AKROS support. It is unlikely that the programme will achieve the full transition to all districts by September. AKROS report that progress has been impeded, in part, by challenges in financial disbursements from UNICEF.

As the programme nears closure, there are concerns on the sustainability of the RTM system developed under ZSHP. UNICEF has supported a technical working group to discuss this, although the number of meetings has been limited, and it is unclear if MoH is actively involved. Findings from this annual review suggest that prospects for sustainability will be increased if the RTM system is modernised (e.g. a shift to an app which can be used on personal phones rather than a system reliant on centrally procured devices), expanded in scope (to cater for the wider reporting needs of water and/or health, and e-governance initiatives), and institutionalised (especially considering the role of MoH at various levels). UNICEF is collaborating with GIZ to support sector dialogue on a WASH Sector-wide Management Information System (MIS), and a ToR is under development for a study on this. The positive (and well documented) impact that the RTM system has had on accelerating and cost-reducing the gains made to date on the project, and also the ‘culture of reporting and analysis’ it has establish for rural sanitation, has made RTM investments very useful to date, even if another platform is selected by the Ministry in the future for national roll-out.

Progress on updating and finalizing the ODF strategy has been slow, partly because the MoWDSEP wished to re-validate documents developed in the former MoLG. This annual review identified that there may not be widespread awareness of Cooperating Partners (CPs) on the ODF Strategy process, and be seen by some CPs as a ‘UNICEF/DFID/project’ rather than national initiative. Recommendations are stated below to address this.

Additional note: Cholera emergency preparedness and response
ZSHP funds earmarked for a post ODF sustainability study were reprogrammed in January 2018 to allow UNICEF respond to the ongoing cholera epidemic. At the time of this review, the log-frame targets for the cholera response were not fully finalised, and a number of activities had started relatively recently before the review itself. Whilst the response work will be covered in the Programme Completion Review (PCR) later this year, initially reported activities[18] include: distribution of chlorine for urban water supply treatment and for disinfection purposes at treatment centres and unprotected wells; provision of water quality testing kits; and supporting coordination of response activities within the WASH sector (WASH, and WASH in Schools coordination groups).
[18] Reported in the UNICEF progress report dated 21st February 2018

Summary of responses to issues raised in previous annual and mid-year reviews

UNICEF to conduct a gap analysis and immediately provide Technical Assistance to MoWDSEP to support establishment of the new Ministry by the end of August 2017.

Met, ongoing: Whist a formal plan for capacity building was not developed, UNICEF has provided considerable TA to the MoWDSEP, as outlined in the narrative above. UNICEF has agreed areas of collaboration and capacity support with MoWDSEP, documented through an exchange of letters.

The programme through UNICEF should support the transition of the RTM/DHIS2 to the new Ministry with clear roles and responsibilities and ensure RTM system is working well in all 68 districts by December 2017.

Delayed, ongoing: The programme is not on track to transition RTM in all the 68 districts, but is supporting the MoWDSEP to develop their capacity at the central level, and has trained provincial ‘coaches’, so there potential for the MoWDSEP to continue in the transition activities. This will depend on their (MoWDSEP) ongoing motivation and resources to do so.

UNICEF should support capacity building of specific MoWDSEP staff to carry out WASH data analysis and be able to share across line ministries for usage in planning, policy debates and discussions at district, provincial and national levels by December 2017.

Partially met, ongoing: Support is being provided to MoWDSEP as described earlier. However the analysis (especially on ongoing system performance and sustaining service levels – not only tracking ‘new’ users) and sharing of data between ministries (especially MoH), has been limited to date. This review suggested that cross-analysis between RTM and health datasets is weak at district, provincial and national levels.

Recommendations

1. Evolve and institutionalise RTM system: UNICEF to support the MoWDSEP and MoH to explore wider national information management system requirements for WASH and whether/how the RMT system supported by ZSHP should fit into that, and/or how indicators which the RTM system is tracking could be integrated within wider government monitoring processes.
2. Finalise and launch the ODF strategy/campaign: Progress on supporting the Ministry to finalise and launch the ODF strategy should be accelerated, and the scope should be expanded to focus on ‘achieving and sustaining ODF’. Ideally this would be launched by the President or senior politicians, to garner momentum in the wider sector for ODF outside of the project. Other CP’s should be encouraged to join in the nationwide ODF initiative and DFID Zambia could provide high-level support to this process as part of its exit from the rural sanitation sub-sector. Where the MoWSDEP is reluctant to release a sub-sectoral strategy before the wider WASH Sector Policy, UNICEF could otherwise support the development of a nationwide ‘Campaign’, which may be easier to rally politicians around. UNICEF should also take the opportunity (suggested by MoCTA in the stakeholder meeting during this annual review), to use the upcoming House of Chiefs meeting in May to garner further momentum on the ODF strategy and discuss post project sustainability issues.
3. Clarify and report on RTM transition targets: UNICEF to confirm what is realistically achievable for the project in terms of transition of the 68 districts to ‘phase 3’ by the end of the programme. Where targets will not be met, a clear plan needs to be developed and agreed by concerned stakeholders, and sent to DFID for agreement by the end of June.

Output 4	Small scale service providers – including individuals- in targeted rural districts are enabled to supply sanitation and hygiene services in response to household demand
Output number per LF		4.	Output Score	B
Risk:		Minor but possible	Impact weighting (%):	10%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicators	Milestones	Progress
4.1 Number of chiefdoms with difficult soil conditions with at least 2 active and accredited service providers enabled to respond to public and private demand for sustainable latrines	65 (target increased from 50 in log-frame revision)	Largely Met (98%) / Achieved 64 chiefdoms and trained cumulatively 575 masons, of which 231 are active. 139 masons trained during the reporting period.

Key Points	Table 2. Toilet sales through trained masons
Period	Cumulative toilet sales
2014/15	500
2015/16	1097
2016/17	1262
2017/18	1516

The project has trained a total of 575 masons, including 139 this year as part of the Sanitation Marketing (San Mark) part of the programme. Total sales reported have been relatively low in comparison to the total number of ‘new users’ of sanitation, although it is acknowledged that getting reliable figures on sales is a challenge.

Whilst there are a small number of masons which have sold over 100 household toilet products to date, most are yet to sell more than a few, if any. The strategic approach to San Mark has not been modified in the final year, despite limited sales figures reported in recent years. UNICEF focussed efforts this year on training more builders, to meet the targets (as set in previous annual reviews) rather than adapt this component. Pit collapse is a widespread issue, and the extent to which San Mark, and the currently promoted range of products has been a scalable solution, appears to be limited.

Summary of responses to issues raised in previous annual review
UNICEF, MoLG, MoWDSEP to continue to strengthen networks and coordination with artisans’ across the 65 chiefdoms during phase 2 of the programme; this will include working with chiefs to involve masons in traditional chiefdom ceremonies and strengthen linkages amongst masons networks and the chiefdom leadership. (on-going in 2017)
Ongoing: Support for traditional chiefdom ceremonies ongoing (15 chiefdoms out of planned 25 chiefdoms supported since Jan 2017). During these ceremonies, demo sites (to show case latrine designs and options) and training of masons form key component of the celebrations.
UNICEF to support MoWDSEP in attaining approval of the revised curriculum under TEVETA. This will enable improved coordination and scaling-up of the training programme through TEVETA certified training centres across Zambia (to be done in the second quarter of 2017) (ongoing).
Met, ongoing: Three TEVETA documents (the job profile, the curriculum chart, and the syllabus) for Sanitation Masonry were developed in 2015/16, feedback has been aggregated and incorporated from all of the stakeholders at stakeholder workshop in April, 2017. The documents are now with MWDSEP for final endorsement and further discussion with Higher / technical education officials.

Recommendations
1. Learn lessons from San Mark, and reflect these in sector strategy/policy: Convene a stakeholder meeting to review experiences of San Mark in the ZSHP and other initiatives in the sector by June. Utilise the expertise of UNICEF regional and global levels for relevant experiences elsewhere. Review and learn lessons, and ensure these are captured in the ODF strategy/WASH policy being aware that it is too early to use the ZSHP approach as a ‘blueprint’.
2. Link masons with customers using community radio: As discussed with ZAMCOM during the review, utilise some of the local remaining talk-show sessions to bring in masons, to explain how to construct durable latrines, and generate demand for their services.

Output 5	Useful learning is drawn from implementation and M&E on sustainability of rural sanitation programmes and quality of behaviour change interaction
Output number per LF		5.	Output Score	A
Risk:		Minor but possible	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
5.1 Impact assessment of the Programme is finalized and government and partners use the findings as they continue to develop and strengthen WASH policies and systems beyond	(revised) Final report for phase 1 validated and disseminated by December 2017	Met / Final reports presented to GRZ and project stakeholders, and findings reportedly fed into discussions in the updating of the second phase of the National Rural Water Supply & Sanitation Programme. UNICEF has reportedly released a management response which highlights recommendations and proposed actions.
5.2 Sustainability checks completed	3rd Sustainability check report validated and disseminated	Met / 3rd Sustainability Check finalised in September 2017 and disseminated to project stakeholders.
5.3 Post-ODF Sustainability Assessment (POSA) finalised	Not to be reported on due to fund re-allocation to cholera response.

Key points
‘End-line and Impact’ surveys were undertaken in 2016, which reviewed Phase 1 activities. With the cancelling of the POSA and Phase 2 end-line survey, there is limited ability to track changes made since 2016, nor to prove outcome and impact achievement, before the next DHS survey.

Whilst data collection was undertaken in mid-2016, the final validated end-line and impact reports were ready only in April and July 2017, respectively. This late finalisation meant there was less time to make programmatic adjustments within the time (and budget) remaining on the ZSHP. Whilst findings from the surveys informed the update of the national Rural Water and Sanitation services (RWSS) programme, the extent which the ZSHP was modified to address some of the important issues highlighted in the impact survey has been limited. Quantitative surveys could have be done earlier and more frequently during the programme, for rapid dissemination of findings and adaptation. Ideally UNICEF would have issued a management response to the reports.

The POSA was planned as a relatively large, 18 month study to be commenced at the end of the programme. This was cancelled and funds were re-diverted to the cholera response. Further consideration could have been given to a ‘mid-way’ option of a ‘lighter’ or ‘quicker’ sustainability review. Whilst there is currently a considerable dataset developed under the RTM, it is currently configured and analysed more for monitoring ‘expanding’ rather than ‘sustaining’ gains. It seems there has been limited considerations on how to use the existing RTM data to analyse sustainability issues, in the absence of a full POSA study.

Summary of responses to issues raised in previous annual
1. UNICEF to contract out the Post ODF (POSA) Assessment and deliver the final report by December 2017. Cancelled.
2. UNICEF to prepare the Terms of Reference for the Programme End-Line Evaluation and share with DFID for quality assurance by October 2017. Cancelled.
3. UNICEF to explore possibilities for further scaling up of the MHM component within the programme supported schools and share plans for execution with DFID by August 2017.
Met, ongoing: Through UNICEF Advocacy (and other partners), the MHM Focal point identified and is based under the Directorate of Planning and Information (under the School Health and Nutrition Unit). MHM Guidelines finalised and launched by GRZ. The Government has allocated ZMW 1 million for procurement and distribution of MHM materials. UNICEF has developed a funding proposal for MHM scale and submitted for a potential donor for consideration.
UNICEF to disseminate findings of the Impact Evaluation Analysis of Phase 1 to all key stakeholders by June 2017.
Achieved: UNICEF presented the findings to IPs, provincial and Ministry stakeholders involved in the project during the 2017 annual review meeting.

Recommendations
1. Demonstrate how the surveys have informed programme design: UNICEF to explain how the ZSHP has been adapted as a result of the learning from the sustainability checks and end-line/impact surveys (to send an update to DFID by end of May), and to ensure findings are adequately reflected on in the development of the BCC and ODF strategies, and the national WASH policy.
2. Analyse secondary sustainability and impact datasets: In the absence of large scale POSA or Phase 2 end-line surveys, secondary data could be quickly (and relatively cheaply) analysed to give indications on sustainability and impact[19]. UNICEF to support the undertaking this of this analysis, ideally to report outputs at the meeting where stakeholders are convened to discuss post-project sustainability plans (see earlier recommendation, by end of May). Where appropriate, findings should be presented for discussion in wider (not only ZSHP) sector forums.
  [19] For example reviewing RTM datasets for: the reporting system performance through time after ODF verification (e.g. rates of reporting, rates of verification, etc); whether service levels of sanitation and hygiene (e.g. use of lids, HWFs, etc) are sustained through time; ODF slippage rates, etc. To undertake basic assessment of impact, RTM datasets could be cross-analysed with MoH disease surveillance data. Education data (e.g. attendance) could be cross-analysed with school WASH intervention datasets. Whilst the analysis of such datasets may have considerable limitations, it should still be possible to obtain relevant and valuable broad trends.
3. Adapt RTM dashboard to track sustainability: Identify the means to adapt RTM monitoring and particularly analysis to track sustainability of the reporting system and service levels over time. Such and presented in Ministry reports and the dashboard in addition to cumulative targets.
4. Develop post-ODF monitoring and support protocol: Support the sector to develop (and disseminate) a protocol for post ODF verification monitoring, support and re-mobilisation. This should include details on who should undertake (and budget for) activities, frequency of community visits, etc. The roles of MoH, MoLG, MoWDSEP, and traditional leaders should be clear. This should be drafted by the end of July. The costs of these activities could be included in the 2018 budgeting process at all levels (and with the associated Ministries).
5. Review and disseminate learning from the programme: This programme was the largest initiative to date in rural sanitation in Zambia, and one of the largest in the Southern African Region. Learning should be collated and disseminated widely. UNICEF to undertake a review of learning and prospects of sustainability of the programme, and share findings at local, national and global levels.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The majority of the programme budget is attributed to CLTS and school WASH activities, as show in the graph below5.

No	Activities	Proportional spend of the total project budget expenditure to date
1	Community Approaches to Total Sanitation (CATS/CLTS)	42%
2	Sanitation Marketing	5%
3	School sanitation and hygiene	22%
4	Hygiene Promotion and Sustainability	6%
5	Sector Coordination	1%
6	M&E and Knowledge management	6%
7	Project support costs	10%
8	Cholera response	2%
	UNICEF recovery cost 8%	6%
	UNICEF recovery cost 7%	1%
	Total	100%

For CLTS, a key cost driver has been capacity building of local stakeholders, particularly supporting the scale-up of RTM, which has been a key focus of activities during the reporting period. It also includes the capacity strengthening of MoWDSEP such as through embedded TA, logistical support and workshops, and also training and support to the nationwide network of community champions through provincial CLTS coaches.

School WASH costs are predominantly infrastructure related, but also cover ‘software’ costs such as SLTS triggering, hand washing promotion and the work on menstrual hygiene management. As the programme relies predominantly on volunteers at the community level, and engages government staff to implement and follow many of the activities (without salary top-ups but does include allowances for workshops and field work), the programme is able to maintain a relatively limited implementation personnel budget.

The total expenditure to date on project support costs, and UNICEF recovery costs (items 7 and 8 in the table above) is 16.9% of the total programme expenditure. This is higher than the proportional amounts allocated for such costs in the original Business Case, which envisaged 13.4%[20]. However since the drafting of the Business Case, the Phase 2 cost extension increased the duration of the programme by two years, without major increases in the project targets. Therefore a proportional increase in support costs is not surprising.
[20] Business Case November 2011. This was for the ‘Phase 1 budget’ of £19,003,200, of which it included £1,300,000 for Programme Support Costs and 1,243,200 for UNICEF Cost Recovery.

VfM performance compared to the original VfM proposition in the business case

The table below shows UNICEF-reported figures relating to effectiveness, efficiency, and economy. It contrasts these with metrics calculated for previous annual reviews, and as presented in the original business case. These figures are interim as the most recent financial report had not been finalised at the time of the AR.

Table 4: VfM changes from 2014/15 to 2016/17
Type	VfM Measure	From Business Case	2014/ 15	2015/ 16	2016-17	2017-18	Comments
Effectiveness	Cost per new sanitation user	£ 1.85 estimated	£ 3.83	£ 2.20	£ 2.20	£ 2.00	Based on CLTS expenditure, excludes sanitation marketing, and includes proportion of overheads. The change in cost per new sanitation user has mainly dropped because of the readjusted applied 1.52USD/GBP exchange rate (weighted average exchange rate over the programme duration)
	Cost per person reached with mass hygiene promotion	£0.37 estimated	£ 0.12	£ 0.18	£ 0.21	£ 0.06	Based on hygiene expenditure (mass communication only); the cost per person reached has dropped following the two hygiene promotion campaigns (use of mass media, media, community and school activations) conducted in 2017.
Efficiency	Village ODF Conversion ratio	Not explicit in business case	22%	35%	46%	53%	Villages ODF verified (11,584) / Total Villages Triggered (22,000)
Economy	Cost of school toilet (£ per drop hole)	£1,266	£ 578	£ 516 (GRZ)	£ 596 (Government school)	£ 557 / (Gov school)	Based on bill of quantities rather than financial expenditure level. Figures are $1,988 for National school design, $855 for interim standard design (for government primary schools; incl Kalingalinga bucket), and $650 for reviewed low cost community school design (materials, transport and labour). Changes in cost due to revised USD/GBP exchange rates.
		(based on the original design of Ministry of Education)	£ 265	£ 348	£ 464	£ 423
					(Community schools)	(Community schools)
	UNICEF Zambia Overhead / Expenditure Ratio	13.1% estimated (excluding cost of purchasing vehicles for GRZ counterparts)	11.50%	10.52%	12%	10%	UNICEF Project Support Costs in Zambia (incl. human resources) as a proportion of total expenditure; excluding the UNICEF recovery costs.

Economy
A considerable cost driver for school WASH has been the construction of toilets. In previous years of the programme, lower-cost designs for toilets were developed and implemented for Government and Community Schools. The original ‘low-cost’ model was found in previous annual reviews to be subject to ‘brittle fracture’, and designs were hence modified to increase the quality of the designs. Whilst some of the toilets constructed using the earlier designs have had to be re-constructed due to poor quality, the updated ‘low cost’ model appears to be more robust and durable, and is still considerably cheaper than standard government designs. UNICEF has undertaken various additional measures to ensure economy, such as: Undertaking bulk procurement of certain materials during the reporting period[21]; UNICEF’s implementing partner (ZAMCOM) has managed to negotiate lower rates for the Community Radio sessions, based on the sessions being for ‘social benefits’; and UNICEF reportedly chose the ‘lower cost’ option of engaging local NGOs for reconstruction of the 50 school toilets, rather than using a contractor.
[21] To increase to value for money, in the reporting year, bulk procurements where done for phones, bicycles, menstrual hygiene management (MHM) demo kits, MHM toolkits and Guidelines (booklets) and supplies used for the cholera response.

Efficiency
The overall rate of conversion rate from ‘triggered’ to ‘ODF’ communities has progressively risen, as efforts continue in mobilizing local authorities and traditional leaders, and social pressure continues to rise against open defecation. A paper published in 2017 by Tiwari et al suggests that the programme approach of engaging the local Chiefs as key agents of change is bringing considerable efficiencies, stating that the involvement of traditional leaders helped to accelerate progress to attaining ODF in chiefdoms by 22%. In contrast, however, during this review, three of UNICEF’s Implementing Partners complained of UNICEF programme management inefficiencies, particularly regarding issues of ‘heavy’ bureaucratic processes, and in one instance, delayed disbursement of project funds (which they report slowed field implementation).

Effectiveness
The ZSHP continues to achieve new sanitation users at a cost similar to those envisaged in the 2011 Business Case. The programme approach of using RTM data to drive progress appears to be adding to the overall programme effectiveness. UNICEF has reported that RTM has led to reducing cost per new user of sanitation from US $2.4 in districts without RTM against US $1.7 with RTM (UNICEF, 2016). In addition, representatives met during the annual review from Kazangula, Namwala, and Zimba Districts all remarked how activities from target schools were being replicated in non-target schools, with the budget of the local authorities and the school’s Parent Teacher Associations[22]. In contrast, however, the effectiveness of the programme may be undermined by challenges of post-project sustainability[23], and certain components of the project, such as Sanitation Marketing, do not seem to be delivering the scale of results (e.g. sales) which were envisaged. The extent to which UNICEF is analysing evidence (such as on Sanitation Marketing Sales, or from the Impact Evaluation) to adapt its programming, seems to have been limited during the last year.
[22] For example, the ZSHP primarily targets community schools in the district, not all schools. The DEBS representative in Namwala mentioned ‘how can we have a community school with better facilities than a government school?! We felt ashamed, and encouraged the Parent Teacher Associations in all schools to reach the standard (for WASH) set in the community schools.’
[23] The collapse of pit toilets continues to be a widely reported issue in the communities, and unless it is adequately addressed, it poses a key risk to the continued, long term use of toilet facilities.

Equity
Specific metrics on equity parameters were not provided by UNICEF for this annual review[24], and it is recommended that such data is captured in the Programme Completion Review. The ZSHP specifically factored equity considerations into its design. A principle tenet of the Community-Led Total Sanitation (CLTS) approach utilised in the ZSHP is that communities find solutions together to ensure that all households have toilets. This often means that traditional leaders and other community members support vulnerable households to construct toilets, and numerous examples of this were identified during the annual review field visits. The programme also continues to focus on the more deprived community schools, which have much higher needs than the government schools. The ZSHP has been instrumental in supporting the Ministry of General Education in the development of toolkits and guidelines on Menstrual Hygiene Management in Schools. Many of the female pupils met during the annual review field visits remarked of their increased attendance following the WASH interventions. Despite these positive actions, UNICEF has not systematically considered disability in all of the infrastructure designs of the school toilets.
[24] Aside from the gender of school pupils in the 1021 targeted schools, which is (174,637 boys and 167,944 girls or 51% boys and 49% girls)

VFM Monitoring

A VFM study was conducted in 2015 by Oxford Policy Management (OPM). This study provided a number of recommendations regarding how UNICEF monitors and reports certain issues, which reportedly led to a number of changes in the ZSHP monitoring framework (documented in the previous annual review).

Despite the recommendations of that study, and a UNICEF organisation-wide commitment to track VFM, UNICEF does not appear to routinely track VFM in the ZSHP. UNICEF Zambia has recently undertaken a visit to UNICEF Zimbabwe which has institutionalised VFM tracking, and reports it intends to commence tracking in Zambia in 2018. Progress on this should be reported by UNICEF in the final ZSHP report, together with final, programme-wide VFM metrics.

Assessment of whether the programme continues to represent value for money
Overall the programme continues to represent good value for money. Whilst UNICEF may not be actively tracking VFM routinely, it is taking active measures to achieve economy of inputs, and using approaches and processes (e.g. engagement of chiefs and RTM) to drive efficiency and effectiveness.

Quality of financial management

UNICEF provided the following expenditure update on 13th March 2018[25].
[25] The expenditures are extracted from the UNICEF financial system in USD; All expenditures are actual expenditures (no fund commitments included); The exchange rate used for the conversion between GBP and USD is the weighted average exchange rate of all funds received since the start of the programme; Apart from the expenditures, funds are committed for a total amount of USD 1,688,992; these commitments include supply orders, signed contracts and recovery costs; If commitments are factored into the calculation, the burn rate stands at 98%; The available balance, which includes under process commitments for CLTS implementation in the 7 districts, the cholera response and sector coordination/capacity building, is USD 704,456 or GBP 463,033’.

Table 3: Budget Utilisation
No	Activities	(a) Budget allocation - Annual review 2015	(b) Proposed budget allocation, Extension budget	(c) / = (a) + (b) Total allocation	Total spent as at 1 Mar 2018 (GBP)
						Proportion of Budget Utilised
1	Community Approaches to Total Sanitation (CATS/CLTS)	7,585,671	1,977,961	9,563,632	8,883,271	93%
2	Sanitation Marketing	1,446,424	100,000	1,546,424	1,092,618	71%
3	School sanitation and hygiene	4,511,957	209,977	4,721,934	4,650,492	98%
4	Hygiene Promotion and Sustainability	1,418,068	220,000	1,638,068	1,374,736	84%
5	Sector Coordination	274,378		274,378	224,626	82%
6	M&E and Knowledge management	800,000	668,577	1,468,577	1,215,867	83%
7	Project support costs	1,720,513	480,866	2,201,379	2,182,003	99%
8	Cholera response				332,309
	Program Total	17,757,010	3,657,381	21,414,391	19,955,924	93%
	UNICEF recovery cost 8%	1,242,991		1,242,991	1,229,067	99%
	UNICEF recovery cost 7%		292,590	292,590	191,788
TOTAL (GBP)		19,000,000	3,949,971	22,949,972	21,376,780	93%

DFID receives quarterly and bi-annual financial reports showing expenditure trends. A set of key financial indicators are generated and reviewed monthly by UNICEF. UNICEF issues interim annual financial reports, while headquarters issue certified annual financial reports for each grant outlining detailed expenditures.

On downstream activity, UNICEF has robust policies and procedures used to select and manage downstream partners, in line with the UN HACT Framework (a financial management system) which requires UNICEF to undertake micro-assessments on the financial management systems for all partners receiving more than $100,000. Financial risk assessments on government institutions are undertaken annually. The grant funding agreements signed with NGOs have standard text on partner’s responsibilities on fraud, bribery and corruption, which complies with DFID standards. Further, DFID still maintains an overall risk on UNICEF as low to medium based on the March 2015 due diligence.

Summary of responses to issues raised in previous annual and mid-year reviews

1. UNICEF to ensure adequate VFM analysis by clearly defining VfM indicators for all outputs (considering the baseline data from the VfM study), assumed outcomes and sustain outcomes, and should all be summarised in UNICEF Progress Reports on how these fit with Phase 2 objectives.

Not done for this annual review or for the January 2018 progress report, and it is unclear if it was followed-up on by UNICEF with MoWDSEP during the reporting period.

2. M2W monitoring data should be used to track sustainability of outputs. Previous annual review response: ‘In progress. Response: A new challenge is the current management of the transition of the M&E functions from MoLG to MWDSEP’.

Not done: the usage of RTM data to analyse sustainability is very limited. Whilst the MoWDSEP management has been in transition, UNICEF has had TA embedded in the Ministry to support on WASH M&E during the review period, and the analysis of sustainability data is not reliant on the actions of MoWDSEP.
Recommendations

Track VFM and sustainability metrics using the RTM data: UNICEF to track VFM metrics in the ZSHP and provide a detailed analysis on VFM for the Project Completion Review in September. This should include comparison with benchmarks in the sector with similar programmes, and disaggregated data should be provided to allow equity analysis. UNICEF should also undertake analysis on the sustainability of outputs and outcomes using the RTM datasets, as recommended earlier in this report. UNICEF should build the capacity of MoWDSEP to do such analysis for the future. UNICEF should provide DFID an update on its intentions for VFM tracking by the end of April.

Date of last narrative financial report	28 February 2018
Date of last audited annual statement	21 April 2017

E: RISK

Overview of programme risk and overall risk rating: Moderate

The ZSHP risk register on the AMP system was updated in late 2017. The main risks in the programme are now related to sustainability.

Five key risks to the ZSHP were identified in 2015 and 2016, and the previous annual review added three additional risks. The five risks are plotted in the risk matrix below, and the additional risks are listed below. Arrows have been added to the matrix to indicate movement from the previous annual review.

Table 6: Risk rating using revised categories
		Impact
		Insignificant	Minor	Moderate	Major	Severe
Likelihood	Almost Certain
	Likely
	Possible		Sanitation marketing approach is not sustainable and effective	Mobile to web (RTM) monitoring system is not successful	ODF communities not sustained because of lack of behaviour change around social norms of latrine usage and handwashing
	Unlikely		GRZ fails to provide adequate resources for sustainability and fails to prioritise sanitation resulting in loss of programme momentum	Low cost school sanitation approaches do not reach required standards/are not maintained
	Rare

The additional risks identified in the previous annual review included:
- The transition of functions from Ministry of Local Government (MoLG) to the new Ministry of Water Development, Sanitation and Environmental Protection (MoWDSEP)
- There are varied Management Information Systems (MIS) in the government e.g. HMIS in health, DHIS2 in WASH, EMIS in education, etc.
- High staff turnover/movement in district offices and communities

Review of the current status of previously identified risks:
- The risk posed by the transition from the MoLG to MoWDSEP is reducing, as the MoWDSEP becomes more established and progressively more in a position to lead and drive forward sector issues. Given that the ZSHP activities cut across ministries, an ongoing risk will be whether or not the MoWDSEP can effectively coordinate and collaborate with other key line ministries and ensure their ongoing engagement and budget provision for related activities.
- The MoWSDEP has also ensured the creation of a specific budget line for sanitation and hygiene, and in 2017 ensured a budget allocation of $2,600 per district to 36 districts, and reportedly aims to provide $10,000 per district for sanitation in 2018. Whilst this is still a very small amount given the competing demands for sanitation in the districts (considering this budget is also for infrastructure), it is a good indication of government commitment to the sub-sector. Without adequate budget commitment from the government and CPs, the sustainability of the RTM system and wider activities of the ZSHP is at risk. This review recommends support to finalise and launch the ODF Strategy or Campaign, to seek high-level political traction and commitment from GRZ to expand and support rural sanitation, and to encourage more CP’s into the sub-sector.
- The risk of the RTM has shifted from whether it is ‘successful’, to whether it is likely to be sustained after the programme. AKROS has undertaken widespread capacity building at national, provincial and district levels, and established a team of coaches to support districts and chiefs in their RTM activities. Ongoing risks to sustainability of the RTM system include: the fact the system relies on procurement/replacement of dedicated handsets (not Apps); the recurrent funding for the RTM system, and to pay the small incentives for Community Champions (CCs) to report[26]; the potential of the voluntary structures of the SAGs and Community Champions decreasing through time. MoWDSEP and MoH should identify if functions of the Community Champions and the SAGs could be mainstreamed into permanent (MoH related) local structures, and explore the RTM system could be expanded either for water and/or health purposes, to be more ‘useful’ on a wider range of topics, meaning a higher likelihood of willingness of government to allocate funds to sustain the system.
  [26] A special system was established for the MLGH to pay via airtime, and it is unclear how well this would be managed without Akros support. This could be a critical factor for success and could fall by the wayside
- The previously identified ‘risk’ of the wider discussions on sector-wide MIS systems could instead be seen as an opportunity, if the ZSHP can integrate into a wider sectoral MIS (either health and/or WASH MIS). As previously mentioned, if the outcome is that indicators from RTM are absorbed into a different MIS process (e.g. the M2W system itself is not continued), it could be considered that at least the RTM system has helped achieve the impressive gains on ODF. It also helped to instil a culture of monitoring and reporting on sanitation and hygiene information, in a wide range of stakeholders at various levels. Therefore the project risk should be more focussed on a lack of continuity of monitoring of ODF, rather than the lack of continuity of this specific RTM software.
- The effectiveness and sustainability of the San Mark activities is yet to be proven, and to date sales figures remain low in many chiefdoms. The wider risk is that toilets constructed using local materials (not including the San Mark designs) continue to collapse.
- Staff turnover at the district and school levels undermines project effectiveness. However, there have been considerable efforts to train national and provincial coaches, who can re-train new recruits.

Outstanding actions from risk assessment

As the programme nears close, the risks of timely completion of the remaining activities, and risks of post-project sustainability become more pressing. Such evolving risks are presented in the table below.

Table 7: Actions to address potential challenges to the programme in 2018
New risks identified as part of this Annual Review	Plans
Timely completion of activities such as school toilet reconstruction, transition of RTM in all 68 districts, and the finalisation and launching of the ODF/BCC strategies	Schools: UNICEF removed the requirement on community contribution of materials, which slowed progress in previous schools, and commits to close monitoring, and frequent progress reporting to DFID / RTM: UNICEF to define what is possible with AKROS in terms of transition of RTM in the 68 districts, and agree with DFID the plan for those not on track to complete. UNICEF to ensure frequent monitoring, and progress reporting to DFID / OFD/BCC Strategies: Where a strategy is not possible, UNICEF to consider instead launching a national ODF ‘Campaign’ (and feeding strategy issues into the wider WASH Policy development)
Inter-ministerial collaboration (particularly between MoWSDEP and MoH, and also MoCTA) affecting institutionalisation and sustainability and effectiveness of the project activities	High-level inter-ministerial meetings will be convened, action plans developed and these would be integrated within the wider post-project planning and budgeting process recommended in this review.
Quality of infrastructural works for the remaining 50 schools and others already constructed of the same design	UNICEF to closely monitor progress on reconstructions and consider engaging a supervisor for this purpose. UNICEF to assess any potential health and safety risks of the design and communicate guidance to schools by June.
Government and CP continued prioritisation and support of the rural sanitation sub-sector	As part of the development and launching of the ODF Strategy/Campaign, UNICEF and DFID to ‘on-board’ other CPs and sector actors into the rural sanitation sub-sector. The public launch of the campaign/strategy should be by the President to demonstrate government’s ongoing priority to ODF. DFID to provide high-level support for the convening of political and CP stakeholders in this process.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
Whilst the programme is broadly on track to achieve most activities by the end of September, many of the log-frame milestones for January were not met, and a number of previous annual review recommendations have seen limited progress. The delays can be attributed in part by slow rates of institutional reform by the MoWDSEP, and slow decision making processes within it. It is likely that HR turnover in UNICEF contributed to some delays in implementation during the period, and certain issues at ministerial level arguably could have been chased by UNICEF with more urgency.

Performance of partnership (s)
This annual review has (briefly and anecdotally) looked at the range of partnerships in the ZSHP:
- UNICEF-DFID: This continues to be a productive partnership. The programme has been hindered by changes in key staff in both UNICEF and DFID during the review period. There have been some delays and communication issues on both sides related to the question of the proposed business case amendment for peri-urban WASH and the no-cost extension.
- UNICEF-Government: Stakeholders met at national, provincial and district levels all remarked satisfaction on the collaboration between UNICEF and government. They particularly appreciated the internal ZSHP periodic review processes, which brought together key stakeholders to discuss progress, and plan activities for the coming period. The MoWDSEP was appreciative on the support provided to their national office. The Director of Water Supply & Sanitation remarked appreciation of support cutting across logistics, capacity building, monitoring, and policy support. He remarked “when we have a need for assistance, they (UNICEF) are there”.
- UNICEF-Implementing Partners: The two NGO partners implementing school WASH during the period mentioned a productive and effective collaboration with UNICEF. However AKROS, who is the main IP of the programme described some challenges to the partnership regarding administrative management and financial disbursements – although UNICEF’s perspective was not captured during this review. All three IPs complained of ‘heavy’ bureaucracy, and delays in processing of financial reports and disbursements.
- UNICEF-CPs/other non-project sector actors: UNICEF has provided ongoing (secretariat) support to the WASH CP group, and through this is coordinating well with partners such as GIZ. The ZSHP is perceived by some stakeholders as a ‘UNICEF’ rather than national programme. The results from sustainability checks and the impact surveys could have been shared more widely in the sector, and there is need to place greater efforts by UNICEF in engaging and learning from other organisations working on rural sanitation in the country, and garnering more interest and ownership in the nationwide ODF initiative from other CPs and NGOs.

Asset monitoring and control
UNICEF manages a fixed asset register, which includes items purchased using DFID funding, in line with its fixed assets policy. During the annual review, programme assets were checked for functionality, condition, management and safety. The review team was satisfied with the condition of all functioning assets. Important to note; bicycles for Community Champions are depreciated as they have worked for a long time on the programme now.

G: CONDITIONALITY

Update on partnership principles (if relevant)

Not applicable.

H: MONITORING & EVALUATION

Evidence and evaluation
The impact survey and third sustainability check were both finalised during the review period. Both studies highlighted some limitations: on the effectiveness of certain activities; on sustainability prospects of various actions; and importantly, whether the programme is on track to achieve envisaged impact and outcome targets. Whilst the findings were reportedly presented to stakeholders directly involved in the ZSHP (not the wider sector), it is unclear the extent to which the findings of the impact study led to modifications being made on the ZSHP. There were delays finalising the report so has been limited time (and funds) to implement corrective actions. Findings did feed into the process of updating the National Rural WASH Programme for 2016-2030.

The analysis on the performance and learning from the San Mark activities seems to have been limited, reflected in the fact that UNICEF focussed on training additional masons during the period, rather than reflecting on learning, and amending the approach taken as needed. Overall, this review brings into question the extent to which UNICEF, during the review period, has used monitoring and evaluation information to adapt and inform programme activities.

Whilst there was a large was a large Post ODF Sustainability Assessment (POSA)[27] planned to be undertaken, this activity was cancelled and funds re-diverted to cholera response activities. There were no clear plans on substituting the POSA with anything ‘lighter’, nor plans in which final programme impact and outcome targets would be verified. This review has proposed recommendations on undertaking a ‘light’ review of sustainability and impact using secondary data, and to convene meetings where sector stakeholders reflect on learnings, for example on San Mark. There may be benefit in the review process also considering the systems/capacities for supporting sustainability at various levels, although this may be more time and cost intensive.
[27] This was envisioned as an 18 month long study, which was expected to cost around USD 0.5m. ToRs were development and bids were received.

Monitoring progress throughout the review period
Feedback from beneficiaries during field visits: Field visits undertaken during this annual review revealed very positive feedback and appreciation from beneficiaries about the ZSHP. The schools visited were still practicing handwashing activities daily at the mass handwashing facilities, and female students mentioned their increased attendance as a result of improved MHM facilities. The quality of infrastructure of school WASH facilities was generally acceptable (aside from one ‘sunken’ toilet), and Parent Teacher Association representatives stated their intention to continue to allocate budget for the upkeep of the WASH facilities. The Chiefs visited were highly engaged on the ODF initiative, and were able to demonstrate usage of the RTM system for monitoring purposes. The improvements in household sanitation and hygiene in the visited communities was more variable. It should be noted that the visits were being undertaken during the rainy season, and unsurprisingly some households complained of collapsed pits.

Monitoring activities throughout the review period include:
Quarterly review meetings, (b) Bi-annual reporting, (c) Ad-hoc monitoring, (d) Annual reviews

The annual review process: This annual review was undertaken during February and March 2018, led by a consultant (Will Tillett, Aguaconsult), provided through the HEART EACDS framework. HEART Quality Assurance inputs were provided by John Pinfold and Peter Burr (Oxford Policy Management). The review was conducted jointly by Will Tillett and Chibesa Chibesakunda (SRO), and included meetings with a wide range of stakeholders[28] at the national, provincial, district and local levels. It also included document review, and field visits by Will, Chibesa, Sarah Goldsmith (Team Leader) and Steve Beel (incoming SRO) to Southern and Central Provinces[29]. The draft findings of this review were presented in separate meetings with DFID Zambia, UNICEF, MoWDSEP, and wider sector stakeholders[30]. The review provided DFID, UNICEF and sector stakeholders with reflections and recommendations not only related to the remaining six months of the ZSHP, but also considerations for the design of similar sanitation and hygiene initiatives in future, and issues for the wider sector to consider following programme closure.
[28] Including CPs, Implementing Partners, UNICEF, DFID, MoWDSEP, MoH, MoCTA, MoGE, Provincial and District Secretaries, Councils, D-WASH Committees, Provincial and District Government stakeholders, teachers, San Mark artisans, chiefs, students and community members)
[29] Including visits to the following districts: Southern Province (Kazangula, Zimba, Namwala, Choma) and Central province (Kabwe, Kapiri Mposhi and Chibombo)
[30] The wider stakeholder group included; government, civil society and cooperating partners.