Annual Review - Summary Sheet

Title: Infrastructure and Cities for Economic Development (ICED)
Programme Value: £33,500,000 (of which £8M ICF)		Review Date: 28 April 2018
Programme Code: 204250	Start Date: / March 2015 / (with varying dates for implementing partners)	End Date: July 2020 / (implementation period 5 years, / with shorter periods for individual components and partners, including ICED Facility)

Summary of Programme Performance
Year	2015/16	2016/17	2017/18	2018/19	2019/20
Programme Score	A	A	A
Risk Rating	Moderate	Moderate	Moderate

ICED is a complex, multi-component and multi-partner programme. The programme was designed to respond to the key binding constraints to growth identified in the Inclusive Growth Diagnostics through large-scale programme in the energy, urban and infrastructure sectors. The programme is consistent with DFID’s Economic Development Strategy, supporting DFID to scale up programming and investment in infrastructure in cities.

There has been good progress over this year, and the programme is on track to meet its objectives. The programme comprises the ICED Facility (an Alliance of suppliers led by PWC), and a number of partners working on aspects of cities and infrastructure in relation to economic development. Across the programme, partners have delivered over 60 knowledge products, scoping studies and reports, 23 learning and training sessions, and two new organisations have formally joined our partners. The review has been carried out by DFID staff, and the review of the Facility was carried out by a staff member outside the programme team.

The ICED Facility is the largest programme component. It has made strong links across the DFID networks and responds quickly and effectively to requests. This year, we have seen the Facility increase its strategic engagement across DFID, where it supported policy priorities and engaged across other government departments, as well as a providing a more coordinated knowledge sharing offer.

Summary of progress and lessons learnt to date
- The ICED Facility has supported DFID country and regional offices in 20 countries and seven central teams to provide technical advice to the design of new, and improve existing, programmes. In 12 cases departments have sought repeat support.
- The ICED Facility “Strategic Pivot” (a framework to enable greater prioritisation and strategic engage with policy and country office priorities) was developed, and communicated across DFID with positive feedback.
- Over this year, the programme has seen greater collaboration between different ICED partners. Examples include the Construction Sector Transparency Initiative (CoST) and the ICED Facility jointly hosting an external roundtable on infrastructure governance; the World Bank partnering with CoST to deliver a PPP disclosure framework in Honduras, now being scaled up; and the Coalition for Urban Transitions (CUT) team working closely with Cities Alliance to develop the CUT programme in Ghana.
- In Burma, the Facility improved understanding of key issues in the energy and water sectors. In Zambia, ICED developed a series of urban growth diagnostics of Zambia’s cities which are being used by DFID Zambia to better target interventions in secondary cities.
- The ICED Facility has focused a core area of work around safeguarding in infrastructure investments, emerging out of an initial scoping assessment to audit safeguarding in two DFID roads programmes in Uganda. They have also ensured mainstreaming of gender and climate issues.

Summary of recommendations from last Annual Review: There were a number of relatively minor recommendations from the last Annual Review, which are listed under each component’s section.

Summary of recommendations for this year

Overarching Programme
- Review the Logframe to ensure it is still fit-for-purpose and encourages the programme to strategically stregthen DFID’s approach to addressing binding constraints to growth and implement the Economic Development Strategy. In particular, to review the Outcome indicators to consider giving more attention to newer priorities, and ensuring the Indicators draw together outcomes across different components.
- Continue to develop collaboration and coherence between the different components, including by holding an ICED programme-wide conference to share outputs and learning from across the programme and explore future opportunities with DFID colleagues and programme partners for closer collaboration.
ICED Facility
- Strategy and DFID engagement:
  - Implement the ICED Facility’s “Strategic Pivot”, including convening an internal, senior, Strategic Advisory Panel to provide direction;
  - Consider how the ICED Facility could support cross-Whitehall engagement and the UK’s prosperity obejctives, as well as with CDC and PIDG;
  - Ensure more systematic engagement with DFID staff on climate and environment;
  - Communicate an updated ICED offer across DFID;
- Management
  - Streamline the fortnightly management team meetings, and review the engagement of DFID workstream leads;
  - Consider focusing down the number of VfM KPIs (36) that are regularly reported on;
  - Review the process for developing ToRs so it is as effective as possible;
  - Future implementation: Take steps to replenish the current ICED Facility to enable it to continue work until mid-2020.
- Knowledge and Learning
  - Put the issues raised by the core Country Offices and the SAP at the heart of knowledge and learning while consolidating and disseminating the tools etc. developed this year, and making full use of the website and other electronic forms of dissemination to a wider audience;
Other Components:
- Output 5 (World Bank): DFID to work with the World Bank (WB) on closing out the programme and ensuring findings are taken up and used by others.
- Output 7 (Strategic Advisory Fund):
  - DFID internal team to work with Chatham House to prioritise finalisation and completion of the Fossil Fuels report.
  - DFID to discuss with HM Treasury moving all Global Infrastructure Hub Funding to HMT, drawing upon their new Prosperity Fund programme.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204250 / Specific link to BC http://iati.dfid.gov.uk/iati_documents/4961485.odt
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204250

Outline of the programme
DFID is providing £33.5 million to the Infrastructure and Cities for Economic Development (ICED) programme over five years (60 months), from April 2015 to July 2020.

This project supports DFID and our development partners through:
- Improving the enabling environment for sustainable, inclusive growth-enhancing infrastructure service delivery in DFID focus countries; and,
- Harnessing the benefits of cities for sustainable economic growth and poverty reduction in DFID focus countries.
Some of this work is delivered by assisting DFID Country offices to scale up bilateral programming; other work is focused on international influencing and delivery of global public goods.

The expected impact is: An improved enabling environment for infrastructure service delivery and better managed and governed cities as drivers of inclusive economic growth in DFID focus countries

The expected outcome is: DFID scales up, enhances coordination and improves the quality of its country/regional/central-level support for an improved enabling environment for infrastructure and planning for cities (including in our most fragile and conflict-affected states).

This will be achieved through the following outputs and partners:

At the country level, and to support DFID’s policy globally:
Outputs 1, 2 & 3 - The ICED Facility includes PWC, Adam Smith International, Engineers Against Poverty, the International Institute for Environment & Development, Social Development Direct, MDY Legal and ARUP. To deliver the EDS, DFID needs more high quality infrastructure and cities programmes at country level. This Facility provides support to DFID country offices and central/regional departments to develop new, and improve existing, infrastructure enabling environment and city economic development programming.

At the global level:
- Output 4 - Scale up and enhance the impact of CoST activities to reduce corruption and increase value for money in public sector funded construction projects;
- Output 5 – Support the World Bank’s Enhancing Economic Performance of African Cities programme - to support economic growth in 4 cities in Africa.
- Output 6 - Shape the strategic priorities of the Cities Alliance and develop and implement its Economic Growth programming.
- Output 7 - Strategic Opportunities Fund (SOF) – to enable additional high priority activities that support this programme’s objectives. The use of the SOF is agreed with the ICED SRO and approved by the Head of DIFD’s Growth and Resilience Department.
- Output 8 - support the Coalition for Urban Transitions - Output 8 – which seeks to build the case for national level support to urban development in developing countries. This component was established in April 2017.

The above components are designed to be complementary.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The ICED Facility is performing in line with its logframe targets whilst also having adjusted flexibly to changing circumstances. It has developed a significant amount of knowledge relevant to DFID’s infrastructure and urban programming, as well as built up an understanding of ways of working across DFID. Driving up value for money requires actions both by DFID and by the consultant team. In particular DFID should quickly implement the “Strategic Pivot” so as to give clear direction to the demand to which the Facility responds. The consultant team needs especially to focus on ensuring that they respond in a timely and effective way around the initial ToRs, and maintain a high quality of engagement all the way through to delivery of a final product that is fit-for-purpose.

Cities Alliance, the World Bank and CoST (Construction Sector Transparency Initiative) are all moving towards delivery of their expected outcome indicators. In particular in reference to the outcome indicator assigned to the CA, the City Level Partnerships have been formed and endorsements secured from the cities it is working with on the initial institutional enabling environment reports it has completed. These reports will form the basis of in-depth fact-based, policy support to improve equitable access to select public goods in the cityover the next year. CoST are making progress, particularly regarding the numbers of projects now disclosing their data.

It was anticipated that DFID would commission an independent review of the ICED Facility in mid-2018. In large part this was driven by the need to inform a decision on a potential replenishment of the ICED Facility. However, the ICED Facility is currently profiled to spend the remaining budget in the next 9 months, which makes a replenishment decision an urgent priority. Additionally, given a lead time for procurement of a new programme of 18 months or so, it will also be crucial to start preparing for a new programme during the next year. This review therefore recommends postposing the independent review until late 2018, to enable it to inform design for a subsequent programme.

It is therefore recommended that the current facility is extended while also ensuring that a) immediate consideration be given to designing a follow up programme, b) significant efforts are made to ensure that the knowledge and understanding gained by the ICED Facility are retained and effectively captured.

Overall output score and description:
Output 1: ICED Facility (1)	A	(impact weighting 30%)
Output 2: ICED Facility (2)	A	(impact weighting 10%)
Output 3: ICED Facility (3)	A+	(impact weighting 20%)
Output 4: CoST	A	(impact weighting 20%)
Output 5: World Bank	A	(impact weighting 5%)
Output 6: Cities Alliance	A	(impact weighting 5%)
Output 7: Strategic Opportunities Fund	A	(impact weighting 5%)
Output 8: Coalition for Urban Transitions	A+	(impact weighting 5%)

The overall programme score is A.

Key actions: See recommendations above.

Has the logframe been updated since the last review? Yes.

## C: DETAILED OUTPUT SCORING

Output Title	ICED Facility - High quality TA provided by ICED to DFID teams (country office, regional and central) to facilitate the delivery of new and improved existing programmes, initiatives and partnerships
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting revised since last AR?	No

Indicator(s)	Milestones	Progress
1.1a Number of active TA substantive interventions (SI) supporting DFID teams to scope new or redesign existing programmes, initiatives, partnerships, approved by DFID	Year 3: 10	Exceeded:15
1.1b Number of Business Cases (BC) supported by ICED, approved by DFID	Year 3: 2	Met: 2 Urban productivity for Khyber Pakhtunkhwa for DFID Pakistan; India- UK Partnership on Smart Cities for Inclusive Growth
1.2 Number of DFID programmes that have adopted ICED development tools and/or programme approaches	Year 3: 8	Exceeded: 12
1.3 Number of successfully delivered short term engagements and advice, for example through call-down requests (not including large scoping studies)	Year 3: 10	Exceeded: 12

Key Points
The ICED Facility significantly exceeded its annual target for active TA substantive interventions supporting DFID teams. Highlights of support to country offices included:
- Assessing options for DFID support for Dodoma as the relocated capital of Tanzania;
- A scoping study to inform a major new water, sanitation and hygiene programme in Ethiopia;
- A Digital Strategic Review for Tanzania.
The Facility also supported DFID advisers in Burma and Zambia to set up new programming.

In addition to supporting country offices, the ICED Facility supported central teams on the thematic areas of youth inclusion, safeguards, and construction sector capacity and jobs. The safeguarding work emerged out of an initial scoping assessment to audit safeguarding in two roads programmes for DFID Uganda for which the office provided very strong positive feedback. A key piece of work on gender has been assisting the Private Infrastructure Development Group (PIDG) deliver on the increased ambition in PIDG’s new Gender Strategy.

The Facility includes Fragile and Conflict Affected States (FCAS) specific work which this year included phase 3 of Value for Money in FCAS. Since large scale infrastructure spend in FCAS is likely to be through multilaterals rather than directly by DFID the DFID/ ICED management team should consider how best to focus the FCAS work to achieve VfM (such as working on Trust Funds), and how to deliver this most effectively to our partners. A `call-down’ window of support was established in Year 2 to respond rapidly to demand in FCAS environments. During Year 3 this was expanded to all ICED Facility portfolios and thematic areas.
Last year country offices raised the need for ICED to make them a clearer offer, and to improve the way the ToRs were developed. Feedback from country offices (DFID Pakistan, Uganda and Zambia) for this AR emphasised that getting the ToRs right tended to involve either significant preparation by the country office, or extensive dialogue with the ICED Facility, or both. Country offices also noted the challenge they typically faced when commissioning such work since it was often in new areas where they had limited understanding. There is scope for the ICED Facility to help country offices handle this challenge.

ICED adapted to a change in DFID demand (from a few large Work Packages to more, smaller ones) during Year 3 compared with Year 2. However, the DFID ICED team identified a key VfM risk that individual requests might not support the overarching strategic direction of team/country priorities. Earlier this year the team therefore proposed a `Strategic Pivot’ which included a new engagement strategy focusing on a list of 11 priority countries and central teams, as well as a Strategic Advisory Panel, comprising the HoDs and senior management of the ICED Facility.This should also ensure that ICED remains aligned with its central objective of helping DFID to deliver the Economic Development Strategy through better urban and infrastructure programming.

Summary of responses to issues raised in previous annual reviews
The last Annual Review recommended that the DFID ICED team should share information and learning more frequently across the Growth and Resilience Department and DFID on knowledge generated to ensure it is used by advisers in their work. This area received significant attention over the last year and is discussed in more detail under Output 3 on Knowledge.

Recommendations
- As already agreed, DFID’s Growth and Resilience Department should provide stronger strategic direction to shape demand through implementation of the “Strategic Pivot” described above. Engagement with Country offices should be at least at Team Leader level to ensure sufficient strategic oversight. Having the first meeting of the Strategic Advisory Panel in the next two months would be an important next step, and need only involve a few country office leads.
- DFID participation in the fortnightly management meetings should be streamlined with a broader cast taking part in more strategically orientated management meetings. The start of a new SRO also gives an ideal opportunity to review DFID leads across the Facility.
- Planning for future work should recognise that new programme design is likely to be a minor component of future work. The ICED Facility’s “offer” across DFID needs to take this into account, while still supporting strategic objectives. Such an offer should include clearer branding of ICED across DFID for new advisors or staff, alongside the “Strategic Pivot” communications and individual relationships, as well as the consolidation of the tools and approaches developed so far, so that they become easier for DFID staff to draw on at low cost.
- At a practical level, the ICED Facility should:
- ensure it routinely considers how to adapt its response at work package level, depending on the expertise / capability / capacity of DFID staff, particularly when developing the initial ToRs.
- ensure that ICED Facility staff continue to have the necessary developmental experience and expertise to engage effectively with DFID staff;
- ensure that ICED Facility staff maintain a high quality of engagement all the way through to delivery of a final product that is fit-for-purpose;
- ensure each ToR explicitly sets out how the assignment fits with DFID strategic priorities.
- DFID ICED team should consider how the ICED Facility might support a cross-Whitehall/ broader UK `offer’ on infrastructure, both centrally and in specific countries.
- The DFID ICED team should also consider the appropriate role for the ICED Facility to play in relationship to the Private Infrastructure Development Group (PIDG) and CDC, where the objective should be to create more value for DFID while recognising that both have their own budgets and need to own the outcomes of any work carried out.

Output Title	ICED Facility - High quality TA provided by ICED to DFID teams (country/regional/central) to facilitate increased access to ICF funding
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting revised since last AR?	Yes

Indicator(s)	Milestones	Progress
2.1 % of ICED-supported business cases that are ICF compliant	Year 3: 100%	Met: 100%
2.2 % of ICED-supported programmes that are ICF compliant having ICF KPIs	Year 3: 100%	Met: 100%
2.3 % of £ value of DFID approved Business Cases in infrastructure/urban development supported by ICED classed as ICF eligible	Year 3: 20%	Exceeded: 37.5%

Key points
The ICED Facility developed a mainstreaming tool during Year 3 to ensure that climate and environment priorities are built into all WPs. This tools was developed in consultation with the DFID ICF Secretariat and builds on DFID ICF integration guidance while also being anchored in the OECD DAC Rio Markers for Climate Change. Mainstreaming has been particularly important given the limited demand from DFID to support programmes with the promotion of low carbon development or climate resilience as their principle objective.

Both Business Cases on which ICED worked were supported to develop Climate and Environment relevant programming.
- Urban Productivity for Khyber Pakhtunkhwa, Pakistan, includes support for promoting industrial energy efficiency and facilitating investment in national-scale renewable energy. Within the planning components, mainstreaming resilience into urban planning and supporting the development of more sustainable and lower carbon cities (e.g. transport, housing) feature heavily as core thematics. This business case includes five ICF indicators.
- The India UK Partnership on Smart Cities for Inclusive Growth business case includes a component looking at the potential development of urban solar parks. City-level investment support aims to facilitate financial flows into sustainable development (e.g. low carbon housing and transport). In addition, capacity building and support to urban planning will focus on improved resource efficiency, reduced environmental impacts and increased resilience for urban populations against climatic and environmental risks.

Summary of responses to issues raised in previous annual reviews
Logframe Indicator 2.1 was amended to recognise that BCs need to demonstrate their programme’s eligibility for drawing down ICF funds.

Recommendations
The ICED Facility should:
- explore with the ICF Secretariat whether there is demand to strengthen the assessment of ICF attribution through the application of the ICF tool developed in Year 3;
- engage more systematically with the Climate and Environment cadre (including its Head of Profession) and the Climate and Environment Department to ensure that DFID is getting the most out of what the ICED Facility can offer in this area.

Output Title	ICED Facility: Knowledge management, research and policy influencing mechanisms in place to improve the basis for international dialogue and action on the infrastructure enabling environment and cities that drive sustainable, inclusive growth
Output number per LF	3		Output Score		A+
Risk:	Moderate		Impact weighting (%):		20%
Risk revised since last AR?	No		Impact weighting revised since last AR?		Yes

Indicator(s)		Milestone(s)		Progress
3.1 Number of quality assured knowledge products (KPs) delivered.		Year 3: 20		Exceeded: 23
3.2 Number of active learning sessions led by ICED (i.e. Events., Roundtables etc.)		Year 3: 12		Exceeded: 14

Key Points
The ICED programme has a significant knowledge and learning component which is critical to the overall success of the Facility. The knowledge that is shared emerges from a mix of (i) drawing lessons out of scoping/design work for wider dissemination (bottom-up), and (ii) providing guidance around emerging issues on DFID priorities to feed into programme scoping and design work (top-down).

During Year 2 the Facility had concentrated on how to share learning in a way that enabled DFID advisers to take up the learning. This led to a new knowledge and learning strategy that was focused on providing more easily digestible, demand responsive material during Year 3. The knowledge products that were shared this year comprised:
- Thematic studies to inform the evidence base for programming: eight knowledge products were produced including; how to address violence against women and girls (VAWG) and broader safeguarding issues in in urban and infrastructure programmes;
- Tools, approaches and frameworks: seven knowledge products, providing practical guidance on how to deliver better infrastructure programming, e.g. for selection of different WASH technologies as well as a decision tree for digital options;
- Summaries of key learnings from DFID roundtables. The roundtables addressed (i) the future of DFID’s infrastructure technical assistance programming; (ii) Women’s Economic Empowerment, a round table co- hosted with British Expertise, and (iii) scenario planning.
- Case studies and blogs – based on country case studies on urban finance options in India and Uganda (co-produced with the New Climate Economy), as well as urbanisation trends in Zimbabwe. ICED also delivered three blogs on the informal economy, smart cities and community finance.

The ICED Facility delivered 14 ”active learning sessions” on topics related to the urban informal sector, governance and infrastructure technical assistance which received good feedback. Some of these sessions sought to share learning emerging from work package on specific topics, others responded to specific DFID requests on priority themes, such as VfM or the future of DFID Infrastructure Technical Assistance.

Summary of responses to issues raised in previous annual reviews
The Year 2 Annual Review made several substantive recommendations on knowledge and learning:
- focus on systemising learning and take up of evidence by DFID and external partners, in order to articulate how knowledge and learning is leading to improved outcomes.
- focus on sharing knowledge products externally to ensure knowledge and evidence generated through programme design is contributing to DFID programming and reaching to a wider audience.
It was also recommended that the DFID ICED team should share information and learning more frequently across the Growth and Resilience Department and DFID.

An Action Plan was produced in Q1 and Q2 according to the revised Logframe. DFID subsequently agreed to drop this indicator to facilitate flexibility in ICED K&L responding to DFID demand, although the Action Plan is still an important feature of the K&L.

In order to strengthen internal outreach ICED increased the number of number of active learning sessions, changed the Quarterly Lesson Learning sessions (including co-hosting with DFID) to respond better to the interests and availability of DFID advisers, and produced over 40 two-pagers/ simple case studies to describe ICED activities and which match better the typical DFID advisory demand.

ICED also increased the number of dissemination channels. This included both online (with a website, regular new articles on the ICED Medium Blog[1] and the launch of the ICED twitter feed), and in-person knowledge sharing.
[1] https://medium.com/iced-facility

Recommendations
- The ICED Facility’s Knowledge and Learning should focus on addressing the issues raised by the core set of country offices and the guidance provided by the Strategic Advisory Panel.
- A tiered approach to dissemination to potential users, with different products for different audiences should help to support prioritisation while still reaching a wide audience. Specific consideration should be given to the next steps for dissemination of the tools, approaches and frameworks developed this year.
- The ICED Facility should also continue to invest in dissemination through the website to ensure all relevant ICED material is fully accessible to DFID, DFID programmes and broader stakeholders.

The Year 2 Annual Review also discussed international influencing under this Output. Feedback during this AR was that this is an area that DFID staff have to lead on and where demand for technical inputs can be limited. On the occasions where expert technical inputs are needed they may still be sought through this Facility.

Output Title	CoST: CoST creates a more transparent enabling environment for publicly procured infrastructure by establishing effective government systems to publish project information through the implementation of a scaled-up business plan
Output number per LF		4	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Outputs
4.1 CoST develops and publishes: a) The ITI methodology that measure transparency within public infrastructure and that will be implemented at a national level by stakeholders is developed and published b) An ODS for infrastructure projects with OCP based on the Open Contracting Data Standard and the CoST IDS is developed and published.	Year 3 (a) ITI and (b) ODS published	Partially met- methologies developed but not yet published: (a) CoST Honduras led the development of the ITI indices and methodology and published their first Index in January. However, it has taken longer to identify a second country, and Guatemala is now testing the ITI with the results expected in April. A beta version will then be published in Q3 2018. CoST will then encourage other countries to test the beta version before a final version is launched in 2019. / The ODS for infrastructure project has proved more complex than expected. These issues have now been resolved and a new workplan is in development. The aim is to publish a beta version at the International Open Data Conference in Buenos Aries in September 2018.
4.2 Training on implementing CoST is delivered in member countries: a) Number of Government staff trained; b) Number of civil society or media representatives trained; c) Number of private sector representatives trained.	Year 3: (a) 1,650 (b) 500 (c) 150	Met - (a) 3,120– exceeded (b) 541 – exceeded (c) 79 – partially met. The low figure for the private sector indicates that the case for training the private sector on the type of data they will be interested in using has not been made. CoST will be developing the case with their Members over the next few months.
4.3. # International and regional organisations recommending CoST tools and standards	Year 3: 3	Met 3 – Transparency International’s new Integrity Pact for Infrastructure recommends the use of the CoST Infrastructure Data Standard. The World Bank Infrastructure PPP team have agreed to further test the CoST tools and standards as part of their PPP Disclosure Framework, following a successful testing process in Honduras. CoST are also developing a proposal with the World Bank Open Contracting team for funding from PPIAF to develop guidance and case studies on CoST.
4.4 Number of knowledge products (KP) that capture activities/results/lessons from implementing CoST that are disseminated.	Year 3: 7	Met: 7
4.5 £2.5m in additional funding is secured to fully fund the new Business Plan.	Year 3: £1m	Exceeded £1.18m – The Dutch Ministry of Foreign Affairs have agreed to renew their funding agreement with CoST. (€1m over 4 years). The FCO South East Asia Prosperity Fund has also agreed to provide £300k over 3 years.

Key Points
CoST directly addresses the challenges of mismanagement, corruption and inefficiency in public infrastructure by working with government, industry and civil society to promote greater transparency and accountability. DFID supports CoST as addressing these challenges is critical to improving the enabling environment for infrastructure and urban development that ICED is trying to address. Greater transparency and accountability helps to inform and empower citizens, enabling them to hold decision-makers to account. Informed citizens and responsive public institutions are mutually reinforcing and help drive reforms that reduce mismanagement, inefficiency, corruption and the risks posed to the public from poor quality infrastructure.

Through the last year, CoST implemented the new Business Plan that was agreed with DFID in 2016, and covers the period mid-2017 to mid-2020. Overall this has felt successful, and in particular, CoST have built on their successful relationships with the World Bank’s PPP team, and new parts of the UK government to implement CoST methodologies in new countries.

CoST currently works in thirteen member countries including the five DFID partner countries (Afghanistan, Ethiopia, Malawi, Tanzania and Uganda) and two additional Fragile and Conflict Affected States (Honduras and Ukraine). It is also exploring the potential for a CoST programme in Burma as part of the Cities & Infrastructure for Growth (CIG) programme and with British High Commissions in India and Colombia to explore how CoST could add value to UK investment in infrastructure in the respective countries. This work helps to contribute towards DFID’s Economic Development Strategy of stronger, more accountable and more open governance institutions and making it easier for companies to enter and invest in markets of the future. This is a critical part of the enabling environment for infrastructure and urban development that ICED is trying to address

During the reporting period the International Secretariat has continued to support Members with their programmes and promoted the importance of transparency and accountability in public infrastructure to the broader international community. Particular highlights not mentioned above include:

1. Publishing a new Business Plan based on the outcomes of the Strategic Review that aims to increase CoST’s global footprint.
2. CoST co-sponsored Open Contracting 2017 with the Open Contracting Partnership, Hivos, The B-Team and Article 19 helping to promote the lessons from the initiative to 200 open contracting practitioners from over 30 countries.
3. Interest in joining CoST from several G20 countries including Argentina, Indonesia, Mexico and South Africa plus interest in DFID partner countries such as Ghana, Liberia and Burma.
4. CoST participated at the World Bank’s Infrastructure Governance Roundtable in Cape Town, hosted by the Development Bank for South Africa (DBSA), the G20 Infrastructure Working Group Symposium in London and at the Open Government Partnership (OGP) Americas Regional Meeting in Buenos Aries and an Inter-America Development Bank Forum in Lima.
5. Over 2000 participants from government, civil society and the private sector participate in over 80 awareness raising events and meetings.

Collaborating with HMG
Following a presentation at the Professional Development Conference (PDC) for DFID Advisors held in Nepal, CoST has been working with the British High Commission in India to explore Government of India nterest in CoST. A Scoping Study has been commissioned that focuses on the potential for CoST to help safeguard infrastructure investments associated with the India Strategic-Partnerships and incentivise UK firms to invest in India. The UK Embassy in Colombia has also commissioned a Scoping Study with a similar approach. The findings from both studies are due in May. The PDC also led to working with the DFID Office in Burma to identify potential interest in CoST within the Government as part of the CIG programme. Commissioning a Scoping Study is currently under consideration.

CoST have explored interest in CoST tools in Liberia and Ghana through the DFID funded AFCAP programme which is developing technical manuals for the road sectors in each country. A Scoping Study that will identify the added value of CoST in Liberia is likely to be commissioned shortly funded by the Millennium Challenge Account. CoST are currently in discussions with a range of stakeholders in Ghana with the Institution of Engineers Ghana taking the lead.

CoST and the ICED Facility, in association with DFID, convened a roundtable meeting in London on the theme: ‘The Role of Governance & Transparency in DFID’s Infrastructure & Urban Programming’.

CoST also continue to have an excellent relationship with the FCO Prosperity Fund. This has led to the Central America Prosperity Fund providing £100k to fund a six month capacity building programme for the CoST programmes in the region, and to the South East Asia Prosperity Fund agreeing in principle to provide £300k in funding over the next three year to support CoST programmes in Thailand and Indonesia.

Summary of responses to issues raised in previous annual reviews

In the last annual review, CoST was encouraged to focus on targeting DFID partner countries to build CoST partnerships. Whilst steps have been taken as set out in the previous section, this has not yet led to DFID partners joining the programme. CoST have also found that primary demand for CoST tools has come from the emerging economies where there is considerable scaling up of public infrastructure but not necessarily the systems to manage the investment.

CoST is currently developing a growth strategy. A key element of this is working with DFID over the next twelve months to encourage 2 or 3 DFID partner countries to join CoST. CoST are also prioritising those countries who are members of the Open Government Partnership (OGP) with commitments to implement open contracting programmes, and anticipate that Governments will then be more open to the CoST approach. OGP are also willing to introduce their government counterparts to help initiate the dialogue.

CoST was also to keep DFID appraised of progress on the ITI and the suggested second country for testing, to ensure that this component gets back on track. A summary of the current status of this project is included in Output 3.1(b). CoST also had to set more realistic milestone targets as part of the new CoST logframe. These were developed with six of the eight met or exceeded over the last twelve months.

Recommendations
- Continue developing the growth strategy, and keep DFID appraised on ITI progress.
- Amend the ICED logframe, based on the experience over the previous 12 months, including increasing the target for the number of projects disclosing data, and slightly reducing the number of countries expected to join CoST.

Output Title	World Bank: Improved analytics and diagnostics, planning of economic reforms and institutional and skills development in cities.
Output number per LF		5	Output Score	A
Risk:		Moderate	Impact weighting (%):	5%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
5.1 Number of knowledge products or tools produced and approved/implemented to support improved information and knowledge in high priority areas for City Governments to enhance economic development	Year 3: / 4	Exceeded / A number of papers have been produced including 2 for Nigeria and 3 for Cameroon in partnership with local research institutes and experts.
5.2 Number of client cities planning specific policy reforms or investment projects as a result of the assistance.	Year 3: / 2	Met – clients in Addis Ababa, Kampala, Douala and the wider Lagos region are planning specific policy reforms and / or investments as a result of the assistance. E.g. Greater Kampala strategy including numerous planned flagship projects and investments; transport and other infrastructure investments through PPPs in Douala; -governance website for obtaining construction permits in Addis Ababa; and finally, transport corridor investments in the South West region of Nigeria.
5.3 A) Number of workshops, trainings and knowledge exchange fora organized with client City Government staff; B) % of participants ‘rating as " very satisfied" or "satisfied"	Year 3: / A) 2 B) >80%	Exceeded – In terms of high level validation workshops to discuss findings and recommendations of the policy reports in each country, 4 workshops were held, one for each country engagement. The average of workshop evaluation sheets indicate the following levels of client satisfaction: Kampala – 95% satisfaction; Addis Ababa – 89%; Cameroon – 94%
5.4 Proportion of client City Government stakeholders rating the support provided by the project as very good or excellent on a four point scale	Year 3: 90%	N/A. This will be assessed through a satisfaction survey to be commissioned by the World Bank’s Trust Fund reporting team, at the time of the annual reporting to DFID (after the end of their fiscal year ending June 30).

Key Points
The World Bank programme aims to support African cities enhance their economic growth and job creation performance. It supports city governments in Africa in two areas - 1) economic analyses that fill knowledge gaps that policymaker’s face, 2) institutional support and capacity development to strengthen their ability to plan and implement relevant reforms.

Since the last review the programme has engaged two additional countries – Nigeria and Cameroon.
In Nigeria the WB engaged with the wider Lagos area raising awareness among policy makers on the importance of spatially coordinated infrastructure investments and complementary reforms. In particular, the report focused on transport corridors and the need for complementary reforms in land use planning and investment in other infrastructure to link local areas and firms with the main corridor.

Cameroon has been an interesting engagement with a country where the government explicitly attempts to limit and cap the urbanization rate. The WB’s analytical work on city competiveness has shown that cities in Cameroon are more productive than rural areas. Based on this work, the Government of Cameroon has expressed interest in investments to improve city competitiveness in Douala and Yaounde – with a particular focus on public transport investments.

Overall this has been a successful programme that has produced research and advice on local economic development plans which are being taken up by city governments. Alongside the development of knowledge products, the just in time technical assistance provided by the project has been successful in helping government counterparts in planning relevant reforms and investments.

There have however been some key challenges encountered in delivery:
City governments are under pressure to come up with immediate solutions and interventions to address the economic challenges that their cities face, particularly youth unemployment, and have expressed impatience at having to wait for the studies and their recommendations to be finalized. A lesson learnt is that quicker and more targeted diagnostics on specific issues (e.g. infrastructure feasibility studies) are more immediately implementable by policy makers.

Clients also have some frustration that donors often finance technical assistance without the identification of the follow on bigger investment financing needed to implement the recommendations of the technical assistance. The WB have tried to mitigate this by establishing close linkages with operational teams working on our target countries to ensure our research recommendations inform operational design components. This raises a broader challenge of working at a city level to deliver targeted support that then requires national level buy in. This remains one of the ongoing challenges of supporting urban development initiatives.
Summary of responses to issues raised in previous annual reviews
A recommendation from last year was for the WB team to engage with other DFID funded work happening in Uganda. This has been implemented. The World Bank and DFID now jointly chair a recently formed urban donor working group, which has been meeting regularly and has discussed support to the GKMA strategy, among other issues. DFID representatives also attended the recent validation and launch workshops for the Kampala report and economic development strategy. Counterparts at the National Planning Authority and Kampala Capital City Authority have requested development partners to jointly pool their resources in support of the implementation of the strategy and of cross metropolitan investments.
This will be the last year of the WB programme. The DFID’s Cities Adviser should work with the WB team to consider how the learning from this programme can be used in both future DFID urban programming and can be supported through other partnerships.

Recommendations
DFID to work with WB on closing out the programme and ensuring findings are taken up and used by others.

Output Title	Cities Alliance: Knowledge management, research and policy influencing mechanisms to improve the basis for international dialogue and action on the infrastructure enabling environment and cities
Output number per LF		6	Output Score	A
Risk:		Moderate	Impact weighting (%):	5%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
6.1 Number of global advocacy events on Equitable Economic Growth in cities has raised awareness on the relationship between public goods and equitable economic growth	Year 3: 1 / Delivered: 6	Target was exceeded. / Responding to external demand, the JWP (Joint Work Programme) has convened in 6 events this year, exceeding the targeted milestone by 5
6.2 Number of peer reviewed global knowledge products are being produced per year addressing the relationship between urbanisation, inequality and growth in cities	Year 3: 1 / Delivered: 1	Target was met. A global knowledge product was delivered documenting the link between inclusive public spaces and the livelihoods and productivity of the informal economic sector.
6.3 Number of completed, peer reviewed Institutional Enabling Environment Reports (IEER) for JWP Countries-Cities (Bangladesh, Uganda, Ghana and Kenya)	Year 3: 2 / Delivered: 2	Target was met. Two reports were completed, for Cape Coast and Agona Swedru (Ghana), providing assessments of the institutional enabling environment of these cities and its impacts on their capacity to deliver public goods and services to formal and informal businesses.
6.4 Number of peer reviewed city level assessment reports and policy briefs on how to foster equitable economic growth in JWP cities delivered	Year 3: 4 / Delivered: 4	Target was met. Four Local Assessment Reports (LARs) were delivered for cities in Uganda and Bangladesh, including research and recommendations on the public goods and services identified by the city-level partnerships to support equitable economic growth.
6.5 Cities Alliance membership increases by 2 members per year (annual)	Year 3: 2 / Delivered: 2	Target was met. The United States Agency for International Development (USAID) and the / International Institute for Environment and Development (IIED) joined the Cities Alliance.

Key Points
The key objective of the Joint Work Programme (JWP) on Equitable Economic Growth is to enable local governments in partner countries to deliver public goods and services, which are accessible and responsive to the needs of all people and businesses in cities.

The JWP met all its targets in Year 3, and exceeded some targets, in particular a real strength has been the development of knowledge products and the advocacy of the programme. There have been some major successes on the advocacy side including the organisation of an interactive panel at the 4th World Forum of Local Economic Development in Praia (Cap Verde) which was focused on gender-responsive services as a pathway to women’s economic empowerment in cities.

Putting the first three years of the JWP into perspective, the following two early learnings and impacts are observed:
- Partnerships on Equitable Economic Growth in Cities receive high political buy-in and mainstreaming support from beneficiaries and development partners alike with strong interest from other donors such as GIZ.
- The Cities Alliance has already fostered a better understanding of the feasibility of future multi-year Technical Assistance Programmes in priority countries to foster equitable economic growth in secondary cities. A large amount of ground work has been laid by this programme in identifying issues and future action in these cities which follow up technical assistance could support.

A key success in this period has been the development of a joint partnership with the World Economic Forum (WEF) around a global activity to support the programme in Uganda and Ghana. This has resulted in a joint programme approach - Local Economic Acceleration through Partnerships (LEAP) - which will a) identify major drivers of revenues and expenditures at the city level including borrowing capacities with the objective of improved understanding of challenges and potential opportunities in improving leverage, and b) set up a facilitated dialogue with domestic and international private sector representatives at the city level on investment requirements and opportunities. The results of this engagement at the city level will inform national debates and a global knowledge product, which provides field-tested guidelines for investments in secondary cities in Africa to achieve equitable economic growth. Given the challenges with pursuing the programme in Nigeria (outlined below) it was agreed to reallocate some of the financial resources earmarked for the Nigeria work to the LEAP project within the JWP programme.

Key Challenges
As mentioned above there has been a challenge in rolling-out the programme in Nigeria and this was identified early on in this year of the programme. These challenges were based on a) the difficulties in finding a suitable implementing intermediary body with adequate in-country capacity to facilitate the work at the local level and b) the high transaction costs related to the city selection process due to the political economy in Nigeria, in which most of the political decision-making power is concentrated at the state level. In consultation with DFID it was agreed that the financial resources earmarked for the Nigeria work would be partly reallocated to the programme in Uganda and Ghana.

Summary of responses to issues raised in previous annual reviews
Year 2 recommendation: DFID to ensure the work of this programme in Uganda is linked in with the CIG programme, given the secondary cities focus of both programmes. The CIG programme has met with and engaged with the Cities Alliance in Uganda including joining the Cities Alliance Assembly meetings in Jinja in 2017.

Suggested logframe changes:
- Output indicator 6.2: As elaborated above, the JWP will produce an additional global knowledge product in year 5 that summarises the engagement of the LEAP activity, which increases the cumulated total deliverables to 8.
- Output indicator 6.3: Due to the strategic decision not to pursue the programme in Nigeria, the milestone value in Year 4 will reduce from 10 to 8.
- Output indicator 6.4: Due to the strategic decision not to pursue the programme in Nigeria, the milestone value in Year 5 will reduce from 20 to 16.

Output Title	Strategic Opportunities Fund (SOF) : Support the utilization of the SOF
Output number per LF		7	Output Score	A
Risk:		Moderate	Impact weighting (%):	5%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
7.1 £ value and number of sub-sector projects approved by SOF	Year 3: 0	As per the 2017 Annual Review it was agreed not to put forward any new projects for funding under the SOF in Year 3.
7.2 £ value and number of projects approved by SOF that have achieved their intended outcome as defined by DFID (on a case by case basis)	Year 3:0	As above.

Key Points
The SOF was set up to support emerging opportunities across, urban, energy and infrastructure issues. However it was agreed at the last Annual Review given the number of components and projects funded as part of the ICED programme that no new funding would be allocated to new projects under the SOF for thay year. Instead this last year has seen the development and consolidation of the existing projects funded under this component. The score of A for this output is therefore based on successful development of these current projects.

This includes the World Resources Report on Cities delivered by the World Resources Institute. DFID agreed £500k funding to the second phase of the report last April and the WRI are on track to deliver against all milestones by June 2018. In particular the project has delivered well received issue papers on housing, energy access and the informal economy. There is potential for DFID to consider support under the SOF for the third and final stage of the WRR but this will be considered in the next few months.

The SOF also supported UN Habitat with a small £200k grant to support the development of the State of African Cities Report on FDI flows into African Cities. All funding to this project was completed in 2017 and the report is now in the final stages of editing and proofreading with the intention to publish this year. UN Habitat held a peer review process for the report with a meeting of key experts (some of whom were nominated by DFID) to peer review the report and provide critical challenge to ensure its analysis is robust and recommendations are useful.

The final SOF component is providing support to Chatham House research on Extractives in Development: Implications for Power and Infrastructure Planning in a carbon-constrained world. This research output has taken longer to develop than planned, however is now entering its final phase. A draft final report has been approved by DFID advisors, and provided all comments are incorporated, it is envisaged that this will be completed by end of May 2018.

Summary of responses to issues raised in previous annual reviews
N/A
Recommendations
DFID team to work closely with Chatham House to ensure effective completion and close-out of the report.

Output Title	Coalition for Urban Transitions (CUT)
Output number per LF		8	Output Score	A+
Risk:		Moderate	Impact weighting (%):	5%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
8.1 - Number of flagship country urban roadmaps developed in low income countries (Tanzania and one additional country in Africa - TBC)	N/A - Roadmaps start to be developed.	On Track / • Tanzania: Coalition launched the Tanzania Urbanization Laboratory (TULab) with three meetings; government endorsed three research pieces to inform final national transitions assessment and roadmap. / • Ghana: Coalition invited to support the government in its 5-year review of National Urban Policy (NUP) and implementation;
8.2 - Number of major high impact, high quality, peer reviewed working papers - supported by relevant regional and country case studies -	5 (working papers from 2016 DFID grant)	Exceeded / • 7 working papers from 2016 DFID grant published / • 1 additional working paper published (commissioned by IPCC for their 1st Cities and Climate Conference)
8.3 - Number of published flagship global synthesis reports capturing the findings of various projects within the workstreams and communicated by the coalition’s leadership council and steering group.	N/A	On Track / • Concept note for flagship global synthesis report developed in consultation with key Coalition Members. Report due in 2019.
8.4 - Number of National Media Assessments completed to lay foundation for successful release of national urban roadmaps	N/A	On Track / • The first National Media Assessment is planned for Tanzania in summer 2018.
8.5 - Number of publications in global outlets, national newspapers or leading sector media by senior Coalition spokespeople and champions (op-eds, blogs, long reads or interviews).	1	Exceeded / • 8 op-eds published / • 8 blogs/articles published
8.6 - Number of "meeting proceedings" (to inform bespoke briefing notes and presentations) from successfully completed bilateral meetings with Heads of State / Ministerial / CEO / IFI Head /Senior decision-maker/official level at which Coalition findings and analysis is discussed.	3	Exceeded / • 23 bilateral meetings held with CEOs / Executive Directors briefing them on the Coalition work programme and emerging findings. / • 1 Urban Leadership Council meeting held when launched at COP 23. / • 3 Steering Group meetings held to discuss Coalition strategy and ULC outcomes.
8.7 - National groups of relevant key policy makers and other important champions facilitated by the Coalition are set up and operational in each focus country.	N/A	On Track / • Tanzania Urbanisation Lab (TULab) established with 50+ key stakeholders to give national ministries, local government, donors and academia a forum to exchange policy ideas.

Key Points
The Coalitions for Urban Transitions (CUT) programme is building the economic case for why urban development is critical to a country’s national development. The programme is seeking to influence national governments, in particular the Ministry of Finance in DFID partner countries about the role urbanisation can play in national economic growth. DFID is funding the CUT to produce robust research and evidence on urban development and develop national level urban plans or strategies with two low income countries – Tanzania and Ghana.

In the first year of CUT all targets have been met or exceeded. The Coalition is currently on track to meet its outcomes including the conditions of the agreed 18-month break clause (September 2018). CUT is developing into a ‘go to’ resource to help shape global agendas on cities. CUT produced a major paper for the IPCC on financing for low carbon, climate resilient urban infrastructure, 1 of only 5 formally commissioned papers for the 1st IPCC Cities / Climate Change Conference; hosted the only major dedicated event at the World Urban Forum on the national-local policy interface; and were appointed as the lead on the cities chapter of next New Climate Economy report 2018.

The CUT team were tasked with seeking further funding sources beyond DFID and within the first year they have secured £5m funding from the Business, Energy and Industrial Strategy department to deliver on their cities and climate change work.

Issues and Lessons Learned
.• For the Country Programme, the risks associated with sole reliance on external research teams to deliver the work programme has been reduced by hiring a research assistant and leveraging the work of other local researchers.
• Political uncertainty in Tanzania and slow-developing relationships in Ghana have slowed the development of the Coalition’s work programme. It will be important to continue to revisit the extent to which progress can be made in Tanzania and Ghana at the rapid pace dictated by the grant whilst continuing to ensure that each country retains and builds strong ‘ownership’ of the process.

The CUT programme continues to engage with many of the partners within the ICED programme. In particular in developing the Ghana programme the CUT team are working closely with Cities Alliance given their existing presence and programme work in country. It will be important that this continues to ensure complementarity between interventions and to enable useful leverage of each other’s work in country.

Summary of responses to issues raised in previous annual reviews: N/A

Recommendations
- There are no amendments to the logframe. However, one clarification is that having assessed the most opportune moment for impact, the global flagship report will be developed in launch at the end of 2019 (rather than the beginning).
- DFID and BEIS to ensure an effective approach to working with the CUT programme, ensuring joint learning can be achieved for the cross-Whitehall agenda on cities.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

VfM performance compared to the original VfM proposition in the business case
The programme operates based on the VFM proposition in the BC. In particular, the ICED Facility reports against quarterly KPIs.

Key cost drivers and performance
The ICED Facility provides specialised technical assistance to DFID, primarily DFID COs. The Facility works by developing specific work packages with country offices to deliver a piece of scoping or design work. These are reviewed first by the country office, and then the budget and number of days are signed off by the DFID SRO. This provides two levels of check, both on the content of the work to be undertaken and the costings.

Consulting time accounts for 96% of the Facility’s total spend. The remainder is allocated to travel and expenses. The two key cost drivers are consultant daily rates (fees) and number of consulting days (input unit).

Partner actions to maximise VfM

Economy

ICED Facility: Average consultant rates have decreased by 4.5% compared to Year 2, driven by comparison against a range of benchmarks. Value has been achieved, for example, by combining reports for the same country into a single WP where possible (e.g. for Bishkek and Dushanbe, or in Burma). The fees related to management costs represent 13.2% of the total fees component. Despite some streamlining of programme management this is only marginally lower than Year 2 (13.6%), and shows the effect of reduced WP size.

The Facility has made efficiency savings from its expenses budget and requested to channel the funds to fee rates providing additional work-package delivery. This is subject to approval within a no cost amendment to the contract which will reflect the additionality and ring-fenced budget. The identified funds will be monitored and work-packages approved according to agreed procedure.

CoST achieves economy by outsourcing the International Secretariat function to Engineers Against Poverty, thus it minimises overheads costs and benefits from using its office space, staff, financial management systems and networks. It selects and uses the best quality international consultants by leveraging on alliances through Engineers Against Poverty to engage consultants that have experience in the field. Staff, consultants and Board members travel economy class and are reimbursed for out-of-pocket expenses on the submission of receipts.

CUT has been successful in negotiating fee rate discounts or co-investments from its downstream partners. For example, the Coalition has secured significant fee rate discounts / investment from LSE Cities to spearhead work on national transport and land use policy, and in Tanzania / Ghana, investment from McKinsey and Siemens for work on new urban mobility solutions.

Efficiency

ICED Facility: The Call Down Facility model, originally developed for FCAS, was extended across the portfolio. This has reduced the time and effort needed for accessing consultants across the Alliance, as the contracting mechanism provides each expert with up to ten days of approved consulting time. This has also been a useful way for DFID teams to test out possible ICED engagement. ICED Facility has been able to reduce the time taken to mobilise teams from nine days in Year 2 to seven in Year 3.
CoST increasingly works in strategic partnerships such as with the Open Contracting Partnership, Transparency International and Hivos to develop joint standards, build capacity and organise joint events or knowledge sharing platforms. It also utilises digital solutions to maximise the efficient running of the programme.

The Cities Alliance has leveraged resources through mobilising members of the CA to provide valuable inputs to the programme to date, including leveraging 20% of additional co-financing by grantees to all issued grants and using existing knowledge repositories of members to inform JWP global dialogues and knowledge products.

Effectiveness

The ICED Facility has met or exceeded all its output level logframe targets for Year 3. The core remit of the Facility is to support the design of new and improved programmes for DFID in the areas of infrastructure and cities. The effectiveness of ICED will ultimately be judged by the future successes of these initiatives. Progress towards achieving this outcome and impact level is shown mainly through the agreed logframe indicators at Outcome and Impact level.

In terms of the Facility’s effectiveness to deliver good programme design, the contract includes a performance-related element where 15% of fees are at risk based on KPIs and milestones. The amounts are paid both on a quarterly and annual basis relating to criteria including reporting and annual review scores. ICED also received its first 10/10 on delivery against the ToR for the DFID Ethiopia WASH scoping study. The ICED team noted that they found the qualitative feedback at least as useful as the numerical rating.

Coalition for Urban Transitions: The progress against the logframe indicators demonstrates the emerging effectiveness of the Coalition effort in a relatively short period of time.

CoST drives effectiveness by institutionalising its approach to transparency and accountability within government systems. CoST also uses a result based approach. This is principally through the funding of the CoST national programmes where applicants must meet certain criteria to be eligible for funding, meeting a set of agreed targets to be able to receive the next tranche of the approved grant.

The World Bank project achieves value for money by informing the design of World Bank operations in each of the target countries. The project has so far directly and concretely contributed to new design components in the following operations, including: the	Uganda Support to Municipal Infrastructure Development Program (USMID), targeting 18 secondary cities, starting in FY 2019, and the	Ethiopia Urban Infrastructure and Institutional Development Program (UIIDP), targeting 117 cities, starting in FY 2019.

Equity

The ICED Facility has continued to promote equity through: i) G&I mainstreaming ICED work packages; ii) G&I specific work packages (i.e. disability study); and iii) conflict sensitive programming approaches under FCAS. In particular, the ICED G&I mainstreaming process established durring the year has been consolidated and integrated into the portfolio delivery model

Assessment of whether the programme continues to represent value for money
This original business case proposition on value for money (VfM) continues to be valid. The ICED Facility, being the largest component of the programme, represents a key area of focus for driving VfM. At DFID’s request, the ICED Facility strengthened its VfM reporting during Year 3. Since Y3 Q2, ICED has therefore been providing a quarterly VfM assessment that is based on a selection of 36 agreed quantitative and qualitative indicators. Based on progress against these KPIs as well as against the overall logframe the ICED Facility represents value for money.

Quality of financial management

ICED Facility: The demand led nature of the ICED Facility means that accurate forecasting is more difficult than for a supply side programme. In January 2018, based on historic spend and expected pipelines, DFID agreed to slightly increase ICED’s original agreed Y3 budget.

CUT: The CUT programme has met the quarterly budget variance target and spending is on track. This has been done whilst managing multiple partners, with varying grant arrangements.

Recommendations
- The quarterly monitoring of 36 KPIs gives a detailed picture on VfM. However, there are two significant challenges with tracking and driving VfM on this programme. The reduced focus on contributing to immediate Business Case design makes it hard to assess the efficient and effective conversion of inputs to outputs and impacts. The second, related, issue is knowing whether the inputs are indeed focused on the right issues, so as to lead in due course to the desired outcome and impact. The `Strategic Pivot’ to focus on developing relationships with a core set of countries, and the establishment of the Strategic Advisory Panel are therefore key steps that DFID can take to reinforce this programme’s VfM. As noted above, it is therefore important that this shift is now effectively implemented.
- Tracking 36 KPIs on a quarterly basis itself entails significant costs. A subset of KPIs should be considered that provides a similar level of assurance about VfM.
- The review recommends that steps should be taken to replenish the current ICED Facility to enable it to continue work until mid-2020. This can be done by reallocating funding between components rather than requiring new funding to the business case, with no impact to the current components and workplans.

E: RISK (½ page)

Overall risk rating: Moderate
The overall implementation of ICED continues to be moderate.

Overview of programme risk given the progress so far:

ICED Facility: Across other partners risks are managed through individual reporting mechanisms and regular updates with lead advisers. Risks for each partner are set out below:

The ICED Facility monitors risks through the quarterly reports to DFID. For the Facility a key risk is a lack of demand from country offices and DFID teams. To mitigate this in Year 2 the Facility worked to make connections with most DFID COs and to mobilise teams to respond to requests quickly. In Year 3 this effort was followed by an effort to ensure the right sort of demand by deciding to focus on a core set of country offices and to give stronger strategic shape to the demand through a Strategic Advisory Panel.

A key risk on DFID’s side that was previously identified is the speed at which WPs are approved. However, a delegated arrangement has now been agreed which has proved to work effectively.

The Facility is acutely aware of the potential conflicts. The ICED Facility has set out clear conflict of interest procedures to manage this. Where they anticipate these they have been quick to alert DFID and work with DFID to resolve these.

World Bank: The main risk that the WB project faces is a decreasing momentum or interest in the economic development agenda now that project financing will cease by the end of this fiscal year. The funding for the local consultants will cease and therefore so will the day to day accompaniment and support to client cities. This will have the greatest impact on progress in Kampala and Cameroon, where the planning and implementation of reforms and investments is at the most advanced level. To mitigate this WB is seeking follow on support and investment. In Kampala DFID’s CIG programme is already working with the WB team and the city authority, so this work will be built on once the CIG programme begins implementation in Spring 2018.

CUT: A clear risk management framework for the CUT initiative has been developed. For CUT the main risk is that the analysis and recommendations for each country and global research pillar (policy, economics, finance) are ignored by governments and do not translate into policy changes. The critical way this is mitigated is by ensuring a strong process of partner engagement and building buy-in in each country and at the international level. The Coalition monitors risks through regular meetings and communication amongst the partners, and collaborative planning and participation in engagements.

Outstanding actions from risk assessment
The programme risk matrix was updated following recommendations from last year.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

The ICED programme is currently on track for all deliverables against agreed work plan and logframe

Performance of partnership (s)

The partnerships with all suppliers under the programme have been consolidated over the last year and are working well.

ICED Facility: The team engage regularly on a fortnightly basis and provide detailed information on work-packages through the development tracker which highlights risk on poor delivery and provides mitigating actions/solutions providing assurance. Forecasting on a monthly basis provides greater accuracy and control over spend and remains within tolerance.

The Facility has performed well under their complex KPI/PbR structure which is scored and achieved on a quarterly and annual basis, and overall feedback from DFID clients is positive. The Facility lead supplier has yet to sign the revised DFID Terms and Conditions as well as the Supply Partner Code of Conduct.

The Facility lead supplier is currently part of the new SRM scorecard assessment pilot which is being developed and evaluated. To date this is still in its infancy and there is dialogue with PCD on the structure and methodology.

CoST, WRI and CA partnerships have been developed over the last year with quarterly reports and
regular feedback provided with the DFID team. Financial performance according to agreements are
consistent and accurate, allowing for slight flexibility especially relating to foreign exchange variances.

The Chatham House accountable grant component has required three amendments which has pushed back delivery of the final paper.

Asset monitoring and control
The ICED programme does not acquire any assets. Any IT software or platforms developed are open access, open source and will constitute a global public good.

G: CONDITIONALITY
Update on partnership principles (if relevant) - Not applicable.

H: MONITORING & EVALUATION

Evidence and evaluation
There is provision for DFID to commission an independent review of the ICED Facility. It had previously been expected to take place in mid-2018, however with the setting out of the Strategic Pivot in early 2018, it is recommended that takes place in late 2018 or early 2019 to be able to assess implementation of the Pivot.

Given the nature of the ICED Facility interventions, providing support to COs and support to strategic priorities and international influencing, the approach to continual evaluation and monitoring of expected results places a stronger emphasis on learning. This learning needs to be able to inform programme direction and feedback into programme design. This approach requires the ICED team to regularly engage in reflections on what they have learned so far and review the delivery of individual work packagess. At present this is being done through learning sessions and events which are opened up to relevant DFID advisers, as well as sessions at wider events, such as the Advisor Professional Development Conferences.

Monitoring progress throughout the review period

Meetings have taken place with all DFID partners under ICED on a regular basis to clarify questions and agree on forward work plans.

In the case of the ICED Facility, the team and DFID meet on a fortnightly basis to discuss progress in DFID and engagement, and to clarify any outstanding specific issues. The ICED Facility have implemented a new work package tracker (as mentioned in the VfM section) which provides an excellent overview of all past and current WPs and links to whether a relevant knowledge product will be produced from the WP. This has already been a hugely useful way to monitor the overall number of WPs being approved and to monitor the spread of these across the cities, energy and infrastructure sectors.

CUT: BEIS will be implementing an independent evaluation contract for their proportion of funding to the CUT programme. DFID will work with BEIS to consider areas being funded by both DFID and BEIS that could be evaluated under this contract.

CoST: CoST have developed a new progress reporting format for CoST Member countries to complete every six months has also been developed.

Cities Alliance: Based on the Results Framework of Cities Alliance JWP, the ICED logframe as well as annual workplans, a distinct reporting system has been established to allow for product-oriented monitoring. All implementation entities of the JWP are obliged to provide a bi-monthly update.