Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Improving Livelihoods and Land Use in the Congo Basin (ILLUCBF)

Programme Value: £18.75m		Review Date: July 2017
Programme Code: 204956	Start Date: July 2015	End Date: August 2020

Summary of Programme Performance
Year	2016	2017
Programme Score	A	A
Risk Rating	Major	Severe

To support local ownership and management of natural resources by policy reforms and establishing social enterprises, while demonstrating the validity of such an approach and sharing lessons across the region on differing approaches.

Summary of progress and lessons learnt since last review

The programme continues to operate in a difficult political and security environment. The situation in Democratic Republic of Congo (DRC) remains volatile, with elections scheduled for Dec 2016 indefinitely postponed. This has made engagement with the DRC interim government difficult, and official contact between UK Government officials and DRC Government officials is discouraged. Travel by both DFID staff and the international Implementing Organisations (IOs) has been delayed. Insecurity and political risk related to engagement from the UK could have been better integrated into the programme from the start but local national organisations continue to operate.

While the programme is scoring an A, there needs to be improvement in delivery and supervision from implementing partners to ensure it can meet its objectives. The log-frame is not accurately capturing activities, nor driving a sufficient level of ambition. These issues reflect the rushed start of the programme. As the programme was designed within a short time-frame it was important that the programme components successfully completed their inception phases and started implementation quickly. This affected the design quality of some elements, in particular the management tools such as the log frame.

Pilot sites for community forest enterprises have been identified to drive the process of formal recognition of rights and ownership, and the regional trainings have to build national capacity. Contracts with Community Forest Enterprises in Cameroon are being signed and communities are being supported to start businesses.

One important lesson related to community enterprise development is the length of time needed to develop an enterprise. The capacity gap is large, and preparation work with communities has taken longer than expected; likewise, World Agroforestry Centre (ICRAF) and TMP systems (a management consultancy specialising in natural resources and sustainability) had to provide more support to the implementing organisations to ensure they could work effectively with forest communities. Enterprise activity is related to the timing of when the forest goods are produced, therefore development needs to be timed to coincide with these seasons.

Summary of recommendations for the next year

DFID needs to review the log-frame to ensure it captures all the activities undertaken and is translating the three components into an overarching log-frame with specified milestone indicators confirmed with each component. A single results framework will drive co-ordination and collaboration between the different components, especially in Cameroon where collaboration and co-delivery is essential and should be targeted related to entrepreneurship and enterprise development. DFID and the main international implementing organisations should co-develop another programme wide co-ordination event, and explore the opportunity for a regional event bringing national partners together.

Signing of the contracts with the Community Forest Enterprises (CFEs) is a priority for the Dryad component and potential delays should be discussed with DFID and tracked in relation to risks. The signing of contracts and dispersal of the funds to support enterprises is essential to overall programme delivery. Sites selected for the piloting of community forestry approaches needs to be continued and lessons learned shared across the components.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204956/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204956/documents

Background
In 2015, Ministers approved £18.75million for ‘Improving Livelihoods and Land Use in Congo Forests’ (ILLUCF) which will operate regionally in five Congo Basin countries; Republic of Congo (RoC), Central African Republic (CAR), Democratic Republic of Congo (DRC), Cameroon and Gabon. The programme was announced by Ministers at the United Nations General Assembly in September 2015 and is considered part of the UK support to the Central Africa Forest Initiative (CAFI). The programme began in July 2015, with the Dryad component initiating work in August 2015, and the two other components starting later in May 2016 for the Rain Forest UK DRC component and in April 2016 for the CoNGOs International Institute of Environment and Development (IIED) led component (see component number 2 below for more details)..

The long term impact of the programme is to reduce poverty and deforestation rates across the Congo Basin. The outcome is ‘Improved land use governance that supports forest dependent communities’.

The Congo Basin is the second largest tropical rainforest in the world and is of global significance, providing both global and local goods and services. These forested areas are home to about 30 million people and support the livelihoods for over 75 million people. However, they are an important resource which is under threat from a wide variety of sources, including numerous market failures and governance shortfalls. This programme sets out to address some of these barriers by enhancing the involvement of local communities and improving transparency in forest and land use management and in decision making and seeking to ensure livelihoods are sustained by demonstrating viable business models. The regional nature of the programme provides a good opportunity for learning across countries around what works and what doesn’t for community forestry. Alignment of the programme with CAFI also provides a good opportunity to link community forestry work with other significant flows of climate finance in the region and to demonstrate that community forestry can be an effective means to deliver Reducing Emissions for Deforestation and forest Degradation (REDD)+ objectives.

Currently, decisions on the use of forests in the Congo Basin are being made in the absence of good information, in a non-transparent manner, and without adequate accountability. There is often confusion with overlapping land allocation rulings by different authorities. Overall, there is little evidence that these land use decisions have considered existing forest occupation by community users, deforestation or delivered real or sustainable benefits to impoverished forest communities. In all five countries the capacity of both government institutions and of organisations that represent or work with forest communities is very limited. There are opportunities to strengthen the legal and regulatory frameworks for effective community forestry, and to build the evidence and organisational capacity of communities in order to influence national policies and processes.
Activities include:
1. Promotion – of effective community based forest models to increase participation, transparency and accountability in land use planning and decision making processes
2. Capacity building and networking - to strengthen the voices of communities and their legitimate representatives, and to build alliances and capabilities of these beneficiaries and stakeholders.
3. Demonstrating innovative approaches to Community Forest Management – by providing support to strengthen legal frameworks for Community Forestry, testing different approaches across the region and through provision on financing for sustainable CFEs.
4. Research and evidence – acquiring the evidence both locally and from good practice elsewhere that can be applied to bringing innovative solutions to the issues.

The three active components in operation are:
1. Dryad: Led by World Agroforestry Centre (ICRAF) in partnership with TMP systems focussed on Cameroon and to establish viable community forestry businesses. It supports communities to operate and establish enterprises using a payment by performance finance model.
2. CoNGOs: NGOs collaborating for equitable and sustainable community livelihoods in Congo Basin forests. This is a consortium of national and international NGOs lead by the International Institute of Environment and Development (IIED) across the five countries. Activities range from legislative analysis to policy development and piloting community forestry approaches.
3. DRC programme: This component is led by Rainforest Foundation UK (RFUK) with delivery done in country by national partners with some capacity development. The focus is on the implementation of community forestry legislation and the piloting of community forestry approaches.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Outcome Indicator	Milestone	Progress
Extent to which countries have effective multi-stakeholder process on land use and improved transparency on land allocations (number and extent of effectiveness): a) number; b) quality of the process	None set for this year	Barriers have been identified in each country, and community mobilisation and support has started to address these barriers and guide future operations. We will revisit this indicator when we revise the log frame.
Number of hectares (Ha) of forest supported through the programme: / a) formally designated to communities; and or / b) sustainably managed by communities	(a and b) / DRC: 0 / Cameroon: 52,500 / Congo: 0 / CAR: 0 / Gabon: 0	Community forests are currently at a pilot stage.
Regional/national or sub-national policy frameworks/plans and programmes that have been influenced by the programme to include community based forest management and/or improved forest communities' rights	3 national forest and farm policy processes and market reforms per country (other countries - IIED) - 1 land use planning pilot exercise in place (DRC)	DRC National Round Table on Community Forestry and technical working groups in place, National Strategy on Community Forestry in draft form and ready for validation (RFUK). / DRC Land Use Planning pilot: Ongoing legal and policy analysis on Land Use Planning and engagement with planning ministry. Study on “Land use planning in DRC and Cameroon: towards meaningful participation and securing of community land rights” ready for publication, and draft Rainforest Foundation UK Land use Plan methodology prepared.
Number of people or community groups supported by the programme who now feel they have improved their tenure rights and/or increased their Community Forests (CF) income: / a) # people with secured rights (perception); / b) # CFs with increased income; / c) # community groups with secured rights	DRC: 0 (for a) / Cameroon: 15 CFs with 10% increase in net income (for b) / 5 countries: 10 ( for c) / A total of 25 community groups reached	CFEs are not in operation and the pilot sites have only just been identified. 12 CFs have been identified in Cameroon, and 13 other pilot sites identified, across 3 countries.

Overall output score and description

The programme is assessed as scoring an ‘A’, given its progress against outputs (see below), and despite a challenging operating environment. Delivery and supervision needs to improve to ensure the programme is meeting expectations and remains on track to deliver its outcome and impact. The current log frame was developed as the programme was being set up does not capture all activities or drive ambition well, or in its current iteration translate into achieving the outcomes for this years’ milestones. The log frame needs to be reformed with indicators and milestones completed, which was not done for each indicator this year.

As the CoNGOs and RFUK led components only started in April/May 2016, activities over the last year have primarily focussed on moving from inception to implementation phase, finalising the country diagnostics and identification of pilot sites for community forest enterprises. It is believed that outcome level reporting will improve in the coming years as the output activities lead to operational enterprises.

The Dryad programme has been delayed in signing contracts with community enterprises, but has mapped out a timetable to move this forward. Any delays or impediments on signing of contracts with community forest enterprises needs to be reported to DFID and should be tracked closely, as failure to sign contracts will impact on the ability of the programme to deliver its outcome, and effectively demonstrate the utility of the enterprise approach.

In Cameroon, greater co-ordination of activities across the different components is needed to ensure that there is no duplication of effort and actions are complimentary. Both of the projects have prioritised their individual national activities and establishing their own national networks; this prioritisation has meant liaison between the activities has been limited. As the programme moves forward concrete action needs to take place to ensure there is an exchange of information and events.

That said, some lesson learning across the different components is already happening. Partners have also been engaged in other national and regional processes which are extremely important in terms of forest governance, and also to the UK and EU namely the Volunteer Partnership Agreements (VPAs) and the Forest Law Enforcement Governance and Trade (FLEGT) processes, to underscore their importance for forestry governance and the relevance of community forestry to these approaches.

Key lessons

The log-frame was not capturing the activities undertaken within the programme and the wording of some of the indicators and failure to include accurate and reportable milestones has hindered reporting by the individual components. Within Dryad the time and resources taken to establish community enterprises was underestimated, which has led to delays in signing contracts with the communities. There has been a revision of the process and greater support given to the Implementing Organisations (IOs) e.g. the national civil society organisations in Cameroon such as Centre d’Appul aux Femmes et au Ruraux (CAFER), Cameroun Ecologie (CAMECO) and The Environment and Rural Development Foundation (ERUDEF) to help communities develop investment ready proposals.

Working in a politically dynamic region requires a flexible approach; there have been times when partners have not been able to travel freely in the region and access has been restricted. However using country based implementing organisations and increasing the capacity of them to operate has ensured that project based activities can still be delivered. The development of the country diagnostics was an important milestone and provide a strong baseline for future action and co-ordination, however if these documents remain solely for the internal use of members of the consortia, an opportunity for wider learning will be lost. Versions should be generated which are available for dissemination to other stakeholders, including international donors who are operating in this field. To demonstrate the utility of community based ownership and management evidence papers and reports need to be produced and shared widely.

The reduction in the value of sterling has also had an impact on the delivery of the programme, having initially costed activities based on a sterling value some of the downstream partners had to scale back on activities to align with the new value of Sterling.

Key actions
1. Update log frame based on feedback with the IOs by September 2017 to reflect on its ability to capture activities and ensure outcomes are delivered. (DFID)
2. Dryad and the Cameroon specific component of CoNGOs to be better co-ordinated, ensure a joint workshop on Community Forest Enterprises takes place
3. Dryad to provide reports on the development and signing of contracts with enterprises on a regular basis based on the agreed reporting schedule.
4. Outreach to other donors and actors such as the World Bank and the Green Climate Fund (GCF) should be increased, to demonstrate the value of the CF approach and potential for Community Forest Enterprises in attracting support. (all components and DFID)
5. Country Diagnostics and other reports need to be shared widely to ensure the community forestry approach and barriers to implementation are well-known throughout the region. (DRC programme and CoNGOs component)
6. Need to continue to ensure that the gendered approach that recognises the needs of girls and women is integrated into learning events and that DFID monitors improvements of participation over time. (All components and DFID)
7. Develop a mechanism for improved collaboration across the components, including annual joint meetings and a sharing of calendar and events, with the first step being a programme wide meeting in October.
8. Engage with partners more during the quarterly forecasting for the next financial year and ensure forecasts are realistic and risk adjusted in good time to prevent last minute changes to the annual forecasts or funds being carried over into the next financial year. (DFID)

Has the log frame been updated since the last review?

Yes. Tripleline, an independent consultancy, were contracted to design a new log-frame and a monitoring framework. The utility of this log-frame has been tested in this Annual Review, with further work needed (by DFID) to ensure all activities get reported and reflected in a new updated framework.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Socially and economically viable models for sustainable community forestry demonstrated
Output number per LF		1	Output Score	A
Risk:		Severe	Impact weighting (%):	40
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y
Indicator		Milestone		Progress
1.1 Number of community forests or community forest enterprises supported through the programme, disaggregated by: a) community forests; b) community forest enterprises		DRC: 0 (a) Cameroon: 15 (b) All five countries: 10 (a & b) Total= 25		Achieved: / DRC: 6 / Cameroon: 14 / All five countries: 5 / Total= 25
1.2 Number of community forest enterprises which: a) are economically profitable or viable; b) have been supported to gain better access to markets and business opportunities		None set for this year.		Too early to measure.
1.3 Number of people or communities who have been supported by the project to: / a) improve their rights to forest tenure; / b) engage in community forestry (through training, employment, and including government staff, Civil Society Organisations (CSO) staff [# individuals] disaggregated by i) Indigenous Peoples (IPs) versus local communities; ii) individuals (disaggregated by gender)		a) 0 people + 25 groups / b) 45 people 50% female		Achieved: Total A: 28 groups / Total B: 1118 people

A wide range of support is being given across the components, from dedicated training on specific issues, such as entrepreneur development through to capacity building of national organisations based on needs assessments. The organisations delivering training and support have track records in their fields and knowledge of the region and are able to deliver tailored approaches.

On indicator 1.1, the work of the differing programme component has collectively achieved the total milestone figure. RFUK together with the national implementing partners, have identified 6 pilot sites in DRC and are supporting the communities to secure land concessions, currently through providing information to communities on community forestry approach and mapping ways to support legal recognition including establishing management plans etc.. CoNGOS consortium have identified sites for community forestry and work with community groups and Non-Government Organisations (NGOs) in Cameroon (13), Republic of Congo (RoC) (3) and the Central African Republic (CAR) (2). Work is progressing in these areas, including in the development of simple management plans. Within the Dryad programme, 15 investment memoranda from the 28 teasers were developed, however progress needs to be maintained in order to ensure sustainability. In a number of countries including Cameroon, progress needs to continue to increase. Within DRC, additional pilot sites need to be identified and communities need to agree to move the process forward. Failure to get continued community support will endanger the delivery of the programme and would make the process unsustainable.

Progress on signing the CFE contracts through Dryad has been slower than anticipated, with 1 signed contract and 2 ready to be signed, a further 2 failed the due diligence process and 3 due diligence missions planned for the coming weeks. There are several reasons for this, including more support needed for the Implementing Organisations (IOs) in Cameroon such as CAFER, CAMECO and ERUDEF. This support will assist in understanding the needs of the business plan and recognising that all business plans and contracts need to be aligned with harvesting cycles to ensure that the business are sustainable. Dryad now has a schedule for signing the remaining number of contracts setting out clearly the process and timeline for achieving future results. In Cameroon, Dryad has procured a monitoring system for the CFEs which will be rolled-out when the CFE contracts are signed

No target was set for indicator 1.2, as it is too early in the business cycle to demonstrate results, as the business enterprises would not have been running long enough. Milestones for this indicator have been set for the outer years to ensure we can accurately capture the activities and utility of the enterprise approach. Capturing such results will contribute to the evidence base for the CFE approach.

On indicator 1.3, for the IIED CoNGOS component, there has been a range of training activities which have been carried out which will directly benefit community forestry, including on entrepreneur identification and development and the establishment of community forest enterprises and capacity building activities. There has been training of trainers for entrepreneurs, and a local organisation has been recruited to help in enterprise development. Training and engagement with community groups will scale up over the coming year, and then consolidate activities ensuring the right people are trained and supported. The impact of this training needs to be reported against; log frame revision will look to address in the coming year. This first year of implementation has concentrated on developing a baseline on which to build future activities. Responding to opportunities as they arise, the IIED work has also made links with 7 artisanal logger associations in DRC, spread across three provinces. This represents a new area of engagement with the private sector which has not been explored in the DRC before and with a sector that may have a significant impact on forest resources.

Summary of responses to issues raised in previous annual reviews (where relevant)

DFID should work with the Monitoring, Evaluating and Learning (MEL) consultants to agree ways to strengthen this output and develop more meaningful indicators to track change. This should be completed by end September 2017.

Response: We contracted Tripleline to complete a new and revised programme level log frame in February 2017. This is the first year of reporting on this log frame and we plan to monitor to ensure it is appropriate based on revisions which will be discussed over the coming months and throughout this operational year.

Recommendations

- Update log frame based on feedback with the IOs by September 2017 to reflect on its ability to capture activities and drive ambition, including capturing the project achievements
- Dryad and the Cameroon specific component of CoNGOs to be much better co-ordinated, ensuring a joint workshop on Community Forest Enterprises takes place.
- Dryad to provide reports on the development and signing of contracts with enterprises on a regular basis aligned with the reporting framework.

Output Title	National and regional learning, networks and alliances are established for influencing policy on land use, as it affects forests, lands and managing forest resources.
Output number per LF		2	Output Score	A
Risk:		Major	Impact weighting (%):	30
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
2.1 Number of pieces of evidence and best practice documented by the programme	0	Met[1] / Total: 8 / 5 Country Diagnostics: / Report ‘Gearing up for Community forestry in CAR’ Technical Brief on Performance-Based Finance in CF
2.2 Number of national and regional networking and lesson-learning events and alliances (virtual and in-person) and % women attending	7	Achieved: 8 / 6 x RFUK: 3rd CF roundtable (21%) & national programme launch (16%), provincial programme launch (20%), national working group on livelihoods (0), national working group on policy (14%) and training of Environment Ministry staff (38%) / 2x IIED MA&D training and Lesson learning event (42%):
2.3 Extent to which learning events and evidence studies demonstrate value of CF in achieving sustainable forest management and improved livelihoods	On-going work which lead to the 2020 target[2]	Too Early to tell / Each component is on track to deliver various / evidence studies and learning events, including: / Pilot sites for testing allocation and management procedures have been selected. / A list of all existing CF pilots has been supplied by DFC, containing location and economic activities of each CF. / ICRAF report looks at value added for CF in terms of REDD+ & also report on effectiveness of CF as social enterprises / IIED report on existing market and financing initiatives for community forest business in DRC
[1] The milestone for this indicator was too low and should have reflected the need to have the country diagnostics completed
[2] RF-UK: i) implementation procedures tested in 5 locations and lessons inform revision of legal procedures; ii) guidance & route maps for national scaling up completed and disseminated; iii) 7 lesson learning events from the implementation of National strategy document and disseminated IIED: Research in key thematic areas (about 5) undertaken, peer-reviewed, evidence published and used as evidence in processes to promote governance and improve the conditions of commercial community forestry Dryad: 6 presentations at policy/stakeholder forums at national, regional and international levels

Key Points

Each component has delivered a range of activities. The programme is on course to deliver on its outputs in the outer years, and develop a comprehensive evidence base through identified research priorities and policy outputs which will provide support for community forestry, and develop mechanisms to promote the approach.

One important activity is the development of the country diagnostics, which present the state of play in relation to community forestry in each country, including key ministries, actors and barriers to implementation. They are working documents developed by the consortia led by IIED (except for the DRC, which was led by RFUK). They have been validated at the national level, and are being formatted as public documents which can be used as policy documents for a wide range of external stakeholders. Other stakeholders including donors have expressed a strong interest in these diagnostics as they also map out their activities in the region. It is important that the evidence and reports produced are shared.

RFUK has identified a range of research activities and areas for future study as part of their work planning for the additional years, as has the IIED CoNGOS programme, with 8 studies near completion. IIED have undertaken a range of training activities and is in the early stages of an intensive six month training period for Cameroon and DRC community forest enterprises. As with indicator 1.2 as we further refine and develop the log frame and future milestones we will work in the IOs to ensure this is captured.

Gender considerations are an important element of the programme, given the challenge of gender dynamics in play across the Congo Basin. Gender consideration has been discussed with the main IOs and in relation to training will be improved, to ensure training and lesson learning is provided in a gender-equitable way. This will be done by seeking to understand constraints to participation and working in country with partners on selection of training for individuals. This element will continue to be monitored, so that all partners understand and address the constraints to female participation and monitor improvements over time.

As several of the components entered implementation stage this year, and were laying the foundations and baselines for future studies it is too early to report on indicator 2.3 but studies and events are being planned which will add to the evidence base for community management of natural resources. This indicator needs to be revised in a future iteration of the log frame.

Summary of responses to issues raised in previous annual reviews (where relevant)

Issues:
•	To accept the proposed changes to wording of this output.
The Log-Frame has been updated and therefore this recommendation no longer is relevant but further revisions and indicator milestones will be needed e.g. Output Indicator Milestone 2.3.

•	Dryad should carefully review the quality of the teasers before investment decisions are made to ensure that a) they are of good quality; and that b) there is a process of ground trothing to ensure that the business plans actually correspond to the resources that can be harvested sustainably according to the community forest management plan. A minimum governance threshold will be established to ensure that CFEs have representative organisational structures are in place before investment.

These have been developed and are part of the due diligence process.

•	Dryad also needs to develop safeguards to ensure that the CFEs have equitable benefit sharing mechanisms in place and that any potential land tenure related conflicts (see risk section for more details) are identified early and mitigating actions are taken. Tacking these issues is built in to the FMS and should hopefully identify issues early.

These have been developed and are part of the due diligence process.

Recommendations

- Update the log frame based on feedback with the IOs by September 2017 to reflect on its ability to capture activities. (DFID)
- Outreach to other donors and actors such as the World Bank and the Green Climate Fund (GCF) should be increased (all components and DFID) to demonstrate the value of the CF approach and potential for Community Forest Enterprises and attract support.
- Country Diagnostics and other reports need to be share widely to ensure the community forestry approach and barriers to implementation are well known throughout the region (DRC programme and CoNGOs component)
- Need to continue to ensure that the gendered approach that recognises the needs of girls and women is integrated into learning events and that DFID monitor’s improvements of participation overtime. (All components and DFID)

Output Title	Increased capacity for engagement and participation in processes related to land use planning and implementation of community forestry
Output number per LF		3	Output Score	B
Risk:		Severe	Impact weighting (%):	30
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
Number of local organisations and associates able to / a) support community forests; / b) advocate for policies; and / c) successfully manage funds/ their financial operations and/or demonstrate strong organisational financial capability	Dryad: 15 IIED: 10 / RFUK: TBC	Below expectations / DRYAD: (b) 4 National Organization and (c) 1 Community Forest Enterprise / IIED: 8 (a&b) / RFUK: (a&b) 4 National organisations, (a) 1 Ministry supported through capacity building activities.
The extent to which community forestry management committees are representative of the social make-up of the community. Criteria for representation to be discussed with the communities and finalised	80% of all community groups have met criteria i & ii[3]	Achieved – 100% / RFUK: DRC partners trained on participatory approaches before doing outreach with communities in CF pilot sites. / Dryad due diligence criteria and processes fully integrate these criteria by having guidance in place and implementing this in the site selection to ensure true representation of the social make-up of the community.
Effective engagement/ participation* of CSOs and communities in policy processes (at sub-national and national levels) to facilitate community based forest models, livelihoods, and sustainable use of forests for the recognition and securing of tenure rights	N/A captured in outer years
[3] Criteria for representation: i) representatives from disadvantaged groups have a seat at the table - Nbr within committees; ii) the committee as a whole as well as the disadvantaged groups (IPs, women etc.) have a good awareness of the need for their engagement/participation;

Key Points

Although a number of activities have taken place which are laying the foundations for successful implementation of the programme, we have scored this output a B as two of the indicators were not achieved (one of which had no milestone). Overall this output needs to be revised and milestones created for each year and indicators completed. Capacity needs assessments have taken place of the national organisations in Democratic Republic of the Congo (DRC) and other national institutions in the Central African Republic (CAR), these capacity assessments are now being acted on by Well Grounded, a CoNGOs & RFUK partner, to increase the ability of national organisations to advocate for policy and legislative reform.

The second indicator on the make-up of forestry management committees has been achieved by effective due diligence and engagement with marginalised groups where they are present. Due diligence of the investment memorandum under Dryad seeks to ensure effective participation, while RFUK and CoNGOS also have policies based on participation of marginalised groups and women. An improved way of monitor effective participation and decision making will discuss in the log frame refinement meeting.

Work to ensure local ownership and commitment to national legal and administrative processes, has taken place including the Voluntary Partnership Agreement (VPA) (related to timber trading between the EU and timber trading country processes in Cameroon) and the locally led roundtables in DRC including a district level meeting. Validation achieved for the country diagnostics and anthropological study in meetings in CAR. Validation of the Republic of the Congo (RoC) diagnostics and Gabon legal analysis has also been achieved in dialogue with national stakeholders. Dryad has worked with sectoral ministries through the advisory board to influence the taxation policy around community forests in Cameroon.

Engagement continues with policy makers; a number of national policy engagements have been identified for targeted action within a range of countries (e.g. Forest Code reform with parliamentarians; VPA; REDD+; CAFI national focal points in RoC and VPA; REDD+; CAFI national focal points; land reform process and the Territorial Collectivises Bill in the Central African Republic.

The DRC National Round Table on Community Forestry has continued to make progress. The third Round Table was held in February 2017 and a national strategy on community forestry has been developed with wide stakeholder input, and is now ready for validation by DRC’s Environment Ministry.

Summary of responses to issues raised in previous annual reviews (where relevant)

•	DFID should strengthen its engagement with CAFI to ensure strong links between community forestry and larger REDD+ investments.

DFID continues to sit on the CAFI Executive Board. Inputs on the Community Forest approach and the programme outcomes have been communicated to other board members.

•	DFID should ensure there is good collaboration and learning across the 3 components: there is a risk that they operate in isolation from one another.

Event held in January 2017 bringing all components together including several of the IOs. There is need for greater collaboration between the components specifically the operations in Cameroon. Mechanisms need to be developed in the first quarter of this year to improve collaboration and lesson learning.

Recommendations

- Update log frame based on feedback with the IOs by September 2017 to reflect on its ability to capture activities.
- Develop a mechanism for improved collaboration developed across the components, including annual joint meetings and a sharing of calendar and events. With the first step being a programme wide meeting in October.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
Key cost drivers remain as outlined in the business case and previous Annual Review and can be split into two main categories:
•	Operational costs: including admin fees, salaries for project staff and consultants; communications work, travel, project launch events; monitoring and evaluation support costs etc...
•	Activities: these vary from project to project but include asset/equipment acquisition and maintenance, technical assistance and associated staff costs, logistical and travel expenses associated with field work and multi-country participation.

Given the remoteness of field sites in the Congo Basin and the logistical constraints of accessing them, field work is a major cost driver of each component. The reduction in value of sterling has presented challenges in relation to the delivery of the programme, several implementing organisations have stated that as field work accounts for a large proportion of the budget some activities have to be scaled back to meet actual in country budgets.

VfM performance compared to the original VfM proposition in the business case

The VfM performance of the programme in comparison to the business case is on track.
Economy (spending less): Prior to final approval of project activities, assets and agreements with partners, DFID analyses project budgets to ensure that all line items are well justified and reasonable. Cost savings have been identified throughout the year through frequent monitoring and reporting. The due diligence process confirmed that all lead partners have procurement policies which ensure project equipment is purchased at competitive prices, strong budget management procedures to ensure funds are well managed, and competitive recruitment policies to ensure hiring of qualified project staff and consultants at appropriate rates. We request and retain the various procurement options to ensure we find the best price and quality in all services and assets.
Efficiency (spending well): All three main programme components are implemented by strong technical partners with considerable experience of working in the region. This has enabled projects to build on existing work, local networks and relationships with government partner and have a good progress in the programme, delivering key outputs.

We have already seen some evidence that the ongoing consortium working will lead to efficiencies across the partners – including sharing of experiences and learning, and consolidating similar themed or overlapping activities, for example certain monitoring trips or workshops. Additional opportunities to consolidate activities will be identified through joint and continuous planning at the consortium level. This should not only help to reduce direct project costs but also strengthen the working relationships and coordination between all parties involved.

Effectiveness (spending wisely): Worldwide examples show that, with political will and an enabling policy and institutional environment, community based forest management is an effective and sustainable way to deliver environmental, social and economic outcomes.

Learning from previous projects in Cameroon (including past failure) and drawing on experience from elsewhere is built into all programme components. For example, as part of the Dryad’s research activities, ICRAF have been carrying out a review of previous experiences of community forestry in Cameroon and Africa – in order to learn from these and to validate and adjust Dryad’s assumptions (risks, capacity etc.). The regional consortium has also produced ‘Country Diagnostics’ to support project implementation. These diagnostics provide a framework to collate and organise the evidence and experiences from all consortium partners in order to better understand the enabling regularly environment, local contexts, capacities and needs, as well as the constraints and barriers to community forestry. They will help ensure the consortium is intervening where it adds most value. ICRAF as part of the Dryad programme had originally considered to disperse funds to community enterprises by mobile money, however an internal review and risk management exercise undertaken by the programme team felt that this was not the correct avenue and would be too risky. They have since changed their approach to guarantee effectiveness in operations, CF are required to have a bank account and demonstrate that they can get access to funds when required as part of the due diligence process, the funds will then be transferred to that account.
Cost – effectiveness: As outlined in the BC, community involvement in the management of forest resources has proven to be very cost-effective elsewhere (including Indonesia, Guyana/Brazil and other countries in Africa) – the overall assumption being that local people – as rights-holders – are closest to forest resources and therefore well placed to manage them efficiently and that longer term potential for scaling up is also high in community-based interventions because incentives (the structure of these positive incentives largely boiling down to rights over land and resources) for good environmental management are built in and do not require external contributions.
The programme also aims to demonstrate that community forestry should be a key building block for the effective delivery of climate finance in the region, including wider HMG programming (through global REDD+ funds). As described elsewhere in this review, through engagement and alignment with CAFI there is strong potential for the evidence and experiences supported in this programme to influence and leverage larger REDD+ investments to support community forestry and strengthen community tenure rights.
Assessment of whether the programme continues to represent value for money

At this stage, we feel that the programme still represents value for money. We keep track of all procurement, savings and asset registries and ensure the programme upholds good practices to provide the best value for money options at all times. The potential for community forestry to develop viable enterprise models has seen increased visibility, with government officials in Cameroon stating their support for the programme and how it can ensure sustainability of the community forest model.

Quality of financial management

Performance against budget: The project spent £3.1m during this financial year with £3.7m annual budget available. Year to date spend is in line with the budget agreed within ARD at the start of the financial year. All 3 programme partners have provided detailed financial forecasts for this year (by quarter) and future years.

All three projects are currently on track against their spending forecasts for this financial year .RFUK have reduced their programme forecast for remaining years by £18,000 after completing a vigorous risk adjusting exercise. All 3 partners are reminded monthly by DFID of the importance of them closely reviewing their quarterly forecasts, and only requesting funds that are actually needed for that quarters work plan activities. DFID has challenged some of the forecasted lines which have resulted in various reductions and savings. Partners have considerably improved the accuracy of their forecasting this year after robustly risk adjusting each item and considering all external factors which may influence the delivery of the programme. Partners have also updated their delivery chain maps to capture their financial flow and risk. These will also be updated as new sites are identified and supported.

During site visits to Cameroon in June 2017, processes ‘walkthroughs’ were undertaken with two organisations. We talked through the process of financial disbursement and how they monitor and account for funds. We also observed their audited accounts. We will continue to look into the issue of funding flows, and when money is being transferred to participant CFEs undertake another process walk through. As we went through this process issues on delays in funding flows in the Dryad programme were highlighted. This was as a result of additional requirements put in place by the UK on dispersal of funds; the financial team within ICRAF were able to establish in recent months a solution to ensure the efficient transfer of funds which has reduced the delays.

Recommendation:
- Engage with partners more during the quarterly forecasting for the next financial year and ensure this is realistic and risk adjusted in good time to prevent last minute changes to the annual forecasts or funds being carried over into the next financial year.
- When the funds are flowing to the CFE undertake another process walk through to observer the process from ICRAF down to the community level

Partner	ICRAF	RFUK	IIED
Date of last narrative financial report	Received 28 July 2017, for period ending 30 June 2017.	Received 28 July 2017, for period ending 30 June 2017.	Received 28th July 2017, for period ending 30 June 2017.
Date of last audited annual statement	Received July 2017 for period ending 31 Dec 2016.	Received July 2017 for period ending 31 Dec 2016.	Received September 2016 for period ending 31 April 2016.

E: RISK (½ page)

Overall risk rating: The last Annual Review in 2016 was marked as major risk, in recognition of the complexities and challenges of achieving impact in forestry and land sectors, as well as the programme’s delivery in a high risk region of Africa. We consider that overall programme has currently risen to severe, given the increasing tensions in the operational areas and frequent issues with visas and travel. We have created a new programme wide risk matrix which reflects these new risks and their trend.

Overview of programme risk:

The programme works in several countries including highly volatile environments such as the DRC and CAR, thus a lot of the programme risk comes from external content and operating environment such as Regional Insecurity (impact severe, likelihood medium), Violence and Conflict affect programme delivery (impact major, likelihood high) and Failure to Government buy-in (impact severe, likelihood high).

The delivery of the programme also comes with some highly impactful risks such as Capacity of consortium partners and local partners not sufficient to manage project expectations (impact Severe, likelihood medium), Violence and conflict is so severe that it affects project delivery (impact Severe, likelihood medium), and Conflicts of ideologies between programme partners (impact major, likelihood medium).

Other substantial risks are fiduciary risks due to Misappropriation of funds/ assets, Inaccurate forecasting or corruption (impact severe, likelihood medium-high), and reputational risks due to General programme and risk management, Project overambitious in its aspirations, Fraudulent behaviour by suppliers and Safeguarding issues (impact severe, likelihood low – medium).

More detail around identified risks and mitigating actions can be found in the programme risk register. We receive quarterly updates from the component leads, and update our risk register accordingly.

Outstanding actions from risk assessment none

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

As outlined in the Business Case, this programme began with a year inception phase (2015-2016) and has since completed the first year of the implementation phase (2016-2017). Despite difficulties such as the reduction in the worth of Sterling, the inception phase was completed successfully and we are overall we are broadly on track with the timeframe set out in the log frame. Going forwards we will continue to keep ambition but need to be aware of the difficult political and social context in which the programme operates.

Performance of partnership (s)

There are 3 key partnerships in the programme (RFUK, IIED and DRYAD) and, through them, relationships with other implementing partners and consortium members. An additional partnership also exists with CAFI. All partnerships are considered to be functioning well. Partners are encouraged to actively raise issues with DFID so that issues can be discussed and resolved as quickly as possible. DFID holds regular meetings with all partners and regularly receives feedback from them, and DFID staff are increasing the number of monitoring field visits they are making, subject to the travel constraints across the region.

CAFI is proving to be an effective partnership to enhance donor collaboration and coordination in the region, as well as for responding to more strategic issues in a coherent way. Efforts to co-ordinate more with CAFI as they expand beyond DRC need to be maintained.

Asset monitoring and control

All partners have asset registers for equipment purchased. We have alerted partners that the asset registry regulations have changed and programme assets cost over £500 (not £1000) and last longer than a year. Partners have provided cost comparisons on assets when challenged and have been able to save a substantial amount of money, whilst maintaining quality.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant): While the programme operates across five countries in the Congo Basin, only one of those countries has a country office, the DRC. Money from this programme does not flow into any government systems. The DRC country office is aware of the programme and we have been consulted in relation and their recommendations have been considered to ensure the programme does is aligned with the national Partnership Principles.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Since the previous Annual Review, DFID have contracted specialist consultants to help strengthen the Monitoring, Evaluation and Learning (MEL) framework for the programme. This has provided an M & E framework that has allowed us to test the assumptions made in the business case and build the evidence base on community forestry over the longer term. We used the new MEL framework and log frame to decide on new more specific and measurable milestones for the programme which are more in line with the programme outputs.

Monitoring progress throughout the first implementation phase:

Progress has been monitored through:
DRYAD - quarterly narrative and financial reporting, regular phone calls, additional face to face meetings in London and Dryad meetings with British High Commission in Cameroon, virtual attendance at DRYAD advisory board in February 2017. A process walk through and review of bookkeeping activities was carried out in June 2017. DFID field visit made in June 2017
- IIED - quarterly narrative and financial reporting, regular phone calls, additional face to face meetings in London.
- RFUK - quarterly narrative and financial reporting, regular phone calls, additional face to face meetings in London and attendance at the programme partner meeting in London in January 2017. DFID field visit made in June 2017

All the partners attended a Partners Programme Meeting in London in January 2017.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the log frame been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the log frame (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the log frame (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc.) / The Annual Review process