## Results Framework
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | Building Urban Resilience to Climate Change in Tanzania
IMPACT | Impact Indicator 1 |  | Baseline | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Dar es Salaam is more resilient to climate risk | Number of Wards benefiting from or implementing flood risk mitigation measures identified in community level risk management plans | Planned | 0 | 0 | 0 | 10 | 15 | 15 | 20
|  | Achieved |  |  | 0
Source
Regional Administrative Secretary
| Impact Indicator 2 |  | Baseline | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
| Improved capacity of government agencies to identify, reduce, finance and cope with disaster risks | Planned | Low | Low | Incipient | Incipient | Appreciable | Appreciable | Good
|  | Achieved |  |  | N/A
Source
Disaster Risk Management Index
| Impact Indicator 3 |  | Baseline | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
| Modelled Economic losses in the Msimbazi basin reduced as a result of structural risk mitigation measures designed | Planned | $47 million per year annual losses (from 2016 report). This baseline will be assessed as part of the programme. | N/A | 2017 baseline Average Annual Loss (AAL) without works | N/A | AAL for 2017 exposure reduced under planned works scenario | N/A | AAL for 2017 exposure further reduced following community actions
|  | Achieved |  |  | 2017 baseline AAL without works
Source
Probabilistic Flood Model
OUTCOME | Outcome Indicator 1 |  | Baseline | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Assumptions
Dar es Salaam utilizes improved evidence base and urban planning to strengthen resilience to climate-related hazards | Number of persons benefiting from improved flood resilience as a result of ICF support | Planned | 0 | 0 | 0 | 250000 | 500000 | 1 million | 2 million | (i) there is credible evidence base for informing climate resilient urban policy and decision making; (ii) evidence is communicated effectively and persuasively; (iii) there is a strong consensus amongst decision makers and other stakeholders supporting the case for climate resilient urban development; (iv) the country has access to necessary skills and financial support to design and implement climate resilient urban strategies; (v) training and capacity building is followed up by execution; (vi) resources are allocated to instituting incorporation of priorities for climate change resilience into urban development; (vii) donors are willing to tolerate a relatively high level of investment risk in order to encourage pioneering initiatives; (viii) demonstration interventions are well-implemented and can be scaled up/replicated; (ix) other climate hazard/disaster mitigation programmes are operational; and other urban governance/urban poverty programmes are operational; (x) there is collaboration with the WB urban portfolio of programmes.
|  | Achieved |  |  | 0
Source
Flood Risk and Exposure Model
| Outcome Indicator 2 |  | Baseline | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
| Extent to which ICF inter­vention is likely to have a trans­formational impact | Planned | 0 | N/A | 1 | 2 | 3 | 3 | 4
|  | Achieved |  |  | TBD
Source
Annual review
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Assumptions
Pillar 1: Information and Data Management for Climate Risk Identification | Improved access to climate risk information in Dar es Salaam | Planned | N/A | Data In­ventory being prepared | Catalogue of existing structured exposure and hazard data completed (Yes/No) | Repository of risk information published for 20 wards of Dar es Salaam with flood inundation scenarios | Repository of risk information published for 70 wards of Dar es Salaam with flood risk scenarios | Probabilistic flood risk information published online for Dar es Salaam including climate scenarios | Dataset downloads of hazard, exposure and risk information (>500) | Technical approaches and mechanisms meet the needs of stakeholders, and are appropriate for the local context
|  | Achieved |  |  | Data model and exposure complete, hazard partially complete
Source
Based on indicators 3.1 - 3.4, 4.3 and 4.6
| Output Indicator 1.2 |  | Baseline | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
| Exposure or Risk assessments applied in major cities (cumulative number of cities) | Planned | 0 | Template developed | Pilot satellite based exposure monitoring service launched | At least 1 monitoring service demonstrated, at least 1 more urban risk service under preparation | At least 2 cities using exposure or risk monitoring service | At least 3 cities using exposure or risk monitoring service | At least 4 cities using exposure or risk monitoring service
|  | Achieved |  |  | Confirmed launched with Planet Labs and EastView Geospatial
Source
Climate Risk Geonade Repository
IMPACT WEIGHTING (30%) | Output Indicator 1.3 |  | Baseline | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Planned
Achieved
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Assumptions
Pillar 2: Disaster Risk Reduction | Cumulative Number of people directly engaged in climate risk reduction activities - number and per­centage of females (WB core indicator) | Planned | 0 | 0 | 0 | 100 | 250 | 500 | 500 | (i) awareness and understanding amongst ULGAs and local-level community organisations of local risks and vulnerabilities, and urban resilience measures (delete this? - covered by new indicator2.3); (ii) clear definition or distribution of political and administrative competences and responsibilities; and (iii) technical approaches and mechanisms meet the needs of stakeholders, and are appropriate for the local context
|  | Achieved |  |  | 50 ( of which 25 female)
Source
Participant lists and registrations from trainings and events
| Output Indicator 2.2 |  | Baseline | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
| Community risk reduction and response plans developed using improved risk information (cumulative number of Mtaas endorsing plans) | Planned | 0 | 0 | 0 | 10 | 20 | 30 | 40
|  | Achieved |  |  | 0
Source
Ward offices and LGAs
IMPACT WEIGHTING (25%) | Output Indicator 2.3 |  | Baseline | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
| Government Risk reduction Activities in Msimbazi Valley are designed and operationalized | Planned | 0 | 0 | Msimbazi flood model establised | Msimbazi Lower Basin Detailed Plan endorsed by government | Msimbazi Flood mitigation works grant effective | Msimbazi Flood mitigation priority actions implemented | Completion Report Large Grant
|  | Achieved |  |  | Concept Memo approved
Source
Secretariat
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Assumptions
Pillar 3: Emergency Preparedness and Response Management | Dar es Salaam emergency contingency plan | Planned | 0 | Template developed | Plan Approved | Detailed Trainings, Exercises and Drills Program agreed | Emergency Operations Center Structure approved | Dar Emergency response Plan Updated to version 2 | Standard Operating Procedures for All DarMAERT members approved | 1. Continued Government support for DARMAERT as the regional DRM stakeholder group.
|  | Achieved |  |  | Dar es Salaam ERP prepared
Source
IMPACT WEIGHTING (20%) |  | ULGA reports
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
Output 4 | Output Indicator 4.1 |  | Baseline | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Assumptions
Pillar 4: Resilience Academy established and operationalised | Cumulative Number of staff and students by gender placed in Urban Resilience Industry placement | Planned |  | 0 | 250 | 500 | 750 | 1000 | 1000 | 1. Sustained demand from Universities to collaborate with TURP in review, adoption and implementaiton of both training courses and real world practicals. 2. Acceptance from authorities for Universities to host and use Risk data.
|  | Achieved |  | 120 | 306
Source
| Output Indicator 4.2 |  | Baseline | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
| Climate Risk Data and Tools Use in research | Planned |  | 0 | 0 | Geosptial Data repository established for 4 Universities | Source Code for InaSafe and Risk Model hosted for Universities | Innovation Challenge Using Risk Data launched | X number of masters theses completed using risk data.
Achieved
Source
IMPACT WEIGHTING (15%)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 5 | Output Indicator 4.1 |  | Baseline | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Assumptions
Program Management and Recipient Executed Works | Program Management, Knowledge and communications adequately handled | Planned | 0 | Partnership Review Note Approved; Program Staff Hired | Launch Event held; Program Outputs review; | Technical Conference held; | Technical Conference Held; program Outputs Review | Urban Climate Risk Report Launched; | Program Final Outputs Reviews Approved
[6 empty] | Program Outputs Review |  | Program Outputs Review
|  | Achieved |  |  | Launched May 30, 2017
Source
IMPACT WEIGHTING (10%) |  | Secretariat
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)