Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Growth, Resources, Opportunities and Wealth Creation in Bihar (GROW-B)
Programme Value: £5 million		Review Date: 25 July 2018
Programme Code:	Start Date: 25 July 2014	End Date: 31 October 2020

Summary of Programme Performance
Year	2015	2016	2017	2018
Programme Score	A	A	A	A+
Risk Rating	Medium	Medium	Medium	Medium

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-204237/documents/
DevTracker Link to Log frame:	https://ec.vault.dfid.gov.uk/OTCS/cs.exe?func=ll&objaction=overview&objid=17409610

A. Summary and Overview
Description of programme
Under the Growth Resources Opportunities and Wealth Creation in Bihar (GROW-B) programme, DFID is providing up to £5 million Technical Assistance (TA) over the period April 2016 to October 2020 to strengthen the transmission of growth for inclusive economic development. By promoting private sector-led growth, improving the Government of Bihar’s (GoB) capacity to raise and mobilise revenue and improving efficiency and effectiveness in how resources are utilised, GROW-B is intended to benefit the people of Bihar – India’s poorest State –, notably the most vulnerable.

Summary supporting narrative for the overall score in this review

This is the fourth annual review. In the past year, the programme has gathered momentum and delivered on its main outputs. It continues to support the roll out of interventions of previous years and has built capacity and capability in institutions such as Bihar Prashasanik Sudhar Mission Society (BPSMS), Bihar Right to Public Grievance Redressal Act (BRPGRA), Bihar Industrial Area Development Authority (BIADA) and Bihar State Minority Finance Corporation (BSMFC).

GROW-B has also taken on new activities, most notably the Chief Minister’s Scheduled Caste (SC) and Scheduled Tribe (ST) Entrepreneur Scheme, the Amritsar Kolkata Industrial Corridor implementation of Start-Up policy; developing an awareness campaign for BRPGRA, support to job fairs, setting up a call centre and online admission system for Labour Resources Department and developing new disbursal schemes for loans made by BSMFC.

For the Industries Department, GROW-B has provided additional resources to support new investment promotion and grounding activities and the State Investment Promotion Board (SIPB) to help approve a greater number of proposals for new investment in Bihar.

Working in partnership with the GoB, the main achievements this year to which the programme’s advice has significantly contributed have been:

- The enactment and implementation of the Bihar Industrial Investment Promotion Act, Rules and Policy, 2016 and the Bihar Start-Up Policy, 2017 resulting in £650m new investment this year
- Operationalising the leather footwear manufacturing common facilitation centre at Moratalab with potential to support more than 100 economically and socially vulnerable households
- Operationalising the GoB’s Comprehensive Financial Management System (CFMS) as well as rolling out of the Bihar Central Audit Portal pilot for the Labour Resources Department
- The GoB’s signing of an MoU with Yamaha (India) to train over 250 students in motor mechanics
- Support on the BRPGRA, which has been recognized nationally by winning the Kalam Innovation in Governance Award.

The main lessons of this review period are:

- While the GoB is a committed partner and has high demands for TA from GROW-B, to sustain the activities supported by GROW-B, future planning will need to take a longer and wider perspective. New thinking is needed on how the partnership may evolve to utilise new financing instruments (development capital); expand interventions into new areas of inclusive development; transfer skills and build capacity in-house and undertake greater coordination with other UK programmes in Bihar to maximise impact.
- Coordination between State Departments could be stronger and would help the whole UK partnership develop greater coherence for impact in Bihar. With annual steering group meetings presently focused on GROW-B objectives, a new process of dialogue that facilitates a wider more inclusive discussion between the UK and the GoB would enhance impact.
- Progress to develop the first common leather facility has taken more time than anticipated but the lessons drawn from this will help expedite the establishment of future facilities across Bihar.
- In the initial years of the programme GROW-B faced a reputational risk from there not being sufficient resources to meet demand. However, careful management of expectations with partner government departments through steering groups and regular meetings with government officials have helped DFID and the government agree realistic and affordable objectives for this programme. The risk now has evolved to ensuring that capacity and capability is transferred to government staff to enable a smooth exit from programme support in two years’ time.

Main recommendations for the year ahead

- For the intervention team and DFID in partnership with the government, assess and develop a strategy for evolving the partnership to utilising new financing instruments (development capital); expand interventions into new areas of inclusive development; transfer skills and build capacity in-house and undertake greater coordination with other UK programmes in Bihar to maximise impact by June 2019.
- For the intervention team in partnership with the government develop a strategy and terms of reference by December 2018 to develop a new dialogue process that includes DFID, other development partners and state departments to ensure interventions are better coordinated for impact.
- For the intervention team in partnership with the government develop and implement a strategy for enhancing linkages between producers and buyers, and encourage producers to evolve their traditional production practices and make greater use of the CFCs by December 2018.
- For DFID and the intervention team to review the logfame in view of the strong progress made this year and the resources available next year by October 2018.
For the intervention team and DFID to prepare for an independent mid-term review assessment, which will focus especially on VfM, by October 2018.

Table of Abbreviations
AG Office	:	Auditor General’s Office
BCAPP	:	Bihar Centralised Audit Para Portal
BIADA	:	Bihar Industrial Area Development Authority
BIIPP	:	Bihar Industrial Investment Promotion Policy
BL	:	Base Line
BPSMS	:	Bihar Prashasanik Sudhar Mission Society
BRPGRA	:	Bihar Right to Public Grievance Redressal Act
BSMFC	:	Bihar State Minority Finance Corporation
CFC	:	Common Facility Centre
CFMS	:	Comprehensive Financial Management System
DDO	:	Drawing and Disbursing Officer
DoI	:	Department of Industries
DPR	:	Detailed Project Report
EoDB	:	Ease of Doing Business
ERP	:	Enterprise resource planning
GIS	:	Geographic Information System
GAD	:	General Administration Department
GoB	:	Government of Bihar
GoI	:	Government of India
GROW	:	Growth Resources Opportunities and Wealth Creation
GSDP	:	Gross State Domestic Product
HRMS	:	Human Resource Management System
ICS	:	Integrated Clearance System
ITI	:	Industrial Training Institute
KIGA	:	Kalam Innovation in Governance Award
LOC	:	Letter of Credit
LRD	:	Labour Resources Department
MoU	:	Memorandum of Understanding
MSME	:	Micro, Small & Medium Enterprises
MWD	:	Minority Welfare Department
NAPS	:	National Apprenticeship Promotion Scheme
NCS	:	National Career Service
NCVT	:	National Council for Vocational Training
NMDFC	:	National Minorities Development & Finance Corporation
PGRO	:	Public Grievance Redressal Officer
PPP	:	Public Private Partnership
SC	:	Scheduled Caste
SCVT	:	State Council for Vocational Training
SIPB	:	State Investment Promotion Board
SOP	:	Standard Operating Procedure
SPV	:	Special Purpose Vehicle
ST	:	Scheduled Tribe
SWCS	:	Single Window Clearance System
VfM	:	Value for Money
Waqf	:	(Arabic word) meaning an endowment made by a Muslims to a religious, educational, or charitable cause
WoW	:	Ways of Working
WRMIS	:	Women’s Reservation Management Information System

## C: DETAILED OUTPUT SCORING Implementation Phase (12 Months)

Output Title	An improved environment for private sector investment in Bihar.
Output number per LF		1	Output Score	A+
Impact weighting (%):		30%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
SIPB Stage 1 Approval Rate (No. Approved/No. Received)	75%	Exceeded: 97% (475 approved of 490 proposals)
Conversion rate of approved investment proposals	4%	Exceeded: 4.7% / Value of stage 1 proposals converted: INR 331.95 Crores (of INR 7074 Crores). No. of stage 1 approvals converted: 47 (of 475)
Average number of days for Stage 2 and 3 approvals	380	Exceeded: 241[1]
MSME-CFC proposals approved	3	Exceeded: 4
New MSME-CFC commissioned	1	Met: 1
Govt. ITIs covered under PPP	13	Met: 13
[1] Note: This is based on the analysis of random sample of investment proposal

GROW-B has delivered the following in this review period:
- For Output 1.1, the development and implementation of an online Integrated Clearance System (ICS) for SIPB Stage-1 applications and enhancements to standard operating practices (SOP) have improved the quality of investment proposals by 20%. Specifically, the online application system for industries has in-built validations and documentation requirements that ensure proposals are complete and error-free when submitted. Revisions to the Bihar Industrial Investment Promotion Policy (BIIPP) supported by well-defined ways of working have also strengthened government decision-making to expedite the clearance process.
- For Output 1.2, GROW-B TA assisted the GoB to operationalize the BIIPP. This included the implementation of an online ICS for timely processing of clearances and disbursement of incentives. TA also supported the implementation of a GIS-based land allotment system for investors to streamline the land allotment process to ensure timely decisions are made on requests for land in industrial areas. The support provided to rollout Bihar’s Start-Up policy has helped nurture more than 175 start-ups this year.
- For Output 1.3, GROW-B assistance on EoDB reforms has helped streamline the licence clearance process and increase new investment in Bihar. Targeted TA helped increase the compliance rate from 75% to 88% in this review period. Effective implementation and advocacy of the BIIPA supported by GROW-B has also attributed to a substantial reduction in days for Stage II & III clearances of new investment proposals.
- For Output 1.4, GROW-B has supported the GoB in the conceptualisation, development and approval of proposals for leather footwear cluster in Moratalab and Muzaffarpur, leather Goods Park in Muzaffarpur and integrated handicraft clusters across Bihar. TA also supported the government to organise five workshops for local leather footwear producers to raise awareness, build trust and increase cluster participation, which has added value to local production and increased producer incomes.
- For Output 1.5, GROW-B TA assisted the GoB to complete civil construction work, procure, install and train key staff to operationalise the common facility centre (CFC) in Moratalab. So far producers using the facility have started to take orders, most notably from the Home (Police) department, and wider interest from large commercial shoe retailers is increasing.
- For Output 1.6, GROW-B TA has supported the Labour Resources Department to form private sector partnerships with Industrial Training Institutes (ITI’s). Strong progress made over the past year has led to two ITIs having signed MoA’s with private sector partners (including an ITI exclusively for women in Patna).
Additional Activities
To promote the investment climate in Bihar, GROW-B TA undertook additional activities this period. Notably, it supported the DoI in implementing the rollout of the Bihar Start-Up Policy. GROW-B provided TA to the DoI to support the design and development of an online portal for start-ups and supported the formation of the Bihar Start-Up Fund Trust, which is the implementing body for the Start-Up Policy. So far the DoI has received 4,000 online applications during this period under the Policy. GROW-B TA has also helped promote Bihar as an investment destination through media articles and advertisements. GROW-B TA to Upendra Maharathi Shilp Anushandhan Sansthan is helping the development of the handicraft clusters in Bihar and support to the Bihar State Khadi and Village Industry Board is helping to increase investment commitments to generate greater employment opportunity across the State.

Lessons identified this year, and recommendations for the year ahead
The main lessons identified are:
- As activities in this review period gained momentum, capacity and capability shortages at GoB were exposed. In the Industries Department, greater impact could have been achieved by training staff in marketing skills enabling the government to more strategically target its investment promotion activities.
- Stronger linkages to markets will be required if the new clusters are to be sustained. Initial progress, particularly linking shoe producers to the Home (Police) Department, has been achieved but efforts will need to be stepped up to strengthen market linkages more broadly if clusters are to sustain.
- More work is needed to change traditional practices and encourage leather producers to use the common facilities. Initial uptake has been slow and partial. Greater effort is needed to demonstrate the advantages of these facilities on productivity and income.
- Relatively low industrialisation in Bihar limits partners for ITIs. A special focus is required to attract partners from other states.
- While the selection of sectors for cluster development was based on state government preferences, an assessment of potential for industrial development and opportunities for new employment, there is a risk that the programme is locked in to sectors that while inclusive do not offer high returns for Bihar in the future.
Summary of responses to issues raised in previous annual reviews (where relevant)

Revisions to the log-frame were completed by October 2017.

Recommendations:

- For the implementing team to support the GoB in the development of a strategy to support the development of start-ups in Bihar by October 2018.
- For the implementing team to support the GoB in the development of a strategy for the Government to adopt that strengthens market linkages by December 2018 to enhance the sustainability of clusters developed in Bihar.
- For the implementing team to support the GoB in the development of a strategy for incentivising participation of leather producers at the CFC by October 2018
- For the implementing team to support the GoB in the development of a strategy to support the development of partnerships with ITIs by December 2018
- For the mid-term review to review the selection process of sectors and clusters to inform the programme on the risk and changes necessary to increase returns and prosperity for Bihar by March 2018
- The output title needs to be changed in log-frame to make it more clearer as “an improved environment for private sector investment in Bihar, notably in informal enterprises and other firms, that increases opportunities for employment, especially among the poor; develops market linkages to increase demand for products produced locally; and enhances productivity to widen the range of locally produced goods and services”.

Output Title	Strong Tax Administration and Financial Management Systems
Output number per LF		2	Output Score	A+
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Departmental coverage of CFMS	25% (11 Dept.) / Functions[2] - 6	Exceeded: 100% (all 44 Dept.) / Functions – 4
2.2 Reduction in outstanding audit paragraphs	10% reduction / (BL: 1475 Paras)	Exceeded – 36% reduction / (931 Paras)
[2] Functions refers to modules/sub-modules of the CFMS application such as budget preparation, budget allotment etc.

Briefly describe the output and provide supporting narrative for the score

GROW-B has delivered the following:
For Output 2.1, to facilitate the rollout of CFMS, GROW-B TA helped develop an implementation and training strategy, test modules, develop guidance and provide advisory support to users. GROW-B TA helped implement an Aadhar-based (unique ID-based) approval process in CFMS, which has helped the Government migrate to a more efficient and cost-effective digital signature-based system. During the implementation phase, the strategy was revised to focus on rolling out CFMS to all 44 Departments.

GROW-B has also helped in implementing major reforms such as abolishing the Letter of Credit (LOC) system to minimize risks of misuse of funds, and rationalise the number of drawing and disbursement officers (25% reduction i.e. 4000+) to reduce the number of payment processing points. These interventions have helped streamline the expenditure management process and improved fund management in Bihar. GROW-B is helping in drafting of amendments to the Bihar Budget Manual, Bihar Treasury Code, which will simplify the public financial management processes and provide legal validity to the business process simplifications enabled through CFMS.

For Output 2.2, GROW-B developed the software for the Bihar Central Audit Para Management Portal (BCAPP). This software will help monitor and expedite audit compliance in all 44 Departments enhancing transparency and accountability across government.

Lessons identified this year, and recommendations for the year ahead linked to this output
- Securing widespread buy-in of all stakeholders to CFMS was vital to ensure capacity was built and sustained. Substantial effort was invested at all implementation stages to demonstrate the benefits of the new system, building trust among users.
- While, the implementing team has been providing effective program management and quality assurance support to deliver the outputs demanded by the Finance Ministry, very little skills capacity has been transferred to Ministry staff. To support the sustainability of GROW-B interventions, government technical staff will need to devote staff resources to work more closely with the TA teams.
Summary of responses to issues raised in previous annual reviews (where relevant)

None

Recommendation
- For the implementation team in partnership with the GoB document the challenges encountered and develop rules of best practices that will inform and expedite future system changes by March 2019.
- For the implementing team in partnership with the GoB develop options that show additionality of rolling out additional functions (beyond 6) under CFMS and additional activities to reduce audit para pendency versus switching resources to other areas of GROW-B by March 2019.

Output Title	Women, SCs and minorities have access to skills and social security programmes
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	40%
Risk revised since the last AR?		No	Impact weighting % revised since the last AR?	No

Indicator(s)	Milestone 2 (2017-18)	Progress
3.1. Percentage of grievances redressed under BPGR Act 2015	61% / (BL: 57.5%)	Exceeded: 75%
3.3. Establish an HRMS: / Offices covered by pay bill automation and e-service book / Number of modules implemented	0 / 0	N/A in this review period / N/A in this review period
3.4. Utilisation of ITIs for vocational training / a) Seats utilization in ITIs / b) Percentage who passes out of it is	72% (BL: 68.7%) / 5% (BL: 7005 students)	Met: 73% / N/A in this review period (exams to be conducted in July 2018)
3.5. Registration of: / a. Job seekers / b. Employers under NCS	5% increase (on 644,616) / 0.5% increase (on 20,146)	Exceeded: 35% / Exceeded: 1%
3.6. Waqf Board cess collection	15% increase / (BL: INR 38.86 Lakh)	Exceeded: 33%
3.7. Loan recovery and access to flow of credit for BSMFC: / a. Loan recovery rate / b. Increased flow of credit	45% (BL: 31%) / 10% increase (BL: 15.4 crores)	Not Met: 38% (7% increase over baseline) / Exceeded: INR 31 crores (94% increase)

For Output 3.1 and Output 3.2, GROW-B TA provided support to implement the BRPGRA. This helped increase the annual redressal rate (from 57.5% to 75% in 2017-18), enhanced Public Authorities’ attendance in hearings (55% in 2016-17 to 95% in 2017-18), reduced erroneous reasons for not resolving grievances and ensured high complainant’s satisfaction (89%).

For Output 3.3, GROW-B TA support to HRMS helped leverage Cabinet approval for INR 52 Crores (£5.8 million) to resource this system and procure implementing contractors. Once implemented fully, the HRMS will enhance staff capacity and capability with departments enabling better decisions to be made and policy impact.

For Output 3.4, TA support to the Labour Resources Department has led to a greater range of vocational training courses offered, higher levels of course participation and stronger interest from the private sector to form partnerships with ITIs. Most notable has been the signing of a MoU with Yamaha (India) that led to over 250 students being selected for two-year shopfloor training.

GROW-B TA also facilitated an Apprenticeship Fair, which led to 1,368 ITI trained students being selected for a monthly stipend of upto Rs. 11,000. GROW-B TA support has been central to developing the Outsourced Career Centre and access to the GoI owned NCVT MIS software. GROW-B TA has also helped procure educational aids and facilitated leadership training of faculty and administrators of ITIs.

For Output 3.5, GROW-B’s recommendation for establishing National Career Service counters in District Registration & Counselling Centres has helped increase job seeker registration (to 35% in 2017-18). GROW-B is also assisting with broadening the scope of Employment Exchanges as Career Centres. Career Centers will have scope to provide counselling as well as last-mile training to enhance employment prospects across Bihar.

For Output 3.6, TA to the Minority Welfare Department led to the design and development of software for an online registration of Waqf Estate, budget, assessment and payment gateway. Rolled out to all 2,500 Waqf Estates, this software will contribute to enhancing cess collection.

For Output 3.7, GROW-B helped rationalise the criteria for selection of a loan beneficiary and developed an automated system of loan application and scoring. TA also defined the functionalities and scope of work to procure an ERP solution, re-engineering the management of the loan process.

Additional Activities

For the MWD, GROW-B helped develop and pilot a Minority Hostel Management System in two locations. For the GAD, GROW-B helped develop WRMIS software to capture the status of vacancy requisition, selection and appointment of women candidates across Government offices. This software enables the nodal GAD to monitor the implementation of this initiative across State and helps increase women participation in government, jobs and gender empowerment.

Lessons identified this year, and recommendations for the year ahead linked to this output
- Bihar’s redressal process is helping the government learn more on the nature of grievances and from this develop new policies to target the root causes. GROW-B needs to evolve to helping the government best use this data in the development of future policies.
- In case of large projects such as HRMS, log frame and risk register should take delays at the Government level into account.
- GROW-B’s outreach efforts – to YAMAHA, LAVA, Cisco, Alstom etc. – are beginning to open up new employment opportunities in Bihar, especially among the youth. This demonstration effect is starting to raise the profile and demand for vocational training across Bihar.
- Low capacity departments such as Minority Welfare Department require more protracted TA support to help staff build confidence and credibility in the decisions tasks they undertake.
- Under BSMFC, there is an increasing need for more innovative pro-poor loan schemes that widen support especially to the most marginalised sections in Bihar.

Summary of responses to issues raised in previous annual reviews (where relevant)

Log frame was revised October 2017.

Recommendations:

- For the implementing team to develop a strategy with the government using the information generated from the grievance redressal process to address the root causes of grievance in Bihar by March 2018.
- For suppliers to develop a strategy with the Minority Welfare Department to strengthen the BMFC to enable access for minority communities to low cost loans.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

The theory of change for GROW-B is summarised in Chart 1.

Chart 1: GROW-B Theory of Change

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

Presently most of output indicators in the programme are well within track:

No	Output	Broad level of intervention	Status	Remarks (linkage with outcome/impact) and the reason for being off track
1	Improved environment for private sector investment	Investment grounding and promotion	On track	Impact on outcome 1
		MSME Cluster Development	On track	Impact on outcome 1
2	Strong tax administration and financial management systems	Implementation of CFMS	On track	Impact on the Impact Indicator
3	Women, SCs and minorities have better access to skills and social security programmes	Strengthening implementation of Grievance Redressal Act	On track	Impact on the Impact Indicator
		Implementation of HRMS	On track	Impact on outcome 3
		Strengthen ITIs	On track	Impact on outcome 3
		Improve employability
		Increased Cess Collection by Waqf Board	On track	Impact on outcome 3
		Strengthen BSMFC to enable better recovery	Off track	Impact on outcome 3 / The delay in implementation of the loan management system is because the Govt. has not decided on the source of funding.

Explain major changes to the logframe in the past year

Indicator Number	Original Indicator	Changes
Impact
1	Development expenditure per capita	Baseline and milestones updated
Outcome
2	Own Tax to GSDP Ratio	Removed as no longer relevant following the cessation of support to the Commercial Taxes Department
3	Higher labour force participation of women and SCs	Baseline and milestone targets updated
Output
1.1	Approval rate of investment proposals	Definition revised to provide clarity
1.2	Conversion of investment proposals	Indicator expanded
1.3	Design and implementation of online SWCS to facilitate the approval process	Indicator revised to better measure process efficiency
1.4	Number of new MSME-CFC proposals approved	Milestones revised to account for the new cluster
1.5	Number of new MSME-CFC commissioned	Milestones revised to account for the new cluster
1.6	Strengthening private sector engagement in technical education	Definition revised to provide clarity
2.1	Increased Non-Tax Revenue from streamlined policies and administration	Removed as no longer relevant following the cessation of support to the Commercial Taxes Department
3.1	Percentage of complaints disposed (with no appeal)	Baseline updated to 2016-17
3.2	Percentage of citizens satisfied with changes to the redressal system	Revised to cover the whole catchment area of GROW-B interventions
3.3	Establish an online HRMS	Removed as the online HRMS will be implemented by the GoB
3.4	Higher seat utilization in government it is	Indicator revised to increase measurement accuracy
3.5	Higher jobseeker and employer registrations under the NCS and SEE	Indicator redefined to provide greater clarity
3.7	Higher loan recovery and access to BMFC credit	Revised as the Minority Welfare Department’s loan has been fully repaid

Describe any planned changes to the logframe as a result of this review

After substantive revisions in the last review period, no further changes are planned to the logframe.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Assess Value for Money (VfM) compared to the proposition in the Business Case, based on the past year

The main cost drivers of TA are fee rates for the technical experts – paid in the form of linked deliverables (49%), quarterly progress reports (40%) and administrative expenses (e.g. rent, travel, etc.) (11%). In this review period 92% (£0.8m) of the budget allocation for 2017/18 was spent, with fees accounting for 87% of this (see Table 1).

Table 1: Cost drivers and performance against budget, 2017/18
	2016/17			2017/18
	Budget (000s)	Actual (000s)	Utilisation (%)	Budget (000s)	Actual (000s)	Utilisation (%)
Fees	807	611	76	736	685	93%
Administrative Expenses	154	74	48	109	91	84%

Total	961	685	71	845	776	92%

Table 1 shows that 87% of the budget was allocated to fees and 13% was to administrative expenses. Budget utilisation has been strong at 92% with a small underspend caused by delays by the State and National Government. Overall, GROW-B financial controls have been satisfactory in keeping costs close to and within budget.

Since the previous review, VfM indicators - economy, efficiency, effectiveness and cost effectiveness - have been developed and measured for each of the GROW-B outputs (see Chart 2). Future work to better monitor and assess VfM will focus on evaluating these indicators over time and against suitable comparators to help inform improvements.

Chart 2: GROW-B Results Chain

The main input costs to GROW-B – staff and admin – have already been reviewed against commercial benchmarks at the selection stage and were judged to meet good VfM standards. As the programme has evolved, GROW-B has consistently remained within budget and typically delivered outputs that have met or exceeded expectations.

Since GROW-B only finances TA, judging whether the programme delivers VfM focuses mainly on how staff are hired and used to deliver outputs and impact. Assessing this for each output:

For Output 1, staff costs per day vary between £110 and £120 per person per day to expedite the approval process of new investment proposals in Bihar; and between £210 and £220 per person per day to approve and commission new MSME-CFC proposals as well as to pair private enterprise with government ITIs. TA staff hired to support the approval process of new investments has saved investors 179 days and has led to £36.9m of additional investment in Bihar. For MSME-CFCs, TA staff have supported the creation of 5 new MSME-CFCs and £3.6m of new investment.

For Output 2, staff costs have ranged between £170 and £180 per person per day with interventions focused on facilitating the rollout of the CFMS across all 44 State Government Departments. With the milestone set at 11 (25% State Government Departments), staff achieved the rollout of CFMS to all departments saving the government substantial servicing charges on its loans from the RBI by enabling better forecasts and planning of departmental budgets.

For Output 3, staff costs range from £289 per person per day to £152 per person per day across a range of activities that support greater access to skills and social security programmes for women, scheduled castes and minority groups in Bihar. Examples of good VfM is found in GROW-B TA that enhanced the grievance redressal system of Bihar by increasing the number of satisfactorily redressed grievances by 93,000 (431 per day) and reducing the percentage share of the top three grievances by 4 percentage points. GROW-B interventions in Bihar’s redressal system have received national recognition. Additionally, GROW-B TA has helped pair two Government ITIs with private sectors firms, increasing the range and volume of vocational training places available and helping to place a greater number of graduates in jobs ( 1 in 5 from 1 in 10).

Across these outputs, while there is variation in staff costs, on average staff costs per day in 2017-18 are £165 and less than half the capped fee prescribed for Project Co-ordination staff by DFID in recent tenders. A benchmarking exercise has not been conducted for this review but it is judged that major initiatives such as industry promotion, introducing financial technology systems, software development and employment enhancement require greater skills and so increase the cost of remuneration. The mid-term review will look more closely at this issue to judge whether there is scope to deliver GROW-B outputs more economically without undermining the quality of the outputs delivered to the GoB.

On additionality, it is not yet possible to measure the full additionality of GROW-B TA but it is clear from the range of outputs in this review that TA has been cost-effective. In the case of Output 1, staff resources directed to expediting the approval process for new investment proposals has generated a high return in terms of new investments into Bihar. Similarly, TA on developing and rolling out CFMS and on developing the Grievance Redressal system have exceeded expectation and are having a substantial impact in Bihar. It is therefore judged that on the basis of these strong examples that GROW-B interventions are delivering additionality for Bihar.

With an independent mid-term review due in the next review period, this review will provide a greater focus on value for money, look closely at measuring additionality, assess whether VfM be more sharply measured, develop sensible comparators to calibrate VfM and draw lessons on how VfM may be enhanced in the future.

Based on this assessment GROW-B is judged to have delivered good VfM in this review period.

Recommendations:

- For the independent mid-term review to assess the drivers that cause dispersion in staffing costs, particularly in Output 1 and 3 interventions, collect benchmarks to assess VfM in daily rates and where possible develop options that ensure better VfM by December 2018.
- For DFID and the intervention team to review the milestones set for 2018/19 to ensure that resources are redeployed to activities that maximise VfM by October 2018.
- For DFID and the intervention team to prepare for an independent mid-term review assessment, especially on VfM, and agree with the GoB a suitable firm to undertake this review by October 2018.

E: RISK

Overview of main programme risk and mitigation

Risk Category: Description	Impact & Mitigation plan
Context: Political instability on account of upcoming national and state elections. A fractured mandate may shift focus from existing reform priorities.	Moderate: Buy-in of senior GoB officials has been secured and implementation agreed with the senior bureaucracy of Bihar. A mid-term review is planned next year which will recommend actions informed by the prevailing political situation.
Reputational: The programme fails to meet timelines or quality standards expected by the GoB	Moderate: Progress is monitored quarterly against key milestones and performance criteria. Review meetings with the partner departments help assess and manage expectations and avoid project overruns or deterioration of quality standards.
Delivery: Risk of deliverables not achieving the impact (optimism bias)	Moderate: Activities are agreed annually with partner department and signed off by the Project Steering Board headed by the Chief Secretary. The Project Steering Board can take a view on priority areas and recommend change if activities are meeting the desired impact.
Delivery: Risk of reduced government interest resulting from staff changes	Moderate: Interventions are signed off by the Project Steering Board which mitigates disruption caused by individual staff changes.
Delivery: Risk of stretching resources too thinly across commitments.	Moderate: Payment-based milestones are set according to agreed deliverables and decided annually. Costs are monitored on a bi-monthly basis, with further checks at annual and mid-term reviews stages.
Delivery: Weak downstream service providers selected by GOB can add to output delivery costs	Moderate: This risk applies to two GROW-B interventions – CFMS and HRMIS – where downstream service providers have not been able to mobilise enough support staff. This has placed strains on GROW-B resources, as the implementation team have had to provide additional support, document lessons, recommend process improvements and build capacity of GoB staff to offset these risks. The implementing team are regularly monitoring this risk and highlighting their findings to the Finance Department as well as the vendor when key deliverables are at risk.
Delivery: Low sustainability after the programme ends	High: All GROW-B interventions are accompanied by a rollout plan, including a change management strategy to inform the beneficiary department on the level of future support needed. The Finance Department is being sensitised to bring in staff to work with the GROW-B team to transfer skills and capability. Similarly, in Industries department, two program management teams have been mobilised from resources of the department. Measures like these are being put in place to enhance the sustainability of programme interventions after the programme ends.
Delivery: Delays in receiving Government approval	High: All plans need to be approved by the government in advance. Any changes in the plan will be documented through proceedings/ minutes of meetings. Issues of delays can be addressed at review meetings.

Performance of partnership(s)
DFID India’s Partnership Principles state that DFID India’s support is based on a shared commitment to the following four principles:
- Helping India reduce poverty and leave no one behind
- A commitment to respecting human rights and other international obligations
- A commitment to strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption
- A commitment to strengthening domestic accountability
In accordance with these, GROW-B complies with DFID India’s partnership principles and where funding is channelled through partner organisations this is done in accordance with these principles. Compliance to these principles is ensured through procedures such as due diligence, financial audits and technical reviews in close collaboration with Government of Bihar.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial and financial issues

In this review period, the Programme had maintained a regular reporting of the various payment linked deliverables which led to the processing of the payment under the Contract. The list of deliverables submitted for last contract amendment are as follows:

Name of Deliverable	Targeted Date	Date of Submission
Quarterly Progress Reports
Quarterly Report No. 5 (July 17 - Sept 17)	10-Nov-17	22-Nov-17
Quarterly Report No. 6 (Oct 17 - Dec 17)	10-Jan-18	29-Dec-17
Quarterly Report No. 7 (Jan 18 - Mar 18)	31-Mar-18	20-Mar-18
Output 1
Project Report (DPR) for development of Leather Goods Complex in Muzaffarpur	23-Oct-17	28-Nov-17
Evaluation Report for selection of PMA for Upendra Maharathi Shilp Anusandhan Sansthan for development of Handloom and Handicraft Clusters	30-Nov-17	23-Nov-17
Report on Common Facilitation Centre at Moratalab Leather Footwear Cluster	31-Dec-17	28-Feb-18
Progress report on operationalization of Online Single Window Clearance System	31-Mar-18	28-Feb-18
Report on the implementation status of Business Reform Action Plan, 2017 under DIPP's Ease of Doing Business framework	15-Dec-17	13-Dec-17
Output 2
Develop a new Model and bidding documents to extend other government run ITIs under PPP by selection of a private sector partner	23-Oct-17	28-Nov-17
Compendium of circulars, notifications, etc. for the Registration Department	30-Nov-17	23-Nov-17
Operationalisation of IT Cell for Finance Department and submission of the report of activities with approval from Department	30-Nov-17	15-Dec-17
Implementing Audit Para Tracking Software Report	28-Feb-17	14-Dec-17
Output 3
Rollout of Bihar Minority Hostel MIS across 21 districts in the state	31-Mar-18	13-Dec-17
A detailed review of Quality of orders under BRPGRA resulting in standardized templates for enhancing quality and compliance	12-Feb-18	20-Mar-18
Review & assessment of BRPGRA performance and recommendations for enhancing Redressal	21-Oct-17	22-Nov-17
Roll out of Bihar Centralised Audit Para Portal in other departments	19-Mar-18	20-Mar-18
Assistance in the procurement of a technical agency for development & Implementation of Human Resource Management System for all GoB departments	19-Mar-18	20-Mar-18
Online Registration and Payment System for WAQF estates	31-Mar-18	28-Nov-17

Till the end of the last contract period, only two deliverables were still pending.

	Fees (GBP)	OPE (GBP)
Total value of contract amendments for the Implementation period (July 2016 – March 2018)	1,648,720	263,000
Actual billed in the same period	1,597,841	230,136

Date of last narrative financial report(s)	N/A
Date of last audited annual statement (s)	Due in end July 2018

G: MONITORING, EVIDENCE & LEARNING

Monitoring

The logical framework has been the basis of performance monitoring. The following monitoring and evaluation mechanisms are used to assess GROW implementation progress:
- Quarterly Progress Reports with output wise information update, and major achievements and challenges being faced in the programme. Information under specific outputs is disaggregated regarding cumulative achievement and monthly achievement.
- Regular visits of DFID Task Team and regular interactions (both formally and informally) with the Head of the Partner Departments, key stakeholders.
- Project steering meeting chaired by the Chief Secretary, to assess progress, identify emerging needs and opportunities and discuss priorities. During the review period, one project meetings were held.
- Payment Based Deliverables – 19 were deliverables submitted to DFID in the reporting period excluding the quarterly reports.
- Review meetings are organized by the Finance Department and individual partner department

To support the findings of this annual review, DFID have undertaken field visits with staff from outside of the programme team (including the Head of Office) to monitor progress and review logframe outputs of GROW-B. Inputs from GROW-B beneficiaries as well as Officials from the state government helped validate findings on outcomes and impacts of GROW-B interventions. In the next review period, an independent mid-term review will take place to ensure that the programme remains relevant to enhancing the prospects of those poor in Bihar; to promote inclusion and reduce inequality in a manner that delivers good VfM.
On safeguarding, the implementation teams of GROW-B have signed DFIDs safeguarding policy as well as attended workshops on safeguarding to ensure that behaviours and ways of working meet and uphold safeguarding standards. DFID will continue to monitor the safeguarding standards in future years of this programme.

Evidence

The programme lays significant impetus on evidence-based planning and implementation. Best practices within the country and from UK/outside are used to design and implement the programme interventions. Further, stringent measures are put in place for establishing baseline wherever possible and arrive at realistic milestones for the programme that will be tracked and monitored throughout the programme lifecycle. There is also a provision for a third party impact evaluation towards the end of the programme. The monitoring and evaluation activities will entail participation of all the programme stakeholders (concerned GoB departments at State level, TA agency, and Task Team).

Learning

The GoB is committed to good governance. There has been a high demand for technical assistance (TA) even for support which often goes beyond the result framework defined within the programme

The initial period had been successfully utilized to develop a trust and a strong bond with the Government, which further improves the coordination and speeds up the implementation

The State Government’s reputation in managing vendors and service providers does not always attract the best of bidders. Weak service providers has the potential to undermine or add to the costs of delivering the outputs of GROW-B.

Progress on recommendations from previous reviews

- Based on the recommendation from the last review, the logframe indicators were reviewed for their adequacy and relevance and accordingly enhanced. The details of revisions made are listed in Section C.
- Detailed VfM indicators have been finalized in consultation with the DFID Task Team
- The mitigation plan for delays on account of pending government decisions have been put in place
      - Smart Guide
## The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.
## The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below as a guide to completing the annual review template.
A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided