FLAG A

Global SME Finance Initiative

Business Case

January 2012

EDRM Number: 3349064

Contents	i	Page

Acronyms	ii	3

Intervention Summary	4-7

1. Strategic Case	7-17
Context and need for DFID intervention	7
Impact and Outcome	14

2. Appraisal Case	18-31
Critical Success Criteria	18
Assessing strength of Evidence	18
Appraisal of options	20
Assumptions	22
Cost and Benefits Estimations	23
Measures to be used to assess value for money	31

3. Commercial case	32-38
Value for Money Through Procurement	32, 38
Selection of Partner Financial Institutions	33
Use of competition to drive commercial advantage	34
Response of market place	37
Underlying cost drivers	37
Procurement process	38
Contract and supplier performance management	38

4. Financial Case	39-43
Total cost	39
How will it be funded	39
How will funds by paid out	40
Building of Pipeline	40
Co-funding from Country Offices	42
How expenditure will be monitored, reported and accounted for	43

5. Management Case	44-55
Oversight	44
Management	45
Conditionality	47
Monitoring and evaluation	48
Risk Assessment	50
Results and benefits management	55
Annex 1 List of Priority Countries	a	57
Annex 2 Theory of Change	b	59

Endnotes	60

Acronyms (to be completed)

DFI	Development Financial Institution
M&E	Monitoring and evaluation
MIS	Management information system
MDGs	Millennium Development Goals
HMG	Her Majesty’s Government
DFID	UK Department for International Development
SME	Small and Medium Enterprise
NGOs	Non Government Organisations
IFC	International Finance Corporation of the World Bank Group
£	Pound Sterling
RCT	Randomised Control Trial
IRR	Internal Rate of Return
CAGR	Compounded Annual Growth Rate
MSME	Micro Small and Medium Enterprises
PSD	Private Sector Department of DFID
DFIs	Development Financial Institutions
DEG	Deutsche Investitions- und Entwicklungsgesellschaft
CDC	CDC Group Plc (formerly Common Wealth Development Corporation)
MDBs	Multilateral Development Banks
OECD	Office of Economic Co-operation Development
DAC	Development Assistance Committee of the OECD
ESG	Environment, social and governance
CSC	Critical Success Criteria
BCR	Benefit Cost Ratio
NPV	Net Present Value
CBO	Community Based Organisations
BAR	Bilateral Aid Review
AME	Annual Management Expenditure
ADB	Asian Development Bank
PE/ VC	Private Equity/ Venture Capital funds
WBG	World Bank Group
SRP	Spending Review Period of HMG
LICs	Low Income Countries
PFIs	Partner Financial Institutions selected under this Initiative
IT	Information Technology
MIS	Management Information System
EBRD	European Bank for Reconstruction and Development

Intervention Summary

Title: DFID support for the IFC Global SME Finance Initiative
What support will the UK provide?
1. DFID will provide up to £100 million over 7 years (2012 -2019) contribution to the Global SME (Small and Medium Enterprise) Finance Facility being set up by the International Finance Corporation (IFC). Of this, £60 million will come from the Private Sector Department’s (PSD) aid framework over the current Spending Review Period (SRP 2011-15), with a provision to bid for an additional £25 million in the next SRP if the independent mid-term review of the programme shows that the Initiative is delivering good results and value for money for DFID. The remaining £15 million is expected as co-funding from DFID Country Offices – £10 million from DFID Nigeria, and up to £5 million from DFID Mozambique. / 2. Our support will be as anchor donor to a Global SME Finance Initiative being put together by the IFC.

Why is UK support required?
3. SMEs can play a major role in job creation and economic development, especially in developing countries. Yet, growth of SMEs is severely constrained by lack of access to capital and business advice. Recognising the important role that SMEs can play and the constraints faced by them, setting up a global programme for scaling up SME financing in poorer countries, is a key deliverable of the DFID Business Plan 2011-15 and the Private Sector Department’s (PSD) Operational Plan 2011-15. It is also consistent with wider UK Government objectives of encouraging enterprise development in developing countries that are facing numerous challenges, including their ability to maintain investments during global economic crises and stimulation of growth in countries emerging from conflict. / 4. The G-20 has also called for greater support to small businesses to harness their contribution to wealth creation and employment generation. The UK will take a leading role by providing anchor funding to a global initiative being developed by IFC as part of the G20 process. This initiative will bring together the combined resources of donors, Development Finance Institutions including the IFC and commercial banks to catalyse significant funding for bridging the global SME financing gap. / What need are we trying to address? / 5. Developing countries in Africa and South Asia, especially the frontier markets and conflict affected markets, need more jobs for their young populations. For example, according to one estimate, Africa will require roughly 7 to 10 million jobs per annum to absorb the new entrants in the labour markets[1]. Failure to do so could disturb social stability and undermine the prospects for finding lasting solutions for peace in conflict and post-conflict countries. / 6. Small and medium enterprises (SMEs)[2] can play a major role in job creation (although SMEs are not the only way to jobs) and economic development, especially in developing countries where they employ on average 66% of the total permanent, full-time employment in a country[3]. But the development of SMEs is widely inhibited by a range of factors that this Initiative seeks to address. In Low-Income Countries (LICs), 43% of small enterprises and 38% of medium enterprises report access to finance as a major obstacle to their operations and growth[4]. / 7. SME financing is severely constrained because of high transaction costs and high perceived risks. Banks do not lend “enough” to SMEs in part because they are not able to assess the risks and so they overestimate them and overestimate the amount of capital that they need to allocate to the lending. The perception of risk is exacerbated by lack of collateral from SMEs and the collateral regime itself is not very sophisticated in many developing countries. Also, neither the banks nor other market players provide much business advice to SMEs because it is difficult to do so cost effectively. Equally, developments in information technology that have transformed other areas such as payments and money transfers have not really affected how banks and other financial institutions deliver financial services to SMEs at lower cost. / What will we do to tackle the problem? / 8. Traditional approaches have tended to concentrate only on providing credit lines to banks and have not always leveraged the banks’ own capital as effectively as they might. Some banks are not liquidity constrained but are choosing to invest their capital in low risk/low return assets. Lines of credit although relevant in liquidity constrained contexts have not always proven to be effective in getting banks to increase their lending to SMEs on a sustained basis. Very often, the financing to SMEs slows down or disappears when the donor support falls away. We propose to take a more comprehensive approach to address the SME financing gap. We believe that (a) providing banks with risk capital, funding for technical advice and technological innovations as well as providing liquidity and (b) improving information about SMEs’ credit worthiness, provides a more rounded package and has a better chance of causing banks to sustainably increase lending to SMEs. / 9. Reforming wider financial structure issues (eg to drive more competition between banks, facilitate market entry) is also part of the solution to drive down lending costs and promote more risk appetite. This iniative is not targeting financial sector restructuring or regulation which requires other skills and approaches but in DFID we are continuing to support such work in parallel, including through the FIRST Initiative (Financial Sector Strengthening and Reform Initiative)). / 10. We believe that the IFC has the experience, network and relationships with major DFIs, banks and financial institutions in our target countries to deliver such an initiative more cost-effectively and quickly than other alternatives. IFC will bring together other donors and DFIs into this facility to increase the size of risk sharing capital that will enable banks to scale up financing for SMEs. / 11. DFID will fund implementation of this Initiative across 15 countries in Africa and South Asia including conflict affected countries. DFID’s funding to the Initiative will comprise three components: / Component 1: Risk Capital: A £38 million risk sharing fund to work in collaboration with about 35 commercial banks (national and international) and non-banking financial institutions (from here on in this document called Partner Financial Institutions – PFIs) for scaling SME financing on a commercially sustainable basis. This fund will be capitalised by donors and by development finance institutions and will provide (i) risk sharing to cover (no more than 50%) the commercial risk in the SME lending portfolio of the PFIs. This will enable higher risk taking by the PFIs and provide capital relief through requiring lower risk weighting in the banks’ own balance sheets and (ii) direct funding lines[1] especially in markets with liquidity constraints. The grant financing along side financing from the DFIs will lower the pricing as well as conditionality of the products to the PFIs compared with a DFI only fund. Risk pooling between the DFIs is also anticipated to lower pricing. The IFC projects that DFIs will put in roughly £325 million based on DFID’s funding of £38 million to this component. This is expected to mobilise an additional £325mn of financing by the PFIs. The balance or mix of these products for any PFI will be driven largely by its needs and objectives for SME financing. / Component 2: Advisory Services: A complimentary £26.90 million Technical Assistance pool to (i) support the PFIs in establishing and strengthening skills, systems and processes (e.g. credit risk appraisal and management) in scaling up their SME financing portfolio and; (ii) support development and improvement in financial market infrastructure (e.g. credit bureaus and asset registries) to improve the information on credit worthiness of SMEs which can in turn bring down the risks and transactions costs in lending to SMEs. / Component 3: Technology-Based Solutions: A £2.9 million Technical Assitance pool to fund three of the fourteen G-20 SME Finance Challenge Winners for scaling up technology based solutions which can help some of the systemic constraints such as lack of credit history for potential SME promoters through innovative, low cost approaches, namely (i) psychometric credit scoring tests which help banks predict the risk profile and entrepreneurial capacity of potential SME borrowers; (ii) web-based tools for SMEs to access new markets locally and overseas and; (iii) internet based platforms to help SMEs gain access to formal/informal investors and mentoring support. / Who will be implementing the support we provide? / 12. The Initiative will be managed and implemented by IFC to deliver the results agreed between IFC and DFID. The decision to go with IFC is based on strategic as well as commercial reasons. We believe we are making a strategic choice in going with IFC as pooling resources through the IFC makes it possible to deliver a global programme of large size and geographical scope in the SME finance space and help deliver on our business plan. Partnership with IFC makes this Initiative rightly ambitious and technically cutting edge. Using the IFC also allows us to pool risk and leverage resources from DFIs on a scale that would not be possible through the efforts of any single donor. In partnering with IFC, we believe we can leverage IFC’s existing network and relationships with commercial banks and international financial institutions, as well as benefit from its technical advisory capacity and management bandwidth on the ground, all of which should help deliver the programme quickly and more cost effectively.
[1] World Bank Africa Regional Strategy, “Africa’s Future and the World Bank’s Support to it” ; March 2011.
[2] There is considerable variation in their definition around the world. A common definition of SMEs includes registered businesses with less than 250 employees. This places the vast majority of all firms in the SME sector: nearly 95 percent of registered firms worldwide. To narrow this category, SMEs are sometimes distinguished from micro enterprises as having a minimum number of employees, such 15 or 20. An alternative criterion for defining the sector includes annual sales, assets, and size of investment.
[3] Ayyagari, M., A. Demirguc-Kunt., and V. Maksimovic (March 2011), “Small vs. Young Firms across the World: Contribution to Employment, Job Creation and Growth”, World Bank.
[4] This is based on World Bank Enterprise Surveys across 124 countries between 2006 and 2009. These surveys define firms with less than 20 employees as small enterprises and those with between 20 and 100 employees as medium enterprises.
[1] For example, if a local commercial bank or NBFI in Mozambique has liquidity constrints in scaling up lending to SMEs in Mozambique, the package of support from the risk capital component to this local bank or NBFI can include a direct lending line, enhancing the local bank’s liquidity for scaling up lending to to SMEs.

What are the expected results?
What will change as result of our support? / 13. The combined size and geographic scope of the Initiative is very large and responds to the market need. Overall, the Initiative is expected to deliver over 700,000 additional SME loan accounts over the baseline (with at least 25% of these loans for women headed enterprises) and help generate some 2.8 million new jobs. / What are the planned Outputs attributable to UK support? / 14. Of the results highlighted above, those attributable to DFID investments will include; / At least 200,000 additional SME loan accounts over the baseline (with at least 25% of these loans for women headed enterprises). / One million new jobs generated by those SMEs. / At least £600 million of DFIs and commercial funding catalysed through the risk capital component. / At least £5 billion of additional lending from the partners financial institutions to SMEs over the programme period through the combined effects of all the three components – risk sharing, TA to PFIs, financial market infrastructure development and the technology based solutions explained in paragraph 10 above. / At least a quarter of the results will come from the frontier markets comprising of South Sudan, Malawi, Sierra Leone, Liberia, Uganda, Mozambique, Bangladesh, and Nepal. Moreover, we expect that 100,000 additional SME loans will be delivered by the end of March 2015 in line with DFID’s SRP targets. / How will we determine whether the expected results have been achieved? / 15. The Initiative will have a comprehensive monitoring and evaluation (M&E) framework. IFC will provide half-yearly reports to DFID of progress against the indicators in the Logical Framework agreed with DFID, and will report key outputs on portfolio indicators of investment and advisory activities based on IFC reporting guidelines. / 16. DFID will undertake and or commission, with full support from IFC as required, annual Output-to-Purpose Reviews to assess progress, an independent mid-term review before end of year three (February 2015), and an end-term Project Completion Review (PCR) to assess whether the targets in the Logical Framework have been achieved and, whether and to what extent the cost-benefit assumptions outlined in the Appraisal Case have been confirmed. While there is strong evidence on the impact of risk sharing, capacity building and development of financial market infrastructure on the level of SME financing, evidence on the impact of SME financing on job creation and income is weak and patchy. Therefore, we will focus specific effort to evaluate this under the Initiative. / 17. Although we expect the programme to deliver 100,000 new SME loans by March 2015 which represents 50% of the deliverable, it is recognised that successful delivery in the more challenging frontier markets will take longer.

Business Case for DFID support to the Global SME Finance Initiative:

1. Strategic Case

A. Context and need for DFID intervention / 18. A prosperous small and medium enterprise (SME) sector is a characteristic of successful economies. There are good conceptual arguments that SMEs are more labour intensive than large firms. There is considerable variation in the definition of SMEs around the world often based on the number of employees, sales, or assets[5]. For the purpose of this programme SMEs are defined as registered formal small businesses with annual turnover of up to US$5 million and/or less than 100 employees. However, there may be a need to relax this limit based on country level diagnostic, as evidence suggest larger firms (100-250 employees) have better productivity. DFID’s overall portfolio includes a variety of programmes on financing of microenterprises, supply chain development, and improvement of the enabling environment, that seek to support small businesses in the informal sector. / 19. SMEs can drive economic development by providing jobs and income, expanding the middle class, and broadening the tax base so essential to raising and sustaining public expenditure on health, education and other social services in the low-income countries. SMEs can also play an important role in building a dyanamic and flourishing private sector in low-income countries over a period of time. / 20. Some commentators however challenge the assumption that SMEs are better for job creation than larger firms. Indeed, some researchers find that large firms provide more stable, higher-quality jobs than small firms[6]. However, in the context of developing countries, recent research provides clear evidence that small firms are good at creating jobs. For example, a World Bank paper[7] (March 2011) based on cross-country database concludes that small firms (in particular, firms with less than 100 employees) and mature small firms (firms older than 10 years) have the largest share in job creation. Moreover small firms, in particular those less than 10 years old have higher job creation rate than large firms. Expansion of the SME sector, therefore, will boost employment and hence reduce poverty. / 21. However, SME financing is severely constrained because of high transaction costs and high perceived risks. In Low-Income Countries (LICs), 43% of small enterprises and 38% of medium enterprises report access to finance as a major obstacle to their operations and growth[8]. / 22. A 2010 study by IFC and McKinsey to assess and measure the credit gap of micro, small and medium enterprises (MSMEs) revealed that over 300 million formal and informal businesses in the developing world suffer from credit constraints and/or have no access to credit (i.e. overdrafts and loans). Of the 25 to 30 million formal SMEs, 70% have insufficient or no access to finance and have an estimated credit gap of US$700-850 billion, which represents 21-26% of current outstanding SME Credit. There are significant differences among regions. Sub-Saharan Africa (SSA) and the Middle East and North Africa (MENA) have the largest credit gap relative to outstanding credit of up to 360% and 150% respectively. / 23. In Africa for example, only 5.4% of the total bank loans went to small firms in Africa as compared to 13.1% in all developing countries[9]. Similarly, bank approvals for loan applications by small firms in non-African developing countries average 81.4%, whe­reas only 68.7% of such applications are ap­proved by banks in Africa. Bank lending to SMEs in developing countries is more costly than in developed countries. Fee charged on SME loans by banks in developing countries was 0.97% of the loan amount compared to 0.37% in developed countries. Interest rates on SME clients are also 6 to 7 percentage points higher on an average in developing countries (average 15.7%) than in developed countries (average 8.8%)[10]. / 24. Firm level studies also indicate that SMEs are undersupplied with finance. One such study showed that when SMEs were offered subsidised financing they often expand operations, rather than substitute for more expensive borrowing. This indicates inadequate supply of finance is constraining expansion of SMEs [11]. / 25. Moreover, recent research into factors affecting transition to self-employment and entrepreneurship in conflict affected countries suggest an important role for financing constraints. For example a World Bank working policy paper (2009)[12] reveal that after controlling for household wealth, having an existing bank relationship increases the likelihood of starting a business with hired employees and increases the chances of survival for the new entrepreneur. / 26. The SME financing gap can be attributed to several factors at different levels. At the macro level, there is strong evidence in certain countries of classic crowding out i.e. large government borrowings to fill fiscal deficits constraining the availability of credit to the private sector and hence SMEs. Structural issues within the financial sector and monetary policy limits on net credit growth also constrain availability of credit to the private sector. It will be important for the proposed programme to work with the grain of fiscal, monetary policy and financial structural reform in particular countries – and not for example try to compensate for high interest rates driven by fiscal policy. / 27. Wider enabling environment related issues also play a critical role, especially government failures that result in weak underpinnings of markets in areas such as property rights, contracting frameworks, creditors’ rights, collateral systems, and information infrastructure (e.g. credit bureau, collateral registry etc); and market failures (such as information asymmetry between financial institutions and SMEs) that make lending to SMEs relatively costly and hence inhibit provision of commercial finance. SME’s survival risk can be high as they are vulnerable to changes in market conditions. Moreover, the performance and survival of an SME are often dependent on an individual owner/manager. Dealing with SMEs may have high costs per transaction for banks. High prices of credit may help banks cover these costs, yet when prices become too high only the very risky SMEs will ask for credit. So the market may not clear at any price. / 28. At the more operational level, risk aversion by banks and financial institutions is another important factor constraining SME financing, especially in developing country context where banks are not under tremendous business compulsions to push the risk frontier. The perception of risk is exacerbated by lack of collateral from SMEs. Moreover, cash-flow and equipment based lending are not very well developed to meet demand from SMEs who are unable to offer collateral. / 29. In addition, developments in information and communication technology that have transformed payments, transfers and some other areas of financial services have not really affected how banks and other financial institutions deliver financial services to SMEs. We believe many of the advances in financial inclusion will be driven by new technologies. There are at least three areas where support for use of technology under this Facility can help achieve a stronger impact (See Paragraph 20) / 30. The challenges described above reveal the need for a comprehensive approach to address the SME finance gap in a sustainable and scalable manner that goes beyond lending. Moreover, the estimated financing gap is too large to be tackled by any single entity and requires a collaborative effort, including with commercial banks, to achieve significant impact. Despite the wide financing gap, 75 to 80% of those formal, emerging market SMEs that do not have access to credit already do have a deposit account[13]. This suggests that there exists functioning relationships with financial institutions that can be built upon to bridge the SME finance gap. / What will we do? / 31. We are proposing a comprehensive and market based approach to address the constraints of financing SMEs which includes the three components or outputs (see paragraph 11). / 32. In order to achieve the above, we are proposing a 7-10 year programme for £75-100 million which will be implemented across 15 countries. We further propose that our funding be routed through the Global SME Financing Initiative being organized by IFC, which is linked to a G20 initiative on scaling up financing for SMEs. We propose to make an initial commitment from DFID of £60 million in this Initiative plus up to £15 million co-funded by DFID country offices: £10 million from DFID Nigeria and up to £5 million from DFID Mozambique. Some other DFID Country Offices such as DFID South Sudan, DFID Uganda, and DFID Zambia have also shown interest for collaboration with the Initiative, including co-funding. If it transpires during the inception and early implementation phase that additional DFID Country Offices wish to fund their in-country SME objectives through this programme under a single composite Business Case – we will increase the total budget commensurately. We also propose the option to increase the size of the programme by a further £25 million for an additional 3 years for a total programme life of up to 10 years, if at the third year the independent mid-term review shows the programme is delivering good results and value for money for DFID. Overall, DFID’s contribution to the Initiative will not exceed £100 million, for which this Business Case has been fully appraised. / 33. The Initiative will operate globally in countries where IFC operates. DFID funding will support implementation of the Initiative in 15 countries identified in the design and appraisal of the Initiative. Pipeline countries include South Sudan, Malawi, Ghana, Sierra Leone, Liberia, Uganda, DRC, Tanzania, Mozambique, Kenya, Nigeria, Bangladesh, India, Nepal, and Pakistan. However, there will be flexibility to add to and/or substitute the list with other DFID priority countries such as Afghanistan, Zambia and Rwanda. Other donors are also expected to participate in this Initiative in support of these and other developing economies. DFID funds may be allocated for projects in other DFID priority countries on an ad hoc basis, subject to a market assessment and consultation with relevant DFID Country Offices. / 34. At the same time Development Finance Institutions such as the IFC, EIB and KfW that have mandates to invest public finance in the private sector in developing countries are not pushing forward the frontiers of SME financing. DFIs have been clear that the risk appetite of their own shareholders and their return on equity targets as well as competition for resources in better off countries limits their willingness to increase exposure in the SME markets without some buffer from additional grant financing. DFIs exposure in the poorest and fragile states remains very limited. They have been clear that without some buffer they would only be be prepared to lend to the facility at significantly higher rates. Our consultation with investors, including private equity investors, and commercial banks provided independent corroboration of the views of IFC and other DFIs that donor grants are required to support lending to SMEs in low income countries and regions. Our funding is aiming to draw the DFIs in to such a facility and to allow them provide their financing at a lower rate of interest than they would have otherwise done. / 35. There are strong arguments for a central initiative on this agenda. The proposed Initiative is ambitious and technically cutting edge. It can pool risk and leverage resources from DFIs on a scale that would not be possible through individual country level initiatives. It leverages IFC’s and other DFIs’ experience, global footprint, commercial rigor and funding -- it is unlikely that multiple small country-level programmes of this type could be undertaken with large DFIs such as IFC and certainly not so cost-effectively. The Initiative also provides flexibility to respond to shifts in country and regional needs over the term of the programme. IFC has an active portfolio of over 50 banks in SME banking advisory alone, 75% of which have received financing support from IFC. On both the investment and advisory side, IFC has a healthy pipeline in DFID priority countries in Sub-Saharan Africa and south Asia. / 36. Moreover, the proposed Initiative can help DFID Country Offices save on design cost and time if they join the programme. This is looking attractive to several country offices who have indicated interest in collaborating with the facility, including providing possible co-funding. The programme will work in close collaboration with the relevant DFID Country Offices with a view to optimise design cost and cost of delivery of DFID Operational Plan targets and priorities. / More Detail on Outputs / Output 1: / 37. The risk capital component has been designed as a catalytic investment vehicle to mobilize US$ 3.5 – $ 4.0 billion in new SME financing. This is designed to include US$ 0.4 billion funding from donors and US$ 1.4 billion from DFIs (led by IFC with US$ 200 million). This is projected to further leverage an additional US$ 2.0 – 2.4 billion in new, direct private-sector financing for SMEs from the banking clients of the facility. IFC is planning to mobilise funding from donors and public funding from DFIs in three closings over the next 6-12 months. IFC expects to achieve the first closing by February 2012 based on DFID’s commitment of £75 million ($120 million). IFC expects DFID’s funding to the Initiative to deliver outputs and results as explained in the diagram below. / *See paragraph 36 for explanation of this number. / 38. DFID is planning to be the anchor donor in the first closing planned for February 2012. The IFC projects that DFID’s investment of £38 million in the risk sharing component in the first round of funding will aim to catalyse £325m of investments from DFIs such as IFC, KfW, EIB, OPIC, OFID and IDB which will be used to provide risk-sharing capital to leveraqage new PFI loans. Maximum risk sharing will be on a 50:50 basis (ie between the Fund and the PFI). When this risk capital is leveraged by the PFIs through their lending as loans to SMEs of average tenure of 2.3 years, the fund can be recycled over the programme period of 7 years. Based on our estimates of leverage that will vary bank by bank IFC estimate that the fund will generate additional volume of lending to the SMEs of the order of £1.6 billion (assuming an utilisation rate of 75%). / 39. Further closings will extend the size and impact of the fund beyond this. IFC is planning to raise $100 million in donor funds and $600 million in DFI funding within the next 6-12 months based on discussions with donors such as the Arab Fund, SIDA and the Dutch and IFIs/DFIs in Asia, Europe and the Middle East. / 40. The risk capital component will provide two different types of products to the Partner Financial Institutions (PFIs - selected commercial banks and non-banking financial institutions) –(i) risk sharing to cover (no more than 50%) of the commercial risk in the new SME lending portfolio of the PFIs. (ii) direct funding lines especially in markets with liquidity constraints. The grant financing along side financing from the DFIs will lower the pricing of the products to the PFIs compared with a DFI only fund. Risk pooling between the DFIs is also anticipated to lower pricing. The IFC projects that DFIs will put in their funding at a price between Libor + 3%-6% based on DFID’s funding of £38 million to this component. Without DFID’s funding, the DFIs would not have increased their support for this sector at all or would have done so at a price that was up to 5 percentage points higher and with significant loan conditionality in frontier markets. This structure is expected to mitigate the risks and lower the ramp-up costs for PFIs to target SME segments they would not otherwise fund. The risk sharing component will reduce the potential losses of PFIs from lending to SMEs and thereby incentivise them to take more risk and increase their exposure in our target markets and do so at a lower price. Grant funding will be complemented by other IFC investment instruments e.g. investments by IFC in the PFIs without any risk sharing under the Initiative. All investment instruments will be structured to take into account country and sector-specific funding needs, the specific risks and gaps being addressed, as well as the needs of the financial intermediaries. There will be a strong focus on (a) expanding access to finance to women in business and (b) SMEs in conflict-affected and poorer countries. At scale; dozens of partner banks and NBFIs would receive funding based on their willingness and ability to address the SME financing gaps in a significant and sustainable way in the identified markets. Most of those FIs are also expected to benefit from capacity building services provided out of this second component of the Initiative. / Output 2: / 41. Approximately £27 million of the DFID funding will be used to fund capacity building support to PFIs and TA for financial market infrastructure development. / 42. Capacity building support will be provided to banks and NBFIs receiving financing under the facility and in need of support, as well as selected others, including: / (a) technical support tp PFIs in developing strategy and market segmentation; / (b) financial services product development; / (c) technical support in development of business sales & delivery channels; / (d) support in development of credit risk management processes and tools including scoring; / (e) IT and MIS. / 43. In addition to working with individual PFIs, this work will support specific SME sub sector focus where there is a need e.g. women owned SMEs, sustainable finance SMEs and SME agri-finance. This includes the development and dissemination of knowledge management tools and benchmarks on best practices through publications, training workshops and conferences. It may further include the strengthening of related environmental and social performance risk management systems of the PFIs. / 44. Support for the development of credit reporting infrastructure will be based on country specific needs. This would entail one or more of the following activities: / (a) Conducting market assessments/feasibility studies and developing a roadmap for developing the credit reporting system, / Supporting the development of the legal and regulatory framework (drafting / contributing to drafting of laws and regulations), / building capacity for local stakeholders through extensive outreach and awareness, in-depth advice and training, / supporting stakeholders in procuring the right technical partner, and providing unbiased support during the project implementation phase, / establishing baselines and indicators for monitoring impact of projects and training clients on monitoring the impact going forward, and / promoting the development of financial literacy aimed at increasing stakeholder knowledge of the benefits of maintaining a good credit history. / 45. Support for the development of secured transactions and collateral registry infrastructure will also be based on country specific needs. This would entail undertaking a number of activities such as: / (a) conducting market diagnostics to assess needs and demand in specific priority countries and develop a roadmap for implementing reforms in movable collateral systems; / (b) supporting the development of the legal and regulatory framework (drafting / contributing to drafting of laws and regulations) for movable collateral lending; / (c) developing or supporting the development of modern electronic collateral registries; / building capacity for local stakeholders (both public and private) through extensive outreach and awareness, in-depth advice and training; and / (d) establishing baselines and indicators for monitoring impact of projects and training clients on monitoring the impact going forward. / Output 3: / 46. We believe many of the advances in financial inclusion will be eventually be driven by new technologies, and the programme will aim to accelerate this process and fashion it for the benefit of SMEs in particular and poor people in general. There are at least three areas where support for use of technology under this Initiative can help achieve a stronger impact; / (a) Entrepreneurial Finance Lab. Use of technology in credit scoring and risk measurement mechanisms may help unlock scalable bank lending to SMEs, by lowering the cost, time and information opacity related to credit decisions. In addition to traditional multivariate credit scoring methodology, the programme will identify opportunities to promote new analytical technologies aimed specifically at the SME sector. The psychometric credit scoring tool by the Entrepreneurial Finance Lab (a G-20 SME Finance Challenge winner) is an example of such a proposal that we intend to fund through this facility to implement the scoring tool in new banks in identified markets. / (b) Peace Dividend Trust. Technology can also be used to provide web-based tools for local vendors to access new markets domestically and abroad and to gain exposure to international buyers. This is a large untapped market for SMEs. Peace Dividend Trust’s 3PF tool is an example where local SMEs in post-conflict economies can gain exposure to bid on large international contracts. The tool translates and distributes large tenders to local vendors and trains SMEs on the bidding process. The grant funds they will receive as winners of the SME Finance Challenge are expected to support the establishment of a 3PF fund which would guarantee credit lines for their SME clients provided by local banks. / (c) BIDweb. Technology-driven approaches such as internet platforms can allow SMEs to gain excessive exposure with formal and informal investors and help mobilize SME investments in a scalable manner. BIDweb, also a G-20 SME Finance Challenge winner, claims to have the current largest SME platform in the world to bring together entrepreneurs, investors and mentors. With the use of grant funds, the company plans to promote and bring its online platform to Government entrepreneurship agencies and incubators to achieve more depth and scale. / (d) G-20 Global SME Finance Forum: DFID will provide a total of $1 million or £670,000 to support the development and operations of the G-20 Global SME Finance Forum over 3 years, which will be hosted by IFC. The Forum will be a virtual platform for knowledge sharing to further identify and promote best practices across countries and institutions and establish baselines / 47. At mid-term review of the Programme, requests may be made to allow for the transfer of up to 20% transfer of allocations between the components based on need, subject to consultation with DFID and other donors. / Fit with UK strategic priorities / 48. The proposed Initiative represents a key deliverable of DFID’s Business Plan for 2011-15. (See paragraph 3-5). / 49. SME financing and development is a key objective of several DFID Country Office Operational Plans. This Initiative can help DFID country programmes in identified markets leverage funding from IFIs and DFIs, and leverage technical expertise of IFC which has a well-established track record in SME finance interventions. Initial consultations indicate good support for the programme and its objectives from several DFID Country Offices and other relevant parts of DFID such as Policy and Research Division, Conflict Humanitarian and Security Department, and Climate and Environment Department. DFID programmes in Uganda, Nigeria, Zambia, Sudan, Rwanda, Kenya, Southern Africa, Mozambique, DRC, Ghana, Pakistan, India, Nepal, and Bangladesh have confirmed the proposed Initiative can support the visions and objectives of their Operational Plans, and some country programme (Uganda, Nigeria, Mozambique, Zambia, and South Sudan) have expressed interest in partnership, including possible co-funding. We will continue to explore collaboration with these country programmes in order to maximize impact and value for money across DFID. / Argument for DFID intervention / 50. DFID has a good track record of financial sector development programme, including SME financing and development at the central as well as country level. SME finance has attracted attention from a range of bilateral and multilateral organisations over the years. However, much of Africa, fragile states and conflict affected countries, and large parts of south Asia are much less well covered than east Asia and eastern Europe. Moreover, traditional methods of addressing the problems such as underwriting lines of credit have not helped solve the problem sustainably, not the least because credit lines alone fail to address the broader enabling environment issues and capacity of local lending banks. Very often, banks stop or reduce lending to the SME target segment when concessional funding lines dry up. We are therefore, proposing a combination of innovative approaches within this programme. These include going beyond credit lines, combining risk sharing instruments with advisory services to commercial banks to help them develop better instruments and approaches for lending to SMEs; providing financing to internet and technology based solutions which can enable commercial banks to scale up dramatically (e.g. using psychometric models for assessing the risk profile of entrepreneurs) and providing financing for market infrastructure such as credit bureaus and asset registries. Our strong track record in supporting financial inclusion programmes is expected to magnify our effect in helping the IFC mobilise other donors with DFID acting as cornerstone investor. / 51. We believe DFID’s experience in and approach of working with the private sector and our influence in the G20 Group can help deliver a step change in addressing the SME financing gap. / Consequences of DFID not intervening : / 52. There are a number of implications if DFID does not intervene. Without the risk capital provided in the first instance by DFID, the risks would be too great for banks to underwrite, and for DFIs to get involved. This could mean that; / The Initiative could be delayed and deployed at significantly smaller scale, missing an opportunity to respond, especially in the event of deteriorating global macro-economic conditions, which is likely to disproportionately impact investment in poorer countries. / DFIs could have far less risk appetite to move into and/or expand investments in high risk and fragile countries, missing an opportunity to respond to the needs of small businesses in frontier markets such as Sierra Leone, Mozambique, DRC, South Sudan, and Malawi, and of women headed businesses. / Development of market-enabling financial sector infrastructure will continue to be slow and neglected, constraining involvement of commercial banks and non-banking financial institutions in SME financing in the poorer countries of Africa and high risk environments of the conflict-affected countries. / Summarise relevant evidence underpinning the intervention: / 53. There is clear evidence that small firms are good at creating jobs, and represent a potential tool for fighting poverty in the context of developing countries. A 2011 World Bank paper[14] based on cross-country database concludes that small firms (in particular, firms with less than 100 employees) and mature small firms (small firms older than 10 years) have the largest share in job creation. Moreover small firms, in particular those less than 10 years old have higher job creation rate than large firms. The paper does highlight risk of potential adverse consequences on productivity and growth, especially if the focus is on smaller SMEs. However, there is no evidence on what is an optimal distribution of firms by size for an economy toassess any adverse growth effect. SMEs contribute on average nearly 40% and 60% to formal sector employment in LICs and MICs respectively, and contribute 16% and 39% respectively to their GDPs[15]. A detailed record of evidence is provided in the subsequent section. Evidence on the current risk appetite of DFIs and their lending strategies and willingness to target frontier markets is contained in their strategies and is well known to us through our shareholding positions. The DFIs have been clear in developing this strategy on their return expectations and the pricing implications without DFID involvement. Evidence on the leverage effect of the risk capital on actual SME lending is based in part on IFC’s current portfolio analysis and experience although there is a limit to the evidence base for lending into some of the riskier markets and the monitoring and evaluation work will track this. / SMEs / 200,000 / - / 250,000 / unserved / or under / - / served / SMEs / reached / over 7 / years / BANKS / 35-40 / Global, / Regional / & / Local / Banks and / NBFIs in / the SME / business / DFID Funding: / Global SME Finance Initiative / ~£1.6 billion* / funding to PFIs / through: / • / Direct Funding / • / Credit / Enhancement / • / Risk Sharing / Facilities / Capacity / Building for / Banks / & / NBFIs / Up to / £6 billion / additional / lending to / SMEs in / 15 DFID Priority / Countries / Donors / Supports / capacity of banks to lend and manage SME risk, and / strengthens SMEs’ ability to monetize assets / IFI/DFIs / ) / Mezzanine Funds from DFIs / (£325 million) / DFID grant funds / (£38 million) / Technical Assistance Pool (£29.8 Million) / (i) Capacity building of PFIs / (ii) Financial infrastructure / (ii) Technology-based solutions / Risk Capital Component
B. Impact and Outcome / 54. The expected impact of the SME Finance Initiative is to scale up SME financing significantly and on a sustainable basis in identified countries, especially poorer and conflict affected countries, and also to expand access to financing to women headed enterprises. This is expected to contribute to the development of the overall private sector, spur job creation and economic growth which in turn will help improves lives of the poor. / 55. The three components together are estimated in the middle case scenario (See the Appraisal Case) to benefit some 236,879 SMEs receiving additional financing of about £6.3 billion from about 35 PFIs. Breakdown of this projected high level impact from the programmes attributable to DFID investments are as follows; / Table 1: Breakdown of estimated combined results from two components / Components No. of SMEs Additional financing to SMEs (£ million) / Risk Capital Component / (Investment Services) 71,401 1,562 / Advisory Services: Capacity building of the PFIs 110,814 3,597 / Advisory Services: Financial Infrastructure 54,664 1,196 / Total 236,879 6,355 / 56. It is anticipated that benefits from the programme would be back loaded over the programme duration, especially in some of the frontier markets where IFC does not have strong presence or an existing network of commercial banks and non-banking financial institutions to consolidate on. The economies of scale and productivity gains inherent in the capacity building through technical support require a degree of saturation before outcomes are fully realised. Moreover, the facilities under development need to pass a ‘tipping point’ in their ability to accelerate benefits. This should be carefully considered at the mid-term review in year three. / Evidence to demonstrate Impact and Outcome are achievable. / Evidence linking risk capital and TA to expanded SME financing / 57. We do not have information on the liquidity position of individual partner financial institutions at this stage. The Institute of International Finance's Emerging Markets Bank Lending Conditions Survey in September 2011 reported that banks in Africa and Asia are experiencing a significant tightening of access to external funding in the aftermath of the economic down turn in Europe. While the domestic funding conditions, especially for top tier banks with access to large local deposits in those markets remains broadly unchanged so far , it is expected that mid-tier banks and banks and non-banking financial institutions in the frontier markets are facing liquidity constraints. Given that the global economic conditions are still in a flux, this position is likely to change over the short to medium term and IFC will have to track the developments and tailor interventions from the Initiative accordingly. / 58. Risk sharing products are a critical tool for expanding access to finance in markets where (1) banks are moving into new markets/conditions where the risks are not totally understood and (2) banks are sufficiently liquid and therefore do not require credit lines. Not all banks will require risk-sharing facilities, but for a certain segment risk-sharing can provide the critical catalyst to support a bank’s move into a new market. Experience from IFC’s programmes indicate that technical assistance/advisory services to banks without investment/risk sharing are much less likely to have the desired impact on the target market; the two pieces are highly complementary[16]. / 59. A review[17] of IFC’s 15 years of experience with risk-sharing facilities in sustainable energy demonstrated that prior to receiving the risk sharing facility, the partner banks were unwilling to put significant levels of their own funding into a new segment such as sustainable energy. However, with risk-sharing arrangements, participating banks’ lending to sustainable energy projects grew by 21% -129% per annum, well beyond what—if anything—had been done in previous years. The same review found, that as risk-sharing model matured and banks became more comfortable with the asset class, the amount of coverage required by the risk-sharing facility declined. Consequently, the leverage on each dollar of concessional lending has increased dramatically from $0.8 to $30 in the IFC’s most recent facilities. / 60. The capacity of the financial institutions, primarily banks, in recognizing and leveraging the opportunity of downscaling to the SME sector is often a challenge. They also need to develop the capacity to predict risk without completely reliable financial information, by using tools such as credit scoring to screen clients more effectively. Finally banks need to adapt their IT and MIS to improve their ability to manage their profitability and risk (IFC SME Banking Knowledge Guide 2010). / 61. The evidence shows that combining finance with advisory services with investment yields better results than stand-alone financing of financial intermediaries. The IFC’s Independent Evaluation Group (IEG) evaluated the operating results and performance of a subgroup of 36 SME financial institutions (FI) and concluded that the SME FIs that received advisory services from IFC had a development outcome success rate of 76%, compared with only 55% for SME FIs that did not receive any advisory services[18]. Such advisory services include staff training, establishing good lending practices and loan portfolio risk management systems. Based on the IEG study, advisory services are considered one of six major factors driving development outcome success rate of IFC’s SME financing projects. DFIs are uniquely positioned to go beyond lending and add significant value by developing projects that combine investment and advisory components. The EU + EBRD SME Finance Facility is a successful example of a regional facility in which EBRD provides loans with comprehensive technical assistance programme and grants funded by the EU to develop the capacity of SME FIs. Results from the programme include over 100,000 loans and over 7,300 FI staff trained with Technical Assistance (TA) funds across all areas of their business. / 62. We recognise the risk of potential conflict of interest in combining lending with technical assistance/advisory services. This has been addressed in greater detail in the Management and Governance sections. / Evidence linking financial infrastructure and SME financing: / 63. Collateral and credit information are critical elements of a functioning credit system. The lack of these elements deepens information asymmetry and increases the risk premium for borrowers who want to access credit. Credit is constrained in markets with information asymmetry (Stiglitz and Weiss, 1981). Moral hazard and adverse selection will be reduced if collateral frameworks and credit information systems are improved, creating a more robust financial sector. Empirical research shows that credit information sharing is critical to lower the financing constraints for small firms, as it mitigates the effects of information asymmetries in the market. A study by Love and Mylenko (2004)[19] shows that the percent of firms reporting financing constraints declined from 49% in countries without credit information sharing systems to 27% in those countries that did have such systems. The same study showed that the probability of a small firm obtaining a bank loan increased from 28% in countries without credit bureaus to 40% in those that did have credit bureaus. A well functioning credit reporting infrastructure helps SME lenders assess SMEs’ risk and creditworthiness profile, make informed credit granting decisions, and monitor and manage portfolio risk. In addition, credit bureaus can act as a disciplining mechanism for SME borrowers since these borrowers are less inclined to default if they are aware that this default will affect their future applications for credit. / 64. Effective secured transactions laws and collateral registries are crucial components of a healthy financial sector and business climate. In their absence; entrepreneurs are unable to leverage current assets into capital for investment. Modern secured transactions systems allow the use of movable assets (both tangible and intangible) such as equipment, inventory, accounts receivable, cash flows, livestock, crops and others as collateral in exchange for loans. Economic analysis also suggests that small and medium-sized businesses in countries that have stronger secured transactions laws and registries have greater access to credit, better ratings of financial system stability, lower rates of non-performing loans (Djankov, McLiesh and Shleifer, 2005), and a lower cost of credit (Chaves, de la Pena, Fleisig, 2004). In emerging market countries, for lack of appropriate secured lending regulations and collateral registries, the assets owned by most firms are a poor match for the assets that lenders accept as collateral. According to the World Bank Enterprise Surveys, in these countries, nearly 80% of firms’ assets are inventory, machinery and accounts receivable, while 78% of the assets taken by financial institutions as collateral are real estate (land or buildings). This “collateral gap” can be significantly reduced by strengthening movable collateral regimes. / Evidence on G-20 SME Finance Challenge Winners / 65. Background: In 2010 the G20 launched a challenge to invite scalable solutions for SME financing. This G20 SME Finance Challenge was managed by a technical review panel with a strong focus on overall impact and innovation and resulted in 14 winning proposals being identified for funding through the G20 process. We have reviewed all 14 proposals and ranked the following winning proposals on the basis of the proposals’ potential to meet two key objectives – (a) using the power of innovation and technology to scale up SME financing; and (b) supporting a proposal which will specifically address SME financing in conflict affected countries. / i) The proposal from the Entrepreneurial Finance Lab, a private institution, seeks to address the problem banks face in identifying potential SME borrowers that do not have collateral or a credit history. The tool has been evaluated with good results across seven countries and eight languages in Africa and Latin America. Standard Bank is implementing a pilot across five African countries. / ii) The second G-20 Finance Challenge Winner we propose to fund under this programme can be catalytic for SME financing in high risk environments. Historically, only 30% of international aid is spent in recipient countries, significantly lowering the impact of this spending on local economies. SMEs seeking to bid for donor procurement contracts in post-conflict/post-disaster economies are at a disadvantage due to their limited knowledge about large bidding processes and lack of access to finance (which inhibits them from delivering the goods or services demanded by donor procurement contracts). Peace Dividend Trust projects have successfully facilitated $514m of new donor procurement spending in Afghanistan and $23m in Timor Leste – 1% of GDP is both cases. / iii) BiD Network Foundation, a non-profit NGO, has created an SME platform to link entrepreneurs, investors, and business coaches. Its proposal to scale up this model is one of the 14 winners of the G-20 SME Finance Challenge. It aims to bring together emerging market entrepreneurs, investors and coaches by taking advantage of the network effects of web-based platforms. The platform (website) innovates by using a multi-country approach to provide business coaching to entrepreneurs to increase their capacity and strengthen their business models. The platform also links local angel investors with entrepreneurs. BiD Network currently has 35,000 members. The network has helped to start 300 SMEs over three years. Being web-based, the model is inherently scalable and unit costs drop as the network expands. These technology based approaches are relatively new and results from early pilots are encouraging. We are recommending a relatively small outlay to help scale up these approaches given their potential.
[5] For example, the European Union (EU) defines SMEs as firms with 10 to 250 employees, with less than Euro 50 million in turnover or less than Euro 43 million in balance sheet total. This definition explicitly distinguishes between micro-firms and SMEs.
[6] Rosenzweig, 1988
[7] Ayyagari, M., A. Demirguc-Kunt., and V. Maksimovic (March 2011), “Small vs. Young Firms across the World: Contribution to Employment, Job Creation and Growth”, World Bank.
[8] This is based on World Bank Enterprise Surveys across 124 countries between 2006 and 2009. These surveys define firms with less than 20 employees as small enterprises and those with between 20 and 100 employees as medium enterprises.
[9] 0.	2 Martinez Peria M.S. 2009. “Bank Financing to SMEs: What are Africa’s Specificities?”. PROPARCO’s Magazine Issue 1, May 2009. This paper uses newly collected data through a survey of 16 banks in 8 African countries in 2007/08 by the World Bank.
[10] Beck. T., A. Demirguc-Kunt., and Martinez Peria.M.S. 2008.”Bank Financing for SMEs Around the World: Drivers, Obstacles, Business Models and Lending Practices”. World Bank Policy Research Working Paper 2009.
[11] Banerjee, Abhijit and Esther Duflo (Revised 2008); “Do Firms Want to Borrow More? Testing Credit Constraints Using a Directed Lending Programme”. Department of Economics, Massachusetts Institute of Technology (MIT) Working Paper Series.
[12] Entrepreneurship in Post-Conflict Transition The Role of Informality and Access to Finance Asli Demirgüc–Kunt; Leora F. Klapper; Georgios A. Panos World Bank Working Policy Paper May 2009
[13] IFC-McKinsey Report October 2010
[14] Ayyagari, M., A. Demirguc-Kunt., and V. Maksimovic (March 2011), “Small vs. Young Firms across the World: Contribution to Employment, Job Creation and Growth”, World Bank.
[15] Data on SME – formal and informal – contribution to GDP and employment is scarce and sketchy. The data here is sourced from Ayagiri, M., T. Beck, and A. Demirguc-Kunt, 2003 and revised in 2007. “Small and Medium Enterprises Across the Globe: a new database” Policy Research Working Paper Series 3127 World Bank and Small Business Economics 29, 415-434 .
[16] IFC. Independent Evaluation Group. 2008. “Financing Micro, Small and Medium Enterprises”.
[17] Independent Evaluation of IFC’s 14 Sustainable Energy Finance Risk Mitigation Facilities being finalised for publication
[18] IFC. Independent Evaluation Group. 2008. “Financing Micro, Small and Medium Enterprises”. Washington DC.
[19] Love, I. and Nataliya Mylenko, (2004), “Credit reporting and financing constraints”, The World Bank, Policy Research Working Paper Series: 3142.

Appraisal Case
2.A. What are the feasible options that address the need set out in the strategic case? / 66. During the design phase we put significant amount of thinking into whether or not we should focus our interventions on debt-led financing or equity led financing or a combination of the two. We made a choice to go with debt-led financing for SMEs. The drawback of equity led financing is its inability to deliver scale or to reach out to a significantly higher number of SMEs. For example, if all of DFID’s £75 million were to be invested in equity based financing for SMEs, we would have been able to reach some 150 SMEs, assuming an average ticket size investment of £0.5 million. It is also difficult to identify evidence of models that make equity finance available at scale to SMEs on a cost-effective and sustainable basis. We believe combining equity and debt based financing approaches across the 15 identified DFID priority countries would have made the programme design unduly complex, as this could not have been delivered through one single delivery mechanism. Although we considered the option of equity led financing for SMEs, we rejected this option as it can not deliver at scale and therefore, we have not done a cost benefit analysis of this option. / 67. Within the debt-financing model, the identification of feasible programme delivery options is based on a couple of considerations; (i) strategic considerations of addressing systemic constraints, leveraging private sector resources for delivering results at significant scale on a commercially sustainable basis and; (ii) management considerations of leveraging the implementing partners’ technical and management bandwidth necessary for delivering a global programme of this nature efficiently and in a cost effective manner. We believed that collaboration with banks and non-banking financial institutions had to be common to whichever delivery option we opted for, because this was key to unblocking systemic constraints as well as ensuring sustainability and replicability. / 68. Based on these considerations, the appraisal assessed the following three Options; / Funding the IFC Initiative to use an integrated and sustainable funding approach that supports the development of markets through commercial risk-sharing schemes in order to leverage public and private capital, build capacity of financial institutions, and strengthen the enabling environment. Grant funds are used sparingly. / Use fully grant-funded approaches to support SME financing through direct support to commercial banks and financial institutions and for the development of financial market infrastructure / Do nothing / 69. Each of these options were assessed against the following three Critical Success Criteria which need to be fulfilled in order for the impact and outcomes documented in the Strategic Case to be achieved. The three conditions were weighted on a scale of 1-5 depending on their relative importance to the success of delivery of the anticipated outcome and impact. 1 is least important and 5 is most important based on the relative importance of each criterion to the success of the intervention. / Table 2: Critical Success Criteria / CSC Description Weighting (1-5) / 1 At least 35 commercial banks and non-banking financial institutions (80% banks / 20% NBFIs) partner with the Initiative to ensure sufficient geographical outreach and scale of financing for SMEs on a commercially sustainable basis. 4 / 2 Markets are developed and made to work more efficiently to finance SMEs on a scaled and sustainable basis by addressing some critical constraints through supporting the development and improvement of financial market infrastructure, building the capacity of financial institutions and providing risk capital to banks to support SME financing in 12-15 countries. 4 / 3 At least 200,000 SMEs accessing finance. 5 / 2.B. Assessing the strength of the evidence base for each of the feasible option / Table 3: strength of evidence / Option Evidence rating / 1. Use an integrated and sustainable funding approach that supports the development of markets through commercial risk-sharing schemes in order to leverage public and private capital, build capacity of financial institutions, and strengthen the enabling environment. Grant funds are used sparingly. Medium: As explained from paragraphs 55-61, there is reasonable evidence to support the premise that combining risk-sharing with advisory services activities yields better results than stand-alone financing of financial intermediaries. Moreover, the UK’s recent Multilateral Aid Review indicated that IFC offers very good value for money for the UK’s aid budget as one of the very few private sector development agencies with significant advisory and investment capacity. Its comparative advantage is the breadth and quality of its technical knowledge, expertise and global reach. Through its size and reach, IFC can have a transformational effect that individual financial institutions can not match. / 2. Use fully grant-funded approaches to support SME financing through direct support to commercial banks and financial institutions and for the development of financial market infrastructure Medium: Interventions operated by DFID and some other donors at the country level offer some useful guidance on risk-sharing, especially through credit guarantee schemes and line of credit. But such intervention tend to have high management cost in the range of 10-12% (e.g. DFID funded SME finance and development programmes in India and Pakistan) / 3. Do nothing Medium to weak: DFIs will continue to behave in the same risk-averse way they have done in the past. The key weakness in this Option is that we do not know ex-ante as to who will be selected as the partner financial institutions for this Initiative, and therefore we do not have information about their SME outreach nor potential to scale up SME financing. However, we do have information on average SME client outreach of banks in each of our 15 priority countries, and the average growth of lending by banks to the private sector in those countries.
2. C. Assessing the potential impact (positive and negative) associated with climate change and environment for each option: / 70. Fundamentally, Options 1 and 2 differ in the approach to financing development solutions and choice of intermediary organisations. This is not expected to alter the type of activities supported on the ground and thus the type of impact they may have on environment/climate change or vice versa, although the scale of activities varies substantially between options 1 and 2. / 71. Under Option 1, from an environmental impact point of view, standard environmental guidance and standards will be applicable to interventions under this Initiative as SME financing and development is a core business for IFC. DFID’s Multilateral Aid Review scored IFC’s performance in meeting UK objectives on climate change and environmental sustainability as “satisfactory”. It noted that IFC’s contribution is quickly growing in prominence, but from a relatively low base compared to peers such as the EBRD. It noted that a range of new initiatives should help to scale-up IFC’s ambition, including IFC’s proposed 2013 Development Goal to reach 20 to 25% of IFC’s portfolio in climate-friendly investments. IFC is increasing its efforts in climate change and environmental sustainability, through its new Climate Business Solutions Department, its Asset Management Company’s potential involvement in the proposed Climate Public-Private Partnership (CP3). IFC have also launched a post-2012 carbon facility aimed at mitigating the uncertainties associated with the Clean Development Mechanism. / 72. We believe that setting very strong climate focussed targets will set this Initiative directly in competition with other facilities that IFC has set up to pursue the climate change objectives. We would link the climate change objectives for this Initiative with our corporate strategy with IFC. IFC’s Development Goals for 2013 intends that 20 to 25% of IFC’s portfolio should be in climate positive investments. In line with this goal, it is intended that at 20% of the PFIs under this Initiative will be provided with technical support for strengthening capacity to identify, screen and support SMEs that either contribute to low carbon and climate resilient outcomes or have a neutral impact / 73. Whereas Option 2 seeks to expand access to finance for SMEs through a myriad of financial intermediaries, and it would be significantly more complicated, costly and uncertain to impose and supervise environmental and social standards on these financial intermediaries and the SMEs they fund. / 74. Option 3 : business as usual. / Table 4: Quality of Evidence and Impact on Climate Change and the Environment / Option Evidence rating Climate change and environment category (A, B, C, D) / 1 Medium D / 2 Weak C / 3 Medium C / A = high potential risk/opportunity; B = medium potential risk/opportunity; C = low/no risk/opportunity; D = core contribution to a multilateral organization
2.D. Appraisal of options / Economic Appraisal: / 74. There are two parts to our economic appraisal of this initiative: (i) how is our subsidy being used to drive a change in the behaviour of DFIs in lending to SMEs; (ii) an analysis of whether the benefits of our interventions outweigh the costs and if so, to what extent. On the first part, based on our knowledge and experience, we know that DFIs are not lending enough to SMEs especially in the frontier markets and without our support to the risk sharing component the DFIs are not likely to participate in this initiative or at a price that would constrain its impact. Through our risk sharing component, we will draw the DFIs in to lend to these tougher market segments and do so at a price, that the IFC estimates will be up to 5% lower than what they would have done otherwise, if they had provided any lending at all. The structure of the risk sharing component with the first loss and mezzanine funding will in turn help lower the price at which the participating PFIs lend to their own SME clients. / 75. The following section addresses the second part of our appraisal and provides an analysis of the high level impact goals of the Initiative through the use of macro data assumptions, such as jobs, wages and revenues expected to be generated by SMEs under the Facility. The assumptions are then used to provide various benefit cost ratio (BCR) analyses for each of the components of the Facility. / 76. DFID will provide IFC with approximately £75 million to implement an SME Finance Initiative over 7 years with the possibility to top up the programme by a further £25m and extend it to 10 years. The three feasible options set out in paragraph 66 have been evaluated against the critical success criteria highlighted in table 2. The logic of interventions and explanations of how the Inputs under the three different components of the Initiative will be converted in to Outputs, Outcome and Impact are reflected in the Logical Framework and also presented in some detail in the Theory of Change in Annex 3. / 77. Commercial banks and non-banking financial institutions in the 15 target countries will continue expanding their SME loans even in the absence of our proposed interventions. Our proposed interventions will be meaningful only if the interventions help expand the SME outreach and achieve a substantially larger volume of SME financing than under the Do Nothing Option. We have assumed that in the absence of our interventions, SME financing will grow at an average growth rate equal to the overall private sector growth in the region in the last ten years. Whilst the risk capital component is critical in driving the risk appetite of the PFIs getting concessional funding under the Initiative, it should be noted that only 15 of the 34 PFIs will recive this funding. The estimated results are therefore largely driven the technical support component, the capacity building support available to all 34 PFIs and the support for development financial market infrastructure. An estimated £4.8 billion of the total £6.4 billion SME loan outreach that IFC expects to mobilize through DFID’s support to the Initiative are projected come from the technical support. / 78. To keep the cost-benefit analysis in the three Options comparable, it is assumed the Initiative will cover 35 PFIs. The 35 PFIs will be selected over the first 2-3 years of the programme implementation, and are therefore not known at this stage. Hence, we are not in a position to establish the baseline for the PFIs at this stage. It has been assumed that each of the 35 financial institutions start with a baseline SME portfolio of 6,363[20] SMEs. The average annual weighted growth of the SME portfolio has been estimated at 2.66 %, which is a weighted average of the credit to the private sector growth in South Asia (5.3%), and Sub-Saharan Africa, (1.3%), weighted by the size of the SME formal sector in each region. We have then estimated how their SME lending operations will expand in the event there is no intervention. Projecting the portfolio gives us an estimated number of SMEs reached of 53,200 in year nine , and 113,500 number of jobs created under the Do Nothing Scenario. / 79. Table 5 gives the projections of the number of SMEs, volume of financing and the number jobs, and associated present value of benefits and costs estimated in the cost-benefit model under the three different Options. The estimated benefits from and cost of the interventions are driven, in particular by the number of banks and non-banking financial institutions covered, and outreach to the number of SMEs which drives the volume of financing. Therefore, additionally, for option 1, the estimated benefits have been analyzed in three different scenarios with the aim to evaluate the sensitivity of the benefit-cost ratio (BCR) when changing key variables such as the number of financial institutions in the programme or the number of SMEs reached. Option 1 is also evaluated by measuring how the additional financing for SMEs is treated in the model: either as a cost or as a benefit (See Sensitivity Analysis). A relatively high discount rate of 10% is used in the cost benefit analysis in this appraisal[21]. / Table 5: Comparison of NPV and BCR (all options) / Option 1 Option 2 Option 3 / Scenario Case Low Middle High / Present Value of Benefits (£ Million) 227 489 723 111 136 / Present Value of Costs (£ Million) 60 57 55 58 89 / Net Present Value (£ Million) 167 432 668 53 47 / Benefit to Cost Ratio 3.8 8.6 13 1.9 1.5 / SMEs Reached (‘000) 144 291 325 115.5 53.2 / Volume of Financing (£ million) £3,856 £6,406 £8,529 £1,636 £693 / Jobs Created (‘000) 632.0 1,050 1,397 268.1 113.5 / SMEs reached as % of total number of SMEs with credit in the 15 priority countries 20% 34% 51% 9% 8% / SMEs reached as % of un-served and under-served SMEs in the 15 countries 6% 10% 14% 3% 2% / Notes:1) SMEs reached with the program compared to overall number of SMEs with credit in SSA and SA - 694k – IFC-Mckinsey study (2010). / 2) SMEs reached with the program compared to overall number of unserved SMEs in SSA and SA - 2,461k / IFC-Mckinsey study (2010). / 80. The analysis suggests that there is a good economic case to support this proposed programme with IFC as even in the low case scenario of Option 1 a BCR of 3.8 is obtained, which is higher than the BCR obtained in the other two options. Projections of the number of SMEs reached, the volume of financing made available to SMEs, and the jobs created increases from 53,243 SMEs, £693 million and 113,500 jobs under the Do Nothing Scenario to 115,534 SMEs, £1,636 million financing and 268,000 jobs under Option 2, and to 291,053 SMEs, £6,406 million of loans, and 1.05 million jobs under Option 1 of supporting the IFC Initiative. / 81. The estimates of cost and benefits are based on the following assumptions; / (i) Based on IFC’s very advanced negotiations with DFIs, the IFC expects that DFID concessional funding of £38 will be leveraged to mobilize approximately £325 million of mezzanine funding from the first round of funders, such as IFC, KfW, EIB, OPIC and DFID. This fund will be deployed through the PFIs on the bais of a 50:50 risk sharing, thus raising an additional £325 million from the PFIs. We assume that 75% of the total fund size of £688 million (£325+£325+£38) are deployed by the PFIs in SME loans. We assume average tenure of 2.3 years which means the funds can be recycled more than three times to generate additional loans £1.58 billion over the seven year period of the programme. / (ii) It is assumed that banks that receive capacity building support will be better equipped to disburse loans to SMEs. Using IFC Reach and Disbursement data, it was estimated that banks that had an IFC advisory component in addition to the investment component, had 40% higher lending in terms of outstanding loans to SMEs compared to banks with an IFC investment only component. The model then assumes in the middle case, for example, that there is a 40% increase in SMEs reached due to the advisory component. It is also implicitly assumed banks’ lending to SMEs is constrained more by high transaction costs and risks than liquidity, and that banks will have adequate liquidity to expand lending to SMEs, once they are able to understand and manage the risk associated with SME lending better. / (iii) (iii) According to "Credit Reporting and Financing Constraints" by Inessa Love and Nataliya Mylenko, there is evidence showing that credit reporting can enhance the speed and approval of loans in the range of 20-40%. As a result, the model also assumes that there is an additional disbursement of loans to the SME sector of 20 to 40% (between the low, medium and high scenarios) when there is financial infrastructure. / (iv) Therefore, based on (ii) and (iii), in addition to the DFID concessional funding effect in (i) above which leverages DFI+ commercial funds and helps PFIs on-lend $1.58 billion to SMEs), the model also estimates separate impacts for the capacity building support and TA for financial market infrastructure development. These three components together help achieve the total results (middle case scenario) of 232, 479 SMEs receiving financing and about £6.4 billion in loans for SMEs from the 35 PFIs. / (v) According to IFC’s cross-country SME Benchmarking survey of 34 banks, the profitability from surveyed banks’ SME portfolio was 4.8%, which is applied to the SME loan portfolio estimated to be reached with the participating banks. The SME Benchmarking survey also indicated the average financial and operating costs, and loan loss provision rates for the 34 SME Bank surveyed. These rates were incorporated in the model to derive the profitability ratio noted above for the SME portfolio. / (vi) SMEs that receive a loan are assumed to generate incremental revenues of 80%[22] of the loan amount per year. Likewise, SMEs receiving a loan are assumed to generate an incremental profit (net income after tax) of 30% of the value of the loan per year (before deducting interest)[23]. This means that for every pound received from the financial intermediary, SMEs are assumed to generate £0.8 in revenues, and £0.3 in profits before interest payments. Because we have also assumed that the interest rates are of 22% per annum (IFC SME Banking Benchmarking Survey), the net profit for the SME is assumed to be 8% or £0.08 for every £1 received. / (vii) For each £4,875 of incremental SME revenue, one additional job is assumed to be created[24] To calculate the new jobs created as a result of the financial services provided to SMEs, we have assumed that the loans to SMEs will enable them to increase their working capital or their productive assets, therefore helping increase revenues. SME revenues would increase by 80% of the total amount of loans received. Using the regional ratios of revenue/jobs we assumed that for each additional £ 4,875 of revenue, 1 job would be created. Assuming that loans are renewed after being paid back by SMEs –which is a norm in MSME finance-, the effect in job creation is amplified over time (see graph). The number of jobs that would be created in option 1 would be 1.041 million. / (viii) The average monthly wage that the new employees incorporated to the formal sector would receive is estimated at £53.87[25]. / 82. For our estimations of benefits, we have assumed the middle case scenario, in which IFC will have fully deployed the risk capital component by year three and significantly advanced capacity building support in 30 PFIs by year four. Nearly half of the estimated results (see paragraph 14) by end of March 2015. By year six, the minimum target of 200,000 SMEs would be reached and surpassed, and assuming an average loan size of £21,875 for institutions that receive concessional funding and £35,000 for institutions without concessional funding[26], £5.7 billion will have been disbursed to SMEs by year six. / Monetization of Benefits Under the different Options / 83. We have estimated costs and benefits attributable to DFID’s investments only. Further, we have estimated benefits in three possible scenarios by changing key variables determining the scale of the Initiative’s Impact such as number of PFIs and SMEs reached: (i) Low Case, (ii) Medium Case and High Case. In the middle case scenario we have estimate that the financial institutions in the program will disburse approximately 237,000 SME loans, equivalent to a portfolio of £6.36 billion. We measure the benefits by capturing the annual profitability made through the SME portfolio (based on assumptions v). / 84. We have estimated monetary value for mainly two benefits: (a) estimating the net income produced by SMEs as highlighted in point (vi) above and (b) the wages received by new workers based on wages in (vii) above. / Estimation of Costs / 85. The costs considered in the model include : (i) the funds that will be invested by DFID to implement this programme with IFC; and (ii) the costs of client contributions for the capacity building component. / The PFIs will need to incur higher costs as they scale up financing to SMEs such as cost of raising capital, operating costs and loan loss provisions. However, these costs are not separately treated in the model because the benefits to PFIs are estimated on a net basis after deducting these costs from revenue earned. The same process has been used in estimating profits of SMEs which is also done net of interest and operating costs. / Costs are distributed over a period of 5 years to reflect the real execution of expenditures. / We have included additional cost estimations for option 1 by changing the way additional volume of lending for SMEs mobilized is treated in the model. In the base (middle) case, the overall amount of investments has been considered as a cost (option 1a). However, one could also argue that the funding given to a financial institution allows it to increase its lending operations and profitability, so the volume of lending mobilized could be treated as a benefit. When considering the volume of lending as a benefit (option 1b), the benefit-cost ratio jumps from 7.7 to 17.8. / Option Option 1 a / (Treating new loans for SMEs as cost) Option 1 b / (Treating new loans for SMEs as benefit) / Present Value of Benefits (£ million) 434 464 / Present Value of Costs (£ million) 56 26 / NPV at 10% Discount Rate 378 438 / Benefit Cost Ratio (%) 7.7 17.8 / 86. To arrive to the overall benefits of option 1, direct benefits calculated for end-beneficiaries and financial institutions are added. The present value of benefits is £378 million, using a 10% discount rate, while the present value of costs is £56 million. The BCR obtained is 6.7. The incremental number of SMEs reached is of 237,000 and the number of jobs created of 1.04 million. The number of SMEs reached under this option is equivalent to 10% of unserved and underserved SMEs in the 15 identified priority countries and to 34% of SMEs with credit in those countries[27]. / 87. It is important to mention that we are only considering benefits related to SME lending products for both financial institutions and end-beneficiaries (borrowers). SME banking involves implementing different kinds of financial products within financial institutions (savings, insurance, etc.) to better serve SMEs and increase the value of clients. According to best practices in SME banking, lending to SME represents only 40-50% of the product income[28]. Consequently, we are underestimating the benefits of the SME product for financial institutions as well as for the borrowers, who also benefit from having different set of products that fully meets their needs. / 3. Analysis of Benefits for Option 2: Direct DFID support to PFIs / 86. Under Option 2 we considered DFID will directly support PFIs with both investment and advisory services. Under this option, there will not be any mezzanine tranche or investment leveraged from DFIs. The leverage ratio of DFID’s concessional funding is, as a consequence, assumed to be half of that under Option1. This is because in the absence of a mezzanine tranche, the commercial funding would have a higher risk, and therefore, the amounts raised would be lower. We assumed that in the absence of risk sharing from DFID, DFIs will have very little incentive to move into the high risk environment in the frontier markets and will make investments in less risky ventures, yielding lower developmental impact than under Option 1. / 88. Further, the program management costs under this option will be 10% of the total DFID funding[29] higher than the program management costs under Option1. Therefore, DFID will have to invest £77.7 million, to absorb the additional management costs, and so that the program delivery cost (advisory + investment) stay the same in Option 2 as in Option 1. / 89. We have retained, for the sake of comparison with Option 1, the same number of PFIs in Option 2 as in Option 1. This means that the average size of concessional funding per PFIs in Option 2 will be lower than in Option 1, because as explained above the total funding leveraged is lower under this option. Therefore, the average size of concessional funding available per PFIs is estimated to fall from £18.5 million in Option 1 to £1.9 million in Option 2. / Analysis of Costs and Benefits for Option 3: Do Nothing / 90. It is assumed that commercial banks and non-banking financial institutions continue expanding their SME loans at an average growth rate equal to the overall private sector growth in the region in the last ten years. To keep this option comparable to the other two, it is assumed there are 35 financial institutions, and we have then estimated how their SME lending operations will expand in the event there is no intervention. (See paragraph 80 above). / 91. The costs under this model are assumed to be the overall financial, operating, and loan loss reserve costs from the SME portfolio disbursed by the financial institutions. The costs used are the ones considered for the lower case in option 1, as it is reasonable to think that the financial institutions would have higher costs –but still be profitable– without the technical assistance from DFID-IFC. On the other hand, the portfolio yield from the SME portfolio is counted as a benefit. In addition, benefits are also estimated for end beneficiaries using the same assumptions as in option 1 and 2. / Graphic 1: Number of SMEs reached under each Option (thousands) / Note: the number of SMEs reached in Opt 1 and 2 includes the number / of SMEs in Opt 3 (Do nothing scenario). / 5. Sensitivity Analysis / 92. For the Low Case scenario, we have assumed that 80% of the middle case SMEs are reached with loans, a total of 32 institutions are reached with concessional funding and/or capacity building, and that there are lower effects for advisory services components in terms of SME outreach for a total incremental effect of 20% instead of 40% assumed for the middle case scenario. The effect for financial infrastructure is also assumed to be lower at 20%. As a result of the lower number of financial institutions reached under this scenario, it is estimated that an additional 136,000 SME loans will be created and roughly 581 thousand jobs are generated. Finally, the financial institution’s profitability is estimated at 1.8 % (rather than 4.8 % in the middle case) and the speed by which the project will allocate the funds is lower in this scenario. Consequently, the BCR ratio obtained is 3.3. / 93. In the High Case scenario 20% more PFIs are reached, taking the total number of PFIs reached with concessional funding and/or capacity building support to 42. Further, Component 2 is assumed to more effective, leading to 50% higher outreach (compared to outreach achieved through concessional funding alone) from capacity building support and 40% higher outreach from the development of financial infrastructure. Altogether, 355,200 SME clients are reached and 1.6 million jobs are created. The profitability made by the financial institutions through their SME portfolio is expected to be 1 % higher (at 5.8 %) than in option 1 and the speed at which funds are spent is also higher in this scenario and all funds are spent in 4 years. The resulting BCR ratio is 13.8. / 94. The factors that can increase the likelihood for the Initiative to deliver at close to the low case scenario are: (i) a global double-dip recession to occur in 2011-12, and (ii) a lower than expected mezzanine and commercial funding. On the other hand, the factors that can take the results delivered closer to the High Case Scenario are: (i) developing a balanced SME banking portfolio that combines reach with impact (large markets vs. frontier markets), (ii) ability to choose a few regional players that can help quickly channel the funding and rapidly implement the IFC’s advisory service package, (iii) adequately disseminating success stories in the region to encourage replication among other players in the market, and (iv) higher than expected funding from other donors and DFIs. / Political Appraisal: / 95. Country assessments will be conducted to ensure a comprehensive and integrated programmatic approach of the three components and their respective activities in meeting market needs. / Option 1: DFID funding will target projects in Sub-Saharan Africa, South Asia and conflict affected countries, where sustainable increases in access to finance for SMEs require strengthening of the enabling environment, including development and improvement of financial market infrastructure. However, financial infrastructure development and reform is a politically sensitive process that requires significant consensus building. Experience shows that this process is most effectively supported through the provision of unbiased technical advice. IFC is well positioned to provide neutral support to the development of financial infrastructure and related reforms in priority markets. The Initiative’s ultimate objective is to increase SME development by scaling up SME financing through public and private financial institutions providing advisory services, investments, and limited grant funds. This is considered a key driver for economic development and is aligned with political interests, unlikely to attract negative political attention. / Option 2: Under this option, grants would be directly provided by DFID for the development of financial infrastructure and to public and private FIs for SME onlending and capacity building. Political risks would vary depending how this process is managed. On the one hand, providing grants to several stakeholders results in minimal political risks, but can be ineffective and slow down the process of both financial infrastructure reform and the sustainable expansion of banks’ SME portfolios, given the large number of stakeholders with different incentives in the process, and lack of guidance to achieve a common goal. On the other hand, providing grants to one stakeholder might not suffice as it would not ensure buy-in from other key stakeholders to the process, which can lead to political tension. / Option 3: Financial infrastructure reform is a long process that requires specific technical expertise and process knowledge on the part of the various stakeholders involved. Given the wide range of stakeholders (both public and private) in the process, ownership of the process is diluted and frequently the market is unable to mobilize itself and take needed action. Inaction on the part of donors and DFIs would further delay the process of much needed financial infrastructure reform in priority markets. / 96. Further, doing nothing would lead to an unresolved SME financing gap in regions and countries where SME support is essential to create job opportunities and promote economic development. Low employment opportunities increase the political and social stability of conflict affected countries and can potentially threaten the stability in other priority countries in Africa and South Asia. / Institutional Appraisal: / 97. We have not done a new institutional appraisal of IFC, as this has been comprehensively covered in the DFID Multilateral Aid Review (MAR) of IFC. According the MAR, IFC’s contribution to the UK’s development objectives is satisfactory. IFC is the largest DFI and the only multilateral DFI with a global reach. It is one of the few private sector development agencies with significant advisory and investment capacity. The MAR, however, highlights that although IFC is the central global player in private sector development and a critical part of the international development system, IFC has not been able to maintain its leadership in some markets, including frontier markets, where other DFIs and private sector operations of regional development banks are able to play a more meaningful developmental role. IFC’s willingness to take this Initiative to a number of small and fragile economies in Africa and Asia is encouraging. / 98. We have also looked at the institutional aspects of the PFIs under the three different options and appraised which of the three options gives the best chance and incentives to PFIs to respond to the challenge of bridging the SME credit gap. / Option 1: Financial institutions in the private sector are driven by profits, and thus need to have in place commercially sustainable business models in order to survive. This option presents an integrated approach to scale up SME finance sustainably, by (i) strengthening the enabling environment through financial infrastructure reform to address barriers such as information opacity and lack of sufficient collateral, in line with standard best practices, (ii) developing the necessary capacity of FIs to better support SME finance based on proven successful models, and good operational, management and lending practices. This includes the integration of social and environmental considerations in FIs’ investment operations, and financing innovative solutions to foster SME lending (iii) providing risk mitigation to promote SME finance and SME portfolio expansion in perceived riskier sectors. (iv) Additionally, limited grant funds will support the development of technology based solutions to strengthen and expand SME finance, as identified through the G20 SME Finance Challenge. As such, this option provides the highest development effectiveness and potential for scalable and sustainable SME finance. / Option 2: Direct provision of grants for the development of financial infrastructure and directly to FIs through multiple smaller programmes tends to limit their outreach and dilute their effectiveness as a result of overdependence on government political guidelines and restrictions and/or unaligned programme targets. Sustainability is also a challenge. Most grant funded programmes tend to disappear when grant funds dry up. Experience from the field indicates that grants should be complemented by technical assistance and support. But this approach may still prove insufficient without the proper structure to catalyze and mobilize additional development and/or private sector funds, which are necessary to make a valuable impact in the SME Finance space. . / Option 3: If we let the market determine its own path to financial infrastructure reform, there is a risk that such reform would be delayed indefinitely due to the diverse group of stakeholders, including various government entities and private sector participants. There is also the risk that the market may adopt sub-optimal models or solutions to expand SME finance which do not meet its long term needs and/or overlook the needs of some stakeholders. Hence, the option of doing nothing limits the institutional development of FIs to scale up access to finance for SMEs, which in turn negatively impacts SMEs ability to grow. / Environmental & Social (E&S) Appraisal: / 99. The E&S appraisals of the three different Options considered in the Business Case are as follows; / Option 1: There is a risk that activities or businesses supported by the Initiative may have negative environmental and/or social impacts. As part of the investment component of the Initiative, IFC’s Sustainability Policy and Performance Standards, approved by IFC’s Board of Directors, will apply to all investment projects to minimize their impact on the environment and on affected communities, and ensure the clients’ compliance with IFC’s standards. IFC’s Environmental & Social Review Procedures Manual defines the approach to assess client compliance and progress with IFC’s Sustainability Policy and Performance Standards on Social and Environmental Sustainability and Environmental, Health and Safety Guidelines. The procedures and guidelines are publicly available through IFC’s website (www.ifc.org/ifcext/sustainability.nsf/Content/EnvSocStandards). / The IFC Performance Standards were developed to manage social and environmental risks and impacts of projects financed by IFC and to enhance development opportunities in private sector financing. / The following standards apply to IFC’s investments for FIs to be set at the FI level: / Social and Environmental Assessment and Management System (ESMS): to manage E&S risks associated with their lending and investments. / Labor and Working Conditions: to ensure fair treatment of FI employees and to promote safe working conditions. / FI clients in turn apply the IFC Performance Standards, national laws and the IFC exclusion list to their lending and investment operations through their ESMS. IFC’s Performance Standards provide a risk management framework to cover labor and working conditions; pollution prevention and abatement; community health, safety and security; land acquisition and involuntary resettlement; biodiversity conservation and sustainable natural resource management; indigenous peoples; and cultural heritage. The IFC Performance Standards may be reviewed at http://www.ifc.org/ifcext/sustainability.nsf/Content/PerformanceStandards. / IFC E&S Specialists are part of each investment project team and provide guidance and support to FI clients and assist with ESMS[30] development through appraisal and in portfolio. Support is also available through IFC’s recently launched client capacity development portal FIRST for Sustainability (www.firstforsustainability.com) which centralizes all IFC developed guidance for FI clients and the wider market. FI clients with a need for additional support to improve the E&S systems may also receive tailored support under the FI capacity building component. / Option 2: The use of grants to directly support FIs and SMEs may prove effective in some instances but tends to be rigid in its approaches or poorly monitored. Past experience has demonstrated that critical to the success of implementing ESMSs in emerging market FIs is the need for institutional support for risk management provided by a comprehensive risk management framework such as the IFC Sustainability Policy and Performance Standards. FIs are more likely to develop comprehensive E&S risk management systems that are integrated into their operations when supported by technical guidance and capacity building programmes as part of an investment relationship. / Option 3: The adoption of sound Environmental and Social Standards is crucial to sustain the development and growth of SMEs and the economy in which they operate. The “Do nothing” option would miss the opportunity to promote and shape sustainable businesses. Further, this option will leave financial services to continue growing at the current sluggish rates and leave certain SME segments largely unserved, including over 50,000 women headed entrepreneurs whose lack of financial support will limit their social security and economic empowerment. / 100. Based on the analysis and scoring, Option 1 is the most preferred option for the Global SME Finance Initiative, with the highest positive impact and projected results. / Table 7: Summary comparison of options with scores (1-5)* / OPTION 1 OPTION 2 OPTION 3 / Economic 5 3 2 / Political 5 4 3 / Institutional 5 4 2 / Environmental & Social / Climate 5 4 2 / Total Score 20 15 9 / *1 being least preferred option and 5 being the most preferred option

E. Measures to be used or developed to assess value for money / 101. The UK’s recent Multilateral Aid Review (MAR) made a detailed assessment of cost consciousness and found that the IFC’s past performance shows relatively good overall control of the administrative budget. / 102. The IFC’s strengths according to MAR are: / Overall cost control is good. / Tracks financial and economic returns. / Strong procurement guidelines, evaluation and audit processes also suggest that it is cost effective. / 103. The IFC’s weaknesses according to MAR are: / Staff pay mechanism inflates salaries at the World Bank and across MDBs. / 104. While the MAR found that IFC’s overall performance on cost consciousness was satisfactory, to be considered strong the IFC would need a corporate culture that seeks savings and commits to efficiency improvements as part of a consistent drive to improve value for money - and not just in response to specific constraints or Board action. / 105. To ensure a systemic approach to improving vfm of the programme, some of the actions we have taken or propose to take are: / Integrating vfm measures in the critical success criteria of this business case, ensuring minimal use of public/donor funds, instead leveraging private funds as much as possible. / Integrating vfm measures in the Logical Framework, and thus in the annual, mid term and project completion reviews, agreeing remedial actions if these measures score low. The benchmark for poor Vfm will be outreach of less than 30% of the targeted SMEs per year. / 106. Overall the benchmark for poor vfm will be if two or more Outcome purpose level indicators fall short of targets by more than 30% at the Mid Term. In this case, DFID will reserve the right to drastically modify the programme course, strategies and partnerships or stop funding to the Initiative. / 107. The following criteria, practical guidance and indicators are proposed to be followed/monitored as appropriate under this Initiative; / Volume of investments leveraged from DFIs and commercial investors for every £ of funding from DFID. / Volume of financing made available to SMEs by the partner financial institutions for every £ risk capital provided by the Facility. / Number of banks and financial institutions adopting new technology in driving financing to SMEs / SME loan application processing time in partner banks and NBFIs. / Number of banks and financial institutions using and participating in credit bureaus. / Number of FIs/NBFIs adopting and scaling up the use of new credit scoring tools.
[20] According to IFC outreach data, on IFC’s partner financial institutions serving the MSME sector, a financial institution on an average had 10,640 SMEs loans. However, these financial institutions benefit from IFC’s advisory services and investments and therefore do not represent the true profile of an average financial institutions in the Do Nothing Scenario. In order to make IFC’s partner financial institutions comparable to financial institution under the Do Nothing Scenario, we subtracted the effect of the advisory services by dividing average client outreach data from IFC’s data base by 1.4 given because on average IFC MSME institutions had a 40% higher outreach due to the AS component. We also discounted the outreach figure by 20% given lower disposable capital for the MSME FI without the presence of IFC or DFID.
[21] A relatively high discount rate of 10% is used in the cost benefit analysis in this appraisal. This is linked to the average coupon rate on 10-year government bonds in the 15 countries in which this programme will be implemented. The 10% figure is a rough average coupon rate for 10-year government bonds in the 15 countries rather than an weighted average as suggested in the guidance on Discount Rate recently issued by the office of DFID’s Chief Economist. These countries have a higher level of risk, whether environmental, civil or socio-political, in comparison with high and upper middle income countries that have typically have a lower discount rate, such as HMT’s Green Book rate of 3.5%. As a discount rate represents the social rate of time preference (that is the rate at which society exchanges consumption today for consumption tomorrow, calculated in annual periods) we would expect a discount rate to increase as uncertainty about the future rises. For example, in an environment where confidence about future stability is high there is little risk in delaying consumption through time and so little compensation is required. As uncertainty increases the degree to which society prefers immediate consumption over delayed consumption increases and, accordingly, the higher the compensation they require to delay that consumption.
[22] According to “Do Firms Want to Borrow More: Testing Credit Constraints Using a Directed Lending Program” by Banerjee and Duflo (2004), a study that analyzed data of a sample of SMEs in India, the impact of loans on sales varies in a range between 0.73 and 0.93 (for each $1 received in loans, SMEs increase their sales between $ 0.73 and $ 0.93). We have assumed in this model an 80% increase in sales per each dollar received in loans which is a middle point between the range found in the study.
[23] ) According to Banerjee and Duflo (2004) there is evidence that in India SME firms generated 73% in higher net income as a result of every rupee in loans obtained. This percentage represents a percentage based on subsidized lending and it represents only 1 country, so it was decided to take a more conservative estimate of 30% higher net income (before deducting interest) that was much more reasonable given the economic environment and the range of countries that the facility would target.
[24] According to the World Bank Enterprise survey data of 2007-2010, on average each formal SME had 19.5 workers in Sub-Saharan Africa and South Asia, and the average revenue per SME was of £ 94,835. Consequently, for every £4,875 pounds in revenue, there is 1 employee in every formal SME.
[25] Information on minimum wages was found in the United States Department of State, 2008 Country Reports on Human Rights Practices and in Workbarometer.com. An adjustment was made for inflation using Economist Intelligence Unit Data on inflation rates in order to have 2011 min wage data. In the case of Mozambique, there was additional information on wages paid in the SME sector which indicated a premium of 20 percent over the minimum wage for that particular country. The assumption made was that this 20 percent premium should be applied for all minimum wages for the target countries of the facility which resulted in an average minimum wage of £53.87 per month given that in many instances SMEs require higher skilled personnel compared to the employee contracted with just the minimum wage.
[26] According to IFC SME outreach data, the average loan size in India, Bangladesh and Nepal for IFC clients was lose to £16,875. For Africa the average loan size was £65,000. The main difference was due to the presence of a few South African and Nigerian banks in the Sub-Saharan case that made very large loans to the medium sector which were raising the average substantially. The model then assumes that 70 percent of the loans given under concessional funding are working capital loans with an average term size of 2 years and average loan size of £12,500, while the remaining 30 percent of loans would be investment linked loans with an average term of 3.0 years and an average loan size of £43,750. This results in a weighted average loan size of £21,875 for institutions that receive concessional funding under the facility. For institutions receiving AS and non-concessional funding, a higher loan size for the loans disbursed was assumed of £35,000 with a loan tenure of 3.5 years given that it is assumed that these institutions are banks that are already lending to the SME sector, and due to the lower implicit risk this allows the institutions to make loans with higher loan balances.
[27] Data on SMEs with and without credit was obtained from World Bank Enterprise Survey Data.
[28] See SME Banking Knowledge Guide, IFC (2009).
[29] Based on the recently approved (and internationally tendered) DFID India’s PSIG programme, and management incurred by DFID in SME finance and development programmes of relatively similar scale in countries such as Pakistan and Bangladesh.

3. Commercial Case

Direct procurement

3. A. Value for money through procurement. / 108. The proposal that our funding be routed through the Global SME Financing Initiative being organized by IFC, which is linked to a G20 initiative on scaling up financing for SMEs, is based on strong considerations of value for money and management cost of programme delivery. We had an extensive consultation process with commercial banks, private equity investors, DFIs and NGOs operating in the SME space leading up to initiatl conception of this programme and the identification of IFC as the implementing partner. The Initiative has been jointly designed with intensive inputs from and consultation with DFID staff. / 109. As set out in the Strategic Case, this Initiative has strong potential to deliver DFID’s objective of supporting sustainable scaling up of SME financing in poorer countries and its Operational Plan target, and is expected to deliver strong value for money. Working with IFC will not only help leverage funding by 8 – 10 times on our funding to the risk capital component; it will also help mobilise the considerable technical resources and expertise of IFC at the global, regional and national level. IFC has an established track record in financing and building the capacity of commercial banks and financial institutions in emerging markets. It has over 60 active advisory services projects worldwide in SME finance where it is partnering with banks and supporting their capacity building to reach out to the SME sector effectively. / 110. Our judgement is that it would cost relatively less to deliver our identified interventions through IFC than it would cost if we were to deliver this in direct partnership with commercial banks. By partnering with IFC, we save on the design cost for the programme and the time that we would have incurred if we were to choose other Option 2 considered in the Appraisal Case. Moreover, IFC’s management cost (that includes the centrally mandated Administration Fee for Trust Funds implemented by the World Bank Group) is £4.8 million or 6.4% of DFID’s programme cost, which compares very favourably with the management cost of DFID funded programmes of comparable scale[31]. Given that this Initiative will work in some of the more challenging environments in the frontier markets, the management cost of a programme like this Initiative could have been significantly higher if we were to do this directly with banks and financial institutions. However, through the partnership with IFC, we are able to leverage IFC’s exiting structure and management bandwidth on the ground, and therefore substantially reduce the management cost. / Indirect Procurement / Procurement/commercial requirements for intervention / 111. Of DFID’s contribution of £75 million, £67.75 million will be spent on programme delivery; £2.45 million on monitoring and evaluation; and £4.8 million for programme management cost, including the centrally mandated Administration Fee for Trust Funds implemented by the World Bank Group. / 112. Of the £67.75 million of the programme delivery funds, £38 million will be used for Component 1 (Risk Capital), £26.2 million for Component 2 (capacity building support to partner financial institutions and financial market infrastructure development), and £2.9 million Component 3 (technology based solutions through three G-20 SME Finance Challenge Winners). We expect that some of the technical assistance will be delivered by IFC’s own staff and will be in effect, paid for by this facility. We believe this is acceptable and critical for the successful delivery of a multi-year, multi- country programme. This becomes particularly relevant in the case of delivery of financial infrastructure which takes time to deliver as there is limited market expertise available and can not be relied on for long term projects. Having the availability of the right quality of people is also critical in the context of delivering in conflict affected environments where again, there is a limited pool of consultants available. The fact that IFC has a strong pool of technical experts on the ground and in the countries that this programme will cover is one of the reasons for choosing to go with IFC. / 113. As a member of the World Bank Group (WBG), IFC will follow WBG standard procurement policies, procedures, and processes. Adminstrative and technical procurement under this Initiative will ensure open and fair competition in all its tenders. IProcurement of goods and services will be mostly through International Competitive Bidding with limited exceptions similar to those used by other multilateral development banks. There will be considerable oversight and scrutiny of IFC’s procurement under this Initiative by the World Bank procurement operations which usually reviews around 5% of all procurements in the WBG are reviewed internally and a smaller amount of operations go to external review every year. Exceptions to open bidding may be granted for contracts below the following thresholds, applicable for all components of the initiative: / Technical procurement/Consulting services: Contracts under $50,000 / Administrative procurement: Contracts under $10,000 (e.g. Office Supplies, Graphic Design, Publications & Print Services) / IFC will award contract to the highest scoring evaluated offer or following the negotiation of an acceptable contract, with detailed terms and conditions to ensure value for money. / Selection of Partner Financial Institutions and Definition of Projects: / 114. The approach here will be to consolidate and leverage IFC’s existing networks and relationships with partner financial institutions. IFC will select at least 35 financial institutions for partnership under this Initiative for advisory services and/or investments. This will include local subsidiaries of regional banks. IFC will target a balanced mix of financial intermediaries that includes: / - Existing financial intermediary investment clients and subsidiaries of parent companies that have a pre-existing investment relationship with IFC. / - Promising financial intermediaries outside IFC’s existing network operating in DFID priority countries. / 115. IFC will select the PFIs based on the following criteria : / - Demonstrable commitment, as measured by existing portfolio and as articulated in its business strategy, to expand its SME portfolio in a sustainable manner. / - Preference will be given to banks and NBFIs that (a) reach SMEs in conflict affected and post conflict regions/countries and (b) have credible plans to reach SMEs owned by women and/or that employ women. / - Preference will be given, especially in the relatively developed markets such as India, Pakistan and Nigeria, to banks and NBFIs that reach poorer and lagging regions in those markets. / - Primarily privately-owned financial institutions. State-owned banks with strong SME segment may be considered on a case-case by case basis. / - PFI is a legal entity and is licensed to operate in its market. / - PFI is financially stable and sound as measured by NPL levels and return on capital, with adequate credit policies and procedures especially in the area of SME financing. / - Commitment to IFC’s E&S standards. / - Compliance with regulations stipulated by the regulator(s), and adequate AML and CFT practices. / Any changes in the selection criteria will be subject to approval by the Steering Committee. / 116. The selection process and articulation of activities (henceforth referred to as called projects) for the PFIs will be carried out by IFC in three stages as follows: / (i) Initial screening criteria for all new target clients: / Size and performance of the existing SME loan portfolio; / Clearly articulated objective to significantly grow SME portfolio above existing levels; / Ability and willingness to move into and or expand lending in fragile states; / Ability and wiligness to expand loans and outreach to women in business; / balance of mix between development and outreach agenda; and / financial position. / (ii) Evaluation of each PFI across several dimensions in line with IFC standards (for new and existing clients): / Compliance with IFC Investment Standards, including rigorous integrity due diligence / Corporate governance and internal controls / Adherence to responsible finance practices / Implementation capacity / Commercial orientation and sustainability / Strength of internal systems / Financial stability / (iii) Project Design: / Financial intermediaries that comply with the selection and evaluation criteria above will be added to the project pipeline under the programme. Investment and advisory teams in the IFC will develop an in-depth design of individual projects tailored to each partner FI, reflecting a combination of the PFI’s self-identified strategy and needs and IFC’s own assessment of the same. The project design will be based on an in depth investment due diligence and advisory assessment of needs. / 117. Project proposals will be developed based on IFC templates and then submitted for approval to the Investment Committee. / Implementation of projects per Programme Component: / Component 1. Risk Capital for Financial Institutions / 118. DFID’s funding of £38 million to the Risk Capital Component will be deployed under IFC management and will not require external procurement, except to the extent that certain back office/middle office functions may be outsourced to improve efficiency. Our funds will be pooled along with other contributions from DFIs and PFIs in to an SPV and will be used to provide concessional finance (financing at softer terms) where justified. Financing at softer terms could be done through either pricing, tenor, rank or security or a combination in order to incentivize the client to do things they would otherwise not be able to do that can have high development impact Decisions on choice of PFIs and amounts of funding will be subject to the approval of the Investment Committee. More details on concessional finance have been covered in the management case in pages 40-41. / Component 2. Advisory services / 119. Advisory services projects for PFIs and financial infrastructure require and leverage on IFC’s in-house expertise and advice. As such, diagnostics of projects will be carried out by IFC’s pool of specialists and short term consultants, who will design the implementation plan. The implementation of PFI projects will be generally outsourced to external consulting firms/consultants with expertise in the required field (e.g. credit risk management, product development, etc) following a competitive selection process. Implementation of financial infrastructure projects will be directly managed by IFC specialists and include feasibility studies, advising and building capacity of local stakeholders, providing support during project implementation. IFC’s role during the selection process is to advise and evaluate the technical proposals, expertise and experience of the consultants, as well as review their financial proposal to ensure an objective selection based on highest value for money. / Component 3. Grants for technology based solutions: / 120. The three G-20 SME Finance Challenge Winners that will be supported under the Initiative from DFID funds have come through a global competition commissioned by G-20 in 2010 and further evaluated and ranked by DFID based on our own criteria. IFC will carry out a diagnostic to validate the activities and budget of the project as well as results to measure the performance of the project. Grants will be documented through an appropriate Grant Agreement between IFC and the project client. The agreement provides client accountability through conditions of disbursements that are triggered by the grantees’ ability to meet the agreed conditions and reach performance results, in line with IFC’s Grants Directive.
3. B. How does the intervention design use competition to drive commercial advantage for DFID? / Component 1: Risk Capital for Financial Institutions / 121. The design of the risk capital component considered several options for managing the investment vehicle, including the possibility of procuring fund management services from an external resource. However, after consideration of other models and service providers, and in consultation with other investors, it was determined that IFC will be cost effective and well suited to managing the core functions, while gaining cost efficiencies by outsourcing some of the middle/back office functions. Some of IFC’s strengths in this area include: (i) an extensive network of staff around the world who are able to deploy funds under this Initiative without significant additional administrative cost (ii) strong relationships with over 100 commercial banks and non-banking financial institutions in Sub Saharan Africa and South Asia (iii) IFC’s broad range of SME products and services (iv) IFC’s global reach and expertise in the SME space, and (vi) a well respected position among DFIs and donors in the SME space. / Component 2: Advisory Services / 122. Capacity building of FIs: IFC will contract the services of consultants for FI projects to carry out the Implementation plan of each client. The selection will be based on individuals’ and firms’ capabilities, intellectual capital, field and industry expertise, and geographic range, among others. The procurement process for the selection is described above, and it is designed to promote competition and provide opportunities for local and international experts, ensuring cost-effectiveness. On average, three firms are evaluated during a selection process. Procurement for products for FI advisory services may take place from time to time, mainly including training material and publications in support of projects. In the case of financial infrastructure, technical systems and related implementation support will be provided to projects on an exceptional basis. Procurement of products will also be competitively procured per the guidelines mentioned above. / 123. Financial Infrastructure: This component will be delivered through IFC’s global pool of experts. The actual development of financial infrastructure will be done through an external provider/vendor, which will be funded by the provider in conjunction with local stakeholders. The contracts will be awarded as per IFC’s procurement processes described earlier. / Component 3: Grants for technology based solutions: / 124. The three proposals pre-identified by DFID for funding under this component have already come through a global competition: G-20 SME Finance Challenge, commissioned by G-20 in 2010 and have been further ranked by us based on their ability to promote financing for SMEs at scale with a relatively small investment from DFID.
3. C. How do we expect the market place will respond to this opportunity? / Component 1: Risk Capital for Financial Institutions / 125. The risk capital component is expected to generate significant interest on the part of potential partner banks and non-banking financial institutions interested in the SME segment but unwilling to pursue key segments due to perceived risk. The projected leverage of £1.56 billion on the back of £38 million DFID funds is an indication of our expectation of the level of interest from the markets. We hope the combination of risk sharing and technical assistance will help banks expand their businesses in the identified DFID priority countries. / Component 2: Advisory Services / 126. The number of technically suitable consultants and consulting firms for every component will vary from country to country, and will depend on both location of the project (or need for specific local knowledge of the market) as well as on the field of expertise. Projects in conflict affected or smaller countries tend to have a limited supply of experts with local market knowledge vis a vis larger and/or more stable economies. Likewise, the more specific the expertise required, the more limited the number of experts available will be. However, in going with IFC, we believe we will have the advantage of their extensive technical expertise and an extended panel of international consultants. / 127. Financial infrastructure: In the case of providing technical expertise and support for establishment and strengthening of credit bureaus, IFC belives there are about 10 internationally recognized credit bureau consultants with expertise and know-how to develop and implement a system, or support system upgrades. IFC supports their clients in sending out Requests for Proposals (RFPs) to all relevant vendors, (including local ones). Actual vendor selection is done by the client (with inputs/feedback from the IFC team after reviewing the RFPs). Actual implementation (and the number of people required for the development or deployment) is determined by the vendor’s business plan. In some cases, the IFC specialist will be requested to act as project manager during the implementation process to oversee the activities of the selected vendor. For Collateral registries, there are about 5-6 service providers with proven expertise in setting up systems. An average of 2-3 consultants are needed for each system set up. / 128. FI capacity building: Based on IFC’s market knowledge and experience, IFC believes that there is an average global pool of approximately 20-30 international and regional consulting firms with the needed expertise to carry out FI advisory projects. Larger countries generally have a broader pool of choices, while smaller countries tend to have a lower supply of service providers. RFPs will be sent to all relevant vendors/ suppliers. Supplier selection is done by IFC in coordination with the financial institution client upon review of the RFPs. An IFC team member will act as project manager during the implementation phase, overseeing and monitoring the supplier’s/vendor’s activities.
D. What are the key underlying cost drivers? How is value added and how will we measure and improve this? / Component 1: Risk Capital for Financial Institutions / 129. With regard to the administration of these funds, the key cost drivers are: (i) pipeline development and supervision (ii) cost of establishing and administering the trust funds and investment vehicle (iii) governance and approval mechanisms (iv) reporting and M&E. Across all of these elements is the question of scale since management and administration can be leveraged across a larger pool of funds. The key evidence of value added will be the utilization of the funds, the mobilization of additional funds from other DFIs and the PFIs, and the satisfactory reporting on the outcomes and impact of the initiative, including learning from the experience. / Component 2 & 3: Advisory Services and Grants for Technology Solutions / 130. Cost drivers for this component of the Initiative are affected by a series of variables, mainly: / - Market context / - Degree of specialization for required project / - Availability of consultants / - Security issues / 131. For instance, projects in conflict affected countries will normally be priced higher accounting for the security risk of the consultants. In the case of technology solutions (under component 2 and/or 3)an important cost driver is the proximity of the service provider to the project location, given the frequent visits needed to oversee its implementation. Another relevant cost difference comes from the availability of technology in a given country. For example, internet access and the availability of hardware is much more expensive in conflict affected countries than in more developed markets. In some countries we need to bring in the needed technology (hardware such as servers for example) at a much higher cost because it is not available within country. Political instability is another factor that can sky rocket costs in a given country due to the longer implementation timeframe, constant change in stakeholders, need for more frequent travel to engage with constantly changing stakeholders, etc. / 132. In the case of credit bureaus, IFC will only provide expert advice, project management support and legal and regulatory framework support for the projects. Cost drivers for the procurement of vendors will be determined by the business plan as well as the type of solution being requested. Further, on-shore technical solutions may be more expensive than off-shore solutions. Costs will vary depending on client demands, disaster recovery site, multi language capabilities and other system features. It should be noted that these costs will incurred by the vendor and the local stakeholders. / 133. IFC uses established benchmarks to determine costs of suppliers. In order to ensure adequate cost controls and consultants/project performance, each project will have a designated IFC regional specialist who will serve as project manager and will monitor and be the point person for the project during the full project life cycle.
E. What is the intended Procurement Process to support contract award? / 134. Contract awards for goods and services under all three components will be assigned by IFC on the basis of the following key selection criteria, adjusting for the specific needs and expertise for each contract: / - Technical capacity of the firm or individual based on the project’s Terms of Reference / - Qualification and of the team or individual based on World Bank’s Qualification Questionnaire. / - Financial proposal. Additional scoring points will be provided to the firm with the lowest financial proposal as part of the evaluation process, to ensure value for money.
F. How will contract & supplier performance be managed through the life of the intervention? / 135. Contract and supplier performance will be guided by the World Bank Group’s procurement policy and detailed output based contracts. / Component 1: / 136. Financing to PFIs through the SPV will be monitored by IFC through their M&E framework. For any third party that provides middle or back-office services for the management of implementation of the risk capital component, contracts would be issued with clear roles, responsibilities, deliverables and negotiated cost structures. IFC would work closely with these entities on an ongoing basis, providing instruction and documentation for the execution of services which the suppliers will be obligated to carry out. / Component 2 & 3: Advisory services and grants for technology solutions / 137. An in-depth design and work plan of each project is tailored to each partner institution, reflecting a combination of the partner’s self-identified strategies and needs, and IFC’s own assessment. Project budgets are defined in line with each work plan and based on in-depth assessments of clients to identify specific/detailed needs, current client situation, and areas for improvement based on good practices. / 138. IFC will sign legal agreements with both the client and suppliers supporting the project, based on IFC’s standard advisory services and grant agreements. The agreement will detail the budget, disbursement schedules, conditions for disbursement and expected performance results which will be signed off and monitored by IFC staff over the life of the project.
[31] For example, the management cost in the DFID India Poorest States Inclusive Growth programme, which went through an international tendering process, is 9.2% of the total programme cost. Likewise, SME finance and development programmes funded by DFID over the past five years or so in India, Pakistan, Nepal and Bangladesh have management cost in the range of 10%-12%.

4. Financial Case

4. A. How much it will cost £ Million / Programme delivery costs (A) £ 67.75 / Risk sharing Investments £38.00 / Capacity Building or TA to selected / Partner financial institutions (PFIs) £20.90 / TA for financial market infrastructure / development £6.00 / TA for technology based solutions (grants to 3 G-20 SME Finance Challenge winners and SME Finance / Policy Forum) £2.85 / Programme Management costs and fee (B) £4.80 / Management costs £3.05 / Trust Fund Administration Fee £1.75 / Monitoring and Evaluation (C) £2.45 / Total (A+B+C) £75 million / 139. Total funding of £75 million includes up to £15 million co-funding from DFID local offices in Nigeria and Mazambique. Of DFID’s contribution up to £75 million, £67.75 million will be spent on programme delivery; £2.45 million on monitoring and evaluation; and £4.8 million for programme management cost, including the standard Trust Fund Administration cost of the IFC. / 140. In the case of Component 1 (Risk Capital), management costs include both the management of the investment facility as well as individual project management costs. The table below gives the breakdown of the management cost for the capacity building and financial market infrastructure component. The trust fund administrative fee will cover cost associated with the management of trust fund expenses, management of central advisory services and support units coordination, reporting to DFID, and cost of the trust fund’s single audit. The individual operating cost to manage each Advisory Service project in components 2 and 3 will be included in the total budget for each project. / 141. Programme management costs and M&E refer to dedicated funding resources that will be needed to manage the full Programme and ensure coordination among Programme components. The table below gives a breakdown of the programme management costs to be incurred in management of Output 2 and Output 3 and will cover the following activities: / Budget Management / Provision of programme guidelines and processes / Creation of regional workplans and coordination with regions / Coordination with Risk Capital and Grant component / Communication and Reporting / 142. Monitoring and evaluation costs will include (i) the cost of a dedicated M&E officer for the Programme and (ii) resources to develop the capacity of partner institutions to strengthen their reporting, particularly to evaluate SME job creation.
4. B. How it will be funded: capital/programme/admin / 143. DFID funding will be classified as programme (R-DEL). DFID’s grant funding for the risk capital component will be routed through an IFC trust fund in to a SICAV SPV. If our share of risk capital is not fully utilised by the end of the term of the facility, it will be paid back in to the IFC trust fund along with any surpluses that may be attributable to DFID. After the mid-term review or closer towards the end of the facility, DFID in consultation with IFC, will take a final call on what DFID will do with the money remaining from its contributions in the risk capital component including any surpluses. Our MoU with IFC will give us the flexibility to take a view on the final destination of the funds and their application and set out a clear protocol for decision making on this. / 144. The risk sharing component from the various initial funders likely to be DFID, IFC, EIB and Kfw, will be pooled in to an SPV. We expect to sign the MoU and have a framework agreement in place by end of January or early February. In case there is a delay from EIB or Kfw, we propose that DFID and IFC sign the Trust Fund Agreement with disbursements conditional on (1) funds only being disbursed when the Framework Agreement or an MOU has been signed indicating the various DFIs' intention to commit up to £325 million identified for first close of the facility and (2) funds only being disbursed in proportion to the funds that have actually been committed into the facility (i.e. DFID’s initial £12 million representing 32% of the concessional funds being matched by £103 million committed from the DFIs to the risk capital component) (3) clear purpose established for the use of funds requiring a disbursement. / 145. There is no contingent liability associated with this funding DFID’s central contribution of £60 million can be financed from within the Private Sector Department’s existing aid framework for the current SRP, and co-funding of £10 million from DFID Nigeria and up to £5 million from DFID Mozambique will come from their respective bilateral aid framework.
4. C. How funds will be paid out / 145. This is designed as a multi-year, multi-country and multi donor Initiative. However, it is possible that some of the donors joining the Initiative later may prefer broadening the scope of the Initiative to include interventions that may not be high priorities for DFID. If this happens, it will be easier for IFC to manage DFID’s intervention through a single donor trust fund. IFC will mobilise the full anticipated level of funding for the programme over three closings over the next 6-12 months. The first closing of the programme will be in January 2012. In the interest of time, and to deliver on DFID’s SRP targets, IFC has agreed to start implementation of the programme immediately after the first closing in January 2012. / Building of pipeline of activities / 147. The process to building the pipeline for the 1st year of the Programme has already started and is broadly divided in two phases: / Engagement with existing IFC advisory services pipeline clients, where the needs and a roadmap for implementation have already been identified, and IFC and the FI client are ready to begin a capacity building project. This will largely apply to projects in larger countries. / An in-depth assessment of specific markets and financial sector players carried out by IFC regional teams from Africa and South Asia, based on information gathering from the market to further develop the pipeline, particularly in frontier markets. / 148. IFC is in a strong position to start implementation of the programme in some of the identified DFID priority countries. This is because this Initiative will consolidate and build on IFC’s past investments and relationships in these countries. IFC already has investments and advisory services relationship with a network of commercial banks and non-banking financial institutions, and can hit the ground running in rolling out the activities of the Initiative in these countries. IFC has already started developing pipeline of activities in some of the DFID priority countries. Projects in larger countries will likely be mobilized at a faster pace making the ramp-up period for such projects also faster. Mid-term results on the Initiative are thus expected to reflect a higher share of projects in larger countries vis-a-vis smaller/conflict affected countries. IFC will seek to ramp up operations in smaller countries, taking into consideration the time needed to develop the pipeline and the fact that projects in such markets typically require more time for their definition and implementation due to higher barriers on information, market sophistication, financial infrastructure, and macroeconomic/political externalities. / 149. The Initiative will consist of two trust funds allocated to : / Risk Capital for financial institutions to expand their risk tolerance and increase their SME portfolio. DFID will transfer these funds to an IFC Trust Fund which in turn will purchase shares on behalf of DFID in a Luxembourg based collective investment structure (SICAV) in the form of Junior or “C” Shares. / Advisory services: these funds will be allocated into a Trust Fund also based in IFC Capacity building of FIs and financial infrastructure, as well as grants for technology based solutions of the G20 SME Finance Challenge winners. / 150. IFC will administer the trust funds in accordance with its policies. Child or sub-trust funds could be established under the two trust funds to implement the respective components. Details of administration of the trust funds will be set out in the Administration Agreement between IFC and the DFID. / 151. A Memorandum of Understanding (MoU) and a Framework Agreement between DFID and IFC will govern the funding arrangements and DFID’s rights under this facility. The £75 million budget envelope can only be exceeded if an additional appraisal is appended to this Business Case and a submission is approved that makes a robust case and funding available in PSD’s budget. / 152. Funds will be paid out on receipt of a call of funds request from the IFC subject to prior agreement of delivery of programme or activity inputs or outputs. A proposed schedule of minimum disbursements will be agreed with IFC as part of the MoU. This funding schedule is likely to be as follows: / DFID FY11/12 - £12 million to be disbursed by March 2012 / DFID FY12/13 - £ 21 million in two half yearly tranches / DFID FY13/14 - £21 million in two half yearly tranches / DFID FY14/15 - £21 million in two half yearly tranches / 153. The financial sector and financial markets infrastructure in most of the identified DFID priority countries for this Initiative are at a very nascent stage of development, and the market is highly underdeveloped in the conflict affected countries and small/frontier markets such as South Sudan, Mozambique, Sierra Leone, DRC, Liberia, Malawi, Uganda, and Nepal. Therefore, we will require longer-term involvement, and we propose a time period of up to 7 years. The pattern of fund disbursment explained above will ensure predictability for IFC and the PFIs of funding for the Initiative while allowing additional funding to be provided subject to completion of or commitment to agreed actions, as set out in the MoU. / 154. Payments will be made to IFC in advance on six monthly basis, but subject to the DFID lead adviser and PSD’s satisfaction that IFC has developed a strong enough pipeline to absorb the funding from DFID. IFC’s regulatory framework requires that funding must be received in full before commitments/contracts to this level can be negotiated. In order to avoid the risk of cash piling up in the trust fund bank accounts, payments will be matched to expenditure/contracting needs for this 6 months. IFC will need to ensure that the spending profile is not evenly spread out through the year, instead IFC should be able to demonstrate the bulk of spending will occur in the three to four months from the date of disbursal from DFID. Funding will be provided on the basis that IFC will commit funds that require additional funding beyond any outstanding disbursed balance from DFID. This will be stipulated in the MoU. In order to manage this effectively, PSD will provide good internal programme management support in order to ensure that the disbursement profile is clearly linked to expected spend profile of IFC, to manage and minimise the impact on DFID's spends as a result of prepayment recognition. For example, ensuring that funds are being provided for use in the short term and ensuring that prior to the next payment to IFC, all earlier funds have been used. / 155. Any interest accruing on the trust funds bank accounts will be recycled back to the programme delivery. / Co-funding from DFID Country Offices / 156. Approval for co-funding from DFID Country Offices will be sought on the basis of this single umbrella Business Case, appending results expected to be delivered in the country. DFID Country Offices will allocate the agreed amount of co-funding for the Initiative on DFID’s ARIES to the Private Sector Department (PSD). PSD in turn will provide funding to the IFC Initiative. PSD will have the responsibility of monitoring all the payments to the IFC Initiative and monitoring progress of results against intended targets, including Country Office specific targets. / 157. IFC on its part will, to the extent possible, ring-fence co-funding from DFID Country Offices. However, ring-fencing will be not be possible for the risk capital component of the Initiative which will pool risk centrally from different investors such as the DFIs and commercial investors. In this case where ring-fencing is not fully possible, IFC will demonstrate that funding from the DFID Country Office has been spent for implementing the Initiative in the country and report what results have been achieved in that country. IFC's M&E arrangement will have system in place to be able to report progress at the country level against at least a few key performance indicators (at the outcome and output level) if not all the indicators in the Logical Framework.
4. D. How expenditure will be monitored, reported, and accounted for / 158. Monitoring, reporting and accounting will follow IFC’s standard policies for trust funds of this nature. As such, IFC will be responsible for the supervision and execution of activities under the programme and will provide progress reports to DFID on a semi-annual basis. The format and content of financial reports shall be consistent with the IFC’s accounting system and include a review of the Programme’s activities and results to allow DFID to assess if performance is satisfactory to support future disbursements. / 159. For the Advisory Services Trust Fund, IFC will provide DFID with an annual single audit report within six months following the end of each IFC’s fiscal year. This report will comprise of (1) a management assertion together with an attestation from the World Bank Group’s (WBG) external auditors concerning the adequacy of internal control over cash-based financial reporting for all cash-based trust funds as a whole; and (2) a combined financial statement for all cash-based trust funds together with the WBG’s external auditor’s opinion thereon. The WBG will bear the cost of the single audit. / 160. For the investment Trust Fund (Risk Capital), IFC will provide DFID with the following information: / Annual audited reports from the investment vehicle / Semi annual progress reports / Quarterly unaudited financial statements / 4. IFC can arrange to have a Single Audit Report / 161. External Audit: In addition, DFID can request, on an exceptional basis, a financial statement audit by IFC’s external auditors. DFID and IFC will first consult as to whether such an external audit is necessary. IFC and DFID will agree on the most appropriate scope and terms of reference of such an audit. Following agreement on the scope and terms of reference, IFC will arrange for such external audit. The costs of any such audit, including internal costs of IFC with respect to such audit, will be borne by DFID. / Financial Reporting and Monitoring. / 162. Call for funds letters from IFC will detail the amount of funds IFC needs for the activities of the Initiative and what the money will be used for. The IFC or the World Bank Group on behalf of the IFC will maintain separate records and accounts in respect of the Donors’ Funds in the Trust Funds and funds disbursed from it by IFC. The IFC will make available to DFID current financial information relating to receipts, disbursements and fund balance in United States dollars with respect to the DFID’s Funds via the World Bank Group’s Trust Funds Donor Centre secure website (https://clientconnection.worldbank.org). / 163. Within six months after all commitments and liabilities under the Initiative’s Trust Funds have been satisfied and the Initiative’s Trust Funds has been closed, the final financial information relating to receipts, disbursements and fund balance in United States dollars with respect to the Initiative’s Trust Fund will be made available to DFID via the WB’s Trust Funds Donor Centre secure website. / 164. DFID will request IFC to provide a annual balance sheet detailing how much has been spent and on what activities and outputs the funds have been spent on as part of the MoU agreements. It will be incumbent on DFID’s programme manager and Lead Adviser for the Initiative to monitor IFC’s expenditure on a annual basis and feed findings into the annual review of our contribution.

5. Management Case

5. A. Oversight / 165. Strategic direction will be provided by the funders through a governance mechanism described below which represents the interest of the key stakeholders. The structure provides a strong role for the funders in shaping the strategic direction of the Initiative, while enabling IFC as the implementing agent to manage day-to-day implementation. / Graph: Governance Structure / 166. IFC will provide management oversight for all three components of the Project. It will be responsible for delivering the results agreed with the funders, and ensuring compliance with all agreements and policies relevant to this Initiative. The key stakeholders of this initiative include the funders, the partner financial institutions and grantees, and the beneficiary SMEs. In addition, other stakeholders which will be involved in various ways across countries including local governments and regulators, the G20 and consultants or NGOs providing services under this Initiative. / 167. The Initiative distinguishes between commercial funders and donors. Donors will provide funding through Advisory and Investment Trust Funds on the basis of Trust Fund Agreements, with oversight through a Donor Steering Committee. Commercial funders will provide funding directly into the investment vehicle on the basis of the Shareholders’ Agreement and their activities will be governed by a Board. As DFID’s Implementing Agent, IFC will sign the Shareholders’ Agreement on behalf of and in consultation DFID. The two groups will be linked through a common Master Framework Agreement outlining the key components of the Initiative and their relationships to one another, objectives and anticipated results. / 168. For the risk capital component, it is proposed that DFID’s funds be paid into a Trust Fund in IFC, and then transferred into the investment vehicle as "C" shares. IFC will receive delegated authority to sign the shareholder agreement and represent DFID’s interests in the vehicle. There are three key documents that will define our interests. First, the Trust Fund Agreement between DFID and IFC - this document would include any specific requirements that DFID will have with regard to those shares, which IFC will be obligated to uphold, including for example, our country requirements, firm size requirements, liquidation rights, etc. Second, there will be a Framework Agreement linking all of the donor and commercial investors which will provide a high-level overview on how the different parties will work together and the key operating principals. Finally, the Shareholders' Agreement will define in very specific detail the rights and obligations of each of the classes of shareholders. IFC will involve DFID in discussions with the other funders about the rights of the various share classes so that that we will be well aware of those rights as they are finalized and are comfortable with them. / 169. Donor Steering Committee. The Donor Steering Committee will focus on strategic issues and direction of this Initiative as well as approve any deviations in the design parameters agreed in this programme. The Committee will advise on the strategic direction for the use of donor funds being used across the three components of the Initiative. The Committee membership will include DFID in its capacity as donor of the Initiative, two IFC representatives from advisory services and investment services respectively, and other donor representatives of the Initiative. Donors may opt in or out of participating in the Steering Committee. The Committee will convene in person or virtually on a semi-annual basis, if required more frequently in the initial inception and implementation period. Its main role with respect to the programme is the following: / Provide strategic direction and guidance / Endorse annual work plans and strategy for the Initiative presented by IFC / Monitor progress against agreed targets / Agree with IFC any adjustments in programme design in order to ensure achievements of objectives and targets. / Review and comment on annual work programmes and periodic progress reports / Consider learning generated from the Initiative and provide feedback on potential performance improvements / 170. Board of Investment Vehicle. The risk pooling component of the Initiative will be rolled out through a collective investment vehicle (SICAV - SPV) to be set up in Luxembourg or through a Master Cooperation Agreement (MCA) type arrangements with investors. In either case, there will be a Board or similar investment governance body that will perform standard governance functions and approve investment policy and operational procedures, which are expected to be based largely on IFC’s own policies and procedures with regards to commercial and concessional investments. Board membership will include an IFC representative and two of the large DFI/IFI investors, which are expected to be KfW and EIB. DFID will make its contribution to the risk pooling component through IFC and on the basic of an MoU with IFC. In its role as Implementing Agent, IFC will represent the donor interests on the Board (see Management Section for more detail). Investment decisions under the financing facility will be made by an Investment Committee of the Board, comprising IFC and the two DFIs. Conflict of interest issues between funders will be addressed by the Board. While DFID will not have direct involvement in the investment decisions of the SPV, our oversight will be through IFC’s Investment Team who will be accountable to us. / 171. IFC as the Implementing Agent for DFID is obligated to ensure that DFIDs interests are protected in any investments issued with DFID funds. IFC has a clear policy which governs the use of donor funds for investments, and well established practices for ensuring appropriate use of concessional funds in particular. In addition to being obligated to uphold any legal agreement with DFID, IFC’s policies require that someone independent of IFC’s investment operations review and endorse all investments made using donor funding. Therefore, individual project approvals will follow IFC’s standard operating procedures which require an independent team to review and endorse the use of concessional funds, ensuring compliance with IFC’s policies and donor agreements.
5. B. Management / Management of the Initiative in DFID / 172. A full time equivalent staff will be allocated to the core management of DFID’s contribution to and engagement with IFC for implementation of this Initiative, including internal financial management of DFID’s funding. Management will be led by the designated Lead Adviser in the PSD’s Investment and Finance Team (50% FTE at A2 grade for the first year of implementation and then gradually reducing to 25% by year 5). There will be supervisory and quality assurance inputs from the IFT’s team leader and support from the project officer on financial and project management issues. There will also be ad hoc support from the A2 PSD Adviser - Conflict affected & fragile economies (CAFEs) in PSD and other team members on thematic areas (10% FTE total at A2 grade). / 173. The Lead Adviser will be accountable for managing delivery and the relationship with IFC on the implementation of this Initiative. We envisage that the Initiative’s performance could need to be monitored by Country Offices providing co-funding and take up to 5% FTE of the relevant lead advisor’s time as part monitoring of country level implementation work. This may include a developing a short monitoring framework by IFT to assist Country Offices providing co-funding to effectively monitor IFC’s performance in the field. / 174. Technical experts may be called down to peer review performance and/or on DFID’s request, against the following criteria: guidelines set out in this project document; evidence base of what works; feasibility based on track record of the organisation and cost efficacy. / Management of the Initiative by IFC / 175. A Programme Coordination Unit within IFC will report to the Steering Committee and will be responsible for coordination among the programme’s components (i.e. advisory and investment services activities). The unit will also have the support of a Financial Officer responsible for the financial management of the programme and its trust funds, and the support of an M&E Specialist who will consolidate and monitor and data and indicators at the programme level, including designing evaluation frameworks. The programme will leverage IFC’s existing management and governance structure, and will focus on achieving development effectiveness. The projects will be managed by teams at the regional level, with the advisory services and risk capital components being managed through the respective Advisory and Investment units of IFC. / Component 1: Risk Capital for Financial Institutions: / 176. The risk capital component will be managed by a central unit in IFC’s Global Financial Markets Department, which will be closely coordinated with the Programme Coordination Unit and the Advisory Services team. This group will be responsible for fundraising, creating and managing the investment vehicle, and managing those funds once they are placed in the investment vehicle. (For donors, the Trust Funds Department is responsible for any Trust Fund accounts, and any funds remaining in the Trust Funds.) Investment projects utilizing the funds will be decided using IFC’s standard operating procedures, which includes a determination from a team independent from IFC’s investment operations that is responsible for ensuring donor funds are used appropriately. / 177. At the project level, the unit will coordinate with investment staff in the field responsible for projects to ensure there is a robust pipeline in the countries of focus that meet the objectives and criteria of Initiative, and that projects, once booked are supervised appropriately. They in turn will coordinate with local teams. / Component 2 & 3: Advisory Services & Grants for Technology Solutions / 178. The two work streams of Component 2 (i.e. Capacity building of financial intermediaries and financial infrastructure) will be managed each by IFC’s current Global Programme Manager for each work stream and will be responsible for the coordination of related activities with regional specialists. Component 3 will be managed by the same programme manager that will oversee capacity building activities for FIs. Senior regional specialists supported by local teams will be responsible for developing client relationships, overseeing the delivery of projects once they have been structured and approved, and coordinating with other advisory and investment teams. We recognise the risk of potential conflict of interest in combining lending with technical assistance/advisory services. Care has been or will be taken during the design phase to build in mechanisms to avoid or manage potential conflict of interest. For example; the investment and advisory work will be done by different teams within IFC, and will have separate but well coordinated management, processes and governance. We also recognise that the blending of donor funds on concessional terms with commercial funds requires strong fiduciary controls and clear governance mechanisms. IFC has extensive experience and policies to manage those fiduciary responsibilities and conflicts, with separate teams responsible for ensuring that donor interests are protected. IFC is currently undergoing a review of its approach in light of the growth of this line of business to further strengthen its management of such funds. This Initiative Facility will follow all IFC corporate policies and principles established through that process. / 179. Selection of FI partners for Components 1 & 2. The process and criteria for selection of the PFIs are explained in detail from paragraphs 114-116 under the Procurement Case. Approval of individual projects will be handled via IFC’s regular advisory services project governance structure. Formal reports for all components will be delivered in consolidated form based on existing IFC project documents. / Performance Management / 180. DFID will undertake and or commission, with full support from IFC as required, annual Output-to-Purpose Reviews to assess progress, a mid-term review before end of year three, and an end-term Project Completion Review (PCR) to assess whether the targets in the Logical Framework have been achieved and, whether and to what extent the cost-benefit assumptions outlined in the Appraisal Case have been confirmed.
C. Conditionality / 181. If, during annual reviews of the programme, or at another time, DFID judges that the programme is seriously off-track or under threat, the programme (or component parts) may be suspended or terminated in line with DFID’s standard procedures. Overall the benchmark for poor performance/vfm will be if two or more Outcome level indicators fall short of targets by more than 30% at the Mid Term. In this case, DFID, in consultation with the Steering Committee, will reserve the right drastically to modify the programme course, strategies and partnerships or stop funding to the Initiative. Moreover, the performance management and monitoring arrangements for the programme will follow standard IFC processes/conditions per each component: / Component 1: Risk Capital: / 182. This Component will use IFC’s standard processes and procedures to approve projects, disburse funds and supervise projects. IFC will undertake rigorous due diligence and appraisal, covering the clients’ business planning and strategy, market and macroeconomic factors, credit issues, operational strengths and weaknesses, social and environmental issues, and reputational risks. The approval process will involve screening and scrutiny by IFC teams which are distinctly separate and not linked to its investment operations. Deployment of funds under this Component will be approved by the Investment Committee comprising of IFC, and a respresentive each from other DFI investors such as Kfw and EIB, ensuring that the criteria established by the donors is applied. Once approved, IFC commits to projects with documentation that includes extensive covenants and conditions for disbursement that ensure the investment remains viable and there are not material adverse changes to the situation of the client. Supervision is done on a quarterly basis, when covenants, agreements and reporting requirements are monitored for compliance. On the SME side, regular reporting is required with regards to the number and volume of SME loans that are issued, and covenants can be included to ensure that agreed targets are met. / Component 2 & 3: Advisory Services and Grants for Technology solutions / 183. All advisory projects (capacity building and grants) delivered under the Initiative will be subject to the same monitoring and evaluation indicator requirements as other IFC advisory projects. This includes the elaboration of appropriate monitoring and evaluation indicators and compliance with project supervision and project completion processes. Clients’ contributions are essential to ensuring client commitment and accountability to the project. / 184. In the case of grants, they will be documented through an appropriate Grant Agreement between IFC and the grant recipient, following IFC’s standard templates by IFC’s Legal Department. The Grant Agreement provides client accountability to IFC through conditions of disbursements of the grants which are triggered by the clients’/projects’ ability to meet pre-agreed conditions and/or reach target outcomes and performance results. The grant recipient is responsible for the contract of consultants to carry out the project as needed. / 185. The implementation of capacity building FI projects will follow standard IFC processes and be carried out through procured consulting firms or consultants, contracted by IFC with the approval of the FI client. No funds are disbursed directly to the clients. IFC oversees performance and monitors consultants in line with IFC’s standard Consultants’ Agreements for Advisory Services and through close follow up with the client. Conditions of disbursements for consultants will be based on the quality of consultants’ work including output-based deliverables which are pre-agreed with the consultants and the FI client as part of the Implementation Plan. / 186. In the case of Financial Infrastructure projects, IFC specialist teams typically execute standard IFC legal agreements with clients once a project has been established. These could be MOUs, Cooperation Agreements or Project Advisory Agreements. The Agreements establish project objectives, deliverables, timelines, roles of both the IFC team and the client, client fees (if any) and also establish performance monitoring metrics that the client commits to report on to IFC post-project completion. These metrics are in line with standard M&E indicators established for the different Financial Infrastructure products. Given the public benefit aspect of Financial Infrastructure Advisory, client cash contributions are fairly nominal and are frequently supplemented with in-kind contributions. In the delivery of financial infrastructure projects, no funds are disbursed to the client. The project leader monitors performance through regular follow up and contact with the client. In rare instances, where projects have stalled due to client inaction, the AS team may be required to pull out, after giving the client ample notice.
D. Monitoring and Evaluation / 187. The Initiative’s activities in monitoring and evaluation will be shaped to try to answer questions essential to the programme’s objectives and learning agenda. The main activities of the Initiative will centre on partnership with a number of selected banks and non-banking financial institutions. These activities as explained above (from paragraph 183 to 187) on the advisory as well as investment side will be designed and implemented by IFC as projects. / 188. The Initiative will design its M&E for a selected sample of projects with the highest degree of rigor possible, within the boundaries of working with commercial institutions in competitive markets and within a reasonable budget. Dissemination activities will seek to share lessons learned from the M&E work, but will also investigate larger questions that may be of some utility within the broader microfinance community. / 189. Recognizing the existing research and learning capacity resident within IFC (Development Impact Department) and the World Bank Group (Development Economics Research Group), as well as among leading research partners (Innovation for Poverty Action) currently active in the SME finance space, the programme will seek to tie the learning agenda into existing initiatives and to collaborate actively. The learning agenda will be shaped by a framework guided by two high level principles: / Delivery: what was the result against goals established at the outset of each project? / Impact: did the programme lead to measurable changes in jobs and other benefits we are targeting for in the given market? / 190. Underpinning each of these larger questions is a set of more specific questions that will inform the programme in monitoring, evaluation and dissemination. / Delivery: / Outcome achievement: have goals set out at the beginning of each project been met? Are there things that could have been done differently that would have improved results? How can approaches be adjusted based on lessons learned from projects implemented under this programme? To what extent has the programme contributed to helping clients build the data and evidence around jobs provided or outreach to underserved SME market segments? / Key success factors: what factors lead to sustainable and rapid growth, both internally and in the external environment? What are the key barriers to growth and replicability? What are the key attributes of institutions that have successfully scaled up? What have been the root causes of failure in institutions that have not been able to achieve sustained growth? What can be replicated across the regions or in similar markets? / Effectiveness of SME finance: does SME finance offer value for money in reaching scale over time? Which components and/or combination of components of the programme deliver the most effective results? How does this programme and/or its components compare with the rest of the market (using data from other available sources as a benchmark)? Do the benefits outweigh the costs, and which of the programme’s approaches or components best demonstrate this? / Approaches to SME product development: what factors drive successful SME product development strategies? What causes them to fail? What are the financial and developmental implications towards establishing long term sustainability? How can lessons learned feed into clients’ strategic vision of how they want to grow their businesses going forward? How does this experience compare across the regions? / Impact: / Profile: what is the business profile of a typical SME client of a partner financial institution? How has the programme affected SME clients after gaining access to financial services? / Purpose: what role does SME finance play in the target markets? Do the findings match the original assumptions/expectations regarding the benefits of SME finance? / Benefits of access: did access to SME finance help to improve the products, services and sustainability of business firms. Has SME finance provided jobs and other benefits, including improved economic opportunity particularly for women and the underserved? / Monitoring / 191. Projects supported by the Initiative will be designed to include a feedback process that allows IFC to strengthen design and implementation of its advisory services interventions. The IFC’s Monitoring & Evaluation Officer will be integral to the Project Team at the outset and plays a prominent role in decisions governing IFC’s monitoring & evaluation process throughout the project’s lifecycle. / Pre-implementation: in this stage, the Project Team addresses questions raised during the concept development stage, (e.g. market studies, potential client interviews). M&E focus is on reviewing objectives and respective logic framework, selecting relevant indicators, as well as sources and methods used for collecting of baseline data. The indicators selected on any given project will depend on component activities undertaken on that project as outlined in the Logframe in Annex 2. / Implementation: this stage covers the execution of project activities defined in previous stages. as well as semi-annual monitoring and supervision of progress against targets established at project inception. IFC will work with its clients and partners to incorporate core M&E indicators into their operations. The indicators are not only aimed at establishing the developmental outcomes of our interventions, but also in helping clients build the evidence to support their longer term sustainability and business proposition. / Post implementation: this stage involves a review of the project to assess the outcomes and impacts achieved in previous stages. Post-completion monitoring and in-depth evaluations are undertaken for selected projects consistent with the Initiative’s broader evaluation and learning strategy described above. / 192. Projects will be regularly reviewed by IFC’s project management team on the ground and complemented by corporate portfolio reviews at both the regional and product levels to assess overall progress against strategic targets, to harness lessons learned and to improve future initiatives. There will be Project Supervision and Completion Reports for each project supported by IFC under this Initiative. These reports will be subjected to review and validation by IFC’s Results Management Unit and a sample of these documents will be subject to independent audit by IFC’s Independent Evaluation Group. / 193. Project level reports will be aggregated to track progress at the overall Initiative level i.e. against the performance indicators in the Logical Framework. The Logframe will be a key mechanism to assess progress and performance of the Initiative. The baseline, mid and end-line columns have been populated based on the anticipated results delivery trajectory over the programme period. As implementation makes progress, milestones will be populated using process monitoring data available in periodic reports from the Initiative’s partner financial institutions and other partners. / Evaluation / 194. The programme’s overall evaluation and learning is built on a foundation of continuous monitoring for every project. As shown in the figure below, project monitoring will be incorporated from the earliest design stages and will run continuously through implementation and post implementation. The programme will engage in selected in-depth evaluations targeted at key learning questions outlined earlier. Both monitoring and selected project level evaluations will flow into an overall programme evaluation. The programme evaluation will incorporate baselines from all projects and engage in a mid term review half way through the implementation stage. The final programme evaluation will be done concurrently with the completion of the implementation stage. The learning programme will embody all elements of the programme and draw on information from monitoring and evaluation as well as ongoing lessons learned gleaned from IFC staff, project partners and consultants. / 195. Recognizing that the value-add to clients is greatest when learning can be shared in real time, the evaluation work will provide a more dynamic feedback process to improve operations or innovate products. Experimental or control group evaluation designs that rely on extraneous data or proxy measures and assumptions will be limited. These have proven to be expensive and hence their costs will be carefully assessed. The level of sophistication of evaluation methods will be defined by the characteristics of individual projects, and our partner institutions’ capacity to provide data and/or undertake in depth analysis. / 196. Evaluation will be an integral part of overall programme management, with different aspects carried out not only ex-post but concurrently with project implementation, building on the foundation of other routine performance measurement techniques, such as monitoring and direct supervision. The monitoring system is designed to track financial and social performance data that are useful for management and evaluators. Additional data required for evaluations will be collected in a way that minimizes extra work or costs to the institution and maximizes value in understanding the impact of their operations. The evaluation approach will apply a mix of quantitative and qualitative techniques and entails working at three levels of analysis: project, product and programme. The three levels of analysis are described below. / Project Level Analysis / Key Question: To what extent did we achieve our project objectives, and what can we learn about implementation and delivery? / 197. IFC will conduct project-level evaluations, employing a qualitative logic to determine which projects will be examined. The aim of the qualitative logic is to maximize the differences between projects evaluated so as to increase learning. Rather than concentrating on the representative sample of typical projects, IFC would select just one standard/typical project and [1-2] projects that differ on one or more dimensions from what we usually do. Variance of projects is maximized by purposefully choosing projects that differ from one another on a number of key characteristics, such as size, years of operation, client base, and political/economic context. . The evaluations are to be implemented in a staggered manner, in line with the natural unfolding of the programme. Doing so will increase learning by building cumulatively on the experience of previous or still ongoing evaluations. / 198. As explained above, evaluation of selected projects will consist of ex-ante, mid-term and ex-post stages which examine progress based on the OECD DAC[32] evaluation criteria (relevance, effectiveness, efficiency, impact, and sustainability) as well as IFC additionality and coherence with programme goals. The ex-ante evaluation is integrated into the project appraisal, and produces a comprehensive analysis of the institution that will serve as a baseline for subsequent evaluation stages. This integration is not only cost-effective and client–friendly, but is also key to early integration of M&E recommendations into project design (e.g. on IT/MIS improvements). / 199. This ex-ante data collection will provide the baseline against which the effectiveness of project delivery can be assessed. In particular, it will allow us to measure whether the project objectives are achieved as well as what we could have done differently to improve results. These data collection methods will be repeated at the mid-term and ex-post (one year after completion) stages with the same staff and clients. Monitoring data will feed into the analysis to produce a comprehensive picture of project performance. This is not an exercise that only provides lessons for future projects, but rather creates an iterative process that is intended to impact the actual implementation of the project being examined. By providing critical information at the mid-term, the evaluation will feed into project management, indicating positive actions that should be continued and raising questions about issues that need attention. / Product Level Analysis / Key Question: To what extent can the programme lead to measurable changes to our target population, for example in terms of expanding jobs supported and/or women-owned businesses? / 200. The analysis will look at the programme’s intervention through banks and NBFIs, as well as through credit bureaus and collateral registries. The programme would further assess the effectiveness of the use of risk sharing mechanisms, as well as technology based solutions to drive SME financing and development in the identified countries. Depending on the willingness and data collection capacity of our clients to engage with us on a deeper impact evaluation, IFC will conduct a quasi-experimental design. In these evaluations, we will conduct an endline (potentially also a mid-line) survey of the same sample. Sample size will be calculated once we have decided specific projects to be evaluated, including in particular the size of the total population covered by the evaluation. / Programme Level Analysis / Key Question: To what extent did this programme accomplish its overall objectives and contribute to broader development impacts? / 201. The programme level analysis will draw from both project and product evaluations. IFC will conduct a theory-based strategic evaluation of the entire programme, which provides an in-depth understanding of the workings of a programme or activity—the “programme theory” or “logic of intervention.”[33] This approach allows for complexity and does not assume simple linear cause-and-effect relationships. The evaluation coupled with field research will be conducted at years 1, 4 and 7 of the programme. The research done in year 1 will provide early feedback about what is or is not working, and why. It will also assist in the identification of unintended side-effects of the programme, and helps prioritize which issues to investigate in greater depth, perhaps using more focused data collection or more sophisticated M&E techniques. Hence it provides the overall framework for the project and product evaluations described above. It will also function as a meta-evaluation bringing together the findings of these individual evaluations in order to generate insights that are greater than the sum of the individual parts. By means of constructing an Intervention Logic, a graphic representation of the programme’s logical framework, the evaluation will map out the factors judged important for success, and determine how they might interact. Based on this mapping, a decision will be made as to which aspects should be examined through the evaluation as the programme develops. Specific Evaluation Questions on these aspects will then be developed and data collection methods defined. / 202. More specific evaluation questions and detailed evaluation work plan will be developed during the inception and initial implementation stage of the Initiative. It is intended that IFC will reach out to other agencies outside the WBG with a view to ensure greater objectivity and to leverage on resources from other organisations. To ensure consistency, the programme level evaluation will continue to be structured around the five OECD evaluation criteria plus IFC additionality and programme coherence, and would seek to address larger questions. IFC will use the information gathered through its monitoring and evaluation activities to support a comprehensive learning agenda for the programme. These lessons learned will be shared through the business line, the Smart Lessons programme, Investment Services teams and with other regional teams. Other pieces of learning will be externally focused, requiring different dissemination strategies and channels. External channels will consist of written materials, in the form of publications, research and knowledge guides, and face-to face interactions, supported through knowledge events.
E. Risk Assessment / 203. The programme is judged to be medium risk and high impact. Key risks are as follows: / Risk Description Probability Impact Mitigation Strategy / Lack of/limited development impact of the Programme Low Medium IFC has proven experience, technical expertise and adequate approval processes in place to select and work with local stakeholders and FI partners that will achieve the Programme’s set goals. Conditions for disbursement and milestones to be met will be negotiated with the client at the outset to create incentives for achieving results. / Deteriorating macroeconomic conditions: continuing slow economic growth in the global economy or another round of financial crisis Medium High Current unstable macroeconomic conditions at the global level may negatively affect the SME Finance Initiative’s ability to achieve the projected leverage for the DFID funds, as a result of diminished appetite from additional donors, DFIs and commercial investors to invest in the Initiative. This may lead to lower projected results if local and regional banks become more risk averse. External conditions will be monitored closely over the coming months to identify potential warning signs. Various scenarios are being evaluated by IFC in the event that conditions do deteriorate, to determine a revised course of action and expected results in coordination with DFID. However, in the event the there is substantial deterioration in the global macroeconomic conditions, the need for interventions similar to this Initiative will be even more. / Limited capacity by partner FIs to build up sizable, good quality SME portfolios Medium High The Programme will seek to work with strong banks in identified countries to stimulate competition, diversify the risk, and have a broader market impact. This risk is also mitigated by building solid performance indicators as part of the projects. There is a down side risk that (i) that PFIs will be more reluctant to scale up lending to SMEs, especially in the conflict affected states, and that (ii) PFIs scale up will last for the duration of the programme and it will not be sustained beyond the life of the programme. We have tried to address the first risk by setting a target that at least a quarter of the high level results are expected to come from the frontier markets. The capacity building support and development of financial market infrastructure will unblock systemic constraints and are expected to ensure that the Initiative’s deliverables will be sustained beyond its life. / Lack of stakeholder commitment and buy-in Medium High Would be mitigated by establishing stakeholder commitment to the process as a condition for involvement, and providing support for strengthening stakeholder buy-in through outreach and awareness work. Promoting cost sharing policies for advisory service activities with clients (per IFC’s advisory services guidelines), with a minimum client contribution of 20% of the project cost. / . / Capacity to deliver / Procurement challenges Medium High Capacity building of financial institutions and financial infrastructure require high levels of technical expertise. Given known challenges in identifying the right calibre of consultants, the IFC teams will have to make procurement a priority once partner institutions have been identified. / Partner FIs ability to develop and implement a comprehensive Environmental & Social Management System (ESMS) to manage the risks associated with onlending. Medium High IFC’s Sustainability Policy requires FI clients to develop ESMSs to manage the risks associated with their onlending. This risk based approach is captured in IFC investment agreements with clients and supported by a large team of IFC E&S Specialists based in Washington DC and in field offices who work directly with clients to ensure implementation of IFC’s policy requirements. IFC provides support to clients when in portfolio through onsite supervision and oversight of client E&S due diligence. / Potential conflict of interest between IFC’s investment portofilio and the deliverbales of this facility Low Medium We are proposing strong management and governance arrangements to address this risk. We have clearly defined the criteria for selection of PFIs and any change of those criteria will require to be approved by the Donor Steering Committee. The investment decisions of the SPV will be taken by the Investment Board which will have representatives of the other DFIs and we will have the opportunity to review the decisions through the Donor Steering Committee. Additionally, IFC will have an independent team reviewing the deployment of funds under the risk capital component of the facility to ensure it follows IFC’s internal guidelines on use of concessionality. / Political risk associated with the implementation of projects Medium High Many of the projects will take place in fragile and conflict affected countries, where the political risk is an important factor when embarking on projects, particularly the legislative reforms required for financial infrastructure. Given the close engagement with the public sector for financial infrastructure work, some practical mitigating measures to be taken by the project team(s) include being mindful of key political events (elections, other changes in government/decision making bodies) and not planning major reforms/changes around those times, since that could significantly delay (if not stall) implementation progress. Other steps to take are to continuously engage a wide range of stakeholders to ensure broad buy-in and commitment to reforms, so that such reforms are minimally impacted in case of political changes. In the event of highly disruptive and unexpected political events, the implementing teams would need to follow WBG protocol, keeping in mind safety of its personnel and contractors first and foremost. This might involve suspending work until the situation has stabilized. / Inability to find other donors for the Initiative Medium High This risk applies to donors of the capacity building and concessional components of the Initiative (commercial investors for the Investment vehicle have already been identified). There is a risk that donors that have indicated an interest in this Initiative will not deliver, or new donors will not materialize in order to reach an Initiative of the size that is being projected (i.e $3.5 – 4 billion). Lack of other donors is not expected to affect the results sought under this Programme, since the set targets are based only on DFID funds and the commercial leverage that they will provide to commercial investors already identified. Ongoing fundraising activities are also being carried out by IFC and the other commercial funders, as well as leveraging on the G20 process to ensure additional donor funding. / Non-performance by hired consultants Low Medium Based on IFC’s Advisory Services Guidelines, IFC retains a right to replace the resident consultant if the advisory firm fails to perform the consultancy work. The advisory firms have strong incentives to perform well in order to receive follow-up contracts under the Programme and/or IFC’s Advisory Unit.
5. F. Results and Benefits Management / 204. The Log frame includes a core set of indicators in each of the three components of the Initiative and these indicators will be tracked and reported on semi-annually, based on portfolio reports from the partner financial institutions and other relevant partners. These will be reviewed within IFC’s governance process and by the Steering Committee, and will be complemented by corporate portfolio reviews at both the regional and product levels to assess overall progress against strategic targets, to harness lessons learned and to improve future initiatives. / 205. Three scenarios were reviewed as part of the analysis of projected results under the programme, as explained in the Appraisal Case: the low case, middle and high case scenarios. The middle case scenario represents the most realistic projection, whereas the low and high cases represent a pessimistic and optimistic scenario, respectively. The table below summarizes the projected results from the programme under the three scenarios. / 1/ SMEs reached with the programme compared to overall number of SMEs with credit in SSA and SA / 2/ SMEs reached with the programme compared to overall number of under and unserved SMEs in SSA and SA / 206. It is likely that benefits from the programme would be back loaded over the programme duration. This is because the economies of scale and productivity gains inherent in the capacity building through technical support require a degree of saturation before outcomes are fully realised. Moreover, the facilities under development need to pass a ‘tipping point’ in their ability to accelerate benefits. This should be carefully considered at the mid-term review in year three. / 207. Results in the range of the high case scenario will be considered as overachievement, while results at or below the low case scenario would constitute programme underachievement. As previously mentioned, the factors affecting such outcomes are varied and include the speed of implementation of projects at the institutional level, speed of execution and reach of SME clients by FIs, and net profitability generated by the FIs. The speed of implementation of the programme can be more directly controlled and will largely depend on IFC’s ability to generate, approve and implement projects. Factors such as speed of FI execution and net FI profitability are less programme dependent and more closely linked to internal factors within the institution such as its ability to perform (including risk management practices, efficiency and cost control, etc) as well as external factors largely beyond the control of the institution (e.g. institutional, economic and political environment) . The programme will seek to address factors affecting the institutions’ performance through capacity building and advice. / 208. Given the size of the Facility and the importance of effectively managing development results, monitoring and evaluation, as well as disseminating key learning, dedicated budget is proposed under the Facility. This will further leverage IFC’s resources throughout its typical project and programme lifecycle for investment and advisory services interventions. Specific learning themes may further be agreed together with DFID as actual projects come to fruition under the Initiative.
[32] Organization for Economic Cooperation and Development – Development Assistance Committee
[33] The theory-based strategic approach has similarities to the LogFrame approach but allows for a much more in-depth examination.

Annex 1: List of priority countries
Priority Countries
No	Countries	Credit Bureaux	Collateral Registries	Financial Institutions Advisory	Risk Sharing Investment in FIs
	Sub-Saharan-Africa
1	South Sudan	+	+	TBC	+
2	Malawi		+	+	+
3	Ghana		+	+	+
4	Sierra Leone	+	+
5	Liberia	+	+
6	Uganda		+	+	+
7	DRC	+	+	+	+
8	Tanzania			+	+
9	Mozambique			+	+
10	Kenya			+	+
11	Nigeria			+	+
	South Asia
12	Bangladesh		+	+	+
13	India*		+	+	+
14	Nepal	+	+	+	+
15	Pakistan			+	+
	Other Potential Countries
16	Rwanda		+
17	Zambia		+		TBC
18	Afghanistan				TBC

*Note: The Initiative will cover India’s poorer states – Bihar, Uttar Pradesh, Madhya Pradesh, Orissa, Chattisgarh, Jharkhand, and West Bengal,

Annex 2: Logic of Interventions and Theory of Change:
Logic of interventions: Component 1

Risk sharing will enable banks to on-lend to new SMEs that they would otherwise not consider reaching without risk mitigation under this facility. Many banks in low income countries do not lend to SMEs due to a perception of high risk poor or non-existent credit history, and absence of tradable collateral. This component will provide cover to the PFIs against potential risk of default by their SME borrowers. This will reduce the potential losses to banks from SME lending and therefore incentivize banks to take more risks and increase their exposure in the sector. They also can make lending to productive SME segments a better alternative to government securities, which are lower risk but are often low-yield. We make an implicit assumption that either risk mitigation or capacity building alone would expand financing to SMEs incrementally, but that without combining them the ramp-up would be slower and the ability of the bank to truly reach new and underserved markets would be more limited. Given that best performing banks in the SME space usually generate only 40%-50% of their income from SME lending[34], coupling advisory services with the financing and risk mitigation will promote not only further lending but also a broader range of financial services for SMEs.

Logic of Interventions: Component 2:

Capacity Building for financial institutions: Banking with SMEs requires a different set of skills from the typical corporate oriented banking models. The traditional corporate banking activity is based on relationship banking: the large value of transactions in the case of big corporate can pay for the high transaction costs involved in relationship banking. Banking with SMEs require an industrial approach in reducing transaction costs through standardized products, streamlined processes and the use of technologies to enhance risk management. Capacity building support to develop and strengthen banks’ and NBFIs’ SME operations will focus on five strategic areas, based on best practices : (i) SME lending strategy and market segmentation; (ii) products design and development; (iii) improving sales culture and delivery channels; (iv) credit risk management; and (v) information technology (IT) and managing information systems (MIS). Building the capacity of banks in these key areas significantly increases the sustainability of their business and is shown to significantly increase the development effectiveness of their operations.

Financial Infrastructure: Credit Bureau can reduce the information asymmetry between SME borrowers and the banks by providing credit history information and referencing on the SME clients. Likewise Asset Registries enable lenders to register collateral easily can help enhance bank’s confidence in and ability to enforce the rights on the collateral. Credit bureau and Asset Registries can make information available to financial institutions at a more cost-effective way creating a common and sharable pool of information. Banks and financial institutions do not have to develop their own data gathering, compiling, cleansing and validating systems to get the information they need. This can help reduce the time taken by banks in screening and processing of credit applications because they can access more complete information than if they were to rely on their own data sources. Moreover, when both the credit bureau and the collateral registry are managed jointly or the systems are linked, economies of scale can also help reduce the cost of credit information both on credit history of borrowers and on collateral. This is expected to decrease information opacity, promote competition and reduce the underwriting risk of banks in the SME sector, given the reduction of risks in relation to adverse selection (e.g. lending to clients without knowing their credit history) and a reduction of moral hazard (e.g. SME borrowers will know that defaulting on their loans will affect their access to financial services in the future). In conclusion, financial infrastructure will help financial institutions grow more sustainably and help them avoid potential losses when becoming more operationally involved in the SME sector.

Endnotes