Annual Review – post April 2018

Title: Poverty and Growth Programme
Programme Value £ (full life): 4,500,000		Review Date: September 2018
Programme Code: 203508	Start Date: 22/7/2013	End Date: 28/12/2021

Summary of Programme Performance
Year	2014	2015	2016	2017	2018
Programme Score	B	A	A	A	A
Risk Rating	Minor	Minor	Major	Minor	Minor

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203508/documents
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5489984.xlsx

A. Summary and Overview

Description of programme
The Poverty and Growth Programme aims to improve prospects for economic reform by making the case for reforms in ways people can understand and by talking directly to policy makers. The programme aims to improve the likelihood of uptake of economic reforms through a mix of communication that reaches the general population and targeted advocacy work. At present, there isn’t strong enough support or demand for change on longstanding economic issues that are harming Pakistan. The main newspapers that are critical about economic policies have a narrow readership. Current affairs shows on television do not seem to be effective in getting across basic messages on tax reform, citizens’ duty to pay tax and other economic issues. The Poverty and Growth Programme attempts to shape grass roots opinion, directly interact with policy makers and operate at other levels in between e.g. with think tanks, civil society organisations and business.

The Poverty and Growth Programme (P&G, total cost £4.5 million) was approved in June 2013. Two components have been completed since then (combined cost of £3.0 million) and the final achievements, scoring and recommendations from these recorded in last year’s annual review. The first completed component, implemented by Adam Smith International, supported communications and advocacy activities for economic reform. Under this component, communication campaigns on television, radio, newspapers and social media helped raise awareness of tax reform and energy conservation issues. A panel of expert economists also advocated sound economic reform policies with political and government bodies; this included supporting the Senate Finance Committee’s ability to influence the national budget. The second completed component, implemented by the World Bank (WB), supported regional integration by assisting government and business in developing two free trade agreements and adopting a regional energy policy.

As anticipated in the 2017 annual review, new components have started in partnership with donor and private sector organisations on reform for economic development, responsible business and modern slavery. £858,000 remains unallocated. Two new components are:

Output 1: Support to the World Bank’s Pakistan@100 process (£369,000), a series of reports and events which will contribute to the debate on Pakistan’s main long term development challenges and opportunities – economic, governance, regional, environmental. It aims to articulate responses for Pakistan to become a successful upper middle income country by 2047 (when it turns 100 years old).

Output 2: Partnership with the Pakistan Business Council (PBC, £259,000) to advocate for improvement in responsible business practices, opportunities for women and disabled persons with businesses and with policy makers, including addressing modern slavery in business supply chains in Pakistan.

Summary supporting narrative for the overall score in this review
This annual review scores an A indicating that the programme’s performance is in line with expectations. The score reflects progress in setting up two new activities, one progressing strongly into implementation.

Output 1: Pakistan@100 (World Bank) Score – A+
- A flagship report is well on track for launch in January 2019 and is being written using a collaborative approach which is contributing to wider ownership of the initiative in Pakistan.
- Pakistan@100 has been highly consultative with the analysis and outputs reflecting consultations with government, major political parties, the international community, civil society, private sector and academia. The report will be discussed with the new government and disseminated widely.
- An outreach partnership with the Lahore University of Management Sciences has progressed well with a conference held on Pakistan@100, four academics selected for a Pakistan@100 Pre-Doctoral Fellowship programme an online knowledge management platform set up.

Output 2: Support to Centre for Excellence in Responsible Business (CERB), PBC – A
- Programme planning and operationalisation measures that were agreed for inception phase were assessed to be on track and according to expectation.
- The Accountable Grant is on pause while PBC and DFID agree if routine reporting to government required by PBC as a recipient of foreign funding is proportionate for a low value grant.

P&G is due to close in December 2021. Pakistan@100 activities will finish in 2019 having made the most of the opportunities to shape economic policies during the early part of the new government. If the Accountable Grant with PBC isn’t continued until 2020/21 as currently planned, DFID should decide whether to bring closure of the overall programme forward.

Recommendations for the year ahead

Recommendations relate to deepening progress under the Pakistan@100 programme of work, reviewing indicators at outcome level and agreeing the way forward for the Accountable Grant with PBC.
- Continue to undertake consultations with a wide set of stakeholders including engagement with the academic community in Pakistan to enrich the analysis and discussions, ensuring they are informed by latest thinking in the country.
- Understanding why some economic reforms are not implemented as planned is complex. Much of the information is not captured systematically and it is often difficult to organise knowledge on the political economy of reform implementation. As such, the focus of discovering why necessary reforms are not being implemented may be more of a longer term process, and the Pakistan@100 report can contribute to it.
- Outreach and communication activities on economic reform need significant planning, resources and specialised skills. There is a need to resource this part of the activity well, but also to start the planning process early enough and to ensure the necessary skills are available, both within World Bank but also with the institutions that World Bank is partnering.
- PBC and DFID will agree by March 2019 whether to continue or conclude the Accountable Grant.
- Outcome indicators for outer years will be added for both components after an impact assessment for CERB has been designed.
- If the PBC Accountable Grant is closed, DFID should also decide whether to bring forward the closing date for P&G earlier than 2021.
Glossary of acronyms

AG	Accountable Grant
CERB	Centre for Excellence in Responsible Business
DFID	Department for International Development
DFID P	Department for International Development Pakistan
EFO	Externally Funded Output (World Bank)
ETI	Ethical Trade Initiative
IDS	Institute of Development Studies
ILO	International Labour Organisation
INGO	International Non-Governmental Organisation
LUMS	Lahore University of Management Sciences
M&E	Monitoring and evaluation
NGO	Non-government organisation
P&G	Poverty and Growth Programme
PIDE	Pakistan Institute of Development Economics
PILER	Pakistan Institute for Labour Education and Research
PPA	Partnership Principles Assessment
PTI	Pakistan Tehreek-e-Insaf
SDG	Sustainable Development Goal
SDPI	Sustainable Development Policy Institute
VFM	Value for Money
WB	World Bank
## B: DETAILED OUTPUT SCORING

Output Title	Support to WB Pakistan@100
Output number per LF		1	Output Score	A+
Impact weighting (%):		50%	Impact weighting % revised since last AR?	Y – new output

Indicator(s)	Milestone(s) for this review	Progress
1.1 High quality analysis prepared in conjunction with Pakistani stakeholders	Consultation event with academia held to discuss seven thematic notes that are inputs to Pakistan@100 report	A+ / Seven thematic notes have been prepared, discussed at LUMS event in March 2018 and undergone internal quality review process at World Bank.
1.2 Analyses disseminated widely through outreach activities	An online platform for a Pakistan@100 Knowledge Management Centre set up	A / Online knowledge platform (website) set up in partnership with Lahore University of Management Sciences, currently being tested

Provide supporting narrative for the score
Pakistan@100 is an initiative to contribute to the implementation of necessary reforms to accelerate and sustain growth through analysis and the generation of debates and discussions. The premise for this work is a realisation that many necessary reforms are not being implemented because of political economy reasons, and an initiative that elaborates on these reasons and seeks way to address them, by involving a wide set of stakeholders, may be more successful than previous analytical efforts. The main activities under this output are preparation of a major report by the World Bank in partnership with the Lahore University of Management Sciences (LUMS) and its dissemination through a wide range of communication channels.

Output 1 this year scores an A+. The report is well on track for launch in January 2019. The areas that Pakistan@100 has focused on reflect consultations with government, major political parties, the international community, civil society, private sector and academia. The Outreach Partnership with LUMS has progressed well with a conference held on Pakistan@100, four academics selected for a Pakistan@100 Pre-Doctoral Fellowship programme and online platform set up. From the beginning an important element of this initiative has been outreach and communications, at least as important as the analysis being carried out to better understand what is constraining faster and sustainable growth. The initiative is being supported by an outreach partnership with the LUMS, but also collaboration with LUMS and other universities to carry out the research. This approach is contributing to wider ownership of the initiative in Pakistan. The consultation process for the concept stage was very wide and the consultations and communications with the policy notes and the overview report will be at least as wide.

Indicator 1.1 – A+: Consultation event with academia on thematic reports. A conference hosted by LUMS was held in March to discuss seven thematic reports. The reports are on: 1) growth and investment, 2) transformation in Pakistan’s economic structure, 3) poverty and equitable growth, 4) regional connectivity, 5) human capital, 6) environment and 7) governance. As well as the LUMS conference, the thematic reports have benefited from engagement with local and international researchers/universities including the Pakistan Institute for Development Economics, the Sustainable Development Policy Institute, the Institute for Development Studies (UK), and a number of local consultants. The thematic notes were reviewed through the World Bank’s internal peer review process in July with DFID technical advisers being peer reviewers for five of seven reports. The draft final overview report has been prepared and will undergo World Bank quality review in October.

Indicator 1.2 – A: Online platform for a Pakistan@100 Knowledge Management Centre set up. A Knowledge Management Centre has been set up by LUMS and is currently being tested. Under the Outreach Partnership with LUMS four fellows have joined LUMS to work on the outreach including converting the findings into policy actions. Post-launch debates will be held.

The team is conscious of the need to reach a wider segment of the population than is usually done with World Bank reports, particularly if the objective is to create demand for reforms. To that end, the team is engaging a number of partners to reach a wider audience, through a comic book to simplify some of the messaging, securing a partnership with a number of celebrities as ‘ambassadors’ of the messages in Pakistan@100, partnerships with media (TV, newspapers), etc. The World Bank has also engaged with the faculty at Cambridge University (UK) in a session to discuss preliminary findings and will continue to engage closer to the launch.

Lessons identified this year, and recommendations for the year ahead linked to this output

- Consultations at the concept stage with a wide set of stakeholders contributed to a strong engagement from donors, academia and other stakeholders.
- Engagement with the academic community in Pakistan has enriched the analysis and discussions in the policy notes, ensuring they are informed by latest thinking in the country
- Understanding why some reforms are not being implemented as planned is easier said than done. Much of the information is not codified and it is often difficult to systematise our knowledge of reform implementation. As such, the focus of discovering why necessary reforms are not being implemented may need to be more of a longer term process, and the Pakistan@100 report can contribute to it.
- Outreach and communication activities need significant planning, resources and specialised skills. There is a need to resource this part of the activity well, but also to start the planning process early enough and to ensure the necessary skills are available, both within World Bank but also with the institutions that World Bank is partnering.

Output Title	Partnership with Pakistan Business Council to promote responsible business practices and address modern slavery in Pakistan
Output number per LF		2	Output Score	A
Impact weighting (%):		50%	Impact weighting % revised since last AR?	Y – new output

Indicator(s)	Milestone(s) for this review	Progress
2.1 Set up implementation arrangements for Accountable Grant with PBC	Work plan for inception phase is agreed with DFID	Work plan for inception phase was agreed with the Centre for Excellence in Responsible Business (CERB)
	Due diligence action plan agreed and implementation initiated	The due diligence action plan has been approved by PBC Board and is being implemented.
	Technical and programme management staff is recruited for Centre for Excellence in Business (CERB), PBC.	Job descriptions developed and approved by the PBC Board. Recruitment currently on hold.
	Contacts made with with think tanks, NGOs, and research entities for future partnerships	CERB has established linkages with three leading organisations.

Briefly describe the output and provide supporting narrative for the score
The Centre for Excellence in Responsible Business (CERB) – part of the Pakistan Business Council (PBC) – has been established to advocate for improvement in business practices, opportunities for women and disabled persons, and addressing modern slavery in business supply chains in Pakistan. PBC is a research-based advocacy body that represents the largest private sector groups, both Pakistani and multinationals. It is a not-for-profit company established under Section 42 of the Companies Ordinance (1984).

An accountable grant agreement (AG) was signed on 15th May 2018 between DFID and PBC to support CERB. The AG will spend £259,000 over the next three years to enable CERB to work with PBC’s business membership and other businesses and also engage with policy makers. It will do this in partnership with other organisations such the International Labour Organisation (ILO), Pakistan Institute for Labour Education & Research (PILER), and the Ethical Trade Initiative (ETI). Activities this year have focused on setting up the implementation arrangements.

Output 2 scored an overall ‘A’ – programme planning and operationalisation measures that were agreed for inception phase were assessed to be on track and according to expectation. As a recipient of foreign funding via a DFID grant, PBC will be required to provide routine reporting to the Government of Pakistan on all of its activities (not just those funded by DFID). The transaction cost to put in place arrangements for this reporting is disproportionate for a low value grant. PBC and DFID are exploring the implications of this and will agree by March 2019 whether to continue the AG or to conclude it.

Indicator 2.1 – A: The work plan for the inception phase has been agreed with DFID.

Indicator 2.2 – A: All recommendations of the DFID due diligence assessment have been approved by the PBC Board and are expected to be implemented by year end. The conflict of interest, risk management, and whistle blowing policies have been drafted and approved by the PBC Board. The internal audit function has been strengthened and procurement module of the financial management software (Quickbooks) is being acquired by PBC.

Indicator 2.3 – A: Job descriptions of technical and monitoring and evaluation (M&E) experts have been finalised and hiring will be initiated in the implementation phase of the AG.

Indicator 2.4 – A: CERB has also made significant strides in building partnerships and reached out to the ILO, PILER, and ETI. CERB and ILO have agreed joint activities as well as capacity building of CERB’s staff. Synergies with ILO are clear and expected to strengthen during implementation.

CERB will continue its current programmes on responsible business. However, additional activities to be implemented with DFID resources will be paused, including staff hiring. No activity will be undertaken that accrues any expense to the AG. If implementation is resumed, the programme will start delivering on the following activities with agreed logframe indicators with businesses and policy makers:

1. Reducing barriers to decent work by encouraging the conduct of responsible business
2. Increasing diversity and inclusion by encouraging equal pay and opportunities for women and disabled persons
3. Supporting growth and increasing accountability in the supply chain by ensuring ethical practices through capacity building.

Lessons identified this year, and recommendations for the year ahead linked to this output

- PBC found the recommendations of due diligence assessment in the interest of the organisation and adopted them regardless of the future of the AG. If the AG goes into implementation by year end, DFID should support PBC’s institutional development to strengthen its potential to promote better businesses in Pakistan.
- PBC and DFID will agree by March 2019 whether to continue the AG or to conclude it.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

The two new activities are consistent with the theory of change in the original business case: by helping improve the use of research in public debate and decision making, DFID can improve the prospects of key reforms which are critical for faster growth and poverty reduction being adopted.

The challenge identified in the business case – and reflected in the design of Pakistan@100 – i.e. is how to ensure that the debate on how to deliver economic reforms is a conversation amongst Pakistani stakeholders. There is no formula that ensures that good research leads to sound policy. However, Pakistan@100 can help improve awareness of research and promoting public debate that demonstrates the need for reform.

The design of DFID’s support to CERB also reflects the evidence on what makes for successful advocacy interventions i.e. knowing what the barriers to change are, and being able to recognise entry points in a constantly shifting political environment[1]. PBC has successful experience of influencing the government on economic reform issues and concerns raised by its business members.
[1] Teles, S. and Schmitt, M. 2011. The Elusive Craft of Evaluating Advocacy. The William and Flora Hewlett Foundation.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

The outcomes for the new components reflect steps towards informing economic reforms by sharing findings with policy makers. Planned milestones have been achieved this year for Pakistan@100, for instance sharing preliminary analyses with political parties and with federal and provincial governments.

	2018 milestones	Progress
Inform public debates and policies	Preliminary analysis shared with main political parties and informed party manifestos	Preliminary analysis and findings was shared with the main three political parties. Discussions with the political parties also informed the Pakistan@100 team’s thinking.
	Preliminary analysis shared with provincial and federal governments	Preliminary analysis and findings was shared with the federal and provincial governments. Further discussions on the draft report are planned with the authorities in October.
Changed responsible practices in businesses	TBD following design of impact assessment

The analysis and draft material prepared for Pakistan@100 has been used to prepare several short notes shared with the incoming administration with recommendations for needed reforms. Work is also underway to disseminate findings of the analysis in line with the theory of chance. Research Fellows have started fellowships at LUMS during the summer of 2018 and will write opinion pieces on the issues raised in the report. A newspaper in Pakistan has agreed to write a series of op-ed pieces on Pakistan@100 when the report is launched – scheduled for January 2019.

Explain major changes to the logframe in the past year
Outputs and outcome indicators have been added to reflect new programme outputs.

Describe any planned changes to the logframe as a result of this review
Outcome indicators for outer years will be added for both components after the design of the impact assessment by CERB.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year
The two new activities were not appraised in the business case but the same principles of VFM at the levels of economy, efficiency and effectiveness for communications and advocacy activities apply.

Key cost drivers and performance
Economy: We have looked closely at the cost and quality of inputs and outputs as proposed in the business case. The main cost drivers for these two activities are technical experts, workshops, roundtables, communications and dissemination activities. Both budgets have been reviewed by DFID and negotiated downwards. Both World Bank and PBC have adequate financial management systems in place to ensure the economy of expenditures (see financial management section).

	2017/18	2018/19	2019/20	2020/21
Pakistan@100	369,000	0	0	0
CERB – Responsible Business	0	100,000	100,000	59,000

Efficiency: The main indicator of efficiency (how well inputs are combined into outputs) is the quality of reports and disseminations activities. For the World Bank this is ensured by a combination of 1) robust internal quality assurance processes for internal reports and 2) services contracts for subcontracted work whereby payments are only made for satisfactorily completed work. For PBC, the due diligence assessment recommended an additional subject matter expert be recruited to support CERB and ensure work with businesses and policy makers in this area is strong.

Effectiveness: Effectiveness will depend on uptake of new research by policy makers as a result of World Bank and PBC communication and advocacy activities supported by DFID. The business case noted that DFID would track policy uptake; the success of the programme would be judged by how well outputs translate into outcomes and impact. Indicators will be developed that link activities with changes in policy for the remainder of the programme, such as 1) numbers of newspaper articles, 2) assessment of uptake of ideas in social media, and 3) qualitative assessments of the policy impact of activities.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
P&G should continue as the two new components are low cost but potentially high impact and fit well with the wider portfolio. Changes in economic policies can have far reaching impact if compelling evidence, graphics and messages on economic reform get traction with policy makers. The timing of these activities – with a new government – means there is a new opportunity to shape economic decisions over a new political cycle. Pakistan@100 in particular has been implemented with a view to supporting a new government in making decisions about economic policy which are possible early in their tenure and will lead to sustainable reform. CERB can be expected to be effective in elevating messages on responsible business to policy makers in the same way PBC has on other economic issues. Both current activities fit well with DFID Pakistan’s other programmes especially support to economic reforms and work to eliminate modern slavery. The decision on whether to keep the current programme end date or to close early will consider VFM in the context of the wider portfolio.

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

Overview of programme risk
The overall risk rating has remained at Minor. The programme operates in a challenging environment as economic reform is both politically and socially a sensitive subject in the general population and within the government. Economic reforms are an emotive and often controversial subject in Pakistan. Safeguarding risk is low reflecting the main activities of research and advocacy. The main risks for both Pakistan@100 and CERB components are delivery, external and reputational.

Delivery Risk: Moderate.
- The main risk of this initiative is that it does not manage to influence policies. The focus on outreach and dissemination is part of managing that risk.
- A related delivery risk is that the analysis will not go deep enough into the ‘how’ of achieving reforms. This has partially been addressed through the focus of the analysis on understanding previous reform efforts, what worked and what didn’t and why not. More importantly, the preparation of the report is only the beginning of the initiative, while the focus on discussion and knowledge platforms, dissemination, wide outreach etc. will mean that discussions on what has worked and what not and why didn’t will continue much after the report is launched.
- For PBC the due diligence assessment identified that PBC’s capacity to deliver would be strengthened with additional subject matter expertise. This is being addressed by planned recruitment of an expert in responsible business.

External Risk: Minor.
- There is a risk that Pakistan@100 gets associated with a particular government or party. The World Bank has managed that risk by engaging with all political parties as well as federal and provincial governments.
- There is also a risk of limited government ownership of the reform agenda being suggested. At the concept stage the team discussed at length the proposed focus of the initiative, including with political parties and many stakeholders. The agenda of the Pakistan Tehreek-e-Insaf (PTI) government is very much aligned with the focus of Pakistan@100 which suggests that there may be ownership.

Reputational Risk: Minor.
As economic reforms are sensitive, there is a risk that DFID is associated with undue influence over economic policies through its work with donors (Pakistan@100). This risk is low, however, as work under the programme is technical, will be peer reviewedand communicated proactively.

Update on partnership principles
The Partnership Principles Assessment (PPA) is regularly discussed with the Economic Affairs Division, Government of Pakistan at the federal level. The PPA was last discussed in March 2018 during our Bilateral Assistance Talks. The PPA sets out DFID’s assessment of the Government of Pakistan’s commitment to the four partnership principles, as demonstrated through its policies and action for reducing poverty and achieving the Sustainable Development Goals (SDGs). These principles cover issues relating to human rights; financial management and corruption; and strengthening domestic accountability.

DFID Pakistan’s overall assessment is that the government is demonstrating a credible commitment to the four principles. DFID can therefore continue to plan and deliver sizeable programming on-budget. Progress towards the SDGs and poverty reduction is proceeding, albeit slowly, given the challenges. Progress on human rights is mixed. On public financial management and anti-corruption the direction of travel is broadly neutral, with some improvements in the areas of transparency on budgets, progress on audit and procurement, more openness on corruption and an appetite to tackle this at the highest levels. Elite capture and its influence are often cited as a concern.

P&G supports Pakistan’s commitment to reducing poverty and achieving the Sustainable Development Goals by promoting dialogue on the conditions for inclusive economic growth. The IMF-led international programme helped stabilise the economy between 2013 and 2016 facilitating higher growth. However, economic policy implementation has weakened since the end of the programme, eroding much of the benefit of stabilisation. P&G will support the quality of debate in Pakistan on economic policies required for sustaining long term economic growth and self-financing an exit from poverty.
F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues
The two initial core components of the programme were completed and reported on in the 2017 annual review. Two new components have been agreed during the last year. An Externally Financed Output (EFO) has been signed with the World Bank (for Pakistan@100 reports and events). (An EFO is a streamlined instrument for donors to fund World Bank interventions with a value less than $2m and which require limited monitoring by DFID.) An Accountable Grant has been agreed with the Pakistan Business Council for its Centre for Excellence in Responsible Business.

Performance of partners:
The World Bank’s Pakistan@100 analytical report is on track and is likely to be delivered within the time frame agreed in the EFO. DFID funds were fully disbursed in November 2017 and an annual financial and narrative progress report is expected in November this year. The key cost drivers include fees of technical experts, costs of consultative workshops, communications and dissemination of final report. The initial commercial proposal from the Bank was negotiated down from £400K to £369K. The technical papers drafted so far have been of good quality. The partnership between the World Bank and DFID has worked very well. The Bank has drawn on technical expertise from DFID and extensively with academia and think tanks in Pakistan. The partnership has been effective and the Bank has been responsive to incorporating DFID’s feedback on technical papers.

The World Bank is monitoring its implementing partners through regular interaction, identifying steps and monitoring progress primarily the LUMS, PIDE, SDPI, IDS, Cambridge University and consultants. The World Bank has used services contracts which have payments staggered; payments throughout the contract are only released upon satisfactory completion of the necessary progress steps.

PBC’s inception phase started on 15th May i.e. soon after signing of the AG letter. PBC has progressed inception phase deliverables well, notably the work plan and taking due diligence recommendations forward. PBC’s key cost drivers include core team salaries, commissioning and dissemination of research and survey reports and advocacy workshops and roundtables. PBC’s initial proposal was of £300,000 over three year period which was negotiated down to £259,000. PBC was ready to undertake implementation phase deliverables but has put activities on hold as set out under Output 2 (above).

DFID’s and PBC’s teams have established a routine of fortnightly telephone catch ups and quarterly meetings in person. The partnership is working well, and DFID has a good understanding of PBC’s inception and implementation plans, their approach towards developing partnerships with likeminded organisations and to risk management. DFID Pakistan has provided guidance to PBC on complying with DFID’s standard financial and narrative reporting requirements.

Financial performance: At the approval stage the total budget of the programme was £4.500m, out of which DFID has spent £3.384m and has committed £0.259m to PBC. This leaves the programme with an unallocated budget of £0.858m. DFID Pakistan should consider reducing the overall programme budget by the end of this financial year in case there are no other activities planned under this programme. DFID funds for Pakistan@100 were disbursed and committed upfront last financial year. PBC’s forecast for this financial year has been adjusted to reflect a pause on AG activities.

Audit:  As per the Externally Financed Output arrangement signed with the World Bank, there is no separate accounting or audit requirement for funds provided through EFOs as these are co-mingled with the World Banks’s own funds. The EFO is therefore subject to World Bank Group’s Single Audit Report which covers contributions from all of the Bank’s donor partners.   The Audit report for the financial year 2017 was received on 16 July 2018.   The report is unqualified with no observations. The first narrative report is due in November (one year after the EFO was signed). The report provides assurance that the Bank has strong Internal Controls over financial reporting.   PBC’s AG letter was signed in May 2018 therefore the audit is not due until 2019.

Date of last narrative financial report	Due in Nov 2018
Date of last audited annual statement	16 July 2018

G: MONITORING, EVIDENCE & LEARNING

Monitoring
Pakistan@100 is being monitored through regular meetings between the lead DFID economic adviser and programme manager and the World Bank team. Draft reports are also shared with other DFID advisers (economist, governance, social development, environment, human development). DFID advisers were part of the World Bank’s internal review for five of the seven thematic reports. Output and outcome level indicators are reported by the World Bank and verified by DFID. The World Bank’s Concept Note for Pakistan@100 sets out key deliverables and updates to plans are discussed with DFID. For PBC, a detailed logframe has been prepared by PBC which will form the basis of monitoring once implementation starts. The inception phase has been monitored by the lead governance adviser and programme manager.

Evidence
Evidence on the relationship between research on economic policies and implementation is reflected in the approach used under P&G and its theory of change. A qualitative assessment of Pakistan@100 could potentially add to existing knowledge on the conditions under which evidence is effective in supporting policy change e.g. consultation, quality of work, timing with political cycle, approach to dissemination.

Learning
Under Pakistan@100, lessons learned include consultation when undertaking communication/influencing activities and lack of systematic information on political economy of reforms:
- The value of undertaking consultations with a wide set of stakeholders to enrich the analysis and discussions, ensuring they are informed by latest thinking in the country.
- Understanding why some economic reforms are not implemented as planned is not captured systematically. Discovering why necessary reforms are not implemented is a longer term process which the Pakistan@100 report can contribute to.

Progress on recommendations from previous reviews
The main recommendation from the previous review, to decide whether to start new work on communications and advocacy by March 2018 has been undertaken.