Annual Review

Title: Yemen: Access, Logistics, Liaison and Accountability (YALLA), 2017-2020
Programme Value £ (full life): £33.77 million		Review Date: 3 October 2018
Programme Code: 300417	Start Date: 1 August 2017	End Date: 31 July 2020[1]
[1] This review takes place over a year since the programme’s start date. This is because funding covering August-October was agreed by DFID Ministers in advance of the initial Business Case submission, given the humanitarian imperative. However, this review covers the performance and results of the programme’s entire duration.

Summary of Programme Performance
Year	2018
Programme Score	A
Risk Rating	Major

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300417
DevTracker Link to Log frame:

A. Summary and Overview (1-2 pages)

Description of programme
The Yemen: Access, Logistics, Liaison and Accountability programme (YALLA) will fund over £33m across three years to provide technical expertise and logistics support to enable a more effective, accountable and coordinated humanitarian response, better access and improved flow of essential goods to alleviate the crisis in Yemen.

Yemen is one of the most challenging operating environments for the international humanitarian community, with an estimated 22 million Yemenis, roughly 75% of the population, in need of humanitarian or protection assistance.[2] Conflict dynamics heavily constrain the humanitarian operating space, requiring the UN to maintain a strong, strategic and accountable humanitarian system to coordinate an effective response at the scale required. Humanitarian actors face severe and unpredictable access constraints both to enter into and to travel within Yemen. The limitations and unreliability of commercial transport companies to reach Yemen by air, sea or land obliges the UN and its partners to rely on alternative solutions. Finally, Yemen is reliant on imports for fuel, medicine and 90% of its food. The UK’s financial and political support through this programme is designed to support access into and throughout Yemen, improving the impact of the international response and to increase import flows to help avert famine.
[2] Protection encompasses all activities aimed at ensuring full respect for the rights of the individual in accordance with human rights law, international humanitarian law. This includes protection against gender based violence, forced recruitment, and physical and mental suffering. https://www.unocha.org/sites/dms/Documents/120405%20OOM%20Protection%20final%20draft.pdf

There are six components to the programme under two pillars:
1. Improve the technical and coordination capacity of the UN-led humanitarian response.
  1. Support the core costs of the United Nations Office for the Coordination of Humanitarian Affairs (OCHA) to enable it to fulfil its role, including negotiating access in country. This includes paying for nine full time access negotiators and key leadership positions outside Sana’a to enable an effective response across the country (£3m since 2017/18)
  2. Provide rapidspecialist support to deliver DFID’s humanitarian portfolio, including UNVIM monitors in Djibouti and humanitarian advisors in London and Amman. (£1.6m since 2017/18)
  3. Strengthen UN performance through secondment of specialist staff to UN agencies. For example, specialist cholera supply expert into the World Health Organisation (£200,000 since 2017/18)
  4. Establish a feedback mechanism for beneficiaries to provide feedback to help guide and improve the humanitarian response (£0m since 2017/18).[3]
    [3] Component start date delayed until 2019/20, primarily due to limited management capacity on the DFID-side. More detail in Section F.

1. Improve commercial and humanitarian access into and within Yemen.
  1. Fund the UN Logistics Cluster[4] including the UN Humanitarian Air Service (UNHAS) to enable the transport of UN and NGO personnel and lightweight cargo into and out of Yemen, in order to deliver the response. Since December 2017, the UK has funded WFP to procure emergency fuel that UNICEF and WHO use for their humanitarian operations. (£11.77m since 2017/18)
    [4] The Logistics Cluster is responsible for providing common services across the humanitarian response (e.g. UNHAS planes, overland transport and cold chains. It is chaired and coordinated by the World Food Programme (WFP).
  2. Fund the UN Verification and Inspections Mechanism (UNVIM) to maintain and improve commercial shipping access and essential imports including food, fuel and medical supplies (£2.6m since 2017/18).

Summary supporting narrative for the overall score in this review

The YALLA programme scored an “A” in its first year. Programme risk is assessed as major. The programme succeeds the Enabling Environment programme[5], which ended on 31 July 2017. This meant the majority of outputs avoided any inception delays and performed from the beginning.
[5] https://devtracker.dfid.gov.uk/projects/GB-1-204016

Output one, core funding to the Office for the Coordination of Humanitarian Affairs (OCHA), did not meet performance indicator targets. While this does not indicate that the international humanitarian system was unable to respond to needs, there are clear areas of coordination, reporting and strategy requiring improvement. DFID Yemen should agree how best to support OCHA and the Clusters next year, including by offering technical expertise and additional capacity where needed.

There were two significant changes from the predecessor programme. First, responding to the severe fuel shortages in Yemen at the end of 2017, DFID provided the finances for a revolving fund managed by the WFP-chaired Logistics Cluster to procure and sell fuel to the humanitarian community to power generators for hospitals and water stations. Second, DFID expanded support to UNVIM through the provision of seven British experts to their operations in Djibouti. These experts were fundamental to increasing the frequency and improving the quality of UNVIM inspections of commercial ships entering red sea ports, thereby providing the Saudi-led Coalition (SLC)[6] additional assurances that no illicit items were entering Yemen on these vessels. Both additional interventions performed well, meeting their targets this year.
[6] The Saudi-led Coalition (SLC) consists of Saudi Arabia and a coalition of nine African and Middle East countries. The military intervention was launched by Saudi Arabia in 2015 responding to calls by Yemeni President Abdrabbuh Mansur Hadi for military support in response to Houthi takeover in Yemen.

Finally, through the Standby Partnership contract, this programme supported the deployment of six technical experts to UN agencies in Yemen. This included a cash expert into OCHA, a gender specialist into UNFPA and a logistical expert focused on the cholera response into WHO. While not measured in the logframe, this strategic support into the UN should be recognised as important in bringing about key decisions which shaped the response.

Recommendations for the year ahead
Theory of Change: The YALLA programme has supported many short-term gaps to strengthen the immediate response. To maintain strategic support to OCHA, and to prevent a web of parallel systems developing, DFID should develop a tailored theory of change showing the criticality of this programme to the wider international humanitarian response. Offers of temporary support and provision of technical expertise should be assessed based on the long term capability for it to be inherited by the humanitarian system.

- Improved information flow and needs analysis: DFID should work with OCHA to encourage the production of better-evidenced need analysis (for example, the 2019 Humanitarian Needs Overview and the Periodic Monitoring Review (PMR)). This will require greater engagement with OCHA at the technical-level to:
  - better understand approaches to needs assessment data collection, analysis and production
  - define information gaps within the response across key sector and thematic areas
  - identify the blockages to gathering and analysing needs data
  - build solutions to remove blockages and fill information gaps[7].
    [7] As outlined below this could include consideration of seconding technical expertise into the OCHA Independent Monitoring Unit, focusing on Humanitarian Affairs Officer and Information Management Officer roles (P3 and below) to bolster OCHA capacity

Coordination with OCHA Sana’a: Donors and OCHA Sana’a should have monthly meetings to improve communication and greater clarity and transparency on OCHA’s planning for needs assessments. The UN Humanitarian Coordinator[8] (UNHC) recently invited donors to be members of the Humanitarian Country Team (HCT)[9]. DFID must use this conduit to gain more clarity and transparency on the Humanitarian Programme Cycle for Yemen, in particular on processes related to the preparation of future Humanitarian Response Plans and their revision.
[8] The United Nations Humanitarian Coordinator/Resident Coordinator (HC/RC) is the highest United Nations official and the chief of UN diplomatic mission in a country. The position of HC and RC is combined in Yemen.
[9] The Humanitarian Country Team (HCT) is a strategic and operational decision-making and oversight forum established and led by the HC. . Composition includes representatives from the UN, international NGOs and the Red Cross/Red Crescent Movement

- WFP Fuel Facility:
  - DFID should maintain the WFP fuel revolving fund as long as the UN Agencies WHO and UNICEF consider it a high priority to keep water treatment plants and central hospitals’ generators running. DFID should support WFP’s ongoing effort to extend this facility to the provision of A1 Jet fuel at Sana’a airport for the use of UNHAS, UN Special Envoy, ICRC and MSF flights.
  - Fuel is a central commodity in Yemen’s war economy. WFP is aware of the high risk of aid diversion and extortion, and has completed a thorough due diligence on its fuel supply chain. To reinforce this, the UK should share relevant elements of its war economy analysis with WFP to strengthen WFP's understanding and navigation of fuel sector dynamics in to help with risk management.

UNVIM: The UK should continue its support of UNVIM which has played an important role in maintaining commercial imports of food and fuel into red sea ports. In addition, its funding of inspectors has increased physical inspections by at least seven-fold. The UK should continue its role on the steering committee. This is vital to improve processes and understanding between UNVIM, Evacuation and Humanitarian Operations Committee (EHOC) and commercial importers.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	The international humanitarian system supports coordination and strategic decision making and the ability to plan for and respond to needs
Output number per LF		1	Output Score	B
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress	Met?
1.1: Key humanitarian programme cycle deliverables (e.g. Humanitarian Needs Overviews (YHNO), Yemen Humanitarian Response Plans (YHRP), and Periodic Monitoring Reviews (PMRs)) endorsed by the Humanitarian Country Team (HCT) in a timely manner.	December 2017: YHNO published and endorsed by the HCT. / January 2018: YHRP published and endorsed by the HCT. / May 2018: Periodic Monitoring Review (PMR) published.	December 2017: YHNO published. / January 2018: YHRP 2018 published. / No Periodic Monitoring Review was produced in 2018. / Additional UN appeal “Countrywide Preparedness Plan” was produced but not shared with donors. / Revision of YHRP 2018 announced but not yet made public in the time of writing this review.	Not met expectations
1.2: Core OCHA Yemen products (Humanitarian Bulletin, 3Ws (what, where, when), Funding Update; and Humanitarian Dashboard) published by OCHA Yemen in a timely manner	Target number of reports between November 2017 and October 2018: / Monthly 3W - 11 / Monthly Bulletins - 11[10] / Monthly Funding - 11 / Bi-monthly Humanitarian Dashboard - 6 / Weekly Humanitarian Update – 36	Actual number of reports between November 2017 and October 2018 / Monthly 3W - 6 / Monthly Bulletins - 2 / Monthly Funding - 6 / Bi-monthly Humanitarian Dashboard - 3 / Weekly Humanitarian Update – 22	Not met expectations / Actual Vs. Target / Monthly 3W – 67% / Monthly Bulletins – 22% [83% before ceased] / Monthly Funding – 67% / Bi-monthly Humanitarian Dashboard - 75% / Weekly Humanitarian Update – 92%
1.3: The humanitarian leadership is informed by national and sub-national coordination bodies, ensuring effective humanitarian action.	October 2018: Weekly HCT, fortnightly Inter Cluster Coordination Mechanism (ICCM)	Not met: Actual number of HCT meetings between November 2017 and August 2018 was 29, an average of 3 per month. / Met: Actual number of ICCM meetings between November 2017 and August 2018 was 22,an average of 2.2 per month	Not met
[10] After January 2018, OCHA replaced their monthly bulletins with weekly updates. The log frame was not updated to reflect this, and requires amending in the next reporting year.

Provide supporting narrative for the score

This output has scored an overall B – outputs did not meet expectations. Throughout the review period, the Office for the Coordination of Humanitarian Affairs (OCHA) did not meet the agreed performance indicator targets. While this does not indicate that the international humanitarian system was unable to respond to needs, there are areas of coordination, reporting and strategy which require improvement.

Indicator 1.1 – Not Met Expectations
Both the 2018 YHRP and the YHNO were published in a timely manner to shape the 2018 humanitarian response. Conducting needs assessments in Yemen remains severely constrained by parties to the conflict, which hinders both the quality as well as the quantity of assessments carried out. In November 2017, the Humanitarian Needs Overview had to draw quite substantially from the “Delfi” methodology meaning that extrapolation was used for districts for which no recent and/or reliable data was available to assess needs. Despite this, there were some assessments made, the findings of which contributed to a better evidence-base for the 2018 YHNO and YHRPs.

No Periodic Monitoring Review was produced in 2018. We expected a PMR to be conducted this year as the April 2017 PMR proved a useful tool for the revision of YHRP 2017. The PMR was expected to re-assess acute needs across Yemen, six months after the release of the December 2017 YHNO and halfway through the implementation of YHRP 2018. Instead, the UNHC decided to put the HCT and clusters’ focus on the Hodeidah Response as well as a Countrywide Multi Sector Preparedness Plan, but this plan has not been shared with donors to date. In June 2018, the UNHC asked the Clusters to prepare a reprioritisation of the YHRP 2018 with a view to direct donor funding towards the most pressing needs in hard to reach areas. More recently, the UNHC announced that the YHRP would be revised, not in terms of substantial reassessment of the extent of the needs, but by incorporating activities that were not included in the January YHRP. This revision has not yet been made public.

Indicator 1.2: Not Met Expectations
This indicator is intended to measure the core products and reports produced by OCHA for the international community. The indicator does not capture the full range of products, including flash updates and specific thematic or sector reports (for example, on access), but focuses on specific types of reports. OCHA did not meet its cumulative targets per product between August and September, issuing on average 4 reports per month. Results are skewed towards Q3 and Q4 due to the introduction of the weekly humanitarian updates.
Number of OCHA reports issued by the type and month (Aug 2017 - September 2018).[11]
	Aug	Sept	Oct	Nov	Dec	Jan	Feb	Mar	Apr	May	Jun	July	Aug	Sept
Monthly 3Ws	1	0	1	1	1	1	1	0	0	1	0	1	0	2
Monthly Bulletin	1	1	1	1	0	1	0	0	0	0	0	0	0	0
Monthly Funding Update	1	0	1	1	1	0	1	1	0	0	1	1	1	0
Bi-monthly Humanitarian Dashboard	1	0	1	0	1	0	1	0	0	1	0	0	1	0
Weekly Humanitarian Update	0	0	0	0	0	0	4	4	4	4	2	4	4
Total # of reports per month	4	1	4	3	3	2	7	5	4	6	3	6	6	2
[11] Reports captured in the table captures the report by release and posting date rather than on reporting period.

 Overall, there is inconsistency in the frequency, type and quality of reports issued and when. There is not an obvious pattern in the publication of reports, which affects situational understanding and thereby decision making as the humanitarian community is reliant on OCHA to provide an up-to-date common operational picture. In addition, reports frequently do not show consolidated numbers, reflect the scale of the issue they report, and situational reports (sitreps) on an emerging emergency are not published promptly after the event takes place. This again impacts the international community’s ability to make policy or programming decisions which adequately respond to the situation on the ground.

Indicator 1.3: Did not fully meet expectations.
OCHA intended to hold fortnightly meetings of the Inter Cluster Coordination Mechanism (ICCM).[12] Over the ten month period (November 2017 – August 2018), there were 22 ICCM meetings organised in Sana’a and chaired by OCHA. This objective was therefore attained.
[12] Inter-Cluster Coordination mechanism is the cooperative effort among sectors/clusters and the HCT to assure coherence in achieving common objectives, avoiding duplication and ensuring areas of need are prioritised.

Both present and former UNHCs have opted for a weekly meeting of the Humanitarian Country Team.[13] There were 29 HCT meetings organised over the 10-month period November 2017 – August 2018 with a high 5 HCT meetings in January 2018 and a low 1 HCT meeting the month before. On average 3 HCT meetings were organised every month between November 2017 and August 2018 and this objective was therefore not met. The objective of one HCT meeting every week is probably ambitious and it seems that the UNHC is currently aiming at 3 HCT meetings per month. It is therefore suggested to update the logical framework target accordingly for the following reasons:
[13] Chaired by the acting UNHC when the UNHC is not in country
One of the former UNHC’s priorities was to decentralise Sana’a humanitarian coordination mechanism by developing inter agency and cross cluster coordination across the newly established hubs. Area HCT’s were established and many regional coordination meetings were held in the 5 hubs.

HUB	FREQUENCY OF RCT/AHCT MEETINGS	ESTIMATED NO. OF MEETINGS IN LAST 12 MONTHS / (Sept 2017 – Aug 2018)
SANA’A	Monthly	17 / (12 regular and 5 ad hoc meetings)
ADEN	Every two weeks	25
HUDAYDAH	Every two weeks	26
IBB	Weekly	52
SA’ADA	Monthly	12 / (10 regular 2 ad hoc meetings)

A new UNHC has been in place since March 2018. She opted for the establishment of an Emergency Cell[14], which is considered good practice in a Level 3 response. The Emergency Cell proved useful in activating a rapid response action around the Hodeidah /Western Coast crises as of early June 2018. This new coordination structure is complementing the work of the HCT and does not supersede it. The UNHC/RC intends to maintain this Emergency Cell beyond the scope and duration of the Hodeidah crisis.
[14] The UN Emergency Cell is a core group of UN and INGO decision makers in Yemen who meet regularly (daily) in times of escalating conflict. It is chaired by the UNHC or a Deputy.
Emergency Cell Meetings
MONTH	No. OF MEETINGS
March 2018	0
April 2018	1
May 2018	5
June 2018	13
July 2018	8
August 2018	5
Total since EC was established / (April 2018 – Aug 2018)	32

It is also important to note that an Emergency Operation Room was established in support to the Hodeidah crisis response, chaired by OCHA. Addressing priorities at the more technical level, this additional OCHA-chaired coordination mechanism has proven useful in addressing day to day constraints to a smooth implementation of the Hodeidah crisis response.
EOR Meetings
MONTH	No. OF MEETINGS
June 2018	10
July 2018	13
August 2018	10
Total since EOR was established / (June 2018 – Aug 2018)	33

Lessons identified this year, and recommendations for the year ahead linked to this output
Provision and analysis of information on the humanitarian situation and response has been a perennial challenge throughout the Yemen crisis.[15] Access continues to be a major constraint, affecting UN and NGO ability to conduct regular independent needs assessments and collect data. Obtaining authorisation to launch large-scale formal surveys is impossible in some parts of the country. Information sharing is one of OCHA’s key functions and it is their duty to ensure the inter-cluster system works well and compiles regular reports. However this requires collaboration and input from the clusters: both UN agencies and NGOs. We must therefore continue to push OCHA to improve its reporting, whilst recognising that the Clusters must also be held to account and require support to improve capacity.
[15] OCHA and the Inter Cluster Coordination Mechanism (ICCM) are also let down by limited communication from the clusters. While its clear that much information exists it is not systematically collated, analysed and shared at ICCM level.

DFID Yemen has seen recent progress on information management within OCHA and several new products have been introduced (including weekly humanitarian updates). However, Donors need to continue to work closely with OCHA on developing quarterly measurement of humanitarian indicators and trend analysis. This includes developing a core set of information asks for OCHA to produce. For example, weekly updates to be published in a timely manner together with a monthly cumulative look at trends.

DFID Yemen should agree how best to support OCHA and the clusters, by offering technical expertise and additional capacity where needed and/or by working with other donors to identify gaps and funding needs. A rapid, light-touch review of information gaps and blockages has already been completed by DFID Yemen, with plans to undertake a more comprehensive assessment and subsequent engagement with OCHA on the findings underway.

Data gathering and analysis remains weak on Yemen. A new DFID partnership with ACAPS[16] and Catapult[17] is in the process of being established to strengthen information and complement OCHA’s products. ACAPS and Catapult will not duplicate OCHA core information products and any new areas of analysis and subsequent information products issued by will be discussed with OCHA to avoid duplication and ensure clarity on roles and areas of focus. [18]
[16] ACAPS is a non for profit organisations providing indepdent humanitarian needs analysis and assessments, supporting the international community to provide better evidence-based responses to affected communities. https://www.acaps.org/
[17] Catapult was established by Innovate UK. It provides access to expert technical capabilities, equipment, and other resources required to find innovative ideas to complex problems (e.g. needs assessments in Yemen) - https://catapult.org.uk/about-us/about-catapult/
[18] OCHA are receptive to ACAP and Catapult role within the Yemen response, however DFID will need to support engagement and partnership between the agencies

UK core funding and UK policy objectives with OCHA go hand-in-hand to ensure maximum impact. Over this reporting year, key asks of OCHA have frequently been dropped or changed as new priorities emerge. This has resulted in disjointed UK lobbying of OCHA, and also means no systematic assessment of OCHA’s progress and challenges has taken place. For example, UK lobbying OCHA to recruit access negotiators in regional hubs has been replaced by de-confliction asks. DFID Yemen should also agree one key focal point to engage with OCHA Sana’a.
It is recommended to adjust the target for national HCT meetings down from 4 to 3 per month in the logical framework. The number of HCT meetings held during this period does not adequately reflect Humanitarian leadership, which was not only informed by national but sub-national coordination bodies as well.[19] The combination has ensured effective humanitarian action over the period August 2017 – September 2018.
[19] DFID should consult OCHA on whether to add an indicator on the number of sub-national coordination meetings

DFID should update Indicator 2.1 to reflect the actual reports OCHA now issue. Specifically, OCHA dropped their monthly bulletins from February 2018 onwards and replaced it with weekly humanitarian updates.

Output Title	The International humanitarian community has access to a safe, reliable and predictable air transport service to and from Yemen by pre-agreed routes
Output number per LF		2	Output Score	A
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress	Met?
2.1 # UNHAS flights to/from Yemen per month.	Average of 20 flights per month	Q1 (Aug 2017 – Oct 2018): 37 flights / Q2 (Nov 2017 – Jan 2018): 20 flights / Q3 (Feb – April 2018): 29 flights / Q4 (May-July 2018): 32 flights / Q5 (Aug – Sept 2018): 30 flights	Exceeded expectations
2.2 Total passengers transported per month	Average of 800 passengers per month	Q1 (Aug 2017 – Oct 2018): 959 passengers / Q2 (Nov 2017 – Jan 2018): 444 passengers per month / Q3 (Feb – April 2018): 854 passengers per month / Q4 (May-July 2018): 962 passengers per month / Q5 (Aug – Sept 2018): 899 passengers per month	Met expectations
2.3 % seat occupancy rate	Above 90% seat occupancy rate per month	Q1 (Aug 2017 – Oct 2018): / Amman-Sana'a 80%; Djibouti-Sana'a 65% Djibouti - Aden 17% / Q2 (Nov 2017–Jan 2018): / Amman-Sana'a 47%; Djibouti-Sana'a 34% Djibouti - Aden 16%. / Q3 (Feb – April 2018): Amman-Sana'a 70%; Djibouti - Sana'a 51%; Djibouti – Aden 31% / Q4 (May-July 2018): / Amman-Sana'a 86%; Djibouti - Sana'a 61%; Djibouti – Aden - 29% / Q5 (Aug – Sept 2018): / Amman-Sana'a 86%; Djibouti - Sana'a 61%; Djibouti – Aden - 29%	Not met expectations

Briefly describe the output and provide supporting narrative for the score

This output has scored an overall A – outputs met expectations. Throughout the period under review, the humanitarian community was able to maintain access into Yemen through the transport of international and national humanitarian staff and light-weight cargo.

Indicator 2.1 – Exceeded Expectations
The number of flights exceeded the target of twenty, ensuring that the international humanitarian community had access to a safe and reliable means to enter and leave Yemen.

The number of flights was lowest during the Q2 (Nov 2017 – Jan 2018) period. Due to the clashes taking place in Sana’a, the UN Designated Official[20] relocated less-critical international staff to Djibouti and then onto Amman. UNHAS successfully operated four flights in one day with its two aircrafts, successfully transporting 124 international staff from Sana’a to Djibouti in December. Due to the prolonged instability in Sana’a after these events, UNHAS aligned the December schedule with the decreased international staff cap that was instituted for Sana’a and northern Yemen, carrying out one flight per week from Amman to Sana’a, and one flight per week from Djibouti to Sana’a.
[20] The Official who stands in for the UN Humanitarian Coordinator when they are absent for the country. In Yemen, this is usually the Director of the largest Agency.

Indicator 2.2 – Met Expectations
With the exception of Q2, the number of passengers using UNHAS services on a monthly basis exceed the target of 800. The reason for the variance in Q2 was due to the drawdown of international humanitarian staff towards the end of 2017. There are currently three routes operating into Sana’a and Aden: two from Djibouti and one from Amman. So far in 2018, UNHAS flights have serviced at least 16 UN agencies and 26 INGOs, and just short of 7,500 passengers.

Indicator 2.3: Not Met Expectations
The Aden route has had a low utilisation rate, which contributed to this output not meeting target. This is due to a decreased demand as a result of both Yemenia Airlines and Djibouti Airlines now operating regular passenger commercial flights to Aden which many NGO staff take advantage of. As per UNHAS worldwide regulations, UNHAS should not compete with commercial flights and UNHAS have stated that they will reconsider the operation of this flight route if utilisation continues to stay under 50%.[21] However, currently neither Yemenia nor Djibouti Airlines fit UN aviation standards and UN staff are not allowed to travel with these companies. The VOS Apollo also does not offer an appropriate alternative due to the relative infrequency of the service and its limited capacity. Therefore despite the lower utilisation rate, this flight route is likely to continue. DFID should also consider whether a target of 90% occupancy rate for this output is too ambitious and should be revised to take into consideration space given to light weight cargo on the flights.
[21] This decision would need to be taken by the UNHAS Steering Committee, on which UK has a seat.

Lessons identified this year, and recommendations for the year ahead linked to this output
UNHAS remains an essential service allowing the agencies and NGOs to move in and out, stay and operate in Yemen. There is no viable alternative, either by air or sea transport, to replace an air service that transports over 800 humanitarian passengers every month and offers a reliable evacuation means. The use of Sana’a and Aden airports for humanitarian air services must therefore be preserved. For the Aden-Djibouti flight route the UN should ensure the most appropriate plane is assigned for the lower occupancy route and look at options to work with existing commercial airlines at the potential to gain clearance for UN aviation standards.

The limited availability of Jet 1 aviation fuel in Sana’a airport continued to be one of the most significant logistical challenges threatening direct UNHAS flights from Sana’a to Amman (refuelling on other routes is either made in Djibouti or Amman). UNHAS have managed through WFP to successfully secure a contract with the Yemen Petroleum Company (YPC) in Aden, whereby fuel is trucked from Aden to Sana’a periodically. However, given the risks involved in transporting - this is clearly a last resort solution. The UK has recently agreed to use our fuel contribution (outlined in output 3) to fund a buffer stock of A1 fuel in Sana’a to reduce this risk. The UNHC and the Office of the Special Envoy[22] should be encouraged to keep looking at safer and more sustainable solutions to ship A1 jet Fuel to Sana’a airport for the use of the Humanitarian flights.[23]
[22] The UN Special Envoy is a senior UN official appointed by the UN Secretary General to deal with a set of specific issues. In the case of Yemen this is to lead the mediated peace process.
[23] A1 jet fuel is used by UNHAS flights, as well as flights operated by MSF, ICRC and the Office of the Special Envoy.

There have been ongoing negotiations between the UN and the relevant authorities in the North and the South to allow for direct Sana’a to Aden flights. This flight path was agreed earlier this year.[24] UNHAS is trialling a new rotation Djibouti – Aden – Sana’a – Aden – Djibouti, and the UK should support these ongoing efforts to ensure that if this route is cost-effective, it can continue.
[24] This route has had some challenges. Specifically, customs issues mean that while it is possible for passengers to travel from Aden to Sana’a and vice-versa, it will not be possible for a passenger to travel from Djibouti to Sana’a, transiting in Aden. Such passengers will need to use the regular Djibouti – Sana’a – Djibouti flight route.

UNHAS services were fully funded in 2018, owing to the large commitment made by Saudi Arabia and the United Arab Emirates. DFID should work with WFP to ensure UNHAS and the Aden boat services continue to be funded in 2019.

Output Title	Flow of commercial goods to Yemen, including food, fuel, and medical supplies is supported by UN Verification and Inspection Mechanism
Output number per LF		3	Output Score	A+
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress	Met
3.1 Average time taken for applicant ships to be verified or referred for inspection, following receipt of documentation	Monthly average under 48 hours	Q1 (Aug-Oct 2018): 29 hours / Q2 (Nov 2017 – Jan 2018): 28 hours / Q3 (Feb – April 2018): 29 hours / Q4 (May-July 2018): 18 hours / Q5 (Aug – Sept 2018): 24 hours	Exceeded expectations
3.2: Proportion of vessels that applied for clearance inspected by UNVIM	At least 40% of ships applying for clearance are inspected by UNVIM	Q1 (Aug- Oct 2018): 43% / Q2 (Nov 2017–Jan 2018): 19% / Q3 (Feb – April 2018): 70% / Q4 (May-July 2018): 79% / Q5 (Aug – Sept 2018): 68%	Exceeded expectations
3.3 Number of UK inspectors contracted to be deployed to Djibouti and regional hubs	7 UK inspectors deployed	Q1 (Aug- Oct 2018): N/A / Q2 (Nov 2017–Jan 2018): 5 deployed / Q3 (Feb – April 2018): 6 deployed / Q4 (May-July 2018): 4 deployed / Q5 (Aug – Sept 2018):	Partially Met expectations (there were 7 UK inspectors on the roster – not necessarily deployed at all times).

This output has scored an A+ – outputs exceeded expectations.
This output measured how the UN Verification and Inspection Mechanism (UNVIM) supported the continued flow of commercial goods into Yemen’s Red Sea Ports. Throughout the reporting period, UNVIM was able to verify, inspect and clear commercial vessels over 100 metric tonnes headed to the ports in line with UN Security Council Resolution (2216). There was a significant drop in the levels of food and fuel imports at the end of 2017. . This is attributable to the knock on effects of the interdiction imposed on Yemen by the Saudi-led Coalition (SLC) after the ballistic missile attack.. UNVIM increased its inspections of vessels during this period in order to offer greater assurance to the SLC. The import picture has improved over the reporting period although fuel overall through ports remains down. This is discussed further in Section C.

Performance on Indicator 3.1 has exceeded expectations. UNVIM met this output, averaging well below the target 48 hours pre clearance process. Predictable and quick clearance times by UNVIM, and improved communication from the UNVIM team on anticipated delays provided shipping companies with confidence in this part of the clearance process.

Performance on Indicator 3.2 has exceeded expectations, with a four-fold increase in the percentage of vessels that applied for clearance being inspected from Q3 and onwards. The increase in the proportion of vessels being inspected became a UK priority at the end of 2017 in order to offer the SLC assurances that UNSCR 2216 was being effectively implemented and therefore that restrictions on the port could be lifted. By April 2018, 91% of all vessels that applied for UNVIM clearance were inspected. However, the high rate of inspections raised concerns amongst key importers around the extra time and cost for repeated inspections and the procedure for identifying which vessels required inspections. Following review and proposals made by UNVIM, the SLC and the wider UNVIM Steering Committee agreed to the adoption of a risk based approach to identifying which vessels required inspections. For example, vessels that travelled to Yemen on a regular basis and contracted by reputable shipping lines did not always need to be inspected.[25] This resulted in a fall of the proportion of vessel inspections to 56% in June 2018. However, in part due to the escalation of the conflict in late summer 2018, inspections increased again – with all vessels applying for clearance being inspected in August 2018.
[25] As agreed in UNVIM Steering Committee in April 2018.

Performance on Indicator 3.3 has partially met expectations, with the number of UK inspectors contracted to be deployed to Djibouti meeting the target of seven.[26] The number deployed in country has fluctuated due to deployment training and contracting times, however the objectives of deployment were fully met. This indicator was added in December 2017 when the UK significantly expanded support to UNVIM. In order to increase the frequency and quality of the UNVIM process, the UK provided personnel support through the deployment of UK Deployable Civilian Experts (DCEs)[27]. The DCEs’ maritime and security experience helped UNVIM significantly increase the number and robustness of their inspections. Additional support provided included advice on training and processes, information management, better analysis of shipping trends and engagement with shipping communities and better links with EUNAVFOR[28] in the region.
[26] The actual numbers deployed to Djibouti are sometimes below seven due to the rotation schedule of the inspectors (mandatory two weeks leave, after ten weeks in post).
[27] Deployment of experts from the roster of DCEs is orchestrated through the Stabilisation Unit (SU) contract with Palladium.
[28] The European Union Naval Force Somalia (EUNAVFOR), is a counter-piracy military operation at sea off the Horn of Africa and in the Western Indian Ocean. It is the first naval operation conducted by the European Union.

Lessons identified this year, and recommendations for the year ahead linked to this output:

The UK provided significant new support to UNVIM from December 2017. This expansion demonstrates how the flexibility of the YALLA programme enabled the UK to respond effectively to a rapid and significant change in the operating environment.

Boosting the capabilities of UNVIM through the provision of British experts was crucial in providing additional assurances to the Saudi-led Coalition to allow continued commercial imports into Yemen’s Red Sea Ports following the severe access restrictions at the end of 2017. Sustained UK presence in Djibouti and in other regional ports to boost the quality of inspections and provide political reassurance remains crucial. Output 3.3 to be reviewed to ensure target consistently sets expectation for numbers deployed in country rather than contracted.

UNVIM’s reporting capacity has improved over the last year. UNVIM’s daily shipping updates are the primary means by which DFID (and the international community) monitor the number of commercial ships berthing at Red Sea Ports. The provision of UK expertise to boost UNVIM’s analytical and reporting capability were crucial for both improving the quality of UNVIM output and increasing the UK’s access to data and understanding of what is happening on the ground. This support should be continued.

The speed and predictability of the clearance process for vessels headed to GoY controlled ports has been a major focus for the international community. Clarification of the process, and a closer working relationship between EHOC and UNVIM resulted in the reduction of EHOC clearance times, and greater certainty for shippers. The UK should continue to monitor clearance times in order to hold all parties to account, and also to regularly consult shipping liners on the other parts of the process that can be sped up.

Over eighty percent of vessels headed to Red Sea Ports either originate or stop en-route at ports controlled by other members of the Coalition (for example, at King Abdullah Port, Jeddah, Sohar, Salalah and Dubai).[29] Deployment of regional UNVIM monitors to these ports should continue to be a priority for the UK. These UNVIM personnel would monitor inspections at these ports, and therefore avoiding the diversion of these vessels to Djibouti. This would save time and money for the commercial liners, thereby increasing the flow of vessels to Yemen.
[29] Figure valid as of July 2018

Significant benefits were reaped from having a P5 Head of OCHA stationed in Riyadh , and ensuring that any technical issues could be quickly resolved at senior level. OCHA should ensure that this post is filled.

UNVIM continues play a critical role in reducing Coalition concerns over arms smuggling while maintaining commercial importer confidence. To avoid any challenges to the legitimacy of UNVIM, the UK should continue to encourage the UN to consider options to formalise its mandate.

UK attendance with observer status at the UNVIM Steering Committee has contributed to operational and more strategic issues being resolved between UNVIM, the SLC and the Government of Yemen. The UK and other donors should encourage UNVIM to convene these meetings regularly.[30]
[30] UK attendance should be at the minimum by the UK Maritime Security Advisor (Riyadh). A member of the YALLA Programme Team (or substitute) should also seek to join.

Output Title	The international humanitarian community has access to a regular supply of fuel through WFP's revolving fuel facility to support their continued operations in country.
Output number per LF		4	Output Score	A
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N (added Dec 2018)

Indicator(s)	Milestone(s) for this review	Progress	Met
4.1 Amount (litres) of fuel stocks procured by WFP for the Fuel Facility for humanitarian purposes.	February 2018: 6.5 mil litres / April 2018: 5 mil litres / June 2018: 5 mil litres / August 2018: 5 mil litres	Feb 2018: 6.5m litres / April 2018: fuel delayed. / June 2018: 5m litres / August 2018: 9.7m litres	Exceeded expectations
4.2: Cumulative amount (litres) of fuel from the Fuel Facility used for humanitarian purposes (broken down by agency and INGO).	Feb 2018: 6.5 m litres (4.6 M for UNICEF/WHO, 0.4 M for INGO/UN humanitarian activities and 1.5 M buffer stock ) / April 2018: 5 million litres delivered and invoiced to partners / June 2018: 5 million litres delivered and invoiced to partners / August 2018: 5 million litres delivered and invoiced to partners	March 2018: 6.5 m litres (4.6 M for UNICEF/WHO, 0.4 M for INGO/UN humanitarian activities and 1.5 M buffer stock ) / June 2018: 10.3m litres (8.6 M for UNICEF 1.7m for WHO and 0.03 M for Logistics Cluster) / August 2018: 13.3m litres (11.6m for UNICEF and 1.7m for WHO, 0.10 m to MoPIC, 5.000 litres to WFP Sub-office and 0.03m to LC)	Met expectations

This output has scored an A – outputs met expectations
The access restrictions imposed by the SLC at the end of 2017 meant fuel risked constraining effective humanitarian response. No fuel entered Yemen for over six weeks[31] which could have had far reaching effects on the ability of water plants and hospitals to function, and for humanitarian aid to reach people in need. DFID therefore worked with WFP Logistics to establish the ‘revolving fuel facility’, whereby an initial injection of £10m allowed WFP to procure fuel which they sold on a cost-recovery basis to WHO, UNICEF and other NGOs. This support had and continues to have a multiplier effect in terms of outputs and outcomes.
[31] Access restrictions were imposed on Yemen on 6 November. The first commercial fuel shipment entered Yemen on 20 December 2017.

Performance on Indicator 4.1 has exceeded expectations. Over the reporting period, DFID funds resulted in 21.1 million litres of fuel being imported to Yemen on three separate vessels. This exceeded the target of 20 million litres of fuel over the period. Imports of fuel into Yemen did not meet the precise quarterly log frame targets due to challenges procuring the fuel and delays in the fuel entering port.

Performance on Indicator 4.2 has met expectations. Over the reporting period, WFP delivered 11.9 million litres of fuel to UNICEF to support the functioning of water facilities, 1.7 million litres of fuel to WHO to power hospitals and the remainder to WFP Sub-offices, the Logistics Cluster and to the Ministry of Planning and International Cooperation (MOPIC). The hospitals and water facilities are located across Yemen.[32]
[32] Full list of distribution sites available on Vault 1024856

While the initial agreement was signed in December 2017, WFP’s initial procurement of fuel did not arrive in Yemen until February 2018. However, given that impact of the import restrictions was not felt until this time (as vessels berthing at Yemen would have been sent three months previously), it can be deduced that the first shipment came at precisely the correct time to mitigate against fuel shortages. In addition, providing fuel to UNICEF and WHO meant that there was more fuel available locally for others to purchase.

Lessons identified this year, and recommendations for the year ahead linked to this output

There is no limit on the duration of the facility as WHO and UNICEF are paying for the fuel on a full cost recovery basis. Given the low cost that WFP can procure the fuel, it is sold to agencies at an affordable price (lower than local fuel prices). This means the project will last beyond the end of the year – which was the initial anticipated timeframe.[33] DFID therefore should extend the end date to their Contribution Agreement with WFP to the end of the programme.
[33] At project inception, fuel was going to be sold to agencies on a partial cost recovery basis. However, given WFP can procure fuel at a lower cost it is viable that agencies buy it on a full cost recovery basis meaning the facility will last beyond one year.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year
The overall theory of change underpinning this and other humanitarian interventions for DFID’s humanitarian response to the crisis in Yemen is shown below. The inputs, processes and outputs relevant to this particular programme are highlighted in yellow. This programme specifically provides technical expertise, funding and staff time at the input level, all of which enable the delivery of the outputs, outcome and impact. It remains relevant one year after the launch of YALLA as factors underpinning it have not changed Access to and inside Yemen remains heavily constrained and donors continue to entrust the UN, led by the UNHC. to implement a principled and well-coordinated humanitarian response in Yemen. Terms of the UNSCR 2216 still apply and donors maintain their support to the UN Verification Mechanism (UNVIM). It is recommended that DFID Yemen develop a tailored theory of change to this programme, showing the criticality of this programme in enabling the wider international humanitarian response.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

Expected Impact of this enabling programme is “Critical humanitarian need is alleviated amongst the targeted population”.
One year on since the launch of the YALLA programme, the humanitarian community has managed to stay and deliver in Yemen in spite of severe access constraints and shrinking humanitarian space. This programme contributed to this success by supporting access by air for humanitarian workers in and out of Yemen. It also contributed to ease access across Yemen in terms of negotiation with local and de faco authorities and de-confliction of fixed and mobile assets with the Saudi-led Coalition. Coordination and Quality Programming has also been strengthened through Standby Partnerships in support to strategic UN staff member roles and through the Humanitarian and Stabilisation Operational Team (HSOT) advisory support to the DFID Yemen team.

A major programme component was added in the course of Year 1 of YALLA implementation with a fuel revolving fund managed by WFP. This revolving fund so far has helped provide regular import and provision of quality-checked diesel fuel to run the generators of the main water treatment plants and to run the electricity generators of central hospitals still functional across Yemen. The fuel provision also supports the wider humanitarian community with three strategic WFP fuel storage hubs in Hodeidah, Aden and Sana’a, wherefrom humanitarian organisations can collect quality-checked diesel at a competitive price, when availability and quality on local markets is not reliable.

It is too early to measure the Impact indicator “Percentage of target beneficiaries identified in the Yemen YHRP reached by humanitarian assistance (reported by sector)”; the Humanitarian Response Plan for 2018 is still being implemented and is just about to be revised. The 2017 Humanitarian Response Plan targeted 12 million people in need and was 73.8% funded. This has allowed the humanitarian community to reach and assist 11.5 million people in need. In 2017, OCHA Yemen scaled up its operations to support expending relief efforts across the country. Working with about 190 humanitarian organisations, OCHA coordinated assistance to more than 7 million people, an increase from about 5.6 million people in 2016. The 2018 Humanitarian Response Plan targets 13.1 million people. It was 62.4% funded as of July. According to latest OCHA estimates, from January to June, humanitarian partners have assisted over 7.6 million people monthly with some form of humanitarian assistance.

Outcome 1: Effective and comprehensive multisector coordination informs timely and appropriate humanitarian strategic planning and response.

The UN-coordinated humanitarian community managed to stay and deliver even though North Yemen under Houthi control was ranked as “non-permissive environment” by the UN in June 2018. In this context the humanitarian community struggled with the conduct of large scale formal surveys in the absence of access clearance issued by de facto authorities. The November 2017 Humanitarian Needs Overview hence did not benefit from recent and reliable data to the extent required for such a large and complex crisis. No Periodic Monitoring Review was produced in 2018. Still, the terms of the Humanitarian Programme Cycle remain relevant in this context with a need for well-coordinated joint assessment of acute humanitarian needs across the various sectors (HNO/PMR) and a need for related annual UN consolidated appeals (HRP). UN leadership was demonstrated through the joint effort of the UN Special Envoy of the Secretary General to Yemen and the UNHC who did unlock the June 2018 access situation through intensive negotiations in Sana’a, thus securing a minimum acceptable humanitarian space for implementing partners to operate in a safe and principled manner. While some improvements were noticed in terms of OCHA real-time reporting on events and their impact on humanitarian affairs, we still miss granularity in OCHA reporting. We need to keep encouraging OCHA for more detailed reporting in Year 2 while DFID will be looking at ways to complement OCHA standard reporting material, including by supporting other agencies (e.g. ACAPS and Catapult).

Outcome 2: Commercial cargo is allowed to berth into Yemeni Red Sea ports in line with regulations as set out in UNSCR-2216.
The levels of food and fuel imports during this reporting period did not remain stable. Food imports varied from approximately 320,000 MT imported through Red Sea Ports in October 2017, to 160,000 MT in February 2018, to 415,000 MT in May 2018 and down to 250,000 MT in July 2018. This demonstrates that while UNVIM is a vital pre-requisite for vessels to access to berths in Red Sea Ports, there are other factors which affect whether commercial lines direct their cargo to this port in the first place. This includes commercial confidence, regional security and the functioning of Red Sea Port operations (for example, availability of tug boats). Indeed, throughout the period UNVIM encountered a number of challenges fulfilling its mandate.. Ann active UK membership at the UNVIM Steering Committee and a close relationship with UNVIM is important to tackle such issues.

 Outcome 3: Number of Humanitarian Agencies in Yemen benefiting from the Logistics Cluster services

The UN Humanitarian Air Services remained essential in providing a safe and regular access in and out of Yemen main airports for hundreds of humanitarian workers every month. Generous support to WFP Logistics by other donors explains why DFID provided no support to other WFP Logistics services. DFID support to those essential logistics’ services however should be considered in Year 2, depending on WFP Logistics’ funding status, given the importance of WFP Logistics support in the form of transport and evacuation means: i.e. sea shuttles between Djibouti and Aden and Djibouti and Hodeida. WFP Logistics also provide critical assistance to the wider humanitarian community by chartering humanitarian cargo flights from Djibouti airport to Sana’a airport, by offering permanent and temporary warehousing structures, and by providing a truck fleet to dispatch UN and NGO humanitarian cargos across the country.

Explain major changes to the logframe in the past year

Addition of Output 4 to the Logical Framework
In December 2017, the UK agreed an additional DFID allocation to WFP Yemen to establish a fuel revolving fund. At that time, no fuel had entered Hodeidah and Salif Red Sea ports since 6 November. The rationale was to provide fuel for humanitarian operations, essential services and ease pressure on the market.

Describe any planned changes to the logframe as a result of this review

Output Indicator 1.3: it is proposed to replace “weekly HCT and fortnightly ICCM” with “average 3 HCT and 4 ICCM meetings per month” better reflecting OCHA and new UNHC approach since March this year and the establishment of an Emergency Response Cell.

Output Indicator 2.1: it is proposed to reduce the 90% UNHAS target occupancy rate, with a lower percentage. The high target implies UNHAS is not performing, whereas in actual fact the majority of planes are also filled with light weight cargo, which are not accounted for in the indicator.

DFID Yemen should consider introducing indicators for the HSOT advisory support to the DFID Yemen team, and for the strategic UN staff members deployed though Standby Partnership. On the latter, DFID supported six positions this year, and progress should be measured.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year

The following value for money (VfM) assessments use DFID’s 4Es (economy, efficiency, effectiveness, equity) approach in determining YALLA’s overall value for money.

OCHA Core Costs
The original Business Case proposed that supporting core costs including staffing and hub management for the OCHA country team promotes VfM by ensuring a more coordinated approach to the wider humanitarian response meaning resources are directed most efficiently to where need is greatest. The quality, timing and widespread use of the YHRP - which sets out the most pressing needs and the joint humanitarian response planning - is an example of the critical coordination role that OCHA fills. As outlined in Section B, the 2018 YHNO and YHRP were published in a timely manner to shape the response. However, there was no Periodic Monitoring Review in the period. In addition, the timing of release, duration and planning of the release of the 2019 YHNO remains relatively opaque to donors – particularly on whether or not it will include Humanitarian Plus activities.[34]
[34] Humanitarian plus refers to extending funding from the humanitarian domain to revive (for example) education, health and water systems, support a basic civil service and rebuild critical infrastructure.

There have been a number of additional examples of OCHA coordination contributing to the effectiveness of the overall response. NGO de-confliction requests are organised through OCHA Sana’a office which streamlines the de-confliction process.[35] In addition, on the basis of OCHA analysis on the exchange rate mechanism in Yemen, the UNHC recommended all humanitarian partners move away from a then artificial official exchange rate of the Yemeni Rial to the USD and instead negotiate with their banks the use of the market exchange rate.[36] An area for improvement that DFID should seek next year is OCHA’s management of exchange rates, and the management of further rapid depreciation of the Riyal. This includes ensuring DFID funds a new Chair of the Cash and Market Working Group (CMWG) in Yemen. Currently OCHA ask their partners to accept the risk of exchange rate losses, but do not question partners on the use of exchange rate gains (which is the case for Yemen), and whether these are reinvested in greater results for the budget. Of a greater concern, OCHA should advise partners on the use of currency gains from projected costs which it does not currently do.
[35] The deconfliction mechanism was established in April 2015 upon the request of the Humanitarian Country Team (HCT) in Sana’a to ensure a safe delivery of humanitarian assistance in Yemen. https://reliefweb.int/report/yemen/deconfliction-mechanism-humanitarian-organisations-operating-yemen-mission-movements

Logistics Cluster: UNHAS
UNHAS offered excellent value for money over the reporting period. The total cost of operating the three flight routes is in the region of $1.05m a month. At the current rate of occupancy if measuring at full cost recovery, the cost per beneficiary is around $1000 per return flight [37]. However, if the flight was fully occupied, the cost per beneficiary would be $625 per flight. These costs should be taken in comparison to the average cost of a return flight from Aden is $900.[38]
[37] In the last quarter (May-July)
[38] Flights operate from Cairo, Sudan or Amman.

Flight route[39]	Cost per flight (excluding indirect costs)	Flight route cost per month (full cost recovery)
Amman-Sana’a Amman	USD 37,988	USD 625,000
Djibouti Sana’a Djibouti	USD 16,706	USD 380,000
Djibouti Aden Djibouti	USD 16,706
[39] There are two flights per week between Djibouti-Aden, three flights per week between Djibouti-Sana’a ($380,000 a month) and three flights per week between Amman-Sana’a ($625,000 a month). This cost is higher than the per monthly cost a year ago but includes the additional Sana’a – Aden flight route.

There has been an increase in commercial flights to Aden over the reporting period, with three commercial airlines now directing flights there. This has resulted in the Aden flight route being underutilised (with an average of 23% occupancy rate over the period), and which increases the average cost per beneficiary significantly. However, given UN and the majority of INGO staff would be unable to make use of commercial lines due to insurance reasons, this flight route must continue and offers its value as there is no alternative. Therefore, while UNHAS services to Aden is a prerequisite to humanitarian presence in the South, DFID should suggest the introduction of various efficiencies (see output 2). For example, by suggesting that use of commercial airlines are reviewed, or by reviewing the size of the UNHAS Aden aircraft if the extra room is not being used by light weight cargo.

It should also be noted that given that Sana’a airport remains closed to commercial airlines, the need for UNHAS flights to the north remains fundamental to enable an effective humanitarian response.

UNHAS has continued to introduced economies and efficiencies though a number of means, including: filling all humanitarian cargo with light, fragile or sensitive cargo whenever occupancy rate is low, maintaining flexible flights and adding extra routes where demand is needed. [40] For example, a route between Sana’a and Aden is currently being negotiated given the long travel time between the two cities by road. UNHAS has also introduced penalties for missing flights, to recover some of the costs and to discourage agencies with a high record of “no shows”.[41]
[40] For example, in August 2018, UNHAS transported 899 passengers along with 31 kg of medicine to Aden and Sana’a
[41] WFP Logistics are assessing whether to apply a similar regime to the sea shuttle to Aden.

Logistics Cluster: Revolving Fuel Facility
An agreement was made with WFP to create a revolving fuel stock, whereby humanitarian agencies, specifically, UNICEF and WHO, would have guaranteed access to fuel from the WFP Logistics Cluster at a rate agreed shortly before distribution. This not only protects the organisations from the volatile spikes in prices and local market shortages but ensured humanitarian programming could continue, improving the effectiveness of the interventions. DFID’s initial investment of £10 million to establish WFP’s revolving fuel facility demonstrated economies of scale. WFP procure the diesel fuel from the international market and conduct an international tender to get the best value fuel. The cost that WFP has managed to procure the fuel at is $0.69 per litre[42] (or YER379.5). Compared to where the exchange rate is now[43] (YER600/$) - which would make the price of fuel WFP are buying 414YER. The difference between WFP and market fuel is therefore about 30-50 YER/litre (or roughly 10%).[44] WFP have therefore made savings which have been reinvested into the fuel facility, allowing more beneficiaries to be reached.
[42] Latest exchange rate pre current currency crisis is YER550 (so 0.69 X550 = 379.9)
[43] Valid as of the 15 September 2018
[44] what fuel is currently on sale on the market. which is on average 400 YER in the North, and 350 YER in the South

DFID’s £10 million established WFP’s fuel facility, which operates on a full cost recovery basis. The facility does not generate profit, but rather ensures a smooth flow of fuel at the most affordable price possible to UNICEF and WHO to provide clean water and health services to the population. Both UNICEF and WHO advance the payment (usually three months in advance), allowing WFP to place the next order.

UNVIM
Yemen relies on imports for 90% of its food. Uncertain waiting times and long clearance procedures in the past reduced the viability of exporting to Yemen, pushing commercial confidence below most exporters’ risk appetite. For a relatively small financial outlay – at approximately £200,000 a month – UNVIM contributes to speeding up the clearance process for vessels headed to Red Sea ports, increasing commercial shipping confidence, and reducing the costs for shipping liners (whose vessels can incur daily costs of up to $15,000 a day waiting to enter ports). This has facilitated the continuation of imports into Yemen, ensured food is available in the markets and enabled humanitarian programming to continue[45]. The key cost drivers of UNVIM are personnel costs of the office which process clearances and the expertise to carry out inspections, and which remained stable over the reporting period.
[45] As many humanitarian agencies import their cargo on commercial vessels to save costs

The efficiency of UNVIM can be demonstrated by the time taken for ships to be verified or referred for inspection once UNVIM have received all documentation. This time has remained under 48 hours. Earlier this year EHOC were criticised for delays in subsequently clearing vessels, following UNVIM clearance. This resulted in extra expense and unpredictability for shipping lines. Proactive engagement by donors and UNVIM engagement with the Coalition resulted in these delays being reduced, and a more efficient verification mechanism. In addition, deployment of UK maritime experts to Djibouti has improved UNVIM’s capacity and efficiency at inspecting vessels by ensuring full staffing capacity. Finally, the effectiveness of UNVIM is demonstrated through the fact that without the existence of the mechanism no commercial vessels would be granted access to Yemen Red Sea Ports.

Technical Advisory Support
This component of the business case covers the deployment of contracted expert humanitarian support. Costs under this component have increased this year due to the UK’s offer to rapidly position UK Deployable Civilian Experts (DCE) with maritime expertise to UNVIM in Djibouti. DFID used the Palladium contract through the Stabilisation Unit. The costs of deployments are approximately £220,000 a year, and were successfully negotiated downwards by the Programme Team While the cost on this component was higher than forecasted, the result was successfully strengthening UNVIM and ensuring the continued flow of commercial vessels into Yemen, and at a lower cost than originally posed by the Palladium contracting team.

In line with the recommendations made in the last programme’s Project Completion Review (PCR) and in DFID Yemen’s Internal Audit, the use of contractors should be reserved for rapidly required, short term, specialist resources. As such, by this review point, DFID has successfully replaced two long term consultant positions, a Humanitarian adviser and a Humanitarian Affairs Officer, with Home Civil Service (HCS) positions. DFID currently contract two other short term positions, which will remain under review.

The flexibility provided by HSOT contractors has offered continued efficiencies to DFID by allowing the volume of humanitarian expertise within the department to expand and contract at short notice. For example, DFID Yemen quickly contracted a specialised Logistics Advisor to support the department’s assessment of port and transport capacity in Yemen. Funding strategic surge positions through Standby Partnerships supports a more efficient and effective UN response. For example, supporting a Gender Based Violence (GBV) sub-cluster coordinator has been critical in improving the effectiveness of the response’s approach to gender sensitivity.

Efficiencies are made by both Palladium and DFID by frequently looking ahead to to identify contracts due to terminate in posts that remain necessary, ensuring continuity and allowing DFID to benefit from renewing contracts for staff who already understand the requirements of the role and have demonstrated good performance.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

This report judges the programme improves efficiencies and effectiveness of the humanitarian response and should continue based on the VFM assessments.

E: RISK

Overview of programme risk and mitigation
Overall risk rating: Major
The overall risk of the programme remains major. There continues to be a deterioration of the political, security and economic situation, and consequently the operating environment for all components. The key risks were monitored and discussed on a minimum quarterly basis with partners and updated.[46] The key escalating risks and mitigation measures are set out below:
[46] Given the number of programme components, the Programme Team assessed each risk by component rather than as one programme.
OCHA Core Costs
Escalating conflict and increased security restricting access by humanitarian partners to parts of Yemen: Since the launch of the programme, there have been a number of peaks in the conflict (notably in November-December 2017, June 2018 and September 2018) resulting in parts of the country becoming temporarily inaccessible to HCT partners. New mitigation measures introduced included:
- OCHA working to strengthen the mechanism to de-conflict field missions, convoys and fixed assets with the Coalition’s notification system.
- DFID working with OCHA to ensure the production of contingency plans in the circumstance that Red Sea Ports are severely restricted.
This resulted in a major residual risk. Next year, DFID should focus on ensuring strong collaboration between OCHA, the UNHC and the Clusters, recognising that a “1UN” approach is crucial ensuring that the UN is sufficiently prepared for any shocks. DFID should also become more focused and systematic in the levers they use to influence OCHA to reform. For example, ensuring there is a key DFID focal point leading the relationship with OCHA Sana’a and that previous priority asks are not forgotten when a new one appears.
Weak coordination between humanitarian actors resulting in a lower level response: Agencies and INGOs relied on OCHA for: the production of the key strategic documents for the humanitarian response; managing information flows as well access negotiations including visas; and leading on de-confliction requests. Over the reporting period, the humanitarian operating space became increasingly squeezed, especially by the de facto authorities in the North, and OCHA became increasingly stretched to respond. New mitigation measures introduced included:
- Being proactive offering strategic deployments into the UN system to bolster human resources and ensure critical coordination and information management roles are in place
- Using Ministers and the UN Missions in New York and Geneva to push for improved planning and high quality staff gap filling.
- Using the UK’s seat on the Humanitarian Country Team (HCT) as a platform to constructively raise key issues to the UNHC.
This resulted in a moderate residual risk.. Next year DFID should explore additional levers they can use to support OCHA on improving their performance on key coordination functions.
UNHAS
Restrictions in flight clearances as a result of heightened conflict with airspace no longer safe to fully operate and/or increasingly stringent policies by the Coalition or the Government of Yemen restricting humanitarian access to Yemen (e.g. double visa requirements. In addition, in times of escalating conflict, there were air strikes in dangerous proximity to Sana’a airport, which if they had struck a flight would have had a detrimental impact on the entire response. Finally, the continued difficulty obtaining A1 Jet Fuel for Sana’a flights remained a key risk – with fuel being transported up by road from Aden throughout the period. New mitigations measures introduced included
- WFP Logistics have identified alternative solutions for the evacuation of humanitarian staff. Specifically by chartering a new vessel (VOS Theia) to be stationed off Hodeidah for evacuation purposes, and as an additional means for humanitarian workers to access the Red Sea Coast.
- DFID agreed to fund A1 Jet Fuel through the Revolving Fuel Facility. Additional funds allowed WFP to create a buffer stock of fuel.
This resulted in a moderate residual risk. Next year, DFID should continue pushing HMG engagement for the re-opening of Sana’a airport for commercial flights. DFID should also continue regular liaison with the Coalition to ensure de-confliction around airports is respected.
Revolving Fuel Facility
WFP or supplier storage capacity becomes unavailable. The dynamics of who controls what within the commercial sector shifted rapidly the period under review, particularly in the North. Most notably the Yemen Petroleum Company (YPC) refused to grant customs exemptions to WFP humanitarian fuel,. New mitigations measures include:
- WFP updating their contingency planning in case storage does become unavailable. This includes moving stocks away from Red Sea Ports.
- DFID to make the most of alternative access routes to influence policy of the de facto authorities. For example, using levers such as the UN Special Envoy, the Omanis and the private sector to help unlock key access issues (e.g. YPC not clearing fuel).

The delivery and fiduciary risk to the delivery of fuel within Yemen remained high. Airstrikes and ground fighting in and around Hodeidah continued through the reporting period, with the potential to jeopardise the delivery of UK procured fuel. In addition, given the continued deterioration in the conflict, diesel increasingly became a commodity of economic and strategic value. As such, there was a higher risk of diversion by armed actors, with the greatest risk downstream during partner distribution. New mitigation measures included:
- WFP used multiple providers in country and regionally to assess cost effective and viable importation and storage options.
- WFP set up a new third party monitoring system for quality and quantity control across the country. WFP, together with its service partners, established a new Monitoring & Evaluation strategy to ensure that an agreed distribution plan was in place, and distribution to on-site locations were monitored and reported.
This resulted in a major residual risk. DFID should continue to finance the fuel facility in the future – subject to sustained demand. The delivery chain that WFP have developed is judged to be robust. However, DFID should continue to work with WFP to monitor whether it is an acceptable level of risk, and also to assess any unintended consequences of the fuel disbursal (i.e. fuelling a war economy).

UNVIM
Government of Yemen or Coalition restrict entry of ships verified and clearance by UNVIM, bypass UNVIM altogether or instruct UNVIM to divert vessels away from Hodeidah without justifiable reasons. Over the reporting period, two mains risks emerged related to this – both related to the Coalition contesting UNVIM’s mandate as the sole authority to clear vessels. First was on “secondary inspections”, whereby the Coalition insisted on inspecting commercial vessels which had already been cleared by UNVIM. These second inspections took a long time (on one occasion over two months[47]), which undermined UNVIM’s initial clearance and commercial companies confidence in the UNVIM process. Second, at the end of 2017 the Coalition restricted all commercial access into Yemen which prevented UNVIM from issuing any clearances. There is an additional risk here that the UK expertise would not be used if UNVIM ports were bypassed by the Coalition or the Northern ports remained closed. New mitigation measures introduced included:
[47] The INCE Atlantic was held by the Coalition for over two months in Jizan port in March 2018
- Improving the Coalition, GOY and UNVIM relationship through: more senior UN presence in Riyadh able to advocate on behalf of UNVIM (though this position is currently vacant, and is a priority to fill); regular Steering Committee meetings to resolve such occurrences; and better communication and information to use in lobbying.
- The UK increasing its own monitoring of the commercial climate including close monitoring of imports into Red Sea Ports. The UK is therefore able to challenge the Coalition over specific blockages, bringing in the context (for example, demonstrating that the failure to clear a vessel will result in a shortage of food that month).
Slow clearance times meaning the process delays vessels entering Yemen Red Sea Ports. This risk originally referred to the UN lacking capacity to verify all ships within 48 hours, meaning inspections and clearances took longer than expected. Further issues emerged relating to the time it took the Evacuation and Humanitarian Operation Cell (EHOC) to clear vessels and the shipping community raising the unpredictability of the mechanism as a disincentive to shipping to Yemen. New mitigation measures included:
- Improved analysis of how UNVIM and EHOC conducted clearances meant data could be used to hold both to account if there were delays.
- The UK Maritime Security Advisor cultivating stronger relationships with EHOC in Riyadh meaning challenges on clearance times could be quickly resolved.
- Initiating roundtable discussions with the commercial shipping community to better understand their views on the mechanism, and what the international community could do to improve commercial confidence.
- Deployment of two Saudi Liaison Officers (SLOs) to Djibouti to oversee operations provided UNVIM a direct line to EHOC in Riyadh.
Technical Advisory Support. Palladium and DFID’ Humanitarian Support Operational Team (HSOT) are responsible for managing the risks associated with the recruitment of contractors such as high day rates and unavailability of experts. The risk has remained moderate, principally due to the uncertainty around the implications of the new Palladium contract risking the loss of contractors. New mitigations included:
- Contracting team keep DFID up to date with all financial, legal and commercial implications of the Palladium contract, with DFID responding appropriately, prioritising value for money and essential resources.
- DFID also has successfully replaced many contracting positions with HCS roles.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial and financial issues

OCHA Core Costs
DFID funded OCHA £1.5m in 2017/18 and is expected to fund an equal contribution in 2018/19. In both years DFID funds equate to around 17% of OCHA total costs. In terms of reporting, DFID’s Humanitarian Advisor regularly met with OCHA, and was able to assess progress against agreed indicators. DFID do not expect donor specific reporting as part of this funding and were able to judge progress and challenges faced by OCHA through their regular reporting (as outlined in Section B). DFID received quarterly financial reports, all which have been received on time in this reporting period. It is recommended that next year:
Review OCHA’s performance on civilian / military planning and coordination. Feedback from partners is that the existence of deconfliction in Houthi controlled areas in the North is a major gap. OCHA Sana’a to work with the UNHC to determine how best to develop an agreed system with the Houthi authorities to protect humanitarian access and distribution. OCHA Sana’a and Riyadh should continue to work with the Coalition to improve deconfliction standard operating procedures.

WFP Logistics Cluster: UNHAS
DFID funded UNHAS £1.77m in 2017/18. A similar amount is expected to be funded in quarter 4 of 2018/19. UNHAS flights broadly operated as expected in this period, despite low occupancy rates for some routes and fewer flights at the end of 2017 when there were access restrictions. DFID’s seat on the UNHAS Steering Committee on the UNVIM donor committee provides the UK with influence and insight. The timeliness of UNHAS reporting has been good, with monthly progress reports submitted to donors. In terms of quality, agreed indicators and risks have been reported although the programme team often had to follow-up with UNHAS to get into more detail. UNHAS is proactive in working with donors to raise certain issues with parties to the conflict as needed, which has helped mitigate risk.

WFP Logistics Cluster: Revolving Fuel Facility
DFID supported WFP to establish the revolving fuel facility through an initial £10m contribution. No further contribution is expected. The fuel was sold to humanitarian agencies on a partial cost recovery basis, and was initially anticipated to last for one year. However, the lower cost of the operation meant the contribution is expected to last into Year 2 (more detail provided on this in Section D). WFP provide quarterly reports and we have fortnightly phone calls – where the fuel contribution is discussed as part of our wider package of support to the organisation (through project number 300434).

On assets, as outlined in DFID-WFP Contribution Arrangement, DFID and WFP will need to jointly decide on how revenues generated from the sales of fuel are used at the end of programme. WFP will either return excess revenues to DFID or come to a mutual agreement on use by the Logistics Cluster in Yemen.

UNVIM
DFID has provided £2.6 to the UN Office for Project Services (UNOPS) since the programme’s inception.[48] In terms of reporting, UNVIM has significantly improved its frequency and quality. DFID does not request donor specific reports from UNVIM but receives the daily, weekly and monthly progress reports published by UNVIM for the international community (in September 2018 UNVIM launched a new website publishing all current and historical reports). DFID has helped develop the content of these reports, and uses the data to track the levels of imports into Yemen. Good quality financial reports are also received by DFID. Other key donors to UNVIM operations are the US and Japan. UNVIM has been successful in widening its financial donor base. It is recommended that next year:
[48] UNOPS are the agency that manage UNVIM.
- Securing senior staff presence in Riyadh needs to be a priority for UNVIM. A close relationship with the Coalition is vital to unblock issues, and to ensure UNVIM can operate within its mandate.
- On assets, DFID has $90,000 worth of assets in Djibouti (cars and computers).[49] As outlined in the UNOPS-DFID MOU, a decision will be made over their future at the end of the programme.
  [49] See UNOPS asset register, July 2018.

Technical Advisory Support
DFID contracts specialist support and humanitarian expertise through DFID’s Humanitarian and Stabilisation Operations Team (HSOT) and the Stabilisation Unit’s contract with Palladium. So far £1.6m has been spent, with a similar amount forecast for next year. Both the contracting team (HSOT) and DFID gave positive feedback on the working relationship, although on occasion there could be better communication on operational issues. Contractors and UN secondees are all contracted for limited periods of time, with individual terms of reference stating what should be achieved. It is recommended that next year:
The DFID Yemen SRO sees that regular meetings with the DFID Yemen Humanitarian Team Lead and the contracting team are set up to discuss workforce planning for contractors. DFID Yemen should provide the contracting team with as much notice as possible for extensions of contracts, or new contracts, to avoid gaps and achieve savings.

Accountability to Affected Populations (UNICEF)
The original YALLA Business Case proposed DFID funding the establishment of a common service platform available to the humanitarian community to gather feedback from beneficiaries on the quality of the humanitarian response. This feedback would be used to inform the YHNO, the YHRP and individual agency and NGO planning. It was anticipated this platform would be managed by UNICEF. Due to limited advisory capacity within DFID, this component has not been taken forward. DFID will look to prioritise its development in the next reporting year.
G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring

OCHA Core Costs: Monitoring OCHA’s performance against its Annual Work Plan has been possible to organise from Amman thanks to the deployment of a Senior Representative to lead the OCHA Yemen office in Amman. Regular meetings discussed progress and challenges in the implementation of this work plan and provided helpful information to the DFID Yemen team in London for example situation reports related to the impact of the conflict.

A new UNHC was appointed in March 2018. She meets Amman-based donors regularly and for the first time in early August 2018, donors were invited to join the Humanitarian Country Team (HCT) meeting. These sessions will help DFID and other donors better understand the situation on the ground in Yemen and the specific challenges related to delivering the humanitarian response. This will also allow DFID Yemen to follow up more closely all processes related to the Humanitarian Programme Cycle, including the production of YHNO, YHRP and any other UN appeals. Finally, this should also contribute to better understanding HCT recommendations and UNHC decisions as regards the use of the Yemen Pooled Fund.

WFP-chaired Logistics Cluster (UNHAS) and Fuel Facility: DFID Yemen remains a member of the UNHAS Steering Committee (SC) which is co-chaired by the UNHC and the WFP Country Director. Few SC meetings were organised over the period under review as the programme has been performing reasonably well and required less consultation with donors and key users of this humanitarian service.
UNHAS has shared monthly statistics with donors and we made sure that these include information required to populate the logical framework of the YALLA programme. In addition, DFID Yemen has been in regular contact with the Sana’a based UNHAS Representative as well as his Representatives in Amman and in Djibouti.

UNHAS is a programme of WFP and issues are discussed at regular WFP Management team meetings in Amman including regular quarterly meetings. DFID Yemen have had fortnightly calls with WFP Sana’a Management Team throughout the period under review, which offered another opportunity to discuss the UNHAS programme as required.

UNVIM: DFID Yemen have taken a more active role in the monitoring of UNVIM this reporting year. DFID conducted a site visit to Djibouti in February 2018. Finally, monthly UNVIM Steering Committees, quarterly shipping roundtables and increased reporting from UNVIM (as outlined in Section F) has provided DFID with more data on import trends.

Provision of Technical Expertise: DFID used of three types of technical expertise:
1. DCEs seconded into UNVIM: There were initial challenges with the UNVIM DCE deployments principally owing to the rapid nature of the initial deployment. DFID therefore increased oversight and monitoring of the deployments – through weekly phone calls between DFID, the SU and UNVIM. DFID are on the interview panel for all new DCEs and brief and debrief new Djibouti deployment. While this is increased staff time, it is recommended the increased monitoring continues over the next year.
2. Humanitarian advisors contracted to work for DFID Yemen: As per the DFID-Palladium contract, DFID monitor all seconded advisors through progress towards their deliverables as agreed in their Terms of Reference.
3. Specialist positions seconded to the UN through Standby Partnership. DFID funded six positions in this reporting period. First, a WHO logistics expert, stationed in Djibouti and responsible for logistics for getting cholera supplies into Yemen. Second, the gender sub-cluster coordinator responsible for ensuring gender was prioritised across all interventions. Third, a cash expert who chaired the Cash Market Working Group (CMWG). Finally, two shelter coordinators through UNHCR who were responsible for coordinating and camp management in Hodeidah. The posts were monitored formally through end of posting reports sent to DFID. Informally, DFID engaged the gender and cash coordinator. It is recommended that next year DFID consider introducing specific indicators to monitor this component.

Evidence

OCHA Core Costs
Without reaching their targets in Year one, OCHA demonstrated their ability to stay and deliver even in time of hardship such as during the fighting in Sana’a city in December 2017 and in spite of what the UNHC described as a “non-permissive environment” in early June 2018. OCHA also maintained its footprint in Sa’ada, Ibb, Hodeida and Aden hubs across Yemen as well as their Amman and Riyadh representations in spite of related staff turn-over and visa issuance challenges. Overall, UNHC Leadership was reinforced by OCHA with the cohesion of the humanitarian community maintained through the Humanitarian Country Team and the cluster system. As a result, OCHA coordination allowed timely release of the HNO in late 2017 and the HRP in early 2018. It continued to strengthen coherence and harmonisation in the humanitarian response through the HCT and related working groups (e.g. recent HCT endorsement of its revised Protection Strategy). Finally, OCHA succeeded in raising the Yemen Level 3 crisis profile and draw more international attention and funding support, including an exceptional un-earmarked $930m donation by KSA and UAE in support to the Humanitarian Response Plan released in January 2018.

Learning

OCHA Core Costs: The Yemen Level 3 crisis further confirms the need for a well-coordinated, targeted and principled response organised under the authority of an empowered UNHC with the support of the OCHA Secretariat. This crisis response also highlights a number of weaknesses, which are not necessarily specific to this crisis and should be addressed at the global level. Such weaknesses include the OCHA overall downsizing whereby any attempt to strengthen the OCHA Yemen organigram leads to difficult negotiations with OCHA headquarters. Another constraint felt in this response is OCHA tendency to over format its response and keep the production of information products to those recommended by headquarters’ guidelines. This results in situational reports that were often perceived by DFID as not being comprehensive enough and not issued in a timely manner. The period under review also coincided with OCHA distancing itself – at the corporate level - with the coordination of cash based transfer programmes. OCHA central guidance however still calls for OCHA country teams’ to support to this function through a “facilitation” role which, in a place like Yemen, leaves unclear the extent to OCHA obligations and effective involvement in cash programming coordination and harmonisation.

UNHAS, WFP Logistics and the revolving fuel fund. OCHA core costs and other enabling programmes have received generous donor donations over the past year. We should encourage WFP to maintain a variety of profiles among UNHAS and WFP logistics’ group of donors. This is important as a matter of sharing the burden among main donors but also as a way to keep these programmes from being associated to any specific donor. For this reason, it is recommended that the fuel revolving fund managed by WFP receives funding from a mix of donors after UK provided seed funding in late 2017.