## Logframe
Yemen: Access, Logistics, Liaison and Accountability (YALLA)
PROGRAMME TITLE | Yemen: Access, Logistics, Liaison, and Accountability (YALLA), 300417
IMPACT | Impact Indicator 1 |  | Baseline (October 2017) | Milestone (April 2018) - average of previous 6 months. | Milestone (October 2018) | Milestone Q3 | Milestone Q4 | Target
Critical humanitarian need is alleviated amongst the targeted population. | Percentage of target beneficiaries identified in the Yemen HRP reached by humanitarian assistance (reported by sector) | Planned | %-age against number of beneficiaries identified in the 2018 YHRP 2017 - Protection - Camp Coordination & Camp management - Early Recovery and Livelihoods - Education - Food security and Agriculture - Health - Nutrition - Shelter & NFI - WASH | TO FILL IN
|  | Actual | [5 empty] | 0
Source
OUTCOME | Outcome Indicator 1 |  | Baseline (October 2017) | Milestone (April 2018) - average of previous 6 months. | Milestone (October 2018) | Milestone Q3 | Milestone Q4 | Target | Assumption
The capacity of the international humanitarian system to respond in Yemen is strengthened, with agencies able to maintain accountable humanitarian operations and scale up delivery where possible | Effective and comprehensive multisector coordination informs timely and appropriate humanitarian strategic planning and response. | [7 empty] | Required funding is made available
|  | Planned |  | Measured by joint assessments; joint plans incl contingency planning and response plans; XXX number of emergency needs responded to in complementarity/jointly |  |  |  | 0 | Humanitarian access remains unconstrained
|  | Actual |  | discuss at next DP. |  |  |  | 0
| Outcome Indicator 2 | Source
Commercial cargo are allowed to berth into Yemeni Red Sea ports in line with regulations as set out in UNSCR-2216.
|  |  | Baseline (October 2017) | Milestone (April 2018) - average of previous 6 months. | Milestone (October 2018) | Milestone Q3 | Milestone Q4 | Target
|  | Planned |  | No restrictions to the berthing of commercial cargo at Red Sea Ports, allowing food and fuel imports to meet Yemen's needs. | No restrictions to the berthing of commercial cargo at Red Sea Ports, allowing food and fuel imports to meet Yemen's needs. | No restrictions to the berthing of commercial cargo at Red Sea Ports, allowing food and fuel imports to meet Yemen's needs. | No restrictions to the berthing of commercial cargo at Red Sea Ports, allowing food and fuel imports to meet Yemen's needs. | 0
|  | Actual |  | Significant import restrictions in November-December 2018. Ongoing restrictions on containerised cargo. Reduced commerical confidence. Throughout period food imports in Hodeidah met 47% of Yemen need and fuel met 24% Yemen needs. |  |  |  | 0
| Outcome Indicator 3 | Source
Number of Humanitarian Agencies in Yemen benefiting from the Logistics Cluster services
|  |  | Baseline (October 2017) | Milestone (April 2018) - average of previous 6 months. | Milestone (October 2018) | Milestone Q3 | Milestone Q4 | Target
|  | Planned | 60 | 60 | 60 | 60 |  | 240 | RISK RATING (Minor, Moderate, Major, Severe)
|  | Actual | [5 empty] | 0
Outcome Indicator 4
Total amount in MT of cargo (food, fuel and other cargo) discharged that was cleared by UNVIM.
|  |  | Baseline (October 2017) | Milestone Q1 (Jan 2018) - average of previous 3 months | Milestone Q2 April 2018) - average of previous 3 months | Milestone Q3 July 2018) - average of previous 3 months | Milestone Q4 October 2018) - average of previous 3 months | Target
|  | Planned | 565,000 Yemen monthly food need, 544,000 Yemen monthly fuel needs | 565,000 Yemen monthly food need, 544,000 Yemen monthly fuel needs | 565,000 Yemen monthly food need, 544,000 Yemen monthly fuel needs | 565,000 Yemen monthly food need, 544,000 Yemen monthly fuel needs | 565,000 Yemen monthly food need, 544,000 Yemen monthly fuel needs
|  | Actual | Food - 359,828; Fuel - 176,571 | Food - 301,793 MT (53% of Yemen's needs). Fuel 80,869 MT (14% Yemen's imports) | Food - 226,395 (40% of Yemen's needs). Fuel - 134,799 MT (24% Yemen's needs) |  |  | 0
Source
Outcome Indicator 5
The percentage of UN agency and NGO humanitarian plans that include joint communication and feedback and accountability mechanisms. - AGREED NOT IN A-R in October 2018
|  |  | Baseline (October 2017) | Milestone (April 2018) - average of previous 6 months. | Milestone (October 2018) | Milestone Q3 | Milestone Q4 | Target
|  | Planned | [5 empty] | 0
|  | Actual | [5 empty] | 0
DFID (£) |  | Source
DFID (£) | 0
OUTPUT 1 | Output Indicator 1.1 | [7 empty] | Assumption
| Key humanitarian programme cycle deliverables (e.g. YHRPs, HNOs and Periodic Monitoring Reviews (PMRs)) endorsed by the Humanitarian Country Team in a timely manner |  | Baseline (October 2017) | Milestone (April 2018) - average of previous 6 months. | Milestone (October 2018) | Milestone Q3 | Milestone Q4 | Target
The international humanitarian system supports coordination and supports strategic decision making and and ability to plan and respond to needs
|  | Planned | n/a | YHRP, HNO and PMR published and endorsed. | HRP 2018 | PMR 2018 | HNO 2019 | 4
|  | Actual | n/a | YNHO pubished December 2017; YHRP (Jan-Dec 2018) published Jan 2018. | Published Jan 2018 |  |  | 0
| Output Indicator 1.2 | Source | Documents published and distributed to partners and available on public OCHA website
Core OCHA Yemen IM products (Humanitarian Bulletin, 3W, Funding Update; and Humanitarian Dashboard) published by OCHA Yemen in a timely manner
|  |  | Baseline (October 2017) | Milestone Q1 (Jan 2018) - average of previous 3 months | Milestone Q2 April 2018) - average of previous 3 months | Milestone Q3 July 2018) - average of previous 3 months | Milestone Q4 October 2018) - average of previous 3 months | Target
|  | Planned | Monthly Hum Bulletin + monthly 3W + Monlty Funding Update + 2-monthly Hum Dashboard | Monthly Hum Bulletin + monthly 3W + Monlty Funding Update + 2-monthly Hum Dashboard | Monthly Hum Bulletin + monthly 3W + Monlty Funding Update + 2-monthly Hum Dashboard | Monthly Hum Bulletin + monthly 3W + Monlty Funding Update + 2-monthly Hum Dashboard | Monthly Hum Bulletin + monthly 3W + Monlty Funding Update + 2-monthly Hum Dashboard | Monthly Hum Bulletin + monthly 3W + Monlty Funding Update + 2-monthly Hum Dashboard
|  | Actual | Jul-Oct 2017: 4 Hum Bulletin + 4 3W+ 4 Funding Update CC + 2 Dashboard | Nov - Jan 2018: | Feb - April 2018 | May 2018 - Aug 2018 | Sept - Dec 2018
| Output Indicator 1.3 | Source | Documents published and distributed to partners and available on public OCHA website
The humanitarian leadership is informed by national and sub-national coordination bodies, ensuring effective humanitarian action.
|  |  | Baseline (October 2017) | Milestone (April 2018) - average of previous 6 months. | Milestone (October 2018) | Milestone Q3 | Milestone Q4 | Target
|  | Planned | Weekly HCT, fortnighly ICCM | Weekly HCT, fortnighly ICCM | Weekly HCT, fortnighly ICCM | Weekly HCT, fortnighly ICCM | Weekly HCT, fortnighly ICCM | 42 HCT + 20 ICCM
|  | Actual | n/a | July-Oct 2017: 8 HCT + 6 ICCCM | Nov 2017-Mar 2018: | Apr-Jul 2018: | Aug-Dec 2018: | Total:
|  | Source | OCHA
| Output Indicator 1.4 | WFP Post-Distribution Monitoring Surveys, WFP-DFID fortnightly calls, WFP external monthly and quarterly reports
Core OCHA Yemen IM products contain sex and disaggregated data
IMPACT WEIGHTING (%) |  |  | Baseline (October 2017) | Milestone (April 2018) - average of previous 6 months. | Milestone (October 2018) | Milestone Q3 | Milestone Q4 | Target
70% |  | Planned |  | ?? | ???
|  | Actual | [5 empty] | 0 | RISK RATING (Minor, Moderate, Major, Severe)
DFID (£) | Output Indicator 1.5 | Source | [6 empty] | Severe
WFP Post-Distribution Monitoring Surveys
|  |  | Baseline (October 2017) |  | Milestone (October 2018) |  | Milestone Q4 | Target
Planned
|  | Actual | [5 empty] | 0
Source
| 0 | WFP Post-Distribution Monitoring Surveys, EMOP
OUTPUT 2 | Output Indicator 2.1 | [7 empty] | Assumption
# UNHAS flights to/from Yemen per month.
The International humanitarian community has access to a safe, reliable and predictable air (and sea) transport service to and from Yemen by pre-agreed routes |  |  | Baseline (October 2017) | Milestone Q1 (Jan 2018) - average of previous 3 months | Milestone Q2 April 2018) - average of previous 3 months | Milestone Q3 July 2018) - average of previous 3 months | Milestone Q4 October 2018) - average of previous 3 months | Target | Aircraft serviceability as per contract (minimum X days every month) Security situation does not deteriorate to a point where air transport services can no longer function Timely receipt of notification of flight cancellation from crew / Occurrences warranting flight cancellations happen more than 12 hours before scheduled departure times Schedule for reviews received from QA Unit (WFP HQ) and security
|  | Planned | JIB-ADE-JIB=08 JIB-SAH-JIB=08 AMM-SAH-AMM=12 TOTAL - 28 | JIB-ADE-JIB=08 JIB-SAH-JIB=08 AMM-SAH-AMM=12 TOTAL - 28 | JIB-ADE-JIB=08 JIB-SAH-JIB=08 AMM-SAH-AMM=12 TOTAL - 28 | JIB-ADE-JIB=08 JIB-SAH-JIB=08 AMM-SAH-AMM=12 TOTAL - 28 | JIB-ADE-JIB=08 JIB-SAH-JIB=08 AMM-SAH-AMM=12 TOTAL - 28 | JIB-ADE-JIB=08 JIB-SAH-JIB=08 AMM-SAH-AMM=12 TOTAL - 28
|  | Actual | 39 flights | 20 | 29 |  |  | 49
| Output Indicator 2.2 | Source
| Total passengers transported per month | UNHAS monthly donor reports
|  |  | Baseline (October 2017) | Milestone Q1 (Jan 2018) - average of previous 3 months | Milestone Q2 April 2018) - average of previous 3 months | Milestone Q3 July 2018) - average of previous 3 months | Milestone Q4 October 2018) - average of previous 3 months | Target
|  | Planned | 800 passsengers per month | 800 passsengers per month | 800 passsengers per month | 800 passsengers per month | 800 passsengers per month | 800 passsengers per month
|  | Actual | 0 | 444 passengers per month | 854 passengers per month |  |  | 0
| Output Indicator 2.3 | Source
| % seat occupancy rate | UNHAS monthly donor reports
|  |  | Baseline (October 2017) | Milestone Q1 (Jan 2018) - average of previous 3 months | Milestone Q2 April 2018) - average of previous 3 months | Milestone Q3 July 2018) - average of previous 3 months | Milestone Q4 October 2018) - average of previous 3 months | Target
|  | Planned | >90% | >90% | >90% | >90% | >90%
IMPACT WEIGHTING (%) |  | Actual | Djibouti - Sana'a 82% Sana'a Amman 100% | Amman-Sana'a 47%; Djibouti-Sana'a 34% Djibouti - Aden 16%. | Amman-Sana'a 70% Djibouti - Sana'a 51% Aden - Djib - 31% |  |  | 0
Source
| Output Indicator 2.4 | UNHAS monthly donor reports
|  |  | Baseline (October 2017) |  | Milestone (October 2018) |  | Milestone Q4 | Target
Planned
|  | Actual | [5 empty] | 0
DFID (£) |  | Source
OUTPUT 3 | Output Indicator 3.1 | [7 empty] | Assumption
Flow of commercial goods to Yemen, including food, fuel, and medical supplies is supported by UN Verification and Inspection Mechanism | Average time taken for applicant ships to be verified or referred for inspection, following receipt of documentation | [7 empty] | Security situation does not deteriorate to a point where sea transport services can no longer function
|  |  | Baseline (October 2017) | Milestone Q1 (Jan 2018) - average of previous 3 months | Milestone Q2 April 2018) - average of previous 3 months | Milestone Q3 July 2018) - average of previous 3 months | Milestone Q4 October 2018) - average of previous 3 months | Target
|  | Planned | 48 hours (as an average of the previous six months) | 48 hours (as an average of the previous six months) | 48 hours (as an average of the previous six months) | 48 hours (as an average of the previous six months) | 48 hours (as an average of the previous six months) | 48 hours (as an average of the previous six months)
|  | Actual | 34 hours | 28 hours | 29 hours |  |  | 0
Source
| Output Indicator 3.2 | UNVIM reports
IMPACT WEIGHTING (%) | Proportion of vessels that applied for clearace inspected by UNVIM
|  |  | Baseline (October 2017) | Milestone Q1 (Jan 2018) - average of previous 3 months | Milestone Q2 April 2018) - average of previous 3 months | Milestone Q3 July 2018) - average of previous 3 months | Milestone Q4 October 2018) - average of previous 3 months | Target | RISK RATING (Minor, Moderate, Major, Severe)
|  | Planned | n/a | 40% of ships applying for clearance are inspected by UNVIM | 40% of ships applying for clearance are inspected by UNVIM | 40% of ships applying for clearance are inspected by UNVIM | 40% of ships applying for clearance are inspected by UNVIM
|  | Actual |  | (24 applied for clearance; 5 inspected) = 20% | (30 applied for clearace, 21 inspected)= 70%. |  |  | 0
Source
| Output Indicator 3.3 | UNVIM reports
Number of UK inspectors deployed in Dijbouti and regional hubs
|  |  | Baseline (October 2017) | Milestone Q1 (Jan 2018) - average of previous 3 months | Milestone Q2 April 2018) - average of previous 3 months | Milestone Q3 July 2018) - average of previous 3 months | Milestone Q4 October 2018) - average of previous 3 months | Target
|  | Planned | 0 | 7 | 7 | 7 | 7 | 7
DFID (£) | 0 | Actual | 0 | 5 | 5.5 | 4
Source
OUTPUT 4 | Output Indicator 4.1 | UNVIM reports
The international humanitarian community has access to a regular supply of fuel through WFP's revolving fuel facility to support their continued operations in country. | Amount (litres) of fuel stocks from the Fuel Facility available for humanitarian purposes.
|  |  | Baseline (December 2017) | Milestone 1 (June 2018) - average of previous 3 months | Milestone 2 (October 2018) - average of previous 3 months | Milestone 3 - (April 2018) - average of previous 3 months
|  | Planned | N/A | 6.5 million litres | 5 million litres | 5 million litres | 5 million litres | 5 million litres montly rotation of stocks
|  | Actual | N/A - Fuel arrived in Yemen on 26/02/18 | 6.5m litres (5m from Hodeidah, 1.5 from Aden) |  |  |  | 0
Source
| Output Indicator 4.2 | WFP
IMPACT WEIGHTING (%) | Amount (litres) of fuel from the Fuel Facility used for humanitarian purposes.
15% |  |  | Baseline (December 2017) | Milestone 1 (June 2018) - average of previous 3 months | Milestone 2 (October 2018) - average of previous 3 months | Milestone 3 - (April 2018) - average of previous 3 months | Milestone Q4 | Target
|  | Planned | N/A | N/A | 6.5 m litres (4.6 M for UNICEF/WHO, 0.4 M for INGO/UN humanitarian activities and 1.5 M buffer stock ) | 5 million litres delivered and invoiced to partners per month | 5 million litres delivered and invoiced to partners per month | 5 million litres delivered and invoiced to partners per month
|  | Actual | N/A | N/A (fuel arrived for distribution on 10/02). |  |  |  | 0
DFID (£) | 10000000 | Source
WFP
BASELINE | 2017-12-01
Milestone Q1 | 01 March 2018 (covering previous three months)
Milestone Q2 | 01/06/2018 (covering previous three months)
Milestone Q3 | 01/09/2018 (covering previous three months)
Milestone Q4 | 01/12/2018 (covering previous three months)