## Sheet1
PROJECT NAME | WB-DFID Partnership for Enabling the Business of Agriculture Trust Fund
IMPACT | Impact Indicator 1 |  | Baseline | 2014-06-01 | 2015-06-01 | (Target: June 2016) | - Political climate is conducive to agricultural policy/regulatory reform in the countries where we collect BBA data. - The process of agreeing to policy changes is inclusive and consultative at country-level
Improved enabling environment and regulatory reforms in the agricultural sector create greater business opportunities for commercially-oriented smallholders and agribusinesses.* | Relative shares of agriculture and agribusiness in GDP * |  | Current status (in BBA focus countries) |  |  | Increase over baseline growth rate.
Achieved
Source
EBA mid-term and end of cycle evaluation
| Impact Indicator 2 |  | Baseline | 2014-06-01 | 2015-06-01 | (Target: June 2016)
| Direct Compliance Cost Savings – being the cost reduction directly informed, influenced or recommended by EBA indicators | Planned | Current status | n.a. | n.a. | Decrease in cost by 5% or more in 10 countries for at least two BBA focus areas as a direct result of the BBA indicators dissemination
Achieved
Source
BBA mid-term and end of cycle evaluation
* The impact level is defined as a ‘Long term wide spread change’ which the outcome contributes towards. The impact statement clarifies how this research programme will contribute to improving the lives of people living in poverty. It clear that it is unlikely that it will be possible to measure any change at the impact level which is attributable to the programme within the life of a programme. Thus the impact is mainly there is order to clarify the ‘direction of travel’ and to explain the logical pathway by which the research programme is anticipated to lead to development impacts. The impact may also be used to guide post-programme evaluations.
OUTCOME | Outcome Indicator 1 |  | Baseline | 2014-06-01 | 2015-06-01 | (Target: June 2016) | Assumptions
EBA becomes a key policy tool for policymakers leading to indicator-informed regulatory reform ** | Countries' understanding of impact of agribusiness enabling environment is enhanced by dissemination of EBA reports. | Planned | Current status | outreach and dissemination plan finalised; external website launched; 3,000 website visits and 10 media clips | 50% increase over last year on website visits. Stakeholder outreach plan under implementation | 50% increase over last year on website visits. | - BBA target countries and agencies are receptive to the BBA approach.
|  | Achieved |  | Outreach plan under initial draft. External website launched (December 2013) 4,270 website visits. No media clips. | The website has received 12,851 visits, a 328% increase on last year. Outreach plan informally shared with CSOs | 28,217 total visits, an increase of 119%
Source
Outreach and dissemination plan, website traffic
| Outcome Indicator 2 |  | Baseline | 2014-06-01 | 2015-06-01 | (Target: June 2016)
| Number of countries actively using the EBA indicators to inform policy improvements. | Planned | n.a. | Discussions engaged with 2 countries to use the BBA indicators to inform policy. | Discussions engaged with 5 countries to use the BBA indicators to inform policy. | 10
|  | Achieved |  | Discussions engaged with 4 countries on BBA indicator use: Rwanda, Spain, Guatemala and Uganda. | Discussions with 8 countries on EBA indicator use: Ethiopia, Guatemala, Rwanda, Spain, Sudan, Tanzania, Uganda and Vietnam | 10 countries engaged: Cambodia, Cote d'Ivoire, Ethiopia, Guatemala, Laos, Russian Federation, Rwanda, Sudan, Tanzania and Vietnam
Source
Based on: (1) Global indicators and Analysis department experience with Doing Business and other policy work, (2) existing evidence and research using Doing Business data, (3) consultations with the WB Investment Climate-Advisory Reform Dept
| Outcome Indicator 3 |  | Baseline | 2014-06-01 | 2015-06-01 | (Target: June 2016)
| Number of laws/regulations/codes enacted or amended - being the enactment or amendment directly informed, influenced or recommended by EBA indicators | Planned | Lack of comparable tools and actionable information for policy makers and the private sector | n.a. | n.a. | 8 cases of laws/regulations/codes enactment or amendment initiated at country level inspired by the BBA project
|  | Achieved |  | n.a. | n.a. | EBA work has directly influenced regulations in two countries (Rwanda and Vietnam). The team are actively engaging with another eight (Cambodia, Cote d'Ivoire, Ethiopia, Guatemala, Laos, Russian Federation, Sudan, Tanzania)
Source
Same as source for Outcome Indicator 2
| Outcome Indicator 4 |  | Baseline | 2014-06-01 | 2015-06-01 | (Target: June 2016)
| Number of procedures/policies/practices/standards improved or eliminated - being the improvement or elimination directly informed, influenced or recommended by EBA indicators | Planned | Lack of comparable tools and actionable information for policy makers and the private sector | n.a. | n.a. | 8 cases of procedures/policies/practices/standards improvement or elimination initiated at country level inspired by the BBA project
|  | Achieved |  | n.a. | n.a. | Tthe EBA has directly influenced the improvement of procedures, i.e. developing seed ordinance and thus improving current practices in seed input markets regulations in Rwanda. As mentioned above, the EBA is closely engaging with nine other countries Direct impact in Rwanda. Actively work with nine others (Cambodia, Cote d'Ivoire, Ethiopia, Guatemala, Laos, Russian Federation, Sudan, Tanzania and Vietnam)
Source
Same as source for Outcome Indicator 2
INPUTS (£) | DFID (£) |  | World Bank Group (£) | Donors (£) | Total (£) | DFID SHARE (%)
| £ 3 mln |  |  | £4.4 mln | £14.3 mln | 21%
INPUTS (HR)
WB's EBA team, technical experts, DFID up to 0.1 FTE (Livelihoods and PSD Adviser combined)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2014-06-01 | 2015-06-01 | (Target: June 2016) | Assumption
Development and roll-out of Doing Business in Agriculture methodology | Number of regulatory indicators developed | Planned | 0 | 6 indicators: (1) Access to Finance, (2-3) Access to Inputs (seeds and fertilizer) (4) Access to secure property rights on land, (5) Access to markets, (6) Access to transport | 9 indicators: (1) Access to Finance, (2-3) Access to Inputs (seeds and fertilizer) (4) land, (5) Access to markets, (6) Access to transport, (7) Water, (8) ICT, (9) and Mechanisation. Gender and environmental sustainability integrated across relevant indicators | 10 indicator topic areas: (1) Access to Finance, (2-3) Access to Inputs (seeds and fertilizer) (4) land, (5) Access to markets, (6) Access to transport, (7) Water, (8) ICT, (9) Mechanisation; and (10) livestock Gender and environmental sustainability integrated across relevant indicators | - Data is collectable and local institutions have the capacity to collaborate with the project team.
|  | Achieved |  | Data collected on 9 indicator areas: (1) Access to Finance, (2-3) Access to Inputs (seeds and fertilizer) (4) Access to secure property rights on land, (5) Access to markets, (6) Access to transport, (7) Contract farming (8) Rural electricity, and (9) ICT | Indicators have been developed for six areas: seeds, fertilisers, mechanisation, transport, finance, and markets. Indicators for the land topic area are being developed following a more in-depth consultation, led by the World Bank lead economist on land. Additional data and indicator areas are being developed for livestock, water and ICT. Separate indicators are not being developed for gender and environmental sustainability. These areas will be integrated across relevant topic areas | Robust indicators have been developed for 10 areas: seeds, fertilisers, mechanisation, land, water, livestock, transport, finance, and markets. Data are presented on ICT, in addition to gender and environmental sustainability which are integrated across relevant topic areas. However, the analysis of the gender and environmental sustainability indicators is not yet sufficient. More detail and depth should be added, including seeking to integrate ‘Women, Business and the Law’ Indicators. Gender and environmental sustainability should have stand alone chapters in future EBA reports.
Source
BBA Annual Reports and Mid term Evaluation
| Output Indicator 1.2 |  | Baseline | 2014-06-01 | 2015-06-01 | (Target: June 2016)
| Number of countries in which regulatory indicators are rolled out | Planned | 0 | 10 Pilot countries | 40 countries | 60 countries
|  | Achieved |  | 10 | 40 countries | 62 countries
Source
BBA Annual Reports and Mid term Evaluation
| Output Indicator 1.3 |  | Baseline | 2014-06-01 | 2015-06-01 | (Target: June 2016)
| Number of regulatory indicator reports produced. | Planned | 0 | Pilot report | Second year report | Third year report
|  | Achieved |  | Pilot report published in November 2014 | Second year report due to be published in December 2015 | Third year report due to be published in February 2017.
Source
DBA reports published.
IMPACT WEIGHTING (%) | Output Indicator 1.4
50% | Number of workshops, seminars, conferences organized or co-organized | Planned | 0 | At least 1 event | At least 2 events | At least 2 events
|  | Achieved |  | 2 events - FAO seminar and SEEP conference | 3 events plus multiples informal stakeholder engagements | 9 events, in addition to 5 webinars
|  | Source |  |  |  |  | RISK RATING
|  |  | Event proceedings |  |  |  | Moderate
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
Up to £1.5 mln
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2014-06-01 | 2015-06-01 | (Target: June 2016) | Assumptions
Development of Deep Dive multi-country studies | Number of Market Metrics developed | Planned | 0 | 6 indicators: (1) Access to Finance, (2-3) Access to Inputs (seeds and fertilizer) (4) Access to secure property rights on land, (5) Access to markets, (6) Access to transport | 9 indicators: (1) Access to Finance, (2-3) Access to Inputs (seeds and fertilizer) (4) Access to secure property rights on land, (5) Access to markets, (6) Access to transport, (7) Water, (8) Rural electricity, (9) and Mechanization | 9 indicators: (1) Access to Finance, (2-3) Access to Inputs (seeds and fertilizer) (4) Access to secure property rights on land, (5) Access to markets, (6) Access to transport, (7) Water, (8) Rural electricity, (9) and Mechanization | Data is collectable and local institutions have the capacity to collaborate with the project team.
|  | Achieved |  | Metrics in 6 topic areas: developed (1) Access to Finance, (2-3) Access to Inputs (seeds and fertilizer) (4) Access to secure property rights on land, (5) Access to markets, (6) Access to transport. This data is not statistically robust nor comparable, and therefore not in a condition to be used or published. | Metrics are under development in 10 topic areas: (1) Access to Finance, (2-3) Access to Inputs (seeds and fertilizer) (4) Secure property rights on land, (5) Access to markets, (6) Access to transport, (7) Water, (8) Rural electricity, (9) and Mechanization (10) ICT | Indicators that capture practice-related dimensions of EBA topic areas continue to be developed, and will be presented in the 2017 Report for 5 topic areas: (1) Seed (2) Fertilizer (3) Agricultural machinery (4) Markets (5) Transport
Source
BBA Annual Reports and Mid term Evaluation
IMPACT WEIGHTING (%) | Output Indicator 2.2 |  | Baseline | 2014-06-01 | 2015-06-01 | (Target: June 2016)
50% | Number of DD reports produced | Planned | 0 | Pilot report | Second year report | Third year report
|  | Achieved |  | No separate report published. Some of the findings of the DD are incorporated in the first year report. | All reporting on these metrics will be integrated into EBA’s third year report | Refocussing of the project to policy relevant information. Policy focussed sections are included in the report. Results on these indicators will be reported in EBA's third year report.
Source
MM reports published.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%) | RISK RATING
| Up to £1.5 mln | [5 empty] | Moderate
INPUTS (HR) | DFID (FTEs)