Annual Review – Summary Sheet

Title: Municipal Services and Social Resilience Project (MSSRP)
Programme Value: £10 million		Review Date: October 2018
Programme Code: 300335	Start Date: 01/12/2016	End Date: 31/12/2020

Summary of Programme Performance
Year	17/18	18/19
Programme Score	B	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5654077.odt
DevTracker Link to Log frame:

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

The Municipal Services and Social Resilience Project (MSSRP) is a scale-up and restructuring of the World Bank-managed Jordan Emergency Services and Social Resilience Project (JESSRP), which ran from 2013 until 2018. The JESSRP was multi-donor funded with UK support, and focused on the objective of helping Jordanian municipalities and host communities address the immediate service delivery impacts of Syrian refugee inflows and strengthen municipal capacity to support local economic development.

The JESSRP was initially a three-year programme due to end in late 2016, but was extended into 2018 to allow delayed sub-projects to be completed. As a result, MSSRP was only finally launched in February 2018. This is therefore the first annual review to be completed after activities have started, but the second in total for MSSRP as it marks the 24 month anniversary of UK funding going into the multi-donor project in November 2016..

The MSSRP is being implemented according to a similar institutional setup to JESSRP and seeks to build on the progress towards the objectives of the programme, but with a greater focus on long-term development objectives and benefits to Jordan. The revised objective is: to support Jordanian municipalities affected by the influx of Syrian refugees in delivering services and employment opportunities for Jordanians and Syrians. MSSRP supports the delivery of municipal services in 26 communities (21 will be receiving municipal grants, with a further 5 (26 total) having access to the Innovation Fund) that are hosting large numbers of Syrian refugees by (i) improving the quality and direction of service delivery; (ii) financing activities that create job opportunities for Syrians and Jordanians through partnerships with NGOs and the private sector, and (iii) delivering an increased focus on building the capacity of the Ministry of Municipal Affairs (MOMA) and the Cities and Villages Development Bank (CVDB) to achieve more sustainable, transparent and accountable service delivery.

Additional finance to MSSRP has expanded the coverage of JESSRP to include seven additional highly-stressed municipalities (from 14 to 21), to respond to risks to social cohesion and to deficiencies in core services. The additional finance will: improve consultation processes, improve the inclusion of women in decision-making processes, and establish an innovation Fund (IF), to provide employment opportunities for Syrians and Jordanians and encourage a long-term developmental perspective. The IF will be allocated on a competitive basis to municipalities to encourage a more commercial approach to their thinking. Bids will be prioritized and selected based on the following criteria:
(i)	focus on women, youth, and marginalized populations as direct beneficiaries;
(ii)	works that require a high labour component;
(iii)	employment generation potential for Syrians and Jordanians;
(iv)	established partnerships with private sector actors and NGOs.

Summary of progress and lessons learned since the last review

There has been a keen focus on learning from the JESSRP programme, during the launch of MSSRP and the finalising of the Project Completion Review for JESSRP. The programme has established a basic activity based results framework, but this is now being revised into an enhanced framework that will be in turn translated into a DFID log frame. While this is being done the review team has, therefore, assessed the programme against its work plan to identify activities that are and are not on track. The review also seeks to analyse if lessons have been learned from the previous programme, JESSRP.

Overall the project scores an A – broken down as follows.

- Output 1, Project Initiation; B, 10%
- Output 2, Municipal Grants, A, 60%
- Output 3, Innovation Fund, B, 20%
- Output 4, Capacity Building, A, 10%

Summary supporting narrative for the overall score in this review (1/2 page)

Progress against the workplan has shown the benefits of building on the back of the completed JESSRP, with established relationships allowing the municipal grants procedure to continue at full speed. The addition of a new and improved focus on consultation has been completed in all areas albeit with lessons to be learnt ahead of any future round of bidding on improving the quality and access of consultation. However, the critical Programme Operations Manual has still not been signed off because of several ongoing rounds of editing – and progress is behind schedule on the Innovation Fund (IF) caused by delays in recruitment and agreeing the best way forward. The team heard good arguments for investing time in getting the IF right now, and these delays ultimately do not change the overall score for the project. The last area of capacity building is on track with the ILO contract agreed, the plan in place and activities fully underway.

Recommendations for the next year (1/2 page)

Recommendations:

1. Log-frame: The project team and the World Bank should ensure that the enhanced results framework is completed by the end of the 2018 calender year. The project team should ensure this is translated into a DFID log-frame to support results tracking in future years. The results should keep a strong focus on the effects of the programme on social cohesion between refugee and host communities and between people and the state (as represented by the local authority).
2. Programme assessment and Learning: The World Bank should complete its baseline for the Results Framework and consider a mid-term review of progress, in addition to the end of project assessment. In addition, the pilot Innovation Fund should be separately reviewed during its implementation to capture whether the assumptions hold and the accuracy of the theory of change.
3. Donor engagement: The UK project team should continue to engage with other donors building a strong understanding of their priorities and helping to ensure where possible a common message can be delivered to the World Bank. One area to examine is whether greater World Bank staff presence in country would be in the interest of all donors and allow the project team to step back from its active partner role, including helping to facilitate communications between the World Bank and the PMU.
4. Community engagement: Lessons should be drawn from the outreach and engagement phase of the municipal grant to inform the next round. In particular the opportunities of online streaming platforms could be explored to greatly enhance the reach and engagement rate of the consultations as well as how to better include the views of people with disabilities. The Innovation Fund meanwhile is currently lacking a community outreach phase. The WB and PMU should reflect on whether this is an oversight. Community engagement in both components would likely build improved participation, both in terms of turnout and engagement of harder to engage groups of women, under 25s and Syrian refugees.
5. Investments: Particularly on the municipal grants the steering committee should discuss whether growth boosting options should be weighted more heavily to encourage lasting effects on local communities. If agreed this should be built into municipal capacity building and outreach so that residents in each area have a greater sense of the options and benefits of a growth orientated choice.
6. Communications and Accountability: The communications team should continue to engage donors and municipalities in a range of platforms in order to create a rich dialogue with communities. Support should be aimed at the smallest and newest municipalities where the capacity gap is most telling. Fundamentally the Grievance Response Mechanisms in PMs should be systematised and training developed to ensure data from online and log books can be collated, the effectiveness and timeliness of responses reviewed, and ultimately that communications becomes a visible reflection of the attentiveness of municipalities to citizen concerns.

List of Acronyms

AA	Administrative Agreement
AR	Annual Review
AF	Additional Financing
CVDB	Cities and Villages Development Bank
GoJ	Government of Jordan
(J)ESSRP	(Jordan) Emergency Services and Social Resilience Project
MDTF	Multi Donor Trust Fund
MOMA	Ministry of Municipal Affairs
MOPIC	Ministry of Planning and International Cooperation
MoF	Ministry of Finance
MSSRP	Municipal Services and Social Resilience Project
MST	Municipal Support Team
NGO	Non-Governmental Organization
PMs	Participating Municipalities
PMU	Programme Management Unit (part of MOMA)
TA	Technical Assistance
WB	World Bank

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Project Initiation
Output number per LF		N/A	Output Score	B
Impact weighting (%):		10%*[1]	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)
[1] *Provisional in absence of Logframe

Indicator(s)	Milestone(s) for this review	Progress
Finalize the MSSRP Programmes Operations Manual and Results Framework	Partially Complete	The POM is drafted and awaiting final comments and approval from the World Bank. It has been turned into a living document so will be updated periodically. The Results Framework is being enhanced with new baseline data
Finalise MSSRP Plans	Partially Complete	All plans have been approved except for the Innovation Fund plan. Completed plans are: Communications Plan, the Gender Action Plan, Monitoring & Evaluation Plan, Outreach Plan and Capacity Building plan The Innovation Fund plan is awaiting final comments and approval see output below.
MSSRP project launch workshop	Complete	Completed on 25 February 2018

Provide supporting narrative for the score

- Nearly all plans are finalised and agreed, but some outstanding concerns are taking time to resolve which means three key documents are yet to be signed off namely: the Programme Operational Manual (POM), the Innovation Fund plan and the results framework.
  - During the review period the POM was expected to be approved imminently and while the delays have not impacted on the first round of project selection, it is a key milestone document which affects the output score.
  - More time is being taken with the Innovation Fund to ensure that it successfully has a private sector focus and achieves high social and labour impacts. Slow completion of this product has had a knock on effect on IF progress.
  - The results framework is completed but the baseline data is being updated after donor concerns required a rethink. The initial draft was based on an independent end-line survey for the JESSRP but lacked any measure linking improvements in local government services to social cohesion. The World Bank is now undertaking a JESSRP impact evaluation to be able to address this issue and will then deliver an enhanced baseline for MSSP. This should allow a more effective measure of the programme theory of change.

The recruitment of subject specialists to the PMU has faced delays, despite the exemption for PMU posts from the broader public-sector recruitment freeze caused by GoJ budget restraints. At the time of the review PMU was still lacking a Monitoring and Evaluation specialist (a recent vacancy) and Innovation Fund specialist among 5 current vacancies. Despite this, many of the PMU posts have been filled since the programme’s launch in February 2018.

The MSSRP project launch workshop took place on 25 February 2018 and successfully established a list of Participating Municipalities and allocations for projects. One municipality was initially concerned with the lack of funds allocated and suggested withdrawal from the programme. The PMU was able to explain the funding formula and re-engage the municipality in the programme.

Lessons identified this year, and recommendations for the year ahead linked to this output

The PMU has successfully built on the lessons from the JESSRP and continued to maintain strong relationships with continuing municipalities as well as expand to the new participating municipalities. Concerns and misunderstanding about the formula for the allocation of funding should be reflected in clear communications, outputs and transparency in any future funding round to offset concerns early; this will be important in the Innovation Funds, where some municipalities do not receive funding.

The CSSF project team should continue to encourage the PMU and the World Bank to work together more closely, to prevent long delays in the delivery of the enhanced Results Framework and other MSSRP plans, such as the Communications Plan. It could do this in collaboration with other donors and if necessary set deadlines with the implementing partners for the completion of key documents to prevent knock on delays.

The PMU should seek to recruit staff more quickly, to ensure that specialists are in place as early as possible for the implementation of the programme.

Output Title	Municipal Grants (First Round)
Output number per LF		N/A	Output Score	A
Impact weighting (%):		60%*	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestone(s) for this review	Progress
Public consultation	Complete	100% Complete
Shortlisting of projects	Complete	100% Complete
Assessment by municipalities	Complete	100% Complete
Agreement by Steering Committee	Complete	100% Complete (49 Projects)
Procurement	In progress	In progress

Briefly describe the output and provide supporting narrative for the score

The Municipal Grant element of the project is open to 21 municipalities selected by the percentage of Syrians refugees they are hosting.

- Public consultation for the use of Municipal Grants has been completed. This is a positive result, as 129 consultations were completed within 20 municipalities in the opening months of the programme (the final municipality has since caught up). Many municipalities are unaccustomed to such a consultation process, therefore capacity-building and completion of these consultations is a good step forward. According to the summary, the community consultations saw 5,963 people participate. Specific focus groups in some areas were held for disabled residents and youth. The disaggregated breakdown saw:
  - Jordanian men: 2060 (35%)
  - Jordanian Women: 1345 (23%)
  - Male Youth: 786 (13%)
  - Female Youth 785 (13%)
  - Male Syrians 551 (9%)
  - Female Syrians 436 (7%)

It is not clear how well the consultation process was advertised, or whether the participating residents featured many of the most marginalised community members. The form of engagement was mainly public town hall events, which may not be as accessible to marginalised groups, such as women and disabled people. However, examples were given of specific groups asking for their needs to be recognised with improved disabled access to parks, and investment in community halls/ meeting places and sports spaces.

After consultations, municipalities checked to assess whether community needs fully matched the prioritised projects. The municipality councils then approved the community selection, and commissioned procurement and work plans to be drawn up.

The two technical committees (equipment and construction) reviewed the plans to determine their viability.

Once the technical committees completed their work, the projects were referred to the overall Steering Committee consisting of the Secretary Generals of the Ministry of Planning and International Cooperation (MOPIC), the Ministry of Municipal Affairs, the CVDB, two rotating Governors, and two rotating Mayors. This group ensured the projects matched the needs of the people, had been verified at the appropriate levels, were appropriately ambitious, and would deliver benefits that would be widely distributed. In three cases the Steering Committee required further information and commissioned additional feasibility studies. In total all 49 projects from the first round of commissioning have moved forward. 22 projects are currently being advertised for tender and 6 have been awarded. A second round is anticipated later in the project funds permitting.

Graphics below in USD show how the multi-donor investments are being disbursed.

As the MSSRP is using a developmental approach there is an added emphasis on sustainability that was not critical under the earlier JESSRP. Critically, this includes ensuring that plans for maintenance are in place and the council is committed to funding these projects going forward. Another shift is the focus on social projects over spending on equipment. JESSRP spent 28% on equipment and 12% on social projects. By contrast MSSRP has tripled social project spending as a percentage of grants with equipment now less than 2% of expenditure.

Lessons identified this year, and recommendations for the year ahead linked to this output

The selection of municipalities based on refugee presence is an extension of the JESSRP and limits the scope of the programme to addressing only one range of pressure and inequality. A review of basic municipal services nationally could reveal a different set of priority municipalities that would also shift the focus to broader stability. While the innovation fund is an extension into the south, as the programme progresses the narrative on refugee presence might become less and less compelling politically if south-north, rural vs urban inequality grows in prominence. This may need to be reflected in the communications strategy.

The PMU noted that there is list of priorities for municipalities linked to decentralisation. Although each council was free to choose their own investment priorities with the community, when the PMU compared the shortlisted ideas with the decentralisation list they noted that all but three were the same. This convergence builds confidence that the choices reflect the genuine needs of the community.

Late in October 2018, the PMU revealed that they had also now checked the projects submitted to the steering committee with the public consultation winners. They discovered that in some cases (number not shared) municipalities had disregarded the public choices for other priorities, notably Mafraq where the council sent a road building proposal to the committee. The municipality has been asked to explain and adjust their choice as appropriate. This is an example of good accountability mechanisms working inline the project rules. However, it also shows that governance norms will not easily change in local authorities. The World Bank will be documenting this case and lessons arising ahead of the next round.

One commentator thought the choice of investment projects was insufficiently strategic and would not generate further growth, noting that 50% or more of the projects were linked to road rehabilitation. This person suggested growth potential should be a new criterion to favour investment in public transport (including bus shelters) which they felt was a major impediment to employment and local enterprise. This is to be considered against the basic lack of quality roads in Jordan and the wide benefits that this can encourage. As one of the main responsibilities of municipalities is planning and facilitating actions to increase economic and social development and enhance livelihoods, a second phase might weight heavily in favour of services that make a locality attractive for investors and business development.

Assessment by municipalities has largely been successful, however there are some concerns about the process for informing unsuccessful municipalities. Some municipalities have less experience of applying for funds as per the MSSRP process. Where municipalities are not successful in the Innovation Fund state, the PMU should provide full feedback to improve their capacity and encourage stronger proposals in the future. Equally, in the few incidents where the steering committee sent back bids for greater analysis, the PMU should maximise this learning opportunity.

Turnout for the consultations looks impressive but a similar exercise in one municipality that was streamed online in another project succeeded in getting 20,000 views for one consultation alone. Ahead of a second round of grants, the project team should consider a mid-term evaluation to review how effective the townhall format is for the participation of women, youths and Syrian refugees, as well as those with disability, residents who live some distance from the town hall or the elderly. Varied outreach methods might be used and tested to attempt to secure the maximum number of participants from marginalised groups in the second round.

Procurement is on-going. According to the workplan, procurement of goods, services and civil works began in August and along with implementation, supervision and compliance checks are now expected to continue until the end of September 2019.

Output Title	Innovation Funds
Output number per LF		N/A	Output Score	B
Impact weighting (%):		20%	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestone(s) for this review	Progress
Comprehensive guide finalised	Approved	In progress
Project proposals finalised	Complete	Not started
Selection of projects	In progress	Not started
Procurement	Not started	Not started

Provide supporting narrative for the score

The Innovation Fund process is behind schedule due to delays in developing the implementation manual and recruitment of the Innovation Fund specialist. Of these the recruitment delays have probably had the greatest effect as this has delayed the launch workshop. By contrast the manual, while it has had a series of iterations and is awaiting approved, will remain a living document that is updated regularly.

The process for the Innovation Fund includes competitive bidding for funding by municipalities; for many, this is a new experience used as they are to receiving funding directly and perhaps not yet appreciating that they cannot bid for the whole funding pot. As the Innovation Fund disbursement will only be done once and is quite different to what has gone before, the review team heard partners express their interest in getting the manual right rather than pushing ahead too rapidly. Three areas are new: a) Competitive Bids, b) Higher Labour content, c) A focus on social impact not only infrastructure. It is a pilot, potentially globally, but it is not being separately reviewed for learning purposes.

Unlike Municipal Grants, the Innovation Fund does not involve significant community engagement. This approach was defended by one informed stakeholder who suggested that ideas for job-creation should come from technically able universities or think tanks, rather than local communities. However, this is a potential missed opportunity to hear from local people to identify ideas and reinforce some of the community engagement methods used in the Municipal Grants.

Research by the International Labour Organisation (ILO) for the IF concluded that at least 30% of grants should be spent on wages, to ensure that the focus is on creating job opportunities. The World Bank has agreed to the Jordanian government’s request for 70% of jobs to go to Jordanian people and 30% of jobs to go to Syrian refugees. This may help to reduce potential sources of conflict between host communities and refugees.

The ILO is also heavily involved in building capacity of municipalities and private sector actors with a significant portion of the budget supporting their work. Underway is the development of guidelines on decent work standards and labour-intensive work practices. Technical support will be offered during the procurement and contracting stages (specifically to contractors on how to make their bids labour intensive), and further analysis and monitoring will be run once the projects are underway. Included in this will be the training of youth to monitor activities on site.

Lessons identified this year, and recommendations for the year ahead linked to this output

There is an ongoing risk that the high labour content may generate a focus on low skill manual work which may be shunned by the local host community and lead to an over reliance on Syrian labour. The project team and PMU should be flexible in this approach and share lessons on how jobs in certain sectors may appeal to different communities. This may not be universally applicable as municipalities have different demographics, and host/refugee communities may have different skillsets. The project team and PMU should aim to create jobs in industries that appeal to both host and refugee communities, to encourage socialisation between the communities and further reducing the risk of conflict.

While job creation is a critical criterion for the project theory of change, where there is scope to include the development of opportunities in key competitive economic sectors locally, these should be encouraged and taken up.

A formal learning track should be established around the IF pilot to capture what works and does not work in Jordan in support of building global evidence around this model.

The Innovation Funds aim to create jobs and focus on women and youth. With women in particular, there are existing barriers to work that have to be overcome from a lack of affordable public transport options; a real difficulty in finding childcare; and cultural norms around segregation. The project team and PMU should ensure that these considerations are incorporated in the design and delivery of the IFs, particularly in more conservative areas.

Output Title	Capacity-building for municipalities
Output number per LF		N/A	Output Score	A
Impact weighting (%):		10% *	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestone(s) for this review	Progress
Work of Technical Staff in PMU	Experts Hired	In Progress
Delivery of the ILO contract	Contract Signed	Completed
Delivery of the Capacity Development Plan	Plan Finalised	Completed

Briefly describe the output and provide supporting narrative for the score

Under the smaller, second component of the programme Institutional Support and Project Management the project aims to deliver high quality technical expertise through the way in which the project is implemented. Much of this has already begun through the work of the technical experts working through the PMU. For instance, the community outreach and consultations were directed by two Amman based experts with focal points in each municipality trained for this purpose. Their work is aimed at engaging greater numbers of youth, women, refugees and the disabled in the consultation process, which in turns should benefit social cohesion by allowing all community members to have a say.

The assumption is that with the right technical support, through the ongoing work of the first component the municipalities will emerge with greater strategic, financial planning, investment/project planning, and safeguarding competency.

The ILO has already produced a range of manuals and instructions tailored to the types of municipal service activities typically implemented in Jordan, and specifically based on a sampling review of implemented activities under JESSRP. Given ILO’s unique expertise, it was agreed that the PMU would contract ILO, to develop guidelines and specifications on labour based methodologies for different categories of works in municipal services; (b) provide capacity building for MoMA, CVDB, participating municipalities, and contractors, and technical support on labour-based technology during implementation of works. The ILO will also monitor progress in achieving the objective of the labour-intensive activities.

The capacity development plan was finalised in mid-October however delivery of formal trainings had already begun going back to the beginning of the project. Trainings were delivered in the first two quarters of the project in Procurement, Participatory Community Outreach, M&E, Communication, Gender, Project Implementation Support, Environmental and Social Safeguards, Finance and Project Planning.

Lessons identified this year, and recommendations for the year ahead linked to this output

19 of the 26 municipalities covered by the project are also supported in the USAID funded CITIES programme that invests heavily in capacity building. The PMU and World Bank have coordinated closely with USAID to ensure there is no duplication and to focus very much on additional needs taking into account existing assessments of capacity and resources. MoMA has its own capacity building plan for municipalities to help coordinate donor engagement.

The focus on delivering the municipal grants risks leaving the much smaller capacity building component under monitored. The results framework focuses on how effectively municipalities implement gender and youth priorities, but also contains results on public financial management, strategic and urban planning. These should be captured in the DFID logframe.

The capacity building component is well placed to not only support delivery of infrastructure investment but also the function of municipalities to partner with the private sector and civil society in pursuit of long term development. This commercial and civic awareness might be separately measured and targeted.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

The MSSRP responds to social tensions caused by the local impact of the influx of Syrian refugees at the municipal level, through enhancements in the relevance and quality of municipal services. Activities under the MSSRP are primarily aimed at (re)building trust between urban residents (host and refugee communities) and municipal authorities, in order to address social tensions and, in turn, promote peace and stability. The project works at both horizontal tension (between individuals and groups) and vertical tension (between those groups and the institutions that govern them).

The theory of change for the project is outlined below.
Service delivery:
If communities experience improvements in access to (and quality of) services; Then grievances over resource competition will be addressed, and there will be a corresponding increase in positive perceptions of the other community.

Municipal governance:
If the municipalities are responsive to the local needs of Jordanian host communities and Syrians; Then individuals will be less likely to allow grievances related to perceptions of inequity to exacerbate fault lines of social tensions;

Participation, engagement and voice:
If the social and economic interactions of Jordanians and Syrians improve, Then their mutual positive perceptions and trust will improve.

The input of additional resources and technical support for MoMA and the municipalities (with CVDA oversight) are intended to deliver a number of outputs including additional services and job creation. The method of working involves meaningful consultations with local communities, aiming for improved service delivery in municipalities, a higher level of capacity within MoMA and greater trust between municipal authorities and local citizens. The Innovation Fund, which has not yet launched, aims to create job opportunities/work experience and improve social cohesion between Jordanian host communities and Syrian refugee communities, with a particular focus on women and youths.

Over the past seven months, the programme has identified 49 projects across 20 municipalities, ranging from a multi-purpose gym to a vocational training centre. Many of the projects relate to road construction or improvement, as chosen by the local community who possibly place a premium on quick win projects rather than longer term initiatives that require more trust in institutions to deliver.

The evidence to show that these outputs lead to the outcomes has not yet been collected, and is therefore to date anecdotal. Stakeholders in Mafraq and Zatari reported greater engagement with the local community as a result of JESSRP and MSSRP, however engagement beyond the remit of these two programmes is not clear.

The review team found no evidence of instability at present in the affected municipalities, despite the large influx of refugees. This may indicate that rhetoric ‘blaming refugees’ has calmed and project had a positive effect on cohesion since the start of JESSRP, or that community resilience was higher than initially thought, or that the financial capability of municipalities has developed to meet the challenge. In all likelihood it is all of the above. The new enhanced results framework with a cohesion indicator in the baseline will allow these themes to be examined and tested in more detail.

However, despite overall stability, stresses are evident. In one municipality that is new to the project the Mayor spoke about the issues of solid waste, the pressure on schools, the extra-long lines in the health centre and the high numbers of unemployed. Stakeholders also tended to identify state-citizen relations as the fragile axis in Jordan, with the arrival of Syrian refugee populations leading to frustration with the state rather than directly with Syrians.

In terms of change, the project team may wish to update the Theory of Change to include the Innovation Fund. In particular to gather evidence on whether Jordanian and Syrian employment creation with a focus on women and youths has a positive effect on social cohesion.

Additionally, the end line evaluation for JESSRP highlighted that social projects were more closely linked with community satisfaction than capital projects. More detail could be added to the theory of change to explore this difference. In response, there has been a shift in project selection within MSSRP towards more socially relevant projects and the Innovation Fund is much more closely aligned to this. However, municipalities still have to build roads and collect waste, which while not particularly innovative is very important. Solid waste management was the main service put under immense pressure when the refugees first arrived, and served as a very visible reminder of how the government was not responding to the needs of an increased population. Comparing across these services could generate insights into the different cohesion or governance effects of social and capital projects.

In contrast to the existing theory of change, the review team found stakeholders who felt the focus on refugee and Jordanian cohesion should be an outcome of greater economic activity at the local level and the generation of revenues for the municipality to spend. This rival approach would argue for a sectoral specific investment programme, rather than a community driven development approach. Emphasis would be put on promoting local development partnerships with the private sector and community groups, building the local to national partnership required to leverage funds and expertise into local authorities, and building infrastructure to match the competitive advantages of different areas.
Some of these ideas can be built into the Innovation Fund, but ultimately it describes an economic goal progamme rather than an identity and cohesion project.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

The MSSRP was launched in February 2018, and the Results Framework is still being finalised. The programme has shown good progress on activities over the past few months in both Component 1 and Component 2 including launching the programme, delivering capacity-building to local municipalities and completing community engagement as part of the Municipal Grants programme. There are still gaps in the PMU, particularly the M&E specialist and the Innovation Fund specialist, however there should soon be filled. There is a delay with the Innovation Fund, however this requires further consideration to ensure that risks are mitigated, before the manual can be agreed and the launch can take place.

The DFID logframe is not yet available however, based on the results framework outcomes are likely to be in the following areas:
- Beneficiaries feel investments under MSSRP reflected their needs, and are satisfied with the performance of their respective participating municipalities
- Access to services improves
- Measures of social cohesion improve related directly or in part to MSSRP
- Participating Municipal Authorities demonstrate more inclusive, transparent and accountable governance

No data has been collected in these areas yet, both because the baseline is being redone, and because the first year of data will be collected at the end of the 2018 calendar year.

Explain major changes to the logframe in the past year (1/2 page)

The DFID logframe is still in draft and has not yet been agreed with the World Bank.

Describe any planned changes to the logframe as a result of this review (1/2 page)

The logframe should be finalised by the end of 2018.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

The MSSRP is subject to the World Bank’s regular project procedures, which includes the requirement for an economic cost benefit analysis. This analysis will be carried out by the World Bank’s MSSRP team, with economic expertise being brought in from other sections of the Bank. The World Bank has agreed to include VfM indicators in the Results Framework.

Economy
Contracts are awarded by competitive procurement. The PMU conducts procurement in-line with World Bank and Jordanian standards. Any large-scale procurements for single items with a value above 300,000 JD are handled centrally by CVDB in line with the World Bank procurement rules. Under 300,000JD, the Government of Jordan’s rules apply. In some cases, the review team heard that these were stricter than the World Bank. For instance, if only a single bidder applies for a contract under GoJ rules the tender must be relaunched.

The PMU will continue to carry out large scale purchasing (often across multiple municipalities), as it has done under JESSRP, in order to ensure the best VFM. This large-scale purchasing has been successfully used within JESSRP, especially in the field of waste management (compactors, containers, vehicles), and PMU will seek to extend this more widely for MSSRP.

Efficiency
The Business Case identified the World Bank’s pooled funding as a means of ensuring greater efficiency in delivery and alignment across the international community, which remains the case. The project team should ensure the World Bank includes indicators for efficiency within the Results Framework. The review team found anecdotal information on efficiency that would at scale tell a compelling story. For instance, in the Mafraq municipality the community had elected to invest in solar power for street lighting. The Mayor expected this to save a large sum of money which could then be reinvested in essential services which he listed as solid waste management, infrastructure, and attracting inward investment into satellite factories for manufacturing in the Zarqa free zone. At scale the reinvestment of savings from the programme could be a useful measure of efficiency. Additionally, the project could measure increases in municipal revenues generate by any economic stimulus caused by investment in local infrastructure.

Effectiveness
The VfM indicators should consider effectiveness in the broadest sense, including to ensure the programme engages with a diverse range of people and caters to marginalized groups. This might include data on option preference by groups with specific characteristics and whether these are prioritized for development.

The project completion report for JESSRP highlighted the sustainability of infrastructure projects in the future as a risk. The project team is managing this risk, with municipalities now required to agree a maintenance plan for the Municipal Grants to ensure that infrastructure is effectively managed. The project team should also measure the long-term accountability processes and citizen engagement that would help to ensure the sustainability of projects. One initiative which will be rolled out next year in every municipality is the Citizen Score Card approach to measuring changes in service delivery quality, but in itself is a catalyzing resource for improving state-citizen dialogue.

Equity
The draft Results Framework includes disaggregation of data into categories of women, youth and Syrian refugees. This will be an important tool for understanding equity and the reach of the programme. An additional measure could be the change in access to quality services across governorates and whether the interventions support narrowing the gap between the highest and lowest performing municipalities.

The Innovation Fund will try and promote greater equity in the project, as it is specifically designed for job creation with a focus on women, youth and marginalized populations. However, there is a risk that the IF will negatively affect smaller municipalities with fewer resources available to devote to bidding for funds, and because it cuts out the consultation activities may lose out on the best or broadest ideas.

Expenditure:

The total budget for the programme is $30m. As a multi donor trust fund costs are not ear marked to specific donor grants. The UK contribution to date is £10m which was disbursed at the end of 2016.

	Agreed budget for Year 1	Budget for 7 months (given late implementation due to the delay in money transfer)	Actual disbursement for period to end of August 2018	Balance held	Actual Balance	Variance (%)	Actual variance (%)
Component 1	$19m	$11.08m	$3.5m	$15.5 (of which $5m for the Innovation Fund.)	$7.58m	-81.6%	68.4%
Component 2	$1m	$583,333	$436,000	$563,729	$147,333	-56%	25.2%
Total	$20m	$11.66m	$3.936m	$16.064m	$7.724m	-80.2%	66.2%

Financial controls are strong and expenditure is on track with the workplan. CVDB has a core role and expertise in tracking expenditure and disbursing it when required. While $3.5m has been disbursed to PMs in anticipation of construction beginning, expenditure is expected to ramp up when construction gets fully underway. The table above only reflects part of the year’s expenditure and covers the low spending initiation period.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

The Results Framework, which will include VfM indicators, has not yet been finalised. These will provide an ongoing assessment of VfM in the programme, including on the 4 Es.

E: Risk and Conflict Sensitivity (½ to 1 page)

World Bank managed Multi-Donor Trust Funds (MDTFs) are a low risk way to manage aid in Jordan. The GoJ stated in their National Resilience Plan 2014-16 (which sets out the international response to support host communities affected by the Syrian refugee crisis) and the Jordan Response Platform 2015 (JRP) that the MDTF is their preferred modality for donors to provide support to municipalities. The JRP specifically states that “the government encourages the international community to make use of the existing WB Trust Fund”.

Overview of programme risk
Below is a summary table of the top four risks for the MSSRP.

Risk	Direction of travel	Likelihood	Impact	Mitigation action
External / Community tensions escalate to conflict, e.g. driven by frustration with local authorities/Government or refugees and host communities.	Increasing	High	High	Observe and study drivers of conflict and target the most vulnerable communities in Jordan. Build on strong relationships with host communities, engage municipalities and governorate councils and key figures in project implementation. Continue to bring refugees and host communities together through social cohesion events and build capacity of local government institutions.
Context on Project / Social norms making it difficult for women to participate in a meaningful way in decision-making bodies and therefore strengthening traditional gender roles	Stable	High	Moderate	Include gender-specific indicators in RFs and ensure formal targets for women's participation in decision-making bodies. Provision of minutes and reports of decision-making forums to ensure participation by women. Appointment of gender specialists to promote inclusion and focus on gender awareness training and enhancing the voice of women. Promote agility in the programme to allow it to draw from gender research included in the programme.
Project on Context / Programme activities are not sustainable and tensions rise once the infrastructure projects are complete and the PMU exit	Stable	Moderate	Moderate	Ensure selection process for projects includes sustainability criteria. Work with the PMU on defining their exit strategy and strengthening the use of social accountability tools. Ensure the PMU provides ways for local government leaders to continue to engage with the project and embrace the decentralisation process.
Project Management / Overlap in assistance between organisations which results in duplication of effort, ineffective use of resources and uneven distribution of support at local level	Stable	Medium	Moderate	Ensure that the IPs are proactive in communicating and sharing information with other organisations including mapping exercises. Close co-ordination with the diplomatic corps and across embassy to ensure programmes are mutually supportive/not duplicating. Good communication with MOPIC should spot any duplication/contradictory programme efforts across the IC.

The first three risks are related to conflict sensitivity and the responsibility placed on the programme to Do No Harm. The ongoing context monitoring, and the recognition that the programme can lead to tensions as well as be affected by evolving tensions is an important one. So too are the actions committed to as part of a conflict sensitive approach. The project places ‘a premium on communication and outreach within the purview of the project and PMs’ [Project Paper, Dec 2017, Para 28].

This is reflected in the level of training to communication focal points based in municipalities to encourage them to reach out to their constituents using a range of methods including social media. An assessment report on communication tools in municipalities has been prepared, along with a communications guideline for PM. Some municipalities, such as Al-Khaldiyah, are already using communications methods extensively with the local community, for example through regular updates of a Facebook page. This has benefits of being transparent and accessible to internet users, with responses to concerns or questions logged for others to see. However, more needs to be done to systemise the Grievance Response Mechanisms (GRM) that exist. The review team heard that the PMU staff had access to complaints logs at the PM level. This combined with online data could generate powerful insights into whether the projects were aligning with community needs and expectations. Necessarily, complaints must be linked to a response to demonstrate municipal accountability and concern for the views of citizens.

The project has considered the risk of local market distortions by setting a 300,000 JD threshold for suppliers following world bank rules, which is beyond the level that local businesses would normally operate. Below this threshold procurement is listed in local newspapers advantaging suppliers in the immediate area. Bid are sealed and opened in a public meeting to build trust in the procurement process.

The World Bank process picked up other concerns that were absent from the law in Jordan. Form 8c covering social screening and resettlement showed how municipal land was being used by Bedouin who had no right to compensation under Jordanian law, but under World Bank guidelines were compensated.

Additionally, the review team raised concerns that the five participating municipalities who would be joining the grant for the Innovation Fund alone would be at a disadvantage for bidding. As a number of these are in the South of the country and grievances between the north and the south already exist around the perception that the North receives the lion’s share of resources, this could be a problem. The team however, already have a plan in place to prioritise the new municipalities for training.

Update on partnership principles

DFID’s partnership principles are in the course of being updated for 2018. The MSSRP intersects with the PPs in two areas.
Direct engagement with the Ministry of Municipal Affairs. Fiduciary risks are managed by the World Bank. The UK does not engage directly, however the efforts under this project to build capacity in budgeting, strategic planning and to build up citizen engagement in governance both suggest that the net effect will be positive on governance, transparency and financial risk management.

b) The status and treatment of refugees. The principles outline the UK and Jordan’s commitment to international humanitarian law as enshrined in the Jordan compact. The work to support both refugees and host communities to benefit economically from job creation is in line with these commitments. In addition, work as day labourers at the municipal level is allowed under the work permit scheme for refugees.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

Delivery against planned timeframe

Despite the delay in the launch of the project by 7 months, delivery against the timeframe since February 2018 has been rapid.

The programme has held 129 public consultations in 20 municipalities, and municipalities have proposed a range of projects that have been assessed by technical committees.

Whilst there are delays with the Innovation Fund, the World Bank is keen to ensure that the process is well considered, to avoid potential conflict between municipalities. The World Bank should ensure that it dedicates sufficient resource and capacity to ensure that the Innovation Fund guide is finalised quickly.

A particularly active area of the work plan has been the attention given to communications. The communications specialist has developed a communications strategy that identifies the major methods of communication for donors and municipalities on the programme. The team has also identified focal points for communications within each municipality.

Lessons identified this year, and recommendations for the year ahead linked to this output

Outreach has been a huge step up from the JESSRP however, examples from other projects suggest investment and training in live streaming or video conferencing of meetings could open up the process yet further. Ongoing communication methods are varied across the programme, the PMU should encourage learning and sharing on communication methods and tools across the different municipalities, to encourage wider programme benefits.

Performance of partnership(s)

To date the trust fund includes the UK, Netherlands, Canada and the USA. The World Bank is adhering to a range of requirements from each donor. The World Bank should continue to engage with donors in a joined-up way, both to ensure coherence of approach and requirements, and to minimise negotiation with the systems of different donors. The UK-World Bank and the UK-PMU relationship is strong. Feedback from both praised the UK’s detailed commitment to the project and responsiveness. Credit in particular should be given to the work of the programme manager who has established strong relationships across the partner and the donors. There was some concern that delays in approvals and sign off from the World Bank to the PMU may have been affected by miscommunication. Additional WB staff in Jordan might support an easier working relationship.

Asset monitoring and control

N/A

Date of last narrative financial report(s)	30th April 2018
Date of last audited annual statement (s)	30th April 2018

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

An indicative results framework has been finalised. Additional work is taking place to enhance it with inputs from the donors and the previous M&E expert in the PMU before the DFID team translate it into a DFID logframe.

The World Bank is currently contracting a supplier to carry out the baseline survey for the programme. The previous end-line survey for JESSRP was not deemed sufficient by donors, therefore a new baseline is currently being established. This is likely to happen in time for the start of procurement. Independent monitoring will also be used to carry out the mid-term and end-line surveys of MSSRP. This is currently being put out to tender to ensure the highest quality possible.

Some known indicators, such as the number of jobs created will be monitoring by the ILO.

The 2018 Annual Review exercise involved field visits to Mafraq and Zatari municipalities, including interviews with a Mayor and lead for the Local Development Unit. The review team engaged with stakeholders from the World Bank, the Cities and Villages Development Bank and the PMU.

Evidence and Learning (1 page)

The end evaluation for the JESSRP (September 2018) made the following recommendations. The box indicates how these are being taken forward as lessons learnt.

Planning for future interventions should ensure that consideration is given to the sustainability of finance for municipalities once the project funding comes to an end.	All projects must have a dedicated maintenance budget, and an operations and maintenance plan signed off by the council. MoMA has signed a compact with councils to ensure that costs are available after the end of the project, and there is periodic monitoring.
Future interventions should give consideration to addressing risks around safeguarding, particularly in working with vulnerable groups throughout the consultation process.	There is a safeguarding lead. The training plan for MSSRP includes a focus on ILS’s environmental and social safeguards. More needs to be done on PSEA and working with vulnerable adults.
All municipalities should ensure that they have an effective grievance and response mechanism in place for people to address any concerns that they have around project interventions.	Currently the GRM is a combination of paper logs, which are regularly monitored by the outreach team, and electronic records on platforms such as facebook. An audit of these could be conducted to note the nature of complaints and how rapidly they are responded to.
Social cohesion indicators need to be developed for future CSSF projects, in order that the project impact on this can be measured effectively.	These are included – as a measure of positive perceptions increasing, and negative perceptions decreasing against Syrians/Jordanians. Vertical measures are also included in terms of perceptions of the state.
Future projects should ensure that their reporting frameworks are designed to promote good quality, sustainable, inclusive interventions with two way communication between community and local government.	Citizen score cards will be rolled out in each municipality in order to have a structured dialogue around service delivery.
There was a variation in project delivery amongst different municipalities. Future interventions should promote lesson learning across municipalities to ensure a consistently high level of delivery.	Informal lesson learning is being enhanced by formal trainings, communications materials (including newsletters in English and Arabic). A rotating group of Mayors is on the Steering Committee.
With a large number of donors operating in Jordan, there is a need for greater coordination with other donors and projects working in municipalities eg USAid’s CITIES programme.	Inter-donor coordination seems to be improving with the four donors talking regularly, including USAID.
Clear Value for Money (VFM) indicators should be developed for future interventions	This is underway.

There are a number of formal learning processes that will feed into the programme or extract results from the work.
- The baseline and endline will supply data on a range of social perceptions data points linked to the work of MSSRP.
- A Global Partnership on Social Accountability project for the world bank is looking at three municipalities in Jordan to develop and test methodology for encouraging CBO-Municipal collaboration in service delivery and monitoring using a rights based approach.
- The Global Facility for Disaster Risk Reduction is conducting a study on solid waste management and local authorities in Jordan
- The ILO will be reporting on the progress of labour intensive programming and the implementation of ILO standards.
- The Centre for Mediterranean Co-Operation has produced guides for local municipalities and encouraged peer to peer learning. The review team witnessed the guideline being used during the visit to Zatari.

Gender and Inclusion

The Gender specialist has assessed the programme and stakeholder needs on gender and building gender understanding. This has formed part of the Gender Mainstreaming Strategy, a training manual and awareness sessions on gender with municipalities. A training programme for staff and stakeholders was delivered, with a Gender Action Plan for Municipalities and named focal points within Municipalities. The PMU and CITIES have also received training on gender.

The consultation process for Municipal Grants included women participants in the town hall events. No specific data is available on the number of women who participated, however anecdotal evidence states that participants tended to be male, middle-aged Jordanians. Stakeholders also noted the absence of large numbers of disabled people in the consultations; future consultations should consider methods to engage people with disabilities more systematically, as the town hall format may not be appropriate for some groups.

The Municipal Grants have tended to be gender-blind, proposing projects that benefit both men and women. In many cases, this may be appropriate, however future consultations should consider the differing requests of men and women, to ensure that the benefits of the grants are shared widely and with the most marginalised people.

The Innovation Funds should consider women from the beginning, to ensure that funds benefit women as well as men. In some instances, this may involve a broader definition for the ‘working day’, to allow for part-time working or overnight working. The IFs should also consider the skills and experiences of both Jordanian and Syrian participants, to ensure that jobs created apply to both communities, and to encourage participants from both communities in the same sectors. The IFs should ensure that jobs and employment is also provided to disabled people, who may require particular adjustments.

Progress on recommendations from previous reviews (1/2 page)

The following progress has been made against the recommendations from the previous annual review:

Recommendation: the UK and the World Bank should work to build stronger relationships with key government agencies, namely MOMA, MOPIC, MoF
  - Progress: PMU leadership strengthened with Project Director replacement in July 2018, WB Project Manager building relationships with Ministries, UK meeting with MOMA in September 2018.

Recommendation: UK and World Bank should ensure lesson learning from similar programmes is integrated into management and implementation of MSSRP
  - Progress: Monthly coordination meeting in place between MC, MSSRP PMU and CITIES, MercyCorps year 3 now integrated within MSSRP and CITIES, exchanges to Lebanon completed in September 2018 and planned for February 2019 with a focus on youth programming. The PCR from the JESSRP has recently been completed; the learning from this programme should be used in this programme.

Recommendation: Inter-municipal learning and cooperation should be used further
  - Progress: PMU facilitating shared learning workshops between municipalities, shared lesson learning was encouraged at MSSRP launch and WB communications regional workshop in community communications includes a selection of MSSRP mayors.

Recommendation: UK to finalise its approach to monitoring progress as the MSSRP is implemented
  - Progress: WB have agreed to include VFM indicators in the Results Framework, which is still being finalised. The completion of this Results Framework should be prioritised

Recommendation: UK to manage staff changeover better to ensure more effective transfer of institutional memory
  - Progress: The CSSF PM has completed SRO training, and been joined by a second team member who is also being trained on DFID systems to ensure that MSSRP knowledge if shared.

Recommendation: The UK programme team should work with the World bank to make use of delivery chain mapping
  - Progress: the team has explained a Delivery Chain Map and agreed to a WB map by the end of October 2018.

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.
The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided