Annual Review – post April 2018

Title: DFID Investment in the UN Development System to Achieve Agenda 2030
Programme Value £ (full life): £518m		Review Date: September-October 2018
Programme Code: 300396	Start Date: 01/04/2017	End Date: 31/03/2021

Summary of Programme Performance
Year	1
Programme Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300396/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300396/documents

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

The UK is providing £518 million between 2017 and 2021 to the UN development system, through the provision of core funding to United Nations Development Programme (UNDP), United Nations Children’s Fund (UNICEF), United Nations Population Fund (UNFPA), UN Women and earmarked funding to support gender data across the UN, via UN Women.
This consists of:
- Provision of core funding to UNDP (£55mill per year), UNICEF (£40 mill per year), UN Women (£12.5 mill per year) and UNFPA (£20 mill per year) of £510 million.
- Provision of earmarked funding in support of an improved UN approach to gender data of £6 million over the four-year period through UN Women’s Making Every Woman and Girl Count Programme and the UN Women and WHO Joint Programme: Strengthening Methodologies and Measurement and Building National Capacities for Violence against Women Data. Reporting and other obligations for this funding will be fulfilled as per the terms of the agreements signed with DFID.
- £2 million over the four-year period for learning, monitoring and evaluation activities. This funding is being retained and managed by DFID.

This funding supports these agencies to deliver globally in critical areas and maintain UK influence. The introduction of Payment by Results aims to ensure the funding helps to accelerate reform.

The desired impact of this funding, reflecting the UK’s development objectives, is to generate momentum and progress towards Agenda 2030 and for the UN agencies to show strong global leadership on this. We recognise that that development system reform is critical to extend the agencies reach and impact, the expected outcomes are therefore accelerated normative and operational development results by UN Development System and UN system providing effective leadership to deliver Agenda 2030.

The expected outputs are:

    1. Improved organisational effectiveness of UN agencies;
    2. United Nations Development System (UNDS) supports more coherent UN approach to peace and security, building resilience, preventing and responding to crises;
    3. UN entities aligned to Agenda 2030 priorities;
    4. Improved UN agency coordination at country level.

The Business Case includes a Payment by Results (PBR) element such that 30% of the allocated funding is contingent on the delivery of three outputs: Leadership and Collaboration, Organisational Effectiveness and Organisational Transparency, Accountability and Efficiency. The PBR indicators for 2017 were agreed between DFID and the four UN Development agencies. These indicators are based on specified improvements derived from the UK’s 2016 Multilateral Development Review and fully aligned with the UN Secretary-General’s reform priorities that were adopted in the June 2017 General Assembly resolution.

Summary supporting narrative for the overall score in this review (1/2 page)

In September 2017 UNICEF, UNFPA and UN Women agreed new four-year Strategic Plans that specifically set out their programmatic, normative and policy leadership on Agenda 2030; the UNDP Strategic Plan was agreed in November 2017. These Strategic Plans are accompanied by Integrated Results and Resources Frameworks that will be the main evidence source for the 2018, 2019 annual reviews and the 2020 PCR. Most of the evidence for this annual review is taken from the Agency reporting against the final year of their 2014 to 2017 strategic plans. This first annual review under the four-year business case can therefore be regarded as a transitional year. Transition to a new Strategic Plan and to the new PBR approach.

Overall in this context, the four UN Development agencies have made good progress during 2017 on both the PBR and non PBR agency specific indicators, specifically around leadership and collaboration, organisational effectiveness, organisational transparency, accountability and efficiency and delivery of agency strategic plans. Progress ranged from all four agencies exceeding the PBR indicator on shared common services, to agencies overall meeting the indicators as set out in the respective Strategic Plans. However, there are a few areas which are not currently meeting expectation, such as on IATI ratings, which will be addressed through the recommendations in this Annual Review.

For the 2017 milestones, UN Development agencies have in the most part met, and in some cases exceeded, the indicators, with one exception as highlighted above. Of the 30 indicators in the logframe, 9 were subject to PBR, all of which are joint indicators between the four agencies. In line with the mutually agreed PBR methodology note, agencies were required to meet or exceed 7 out of 9 milestones in order to secure full PBR payment (30% of the total available core funding for the year). All indicators (both PBR and non PBR) were negotiated with agencies and the majority derive from agencies own reporting.

At their June 2018 Executive Boards all four agencies specifically agreed to continue to engage with the Secretary-General, other United Nations development system (UNDS) entities and Member States, to support full implementation of General Assembly resolutions of 31 May 2018 on the repositioning of the United Nations development system. This was followed in September 2018 by their agreement to meet their full financial obligations under the new Resident Coordinator funding arrangements. Whilst these developments are not specifically covered by indicators in the logframe for 2017, they importantly reflect the agencies commitment to key objectives of this funding and to UN Development System Reform more broadly.

 This is the first annual review conducted for the 2017-2021 business case and the first where payment of core funding has been linked to PBR. Over the course of the review period, DFID and UN agency staff have worked collaboratively together, both through bilateral engagement including the annual Strategic Dialogues, senior level meetings and the Executive Boards. The first year of implementing the new business case, including the roll out of PBR, has helped shape the programme going forward and embedded the concept of PBR into DFID core funding. Although agencies are somewhat hesitant about the use of PBR for core funding, we are in the process of finalising future years indicators building on the lessons learned during year one.

Recommendations for the year ahead (1/2 page)

The review team recommends that the PBR indicators for future years are finalised as soon as possible, along with a revised indicator on Prevention of Sexual Exploitation and Abuse (PSEA) which meets both the UK and UN’s enhanced ambition on this critical issue. Also, where progress could be improved, such as around IATI ratings, efforts should be made to improve performance.

In addition, the team also recommends that DFID and UN agencies undertake a joint lesson learning exercise post annual review to identify best practice for future year reviews, including ways to streamline the process.

Furthermore, the team also recommends that agencies consider undertaking further review/quality assurance process of data prior to submission to the Executive Board where appropriate. During the annual review process there were a few occasions where information that had been submitted to DFID as part of the review process differed from that which had been submitted to the Executive Board.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Leadership and Collaboration: / Effective UN Resident Coordinator system empowered to assess and coordinate UN country teams coherently and with corresponding accountability. / UN agencies operating as a joint platform in country. / Greater collaboration between UN development and humanitarian agencies. especially in fragile and conflict affected states.
Output number per LF		1	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Fraction of the entities recognising reporting obligations to the resident coordinator on: / i) Resource Mobilisation / ii) Programme Implementation Performance	75% (2018 data, 3 out of 4 agencies)	Met. 75% (2018 data from United Nations Department of Economic and Social Affairs, 3 out of 4 agencies) / Note: This result is preliminary. The source for indicator 1.1, the 2017 Quadrennial Comprehensive Policy Review (QCPR) report, will be published in early/mid 2019.
1.2 % of UN Country Teams (UNCT) in which at least 3 agencies have country offices that are applying at least 8 elements of the Standard Operating Practices (SOPs) (out of 15, in Delivering as One (DAO) countries)	88.7% (47/53)	Met. 88.7% (47/53)
1.3 % of UNCTs (as applicable) in countries with significant humanitarian assistance needs, where humanitarian and development actors have, in the last two years, engaged in: / i) joint needs assessment / ii) joined up planning	i) 90.9% (joint needs assessment) / ii) 81.8% (joined-up planning)	Met. i) 90.9% (joint needs assessment) / Met. ii) 81.8% (joined-up planning)

Briefly describe the output and provide supporting narrative for the score

All four agencies have made good progress on output 1.1, with only UNICEF still to fully recognise its reporting obligations to the resident coordinator. It is anticipated that UNICEF will meet this indicator by the end of 2018. Discussions are currently underway with agencies to finalise future indicators and milestones to raise the level of ambition for this indicator.

Progress on indicator 1.2 shows good achievement on SOPs, critical to in-country UN coherence which has been a requirement since 2014 for DAO countries and encouraged in all countries since the 2016 QCPR. It is acknowledged that some SOPs are harder to deliver on than others, but going forward we need to maintain momentum and prioritise those which are fundamental to increasing in country coherence. This is in line with the focus in the Secretary General’s reform report on substantially increasing use of the SOPs by 2021.

Strong progress was made on indicator 1.3 as a result of more joined-up analysis and planning in countries in crisis.

Lessons identified this year, and recommendations for the year ahead linked to this output

The review team recommend that agencies look at more qualitative case studies based on in-country reporting in line with Inter Agency Standing Committee (IASC) case studies. These case studies are currently being used on a similar indicator on joined-up working in the humanitarian agency PBR context.

In addition, more needs to be done to monitor delivery of collective outcomes and broadening the focus to prevention in countries that are in fragile contexts, as this indicator is fundamentally about joint planning and coordination as a means of mitigating the drivers of conflict.

Output Title	Organisational Effectiveness: / Common system for results reporting, using common methodology. / All agencies promoting gender equality and the empowerment of women. / All agencies step up their support to Leave No One Behind (LNOB).
Output number per LF		2	Output Score	A+
Impact weighting (%):		10	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Proportion of UNCTs in DaO countries in which all 4 agencies have country offices, presenting single annual report to the programme country government on progress in implementing UNDAF	72% (18/25)	Met. 72% (18/25)
2.2 % of United Nations System-wide Action Plan on Gender Equality and the Empowerment of Women minimum standards, where relevant that are met or exceeded	i) UNDP - Meets or exceeds requirements for 12 out of 15 relevant indicators / ii) UNICEF - Meets or exceeds requirements for 11 out of 15 relevant indicators / iii) UNFPA - Meets or exceeds requirements for 14 out of 15 relevant indicators / iv) UN WOMEN - Meets or exceeds requirements for 12 out of 13 relevant indicators	UNDP – Met. 12 out of 15 relevant indicators / UNICEF – Met. 11 out of 15 relevant indicators. / UNFPA – Met. 14 out of 15 relevant indicators. / UN WOMEN – Exceeded. All 13 relevant performance indicators for UN-SWAP (Sector-Wide Approach) reporting
2.3 Agencies demonstrate commitment to SWAP 2.0	i) UNDP – a) To adopt a Gender Equality Strategy 2018-2021 aligned to the UN SWAP 2.0 / b) Communicate and disseminate UN SWAP 2.0 to senior management to create ownership and commitment / ii) UNICEF - Gender human resources architecture at HQ and RO is resourced and functional / iii) UNFPA - Gender Strategy is developed and framed within the UN SWAP 2.0 iv) UN WOMEN - Coordinate and lead the development and roll-out of UN-SWAP 2.0	i) UNDP / a) Met. UNDP's Gender Equality Strategy (GES) 2018-2021 has been submitted to the Executive Board, which is strongly aligned with the UN SWAP 2.0. / b) Met. UNDP’s Gender Equality Strategy 2018-2021 is SWAP 2.0 compliant. / ii) UNICEF Exceeded. UNICEF gender architecture at HQ and RO was fully resourced and functional in 2017. The target of 14 senior gender experts was exceeded, with the placement of 16 senior staff at headquarters and the seven regional offices in 2017. / iii) UNFPA Met. Gender Strategy is developed and framed within the UN SWAP 2.0. / iv) UN WOMEN Met. UN WOMEN has successfully led the development of UN-SWAP 2.0. which has now been rolled out.
2.4 Agencies demonstrate increased commitment to LNOB, including persons with disabilities through strategies, guidelines and tools	i) UNDP - Updates guidance on disability-sensitive programming in UNDP and specifically mainstreaming of disability in Country Programme Documents (CPDs) / ii) UNICEF - a) Disabilities mainstreamed in new Strategic Plan (27 indicators, 1 specific result) / b) Development and launch of guidance on Including Children with Disabilities in Humanitarian Action / c) Issued executive directive on Accessibility for Programme-related Construction Activities / iii) UNFPA – a) Increased number of distinct result indicators on disability in the Strategic Plan and of disability disaggregation / b) Advocating for inclusion of Washington group questions in census when possible / c) Guidelines for Providing Rights-Based and Gender-Responsive Services to Address Gender-Based Violence and Sexual and Reproductive Health and Rights for Women and Young People with Disabilities finalised as part of preparatory work for UNFPA's strategy on disability / iv) UN WOMEN – a) Increased number of results indicators disaggregated by disability status in the Strategic Plan 2018-2021 / b) Guidance for new strategic Notes (CPDs) starting in 2018, includes the need to have results data disaggregated by disability status. / c) Enhancement to information systems to allow field offices to report data disaggregated by disability status included in the corporate annual workplan for 2018. / d) Preparatory work initiated for UN Women's strategy on disability	UNDP Met. Efforts in 2017 focused on mainstreaming disability in the Strategic Plan 2018-2021 and laying the foundation for mainstreaming of disability in CPDs. / ii) UNICEF Met. / a) Disabilities have been mainstreamed into the new SP. / b) UNICEF has finalised and launched in 2017 the Guidance (Including Children with Disabilities in Humanitarian Action) / c) UNICEF has finalised and launched in 2017 the Executive Directive on Accessibility for Programme Related Construction. / UNFPA Met. / a) The distinct results indicators on disability included in the results and resources framework of the strategic plan 2018-2021 have increased by 400 per cent compared to the previous strategic plan / b) UNFPA released UNFPA Strategy for the 2020 round of census in 2017 which prioritised the inclusion of the Washington group questions on disability into the census. / c) UNFPA finalised Guidelines for Providing Rights-Based and Gender-Responsive Services to Address Gender-Based Violence and Sexual and Reproductive Health and Rights for Women and Young People with Disabilities. / iv) UN WOMEN Met. / 25% of the Strategic Plan- SP (2018-2021) outcome level results and 16% of SP output level result includes indicator that collects, and track data disaggregated by different LNOB categories including disability. / Strategic Notes (CPDs) guidance was strengthened to include LNOB principle including disability in the strategic note result framework through data disaggregated by different relevant categories including disability. / UN Women’s results management system is undergoing changes to allow country offices to report data disaggregated by disability status. / d) UN Women has developed a corporate strategy document on disability.

Briefly describe the output and provide supporting narrative for the score

This output measures key aspects of organisational effectiveness for UNDP, UNFPA, UNICEF and UN Women. Agencies have met, and in some cases exceeded, the milestones for the reporting period. The indicators, which were subject to PBR, were developed following substantial consultation with agencies. Work is now currently underway with agencies to finalise the indicators and milestones for 2018, building on lessons learned during the development of the 2017 indicators and the annual review process.

Over the course of the reporting period, significant progress was made by agencies in areas such as gender equality and disability. For example, on gender equality, UN Women exceeded its milestone and met all 13 relevant performance indicators for United Nations System-wide Action Plan (SWAP) on Gender Equality and the Empowerment of Women minimum standards. In addition, UN Women successfully led on the development of UN SWAP 2.0 which has now been agreed and is in the process of being implemented across the UN Development and Humanitarian system.

UNDP’s gender equality strategy for 2018-21 was drafted and was submitted to the Executive Board in September 2018. Substantial work undertaken during the review period helped shape the strategy, including the analysis of results achieved under the former (2014-17) gender equality strategy and lessons learned from implementation. UNDP also held extensive consultations with a range of internal and external partners on gender equality, the integration of gender across the three Strategic Plan outcomes, institutional results, as well as intensive discussions on financing targets and the gender marker. The strategy integrates gender-sensitive results indicators which have been incorporated into the 2018-21 Strategic Plan.

Similarly, UNFPA drafted its gender strategy (2018-21) which was developed and framed within the UN SWAP 2.0. The strategy outlines UNFPA’s main approach to gender mainstreaming and stand-alone initiatives across its core programming. The SWAP is also embedded in UNFPA’s Strategic Plan, which the gender strategy is fully aligned to.

UNICEF exceeded its target in this area by ensuring the headquarters and regional offices were fully resourced and functional during the reporting period. The target of 14 senior gender experts was exceeded, with the placement of 16 senior staff at headquarters and the seven regional offices.

On disability, UNDP, for example, focused on mainstreaming disability in its 2018-21 Strategic Plan and laid the foundations for mainstreaming disability in its country programme documents. As part of the new results framework approved in November 2017, UNDP introduced six indicators out of 83 outcome and output indicators (7%) which are disaggregated by people with disabilities or addresses the needs and rights of people with disabilities. Furthermore, for the first time an institutional-level indicator was also introduced to better support efforts to mainstream the needs and rights of persons with disabilities in all country programme documents and enable UNDP to measure mainstreaming of disability country programme documents. In addition, UNDP commenced development of a range of additional markers (including on people with disabilities) to be operationalised in 2018.

Similarly, UNFPA incorporated distinct disability indicators in the results framework. The net result is a 400% increase in the number of disability indicators compared to the previous (2014-17) Strategic Plan. In addition, all relevant indicators in the results framework have been disaggregated by disability. This applies to beneficiary-level indicators measuring service delivery. UNFPA also released its strategy for the 2020 round of census which prioritised the inclusion of the Washington group questions on disability into the census. Furthermore, UNFPA finalised guidelines for Providing Rights-Based and Gender Responsive Services to Address Gender-Based Violence and Sexual and Reproductive Health and Rights for Women and Young People with Disabilities.

UNICEF also mainstreamed disability into its new Strategic Plan. This includes a specific result area on disability under outcome statement 5 (Girls and Boys are provided with an equitable chance in life). The output statement is: “Countries have implemented inclusive programmes and services to promote participation of children with disabilities in society”. In addition, UNICEF finalised and launched guidance on Including Children with Disabilities in Humanitarian Action and issued an Executive Directive on Accessibility for Programme Related Construction.

UN Women incorporated distinct disability indicators in its new results framework (2018-21). The net result is that 25% of outcome and 16% of output level results include indicators that collect and track data disaggregated by a number of leave no on behind categories, including disabilities. In addition, strategic notes guidance was strengthened to include the leave no one behind principles, including disability and data disaggregation. Furthermore, UN Women has developed a corporate strategy document on disability which is currently with senior management for approval.

Lessons identified this year, and recommendations for the year ahead linked to this output

Agencies should continue to strengthen efforts to move towards achievement of all relevant SWAP indicators, promote actions to deliver on SWAP 2.0 and on people with disabilities as delivery of new Strategic Plans continues, including further progress, where necessary, on disaggregation of data.

Output Title	Organisational Transparency, Accountability & Efficiency: / UN agencies committed to, and demonstrating, full transparency / All agencies have robust systems in place to prevent and respond to fraud / Agencies adopt harmonised approaches to streamline services and reduce costs
Output number per LF		3	Output Score	A
Impact weighting (%):		10	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Extent to which agencies retain or improve their IATI ratings for: / i) timeliness / ii) comprehensiveness / Rating score: / Very strong: 75-100 / Strong: 50-74 / Weak: 25-49 / Very weak: 0-24	i) UNDP Timeliness – retain or improve Very strong (88 points) Comprehensiveness – retain or improve / Very strong (87 points) / ii) UNICEF Timeliness - retain or improve / Very strong (88 points[1]) Comprehensiveness - retain or improve / Vert strong (95 points) iii) UNFPA Timeliness - retain or improve / Strong (63 points) Comprehensiveness - retain or improve / Very strong (95 points) iv) UN WOMEN Timeliness – improve / Weak (25 points) Comprehensiveness - retain / Strong (62 points)	UNDP Exceeded / Timeliness – Very Strong (100 points) / Comprehensiveness – Very Strong (89 points) / UNICEF Exceeded / Timeliness – Very Strong (88 points) / Comprehensiveness - Very Strong (96 points) / UNFPA Not met / Timeliness – Strong (50 points) / Comprehensiveness - Very Strong (92 points) / UN WOMEN Exceeded / Timeliness – Strong (50 points) / Comprehensiveness - Very Strong (79 points) / IATI Statistics updated as of 2 August 2018
3.2 Percentage of relevant recommendations of the 2016 Joint Inspection Unit Report on Fraud Prevention and Detection implemented	UNDP - 87% / UNICEF - 64% / UNFPA - 40% / UN WOMEN - 73%	UNDP Met - 87% (13 out of 15 recommendations implemented) / UNICEF Met – 64% / UNFPA Met – 40% as of 31 December 2017 / UN WOMEN Met - 73% (as at 31 December 2017)
3.3 Percentage of country offices implementing common services on: / i) procurement / ii) human resource management / iii) information communication technologies / iv) financial management services	i) UNDP procurement - 45% human resource management - 34% information communication technologies - 60% financial management services - 28% ii) UNICEF procurement - 61% human resource management - 30% information communication technologies - 34% financial management services - 25% iii) UNFPA procurement - 55% human resource management - 46% information communication technologies - 58% financial management services - 47% iv) UN WOMEN procurement - 45% human resource management - 37% information communication technologies - 53% financial management services - 41%	UNDP Exceeded / Procurement – 50% / Human resources – 40% / Information communication technologies – 63% / Financial management services – 37% / UNICEF Exceeded / Procurement 72% / Human resources 45% / ICT services – 66% / Financial management services – 43% / UNFPA Exceeded / procurement - 64% human resource management - 47% information communication technologies - 58% financial management services - 76% / UN WOMEN Exceeded / procurement - 51% human resource management - 51% information communication technologies - 63% financial management services - 51%

Briefly describe the output and provide supporting narrative for the score

This output measures organisational transparency, accountability and efficiency of UNDP, UNFPA, UNICEF and UN Women. Overall progress under this output is good, with a number of milestones met or exceeded and only one milestone not met (3.1) where UNFPA did not meet the target. Further details on this is captured below. The indicators, which were subject to PBR, were developed following substantial consultation with agencies.

Over the course of the reporting period, significant progress was made by agencies in areas such as transparency (noted exception of UNFPA) and common services. On transparency, UNDP exceeded the milestone and retained the ‘Very Strong’ rating for both timeliness and comprehensiveness of the International Aid Transparency Initiative (IATI) statistics score. In recognition of UNDP’s role as a global leader in transparency, UNDP is providing support to other UN Agencies and development partners to increase aid transparency and compliance with the IATI standard. UNDP and UN Women signed the first UN to UN Contribution Agreement and UNDP has provided technical support to help UN Women enhance transparency and the level of compliance with the IATI standard. UNDP is planning to build on the experience with UN Women and expand this business model to the other UN Agencies and development partners.

UNICEF was ranked 9th out of the 45 organisations assessed in the 2018 Aid Transparency Index.  Even though this is a drop to ‘Good’ from the ‘Very Good’ category attained in the last index in 2016, from a trends perspective, UNICEF is still considered as the organisation that has made the most improvement in its overall ranking over the years. In addition, transparency is an important element of one of our Enablers in UNICEF’s Strategic Plan (2018-21), which presents UNICEF with an opportunity to reflect on the policies and practices required for more transparency and accountability in the delivery of programmes at all levels.

UNFPA retains a score of strong for timeliness and very strong for comprehensiveness. However, during the reporting period, the quality of UNFPA’s reporting was affected by unexpected staff turnover, explaining the decreased scoring on comprehensiveness from 63 to 50. UNFPA made great efforts to re-establish and maintain the strong score for timeliness, and met the required number of updates to be made in the IATI dashboard for the duration of the reporting period. As part of UNFPA’s efforts for continuous improvement, UNFPA will further improve on the reporting timelines and will continue to report on a quarterly basis.

UN Women exceeded the milestone for the sub-indicator on comprehensiveness. Furthermore, UN Women has improved its IATI publishing process and has moved towards automating IATI publishing using data from its results management system (RMS) and financial management system (ATLAS). This will allow UN Women to improve on the frequency of publishing data to IATI. UN Women has now started publishing to IATI on quarterly basis and will move to monthly publishing starting 2019. As part of their commitment to transparency, UN Women will continue to pursue a series of measures to underpin the principle of transparency in its operations.

With regards to indicator 3.2, all four agencies have continued their efforts to implement the recommendations of the UN Joint Inspection Unit’s 2016 report on fraud prevention, detection and response in the UN system. That report set out a number of measures that UN entities should take – if not already met – to strengthen their counter-fraud capability. These were enshrined in 16 formal recommendations, one of which was for governing bodies and the remaining 15 for agencies.

At the point of issuing of the JIU’s report each of the agencies already met a number of these 15 recommendations, but some already met more than others. This meant the starting point for each agency was different and has been reflected in the baseline and milestone, but with the objective that over the course of this programme all would have implemented the key recommendations, achieving equivalent organisational strength.

By the end of 2017 each of the four agencies had met their milestones for 2017. As of the end of December:

UNDP had implemented 13 of the 15 recommendations, with progress made on the two outstanding recommendations. These relate to the development of a fraud awareness training course (which is to be rolled out in 2018 and made mandatory for all staff) and the introduction of a statement of internal control. On the statement of internal control, the first phase of a system of attestation was recently introduced for business units, the second phase will introduce fraud certification. UNDP are still considering what exact form, or where, the statement of internal control will be most appropriate. We understand the aim is for this to be in place by the end of 2019.

UNFPA had implemented six out of the 15 (40%) accepted JIU fraud report recommendations, and has committed to follow up on the implementation of the remaining recommendations relevant to UNFPA and to continuing its contribution to the various JIU initiatives in the future. Actioning of JIU recommendations are monitored and closed by UNFPA’s independent Office of Audit and Investigation Services.

Furthermore, UNFPA has been working since 2017 to integrate fraud risk and controls into its main policies. This has already been achieved for the key processes of management of cash transfers to implementing partners, and management of programme supplies, which account for close to half of UNFPA total programme expenditures. Work is ongoing with regards building fraud risks and controls into the procurement and project cash advances policies, currently under review. The comprehensive anti-fraud strategy and action plans, and fraud control framework are under development, building on the work performed around the previously mentioned key policies; the fraud strategy and framework work includes the development of detailed fraud risk scenarios for each of the processes mentioned. UNFPA committed to continuing to expedite the implementation of the outstanding recommendations, as evidenced in the revised targets for this indicator for years 2 and 3. DFID continues to monitor progress at Board level of the implementation of all relevant outstanding recommendations.

UNICEF had implemented 9 of the 14 recommendations (note 1 of 15 recommendations has been deemed inapplicable by UNICEF). The 5 in progress at the end of 2017 relate to conducting a corporate fraud risk assessment, developing anti-fraud strategies/action plans for implementing its fraud policy, reviewing its internal control framework, developing a statement of internal controls and ensuring that fraud prevention and detection capabilities are a part of automation systems’ functionalities. In the course of 2017 UNICEF took further steps to implement these recommendations in particular focusing on the development of a new anti-fraud strategy (since approved and currently being rolled out). Internal controls capacity is also being enhanced, and steps taken to enhance consistency in efforts to recover losses across the organisation. UNICEF will provide an update on the JIU website on the outstanding recommendations as actions are being implemented. DFID will have access to these updates and can enquire from UNICEF if these need to be clarified.

UN Women had implemented 11 of the 15 recommendations. Steps taken include development of a new Anti-Fraud Policy Framework; roll out of anti-fraud and ethics training to UN Women personnel; undertaking fraud risk assessments for key functions and processes; incorporating findings from those risk assessments into a new counter-fraud plan which is being developed; reviewing the adequacy of its fraud controls in its internal control framework; and following a review, revising its instruments for engaging implementing partners to ensure all template agreements include anti-fraud provisions. There are 4 recommendations in progress which relate to fraud awareness training for personnel, integrating fraud risk and controls into its main policies, developing a comprehensive anti-fraud strategy and action plans, and introducing a statement of internal control.

Lessons identified this year, and recommendations for the year ahead linked to this output

Agencies should continue to:
- Promote transparency across their organisations and with partners in order to build on strong results
- Work towards meeting all of the recommendations in the JIU report on fraud prevention, detection and response, including articulating specific actions and progress with those not yet met, and processes for embedding those met within existing practice across the organisation. Identify ways to measure the effectiveness of the frameworks and systems put in place.
- Make progress on coverage of common services and articulate how they aim to move towards full coverage.

UNFPA, specifically, should pay particular attention to its IATI rating and ensure that adequate human and financial resources are deployed going forward to improve its rating.

Output Title	UNDP is delivering the results set out in its Strategic Plan 2018-2021
Output number per LF		5	Output Score	A
Impact weighting (%):		17.5	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 All participating agencies provide assurance that they are taking action to prevent all forms of Sexual Exploitation and Abuse (PSEA), and taking prompt and appropriate action on reported allegations within available resources	An online training module for personnel on prevention of PSEA developed jointly between UNDP, UNFPA, UNICEF and UN Women and rolled out.	Met. In 2017, UNDP rolled out mandatory training for all staff and consultants on PSEA
4.2 Number of internal audit recommendations outstanding for more than 18 months	6	Met. 6 recommendations outstanding for more than 18 months
4.3 2017 only: Percentage of countries where national and/or sub-national institutions show improved capacities to lead and coordinate the early recovery process within 18 months of the start of the crisis and/or of UNDP interventions	70%	Not met. 67%
4.4 2017 only: Percentage of conflict-affected countries more effectively bringing together sub-national, national institutions and communities, including women, for peaceful resolution of recurrent conflicts within 18 months of the end of conflict	68%	Not met. 64%
4.5 2017 only: Number of post disaster and post conflict countries having operational strategies to support recovery and address the causes or triggers of crises: / a) Disaster / i) Number of affected countries with causes and triggers of crisis identified and a strategy to address them / ii) Number of affected countries with an operational strategy to address causes and triggers of crisis / b) Conflict / i) Number of affected countries with causes and triggers of crisis identified and a strategy to address them / ii) Number of affected countries with an operational strategy to address causes and triggers of crisis	a) i) 4 ii) 0 / b) i) 3, ii)	Exceeded / a) i) 7 ii) 3 / b) i) 12, ii) 7

Briefly describe the output and provide supporting narrative for the score

This output relates to the implementation of UNDP’s Strategic Plan. Due to the reporting period in question, a number of the indicators and milestones relate to the 2014-17 Strategic Plan. These indicators have been selected to act as an overall proxy for UNDP’s Strategic Plan. As a result, a number of the indicators will change from 2018 onwards and will be taken from the new Strategic Plan (2018-21), however, where possible we have tried to ensure that the individual thematic areas have been carried over.

Regarding the audit indicator, the reduction to six long outstanding audit recommendations represents a major improvement from 2016, when 17 recommendations were outstanding for 18 months or more, and 2015, when 20 recommendations were outstanding for 18 months or more. We understand that this number has been further reduced in 2018.

Although there has been some progress, the specific indicators on early recovery from crisis and on peaceful conflict resolution were not met. However, as reported by UNDP in the Annual Report of the Administrator for 2017, year to year progress over the four-year Strategic Plan period was strong. On early recovery, performance increased from 22 per cent in 2014 to 67 per cent in 2017; and on conflict resolution, performance increased from 47 per cent in 2014 to 64 percent in 2017.

Having noted the above, it is important to underscore the difficulty in setting sensible targets in the area of early recovery over multiple years due to the unpredictability of crisis situations. In addition, the number of countries in early recovery is limited (i.e. small sample size), which means overall performance can be disproportionately affected by change in a small number of countries

4.5 This is an outcome indicator in the SP IRRF for 2014-2017. It is not reported on annually and the methodology was refined in 2015. However, the figures reported show an increase from the 2013 baseline. Baselines and latest progress data for 2017 are based on reports from 20 relevant countries affected by disaster and/or conflict in 2017.

Lessons identified this year, and recommendations for the year ahead linked to this output

4.2 In line with Executive Board decision 2018/6, UNDP will strive to continue progressing in implementing outstanding audit recommendations, especially those flagged as high priority, in 2018.

4.3-5 UNDP identified lessons learned over the 2014-17 Strategic Plan to feed into the development of the new Strategic Plan 2018-2021. The IRRF for the 2018-2021 Strategic Plan, similarly incorporated lessons from the previous IRRF.

Output Title	UNICEF is delivering the results set out in its Strategic Plan 2018-2021
Output number per LF		5	Output Score	A
Impact weighting (%):		17.5	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1 All participating agencies provide assurance that they are taking action to prevent all forms of Sexual Exploitation and Abuse (PSEA), and taking prompt and appropriate action on reported allegations within available resources	An online training module for personnel on prevention of PSEA developed jointly between UNDP, UNFPA, UNICEF and UN Women and rolled out.	Met. In 2017, UNICEF rolled out mandatory training for all staff and consultants on PSEA
5.2 2017 only: Offices/divisions with audit recommendations outstanding for more than 18 months	< 10 per year	Met. 2 in 2017
5.3 2017 only: Countries with costed implementation plans for maternal, newborn and child health care	75	Not met. 67
5.4 2017 only: Countries with policies on inclusive education covering children with disabilities	46	Exceeded. 56%
5.5 2017 only: Countries (of those in which child marriage prevalence is 25% or higher) with national strategies or plans on child marriage with a budget	12	Met. 12

Briefly describe the output and provide supporting narrative for the score

This output relates to the implementation of UNICEF’s Strategic Plan. Due to the reporting period in question, a number of the indicators and milestones relate to the 2014-17 Strategic Plan. These indicators have been selected to act as an overall proxy for UNICEF’s Strategic Plan. As a result, a number of the indicators will change from 2018 onwards and will be taken from the new Strategic Plan (2018-21), however, where possible we have tried to ensure that the individual thematic areas have been carried over.

UNICEF demonstrated progress in the majority of these indicators during the reporting period and the final year of the 2014-2017 Strategic Plan and work on these important issues is being taken into the new Strategic Plan 2018-21. In 2017, UNICEF rolled out a mandatory online training module for all staff and consultants on PSEA as part of its efforts to end abuses committed by those serving under the United Nations flag in any capacity. By the end of March 2018, 90% of UNICEF staff had completed training. During the reporting period, UNICEF scaled up its work on PSEA across the organisation, with a focus on more than 10 countries, mostly those affected by emergencies with large missions or humanitarian operations. UNICEF worked closely with the United Nations Sexual Exploitation and Abuse Working Group, the Inter-Agency Standing Committee Task Team on Accountability to Affected Populations and Protection from Sexual Exploitation and Abuse and other implementing partners to strengthen and scale up programmes to prevent and respond to PSEA.

UNICEF’s work focused on:
- Strengthening reporting PSEA allegations, for example, by putting in place an internal Notification Alert system that facilitates immediate reporting of PSEA allegations against children from the field to the highest levels of the organisation within a mandatory 24/48 hour period. UNICEF also worked with other UN agencies to set up Community-Based Complaints Mechanisms at field level and is currently exploring how to adapt existing SMS-based technology, such as U-Report, to enable communities and victims to report cases of PSEA faster, safer and confidentially.
- Leading several initiatives on responding to victims and offering them assistance. For example, UNICEF budgeted over US$3 million in priority countries to provide immediate and tailored support to victims, which typically includes medical care, psychosocial support, dignity kits and referrals for legal assistance.
- Developing the capacity of staff and partners. UNICEF launched a mandatory PSEA online training for all staff members, which is now being adapted for UNICEF’s implementing partners too.
- Preventing PSEA, including through inserting legal provisions in contracts with vendors, contractors and civil society implementing partners to prohibit PSEA.

One of the targets which was not met is countries with costed implementation plans for maternal, new-born and child health care. UNICEF helped 67 countries in 2017 (up from 52 in 2014) develop costed implementation plans which are essential for prioritising maternal, newborn and child health. Evidence-based planning and budgeting exercises at national and subnational levels in Southern and Eastern Africa and in East Asia and the Pacific regions helped enhance the capacities of health managers at district or subnational levels in devolved country settings such as Bangladesh, Indonesia, Nepal, Pakistan and the Philippines. Slower progress on this indicator is partly explained by the fact that, in many countries, plans that had been developed expired and new plans were being developed, or plans were developed but could not be costed.

Lessons identified this year, and recommendations for the year ahead linked to this output

As outlined in greater detail in its 2017 Executive Director’s Annual Report, several cross-cutting lessons emerged or were reconfirmed in 2017. Many are already reflected in the Strategic Plan, 2018–2021. UNICEF noted the need for more integrated, multi-sectoral programming to advance progress for children in a range of areas, including reducing HIV infections; delivering cash assistance in emergencies; improving child survival, growth and development by addressing social determinants and factors that keep the most vulnerable children out of school and providing them with opportunities to learn; and using integrated advocacy, communications and fundraising efforts to promote policies and investments that benefit children.
Recent experience, including in work on health, HIV, nutrition, education and gender, also highlighted the importance of an increased focus on adolescence, with targeted, resourced and evidence-based programming to address unmet needs and build upon progress made in the first decade of life. Another important lesson is the need to strengthen national systems to assist the most disadvantaged children, including through strong data management and use, and to scale up equity-focused programming and advocacy. Lessons from child protection indicate that scaling up action to address violence against children will require work on systemic factors, including by prioritising social service strengthening.

Output Title	UNFPA is delivering the results set out in its Strategic Plan 2018-2021
Output number per LF		5	Output Score	A
Impact weighting (%):		17.5	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
6.1 All participating agencies provide assurance that they are taking action to prevent all forms of Sexual Exploitation and Abuse (PSEA), and taking prompt and appropriate action on reported allegations within available resources	An online training module for personnel on prevention of PSEA developed jointly between UNDP, UNFPA, UNICEF and UN Women and rolled out.	Met. UNFPA launched an E-learning tool on prevention on of all forms of Sexual and Exploitation and Abuse as part of mandatory learning by all staff and for implementing partners.
6.2 Number of internal audit recommendations outstanding for more than 18 months	30	Met. 30
6.3 2017 only: Number of countries using a functional logistics management information systems for forecasting and monitoring reproductive health commodities	111	Not met. 105 / UNFPA could not reach the target due to financial constraints and changing national priorities. In addition, 2 countries could not maintain the functionality of the system over the years, due to technical and resource constraints.
6.4 2017 only: Number of countries in which civil society organisations have implemented accountability mechanisms for addressing the reproductive rights of women and girls and marginalized and key populations	64	Exceeded. 80
6.5 2017 only: Number of countries in which a National Human Rights Institution has conducted a national inquiry concerning the exercise of reproductive rights and right to sexual and reproductive health	35	Met. 35

Briefly describe the output and provide supporting narrative for the score

This output relates to the implementation of UNFPA’s Strategic Plan. Due to the reporting period in question, a number of the indicators and milestones relate to the 2014-17 Strategic Plan. These indicators have been selected to act as an overall proxy for UNFPA’s Strategic Plan. As a result, a number of the indicators will change from 2018 onwards and will be taken from the new Strategic Plan (2018-21), however, where possible we have tried to ensure that the individual thematic areas have been carried over.

Contraceptives provided by UNFPA in 2017 helped avert over 13 million unintended pregnancies, 4 million unsafe abortions and 32,000 maternal deaths. Through its advocacy in this period, nearly 3,000 communities abandoned female genital mutilation.

During the reporting period, UNFPA launched an E-learning tool on prevention of all forms of Sexual and Exploitation and Abuse, as part of mandatory learning by all staff and for implementing partners. To date it has a 96% compliance rate with online training for all staff, non-staff and contractors. The target is 100% compliance. The Executive Director is following up regularly on the compliance rate for each office. Managers are held accountable for 100% compliance. Furthermore, UNFPA Executive Director appointed the Deputy Executive Director (Management), as the senior focal point for PSEA in UNFPA. A dedicated staff member was recruited to ensure that UNFPA has a coordinated and effective response to all aspects of sexual exploitation and abuse, including programming. In addition, UNFPA is in the process of issuing “No Excuse” cards in 3 languages to all staff at HQ and in country.

The number of internal audit recommendations outstanding for more than 18 months reduced compared to 2016, with progress noted in areas such as inventory management whereby 23 out of 25 outstanding recommendations were implemented and closed. Of the 72 outstanding recommendations that were due for implementation by 31 December 2017, 30 remained unresolved for 18 months or more, compared to 50 recommendations in 2016. Of the 30 recommendations, 13 correspond to procurement processes; 6 to various ICT processes, requiring a combination of procedure improvements (e.g. the procurement procedures revision or the development of a more robust ICT internal control framework) or the ICT transformation; 5 to two country offices (e.g. related to decentralised offices, budget and monitoring); and the remaining 6 to three organisation wide processes (related to programme implementation and human resources in particular).  The percentage of closed recommendations has increased over previous years. To this end, 249 of 321 outstanding recommendations, due for implementation in 2017, were successfully implemented and closed.

UNFPA did not meet indicator 6.3, due to financial constraints and changing national priorities. In addition, 2 countries could not maintain the functionality of the system over the years, due to technical and resource constraints.

Lessons identified this year, and recommendations for the year ahead linked to this output

Whilst indicator 6.3 was taken from the 2014-17 results framework, a similar indicator was selected from the 2018-21 results framework and will be used to monitor progress from 2018 onwards. We therefore recommend that UNFPA continues to prioritise logistics management in order to better manage the distribution of family planning commodities.

Output Title	UN Women is delivering the results set out in its Strategic Plan 2018-2021
Output number per LF		6	Output Score	A
Impact weighting (%):		17.5	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
7.1 All participating agencies provide assurance that they are taking action to prevent all forms of Sexual Exploitation and Abuse (PSEA), and taking prompt and appropriate action on reported allegations within available resources	An online training module for personnel on prevention of PSEA developed jointly between UNDP, UNFPA, UNICEF and UN Women and rolled out.	Met. UN Women launched an E-learning tool on prevention on of all forms of Sexual and Exploitation and Abuse as part of mandatory learning by all staff and for implementing partners.
7.2 Percentage of internal audit recommendations implemented	90%	Exceeded. 99%
7.3 2017 only: Number of countries supported by UN Women which have a gender-responsive policy framework (including legislation, policies and budgets) in national, local or sectoral planning documents	50	Exceeded. 55
7.4 2017 only: Number of agencies that track and report on allocations and expenditure using gender markers validated by a quality assurance process	29/65	Not met. 28
7.5 2017 only: Number of countries supported by UN-Women where Ministries of finance issue gender responsive budgeting (GRB) guidelines	40	Exceeded. 45

Briefly describe the output and provide supporting narrative for the score

This output relates to the implementation of UN Women’s Strategic Plan. Due to the reporting period in question, a number of the indicators and milestones relate to the 2014-17 Strategic Plan. These indicators have been selected to act as an overall proxy for UN Women’s Strategic Plan. As a result, a number of the indicators will change from 2018 onwards and will be taken from the new Strategic Plan (2018-21), however, where possible we have tried to ensure that the individual thematic areas have been carried over.

Spearheaded by UN Women, the UN System-wide Action Plan or UN-SWAP, holds UN entities accountable for incorporating gender perspectives in all institutional functions. In 2017, a record 66 UN entities, 94 per cent of the total, reported on indicators of progress under the UN-SWAP. In addition, UN Women’s support was pivotal for the adoption or implementation of national plans, policies, strategies and legislation to promote women’s economic empowerment in 55 countries. An example of this activity in 2017, was when UN Women supported two countries (Barbados and Senegal) within national, local or sectoral planning documents.

In late 2017, the UN Secretary-General established a task force dedicated to formulating a rigorous common approach to addressing and preventing sexual harassment across the UN system. Bringing together representatives from all UN organisations, the task force is currently reviewing sexual harassment policies as well as investigation mechanisms. UN Women provided expertise on a number of core issues, including the creation of a joint assistance helpline for UN personnel.

Whilst indicator 7.4 was not met, fifty-four per cent of reporting entities (28) met or exceeded requirements in 2017, an increase of 4% (or net increase of two entities) since 2016. This represents an increase of 32% since 2012. Encouragingly, seven entities reported working to adopt resource tracking mechanisms. Several UN Secretariat Departments expressed continued complications presented by Umoja (the UN’s global system for financial, human and physical resource management and programme delivery) in the development and implementation of a gender marker. Thirty-five per cent of entities reported “missing” and “not applicable” ratings, remaining consistent with 2016, and reflecting a 14% decrease since 2012. Additionally, resource tracking is an area targeted by entities for enhancing performance; 12 entities noted it as an area of focus in 2017.

UN Women also played a pivotal role in the continued advancements in the area of tracking resources for gender equality and the empowerment of women, including through its leadership and coordination of the Inter-Agency Network on Women and Gender Equality (IANWGE), development of guidance materials, chairing of the working group on gender markers of the inter-agency Finance and Budget Network and provision of considerable technical support.

Lessons identified this year, and recommendations for the year ahead linked to this output

Indicator 7.2: Percentage of internal audit recommendations implemented.

Lessons identified: In 2017, UN-Women identified options for the most appropriate model to deliver internal auditing, including the financial resources required for the management and administrative structure of the function and its implementation. Additionally, the annual risk assessments of headquarters’ entities and processes and field offices were refined to reflect changes to UN-Women’s organisational structure and strategic and operational priorities.

Recommendations: During the year ahead, UN Women will continue to support the planning and implementation of the in-house internal audit function. UN Women will also continue to address recurring audit issues at both the field and corporate level.

Indicator 7.4: Number of agencies that track and report on allocations and expenditure using gender markers validated by a quality assurance process.

Lessons identified - UN Women have found challenge in meeting or exceeding indicator 7.4 through UN-SWAP, and have experienced particular difficulty in bringing the UN Secretariat on board with this system. On UN-SWAP, it is still challenging to increase ratings on the resource tracking indicator to meet or exceed rating, bringing the UN Secretariat on board is particularly challenging. The transition to the UN’s global management and programme delivery system (Umoja) has been a challenging factor for UN Women achieving this indicator, but the success of UN Economic and Social Commission for Western Asia (ESCWA) in modifying their gender marker to work within Umoja is a strong indication that this goal is achievable for the UN Secretariat and associated entities to fully adopt resource allocation and tracking. This would be a very big leap forward having the majority of the 66 reporting entities implementing and able to report resources allocated/budgeted and tracked/spent of GEWE.

Another challenge for UN Women in achieving Indicator 7.4 is assuring that the gender marker criteria is being consistently applied, and that data collected is regularly analysed and utilised to advocate for more and more effective financing for gender equality. In order to address consistency and standards, UN Women (through its Chairing of the Gender marker working group in the inter-agency Finance and Budget Network), has completed separate Guidance Notes on Coding Definitions and Quality Assurance - tools many UN entities had expressed a need for. UN Women will continue to coordinate efforts to improve and harmonise efforts to track resources for gender equality and the empowerment of women.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

As set out in the original business case, the theory of change was based on a shift from four separate business cases with associated logical frameworks to one business case with a corresponding logical framework. The rationale behind the single business case was that it provided a mechanism to achieve a strategic framework for UNCD’s funding with common objectives and indicators, supports our ability to emphasis common objectives with the agencies and stimulates collaboration between them. The existing theory of change remains valid at this stage and there have been no major changes in the past year.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

Although this is only the first annual review of the four-year business case, initial indications, based on the evidence submitted to DFID, are that the shift to a single business case is achieving the intended outcomes around a) accelerated normative and operational development results by UN Development System and b) UN system provides effective leadership and collaborates to deliver Agenda 2030 – norm-setting, coordination and monitoring across key sectors.

Work is currently underway with UN Development Agencies to agree PBR indicators and milestones for the remainder of the programme, as well as for the indicator and milestones relating to PSEA, which will match DFID’s enhanced ambition. This should help ensure that the programme remains on track to contribute to the expected outcomes and impact.

Explain major changes to the logframe in the past year (1/2 page)

There have been no major changes to the logframe in the past year.

Describe any planned changes to the logframe as a result of this review (1/2 page)

As highlighted elsewhere in the review, work is currently underway with agencies to agree PBR indicators and milestones, as well as one on PSEA for the remainder of the programme. These indicators and milestones will build on the success of year one which set a solid basis and foundation for delivery, as well as matching our high level of ambition for UN Development agencies.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

The original business case clearly sets out the rationale for UK investment in UN Development agencies. Although it is still early days, we are beginning to see progress in a number of areas, including those under output 2, Organisational Effectiveness, and output 3, Organisational Transparency, Accountability and Efficiency. Under these outputs, the four development agencies are working together on areas such as harmonising reporting at country level and increasing the use of common services on procurement, human resource management, information communication technologies and financial management services, all of which will ultimately lead to efficiency and effectiveness gains.

Over the course of the reporting period, agencies themselves also undertook a number of measures to maximise VfM. For example, UNFPA underwent a Comprehensive Resource Review (CRR) which resulted in a revised Integrated Budget being submitted to the Executive Board for approval in September 2018. As a result, UNFPA’s revised institutional budget is now $701.1 million, $7.3 million lower than the originally approved budget. The institutional budget decrease was mainly driven by the savings identified in the CRR, primarily in headquarters. Furthermore, country office realignments and regional office adjustments contribute to the reduced institutional budget. These reductions were partially offset by investments in three key areas: (a) strengthened field offices; (b) strengthened protection against sexual exploitation and abuse (PSEA) coordination; and (c) a strengthened investigations function.

In addition, UNDP, UNFPA together with UNOPS (not funded under the UN Development business case) continue their commitment to joint procurement by initiating, supporting and participating in initiatives and activities globally to pursue benefits and opportunities that results in stronger procurement practices, more efficient processes and lower costs. Examples include, UNFPA utilizing the global third-party logistics services which resulted in savings of $217,500 in four shipments, which represents a 28 per cent freight cost saving, compared to offers made by manufacturers through their own freight forwarders.

By consolidating air travel ticketing, the field offices of UN Women reduced expenditure on air fares by a third. The savings where channelled to programme activities. Through the UN system’s Procurement Harmonization Working Group, for UN Agencies with headquarters in USA, chaired by UN Women, participating agencies with headquarters in the USA mapped their procurement needs into a “common user items list” that identified over 30 services and goods that they commonly procure. The UN agencies then jointly developed and/or identified over 100 Long Term Agreements (LTA) with suppliers. These LTAs offer better contractual terms and reduce the average transaction lead-time by 5-20 days per transaction. Capitalising on these arrangements, UN Women has sourced in 2017 over 40% of its goods and services through the use of LTAs, which reduced transaction costs for these purchases by over 70%.

Furthermore, UNDP, UNFPA and UNICEF collaborated on the establishment of a fleet management and vehicle tracking contract that has proven to be very useful for many country offices and resulted in savings on the management of vehicles. The three agencies also implemented carpooling in five country offices, resulting in efficiency gains in fleet management.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

DFID’s core funding contribution to the UN Development agencies continues to provide a strong value for money case, enabling the agencies to deliver against their respective mandates which are key if Agenda 2030 is to be realised.

Core funding provides the UK with leverage and influence through our partnership with the agencies. Through the Executive Boards, annual strategic dialogues and high level engagement, including UNGA, ensures that UK priorities remain an integral part of agencies own Strategic Plans.

The shift from four separate business cases to the single business case has provided us with a mechanism to achieve a strategic framework for UNCD to channel funding, developing common objectives and indicators and enabling our own funding choices and management to stimulate collaboration across the UN development system. It has also provided space for UNCD to further explore how to generate stronger incentives for collaboration and integration within the UN, and help to maximise what we achieve with our programme and relationship management resource.

As a consequence to our more joined up approach (e.g. negotiating a single the MoU), we have seen agencies come together in a more coherent way to provide us with a joined up response. We are therefore seeing positive effects in terms of greater collaboration and coherence across the agencies, although it’s still too early to judge precisely how much of this is as a result of our new funding approach, as opposed to our political messaging and that of other donors.

Whilst delivery partner choices for non-core funded programmes are made by DFID country offices and headquarters-based spending departments, decisions are often market driven. UNCD has increased the information and support it provides to DFID country offices and the use of UN agencies to deliver where they have a strong comparative advantage. Given the large DFID multi-bi spend through UN development agencies, our coherent approach further drives VfM in the wider DFID programme portfolio.

Agencies themselves have continue to improve their measurement of value for money. This includes consideration of cost efficiency, programme quality and impact to enhance the organisations’ effectiveness and efficiency, both individually and jointly as per the indicators in the logframe.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

At the start of this programme DFID assessed the overall risk rating as moderate and it remains at this level. DFID ensured robust risk management arrangements throughout the reporting period. The risk register is live and kept up-to-date.

The majority of the risks identified at design stage remained applicable. These included: contextual risks, for example failure of the UN Secretary General to drive forward reform, or Member States diverging views dilute agency focus on key priorities such as on Sexual Reproductive Health and Rights (SRHR) and reforms; fiduciary risks, including fraudulent use of DFID funds, and; delivery risks, for example failure of agencies to raise sufficient contributions from other partners to resource delivery of their 2018-21 Strategic Plans, or agency incapacity or weak leadership hindering performance and reform. Although DFID has limited direct control over these risks, we actively monitored and managed risks through partnership with agencies and other member states.

During the reporting period, increased attention and focus was given to PSEA. PSEA is a key priority area for DFID, and the UK has played a crucial role in helping to lead the international community in this regard. As a result of UK and other member state input, PSEA now features formally on the Executive Board agenda for UNDP, UNFPA and UNICEF and will be discussed on an annual basis at the UN Women Board.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

UN Development agencies are governed by Executive Boards which DFID officials attend. Each agency has its own Executive Board which meets three times per year (January/February, June and September). Over the course of the year, the boards cover a range of topics such as audit, finance, programme management, results achieved and risk management. During the reporting period, DFID officials made a number of National Statements across each of the four agencies which highlighted DFID priorities including on UN reform and PSEA. Furthermore, the UK lead (on behalf of a number of other member states) a series of statements on issues such as audit, whilst joining other statements on things like evaluation. The UK also plays a key role in drafting and negotiating formal decision language for adoption at the boards. DFID recently helped secure significant decision language on reform and working methods of the boards despite strong opposition from other member states.

In addition to the formal boards, there were a number of high level meetings/engagements between DFID Ministers/Senior Management and agencies where DFID priorities were discussed. Strategic Dialogues took place with all four agencies in late 2017/early 2018. The meetings were held in London with agency heads or deputies present and provided a platform to have an open discussion on DFID priority areas, ways of working, as well as setting out our expectations for the year ahead. The next series of Strategic Dialogues are scheduled to take place in New York at the end of 2018. Furthermore, a number of Ministerial meetings with agency heads took place over the year, including in the margins of the UK hosted Disability Summit and at the UN heads of agencies meeting in London.

Annual Audited Statements were published within agreed timelines. No significant issues were identified in the Annual Audited Statements.

The Memorandum of Understanding (MOU) for 2018 payment is still being negotiated with agencies to take account of DFID’s strengthened position around PSEA, fraud, corruption etc. It is anticipated that the MOU will be agreed and finalised by October 2018. In addition to agreeing an MOU, DFID are also in the process of negotiating a Performance Agreement with the four agencies which sets out DFID’s expectations for agencies. Furthermore, in light of the revised MOU, DFID is also updating its Framework Agreement with agencies which other DFID departments utilise when working with UN Development agencies. Work is also underway to update agency Central Assurance Assessments which is scheduled for completion early 2019.

Asset management is not applicable to core funding.

Date of last narrative financial report(s)
Date of last audited annual statement (s)

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

As outlined above, DFID meet with agencies three times per year as part of the Executive Board. In addition to this, we meet on an annual basis as part of the strategic dialogue. Over the past few months, we have been meeting with agencies on a fortnightly basis to manage the complex programme of work around the MOU, Annual Review, Performance Agreement etc. Other ad-hoc meetings take place as and when required.

The DFID team have also engaged regularly with DFID country offices as they manage bilateral funding to these agencies, both to provide support and answer specific questions and queries, and to gain any insights into overall progress on agency performance, linking in with the core funding. The DFID team also liaise with DFID country offices in advance of the Executive Board if any country programme documents have been submitted for approval. During the reporting period, UKMIS colleagues joined UN missions to Haiti, Malawi and Rwanda to see how agencies operate in the field. Reports of these visits was presented at the September 2018 Executive Board. There have not been any requests for beneficiary feedback specific to this core funding over the past year.

This Annual Review was conducted by a team from DFID consisting of agency Senior Responsible Officer and various colleagues. Agencies submitted their annual report in June 2018 detailing the progress made against each of the indicators in year 1 of the programme (calendar year 2017). The DFID review team assessed this information, engaged with the organisations to clarify and follow up on various points and drew on this information when compiling this review.

DFID is in the process finalising the appointment of an M&E contractor for development and humanitarian core funding, as well as our core funding to the Red Cross. Starting in 2019, the contractor will provide independent input into future annual reviews, provide analysis to inform DFID's future PBR approach and in the longer term an assessment of the extent to which the PBR approach has achieved its objective. Further information will be provided to agencies once the contractor is in place.

Evidence (1/2 page)

As referenced elsewhere in the review, a number of the indicators and milestones will change going forward, as they were drawn from the old agency results framework (2014-17). The new agency results framework (2018-21) pay particular attention to LNOB which means that much of the data can be disaggregated accordingly and used to driver better targeting of resources.

In terms of the broader approach, a Monitoring and Evaluation Supplier is being contracted by DFID to undertake an evaluation of the business case, evaluating the impact of the intended ‘reforms’ and also evaluating the impact of the Payment by Results approach.

The indicators and milestones in the logframe were negotiated with agencies and were primarily taken from agencies own reporting frameworks such as the Integrated Results and Resources Frameworks (IRRF), QCPR etc.

Learning (1/2 page)

Specific learning points can be found under each sub-output in Section B and within other sections. In response to these, the DFID programme team and the agencies look forward to using the Annual Review process to identify ways in which we can collectively learn and adapt as necessary. There are also plans to work with agencies to learn lessons from this year’s annual review process so that we can minimise the burden on both parties.

Progress on recommendations from previous reviews (1/2 page)

N/A first annual review

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.
The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided