BUSINESS CASE

Reducing Maternal and Newborn Deaths in Kenya

October 2013
Acronyms

ANC	Antenatal care
ASAL	Arid and Semi-Arid Lands of Kenya
APHIA +	Aid Population Health Integrated Assistance
BEmONC	Basic emergency obstetric and neonatal care
CDC	United States Centers for Disease Control
CEmONC	Comprehensive emergency obstetric and neonatal care
CFR	Case fatality rate
CHMT	County Health Management Team
DALY	Disability-adjusted life year
DCP	Disease Control Priorities Project
DPHK	Development Partners in Health Kenya
DHMT	District Health Management Team
DHS	Demographic and Health Survey
EHS	Essential Health Services
FBO	Faith Based Organisation
FGM/C	Female genital mutilation/cutting
FIGO	International Federation of Gynaecology and Obstetrics
GAVI	Global Alliance for Vaccines and Immunisation
GEFA	Global Evaluation Framework Agreement
GDP	Gross Domestic Product
GIZ	Deutsche Gesellschaft für Internationale Zusammenarbeit
GOK	Government of Kenya
HFMC	Health Facility Management Committee
HRH	Human resources for health
HSS	Health system strengthening
HSPS	Health Sector Programme of Support
HSSF	Health Sector Services Fund
ICC	Interagency Coordinating Committee
ICAI	Independent Commission on Aid Impact
ITU	International Telecommunication Union
KEHP	Kenya Essential Health Package
KEMSA	Kenya Medical Supplies Agency
KFW	KfW Entwicklungsbank (German Development Bank)
KHP	Kenya Health Programme
KHSSP	Kenya Health Sector Strategic Plan
KMTC	Kenya Medical Training College
KPI	Key Performance Indicator
Ksh	Kenyan shilling
KSPA	Kenya Service Provision Assessment
LIST	Live Saved Tool
LSS	Life-saving skills
LSTM	Liverpool School of Tropical Medicine
MAR	Multilateral Aid Review
M&E	Monitoring and evaluation
MCH	Maternal and child health
MDG	Millennium Development Goal
MDR	Maternal death review
MiH	Making it Happen programme
MNH	Maternal and neonatal health
MOH	Ministry of Health
MOMS	Ministry of Medical Services
MOPHS	Ministry of Public Health and Sanitation
MOU	Memorandum of Understanding
MTP	Medium Term Plan
MTEF	Medium-Term Expenditure Framework
NGO	Non-Governmental Organisation
NBTS	National Blood Transfusion Service
NHIF	National Hospital Insurance Fund
NHSSP	National Health Sector Strategic Plan
OBA	Output-based aid
PEAKs	Professional Evidence and Applied Knowledge services
PBF	Performance-based funding
PMNCH	Partnership for Maternal, Newborn and Child Health
PNC	Post-natal care
QI	Quality improvement
RCOG	Royal College of Obstetricians and Gynaecologists
RH	Reproductive Health
RMC	Routine Maternal Care
SBA	Skilled birth attendance
SBR	Stillbirth rate
THE	Total health expenditure
TWG	Technical Working Group
UNFPA	United Nation Fund for Population and Development
UNICEF	United Nations Children’s Fund
USAID	United States Agency for International Development
VFM	Value for money
WHO	World Health Organisation
WRA	Women of Reproductive Age
Intervention Summary – Reducing Maternal and Newborn Deaths in Kenya

What support will the UK provide?
The UK will invest up to £75 million over 5 years (2013-2018) to reduce maternal and newborn deaths in Kenya by increasing access to and uptake of quality maternal health care. This will support health worker training (£9.3 million), county level health systems strengthening and testing of innovative approaches (£48.7 million), national level health systems strengthening (£1.4 million) and access to services for the poorest women (£11.4 million). £1.7 million is allocated for monitoring and evaluation with the remaining balance of £2.5 million set aside as contingency[1].
Why is UK support required?
What need are we trying to address? / Kenya has one of the highest rates of maternal mortality in the world, at 488 per 100,000 live births, and there has been little progress in the last decade. Deaths in young children have fallen since 2003, but newborn mortality has not. High death rates are due to poor access to quality delivery and emergency obstetric and neonatal care and low use of available services. Over half of women give birth at home without skilled care. Only one in three health facilities provide maternity services and one in ten hospitals provide basic emergency obstetric care. There are significant geographical and wealth inequalities. The proportion of women delivered by a skilled birth attendant ranges from 26% and 34% in Western and Rift Valley provinces to 89% in Nairobi; less than one in ten women in Turkana County (in what was Rift Valley province) give birth with support from a trained health worker[2]. The wealthiest women are four times more likely than the poorest to be delivered by a skilled birth attendant. / Health system challenges affecting maternal care include shortages of health workers, supplies and equipment, poor health worker competencies and weak referral systems. Inadequate financing, the underlying reason for many of these challenges, could be exacerbated by reforms following the recent election, as responsibility for health services is devolved to 47 newly-established counties. There are also financial, cultural and other barriers that prevent women using maternal care services. Addressing these challenges will require new ways of working and innovative approaches to improving service quality and tackling demand-side barriers. The new Kenyan Government has made commitments to introducing universal health coverage, but DFID support is still needed in the meantime to ensure that the poor receive basic health care and to reduce maternal and newborn death. Other donor funding for health is mostly for commodity procurement, HIV, malaria and tuberculosis. / What will we do to tackle this problem? / Training: Support for scale up of training for public sector doctors, nurses and clinical officers in emergency obstetric and neonatal care in five provinces to achieve national coverage, complementing the centrally DFID-funded Making it Happen programme in Kenya’s other three provinces. / Health systems strengthening: Support in three counties (Homa Bay, Bungoma and Turkana) with high rates of poverty and maternal and neonatal death, to build local government capacity to plan, budget, manage and deliver health services, strengthen accountability and referral mechanisms, and increase community demand. Extra support will be needed in Turkana to address the lack of health infrastructure and of health workers and to reach nomadic populations. The emphasis will be on flexible support for the transition to devolution and for piloting innovative approaches to improve delivery of and demand for maternal health services. Lessons will inform policy and practice more widely in Kenya as well as how development partners engage with new county governments. We will also continue to provide technical assistance for health systems strengthening to the Ministry of Health at national level. / Support to address financial barriers to maternal and newborn health care: We will support demand-side financing strategies, such as output-based aid (OBA). This is likely to be implemented through voucher schemes to enable the poorest women in the same three counties to access services at subsidised rates and improve the responsiveness and quality of services. The new Kenyan Government is committed to eliminate fees for maternal health care, but is still exploring options for implementation. The implications of this for voucher schemes will be monitored but at present we believe that measures to reduce financial barriers for the poorest women will continue to be required. / Training has been shown to improve maternal and newborn health outcomes internationally and in Kenya. The DFID Essential Heath Services programme in Nyanza province, which included training, health system and community interventions, resulted in significant improvements in maternal and newborn health outcomes. OBA pilots in Kenya have increased use of maternal care by the poorest women. Training will be delivered by the Liverpool School of Tropical Medicine (LSTM), which manages the Making it Happen programme, to ensure consistency of approach and quality, build on existing relationships and minimise additional costs. A service provider will be contracted to support health systems strengthening and demand-side interventions in Bungoma, and UNICEF Kenya will implement the same interventions in Turkana and Homa bay, where it already has a presence. UNICEF will also provide management oversight of LSTM and the service provider, and support for central health systems strengthening. The service provider will also lead on the implementation of an innovation fund in the three focal counties. / How will this intervention contribute to UK and DFID commitments and results? / The intervention will contribute to the UK’s strategy for Kenya and development priorities of reducing poverty, improving service delivery to the poorest and empowering women and girls. It will contribute to DFID 2011/15 Business Plan commitments to: save the lives of 50,000 women in pregnancy and childbirth; stop 250,000 newborns from dying; support at least 2 million safe deliveries; and ensure long-lasting improvements in quality maternity services, particularly for the poorest 40%. It will directly contribute to the DFID Kenya 2011/15 Operational Plan headline result: support 15,000 women to deliver with a skilled birth attendant by 2015.
What are the expected results?
The impact is reduced maternal and neonatal mortality in Kenya. The outcome is increased access to and utilisation of quality maternal and newborn health services. Outputs are: health workers in 5 provinces have the knowledge and skills to provide quality delivery care and emergency obstetric and neonatal care; health systems strengthened to manage and deliver maternal and newborn health services in Homa Bay, Bungoma and Turkana counties; and increased demand for and uptake of maternal health services in the same 3 counties. By 2018, DFID will contribute to preventing 1,123 maternal and 4,223 neonatal deaths. Benefits will continue after 2018; we estimate that 3,170 maternal and 10,372 neonatal deaths will be prevented between 2013 and 2022. Specific results include: / 9,000 health workers trained in 5 provinces. / 95,000 additional births attended by skilled birth attendant in the 3 counties / Proportion of births attended by a skilled attendant increased from 44% to 65% nationally; and from 18% to 43% in Homa Bay, 28% to 53% in Bungoma and 7% to 32% in Turkana. / Increase in number of facilities providing basic emergency obstetric and neonatal care to at least 16 and comprehensive emergency obstetric and neonatal care to at least 4 in each of 3 counties. / Subsidised vouchers for maternal health care provided to 130,000 women in 3 counties. / Reports from implementers, data from monitoring and the health information system, and surveys will be used to determine whether results have been achieved. Specific issues will be evaluated, including the effectiveness and efficiency of different approaches to delivering services, increasing quality and demand and building capacity. The intervention represents very good value for money: by 2022 it is expected to save about 650,000 Disability Adjusted Life Years (DALYs) at a unit cost of about £100. The long term outlook for sustainability is good, as the new Kenyan Government’s commitment to move to universal health coverage implies an increase in government financing.
[1] Contingency has been factored in due to the vast uncertainties around devolution as outlined in detail in the business case.
[2] Kenya’s eight provinces, which were sub-divided into districts, are being replaced by 47 counties.