BUSINESS CASE

Reducing Maternal and Newborn Deaths in Kenya

October 2013
Acronyms

ANC	Antenatal care
ASAL	Arid and Semi-Arid Lands of Kenya
APHIA +	Aid Population Health Integrated Assistance
BEmONC	Basic emergency obstetric and neonatal care
CDC	United States Centers for Disease Control
CEmONC	Comprehensive emergency obstetric and neonatal care
CFR	Case fatality rate
CHMT	County Health Management Team
DALY	Disability-adjusted life year
DCP	Disease Control Priorities Project
DPHK	Development Partners in Health Kenya
DHMT	District Health Management Team
DHS	Demographic and Health Survey
EHS	Essential Health Services
FBO	Faith Based Organisation
FGM/C	Female genital mutilation/cutting
FIGO	International Federation of Gynaecology and Obstetrics
GAVI	Global Alliance for Vaccines and Immunisation
GEFA	Global Evaluation Framework Agreement
GDP	Gross Domestic Product
GIZ	Deutsche Gesellschaft für Internationale Zusammenarbeit
GOK	Government of Kenya
HFMC	Health Facility Management Committee
HRH	Human resources for health
HSS	Health system strengthening
HSPS	Health Sector Programme of Support
HSSF	Health Sector Services Fund
ICC	Interagency Coordinating Committee
ICAI	Independent Commission on Aid Impact
ITU	International Telecommunication Union
KEHP	Kenya Essential Health Package
KEMSA	Kenya Medical Supplies Agency
KFW	KfW Entwicklungsbank (German Development Bank)
KHP	Kenya Health Programme
KHSSP	Kenya Health Sector Strategic Plan
KMTC	Kenya Medical Training College
KPI	Key Performance Indicator
Ksh	Kenyan shilling
KSPA	Kenya Service Provision Assessment
LIST	Live Saved Tool
LSS	Life-saving skills
LSTM	Liverpool School of Tropical Medicine
MAR	Multilateral Aid Review
M&E	Monitoring and evaluation
MCH	Maternal and child health
MDG	Millennium Development Goal
MDR	Maternal death review
MiH	Making it Happen programme
MNH	Maternal and neonatal health
MOH	Ministry of Health
MOMS	Ministry of Medical Services
MOPHS	Ministry of Public Health and Sanitation
MOU	Memorandum of Understanding
MTP	Medium Term Plan
MTEF	Medium-Term Expenditure Framework
NGO	Non-Governmental Organisation
NBTS	National Blood Transfusion Service
NHIF	National Hospital Insurance Fund
NHSSP	National Health Sector Strategic Plan
OBA	Output-based aid
PEAKs	Professional Evidence and Applied Knowledge services
PBF	Performance-based funding
PMNCH	Partnership for Maternal, Newborn and Child Health
PNC	Post-natal care
QI	Quality improvement
RCOG	Royal College of Obstetricians and Gynaecologists
RH	Reproductive Health
RMC	Routine Maternal Care
SBA	Skilled birth attendance
SBR	Stillbirth rate
THE	Total health expenditure
TWG	Technical Working Group
UNFPA	United Nation Fund for Population and Development
UNICEF	United Nations Children’s Fund
USAID	United States Agency for International Development
VFM	Value for money
WHO	World Health Organisation
WRA	Women of Reproductive Age
Intervention Summary – Reducing Maternal and Newborn Deaths in Kenya

What support will the UK provide?
The UK will invest up to £75 million over 5 years (2013-2018) to reduce maternal and newborn deaths in Kenya by increasing access to and uptake of quality maternal health care. This will support health worker training (£9.3 million), county level health systems strengthening and testing of innovative approaches (£48.7 million), national level health systems strengthening (£1.4 million) and access to services for the poorest women (£11.4 million). £1.7 million is allocated for monitoring and evaluation with the remaining balance of £2.5 million set aside as contingency[1].
Why is UK support required?
What need are we trying to address? / Kenya has one of the highest rates of maternal mortality in the world, at 488 per 100,000 live births, and there has been little progress in the last decade. Deaths in young children have fallen since 2003, but newborn mortality has not. High death rates are due to poor access to quality delivery and emergency obstetric and neonatal care and low use of available services. Over half of women give birth at home without skilled care. Only one in three health facilities provide maternity services and one in ten hospitals provide basic emergency obstetric care. There are significant geographical and wealth inequalities. The proportion of women delivered by a skilled birth attendant ranges from 26% and 34% in Western and Rift Valley provinces to 89% in Nairobi; less than one in ten women in Turkana County (in what was Rift Valley province) give birth with support from a trained health worker[2]. The wealthiest women are four times more likely than the poorest to be delivered by a skilled birth attendant. / Health system challenges affecting maternal care include shortages of health workers, supplies and equipment, poor health worker competencies and weak referral systems. Inadequate financing, the underlying reason for many of these challenges, could be exacerbated by reforms following the recent election, as responsibility for health services is devolved to 47 newly-established counties. There are also financial, cultural and other barriers that prevent women using maternal care services. Addressing these challenges will require new ways of working and innovative approaches to improving service quality and tackling demand-side barriers. The new Kenyan Government has made commitments to introducing universal health coverage, but DFID support is still needed in the meantime to ensure that the poor receive basic health care and to reduce maternal and newborn death. Other donor funding for health is mostly for commodity procurement, HIV, malaria and tuberculosis. / What will we do to tackle this problem? / Training: Support for scale up of training for public sector doctors, nurses and clinical officers in emergency obstetric and neonatal care in five provinces to achieve national coverage, complementing the centrally DFID-funded Making it Happen programme in Kenya’s other three provinces. / Health systems strengthening: Support in three counties (Homa Bay, Bungoma and Turkana) with high rates of poverty and maternal and neonatal death, to build local government capacity to plan, budget, manage and deliver health services, strengthen accountability and referral mechanisms, and increase community demand. Extra support will be needed in Turkana to address the lack of health infrastructure and of health workers and to reach nomadic populations. The emphasis will be on flexible support for the transition to devolution and for piloting innovative approaches to improve delivery of and demand for maternal health services. Lessons will inform policy and practice more widely in Kenya as well as how development partners engage with new county governments. We will also continue to provide technical assistance for health systems strengthening to the Ministry of Health at national level. / Support to address financial barriers to maternal and newborn health care: We will support demand-side financing strategies, such as output-based aid (OBA). This is likely to be implemented through voucher schemes to enable the poorest women in the same three counties to access services at subsidised rates and improve the responsiveness and quality of services. The new Kenyan Government is committed to eliminate fees for maternal health care, but is still exploring options for implementation. The implications of this for voucher schemes will be monitored but at present we believe that measures to reduce financial barriers for the poorest women will continue to be required. / Training has been shown to improve maternal and newborn health outcomes internationally and in Kenya. The DFID Essential Heath Services programme in Nyanza province, which included training, health system and community interventions, resulted in significant improvements in maternal and newborn health outcomes. OBA pilots in Kenya have increased use of maternal care by the poorest women. Training will be delivered by the Liverpool School of Tropical Medicine (LSTM), which manages the Making it Happen programme, to ensure consistency of approach and quality, build on existing relationships and minimise additional costs. A service provider will be contracted to support health systems strengthening and demand-side interventions in Bungoma, and UNICEF Kenya will implement the same interventions in Turkana and Homa bay, where it already has a presence. UNICEF will also provide management oversight of LSTM and the service provider, and support for central health systems strengthening. The service provider will also lead on the implementation of an innovation fund in the three focal counties. / How will this intervention contribute to UK and DFID commitments and results? / The intervention will contribute to the UK’s strategy for Kenya and development priorities of reducing poverty, improving service delivery to the poorest and empowering women and girls. It will contribute to DFID 2011/15 Business Plan commitments to: save the lives of 50,000 women in pregnancy and childbirth; stop 250,000 newborns from dying; support at least 2 million safe deliveries; and ensure long-lasting improvements in quality maternity services, particularly for the poorest 40%. It will directly contribute to the DFID Kenya 2011/15 Operational Plan headline result: support 15,000 women to deliver with a skilled birth attendant by 2015.
What are the expected results?
The impact is reduced maternal and neonatal mortality in Kenya. The outcome is increased access to and utilisation of quality maternal and newborn health services. Outputs are: health workers in 5 provinces have the knowledge and skills to provide quality delivery care and emergency obstetric and neonatal care; health systems strengthened to manage and deliver maternal and newborn health services in Homa Bay, Bungoma and Turkana counties; and increased demand for and uptake of maternal health services in the same 3 counties. By 2018, DFID will contribute to preventing 1,123 maternal and 4,223 neonatal deaths. Benefits will continue after 2018; we estimate that 3,170 maternal and 10,372 neonatal deaths will be prevented between 2013 and 2022. Specific results include: / 9,000 health workers trained in 5 provinces. / 95,000 additional births attended by skilled birth attendant in the 3 counties / Proportion of births attended by a skilled attendant increased from 44% to 65% nationally; and from 18% to 43% in Homa Bay, 28% to 53% in Bungoma and 7% to 32% in Turkana. / Increase in number of facilities providing basic emergency obstetric and neonatal care to at least 16 and comprehensive emergency obstetric and neonatal care to at least 4 in each of 3 counties. / Subsidised vouchers for maternal health care provided to 130,000 women in 3 counties. / Reports from implementers, data from monitoring and the health information system, and surveys will be used to determine whether results have been achieved. Specific issues will be evaluated, including the effectiveness and efficiency of different approaches to delivering services, increasing quality and demand and building capacity. The intervention represents very good value for money: by 2022 it is expected to save about 650,000 Disability Adjusted Life Years (DALYs) at a unit cost of about £100. The long term outlook for sustainability is good, as the new Kenyan Government’s commitment to move to universal health coverage implies an increase in government financing.
[1] Contingency has been factored in due to the vast uncertainties around devolution as outlined in detail in the business case.
[2] Kenya’s eight provinces, which were sub-divided into districts, are being replaced by 47 counties.

Business Case

Strategic Case

A. Context and need for DFID intervention / DFID intervention is needed to address high rates of maternal and neonatal mortality in Kenya. These reflect a combination of health system weaknesses, poor quality of care and barriers that limit women’s access to maternal health services. The health sector is undergoing significant changes, with responsibility for service delivery being devolved to counties in line with the new Kenyan Constitution, following the election in March 2013. Map 1 shows the previous provinces; map 2 shows the new counties. This intervention includes support for three counties: Homa Bay, formerly part of Nyanza province; Bungoma, formerly part of Western; and Turkana, formerly part of Rift Valley. Data in this business case refers in the main two provinces as county data is not yet available. / Kenya is also at risk of violence, conflict and insecurity. An estimated 135,000 people were displaced due to violence in 2012, most for a short time, although around 35,000 are still living in camps in North Eastern and Coast provinces. Outbreaks of political and ethnic violence, whilst mostly localised, are difficult to predict. Violence and conflict can have a significant impact, making it hard to work in affected areas and to reach affected or displaced populations, interrupting service delivery and, in some cases, creating the perception that some groups are favoured over others. / Map 1 Map 2 / (i) Maternal and neonatal health in Kenya / There has been little progress in reducing maternal and newborn death. Maternal and neonatal mortality rates are declining globally[1], but not in Kenya, where the rate is among the highest in the world, at 488/100,000 live births. This has changed little in the past decade and the Millennium Development Goal (MDG) target of 147/100,000 is unlikely to be met. Maternal deaths represent around 15% of all deaths in women aged 15-49 or 8,000 deaths each year[2]. Early age of first pregnancy, unmet need for contraception and high fertility rates, which increase the lifetime risk of maternal death, are key factors. More than 10% of girls are married before the age of 18 and nearly 20% aged 15-19 have begun childbearing, with higher rates in Nyanza, Coast, North Eastern and Rift Valley provinces. The highest fertility rates are in North Eastern, Western and Nyanza provinces, at 5.9, 5.6 and 5.4 respectively[3]. Neonatal mortality fell only slightly from 33/1,000 to 31/1,000 live births between 2003 and 2008/9[4]. Deaths in newborns account for 60% of infant and 42% of under-five deaths[5]. A review of the National Health Sector Strategic Plan 2005/10 (NHSSP II) found improvements in all indicators except maternal and neonatal mortality, skilled delivery and nutrition[6]. / Death rates are higher in the poorest provinces and the poorest women. Maternal and neonatal mortality rates are higher in North Eastern, Rift Valley, Western and Nyanza provinces[7]. UNICEF identifies as most at risk the poorest women in North Eastern and Rift Valley, HIV-positive women in Nyanza, particularly in what are now Homa Bay and Siaya counties, and women in urban slums[8]. The maternal mortality rate in Turkana County is estimated at over 1,000/100,000 live births, more than twice the national average[9]. Disparities reflect poverty, poor infrastructure, high fertility and a nomadic population in Turkana and a high burden of HIV and poor service quality in Nyanza. According to the 2008/9 DHS, Nyanza has the highest HIV prevalence rate in Kenya at 14% (compared with 6.3% nationally), with 16% prevalence in women aged 15-49 (8% nationally). The second highest rate, at 7%, is in Western and Nairobi; HIV prevalence in Turkana County is 6.3%. / Most of these maternal and newborn deaths are preventable. Conditions during the perinatal period are the second leading cause of death in Kenya[10]. The main direct causes of maternal death are haemorrhage (25%), infection (15%), hypertensive diseases of pregnancy (13%), obstructed labour (12%) and abortion complications (8%)[11]. Most neonatal deaths are due to prematurity, low birth weight, infection and birth asphyxia[12]. These deaths are largely preventable, if women and newborns receive appropriate care from a skilled health worker[13]. Maternal mortality can be reduced significantly if women have access to skilled birth attendance, 24-hour basic and comprehensive emergency obstetric care, family planning and safe abortion. Skilled delivery, emergency newborn and immediate post-natal care can significantly reduce neonatal mortality[14]. / More than half of women in Kenya give birth at home and without skilled care. Although 92% of pregnant women receive antenatal care (ANC) only 43% give birth in a health facility[15]. There has been little change since 2003, when 40% of women delivered in a health facility[16]. Nationally, only 44% of women are delivered by a doctor, nurse or midwife. Many are assisted by traditional birth attendants (28%), relatives or friends (21%)[17]. Low rates of skilled birth attendance reflect low availability and low uptake/use of services. / Coverage and quality of maternal health services is inadequate. The single greatest risk factor for maternal and neonatal death is poor access to skilled birth attendants and emergency referral services[18],[19]. WHO recommends that, for every 500,000 people, there should be four facilities providing basic emergency obstetric and newborn care (BEmONC) and one providing comprehensive emergency obstetric and newborn care (CEmONC), with provision defined by signal functions[20]. In Kenya, only one in three facilities offers basic maternity services and only one in ten hospitals offer BEmONC services; fewer provide CEmONC[21]. Only 9% of facilities providing delivery services can perform all signal functions for BEmONC[22]. Few can offer blood transfusion, caesarean section and life-saving interventions for newborns. Other surveys show that most facilities offering maternity services do not meet the criteria for EmONC provision[23],[24]. In a national assessment of EmONC services, most could not perform many of the signal functions. Blood transfusion was least likely to be provided in Rift Valley and caesarian section in Rift Valley and Nyanza. Lack of training, supplies and equipment were key factors influencing availability of care[25]. The NHSSP II review noted that only 19% of facilities provide 24-hour services; another review put the figure at 30%[26]. / There are significant geographical and wealth inequities. The draft health sector Medium Term Plan II highlights urban-rural disparities in service availability; the cost of services is also a barrier to access for the 46% of the population living below the poverty line. Poor distribution of facilities, lack of transport and weak referral systems perpetuate unequal geographical access to services[27]. The proportion of women delivered by a skilled birth attendant ranges from 26% in Western, 32% in North Eastern and 34% in Rift Valley provinces to 89% in Nairobi. Wealthy women are four times more likely (81%) to be delivered by a skilled birth attendant than the poorest women (20%)[28]. A review scored the equity of skilled birth attendance in Kenya at 18 out of 54, with 54 being the highest level of equity[29]. Rates of facility-based delivery range from 17% in North Eastern to 89% in Nairobi (rates in Nyanza, Western and Rift Valley are below 50%) and from 18% in the poorest to 81% in the wealthiest quintiles. Urban women (75%) are more than twice as likely to deliver in a heath facility as rural women (35%)[30]. There are similar differences in caesarean section rates; in Western (3.5%) and Nyanza (4.4%) these are below the national average of 6.2%, and they are 2% and 3% in the lowest two wealth quintiles[31]. According to WHO, acceptable rates are within a range of 5-15%[32]. / High maternal and neonatal mortality and low availability and utilisation of maternal care reflect inadequate health worker skills, health system weaknesses, and factors that limit demand. / (ii) Health worker knowledge and skills / Health workers lack skills to provide quality care. Reducing maternal and neonatal mortality requires a health workforce that can provide quality delivery care and manage complications[33]. The National Maternal and Neonatal Health Road Map identified inadequate health provider skills as a key constraint. An assessment of competencies among trained workers providing emergency obstetric and neonatal care found that, across five core procedures, the proportion performing to an acceptable standard ranged from 23% to 56%[34]. A survey of quality of care for prevention and management of maternal and newborn complications found that health workers scored fairly well on knowledge of routine delivery (71%) and newborn care (65%), but less well on knowledge of management of complications: only 1% knew the correct steps to manage post-partum haemorrhage, 4% the steps to manage obstructed labour and 12% how to manage newborn asphyxia[35]. / Coverage with in-service training is inadequate. In-service training is critical, as current pre-service training does not provide health workers with adequate knowledge and skills in emergency obstetric and neonatal care. The 2010 Kenya Service Provision Assessment (KSPA) found that only 36% of health workers providing maternal care had received such in-service training in the past three years. A recent joint donor mission recommended that support should focus on improving the availability of skilled birth attendance and emergency obstetric care and, specifically, scale up of health worker training through expansion of the DFID-funded Making it Happen programme[36]. / (iii) The health system and maternal and newborn health care / Government share of total spend on health is low. Total health expenditure increased from Ksh 82.2 billion in 2001/2 to Ksh 122.9 billion in 2009/10 and in per capita terms from US$34 in 2001/2 to US$42 in 2009/10. However, government’s share has remained at around 29%. Households make the largest contribution, at 37% in 2009/10; the donor contribution increased from 16% in 2001/2 to 35% in 2009/10. Only 20% of the population is covered by health insurance, mostly through the National Hospital Insurance Fund (NHIF)[37]. Government expenditure on health is also low. Government spending on health increased from KSh 24.3 billion in 2001/2 to KSh 35.4 billion in 2009/10. In per capita terms this represents an increase from US$9.9 to US$12.1[38]. But since 2003 the share of total government expenditure allocated to health has been between 5.3% and 6.7%, below the Abuja target of 15% and insufficient to meet existing demand or to improve the availability of maternal health care. Hospitals absorb 70% of expenditure[39]. Medium-term projections in 2011 showed no increase in the budget share allocated to health, suggesting that this would remain at around 6.1% between 2011/12 and 2013/14. Recent Government of Kenya commitments could result in an increase in the budget allocation for health, but this is not certain. In addition, counties will make spending decisions and may opt to use central funds allocated for health to other sectors. / Higher government expenditure on health and reform of health financing is critical to improve health outcomes. The Health Sector Review for the Medium-Term Expenditure Framework (MTEF) 2012/13-2014/15 suggested the government would need to double current funding to achieve its health objectives. Through its Kenya Health Programme, which runs to 2015, DFID is supporting the Government of Kenya and WHO to strengthen budget processes in the health sector, focusing on the MTEF (see Economic Appraisal for Terms of Reference). Kenya has also made several unsuccessful attempts to introduce reform of health financing. As a result, there has been a proliferation of parallel financing schemes and Kenya still lacks a comprehensive health financing strategy[40]. Introduction of universal health insurance coverage is a priority, but there is no consensus on how this will be implemented. Experience elsewhere, including in Ghana, Rwanda and South Africa, suggests that income growth can catalyse a shift towards universal coverage and increased health spending, with pooled public expenditure representing a rising share of total health expenditure[41]. / Shortages and inequitable distribution of health workers are a major challenge. The availability of trained health workers is crucial to reducing maternal and neonatal mortality. WHO recommends a minimum of 25 doctors, nurses and midwives per 10,000 population. The figure for all health workers in Kenya is 17/10,000, with only 0.18 medical specialists, 0.25 medical officers, 1.82 registered nurses and 3.08 enrolled nurses per 10,000[42]. Between 2009 and 2011, an additional 7,000 health workers were employed and production of mid-level cadres increased. However, vacancy rates are estimated at 29%, with the most acute gaps in clinical officers, enrolled nurses and community health workers, all critical to maternal and newborn care. The staff-to-population ratio is around 7/10,000 in rural areas compared with 15.9/10,000 in urban areas. Nairobi has 8% of Kenya’s population but 25% of public sector doctors. North Eastern and Rift Valley have the most significant gaps in the health workforce. Turkana has one of the lowest nurse-to-population ratios in the country[43] and many staff are poorly trained[44]. Homa Bay and Bungoma counties also have staff-to-population ratios below the national average[45]. Recruiting and retaining health workers in rural areas is difficult due to poor working conditions, lack of incentives and limited training and career opportunities. A scheme to attract health workers to rural posts has had some success, but shortages remain. There is a lack of reliable data about the number, distribution and skills of the existing workforce. Human Resources for Health (HRH) mapping to inform planning has only covered national and provincial staff so far. The HRH Transition Plan 2011/14 includes actions to support devolution of HRH responsibility to counties. / Despite expansion of health infrastructure, some areas remain under-served. The public sector runs 55% of health facilities, with the remaining 45% comprised of private for-profit, faith-based and NGO facilities. In addition to two national referral hospitals, the health system is organised at five levels: secondary and provincial general hospitals (level 5); county and district hospitals (level 4); health centres (level 3); dispensaries and clinics (level 2); and community (level 1). Infrastructure increased from around 5,600 to 7,100 facilities, mainly at primary care level, under NHSSP II 2005/10. Some health centres and dispensaries have been rehabilitated and hospital infrastructure is being improved, but many facilities do not meet current norms and standards[46]. Only 52% of the population live within 5km of a health facility, and facilities are unevenly distributed across the country. Populations are particularly poorly served in North Eastern and Rift Valley, where the distance to facilities can be as far as 90km. Facilities are typically located in towns and coverage has not improved for nomadic communities for whom static services are less appropriate[47]. The joint donor mission recommended allocation of additional donor funds for infrastructure at level 2 and 3, especially in Nyanza, Western, Coast and North Eastern[48]. / Availability of drugs and supplies has improved, but stock outs occur and facilities lack basic equipment. In the past there were shortages of life-saving drugs for maternal and newborn care, but supply has improved following reform of the Kenya Medical Supplies Agency (KEMSA)[49]. The 2010 KSPA confirmed that availability of medicines and supplies to manage complications of delivery had improved. However, other studies have found shortages of essential drugs for maternal care and the KSPA found shortages of essential supplies and equipment for maternal care in most facilities. / Recent investment has improved availability of transport but referral systems remain weak. An assessment in 2008 found that only one in three (37%) facilities complied with national standards for the availability of ambulances in working order[50]. During the past two years, 300 ambulances provided by the Government of Kenya and United Nation Fund for Population and Development(UNFPA) have been distributed to districts. However, referral remains problematic in areas where infrastructure is poor, distances to health facilities are far and transport is limited. The Community Strategy (see (v) below) includes establishing emergency obstetric referral systems through Community Units, but progress in scaling this up has been slow. / Comprehensive data on maternal and newborn health is not available. In line with the Heath Information System Policy 2010/3, which aims to improve data availability and use, there has been significant investment in strengthening the system, including roll out of a web-based district health information system. However, there is a lack of disaggregated sub-national and wealth quintile data and of facility-based data on maternal and neonatal health indicators. Challenges include parallel data collection and storage systems and weaknesses in data analysis, dissemination and use. / There is scope to improve health service delivery through use of innovative approaches and new technologies. Although there is considerable support for innovation and new technologies at the highest political level, and Kenya’s private sector is among the most dynamic in East Africa, the public sector has been relatively slow to implement innovative approaches to improve the reach and quality of health services. New ways of working are required, not just in the context of devolved government, but also to address the current weaknesses in provision of quality basic services to poor people. Tapping into the creativity and different ways of working of Non-Governmental Organisation (NGOs), Faith Based Organisation (FBOs) and the private sector could help to identify approaches with potential for wider application. There is scope to use new technologies in areas such as data collection, training, clinical management in peripheral facilities and community education. The Government of Kenya has launched an e-health strategy that includes telemedicine, e-learning, m-health and information for citizens. Established innovations include use of biometric smart cards by health insurance companies and electronic claims processing by the NHIF. Other uses of tablets and smart cards in the sector are being explored, as is the use of mobile phones to improve communication for referral[51]. Mobile phone access in Kenya increased from around 23,000 to 22 million between the 1990s and 2010; internet access increased from around 2,500 in 1996 to almost 4 million in 2009 according to the ITU(International Telecommunication Union) and national regulators’ data. There is growing evidence that electronic and mobile technologies can improve service delivery in a range of sectors[52], including health[53]. / Accountability mechanisms exist but need strengthening Improving accountability and transparency is central to the new Constitution and proposed devolution of powers, and to DFID Kenya’s anti-corruption strategy. Social accountability – to improve public perception of health services, performance reporting, transparency and public participation in decision making – is one of the principles of the National Health Policy. The KHSSP III highlights accountability challenges and aims to establish anti-corruption committees in all 47 counties and 100% of health facilities by 2018. The Community Strategy (see (v) below) includes health facility committees and community health committees, but the extent to which these have been established and are functioning varies. To improve accountability for performance of new county governments, efforts will be needed to build their capacity to engage citizens, gather feedback and share information and to support civil society organisations and communities to participate effectively in planning, budgeting and monitoring. / (iv) Factors limiting demand / Lack of transport is a major barrier. In the Demographic Health Survey (DHS) 2008/9, 42% of women cited distance and lack of transport as the main reason for not delivering at a health facility. The poorest women were more likely to give this as a reason (49%) than the wealthiest women (26%). Abrupt delivery was cited by 18% of women, reflecting lack of birth preparedness as well as distance. UNICEF reports that in Turkana physical access is the main problem, but low rates of facility delivery also reflect the influence of structural, economic and cultural factors on women’s decisions about where to deliver. / Limited awareness and socio-cultural factors also play a role. The 2009 Road Map identifies low recognition of danger signs in pregnancy and delivery, and socio-cultural barriers, as factors in failure to seek care or delays in seeking care. Kenyan households are less likely to seek care for pregnancy and delivery-related concerns than for a sick child[54]. One in five women (21%) does not deliver in a health facility because it is not deemed necessary[55] suggesting the need for better awareness of the importance of skilled attendance. Cultural beliefs about pregnancy and birth, use of traditional birth attendants and concerns about health worker attitudes and quality of health services are also factors. In addition, female genital mutilation/cutting (FGM/C) has serious consequences during childbirth, especially for women who have undergone extreme forms of the procedure. According to WHO, FGM is linked to increased complications in childbirth and maternal deaths. FGM also puts babies at risk during delivery. Although outlawed by the Children Act of 2001, it is still practised in many Kenyan communities. Current estimates are that 27% of women are cut/circumcised although the practice is more prevalent in some communities including the Somali, Kisii and Masai[56]. The rate of FGM/C in Rift valley is 31%.[57] / Gender inequality is also a factor. In 2011, Kenya ranked 143 of 187 countries (with 1 being the most equal and 187 being the least equal) on the UNDP Gender Inequality Index[58]. Economic inequality, socially-ascribed gender roles and limited access to education, training and productive resources limit women’s voice and opportunities[59]. The prevalence rate for gender-based violence is high; in the DHS 2008/9, 39% of women reported experiencing physical violence in the previous 12 months. Health indicators show that women of reproductive age are among the most adversely affected by the lack of affordable, quality health services[60]. Women are also more likely to be infected with HIV, with prevalence among those aged 15-49 years at 8.8% compared with 5.5% among adult men[61]. Although little data is available about the impact of lack of autonomy on women’s health care-seeking behaviour, gender inequality influences women’s ability to seek care. There is limited awareness of the role of gender as a determinant of health and in delivery of services; the health sector is currently developing a gender policy to address this. The new Constitution guarantees the right to the highest attainable standard of health including reproductive health and requires an understanding of how roles, access to resources, decision-making and power relations between women and men affect health outcomes. / Cost is a deterrent for poor women. Despite economic growth, nearly half of the population of Kenya lives below the official poverty line[62]. Poverty has been exacerbated by post-2008 election disturbances and displacement, drought and rising food prices, with children, women and rural populations most affected. In the DHS 2008/9, 17% of women cited cost as the main reason for not delivering in a health facility. Cost was more often given as a reason by the poorest women and by young women. International evidence shows that user fees prevent the poorest women from using maternal health services. User fees were introduced in government health facilities in Kenya in 1989. Since then, these have been removed and partially reinstated. A user fee reduction policy (10/20 Policy) was adopted in 2004, with exemptions for antenatal and delivery care. (Commitments made by the new government to eliminate fees for maternal health care are discussed in (v) below.) However, unofficial charges are common; 80% of facilities still charge user fees for maternal health services[63]. Primary health care facilities are dependent on user fees, so adherence to official policy is low, at less than 33% for antenatal and delivery care[64]. Women often incur additional charges if they are referred to higher-level facilities for management of obstetric complications and there are reports of mothers and babies not being allowed to leave until payments are made. / (v) National policy and health sector context / Improving health is a Government of Kenya priority. Vision 2030, which aims to transform Kenya into a middle-income country, recognises that improving health is essential. It emphasises the need to reduce inequities through the introduction of universal health insurance, use of innovative approaches including OBA, and improving performance, including in maternal and infant survival. Maternal and neonatal health features in the Government’s MTEF. The Health Sector Policy is based on the principles of the Constitution and aims to ‘build a progressive, responsive and sustainable technologically-driven, evidence-based and client-centred health system for accelerated attainment of the highest standard of health for all Kenyans’. The health sector MTP II 2013/17 is being revised to reflect priorities and flagship projects in the manifesto of the new Government[65]. These include: national scale up of high impact interventions, with a focus on maternal, neonatal and child health; improved referral systems; construction of model level 4 hospitals; social health protection; reform of HRH; establishing e-health hubs in 58 health facilities; and strengthening health research. / There is a supportive policy framework for maternal and newborn health. The KHSSP III aims to reduce maternal mortality to 300/100,000 by 2015 and 150/100,000 by 2018. It sets ambitious service delivery targets including increasing the proportion of deliveries by skilled birth attendants to 60% by 2015 and 65% by 2018[66], the proportion of facilities providing BEmOC to 80% by 2015 and 90% by 2018 and hospitals offering caesarean section to 85% by 2015 and 95% by 2018. The Road Map aims to accelerate the reduction of maternal and newborn mortality through skilled attendants, supportive health systems and community action; specific mention is made of scaling up BEmONC at level 2 and 3 facilities, CEmONC at level 4 facilities, and OBA. Other key frameworks include the National Reproductive Health Policy 2007; National Reproductive Health Strategy 2009/15; Kenya Essential Health Package (KEHP), which defines the package of care to be provided at each level of the health system; and 2011 Acceleration Plan for the Attainment of Maternal and Newborn Health, which identifies a package of evidence-based, high-impact interventions. There is a nationally agreed 5-day curriculum for in-service training on emergency obstetric and neonatal care and national guidelines for maternal and perinatal death notification and review. The draft Health Sector Gender and Equality Policy seeks to focus attention on gender as a determinant of health and to strengthen gender-sensitive research, service delivery, community education and data collection and analysis. / The government’s Community Strategy 2006 revolves around a Community Unit, training community midwives, increasing awareness and demand, and strengthening links between communities and facilities. However, limited resources have been allocated and implementation has been slow. By 2012, only 2,530 Community Units had been established, less than the target of 8,500. In November 2012, the Government of Kenya launched a Rapid Results Initiative to scale up provision of BEmONC to 120 health facilities across the country – a baseline survey identified lack of EmONC skills and poor attitudes among health workers as key problems – and a second phase is planned. The new Government has also committed to scale up of high impact community health interventions. How this and the Rapid Results Initiative will be funded and implemented has yet to be decided. / The new Government has made commitments on maternal health and health financing. Priorities include consolidating and expanding existing mechanisms to achieve universal health coverage, progressive elimination of user fees in public health facilities and free primary health care. Provision of free maternal care in all public health facilities is an immediate priority. How this will be implemented, including mechanisms for reimbursing facilities is under discussion, but the government’s manifesto included a commitment to increase the share of total government expenditure allocated for health to 15%. There is also an ambitious vision for the private sector in health but, while basic health indicators for much of the population remain poor, it will be important to strike the right balance between encouraging private sector provision and ensuring that government financing is sufficient to meet the demand for health services from the country’s large low-income population. Increased and sustainable financing for health will depend on identifying the right combination of pooled public, private and insurance mechanisms[67] as well as political commitment. / National government structures and responsibilities for health are undergoing major change. Responsibility for health has been divided between the Ministry of Medical Services and the Ministry of Public Health and Sanitation. Following the election, these two ministries are being merged. The role of the new national Ministry of Health will change to reflect devolution of responsibilities to the 47 new counties, with a Health Act providing the legislative framework. The new Ministry will be responsible for policy, legislation, coordination, standards, quality monitoring, technical planning and national referral hospitals. Functions where the division of responsibilities between central and county levels has yet to be finalised include management of provincial hospitals, procurement of drugs and supplies, public health, and monitoring and evaluation. The roles of Kenya Medical Training Colleges and counties in production and training of HRH are also still to be determined. Restructuring of human resources is planned with some national and all provincial staff being transferred to counties. The HRH transition plan will require resourcing and technical support. Ensuring that the merger of the two ministries and devolution of functions do not disrupt service delivery will be critical. / Management and delivery of health services will be decentralised. New County Health Departments will be responsible for delivering health services, including maternal and child health care, with devolved budgets and authority. There will be a 3-year transition period, with devolution of functions and funding determined by county capacity. Service delivery will continue to be funded centrally until county treasury and public financial management structures are established. Counties will be able to create positions and recruit their own health staff; this is expected to address bureaucratic delays in filling vacancies and ensure that staffing matches local needs. However, devolution will add to the complexity of planning and budgeting in the health sector. Counties will fund some health services from a block grant and others through specific grants and nationally-managed programmes. Under the new Constitution, each county will receive not less than 15.5% of total government revenue. A further 0.5% will be distributed to the poorest counties via an equalisation fund. Some counties will be worse off than at present, while others will have additional resources available. The three counties to receive targeted support through this intervention fall into the latter category. Counties will need support on health financing[68] as well as for health planning and financial management, contract and performance management, human resource and supplies management, data analysis and use, and accountability. National government will provide some assistance but additional technical support will be required, as will the flexibility to respond to the specific heath systems strengthening needs of different counties. In addition, development partners will need to develop new ways of working with county governments and health departments. / (vi) Other development partner support / There is relatively little donor support for maternal and newborn health. The USAID-funded Aid Population Health Integrated Assistance Plus (APHIA +) maternal, neonatal and child health programme 2011/15 focuses on HIV and family planning and is mainly delivered through non-state partners. USAID, UNICEF and other partners are supporting the Community Strategy. Safe blood is critical to reducing maternal mortality and US CDC has provided significant support to the National Blood Transfusion Service. UNICEF works in safe motherhood and neonatal and child health and is supporting interventions in northern Kenya. UNFPA support focuses on fistula prevention and management. DANIDA funds sexual and reproductive health services through NGOs under its Health Sector Programme Support (HSPS) 2012/16. / DFID is the only donor supporting training in maternal and neonatal care at scale. Kenya is one of the countries included in the second phase of the Making it Happen (MiH2) programme, funded by DFID centrally, which will run from 2012 to 2015. It will train national trainers across the country and support training for health workers in Central, Western and Nyanza provinces. UNFPA has trained community midwives and nurse anaesthetists in four districts and provided limited support for roll out of maternal death review (MDR). A review of the National Human Resources for Health Strategic Plan 2009/12 concluded that there was insufficient funding for in-service training. / There are gaps in donor funding for health systems strengthening. The US, through various implementing partners, is providing support to strengthen health leadership and management, human resources, health information systems, the supply chain and health infrastructure. For example, in Nyanza and Western, PATH is supporting health systems and community health workers, mainly in relation to HIV, and the 5-year FUNZO programme is expanding pre-service training capacity and strengthening national health workforce planning and information systems. USAID is considering support to 20 counties but the scope of this is not yet clear. DANIDA supports the Health Sector Services Fund (HSSF), which channels funds to primary care facilities, and capacity building in planning, budgeting and commodities management. The World Bank also supports the HSSF and commodity procurement and management. JICA is focusing on universal health coverage. DANIDA and GIZ have provided support for management and leadership training. The World Bank has piloted performance-based financing of facilities in Samburu county, linking payments to use of maternal and child health services. Planned Global Alliance for Vaccine and Immunisation (GAVI) support for health system strengthening aims to improve access to maternal, newborn and child health services, with a focus on immunisation, in the arid and semi-arid lands (ASAL) region[69]. / Some areas of the country receive very little donor support. A mapping of support for maternal and neonatal health noted that development partners are present in almost all districts, but only the HSSF and the APHIA Plus programme are national in scope. DANIDA has, until recently, focused on Coast and DFID on Western and Nyanza provinces[70]. Donor presence in Rift Valley and North Eastern is minimal. USAID support for maternal health in northern Kenya focuses on HIV and community health workers. The European Union is funding maternal and child health, family planning and nutrition in the ASAL region, mainly through non-state actors. UNICEF is one of the few organisations working more comprehensively on maternal and child health in northern Kenya, including in Turkana. As noted above, GAVI support for the ASAL counties will commence in 2014. / (vii) Rationale for DFID intervention / Need for DFID support. No other donor plans to provide the support to maternal and newborn health set out in this intervention. There is relatively little other donor support for governance, human resources, health financing and monitoring and evaluation of health systems strengthening[71]. This intervention would address some of these gaps and complement other donors in line with the division of labour agreed by partners. The health sector is underfunded; in the short-term, the Government of Kenya and other donors are unlikely to make the investment required to ensure all women receive quality maternal care. There is a strong equity and development case for intervention and the DFID Kenya Operational Plan highlights the importance of donor assistance to develop new approaches to service delivery and governance so that the poorest Kenyans benefit from the country’s progress. DFID is one of the few donors positioned to support testing innovative approaches and use of new technologies to improve service quality, value for money and sustainability. / UK priorities and commitments. Kenya matters to the UK for foreign policy, commercial, economic and security reasons. The intervention will also contribute to the UK’s development priorities of reducing poverty, improving service delivery for the poorest, supporting innovation and empowering women and girls. The UK is committed to accelerating progress on MDGs 4 and 5 and the intervention will contribute to DFID 2011/15 Business Plan commitments to: save the lives of 50,000 women in pregnancy and childbirth; stop 250,000 newborns from dying needlessly; support at least 2 million safe deliveries; and ensure long-lasting improvements in quality maternity services, particularly for the poorest 40%. It is aligned with DFID’s Framework for Results for improving reproductive, maternal and newborn health in the developing world, specifically to: remove barriers that prevent access to quality services, particularly for the poorest and most at risk; expand the supply of quality services, delivering cost-effective interventions for family planning, safe abortion, ANC, delivery and emergency obstetric care, postnatal and newborn care through stronger health systems; and enhance accountability for results. DFID also recognises the need for innovative approaches to make good basic services available for all and this intervention will contribute to and benefit from DFID’s Innovation Hub. As Kenya graduates from reliance on donor funding for basic services, support to develop and test new approaches will become more important. Experience in countries such as China shows that this is where DFID can add most value. / Deliver key results in the DFID Kenya Operational Plan 2011/15. In the health sector, DFID Kenya aims to influence and support national level policy development and implementation for malaria, reproductive health, HIV/AIDS and health systems, including financing and human resources for health, and to support strategies that increase poor people’s access to quality health services. Improving service delivery is one of three overarching DFID strategies and improving maternal and neonatal health is a priority for DFID Kenya – this intervention will contribute to the headline result in the 2011/15 Operational Plan: support 15,000 women to deliver with a skilled birth attendant by 2015. / Build on DFID experience and track record. DFID is one of the largest donors in Kenya and has been active in health for many years, including as the donor lead in the Reproductive Health Steering Committee. It has well-established links with the Government of Kenya and other sector partners and is well positioned to support a new programme to reduce maternal and neonatal mortality. This intervention will build on previous DFID investment in the Essential Health Services (EHS) programme, which provided national support for policy and stewardship of the KEHP and health systems strengthening and community support with a focus on maternal and neonatal health in Nyanza, and on central DFID investment in the MiH programme; the joint donor mission recommended that DFID expand EHS and scale up support for training in maternal care[72]. / Complement and leverage other DFID Kenya investment. The intervention will complement DFID investment in family planning (£31m 2012/17), malaria control (£31m 2013/15), private sector pro-poor interventions (£3.8m 2013/15) and the Kenya Health Programme (£106m 2010/15), which includes funding through WHO to provide national support for health systems strengthening. It will also complement DFID Kenya support in other sectors, in particular for girls’ education, cash transfers and wealth creation, all of which will contribute to improving the health of women and girls, as well as central DFID support for MiH and DFID-supported regional initiatives to empower adolescent girls, reduce unsafe abortion and tackle FGM/C. The Box below provides a brief summary of links between this intervention and DFID investment in other areas of maternal and reproductive health. / Summary Links with maternal and newborn health / Family planning DFID Kenya £31m programme 2012/17. Investment in private sector and NGO family planning service provision and strengthening the public sector family planning programme (commodities, training, and policy). Aims to increase contraceptive prevalence rate from 44% in 2012 to 55% by 2017 and provide family planning services to at least 1.9 million new users High fertility and unmet need for contraception increase the risk of maternal mortality. Family planning plays a key role in reducing maternal death, through delay and spacing of childbearing, reducing lifetime risk of maternal death and reducing risk of unwanted pregnancy and unsafe abortion. Child spacing benefit infants and young children. Delivering family planning services together with maternal health services costs less than delivering maternal health alone; investments in family planning offset the costs of improved maternal and newborn healthcare[73] / Adolescent girls DFID Adolescent Girls Initiative. £13.62 million over 6 years. DFID Kenya providing support to build the assets, health and education of adolescent girls, benefiting at least 15,000 girls Improving girls’ access to education and assets and keeping them in school can delay age of sexual debut and first pregnancy – early pregnancy is associated with higher risk of maternal mortality. Educated and empowered girls are more likely to use family planning and maternal health services / FGM/C DFID (Africa Department, Policy Division, Research and Evidence Division) £35m regional programme 2013/18. Support for research, policy, legislation, communication and direct community work FGM/C increases risk of complications in childbirth. Eliminating the practice will improve the health of women and girls and reduce the risk of maternal and neonatal mortality and morbidity associated with complications during delivery / Malaria control DFID Kenya £31m programme 2013/15 Pregnant women are more vulnerable to malaria and complications of malaria; malaria also increases risk of maternal death. Improved malaria control will contribute to reduced maternal (and child) mortality / National health systems strengthening DFID Kenya Health Programme £106m 2010/15 National support to strengthen central ministry functions, including budget processes, which will be critical to ensure adequate financing for health, technical support to new county health departments and national strategies to ensure adequate health infrastructure, workforce, drugs and supplies / Complement and leverage DFID Kenya support to strengthen health financing. This includes current support, referred to earlier, to assist the health sector to make a stronger case for additional resources to the Ministry of Finance, specifically to support the Ministry of Health during preparations for the 2014/15-2016/17 budget cycle and its engagement with MTEF and annual budget processes. This intervention will take forward this work in the three target counties, supporting county health teams to improve budgeting and allocation of resources, as well as to secure adequate funding. In parallel, DFID will strengthen national engagement through the health financing working group and technical support for reform of mechanisms such as the NHIF[74] and development of a coherent approach to universal health insurance[75]. Ongoing support for national level health systems strengthening will be critical to ensure that policy and operational frameworks are in place. / Opportunities and challenges of devolution. The shift to devolved governance is an opportunity to create more equitable health services, but there is also a risk of service disruption or deterioration, especially in historically under-served areas. Through the Kenya Health Programme, WHO will provide some management support, but WHO capacity to work at sub-national level is limited. Experience in other countries suggests that, unless well managed, decentralisation can exacerbate existing fiscal and human resources inequalities[76] and adversely affect reproductive health services, if these are not prioritised by local governments[77]. DFID support will help to ensure that priority is given to maternal care services and the health of mothers and newborns. / Scope for innovation and learning. DFID can play an important role in bringing international and regional experience, introducing innovative approaches and alternative models of service delivery and demonstrating that such approaches can be adopted at scale. The intervention has the potential to strengthen the evidence base on the: (i) role of new technology in enhancing training, referral and other aspects of service delivery; (ii) effectiveness of demand-side financing; (iii) innovative approaches to improve service delivery, including in remote areas and for nomadic populations, and to demand creation; and (iv) capacity development for decentralised management of health services.
B. Impact and Outcome that we expect to achieve / The impact is reduced maternal and neonatal mortality in Kenya. The outcome is increased access to and utilisation of quality maternal and newborn health services. DFID support will contribute to: / Preventing 1,123 maternal deaths / Preventing 4,223 neonatal deaths / Specific expected results that will contribute to reduced mortality and reflect improve availability and utilisation of quality maternal health care services include: / 95,000 additional births delivered by a skilled birth attendant / An increase in proportion of births attended by a skilled attendant: / National: from 44% to 65% / Homa Bay: from 18% to 43%; Bungoma: from 28% to 53%; Turkana: from 7% to 32% / An increase in the caesarean section rate: / National: from 2% in the lowest and 3.1% in the second lowest wealth quintiles to 5% / Homa Bay: from 1.2% to at >5%; Bungoma: from 1.4% to >5%; Turkana: from 1% to 5% / An increase in facilities able to provide BEmONC and CEmONC: / National: proportion of health facilities providing BEmONC from 10% to 50%; / National: proportion of hospitals providing CEmONC from 20% to 50% / Homa Bay, Bungoma and Turkana: BEmONC 16 per county; CEmONC 4 per county / A reduction in the obstetric case fatality rate[78]: / National: from 2.9% to 2.5% / Homa Bay: from 2.4% to 1.5%; Bungoma: from 2.5% to 1.5%; Turkana: from X% to 1.5% / 9,000 doctors, clinical officers and nurses trained to provide quality delivery care and life-saving emergency obstetric and neonatal care in 5 provinces / Subsidised vouchers for maternal health care provided to 130,000 women of reproductive age in Homa Bay, Bungoma and Turkana.
[1] WHO, 2008. Trends in maternal mortality 1990-2008.
[2] DHS 2008/9
[3] DHS 2008/9
[4] DHS, 2003; DHS 2008/9
[5] DHS, 2008/9
[6] KHSSP 2012/18
[7] Division of Reproductive Health, 2011. Emergency obstetric and newborn care assessment.
[8] UNICEF, 2013. Equity in maternal and newborn health in Kenya.
[9] UNICEF proposal, February 2013.
[10] Review of the Kenya Health Policy Framework 1994-2010.
[11] NCAPD, 2010.
[12] National Reproductive Health Policy, 2007; Ministry of Health, Annual Statistical Report 2008.
[13] PMNCH, 2011. A global review of the key interventions related to reproductive, maternal, newborn and child health.
[14] Campbell O and Graham W, 2006. Strategies for reducing maternal mortality: Getting on with what works. Lancet 368: 1284-99; PMNCH, 2010. Sharing knowledge for action on maternal, newborn and child health; Paxton A et al, 2005. The evidence for emergency obstetric care. J Ob Gyn 88: 181-93.
[15] DHS, 2008/9.
[16] DHS, 2003.
[17] DHS, 2008/9.
[18] UNICEF, 2013. Equity in maternal and neonatal health in Kenya.
[19] Government of Kenya, 2009. National Road Map for Accelerating the Attainment of the MDGs related to Maternal and Newborn Health.
[20] BEmONC facilities provide seven signal functions: parenteral administration of antibiotics, oxytocics and anticonvulsants, manual removal of the placenta, manual vacuum aspiration, vacuum extraction, newborn resuscitation (plus stabilisation of the mother and newborn for referral); CEmONC facilities provide all basic signal functions plus caesarean section and safe blood transfusion.
[21] KPSA, 2010.
[22] Use of parenteral oxytocin and parenteral antibiotic were the most commonly performed signal functions; assisted delivery was the least commonly performed function.
[23] Echoka E et al, 2011. Challenges in implementing EmONC in Malindi district, Kenya: A maternity facility survey. African Journal of Health Sciences 19.
[24] Ziraba A et al, 2009. The state of emergency obstetric care services in Nairobi informal settlements and environs: Results from a maternity health facility survey. BMC Health Services Research 9:26.
[25] Division of Reproductive Health, 2011. Emergency obstetric and newborn care assessment.
[26] Lehmann L et al, 2011. Joint Mission: Harmonising support to reproductive health in Kenya.
[27] KHSSP III 2012/18.
[28] DHS 2008/9.
[29] Barros A et al, 2011. Equity in maternal, newborn and child health interventions in Countdown to 2015: A retrospective review of survey data from 54 countries. Lancet 379 (9822): 1225-33.
[30] DHS 2008/9.
[31] DHS, 2008/9.
[32] Gibbons et al, 2010. The global numbers and costs of additionally needed and unnecessary caesarean sections performed per year. World Health Report Background Paper No. 30.
[33] Support the Workforce. Knowledge Summary 6. PMNCH.
[34] Health workforce competence and facility readiness to provide quality maternal and newborn health services in Kenya, presentation at dissemination meeting, March 2011.
[35] Kagema F et al, 2010. Quality of care for prevention and management of common maternal and newborn complications: Findings from a national health facility survey in Kenya.
[36] Lehmann L et al, 2011. Joint Mission: Harmonising support to reproductive health in Kenya.
[37] Savedoff W et al, 2012. Transitions in health financing and policies for Universal Health Coverage: Final report of the Transitions in Health Financing Project. Results for Development Institute.
[38] KHSSP III 2012/18.
[39] Kenya National Health Accounts, 2010.
[40] African Health Markets for Equity, 2013. Kenya Country Report.
[41] Savedoff W et al, 2012. Transitions in health financing and policies for Universal Health Coverage: Final report of the Transitions in Health Financing Project. Results for Development Institute.
[42] KHSSP III 2012/18.
[43] CRA, December 2011. Kenya County Fact Sheets.
[44] Human resources for health assessment of northern Kenya, Capacity Project, presentation October 2012.
[45] CRA, December 2011. Kenya County Fact Sheets.
[46] KHSSP III 2012/18.
[47] KHSSP III 2012/18.
[48] Lehmann L et al, 2011. Joint Mission: Harmonising support to reproductive health in Kenya.
[49] KEMSA presentation, February 2012.
[50] Mutungi A et al, 2008. Kenya: Assessment of health worker competency and facility readiness to provide quality maternal health services. USAID.
[51] Gathara V, 2012. Report on facilitated roundtable on the use of mobile phone technology for public health.
[52] UNDP, 2012. Mobile technologies and empowerment: Enhancing human development through participation and innovation.
[53] Saving lives at birth, 2011; Dentzer S, 2010. E-health in the developing world. Health Affairs 29:2; 2010 mHealth Summit. See also WHO survey of Member States’ utilisation of mHealth (http://resultsfordevelopment.org).
[54] DHS, 2008/9.
[55] DHS, 2008/9.
[56] National Coordinating Agency for Population and Development, 2010. Maternal death on the rise in Kenya: A call to save women’s lives. NCAPD Policy Brief No.9.
[57] Country profile. FGM in Kenya. May 2013. 28Toomany
[58] The Gender Inequality Index measures gender inequality based on 5 indicators (maternal mortality; adolescent fertility; parliamentary representation; educational attainment; labour market participation) in three dimensions (reproductive health; empowerment; and the labour market).
[59] Nzioki (undated). Gender dimension of risk, vulnerability and Insecurity for social protection: Kenyan study. Draft report. Intergovernmental Authority for Development and European Development Fund.
[60] Kenya National Commission on Human Rights, 2012. Realising sexual and reproductive health rights in Kenya: A myth or a reality? A Report of the Public Inquiry into the Violations of Sexual and Reproductive Health Rights in Kenya.
[61] National Council for Population and Development, 2009. Kenya Demographic and Health Survey 2008-2009. Calverton, Maryland: Macro International Inc
[62] KIHBS, 2005/6.
[63] KPSA, 2010.
[64] KEMRI-Wellcome Trust, Government of Kenya, 2011. Health service delivery, governance and supportive supervision under the HSSF: National baseline survey.
[65] Transforming Kenya: securing Kenya’s Prosperity 2013-2017. Jubilee Coalition Manifesto.
[66] Note that the new Government of Kenya expects the elimination of fees for maternal health care to increase this to 80% by 2018.
[67] Savedoff W et al, 2012. Transitions in health financing and policies for Universal Health Coverage: Final report of the Transitions in Health Financing Project. Results for Development Institute.
[68] World Bank, 2012. Devolution without disruption: Pathways to a successful new Kenya.
[69] Turkana, Marsabit, Samburu, Isiolo, Mandera, Wajir, Garissa, West Pokot, Baringo and Tana River. GAVI support will also be used to improve infrastructure in Narok and Kajiado counties which have nomadic populations.
[70] Lehmann L et al, 2011. Joint Mission: Harmonising support to reproductive health in Kenya.
[71] Lehmann L et al, 2011. Joint Mission: Harmonising support to reproductive health in Kenya.
[72] Lehmann L et al, 2011. Joint Mission: Harmonising support to reproductive health in Kenya.
[73] Singh, S et al (2009) Adding It Up: The Costs and Benefits of Investing in Family Planning and Maternal and Newborn Health. New York: Guttmacher Institute and UNFPA.
[74] The Government of Kenya is currently exploring options for health financing and channelling funds for reimbursement of health facilities following the elimination of user fees for primary care; the National Hospital Insurance Fund (NHIF) is one of the options. Issues under consideration include changing the name of the NHIF to the National Health Insurance Fund and reviewing its regulatory framework and governance.
[75] Savedoff W et al, 2012. Transitions in health financing and policies for Universal Health Coverage: Final report of the Transitions in Health Financing Project. Results for Development Institute.
[76] Kolehmainene-Aitken R-L, 2004. Decentralisation’s impact on the health workforce. Human Resources for Health 2:5.
[77] Berman P and Bossert T, 2000. A decade of health sector reform in developing countries: What have we learnt?
[78] Obstetric case fatality used as a proxy measure of service quality improvement in health facilities.

Appraisal case

A. What are the feasible options that address the need set out in the Strategic Case?

(i) Feasible options

Three options, as well as a ‘do nothing’ option, are considered to address the need set out in the Strategic Case and achieve the expected impact. In summary, these options are:

- Option 1: National scale up of a training-centred approach
- Option 2: Scale-up of a training-centred approach together with targeted support for health systems strengthening in three counties (Homa Bay, Bungoma and Turkana) i.e. Option 1 with the addition of targeted health systems support
- Option 3: Scale-up of a training-centred approach together with targeted support for health systems strengthening and demand-side financing in three counties (Homa Bay, Bungoma and Turkana) i.e. Option 2 with the addition of demand-side financing
- Option 4: Do nothing

The option of including an alternative county to Turkana in Options 2 and 3, specifically Nyamira in Nyanza or Kakamega in Western, was considered initially. Both have rates of skilled birth attendance below the national average, although not as low as Homa Bay and Bungoma. They also have fewer challenges than Turkana, where the cost of delivering interventions is higher because of the difficult topography, low population density, limited infrastructure, and nomadic population. Consequently, it would be easier to achieve greater results in the short term in either of these counties than in Turkana. However, there is a compelling equity case for providing support in Turkana (see (a) rationale for selection of counties under Option 2 below) and these alternatives were therefore ruled out. A brief description of each option, with a summary of available evidence, is provided below.

Option 1: National scale up of a training-centred approach

Building on the success of Phase 1 of the DFID centrally funded Making it Happen (MiH1) programme (2009/11) in five countries including Kenya, this option would complement Phase 2 of Making it Happen (MiH2) (2012/15) in order to achieve national coverage with training in EmONC for all health workers who provide maternal health care in all public sector hospitals and selected health centres. The first phase of the MiH programme resulted in demonstrable improvements in health worker competencies and maternal and newborn health outcomes. The second phase, also funded by DFID centrally, has started in 3 provinces. The MiH approach centres on training master trainers and practical, competency-based in-service training in EmONC. MiH1 trained around 60 master trainers and 400 health workers at provincial and district hospital level. MiH2 will:

- Train 180 master trainers, including medical, clinical officer and nurse tutors, obstetricians and senor midwives, in Kenya Medical Training Colleges (KMTCs) and provincial general hospitals, covering all 8 provinces.
- Provide training equipment for KMTCs in 3 provinces (Central, Nyanza and Western) to support pre-service and in-service training.
- Support in-service training in EmONC using the agreed national 5-day curriculum for up to 3,200 doctors, clinical officers and nurses who provide maternal care at hospital and health centre levels in the same 3 provinces.
- Support regular follow-up and mentoring of trained staff, including through e-learning, in the 3 provinces.
- Conduct additional training for County Health Management Teams (CHMTs), hospital managers, senior clinicians and midwives in quality of care, in particular implementation of maternal death review (MDR)[79] and in M&E(Monitoring and Evaluation) to improve quality and use of data, in the 3 provinces.
  [79] Maternal death review is a means to examine the causes of deaths and to reflect on steps that could have been taken to avert each death.
- Provide essential life-saving equipment for EmONC to facilities as required.
The design of MiH2 reflects lessons learned and recommendations from the final appraisal of MiH1 including the need to: establish a national pool of trainers; standardise national training; deliver training at scale; and strengthen supportive supervision, quality improvement, MDR and M&E.

The Ministry of Public Health and Sanitation identified scaling up training of health professionals in EmONC as a priority and requested DFID Kenya support to expand MiH2 to cover the whole country. To achieve national coverage, this option would therefore:

- Train master trainers in hospitals run by national faith-based organisations and NGOs, which are not covered by MiH2.
- Provide training equipment for KMTCs in the 5 remaining provinces (Coast, Eastern, Nairobi, North Eastern and Rift Valley).
- Support in-service training in EmONC using the agreed national 5-day curriculum for up to 9,000 doctors, clinical officers and nurses who provide maternal care at hospital and health centre levels in these 5 provinces[80]
  [80] The expected number of health workers to be trained through this intervention is calculated on the basis of KHSSP III data on the number of government health facilities in the country and the number of health workers to be trained per facility at each level used by MiH2, taking into account facilities in the 3 provinces to be covered by MiH2. Given Government Kenya plans to recruit additional health workers, and staff rotation, the total also includes an assumption that there will be a 20% increase in the number of health workers needing to be trained during the period 2013/18. (See Appraisal Case Section C for detailed figures.)
- Support regular follow-up and mentoring of trained staff in the 5 provinces.
- Conduct additional training for CHMTs, hospital managers, senior clinicians and midwives in quality of care, in particular implementation of MDR, and in M&E to improve quality and use of data, in the 5 provinces.
- Provide essential life-saving equipment for EmONC to facilities as required.

In addition, this option would support coordination and planning of in-service EmONC training at national and county levels, and work in partnership with the Ministry of Health, WHO and other partners to modify pre-service training curricula to include EmONC competencies. The latter is critical to building sustainable training capacity and to reduce the need for large-scale in-service training in future. Consideration will also be given to scale up of training for nurse anaesthetists, building on UNFPA training, based on needs assessment and consultation with the Ministry of Health and other stakeholders.

Option 2: Scale-up of a training centred approach together with targeted support for health systems strengthening in Homa Bay, Bungoma and Turkana counties

Option 2 would support scale up training as described under Option 1 and, additionally, provide targeted support for health systems strengthening in three counties, including for piloting and implementing innovative approaches to improving service quality and increasing demand for maternal health care. It would also include some technical assistance for central level health systems strengthening. This option would deliver both quick wins country-wide and more sustainable improvements in maternal and newborn health in the selected counties. Provision of health systems strengthening support to additional counties is not feasible within the available resource envelope, so counties have been selected based on need and where the potential to reduce maternal and neonatal mortality is greatest. The rationale for selection of the three counties and a description of proposed health system strengthening activities are outlined below.

(a) The counties selected for additional health systems strengthening support are Homa Bay, Bungoma and Turkana

This is based on criteria including poverty rates, maternal and neonatal mortality rates, availability and uptake of maternal health services, prior DFID support, other development partner support and agreed donor division of labour, as well as scope to develop alternative models of health systems strengthening in the context of devolution and of service delivery in a range of different settings. Table 1 provides a summary of key data.

Table 1: Key data for Homa Bay, Bungoma and Turkana counties

Sources: Population: 2011 projected, AOP; population density: census 2009; poverty: % of individuals below the national poverty line, Kenya Integrated Household Budget Survey 2005/6; skilled birth attendance: DHS 2008/9; delivered in a health facility: Kenya Integrated Household Budget Survey 2005/6; population/nurse and population/doctor: Kenya County Fact Sheets 2011.

The selection also reflects parameters proposed by the Government of Kenya: counties with very low rates of skilled birth attendance; inclusion of one county which was included in the EHS programme in Nyanza in order to build on success; inclusion of one county in Western, which faces similar problems and conditions to Nyanza; and inclusion of Turkana.

The ASAL region, which includes Turkana, has historically been marginalised in national policy and development and severely under-resourced and under-exploited[81]. The region remains chronically poor – Turkana has one of the highest poverty rates in the country – and is vulnerable to shocks and stresses, including frequent drought. The environment is harsh, infrastructure is basic, the economy is poorly developed, services are few, and insecurity remains a threat[82]. The new Constitution and the recently revised ASAL policy and institutional framework[83] highlight the need for the region to be brought fully into the country’s political, economic and social development and to receive specific support to address its unique challenges for health system development and health service delivery.
[81] Kenya Vision 2030.
[82] Government of Kenya (Draft 4 February 2013). Drought Risk Management and Ending Drought Emergencies Medium Term Plan 2013-2017.
[83] Ministry of State for Development of Northern Kenya and other Arid Lands. Sessional Paper No. 8 of 2012 on National Policy for the Sustainable Development of Northern Kenya and other Arid Lands: ‘Releasing Our Full Potential’ 11 October 2012.

Rift Valley, Nyanza and Western provinces are reported to have among the worst indicators for maternal and newborn health in Kenya. Only North Eastern Province has worse indicators, but operations are limited there by security concerns. Rates of skilled birth attendance are low in Homa Bay and Bungoma and especially low in Turkana. Rates of facility delivery are also well below the national average in Bungoma and Turkana (see Table 1). Bungoma is ranked 41 of 47 counties in facility-based delivery and 43 of 47 in qualified medical assistance during birth; Turkana is ranked 46 of 47 in both[84]. DFID Girl Hub data, mostly drawn from the DHS 2008/9, also suggests that Rift Valley and Nyanza provinces have some of the worst indicators for girls. For example, Rift Valley and Nyanza have the highest proportion of girls who have had sex by age 15, at 22% and 14.2% respectively; Rift Valley has the second highest proportion (after North Eastern) of girls who do not know a modern contraceptive method, at 19.6%. Western, Rift Valley and Nyanza are also three of the four provinces with the highest proportion of adolescent girls who deliver without a skilled birth attendant, at 71.1%, 64.3% and 50.7% respectively.
[84] CRA, December 2011. Kenya County Fact Sheets.

According to UNICEF, mothers and newborns in Turkana are among the most vulnerable in Kenya due to extremely poor access to health services, poor service quality and socio-cultural barriers to care seeking. Only two-thirds of health facilities are functional. Facilities in Rift Valley province are least likely to provide antenatal and post-natal care[85].Most of Turkana’s population has limited access to basic health services; less than 10% live within two hours of a facility that provides emergency obstetric and neonatal care. Poor service availability and quality reflect severe shortages of human resources, with 60% of nursing and 90% of doctor posts unfilled and high staff turnover resulting in frequent closure of facilities, and shortages of essential drugs and supplies, with an estimated 60% of facilities experiencing regular stock outs of delivery kits and other supplies for maternal and newborn health in 2012. Barriers to care seeking include a preference for home delivery and the nomadic lifestyle of much of the population[86].
[85] KPSA, 2010.
[86] UNICEF, 2013. Project proposal to DFID. Leadership and equity for maternal and newborn health in Turkana County. February 2013.

A recent UNICEF bottleneck analysis identified shortages of health workers and access to maternal and newborn health services, in particular EmONC, as the most critical issues to be addressed in Turkana[87]. A similar bottleneck analysis in Homa Bay highlighted increasing the availability of EmONC as an immediate priority. Improving health worker competencies, supervision and quality mechanisms and maternal and newborn health supplies, together with implementation of the Community Strategy and OBA, to improve both service quality and uptake, were identified as the most important issues[88].
[87] UNICEF, 2012. Evidence-based planning and budgeting for county health systems. Briefing: Turkana. October 2012.
[88] UNICEF, 2012. Evidence-based planning and budgeting for county health systems. Briefing: Homa Bay. October 2012.

Both Bungoma and Turkana are at risk of conflict. The main drivers of conflict in Bungoma are ethnic tensions and conflict related to land rights and distribution; in Turkana they include ethnic tensions, cattle raids, resource-based conflict, proximity to borders with Ethiopia, Sudan and Uganda, and a proliferation of weapons. Conflict has implications for the health of mothers and children, and for the management and delivery of health services, for example, on occasion resulting in the closure of facilities in Turkana.

DFID support has historically focused on Nyanza and Western provinces and the recent DFID-funded EHS programme was implemented in Nyanza. Targeting Homa Bay and Bungoma would build on previous DFID investment and achievements, in particular in Homa Bay, meet the criteria identified by the Division of Reproductive Health and align with the division of labour proposed by the joint donor mission[89]. As noted earlier, Turkana has received little donor support. It is assumed that there will be some health systems strengthening support provided by other partners, for example, USAID, in most other counties and that this will complement DFID training-centred support in these counties. The donor mapping exercise in 2011 showed that many districts of Kenya were receiving some degree of support for health systems as well as for community interventions[90].
[89] Lehmann L et al, 2011. Joint Mission: Harmonising support to reproductive health in Kenya.
[90] Lehmann L et al, 2011. Joint Mission: Harmonising support to reproductive health in Kenya.

(b) The health systems strengthening component will build on the successful elements and lessons learned from the EHS, which was implemented in selected districts in Nyanza, including Homa Bay, and incorporate funding to develop innovative approaches to tackling supply and demand challenges

EHS included skills development and capacity building of providers, improving the enabling environment and improving quality of care. Supply-side interventions included EmONC training for clinical officers and nurses, construction and renovation of maternity units and theatres, provision of essential equipment and supplies, supportive supervision and quality improvement, including use of MDR, strengthening district health team and facility management, HMIS and use of data for decision making, and improved referral and communication systems. Demand-side interventions included establishing Community Units, training community midwives, improving community awareness and use of verbal autopsy.

This option builds on the international evidence[91] and the EHS final evaluation finding that an approach that supports both improvements in skills and in the functioning of health systems, combining both supply and demand interventions, is most likely to achieve the greatest reductions in maternal and neonatal mortality. The EHS final evaluation recommended: strengthening collection and use of data; strengthening analysis and use of MDR and verbal autopsy to identify the causes of maternal and neonatal deaths and improve the quality of care. Training in M&E and MDR has been included in MiH2 and is therefore part of the training component in all three options considered.
[91] Hulton L et al, 2009. The evidence towards MGD5. Working paper commissioned by NORAD and DFID.

The EHS evaluation also identified elements of the programme that had been less effective, including use of motorcycle ambulances and mothers’ waiting homes to address referral challenges, and these have therefore not been included in proposed health systems strengthening. However, the Kenyan Government is interested in the potential role of mothers’ waiting homes in areas where women have to travel long distances on poor roads to receive skilled delivery care, so inclusion of this in health systems strengthening support may be considered in Turkana. In addition, the evaluation found that community midwives only represented 2.6% of deliveries with a skilled birth attendant; a Value for Money (VFM) assessment[92] also highlighted the high cost of training them. For this reason, this has also not been included. In sum, the health systems strengthening component of this intervention would support selective interventions from the EHS in order to achieve similar impact with lower unit costs.
[92] Denton E, 2011. DFID support to the delivery of Essential Health Services, Kenya: Value for Money.

Health systems strengthening for county health departments and MNH(Maternal Neonatal Health)-related service delivery would take a needs-based approach specific to the county, but is likely to include:

- Management – Support to newly-established CHMTs to manage health service delivery, focusing on establishing systems for planning, budgeting and financial management, human resources, health facilities, drugs and supplies, strengthening monitoring and use of data for decision making, and mechanisms for engagement and coordination with partners including donors and other development partners. Building this capacity will be critical to enable counties to meet the criteria for devolution of funding and functions and their obligations for delivery of health services.
- Accountability – Support to strengthen accountability, including through anti-corruption and health facility and community health committees, as accountability is key to achieving the devolution vision as well as to improving availability and quality of care.
- Community Strategy – Support for demand-side activities, focusing in particular on establishing Community Units, improving community awareness and referral strategies.
Additional support will be needed to address specific challenges in Turkana, including weak capacity and logistical and environmental challenges. This is expected to include:

- Infrastructure – Limited support to upgrade a number of facilities to be able to provide BEmONC and CEmONC, specifically minimal infrastructure upgrading, equipment and improvements in communication for four district and sub-district hospitals, development of a functional referral system and provision of ambulances to two of these facilities. Consideration will also be given to strengthening nomadic and mobile clinics.
- Human resources for health – Specific support for task shifting and strategies to improve recruitment and retention, given the severe shortage of health workers.
- Drugs and supplies – Specific support for procurement of essential drugs and supplies for maternal and newborn care to support provision of BEmONC and CEmONC, as well as to build facility capacity in supply chain management.
- Prevention of mother-to-child transmission of HIV – Support HIV-positive pregnant women through provision of information and HIV care and support and implementation of the Government of Kenya’s commitment to provide all HIV-positive pregnant women with life-long antiretroviral therapy in order to eliminate new paediatric HIV infections by 2015 and improve maternal, newborn and child survival. This intervention will not provide support for HIV-related services within maternal care in Bungoma and Homa Bay, as this is already well funded by USAID among others.
UNICEF and others have supported alternative approaches to delivering services to nomadic communities. For example, with support from the DANIDA-funded HSPS, the Government of Kenya has established nomadic clinics to improve the availability and accessibility of health services in areas not covered by static health facilities. Available evidence shows that these have increased the number of people accessing health care.

The emphasis will be on flexible support, one of the key success factors of the EHS, including to: (i) provide additional technical assistance to address unanticipated needs resulting from devolution; (ii) address critical gaps; and (iii) test use of new technologies and innovative approaches to delivering services to hard-to-reach and nomadic populations. In addition to targeted support to county health teams, this option also includes a specific budget allocation – of £4.5m per county over 5 years – to fund innovative and creative approaches to service delivery, improving service quality and increasing demand for maternal health services. This ‘innovation fund’, which would be managed by the service provider in Homa Bay and Bungoma and by UNICEF in Turkana, would fund non-state local partners, for example, NGOs, FBOs and the private sector, to pilot and implement initiatives that aim to deliver better results for maternal and newborn health. Lessons learned from health systems strengthening support and innovation funding in Homa Bay, Bungoma and Turkana will inform policy and practice more widely, including national Ministry of Health support to and approaches in other counties.

(c) This option would also include ongoing support for central level health systems strengthening

As noted earlier, DFID’s Kenya Health Programme is currently providing health systems strengthening support at national level through WHO. The programme ends in 2015 and it is envisaged that ongoing technical assistance will be required for the new central Ministry of Health, to ensure that policies and frameworks are in place to support counties and to take forward existing work on health financing. This would be managed through UNICEF.

Option 3: Scale-up of a training centred approach together with targeted support for health systems strengthening and demand-side financing in Homa Bay, Bungoma and Turkana counties

Option 3 would encompass Options 1 and 2 and, additionally, implement interventions to tackle barriers that hinder access to services. In particular efforts will focus on reducing financial barriers; currently it is anticipated that demand-side financing will be through implementation of output-based aid (OBA) in the three counties. Options for providing limited support to address transport barriers in Turkana specifically will also be explored.

Support for scale up of OBA is currently a priority for the Government of Kenya, but the policy context is evolving rapidly and flexibility will be needed to respond to developments including elimination of user fees and growing interest in results-based financing. Given the rapidly changing context and the new Kenyan Government’s commitment to provision of free maternal health care, the exact mechanism for implementation of demand-side financing will be determined during the inception phase. At present, it is anticipated that this is likely to take a similar approach to a successful OBA pilot project supported by GIZ and KfW, which aimed to improve access to reproductive health care for poor women through marketing and distribution of vouchers to enable women to access maternal care, family planning and gender-based violence services at highly subsidised rates. OBA is intended to improve the responsiveness and quality of services through: (i) accreditation of health facilities; (ii) competition among service providers; (iii) quality assurance monitoring; and (iv) increased freedom of choice and purchasing power for poor women. Option 3 would therefore potentially include:

- Marketing and sale of subsidised vouchers to women of reproductive age for maternal care and gender-based violence[93] services, with some flexibility to allow provision of free vouchers to the poorest women to cover user fees and transport. Based on the pilot, this would be expected to cover 25% of women in the lowest two wealth quintiles.
  [93] Family planning would not be included as this is addressed by other programmes including those funded by DFID and USAID.
- Accreditation of facilities with the capacity to provide quality maternal health services.
- Reimbursement of facilities based on agreed outputs with pre-defined quality.
- Quality assurance monitoring of services delivered by facilities.
Option 4: Do nothing

No DFID Kenya resources would be allocated for maternal and neonatal health in Kenya. Support would be limited to family planning, which will make a contribution to reducing maternal mortality, and national health systems strengthening under the Kenya Health Programme. The scope of health worker training would be limited to the three provinces covered by the second phase of the Making it Happen programme. Failure to provide support for national scale up of training, more intensive health systems strengthening support and additional demand-side activities would result in slower reduction in maternal and neonatal mortality, both nationally and in the three target counties. It would also represent a missed opportunity to support devolution and establishment of effective structures and systems to manage county health services as well as potentially reducing DFID’s scope to engage in policy dialogue with the new Ministry of Health.

Delivery options considered are discussed in the Management Case.
Theory of Change

Outputs:
Health workers in the public sector have the knowledge and skills to provide quality delivery and emergency obstetric and neonatal care

Counties have the capacity to deliver maternal and newborn health services

Increased community awareness and demand for maternal health care
Inputs:
DFID funds and staff resources
Outcome:
Increased access to and utilisation of quality maternal and newborn health services

Competency-based in-service EMONC training and follow up for doctors, clinical officers and nurses

Increased number of facilities able to provide all signal functions for BEmONC and CEmONC

Increased health worker knowledge, skills, confidence, motivation and team work
Training and scale up of QI and MDR

Increased caesarean section rate
Improved availability of care

Essential MNH supplies and equipment
Impact:
Reduced maternal and neonatal mortality in Kenya

Reduced obstetric case fatality rate

Infrastructure upgrading infrastructure

Improved quality of care

Increased county capacity to deliver maternal and newborn continuum of care
Reduced stillbirth rate

Strengthening referral systems including transport

Management support for county health structures in planning, financing, budgeting, HRH management, monitoring and use of data
Increased demand for care
Increased proportion of women delivering with a skilled birth attendant

Increased motivation

Increased number of women with complications managed by health facilities

Increased community awareness

Support for Community Units, community education and accountability structures

Increased referral rate

Improved performance of health facilities

Reduced demand-side financing barriers to care

Demand-side financing e.g. OBA

Innovation funding

(ii) Theory of Change and evidence / The results chain is shown in the logical framework and in the Theory of Change. The impact is reduced maternal and neonatal mortality in Kenya. The outcome is increased access to and utilisation of quality maternal and newborn health services. The outputs are: (i) health workers in the public sector in 5 provinces have the knowledge and skills to provide quality delivery and emergency obstetric and neonatal care; (ii) capacity developed to manage and deliver maternal and newborn health services in 3 counties; and (iii) increased community awareness and demand for maternal health care in 3 counties. / The Theory of Change reflects available evidence about what is needed for maximum impact on maternal and neonatal mortality in Kenya. It is also consistent with the concept of the ‘three delays’[94], which has been widely used to identify the causes of maternal death and appropriate interventions. The first two delays – delay in deciding to seek care and delay in reaching appropriate care – relate directly to the issue of access to care, encompassing factors including community knowledge, demand, distance, transport and financial barriers. The third delay – delay in receiving care at health facilities – relates to health service factors, including quality of care. All three delays need to be addressed to reduce maternal and neonatal mortality. The Theory of Change assumes: / Access to skilled birth attendance and management of obstetric complications is central to saving lives. / Competency-based training will improve the knowledge and skills of health workers who provide routine and emergency maternal and newborn care, and training doctors, clinical officers and nurses together will promote team work and facilitate task sharing, reducing dependence on doctors and delays in receiving life-saving care. / Trained staff will mainly stay in the same areas, as the national scale up of training will mean that their skills will be less marketable, and health workers may be less mobile when they are recruited and hired by counties. / Increased health worker competencies will improve both the availability of skilled birth attendance, including emergency maternal and newborn care, and the quality of care. / Improving the quality of care is expected to improve the outcomes of deliveries that are assisted by a skilled birth attendant, reducing maternal and neonatal deaths. / Strengthened supervision, mentoring and follow-up to ensure that new knowledge and skills are put into practice, together with training and support for implementation of wider quality improvement interventions, including MDR, are also expected to improve quality of care and maternal and newborn health outcomes. / Training needs to be complemented by wider health systems strengthening to improve the coverage and quality of maternal and newborn health services in Kenya, in order to achieve greater reductions in mortality. At a minimum, delivery of quality maternal health care depends on the availability of essential drugs, commodities and equipment and basic infrastructure. / In the context of devolution, support will be required for newly-established county structures to manage and deliver services and, in particular, to assume devolved responsibility for health planning and budgeting, health financing, human resources for health and monitoring. / Improved availability and quality of care can increase demand for maternal health services. However, supply-side interventions alone will not be sufficient to increase utilisation of services in Kenya, given current low rates of facility-based delivery and skilled birth attendance. Additional intervention is therefore required to increase awareness and demand, and to address barriers to access. The assumption is that support for key elements of the Community Strategy, including community education and mobilisation, Community Units and strengthening links between communities and facilities, including referral systems, together with a voucher scheme targeting the poorest women, will increase uptake of services. / Innovative approaches to improving service coverage and quality and increasing demand for maternal health care services will be identified and there are non-state partners with the capacity and interest to apply for innovation funding. / Demand-side financing and effective accountability structures will improve demand and the performance of health facilities and the quality of care, and thereby improve health outcomes. / The following summarises the evidence to demonstrate that training, health systems strengthening and demand side financing result in improved maternal and newborn health outcomes. / International evidence / Only trained health workers can deliver the high-impact interventions that can reduce maternal and neonatal mortality. Although more significant and sustainable reductions in maternal and neonatal mortality depend on health system strengthening, available evidence suggests that implementing a training-centred approach at scale can accelerate mortality reduction, yielding ‘quick wins’ while other aspects of health system strengthening that require more time and resources are addressed. / International evidence demonstrates the potential impact of skilled health professionals who are trained in simple life-saving skills[95]. Research indicates that 13%-33% of maternal deaths could be averted by the presence of a skilled birth attendant[96]. For example, the availability and use of skilled birth attendants was a critical factor in reducing maternal mortality in countries such as Sri Lanka[97] and Malaysia[98]. The significant decline in maternal mortality in Bangladesh is attributed largely to improved access to emergency obstetric care and increased provision of caesarean section[99]. In India, upgrading of training centres, followed by emergency obstetric care training of general medical officers resulted in an increase from two to ten in the number of health facilities providing all BEmOC signal functions[100]. In Ethiopia, an initiative focused on emergency obstetric care capacity building for various facility-based providers observed a reduction in the obstetric Case Fatality Rate (CFR) from 7.2% to 4.6% over a 3-year period, an almost six-fold increase in the caesarean section rate, and a 41% increase in delivery care seeking[101]. / Similarly, global modelling indicates that skilled delivery care can result in a 20-30% reduction in all-cause neonatal mortality, emergency obstetric care can result in a 10-15% reduction and emergency neonatal care can result in a 15-50% reduction[102] in neonatal mortality. Other analysis suggests that skilled care during delivery can avert an estimated 30-45% of newborn deaths and 25-62% of intra-partum stillbirths[103] and that improved management of newborns could reduce deaths associated with low birth weight and sepsis by over 60%[104]. A recent study found that a Helping Babies Breathe[105] training programme in eight hospitals in Tanzania was associated with a sustained 47% reduction in early neonatal mortality within 24 hours and a 24% reduction in stillbirths after two years[106]. / Scaling up the training of health professionals is recognised as only one component of an effective strategy to reduce maternal and neonatal mortality. While training can have an impact on maternal and neonatal mortality, particularly in the short-term, training alone will not be enough to achieve optimal or sustainable reductions in mortality. Training-centered approaches in Africa and India have involved training for health workers together with provision of basic equipment, essential supplies and drugs, and strengthening information systems to identify and address quality of care gaps[107]. International evidence shows that a training-centered approach coupled with minor health system improvements, can be a cost-effective option to reduce maternal and neonatal mortality[108]. Gains made in countries such as Bolivia, Chile, Egypt and Jamaica are attributed to scale up in coverage of skilled birth attendants together with provision of adequate facilities and equipment[109]. / MiH1 also demonstrated the effectiveness of training combined with targeted health systems support. Across the five MiH countries, the proportion of health facilities with increased signal functions ranged from 65% to 100%, the number of women receiving emergency obstetric care increased by 50%, and there was a 50% reduction in the obstetric CFR and a mean reduction of 15% in the stillbirth rate[110]. The MiH1 final appraisal concluded that training, provision of equipment and facility-based supportive supervision had improved knowledge, skills, clinical practice and team work, translating into an increase in the number of signal functions provided, improved care of uncomplicated births and obstetric emergencies as well as reduced delays in management of emergencies. MDR is associated with quality of care improvements, increased client satisfaction and a reduction in maternal deaths[111]. / However, no single intervention will substantially reduce maternal and neonatal mortality[112] and it is universally accepted that reducing maternal and neonatal mortality requires a functioning health system that provides a continuum of care[113]. DFID’s Framework for Results 2010 also recognises that strong health systems are needed to deliver sustainable improvements in maternal and newborn health. / Training and health systems strengthening can deliver improvements in maternal and neonatal health, but only for those women who use health services. As discussed in the Strategic Case, less than half of women in Kenya deliver in a health facility and with the assistance of a skilled birth attendant. To maximise mortality reduction and improvements in health outcomes, supply-side intervention needs to be complemented with demand-side intervention, including community strategies to improve knowledge and address social and cultural barriers, as well as action to reduce transport and cost barriers. Multi-country analyses on neonatal mortality reduction indicate that only a combination of expanded coverage of quality clinical care and community strategies will bring about reductions in neonatal mortality that exceed 50%[114]. / Significant progress in reducing maternal and neonatal mortality will only be made in Kenya if there is a substantial increase in the proportion of women who are delivered in a facility by a health professional. The new Government of Kenya’s commitment to eliminating fees for maternal health care is intended to support this[115]. However, it is likely to be some time before this is implemented across the country and, in addition, women often pay additional charges. Support will therefore continue to be required to address financial barriers to access for the poorest women in the short- to medium-term. There is a range of approaches to benefitting the poor with health services, many of which involve the removal of financial barriers[116]. Demand-side financing schemes are increasingly being used to promote access, including voucher schemes, which are an example of OBA. International evidence shows that, although the effectiveness and cost-effectiveness of using vouchers to reduce inequality is not strong, health voucher programmes have been successful in increasing utilisation of health goods and services, targeting specific populations and improving quality of services[117]. The strength of evidence and findings are similar for vouchers for reproductive health services[118]. / Kenya-specific evidence / The final evaluation of the DFID Kenya EHS programme in Nyanza, which included EmONC training for clinical officers and nurses, concluded that this training had resulted in improvements in the clinical skills and confidence of providers to detect, manage and refer obstetric and neonatal complications[119]. There is also Kenya-specific evidence on the effectiveness of training as a means of improving case management of specific obstetric complications. Recent training was shown to be significantly and positively associated with the ability to provide quality care for postpartum haemorrhage and unsafe abortion, and positively associated with the ability to provide quality care for retained placenta[120]. / Analysis suggests that in Kenya an estimated 19% of maternal deaths could be avoided each year if all women who deliver in a health facility had access to comprehensive emergency obstetric care[121]. This is reinforced by preliminary MiH1 data, which suggested that during the previous 12 months the number of women receiving CEmONC increased by 49% and that there was a 30% reduction in the obstetric CFR among women receiving emergency obstetric care and a 25% reduction in the stillbirth rate[122]. The same analysis calculated that 80% of maternal, newborn and child deaths in Kenya could be avoided if coverage of essential services was scaled up to 90%[123]. A recent joint donor mission also concluded that there would need to be substantial and sustainable improvements in service delivery and coverage with high-impact interventions to achieve significant progress in reducing maternal and neonatal mortality[124]. / The EHS programme showed that demonstrable improvements in maternal and neonatal health outcomes can be achieved in Kenya. These included: an increase in births delivered by a skilled birth attendant by an average of 3.7% a year (the national average rose by 0.4% annually) to 27.7-44.6% (average 35%); an increase in the caesarean section rate from the average at baseline of 0.7% to 2.5% in five of the seven targeted districts; improvements in capacity to perform signal functions in all 20 facilities covered; and fewer women with postpartum haemorrhage, retained placenta and incomplete abortion referred to hospitals because staff in BEmONC facilities had the confidence, capacity and means to treat them. Other achievements included: development and institutionalisation of annual planning processes; routine use of data for monitoring and decision making; staff ownership and pride in visible achievements such as the decrease in maternal deaths; improvements in client satisfaction; and improvements in the referral system resulting from use of a standardised tool for referring obstetric emergencies and provision of mobile phones to health facilities. / Lessons learned included: the importance of inter-personal skills as well as clinical competency – positive client-provider interaction can improve client satisfaction and demand; the need for creative service delivery modalities to facilitate access to CEmONC by the poorest women; the need for training follow up; and the value of MDR in institutionalising quality of care and of verbal autopsy as an opportunity to increase community awareness of maternal death. Challenges included: the continuing effect of women seeking care from traditional birth attendants and the negative impact of poor reception at health facilities; poverty, lack of affordable transport and long distances to facilities were identified as more intractable problems. / Overall, the final evaluation found that the combination of EmONC training with simultaneous improvements in the enabling environment through strengthening of provincial, district, facility and community health management teams, provision of equipment and supplies and strengthening supportive supervision and Quality Improvement, had resulted in notable improvements in quality of care and outcomes. Support for the Community Strategy resulted in women and their families being better informed and aware of the benefits of delivering in facilities. Improvements in quality of care and in community awareness resulted in increased uptake of skilled birth attendance in facilities. The EHS Project Completion Review (PCR) concluded that the approach of pursuing simultaneous supply and demand side strengthening had demonstrable impact and recommended that it be extended. / Experience of OBA or voucher schemes in Kenya suggests that this approach can increase uptake of maternal care, by removing financial barriers and empowering women to use health services. The greatest uptake so far using vouchers has been for safe deliveries[125]. OBA schemes have been piloted in Kenya by UNICEF and by GIZ and KfW[126]. UNICEF reports that its OBA scheme for pregnant women has increased delivery in health facilities among poor women in northern Kenya. The Phase II evaluation of the GIZ-KfW OBA pilot in December 2012 also concluded that the scheme had increased uptake of maternal care services. The GIZ and KfW pilot was implemented in two phases in Kisumu, Nairobi, Kifili, Kitui and Kiambu. Cumulatively over the two phases, an estimated 234,886 women of reproductive age, 24% of the target population, was reached. Data for Phase II showed a significant increase in the number of facility-based deliveries, to 74% and in the number of women treated for complications, which increased from 512 in 2008/9 to 7,874 in 2010/11. / Evaluation of the pilot found that: the majority of vouchers were used by poor clients; the majority of voucher recipients used the vouchers and were able to overcome transport and cultural barriers; more poor voucher clients compared to poor non-voucher clients delivered at a health facility; and the gap between poor and non-poor facility deliveries was narrower among voucher clients. In addition, accredited service providers improved their management skills and increased investment in service capacity, increasing staff morale and improving service delivery. Positive impacts reported by women included reduced waiting times at facilities, cleaner facilities, better availability of medicines and more positive health worker attitudes. Factors contributing to success included: government commitment and leadership; empowerment of women through choice of provider; provider competition; emphasis on quality through accreditation, accountability of providers and reward mechanisms for good performance and appropriate sanctions for poor performance; independent quality control; and separation of responsibilities to ensure transparency and minimise risk of fraud. / Based on available evidence, of the feasible options only Option 3 would address all the elements of the Theory of Change and maximise impact, and is therefore the preferred option. Option 3 includes a combination of interventions that will address supply and demand challenges, improve quality of service delivery, and generate immediate results as well as longer term sustainable change. The core HSS package in Option 2 will be at least as effective in delivering the impact seen in earlier DFID interventions. The addition of an innovation fund in Option 2 will help tackle difficult supply-side constraints to help reach geographical areas and marginalised groups in a way that has not been done in Kenya before. Options 1 or 2 alone would address specific challenges but would have less overall impact, particularly in the three target counties due to the significance of demand-side factors in limiting uptake of maternal health services by the poorest. Option 3 addresses demand constraints directly. Given the challenges of devolution and the rapidly changing context, the added interventions in Options 2 and 3 offer opportunities to deepen engagement and test a range of different interventions in the three counties that could bring additional benefits to other areas of our work.
B. Assessing the strength of the evidence base for each feasible option / The following rates the quality of evidence for each option as either Strong, Medium or Limited. / Option Evidence rating Comment / 1 High Number of studies, and evidence from Making Happen Phase 1, that competency-based training can increase health worker knowledge and skills and contribute to improvements in maternal and neonatal health outcomes. However, limited evidence about the extent to which the benefits of training are sustained. / 2 Medium As 1 for training. International and Kenya-specific evidence suggesting strengthening health systems is fundamental to significant and sustainable reductions in mortality and can lead to demonstrable improvements. However, limited evidence about which elements of health system strengthening have the most impact and difficult to establish attribution to specific interventions. / 3 Medium/Low As 1 for training and 2 for health systems strengthening. Growing evidence base for effectiveness of OBA and evidence from pilot projects in Kenya of impact on service utilisation by poor women. Again, limited evidence about sustainability of changes in client and provider behaviour. Also limited evidence for impact in practice of combination of training, health systems strengthening and demand-side financing. / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Kenya is vulnerable to the impact of climate change, including more frequent and severe droughts and floods. Higher temperatures and a succession of years of below average rainfall have resulted in prolonged drought conditions, especially in northern Kenya. The 2011 drought was one of the worst for many years[127].This has affected livelihoods and food security and exacerbated poverty, particularly for women and children. Accelerated land degradation means only a small proportion of rainfall is accumulated and stored for productive use. The health sector is impacted by the direct effects of climate change, including the effects on health of changes in disease vector development, water availability and quality, food security and nutrition. Wider environmental factors that impact health and are outside the direct control of health services, such as improved water supply and sanitation, will require action across sectors; opportunities to leverage such action will be identified, including working with other sectors at county government level and with other development partners. / Clear policies and strategies are needed to deal with the impacts of climate change on human health and health systems. Option 1 provides an opportunity to do this through the health workforce and Options 2 and 3 to do this through the health workforce and a broader health systems approach, at national level and in the targeted counties. The latter two options would enable climate change issues to be addressed both through increasing the knowledge and skills of the health workforce and integration into county health planning and budgeting and the remit of Health Facility Management Committees (HFMC). In addition, there are opportunities through support for infrastructure upgrading including installation of solar panels and other green energy solutions, and water conservation measures in health facilities. This intervention will seek fund for hybrid mini-grids for health facilities in Turkana, in order to improve service delivery, through the Climate Change Fund. / For Options 2 and 3, environmental risks are associated with (a) procurement of drugs and commodities, (b) infection control and disposal of medical waste at facility level, (c) logistics including use of transport and (d) infrastructure. For Option 1, (c) is most relevant. Measures to mitigate these risks will include ensuring that implementing partners employ sound environmental management procedures in their procurement guidelines and select procurement options with a minimal carbon footprint and health facilities implement procedures for safe disposal of medical waste and infection control. Measures to reduce environmental risk, and relevant elements of disaster preparedness, for example, factoring these into location and design of infrastructure, will be integrated into county health sector and facility plans. Related capacity development for county health teams, facility committees and the health workforce would be implemented. Key issues include: / Disposal of waste – The expected increase in service provision is likely to increase the amount of waste, mostly sharps, but also potentially infectious bodily fluids. Over 90% of level 2 and 3 facilities have sharps boxes and 94% use a composite pit[128], and 64% of facilities have adequate final disposal system for infectious waste[129]. Health system strengthening within this intervention would ensure that all facilities in the targeted counties dispose of sharps and other waste correctly and guidelines are in place and followed; this will also be integrated into supervision support. / Infrastructure – 87% of level 2 and 3 facilities have a water source and more than 90% have a refrigerator. Limited infrastructure support will be provided as required, in particular in Turkana, for renovation of facilities, including installation of solar panels where electricity supply is inadequate and of water conservation measures. The costs and sources of materials and opportunities to reduce energy and fuel consumption will also be considered. / Logistics – Travel associated with training, increased supervision, provision of mobile services and programme management is likely to result in a modest increase in carbon emissions. The opportunity to reduce the need for travel through use of new technologies will be explored. / Although the intervention is expected to have limited impact on climate change and environment, implementing partners will be required to undertake further analysis, identify opportunities to minimise environmental impact and reduce carbon emission, and monitor and report on mitigation actions. The options are rated as A: high potential risk/opportunity; B: medium/manageable potential risk/opportunity; C: low/no risk/opportunity; D core contribution to multilateral organisation. The preferred option, Option 3, is rated C in terms of climate change and environment risks and B in terms of climate change and environment opportunities. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C C / 2 B B / 3 B B
C. What are the costs and benefits of each feasible option? / This section sets out the costs and benefits of each option and shows the cost effectiveness of options in terms of cost per DALY and per life saved. (In the following sections the year 2013 refers to DFID financial year 2013/14 and 2017 to financial year 2017/18.) / C1. Costs of each feasible option / Option 1: National scale up of a training-centred approach / As described above, the approach is to expand the MiH2 programme from three provinces of Kenya to cover the rest of the country. / Table 2 below is derived from detailed costing for MiH2. Additional costs include follow-up mentoring which is not part of MiH2. The main elements within this budget are for in-service training and follow-up mentoring. The main cost drivers of these elements are travel, subsistence and per diem attendance allowances for health sector staff. Per diems for doctors and nurses are over half the cost of these budget lines. These rates are set by the Government of Kenya in common with practice in other countries. / Table 2: Costs of training and follow-up mentoring (£) / Option 2: Scale-up of a training centred approach together with targeted support for health systems strengthening in Homa Bay, Bungoma and Turkana counties / Option 2 involves the additional costs of health systems strengthening in three counties. These costs have been projected based on data and views from: the EHS; from UNICEF (specifically for Turkana); and other health sector specialists including Government of Kenya officials and consultants. / Table 3 summarises projected programme and administration costs for Homa Bay and Bungoma, for Turkana and for all three counties. Showing the projected costs in this way also shows the budget that will be managed through a service provider for Homa Bay and Bungoma and UNICEF for Turkana. There are three subcomponents to the additional work under Option 2. / HSS: an HSS package of interventions broadly equivalent to the package of interventions under EHS / HSS Innovation Fund: additional interventions to managed under a competitive fund to reach otherwise unmet needs in terms of geography, poverty of beneficiaries / Central HSS interventions: improvements to policy, planning and budgeting. / Table 3: Costs of health system strengthening: Homa Bay and Bungoma; Turkana; and three counties combined (£) / Homa Bay and Bungoma together have a population of roughly 2.8 million; Turkana has a population of about 0.9 million. Despite this difference, the total costs for Homa Bay and Bungoma are only about 40% higher. This is because the cost of operating in Turkana is far higher due to size, low population density and other factors; the estimated per capita cost of delivering health systems strengthening in Turkana is approximately 2.2 times higher than in non-ASAL counties. The combined cost of investing in all three counties is projected to be around £31.6m over 5 years to secure benefits in line with those under EHS (see Benefits section below). An additional allocation has been made of £4.5m per county over 5 years for an ‘innovation fund’, to support piloting and implementing innovative HSS-related initiatives that improve the quality of service delivery and tackle demand-side barriers. Including £1.4m for support to central ministry policy, planning, budgeting and other central HSS functions, the total for health systems strengthening comes to £49.5m. / Administration costs for Homa Bay and Bungoma are estimated at 18% of total costs (administration and programme costs combined), which was the actual overhead cost of EHS using a broad definition that includes some inputs that are significantly contributing to capacity building. 7% overhead costs for Turkana and Homa bay is the administration fee charged by UNICEF. / Health systems strengthening work plans for each county will be developed during inception and the balance of activities will depend on needs of systems and facilities. The breakdown of costs above, however, will approximate to those under EHS, though with some significant differences. For EHS, the main types of expenditure were (approximate shares in brackets): technical assistance, long term (24%) and short term (16%); activity support (35%); procurement (5%); and infrastructure (19%). The Government of Kenya is likely to prioritise infrastructure less highly than under EHS, based on discussions to date. The costing take this into account. Under EHS, support focused on system strengthening support to central ministries (26%), sub-national government (10%) services (30%), demand creation (14%) and programme management (18%). Under this intervention, devolved institutions will benefit from a relatively higher level of effort and support to central government will be significantly lower; £1.4m over 3 years has been budgeted separately to continue national level technical assistance for HSS after the Kenya Health Programme ends in 2015. / These financial costs are best estimates based on experience of the EHS programme and expert judgements from the appraisal team. The cost projections are, nonetheless, a source of financial risk with similar upside and downside risks which will be managed proactively throughout implementation. £13.5 million (£4.5 million in each county) has been budgeted for the Innovation Fund (plus £2.9 million for administration costs; 18% of total costs). / Option 3: Scale-up of a training centred approach together with targeted support for health systems strengthening and output-based aid in Homa Bay, Bungoma and Turkana counties / The objective of the demand-side financing component is to improve access to maternal health services for 25% of poor women of reproductive age (WRA) over the duration of the intervention. Table 4 below shows the coverage target for this component. The population estimate is a projection for 2015 and 42% of women are estimated to be of reproductive age. Based on province-specific poverty rates and the 25% target, the total is around 130,000 poor women. This number is very approximately one quarter of the number of births that poor women are likely to have in the 4 years from 2014/15 in the three counties. / Table 4: Basis for demand-side financing coverage target / Costs and other key parameters have been taken from evaluations of the GIZ OBA pilot, an example of the type of intervention that could be included in this component. Table 5 shows the mix of uses of vouchers purchased for safe motherhood between 2009 and 2011 under this pilot. The first three rows (i.e. reimbursements for delivery-related costs) sum to 100%; ANC vouchers are treated as additional to the target caseload. The rates used for reimbursements to facilities, based on the GIZ pilot, are KSh1,000 for antenatal care, KSh4,000 for normal delivery and KSh 20,000 for a caesarean. Complications which were reimbursed on a cost basis have been calculated at about KSh11,000. / Table 5: Mix of voucher uses for safe motherhood in the GIZ OBA pilot (final column, £) / Table 6 brings together these parameters to give an indicative costing of voucher payments in the OBA component. (The underlying number of vouchers is given in the benefits section below.) / Table 6: Indicative value of voucher reimbursements (£) / Table 7 below projects total costs for the demand-side financing component. Non-voucher costs started at 29% of total costs in year 1 of the GIZ pilot, declined to 22% by the year 3 and are projected at just below 20% of voucher costs for the next period. The main administrative costs are the voucher management agency and project management unit. DFID’s costs have been profiled to fall from 25% in 2014/15 to 16% in 2017/18. Such programmes targeted at the poorest groups and requiring significant behaviour change amongst beneficiaries can appear costly. Ultimately these programmes are likely to be incorporated within the GoK (Government of Kenya) budget. In this programme we expect to limit the non-voucher costs through procurement and implementation phases with a view to GoK adopting key features of the programme. The declining profile of costs in this analysis provides a reference point for subsequent reviews in gauging VFM during implementation. / Table 7: Total cost for demand-side financing component (£) / Overall programme costs / Table 8 below summarises the overall programme cost including monitoring, evaluation and contingency. / Table 8: Total programme costs / C2. Benefits of each feasible option / Benefits accrue to poor women of reproductive age through increased use of maternal health care services. The value for money section below shows a range of metrics that need to be monitored to test how these services can be provided and accessed in acceptable and affordable cost ranges. This section attempts to quantify the impact of increased use of maternal health services. The following section – comparing costs and benefits of the programme – considers whether the expected impact is likely to come at unit costs in accepted ranges for health investments. / Health impact for Options 1 and 2 are measured primarily in terms of numbers of lives saved and the resultant numbers of additional life years saved. These measures and their calculation, especially in developing countries with significant data limitations, are subject to considerable uncertainty and need to be interpreted cautiously. For Option 3, the benefits of the additional demand-side financing component are demonstrated in terms of equity; while lives are saved through the demand-side financing component, unpacking the proportion of beneficiaries who are additional to those that may have benefited from improved training and health system strengthening in the three counties is difficult at this stage (although monitoring can attempt to highlight the proportion of beneficiaries of demand-side financing whose access to improved services can be considered additional). / Two models have been used to project lives saved. The first is the excel-based model used by the appraisal team, which combines several sources of Kenya-specific evidence and parameters to project impact. The second is the Lives Saved Tool (LiST). LiST assumptions are based on wide-ranging international evidence. Both models require inputting changes in numbers of births attended by skilled birth attendants – this important assumption is the same for both models. The first model takes LiSTs values for facility quality (i.e. the share that provide ‘routine’, basic and ‘comprehensive’ emergency obstetric care), but the assumptions relating a given change in births attended by a skilled birth attendant in facilities to reductions in lives saved are different. This and other factors mean that the results are very different – LiST generally projects lower impact, whereas the appraisal model projects higher impact. Both projections are presented as they have different strengths. The conclusion is that the programme would be expected to have considerable impact in terms of lives saved, but the impact is subject to considerable uncertainty. / The calculations of DALYs are approximate; they are based on Disease Control Priorities Project (DCP) estimates of DALYs and DFID projections of additional life years based on an average life expectancy of 59 years[130]. This means that they conflate DALYs (which take into account quality of extended life) and life years saved. The inclusion of some elements of DALY measures that are only additional life years understates the DALY calculations; the impact of reduced morbidity as opposed to reduced mortality is not included. / Benefits are projected to 2022 but are also reported to the end of the programme. Including benefits up to 2022 allows some of the legacy impact of the investment to be captured. The results are sensitive to changes in how this calculation is done. The impact is tapered after the end of the programme in order to model factors such as reduced effectiveness of training delivered over time and to reflect only benefits attributable to DFID support. The focus of this analysis is narrow in that it focuses on the direct impact of DFID support. However, the wider objective is to influence the shape of health service delivery and financing. / Option 1: National scale up of a training-centred approach / In the appraisal model, MiH evidence is used to project the impact of training health workers. Training benefits are modelled as an improvement (decrease) in the Case Fatality Rate (CFR) for births attended by newly skilled birth attendants. (The term SBA is used in this section for a ‘birth attended by a skilled birth attendant’ and SBA for ‘skilled birth attendants’ themselves.) A small increase in numbers of SBA is also included (0.2% per year) reflecting increased demand SBA due to improved quality. The total number of SBA is projected and the share of those births that will be attended by DFID-trained staff is estimated at two thirds nationally. The CFR for mothers reduces by 25% where newly trained staff are expected to be present – half the impact detected in an MiH impact study. / However, the MiH impact study looked only at maternal mortality. Neonatal lives saved tend to be of a larger order of magnitude than maternal lives saved, as predicted by LiST. In the absence of clear data, the same ratio of neonatal to maternal lives saved has been projected as for option 2 (discussed below). This ratio of 5:1 compares with a ratio of about 10:1 in LiST projections i.e. LiST projects 10 times as many neonatal lives saved as maternal lives saved. Table 9 summarises the projected number of maternal and neonatal deaths averted based on MiH impact and LiST. The benefits are phased in and phased out using assumptions about roll out of training and a reduction in the effectiveness of training in the years following training. / Table 9: Projected number of maternal and neonatal deaths averted / Option 2: Scale-up of a training centred approach together with targeted support for health systems strengthening in Homa Bay, Bungoma and Turkana counties / In summary, benefits for the three components of health system strengthening are estimated as follows: / HSS: The health systems strengthening package of interventions in each of the three counties is projected to have the same impact on SBA rates as EHS. / HSS Innovation Fund: the impact is anticipated to be additional to that achieved under EHS. These additional benefits are projected to be achieved at the same rate of cost effectiveness as under EHS. Effectively, there are constant returns to investment anticipated. / Central HSS interventions: These interventions will have a national impact, but the Theory of Change from improving capabilities in areas such as policy, planning and budgeting to saving lives is clearly longer than interventions under A which include more direct improvements to service delivery. Benefits from Central HSS interventions are also included at the same rate as EHS. / The majority of this section describes the basis for modelling benefits to the HSS package broadly equivalent to the EHS programme. Benefits from health system strengthening are based on two main parameters: / A. HSS package of interventions / Differences in SBA rates due to intervention. Both models project an increase in SBA rates due to the project of 3.7% per year growth. This means that in the three counties, SBA growth is 3.7% higher than in other counties. The underlying trend in SBA growth in Kenya is assumed to be 0.4% based on DHS data. The EHS impact assessment found that SBA growth was 4.1% in EHS districts. Numbers of SBA can then be projected based on information about county population size and growth and crude birth rates. Table 10 shows the number of SBA projected using the appraisal model. The projections continue for 5 years after the programme has ended as it will continue to have significant benefits after activities have finished. / Table 10: Number of births attended by skilled birth attendants / Health system strengthening then improves the quality of the environment in which births in facilities take place. It improves systems (staff, supplies, facilities etc) and emergency response from ‘routine maternal care’ to ‘basic’ to ‘basic or comprehensive’ quality maternal care. This shift is common to both models although it is greater in the appraisal model. / Table 11 shows the assumed changes in the proportion of SBA births that take place in an environment of routine or basic/comprehensive maternal care over the life of the programme. This parameter is the same for the appraisal and LiST models. This parameter says that in the first year, 44% of SBA take place in an environment with ‘routine maternal care’ and 56% with ‘basic or comprehensive care’. By the fifth year, the proportions improve to 20% routine and 80% basic or comprehensive care. This change in quality of the environment in which births take place is attributed to the intervention. The analysis treats separately the benefits from additional SBAs due to the project from improvements in facility quality for births that would have been attended by an SBA without the project (see Economic Annex for explanation). / Table 11: Shift in quality of facilities in which additional births take place due to health systems strengthening / This is modelling by drawing on ‘states’ set out in the DCP paper[131]. ‘RMC’ is equated with state 1 ‘routine maternal care’ (RMC) which is defined in the paper. Similar environments where ‘EmOC’ services are available are equated with state 5a ‘improved overall quality of maternal care and coverage with nutritional supplements’. Health outcomes attributable to health system strengthening improve as a population moves from 1 'routine maternal care' to 5a 'improved overall quality of maternal care’. DCP estimates the DALY health benefits for maternal and neonatal health impact of moving between these states. Table 12 summarises the total deaths and DALYs averted in the appraisal model based on DCP parameters per million people reached. / Table 12: Total deaths and DALYs averted per million due to better quality maternal care / Table 13 combines the above data on SBA, change in service quality and impact of improvements and shows projected maternal and neonatal deaths averted and life years saved by the programme using the appraisal model. Around 200 maternal deaths are projected to be averted. By 2022 the lagged impact more than doubles the impact to 628 maternal deaths averted. Impact on neonatal deaths is about five times higher. / Table 13: Projected maternal and neonatal deaths averted and DALYs saved / Table 14A summarises the numbers of lives saved for both the appraisal and LiST models for each county and combined under the health system strengthening component. Totals are shown for the programme period and for 2013-2022. / Table 14A: Projected lives saved / Other combinations of counties were considered in the early stages of appraisal in order to gauge which counties would deliver the best results and greatest cost effectiveness. The Economic Appraisal summarises this analysis concluding that the highest results can be achieved by concentrating on densely populated counties with low maternal health indicators. Reaching the poorest in more sparsely populated counties comes at a higher unit cost. The discussion of feasible options concluded that a design that did not include a very poor county with a difficult operating environment would not only miss the opportunity to reach the most vulnerable women directly but also to shape Government of Kenya and other partners’ approaches in the poorest counties. / B. HSS Innovation Fund / The innovation fund will go beyond the level of effort and type of activities that were part of EHS and on which the benefits for HSS component A were based. There is less of an evidence base still for forecasting benefits to the innovation fund over and above those that have been attributed to A. In this appraisal, the benefits in terms of improved service delivery and ultimately lives saved are assumed to continue to accrue at the same rate of cost effectiveness to DFID as under component A. This is a simplistic but transparent assumption; the important issue is to monitor the combined and separately attributable impact of these two aid instruments in improving health care and their relative cost effectiveness. The innovation fund will seek to avoid areas where there are likely to be diminishing returns from investing in similar interventions and locations. Given the scale, geographical spread and variety of need across each of these three counties, the scope for a responsive fund to innovate and identify additional needs and tailored responses is intuitively high. Furthermore, such a fund provides further opportunity for demonstrating effective and cost-effective approaches that are applicable in the rest of Kenya. / There is an underlying trade-off in this judgement between depth of engagement in the three counties and including one or more additional counties with HSS activities. The decision to opt for greater depth reflects the expectation of greater future benefit from trialling different delivery mechanisms in the focus counties. Based on this assumption, Table 14B shows the projected lives saved from both component A and B. / Table 14B: Combined lives saved from Components A and B / C. Central HSS policy, planning and budgeting / Support to central functions will also contribute to service delivery but the theory of change and results chain relating to these enabling interventions to lives saved is longer and more complex. These interventions will inter alia improve the allocative efficiency of resources in the health sector (e.g. better intra-sectoral allocations towards higher priority areas, more predictable financing, improvements to human resource management) as well as increase the level of resources drawn to the health sector by central and county-level budget processes (e.g. through better participation by central Ministry of Health and county health departments in budget processes). However, in this appraisal these benefits have not been added in the same way as the innovation fund. / Option 3: Scale-up of a training centred approach together with targeted support for health systems strengthening and demand-side financing interventions in Homa Bay, Bungoma and Turkana counties / The costs and benefits of this component are based on an output-based aid intervention. The benefits of vouchers are expressed in terms of access to maternal health care for poor women of reproductive age. Table 15 below shows the numbers of reimbursements projected in order to meet the target caseload of 25% of poor women of reproductive age in the three counties. The net impact of the demand-side financing component will depend on targeting effectiveness – whether beneficiaries meet intended poverty criteria – and, specifically, the extent to which vouchers result in a net addition in access to maternal health care above the increase due to health systems strengthening. / An evaluation of the GIZ voucher programme found a reduction in socio-economic inequities in service utilisation among voucher clients: the gap between poor and non-poor women regarding the use of long-term family planning methods, facility-based delivery and skilled delivery care was narrower among voucher compared to non-voucher clients, based on concentration index that measures the degree of socio-economic inequities in health. Design and monitoring of the programme will need to gauge both the effectiveness of poverty targeting and the extent to which service utilisation is additional. / Table 15: Indicative numbers of reimbursements for births and antenatal care / C3. Comparing costs and benefits of feasible options / This section presents the cost per benefit for training and health systems strengthening components and cost efficiency metrics for the demand-side financing component. The benchmark for cost per DALY is Gross Domestic Product (GDP) per capita for interventions to be cost effective and three times GDP per capita for interventions to be highly cost effective. These benchmarks have been used widely since the Commission of Macroeconomics and Health Report in 2000 including by CHOICE. GDP per capita in Kenya was US$808 in 2011 (World Development Indicators). Reference points of US$800 and US$2,400 or approximately £500 and £1,500 represent very cost effective and cost effective health interventions. / DALY unit cost calculations have not been undertaken for LiST which does not produce DALY estimates. Reflecting the variation in results projected through the appraisal model and LiST there is a significant difference in range in project cost-effectiveness metrics. / Option 1: National scale up of a training-centred approach / Table 16 shows cost-effectiveness metrics for the training component. The unit cost per DALY for training suggests very high cost effectiveness. / Table 16: Training cost per life saved and per DALY (£) / Option 2: Training plus health systems strengthening in three counties / Table 17 shows projected costs per DALY separately for Homa Bay and Bungoma and for Turkana. As discussed, the unit costs of health improvements in Turkana are higher due to higher per capita costs and the population size. The Homa Bay and Bungoma unit cost is closer to that for training. When looking only at narrow per capita costs, Turkana acts as a drag on programme cost effectiveness. But the poverty rate and poverty severity are much higher and deeper in Turkana. The costs and benefits of the innovation fund are included but those for the support to central HSS functions are not. / Table 17: Health system strengthening cost per DALY (£) / NB: The TOTAL row is a weighted average of the costs per DALY of the three provinces. / Table 18 brings together the costs, benefits and cost effectiveness metrics of Options 1, 2 and 3. Option 2 is the aggregate of the training and health systems strengthening components. Option 3 adds the demand-side financing component, having a poverty impact as well as an additional access effect. As this has not been quantified due to very high risks of double counting, Option 3 looks poorer value for money but there are significant distributive benefits not included. / Table 18: Comparison of Options 1, 2 and 3 – DALYs and cost per DALY (£) / C.4 Risk and uncertainty: sensitivity analysis of costs per DALYs / This section sets out some of the main risks to the programme’s cost effectiveness. The main risks for DFID costs are higher than expected Kenya inflation not offset by depreciation of the shilling against sterling or specific cost increases including drugs, staffing, per diems and other training costs and logistical and operational expenses such as transport. These risks are likely to be manageable although could affect cost effectiveness if corresponding savings or efficiencies cannot be made. Of greater significance is the risk of impact being lower than projected. Risks include: / Lower than projected increase in SBA. / Lower decrease in CFR due to training and health systems strengthening components having less impact on quality – the shift from routine to basic or comprehensive obstetric maternal care. / Government of Kenya funding and other funding for service delivery reduce in real terms. / Table 19 compares cost per DALY for Option 3 to benchmarks of cost effectiveness. A value below 100% means the cost per DALY is below the benchmark. All the metrics have some headroom for cost increases and/or lower impact. / These results can be interpreted in light of the differences between the appraisal and LiST models. DALY estimates from the LiST projections would lead to higher unit costs – in the range of two to three times higher, corresponding to fewer lives saved of that order of magnitude. The models are not intended to represent maximum or minimum scenarios for lives saved. However, the robustness measures provide an indication of the buffer before the programme would seem costly if the LiST level of impact was closer to the reality. / Table 19: Robustness of cost effectiveness metrics to changes in assumptions / The high cost effectiveness is driven by training. Table 20 therefore looks at the health systems strengthening component that has higher unit costs and greater difference in cost per impact in different counties. The cost per DALY saved for Turkana based on DALYs within the timeframe of the programme is 242% of the £500 threshold (GDP per capita) through 81% of the £1,500 threshold (three times GDP per capita). When looking at benefits that accrue in Turkana due to the programme in the subsequent five years, the interventions are ‘very cost effective’ (i.e. 80% of the £500 benchmark). / Table 20: Robustness of cost effectiveness of health systems strengthening specifically / The benefits modelled in this analysis are based on a period that reflects existing levels of financing to the health sector. The future outlook is uncertain due to the devolution of functional and funding responsibilities. But there are reasons to expect future allocations to be higher: the economic outlook is positive and early signals from the new government are that maternal health financing will be given high priority. Devolution itself is likely to make the three counties relatively resource rich, although these resources need to be channelled to and spent well in the health sector. As discussed earlier, DFID’s wider work will seek to improve the link between policy and expenditure in the health sector.
D. What measures can be used to assess Value for Money for the intervention? / Monitoring VFM is challenging in areas such as health systems strengthening. Key metrics will be included in monitoring plans to ensure VFM is integrated within M&E rather than addressed separately. Specific measures that could be used are summarised in Table 21. These will be confirmed during inception for all components and performance assessed by annual reviews. / Table 21: Summary of possible Value for Money indicators / Indicator ‘3Es’ Data source Comment / Unit cost per health worker trained Economy Quarterly reports Comparison with similar programmes in Kenya / Administrative cost per voucher and administrative costs as a % of total costs Efficiency Quarterly reports Comparison with similar programmes in Kenya, including cash transfer programmes / % of vouchers utilised Efficiency Quarterly reports TBD in design phase / Poverty inclusion errors for OBA voucher programme Effectiveness Quarterly reports TBD in design phase / Cost per maternal death averted Cost Effectiveness Economic modelling / Cost per percentage point increase in skilled birth attendance Cost Effectiveness Comparison with non-programme sites / Cost per percentage point difference in skilled birth attendance rate over past 12 months Cost Effectiveness Data for calculating available from HMIS Included as logframe indicator / Comparison with non-programme sites / Cost per percentage point difference in obstetric case fatality rate­­­­ over past 12 months ­ Cost Effectiveness Data for calculating available from HMIS Comparison with non-programme sites / All VFM metrics to be generated for operations in the three counties separately Cost Effectiveness Quarterly reports
E. Summary Value for Money Statement for the preferred option / Option 3, the preferred option represents very good, high level value for money compared to international benchmarks. By 2022 the programme is expected to save about 650,000 DALYs at a unit cost of just over £100. This compares favourably with GDP per capita of £500, a reference point for determining that health interventions are very cost effective. This option is preferable to Options 1 and 2 because it provides the most credible and responsive approach to tackling the constraints to demand for services and improving their supply in the complex environment facing the health sector in Kenya at the moment. / These calculations are, however, simplistic and uncertain. Costs are subject to some variation. Benefits will depend on impact on parameters that are difficult to influence, itself the reason for taking a health systems strengthening approach. These parameters include: increasing births attended by SBA, improving facility quality and bringing down case fatality rates. The cost effectiveness results suggest headroom for less impact in order for the programme to remain good VFM. There is also a growing evidence base in Kenya of the effectiveness of interventions in affecting these parameters and this programme will contribute to this evidence base through monitoring and evaluation. The unit cost metrics also omit the potential benefit of much systemic change that this programme seeks to secure e.g. improving maternal health policy; improving equity; addressing health sector financing; supporting health management and service delivery in newly devolved counties; and piloting systems strengthening and demand-side financing in the poorest areas of Kenya. / The outlook for sustainability and improved Government of Kenya funding is positive: new government commitment to maternal health and equity in health financing is promising; and devolution provides opportunities for county financing of service delivery. There is also scope for significant improvements in budgeting and planning systems, human resource deployment and procurement, although securing performance improvements in these areas will remain challenging. / F. For fragile and conflict affected countries, what are the likely major impacts on conflict and fragility, if any? / The three options considered are not expected to have a significant positive or negative impact on conflict or fragility. All three options would contribute to national coverage of training so should not have implications in terms of favouring particular ethnic or population groups. Selection of facilities for health systems strengthening support will need to be considered carefully in the three counties, to avoid exacerbating ethnic tensions. Similar considerations will apply with respect to demand-side financing, if particular ethnic groups are over-represented among the poorest women. The risk of conflict in Bungoma and Turkana could have implications for successful implementation of the different components of the preferred option, including disruption of training activities and of service delivery. Devolution could help to mitigate the risk of local conflict but this will depend on the political and ethnic composition of county political and administrative structures and implementing partners will need to be aware of the risk of programme activities becoming politicised and take steps to avoid this.
[94] Thaddeus S and Maine D, 1994. Too far to walk: maternal mortality in context. Soc Sci Med 38: 1091-1110.
[95] Countdown to 2015 decade report: Taking stock of maternal, newborn and child survival, 2010. Lancet 375:2031-44.
[96] Graham W et al, 2001.
[97] Seneviratne and Rajapaksa, 2000.
[98] Pathmanathan et al, 2003.
[99] Chowdhury et al, 2007.
[100] Evans C et al, 2009. Where there is no obstetrician – increasing capacity for emergency obstetric care in rural India: An evaluation of a pilot programme to train general doctors. International Journal of Gynaecology and Obstetrics 107:277-82.
[101] Mekbib T et al, 2003. The FIGO Save the Mothers Initiative: The Ethiopia–Sweden collaboration. International Journal of Gynaecology and Obstetrics 81:93-102.
[102] Darmstadt G et al, 2009. Evidence-based, cost-effective interventions: How many newborn babies can we save? Lancet (Neonatal Survival Series) 365:977–88.
[103] Science in Action, 2009. Saving the lives of Africa’s mothers, newborns and children.
[104] Duke T et al, 2000. The effect of introduction of minimal standards of neonatal care on in-hospital neonatal mortality. PNG Medical Journal 43:127-36.
[105] Helping Babies Breathe is an alternative approach to training in neonatal care; this has been integrated into the national 5-day in-service training curriculum in Kenya.
[106] Msemo G et al, 2013. Newborn mortality and fresh stillbirth rates in Tanzania after Helping Babies Breathe training. Paediatrics 131:2.
[107] Evans C et al, 2009. Where there is no obstetrician – increasing capacity for emergency obstetric care in rural India: An evaluation of a pilot programme to train general doctors. International Journal of Gynaecology and Obstetrics 107:277-82; Kayongo M et al, 2006. Making EmOC a reality: CARE’s experiences in areas of high maternal mortality in Africa. International Journal of Gynaecology and Obstetrics 92:308-19; Mekbib T et al, 2003. The FIGO Save the Mothers Initiative: The Ethiopia–Sweden collaboration. International Journal of Gynaecology and Obstetrics 81:93-102
[108] Campbell O and Graham W, 2006. Strategies for reducing maternal mortality: Getting on with what works. Lancet 368: 1284-99; McCoy et al, 2010. Maternal, neonatal and child health interventions: moving from knowledge of what works to service delivery. International Health 2:87-98; Project Appraisal, 2011. Making It Happen – Capacity Development of Human Resources for Maternal and Newborn Health. ARIES REF: 200421.
[109] Canavan, 2009.
[110] Project Appraisal, 2011. Making It Happen – Capacity Development of Human Resources for Maternal and Newborn Health. ARIES REF: 200421.
[111] Pearson L et al, 2009. Maternal death review in Africa. International Journal of Gynecology and Obstetrics 106:89-94; Dumont A et al, 2006. Facility-based maternal death reviews: Effects on maternal mortality in a district hospital of Senegal. Bulletin of the World Health Organisation 84:218-224.
[112] Science in Action, 2009. Saving the lives of Africa’s mothers, newborns and children.
[113] Campbell O and Graham W, 2006. Strategies for reducing maternal mortality: Getting on with what works. Lancet 368: 1284-99; PMNCH, 2011. Essential interventions, commodities and guidelines for reproductive, maternal, newborn and child health: A global review of key interventions.
[114] Darmstadt G et al, 2009. Evidence-based, cost-effective interventions: How many newborn babies can we save? Lancet (Neonatal Survival Series) 365:977–88.
[115] Priority areas in health care financing 2013-2017. Kenya Vision 2030. Presentation April 2013.
[116] Ashford L et al, 2006. Designing health and population programmes to reach the poor. Population Reference Bureau.
[117] Meyer C et al, 2011. The impact of vouchers on the use and quality of health goods and services in developing countries: A systematic review. EPPI-Centre, IOE, University of London.
[118] Bellows N et al, 2010. The use of vouchers for reproductive health services in developing countries: A systematic review. Tropical Medicine and International Health.
[119] Ollier L and Stanton C, 2011. End of project evaluation of DFID support to Essential Health Services, Kenya.
[120] Olenja J et al, 2009. Influence of provider training on quality of emergency obstetric care in Kenya. Kenya Working Papers No. 3. Calverton, Maryland, USA: Macro International Inc.
[121] Science in Action, 2009. Saving the lives of Africa’s mothers, newborns and children.
[122] LSTM, personal communication, August 2012.
[123] Science in Action, 2009. Saving the lives of Africa’s mothers, newborns and children.
[124] Lehmann L et al, 2011. Joint Mission: Harmonising support to reproductive health in Kenya.
[125] Population Council, 2011. The reproductive health vouchers programme in Kenya: Summary of findings from programme evaluation.
[126] The GIZ and KfW pilot included vouchers for safe motherhood, family planning and gender-based violence services.
[127] DFID, 2012. Kenya multi-hazard disaster risk assessment.
[128] KEMRI-Wellcome Trust, Government of Kenya, 2011. Health service delivery, governance and supportive supervision under the HSSF: National baseline survey.
[129] KSPA, 2010.
[130] Disease Control Priorities in Developing Countries | Wendy J. Graham, John Cairns, Sohinee Bhattacharya, and others, p. 520, chapter 26 ‘maternal and perinatal conditions’, Table 26.8
[131] Ibid, Table 26.6

Commercial Case

The appraisal considered, and ruled out, a number of options for delivering this intervention. / Firstly, the option of directly financing through Government of Kenya systems has been ruled out for now as procurement and financial management systems are not adequate to provide fiduciary assurance. Fiduciary risk is significant, although reducing. Public Financial Management in Kenya, including systems in the health sector, is relatively good compared with other African countries; the 2009 Public Expenditure and Financial Accountability score showed improvements in many areas. However the impression of persistent corruption and impunity by business, government and political leaders mean that Kenya ranks low on Transparency International’s corruption perception index, at 139 out of 176 countries in 2012. As a result of concerns around fiduciary risk and the quality of public sector financial management systems DFID, in common with most other development partners, makes limited use at present of government systems to channel aid funding. However, the situation may change following devolution to county level. Annual reviews will consider the scope to progressively integrate programme activities within Ministry of Health systems, particularly at county level. / Secondly, the option of identifying one service provider to deliver all three components was considered. However, this was ruled out as there is a strong argument for contracting the LSTM to implement scale up of training (see Indirect Procurement section), and the LSTM does not have the requisite expertise to manage other components or experience to work in Turkana. Consideration was also given to using UNICEF Kenya to deliver all three components but UNICEF does not have the relevant expertise to implement the training component. A combination of UNICEF for two counties and a competition for the other county for the health systems strengthening and demand-side financing offers the opportunity to start implementation quickly in one county through UNICEF who are already well established in Turkana and Homa bay, the potential to achieve better VFM through competition for implementation of activities in the other county, and the opportunity to compare effectiveness and VFM of delivery through UNICEF and through a reproductive health framework partner in similar counties, as well as the opportunity to compare UNICEF delivery in two very different county contexts . / The intervention will therefore involve: / Component Proportion Procurement Route Direct/Indirect / Scale up of training and related support in five provinces Accountable grant with LSTM Indirect / Health systems strengthening and demand-side financing in Bungoma, and implementation of the innovation fund across 3 counties A mini competition will be run with Procurement Group to identify the most technically competent and VFM service provider of the seven providers that have an arrangement with DFID under the Reproductive Health Framework Direct / Health systems strengthening and demand-side financing in Turkana and Homa bay DFID Kenya will sign an Memorandum of Understanding (MOU) with UNICEF. This will also include managing DFID funding for central HSS, and providing management oversight of LSTM and the service provider (above). Indirect / (Multilateral) / Monitoring and independent review A % allocation towards a call down agreement through Professional Evidence and Applied Knowledge Services (PEAKS) or the Global Evaluation Framework Agreement (GEFA) across DFID Kenya’s entire health portfolio Direct / Evaluation – 3 studies A mini competition through the GEFA to identify the most technically competent provider for the best VFM Direct

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / Direct procurement of three service providers: 1) to manage support for health systems strengthening and implementation of demand-side financing in Bungoma and to manage the innovation fund across the three counties; 2) to provide support towards DFID’s monitoring across the entire health portfolio; and (3) to provide evaluation inputs for this programme. / 1) Health systems strengthening and demand-side financing in Bungoma and management of the innovation fund across the 3 counties – The service provider will be selected through a competitive tender process, which will be limited to pre-qualified providers identified under the global DFID Reproductive Health Framework Agreement. The contract will take the form of a call down contract which will be open to single organisations and consortia. It will be for applicants to determine optimal working arrangements. The contract will be include a break point at 3 years. At this point DFID will consider whether changes in the operational environment through devolution allow a shift to different financing mechanisms such as direct financing of national or county health strategies or whether to extend the contract with the service provider for a further 2 years. / 2) Monitoring support – The monitoring support will be through a call down framework agreement through the PEAKS or GEFA frameworks. This programme will provide a contribution towards a framework agreement that covers the entire DFID health portfolio of which this programme forms a major part. The monitoring looks at DFID’s overall contribution to health improvements beyond specific projects or programmes. / 3) Evaluation inputs – The evaluation will be tendered through the GEFA evaluation framework.
B. How do we expect the market place will respond to this opportunity? / 1) Health systems strengthening and demand-side financing e.g. OBA in Bungoma county, and management of the innovation fund across the 3 counties – Potential bidders will be identified at a global level by DFID Procurement Group. Although the number of pre-qualified service providers is limited, DFID Kenya expects that there will be considerable interest in bidding for this work. / 2) Monitoring support – For the monitoring through PEAKS or GEFA we expect substantial interest from the market as there are numerous national and international consultants and consultancy firms who have the required skills to undertake this work. / 3) Evaluation studies – For the evaluation studies we expect considerable interest as there are many organisations who have the required skills to undertake this work, many of whom are likely to have relevant skills and experience in Kenya or East Africa. DFID Kenya has previously undertaken reviews for the health sector and received sufficient quality bids to ensure good value for money.
C. How does the intervention design use competition to drive commercial advantage for DFID? / A mini-competition will be run between pre-qualified reproductive health framework providers that have already been identified through global competitive tendering. Rates will be centrally negotiated to ensure VFM. Most of the seven eligible reproductive health bidders are already active in Kenya and the East African region and many are expected to bid for the service provider function. Similarly a large response is expected through GEFA. / While quality, technical expertise and innovation will be key considerations in selection of the service provider and the evaluation provider, DFID Kenya will give high priority to efficiency and the ability to deliver the intervention at the lowest reasonable cost. Similar stringent criteria will be used to select consultants for monitoring through PEAKS or GEFA.
D. What is the intended Procurement Process to support contract award? / DFID Kenya will finalise the Terms of Reference, selection criteria and schedule for the procurement processes for the Reproductive health service provider, the monitoring support and the evaluation provider. DFID Kenya will provide Procurement Group with information required for the procurement processes. For evaluation, the pre-qualified providers will be invited to submit expressions of interest; those that meet the essential selection criteria will be invited to submit a full proposal and budget. DFID Kenya and Procurement Group will select the providers. Selection will be based on evidence in the bids of capacity in leadership and management, technical, financial and grant management, VFM, innovation, collaboration with the public sector, monitoring, and the extent to which the bids are judged likely to deliver the log frame targets. The tendering processes will commence in November 2013 and the successful suppliers are expected to be in place in January 2014.
E. How will contract & supplier performance be managed through the life of the intervention? / The agreements with the selected service providers will set out key performance indicators (KPI) that will be linked to payments. Programme performance will be assessed against the KPI and annual work plans agreed with DFID Kenya. DFID will: / Agree with the providers a work schedule with milestones and KPI. / Assess performance as part of annual reviews and include break clauses to manage performance. / Track performance and budget execution through narrative and financial reports submitted according to an agreed schedule, and as part of annual reviews. / Ensure that the providers have quality assurance procedures in place to ensure services are fit for purpose. / Ensure the agreements incorporate steps to be taken in the event of poor performance and failure to deliver expected results and VFM.
F. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / The main costs drivers will be personnel; procurement of equipment and supplies; logistics; and management fees. Evaluation of bids will ensure these costs are at an appropriate level and benchmarked against similar programmes especially those in neighbouring countries. Existing arrangements with procurement agents will be considered as an option for procurement. Proposals received from potential applicants will be judged against the VFM criteria of economy, efficiency and effectiveness. Elements that will be considered include: competitive fee rates, total cost to deliver the programme, provision of a clear and effective financial plan and payment by results / Competitive tendering will ensure value added in that accredited staff and consultants with sufficient capacity to perform the tasks required to a high standard are expected to be chosen. As appropriate, DFID will negotiate management charges to ensure these are set at an acceptable level. Once the Terms of Reference have been finalised, they will be used to define the framework within which the providers are expected to operate. Contract continuity will be subject to performance and satisfactory delivery of agreed milestones.

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / The rationale for selection of these implementing partners is as follows: / DFID Kenya will contract the Making it Happen partnership to scale up training and related support in 5 provinces / The Making it Happen partnership between the Royal College of Obstetricians and Gynaecologists (RCOG) and the Liverpool School of Tropical Medicine (LSTM) has a track record in effective training for health workers in emergency obstetric and neonatal care. Although other groups, such as FIGO (International Federation of Gynaecology and Obstetrics), have been engaged in similar activities, such efforts have been small scale. / The partnership was supported by DFID from 2009 to 2011, and demonstrated success in the training and support of health workers in five countries, including Kenya, and in saving mother and newborn lives. There was an observed 50% reduction in maternal case fatality and a 15% reduction in stillbirths at participating facilities. Based on this success, participating countries requested further support and DFID is funding a second phase of the programme in 12 countries, including Kenya, from 2012 to 2015. / The RCOG has strong international credibility in setting standards and providing higher specialist training for Obstetricians and Gynaecologists. Current membership of the RCOG is 12,000, with members representing over 80 countries. LSTM currently has 250 research projects in 70 countries and long experience of building capacity of health systems and health professionals in both Asia and Africa. The partnership can draw on a substantial pool of specialist obstetric and midwifery trainers. / Single sourcing of LSTM is the preferred option for DFID Kenya. There is a strong efficiency and effectiveness case for not going to tender, although DFID Kenya recognises that there may be other suppliers who could deliver this service. Working through the Making it Happen partnership would enable rapid implementation and scale up of the programme building on an existing relationships and experience. Making it Happen/LSTM has an established office and staff in Nairobi and is registered to operate in Kenya. Identifying an alternative implementing partner and establishing a parallel programme would take time, delaying scale up. It would be unlikely to deliver cost savings and would create additional transaction costs in terms of coordination, as well as challenges in ensuring consistency of training across the country. The case, in sum, is as follows: / Commencing quickly – The partnership is already working in three provinces and would be ready to start immediately. / Experience and track record – LSTM has prior experience in implementing the same training in Kenya and elsewhere and the approach and results have been positively evaluated. / Credibility – LSTM has established relationships with the Ministry of Health. The Government of Kenya is keen to expand the Making it Happen programme and LSTM is the preferred partner. Working through a different organisation would delay scale up; time would also be required to establish credentials and working relationships with government health officials. / Consistency – The partnership designed the in-service training curriculum, which has been well received and positively evaluated. Using the same provider across the country will help to ensure consistency in training content, approach and quality. / Cost – We envisage that costs will be lower. This is based on estimates from a consultancy during the programme design process assessed against current LSTM costs for similar work in the current MiH2 programme in 3 provinces. It is also based on potential reduced costs achieved through economies of scale and only paying one set of overhead costs. / Coordination – Working through one provider that covers the whole country will ensure effective coordination and reduce transaction costs for DFID and the Ministry of Health. In addition, LSTM has already started implementing MiH2, including in two of the three counties that are proposed for inclusion in this intervention (Homa Bay and Bungoma). Using the same provider will make attribution of results to DFID support more feasible as well as comparison of differences in outcomes between counties receiving training and additional health systems and OBA support versus other counties only receiving support for training. / DFID will sign a Memorandum of Agreement with UNICEF Kenya to support health systems strengthening and demand-side financing in Turkana and in Homa bay, manage DFID support for central health systems strengthening, and provide management oversight of LSTM and the service provider in Bungoma / UNICEF Kenya’s health programme aims to increase access to and use of evidence-based quality maternal and child health services and to support the Government of Kenya to achieve the health-related Millennium Development Goals. UNICEF’s programme focuses on two areas: safe motherhood and neonatal health; and child health. / UNICEF has a track record in northern and Western Kenya, (in Turkana and Homa Bay) in maternal and child health programming and supporting health systems strengthening to improve delivery of routine and emergency maternal care services. In Turkana, UNICEF has been piloting OBA and also began implementing leadership and management capacity development for health managers at district level in 2012, and early results are reported to have been positive. / UNICEF has an established regional office in Nairobi with management, financial and administrative procedures in place. UNICEF adheres to International Financial Reporting Standards. UNICEF’s administrative costs at 7% represent good VFM compared with other potential partners and international benchmarks. / UNICEF has political and technical credibility and a strong working relationship with the Ministry of Health and sub-national health structures as well as with NGOs and FBOs. / UNICEF Kenya is one of the few partners that already has a programme and a field office in Turkana and has well established relationships with local health officials and facilities in both Turkana and Homa bay. UNICEF has also conducted an assessment of existing maternal health services using bottleneck analysis in Turkana and is well acquainted with the operational environment and the challenges this poses. Consequently, UNICEF is better positioned than other potential partners to start implementation quickly in Turkana and Homa bay. / UNICEF’s mandate and UNICEF Kenya’s Strategic Plan 2013/18 are consistent with UK priorities. The DFID Multilateral Aid Review (MAR) scored UNICEF as strong on contributing to the UK’s international development and aid objectives. UNICEF was also highly rated by the MAR for its contribution to results, delivery at country level and role in delivering the maternal and child health Millennium Development Goals. / The recently published Independent Commission for Aid Impact (ICAI) report on DFID’s work through UNICEF[132] rated this work Green-Amber. The report concludes that UNICEF delivers tangible benefits and performs relatively well overall against ICAI’s criteria for effectiveness and VFM. / The ICAI report highlights the advantages that UNICEF offers as a delivery partner. These include its proximity to communities and government; its significant local presence across conflict, fragile and post-conflict zones and ability to operate in these zones; its ability to manage delivery chains of both government and non-government partners and to provide these partners with capacity building support; and its long-term engagement beyond the timeframe of donor-funded programmes, which has the potential to ensure sustainability. / As for the contract with the RH service provider, this MOU will include a break point at 3 years. At this point DFID will consider whether changes in the operational environment through devolution allow a shift to different financing mechanisms such as direct financing of national or county health strategies or whether to extend the MOU for a further 2 years.
B. Value for money through procurement / VFM considerations are as follows: / UNICEF engages in competitive tender for goods and services in accordance with international policies and procedures; procurement of equipment, drugs and supplies will also benefit from UNICEF’s ability to achieve economies of scale. DFID will, however, take steps to ensure that UNICEF secures VFM in procurement. / UNICEF’s proposed overhead rate is 7%; this is in line with international benchmarks and management fees charged by other UN agencies, private consulting firms and NGOs. The Multilateral Aid Review assessed UNICEF as offering good VFM to UK aid. / As discussed above, working through the MiH partnership will deliver cost savings and VFM. / DFID Kenya will also, for both LSTM and UNICEF: / Review annual budgets to identify cost savings. / Track progress and budget execution through quarterly narrative and financial reports and quarterly review meetings. / Ensure that agreements/MOU include monitoring procurement, financial management and sub-contracting processes in order to ensure VFM. / Include monitoring of efficiency, cost savings and VFM in annual reviews. / Strengthen its management of UNICEF’s local programme delivery in line with good practice and the ICAI recommendation that DFID shift to managing its relationship with UNICEF on a more commercial basis as for other service providers, with a stronger focus on results and VFM.
[132] ICAI, 2013. DFID’s work through UNICEF. Report 21. March 2013.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / Overview of costs / DFID will contribute up to £75 million over 5 years, from October 2013 to September 2018. The indicative budget summary is shown below. The budget includes funding to: LSTM for scale up of training in five provinces; a service provider for support for health systems strengthening and demand-side financing in Bungoma and management of the innovation fund ; UNICEF for support for health systems strengthening and demand-side financing in Turkana and Homa bay, support for central health system strengthening at national level, and management oversight of LSTM and the service provider for Bungoma and the innovation fund; independent annual reviews and evaluation studies. Cost forecasts will be based on annual work plans and budgets agreed with LSTM, the service providers and UNICEF. The contingency is included to build in scope to manage the uncertainty over instruments to deliver programme objectives. These uncertainties relate in particular to (i) GoK’s evolving policies and approaches to eliminating user fees and to (ii) devolution process. The contingency will be managed by the lead adviser with authority provided at appropriate levels of delegation. / Component detail / Component 1 – Appraisal and Design / Funding Type : 104 – Procurement of Services / Benefitting Country - Kenya / Input Sector Input Sector Code Percentage Allocation / 1 Reproductive Health Care 13021 20 / 2 Maternal and Neonatal Health Care 13022 80 / 3 / Component 2 – Implementer (mini-competition within Reproductive Health Framework) / Funding Type : 104 – Procurement of Services / Benefitting Country - Kenya / Input Sector Input Sector Code Percentage Allocation / 1 Reproductive Health Care 13021 20 / 2 Maternal and Neonatal Health Care 13022 80 / 3 / Component 3 - UNICEF / Funding Type : 109 – Multi- Lateral Donor / Benefitting Country - Kenya / Input Sector Input Sector Code Percentage Allocation / 1 Reproductive Health Care 13021 20 / 2 Maternal and Neonatal Health Care 13022 80 / 3 / Component 4 – Training Component (LSTM) / Funding Type : 111 – Not for Profit Organisation / Benefitting Country - Kenya / Input Sector Input Sector Code Percentage Allocation / 1 Reproductive Health Care 13021 20 / 2 Maternal and Neonatal Health Care 13022 80 / 3 / Component 5 – Monitoring (selection within PEAKS or GEFA frameworks) / Funding Type : 104 – Procurement of Services / Benefitting Country - Kenya / Input Sector Input Sector Code Percentage Allocation / 1 Reproductive Health Care 13021 50 / 2 Maternal and Neonatal Health Care 13022 50 / Component 6 – Evaluation (selection within GEFA) / Funding Type : 104 – Procurement of Services / Benefitting Country - Kenya / Input Sector Input Sector Code Percentage Allocation / 1 Reproductive Health Care 13021 50 / 2 Maternal and Neonatal Health Care 13022 50
B. How will it be funded: capital/programme/admin? / The full contribution will be drawn from DFID Kenya programme resources and has been budgeted for in the Country Operational Plan. No contingent or actual liabilities are foreseen. As the proposed programme timeframe goes beyond the current spending review, the business case will require HMT approval via FCPD.
C. How will funds be paid out? / Funds will be paid out as follows: / DFID Kenya will advance funds to LSTM on a quarterly basis. LSTM will be expected to provide a forecast expenditure requirement for the quarter to be covered by the advance. A statement of actual expenditure incurred during the previous quarter will be required for subsequent advances. Disbursement will also be dependent on satisfactory performance. / DFID Kenya will disburse funds on a quarterly basis in arrears to the contracted service provider Bungoma. Disbursement of funds will be linked to performance against the KPI in the contract and expenditure reports for the previous quarter. / DFID Kenya will advance funds to UNICEF on a Semi-annual basis. UNICEF will be expected to provide a forecast expenditure requirement for the period to be covered by the advance. A statement of actual expenditure incurred during the previous six months will be required for subsequent advances. Disbursement will also be dependent on satisfactory performance. / Payments for directly procured independent review and evaluation services will be made in arrears, and will be governed by the terms of the contract.
D. What is the assessment of financial risk and fraud? / Financial risk and risk of fraud is assessed as medium, as funds will be channelled through recognised partners with approved financial management and audit systems. LSTM, approved providers under the Reproductive Health Framework and UNICEF have effective systems in place for financial accounting and management; pre-qualified providers meet DFID requirements for financial management, reporting and audit.
E. How will expenditure be monitored, reported, and accounted for? / DFID and the implementing partners will agree annual work plans and budgets. All implementing partners will provide DFID with quarterly financial forecasts, quarterly and annual financial reports and a certified annual audit statement within 6 months of the financial year end. These requirements will be included in the agreement with LSTM, contract with the service provider and MOU with UNICEF. UNICEF will also be required to manage, monitor and report on grant funding under the innovation fund. DFID will report on programme budgets and expenditure to the Ministry of Health. Implementing partners will also maintain an assets register. Any capital assets procured will be treated in accordance with DFID procedures. / DFID Kenya takes a comprehensive approach towards risk identification, prevention and mitigation. / At the Operational level DFID Kenya reviews operational risks each quarter. Risk owners, in the senior leadership team assess risks and mitigating actions. The leadership team also identifies two operational level risks (currently fraud and devolution) for each programme to identify how the risk impacts their programme. / At the programme level, all programmes maintain a live programme risk matrix that is updated as and when risks change. The risk matrices are reviewed at programme team meetings and shared with partners. Twice per year, the Accountability and Results team, review the programme risk matrices together with the pillar teams, to identify further mitigating actions not identified. Each year during the annual review each programme is assessed for residual fraud risks. / DFID Kenya carries out due-diligence assessments of partners, before funding begins. The process highlights risks and provides recommendations for the partner to implement. Partners are required to provide organisation Annual audit statements each year, and where we feel there are weakness in the financial reporting, we commission an enhanced audit which focuses on the expenditure verification and providing any further recommendations to improve the control environment. In the event that an enhanced audit discovers occurrence of fraud, we commission a forensic audit to establish the extent of the loss, to get lost funds back from the partners.

Management Case

A. What are the management arrangements for implementing the intervention? / DFID management and contractual arrangements / These will be as follows: / DFID will provide direct management oversight of UNICEF and of the monitoring and evaluation suppliers both for this programme and for DFID Kenya’s health portfolio overall. / DFID will have direct contracts, grant or MOU arrangements with LSTM, UNICEF, the service provider for HSS in Bungoma and the innovation fund, and monitoring and evaluation suppliers. / UNICEF will provide management oversight of LSTM and the service provider for HSS in Bungoma and the innovation fund. / These arrangements are summarised in the diagram. The black arrows represent management oversight; the red arrows represent a direct MOU or contract or accountable grant with DFID. / Oversight, coordination and management arrangements / These will be as follows: / Within the programme: / An Implementation Working Group will be established that brings together the three lead implementing partners – LSTM, the Reproductive Health (RH) service provider and UNICEF, to ensure effective phasing of activities and coordination between the training and health systems strengthening components and to promote consistency, sharing of experience and lessons learned with respect to health systems strengthening, innovation funding and demand-side financing in the three counties. DFID and Ministry of Health representatives will participate in meetings of this group, as required, which will be held quarterly. Implementing partners will also be expected to participate in and report to the Steering Group (see c) below). / The service provider and UNICEF will also be expected to establish arrangements for management and coordination of activities at county level with all relevant stakeholders. County coordination mechanisms are not yet in place, and therefore arrangements for the implementing partners will be determined during the inception phase. It is anticipated that LSTM will participate in these with respect to planning, implementation and monitoring of the training component, and DFID Kenya expects LSTM and the service provider and UNICEF to collaborate as appropriate. (NB. The programme will have 2 inception phases. The first, with the lead partner UNICEF, will be for a period of 3 months when the programme starts up, and the other with the RH service provider for a period of 2 months once they are contracted following a tender process. UNICEF will have a longer inception phase because they will be taking the lead role in programme coordination and oversight for providers for all programme components. They will use the time to establish the governance, implementation, and coordination mechanisms and ensure that roles and responsibilities of each partner are clear from the outset. During both inception phases UNICEF and the RH service provider will establish their county offices, establish working relationships and networks in their focal counties and select target health facilities and community units and collect baseline data for indicators). / The RH Service provider with support from UNICEF will be expected to establish grant management and governance arrangements for the innovation funds in Homa Bay, Bungoma and Turkana. It is anticipated that county government and health department representatives will be involved in review of applications and decision-making about grant awards, subject to conflict of interest provisions. / UNICEF will manage funding and support for central HSS activities including working with relevant partners such as WHO and technical assistance providers. / LSTM will manage implementation of the training component. They will work closely with the Ministry of Health and training institutions, including KMTCs. / The RH service provider and UNICEF will be responsible for implementation of health systems strengthening and demand-side financing in Homa Bay and Bungoma, and in Turkana, respectively. / UNICEF will be responsible for management oversight, on DFID’s behalf, of LSTM and the RH service provider. / Within DFID: / The DFID Kenya Health Team including the Senior Health Adviser, Reproductive Health Adviser, Senior Programme Officer and Programme Officer will be responsible for programme oversight; the Reproductive Health Adviser will be the lead adviser. The DFID team will also be involved in final decisions about innovation funding grant awards. / Other focal staff within DFID Kenya (e.g. Accountability and Results Team Leader, Economist and Results Adviser) will be engaged as appropriate. / To the extent feasible and appropriate, the Health Team will coordinate planning and periodic reviews between this and the DFID family planning programme to ensure that synergies and learning between the two programmes are fully exploited. / With Government of Kenya: / DFID and the Ministry of Health will provide oversight through a Steering Committee, which will meet quarterly. At national level, the Department of Family Health or its replacement following reform of the health ministries will be the focal point for oversight of all components of the programme. The Steering Committee will also include representation from county health teams as appropriate, as well as the implementing partners. / The implementing partners will establish an MOU with county governments and/or health departments as appropriate. The MOU will include commitment to ensuring staff availability for training and support to health system strengthening. LSTM, UNICEF and service provider will provide quarterly updates to county health officials. / With development partners: / Existing Inter-agency Coordinating Committees (ICCs) and technical working groups (TWGs) that report to these ICCs are currently the primary mechanism for ensuring harmonisation and coordination with other development partners. Key fora are the Health Sector Coordinating Committee and Service Delivery and Health Financing working groups, Human Resource for Health ICC and its TWG for National Training, and the Reproductive Health ICC and its MNH TWG. DFID will use these fora, or whatever structures are established in their place in the new context, to ensure buy-in, joint planning, coordination and co-funding. Partners on this programme should also attend these fora. / The DFID Kenya Health Team will also ensure coordination with other interventions in the sector through the DPHK forum and other national sector coordination mechanisms to be constituted following health ministry reform. / Terms of reference for the Implementation Working Group and the Steering Group will be developed during the inception phase. / The following diagram summarises the proposed structures for oversight, and coordination. The arrows represent the flow of information. / National / County / Monitoring and evaluation of programme implementation / DFID Kenya will contract independent monitoring and evaluation support for the overall DFID Kenya health portfolio of which this programme is a part. In addition, DFID Kenya will contract evaluation services specific to this programme. as discussed above. The Steering Group will review annual work plans, quarterly progress reports and the findings of independent annual reviews, as well as ensuring effective dissemination of lessons learned. / Beneficiary perspectives will be sought through 1) health facility and community health committees; 2) mechanisms established to solicit feedback on service delivery and quality; 3) accountability mechanisms at county level; 4) health worker feedback through evaluation of in-service training; and 5) use of participatory monitoring and evaluation approaches by implementing partners and annual reviews. Consideration will be given to how to get feedback from community members who do not use health facilities to ensure their views are captured. These mechanisms will also be used to ensure that beneficiaries receive feedback on progress and have an opportunity to propose corrective measures to improve outcomes. / DFID Kenya / Evaluation service provider for this programme / Monitoring and evaluation contract across DFID Kenya health portfolio / UNICEF Kenya (HSS Turkana and Homa bay, central HSS, management oversight / Service provider (HSS Bungoma and management of the innovation fund) / Liverpool School of Tropical Medicine (training in 5 provinces) / Programme Steering Committee / DPHK forum / Inter-agency Coordinating Committees and Technical Working Groups / LSTM to establish coordination arrangements for training at national and county levels / Implementation Working Group / HSS Bungoma and innovation fund: MOU between service provider and county government. / County coordination mechanisms to be established / HSS Turkana and Homa bay: MOU between UNICEF and county government. / County coordination mechanisms to be established
B. What are the risks and how these will be managed? / The two most significant risks are associated with the political environment in Kenya and with the major institutional and structural changes that are taking place following the recent election. Inter-communal violence erupted after the election of 2008, with effects that continue to the present day, and there is potential for further disruption and for localised outbreaks of conflict in future. / A major area of policy risk is uncertainty about how the new Government of Kenya’s commitments on health financing will be taken forward. Specific concerns have been raised, for example, about financing for procurement of drugs and supplies at local level if reimbursement is insufficient to compensate facilities for reduced income resulting from the elimination of user fees, and about financing the additional drugs, equipment and human resources that will be needed to meet increased demand for free primary health care. / Reform of central ministries, in particular the merger of the two existing ministries into one new Ministry of Health, will take time and may create uncertainty and delay decision making until posts are filled. The merger may also have ramifications for national sector coordination structures and mechanisms for government-donor engagement. There are also concerns that without a dedicated ministry, the merger could result in a downgrading of public health and this, together with devolution of authority and budgets to new counties, could lead to disproportionate allocation of resources to hospitals and medical services. At county level this would have implications for services at primary care and community level and for demand-side activities. / There are also risks associated with devolution and the transition of functions and funding to the new county governments. There is a push to transfer functions, and staff, as quickly as possible but service delivery could be disrupted, unless the transfer is well managed. There are concerns about the 2013/14 county budget process, which has been delayed, as a result of which counties do not know how much they will receive in national transfers, as well as about the unknown proportion of county revenue that will need to be used to pay salaries. As discussed in the Strategic Case, it is not yet clear where responsibility will reside for key functions, including human resources for health, procurement of drugs and supplies, provincial hospitals, public health, and monitoring and evaluation, and lack of clarity could have significant implications for service delivery. Counties will, however, determine their own priorities across sectors and determine their own budgets. One possible risk of this is that counties will reduce health allocations and, within health budgets, prioritise curative over preventive care and construction of infrastructure and procurement of vehicles over service delivery. Budget tracking will therefore be a key element of health systems strengthening support and, as required, policy advocacy. / Until county structures are established and senior staff are in post, it will be difficult for programme implementing partners to support planning, budgeting and other aspects of systems strengthening or capacity development. Major restructuring of human resources, with some national staff and all provincial staff being appointed to newly-created county structures, will also have implications for planning and implementing in-service training[133]. Working with a limited number of counties to develop systems, guidelines and procedures that can later be rolled out nationally may be more immediately effective, but it will be important to secure national buy-in. / A summary of risks and mitigation strategies is provided below. / Risk Impact Probability Risk mitigation Residual risk and contingency plan / 1. Political instability and escalation of civil unrest and political violence that could limit implementation of programme activities High Medium DFID and UNICEF have been able to maintain good relations with the Ministry of Health during previous instability and will continue to engage in regular dialogue. The UN is able to continue to support service delivery even in periods of crisis. DPHK has developed a comprehensive contingency plan. TOR for implementing partners to include experience in working in different parts of the country, including during periods of unrest, contingency planning and development of contingency plans. Security plan in place for all establishments and moveable assets. Medium Contingency: If need be, implementation will focus initially on areas that are more stable and secure. Use of ICT approaches to training. Service provider to include appropriate insurance cover. / 2. Delays and disruption to financing and delivery of health services resulting from Ministry of Health restructuring and reform and uncertainty about responsibility for functions such as procurement of drugs High Medium Transition will be in a 3 year phase as counties are assessed as ready to assume responsibility for managing health service delivery. Support through the Kenya Health Programme and flexible health systems strengthening support will be provided to target counties. Other development partners will provide support through the transition period in other areas of the country. Phased implementation of training as counties become able to manage HRH and health workers are in post. Medium Contingency: Where monitoring reveals major shortcomings, provide additional technical support and work with government and other development partners as appropriate. / 3. Changes in development partner priorities including implications of expanded USAID support for health systems Medium Medium Other donors may face constraints due to domestic financial constraints. However, in principle, commitments have been made to financing the Government of Kenya’s reproductive health business plan and donors’ individual strategies for support to the health sector. Donor inputs are harmonised through coordination structures. Potential expansion of USAID support to cover 20 counties could have major implications for this intervention; DFID will engage in dialogue with USAID to minimise risk of overlap. Low / 4. Delays in establishing county health structures and appointing key staff and ongoing capacity limitations at county level High Medium Transition will be phased and counties will take on responsibility for health only when ready. Development partners have been supporting the Government of Kenya to prepare for devolution and health is one of the most advanced sectors. Implementing partners would work with existing district health teams and with training institutions to plan and implement feasible health systems strengthening and training activities and initiate OBA. Medium Contingency: Pursue MOUs with entities that have decision-making authority for key issues. Provide supplemental technical assistance as needed. Sequence of roll out of training will use readiness criteria including existing support for health systems strengthening and maternal health from other partners, existing Community Strategy activities. / 5. Continued shortages of HRH and rotation of health workers undermines service delivery and training efforts Medium Medium HRH key element of HSS support to counties. Ongoing support provided at national level by WHO through the Kenya Health Programme. Links with other HRH projects including US-funded Capacity Project. Devolution of authority for staff has the potential to address shortages and reduce staff rotation. Skills acquired as a result of training will be used elsewhere provided staff remain in the public sector. Low / Contingency: Pursue MOUs with entities that have decision-making authority for key issues. Provide supplemental technical assistance as needed. / 6. Insecurity, conflict, drought, environmental disaster in particular in Turkana and Bungoma High Medium UNICEF has extensive experience in addressing such challenges and mitigating their impact on service delivery. TOR for service provider for Bungoma and Homa Bay to include relevant experience and expertise. All implementing partners to develop contingency plans in the event of conflict or environmental disaster and strategies to minimise risk of politicisation of programme activities. Low / Contingency: Co-ordinate and work closely with DFID Kenya humanitarian pillar on building resilience in this programme. / 7. Continued low rates of service utilisation by some population groups of women Medium Low Targeted community awareness raising and mobilisation, and targeted implementation of subsidised vouchers. If necessary, operational research to improve understanding of barriers to uptake of services and develop additional strategies. Low / Contingency: Develop additional strategies and if needed provide more support to the government Community Strategy. / 8. Fraud, corruption or misuse of DFID funds, in particular with respect to innovation funding Medium Low Implementing partners meet required standards for fiduciary management and procurement. Fiduciary risk management plans to be developed by service provider, LSTM and UNICEF, and monitored by DFID. Regular audits to be conducted. Direct procurement safeguarded through standard DFID supplier selection and management processes. Service provider and UNICEF to establish and implement appropriate measures to minimise risk of fraud, corruption and misuse of DFID funds by innovation fund grant recipients. Low / Contingency: Monitoring to be intensified and regular audits supplemented if risks found to be unacceptably high. / 9. Shortages of essential drugs and supplies, if procurement responsibilities are devolved and/or inadequate funds are available as a result of eliminating user fees, and of safe blood High Low Funds allocated to address emergencies and shortfalls if the need arises. Availability of supplies to be monitored by implementing partners and key element of HSS support for targeted counties. Medium Contingency: Re-programme additional funds to procure drugs and supplies or supplement CDC support for blood supply, if the need arises. / 10. Newly-created counties receive inadequate health financing from central government and/or reduce allocations for health High Medium HSS to targeted counties to build capacity for planning and budgeting and development of health financing strategies. Budget tracking by UNICEF and the service provider in Bungoma and Homa Bay and policy advocacy. Medium / Contingency: / 11. Delays in DFID procurement of service provider delays programme start up and thus not achieving results Medium Medium Risk should be minimised by limiting competition to pre-qualified providers. UNICEF and LSTM well positioned to commence activity quickly. Low / 12. Financing gap in health sector due to reduced Global Fund funding and/or changes in financing modalities, with implications for Ministry of Health budget for other areas of health care Medium Medium Assessment of financing gaps, impact and mitigation measures currently being undertaken with support from USAID and GIZ; implications are need for increased Government of Kenya funding, seeking new Global Fund grants (including participating in new funding model pilot). Low / 13. Government of Kenya unable to meet commitments to introducing universal health coverage and elimination of fees for maternal health care Medium Low DFID, WHO and other development partner engagement with Ministry of Health and Ministry of Finance to sustain support for critical policy issues including health financing, elimination of user fees, human resources for health and demand-side financing. Advocacy, community education and accountability work will increase awareness of heath rights, including to exemptions from user fees. Low / 14. Government of Kenya and other donors shift away from demand-side financing in view of proposed user fee elimination Medium Medium Implementing partners will need to take a flexible approach; approach to be determined during inception phase. Build in scope to phase out/adapt support for demand-side financing in programme planning and monitor situation regularly. Low / 15. Products and/or service delivery fail to adhere to quality standards and a client experiences an adverse event Low Low Training will ensure that all providers are aware of what to do in case of an adverse event, and standard operating procedures developed for adverse events. Referral mechanisms put in place to ensure adverse events are referred to higher level facilities quickly and efficiently. / Quality assurance plans put in place by implementing partners. Low / Risk matrix summary / IMPACT / HIGH MEDIUM LOW / PROBABILITY HIGH / MEDIUM [1] [2] [4] [6] [10] [3] [5] [11] [12] / LOW [9] [7] [8] [13] [14] / The overall risk is medium.
C. What conditions apply (for financial aid only)? / Not applicable.
D. How will progress and results be monitored, measured and evaluated? / The logical framework (see Annex 1) sets out the delivery trajectory and expected results (impact, outcome and outputs), proposed indicators and milestones to measure progress, and data sources for monitoring. The following distinct elements of monitoring and evaluation are envisaged and have been included in the budget allocation. / Monitoring Routine monitoring of activities will be managed by implementing partners (LSTM, the RH service provider and UNICEF Kenya) and overseen by DFID. There will be two key components to monitoring: developing and establishing the monitoring system and collecting baseline data; and using data generated to assess progress. Specific monitoring systems and indicators for the innovation fund component of health systems strengthening will be established jointly by the service provider and UNICEF. / Routine monitoring will be based where possible on existing national systems, in order to avoid creating a parallel system. Specifically it will draw on the web-based district health information system that has been rolled out across the country. At present, morbidity surveillance reports are reported immediately or weekly for notifiable diseases, while service delivery reports from health facilities are generated daily on tally sheets and monthly summaries are sent manually to district level for review and verification before being uploaded onto the district health information database. Data entry to this system, permitting analysis by ward and county, is expected to continue during devolution, although there are likely to be some challenges during the transition phase. Implementing partner – UNICEF and the service provider – support for health systems strengthening will include support for improving the health information system and routine data collection and reporting in the three counties, to ensure that information required for monitoring is available. Monthly review meetings held at health facility level will be used to monitor performance and quality of care, as will use of MDR. Additional information on progress that is not captured by the district health information system, for example, infrastructure and referral system improvements, supervision reports, financial reports and staff establishment will also be collected and reviewed, as well as feedback from community and health facility committees. / In addition, data is generated through the national population census, household surveys (including the Kenya Demographic Health Survey, Kenya Household Indicator Survey, Kenya Aids Indicator Survey, Kenya Immunisation Coverage Survey, Kenya Malaria Indicator Survey and Kenya Micronutrient Indicator Survey), registration of vital events including births and deaths at community and health facilities. These sources, national health facility assessments and national monitoring of progress with devolution will be used to confirm baselines, inform planning and measure programme progress. MDG reporting and the next round of the DHS will be also be key data sources for monitoring the programme at outcome and impact levels. DFID has set aside separate funding for the DHS if this required and is represented on the DHS working group. / DFID Kenya will work together with all three implementing partners to ensure that their M&E frameworks and systems and reporting formats will generate the data required for DFID monitoring purposes. All three partners will be expected to report against the programme logical frame and hence will use a core set of common indicators. Monitoring data will be analysed to generate recommendations for adjusting and improving implementation. The implementing partners will submit quarterly progress reports to DFID Kenya, reporting against agreed annual work plans and on progress towards milestones and targets in the logical framework. DFID Kenya will meet quarterly with the service provider and UNICEF to monitor progress towards expected results; these meetings will be linked to quarterly progress reporting. / Annual reviews DFID Kenya will commission independent annual reviews to monitor progress against the indicators and milestones in the logical framework and annual work plans at the end of each year of implementation, with a Project Completion Review at the end of year 5. It is expected that these will be commissioned through the external M&E contract. / Evaluation DFID Kenya has a new evaluation strategy aimed at improving the impact of its programme portfolio by ensuring that investments and decisions are based on reliable and robust evidence. To inform future programming decisions of DFID Kenya as well as those of other development partners, three evaluation questions will be addressed in relation to this programme, through separate studies, and a retrospective whole programme evaluation will also be commissioned. There will be one independent evaluation contract to cover these three studies, through the GEFA. The questions of interest are: / How do maternal health outcomes compare in counties where training and systems strengthening work is undertaken, compared with counties which only receive the training intervention? (This responds to a current lack of evidence around the benefits of health systems strengthening work.) / How does delivery through UNICEF compare with delivery through a RH service provider in similar counties in Western Kenya, and how does UNICEF delivery in Homa bay compare to UNICEF delivery in the different, potentially more challenging context of Turkana. / What is the assessment of this whole programme with regard to DAC evaluation criteria of efficiency, effectiveness, relevance, equity and impact? / In addition, LSTM in the course of their programme will look at the following question:How do QI and MDR training affect the quality of care provided? / It is envisaged that the first question will use county-level DHS data due to be collected in late 2013 as a baseline and potentially repeat DHS data as an end-line after 5 years. However it is also likely that a separate survey assessing the extent of skilled birth attendance in counties will be required. There are 47 counties where training is being or will be delivered (through this programme or a DFID HQ programme) and three which will also receive systems strengthening support (one being Turkana where the context is also somewhat different). The full study design will be worked up by the evaluators, but as well as the quantitative work outlined above, it is likely that the evaluation will require collation of some service use data from health facilities and some qualitative interviews. / For the second question, UNICEF delivery will be compared across two different counties (Homa bay and Turkana), and will be compared with delivery through the RH service provider in one similar county (Homa bay and Bungoma). The full study design will be developed by the evaluators and will include quantitative as well as qualitative work as for the first study question above. / The retrospective evaluation at the end of the programme will include assessment of the efficiency, effectiveness, relevance, equity and impact of the support provided by DFID. It will aim to assess the extent to which the intervention has contributed to averting maternal and neonatal deaths; improved health workers knowledge and skills and the quality of maternal and newborn care they provide; strengthened health systems and management of health services in the three targeted counties; and has increased demand for and uptake of maternal health care in these counties. It will also consider whether lessons learned can be applied elsewhere. This evaluation is expected to be based on some interviews with key informants and beneficiaries, as well as a wide range of documentary sources, including the above evaluations, Kenya’s DHS and national level MDG reporting, programme baseline data and routine monitoring, training follow-up, analysis of financing data, and client satisfaction interviews. / For the final LSTM related question, the study will need to select a quality of care tool (a number are in existence) and do a baseline and end-line assessment, before and after training to see how staff alter their approach to treatment of mothers and newborns. This is currently being evaluated through the LSTM programme, and will therefore not be a part of the independent external evaluation. / DFID Kenya is developing a joint external M&E framework to cover all of its health programmes. This will require an external contractor to guide M&E design, quality assure M&E outputs and validate reported progress. Implementing partners for this intervention and the independent evaluators will be required to provide data to the external M&E contractor but the M&E contractor will not design or undertake the evaluation work outlined here. Consideration will also be given to the potential to assess issues that are common to this intervention and other DFID Kenya health programmes, for example, the role of new technologies and e-health, demand-side financing, and models of service delivery in difficult operating environments. / The Project Completion Review (PCR) at the end of Year 5 will be based largely on the retrospective evaluation outlined above. / Operations research Opportunities for operational research, to be implemented by the programme implementing partners, will also be explored. (MiH2 is planning to conduct specific operations research on health worker skills and knowledge retention; severe pre-eclampsia and eclampsia; and a post-partum haemorrhage audit study). Possible areas for operations research, to be explored with key stakeholders, could include: / Does use of new technologies in training, supportive supervision, referral and other areas of service delivery enhance effectiveness and VFM? / What are the most effective approaches to building sustainable capacity for health services management, delivery and accountability at devolved level? / How does OBA compare with other demand-side financing approaches to increasing uptake of maternal health care services by the poorest women? / What is the most effective, and cost-effective, way to provide delivery care and emergency obstetric and neonatal care to nomadic populations? / Terms of reference for the evaluation work will be developed prior to business case approval to ensure that we can quickly go to tender on this work and have a contract in place in time to gather required baseline data. / Governance arrangements will be set up for the evaluation work to ensure independence and technical quality. Key stakeholders will be involved and will also assist with dissemination of findings to ensure lessons learned are applied. Advice on evaluation and operations research design and methods will be sought from DFID’s Research and Evidence Department (which includes the Evaluation Department). Users of the findings will include (a) DFID Kenya; (b) Ministry of Health and other key line ministries; (c) other donors; and (d) DFID country programmes and HQ. Findings will be disseminated through the Development Partners in Health Kenya(DPHK) forum, national sector coordination mechanisms and technical working groups as well as to international and regional organisations, technical implementing agencies, NGOs and academic institutions with an interest in maternal and newborn health.
[133] Dutta A et al, 2012. Risk and impact analysis for Kenya of changes in Global Fund financing modalities (Draft).

Annex 1: Economic appraisal

The Economic Appraisal and accompanying excel work book are on Quest:
Economic Appraisal 21 June v0.6
QUEST document number: 4172910
Copy of kenya MNH BC model v1 36 20 Sept
QUEST document number: 4172911

Annex 2: Climate and environment assurance note

Intervention Details
Title	Home Department	Budget
Reducing Maternal and Neonatal Deaths in Kenya	DFID Kenya	£75m over 5 years (2013-2018)

Responsible Officers
Title	Name	Department
Project Owner	Louise Robinson	DFID Kenya
Climate Change Adviser	Virinder Sharma	DFID Kenya

Appraisal
Success Criteria	Sensitivity Analysis
NA	N-Sensitivity analysis was not carried out for each option

Climate and Environment Category
Risks and Impacts	Opportunities
Category B- Low Potential Risk	Category B- Medium Potential Opportunities

Management
Risks and opportunities defined	Climate Change/Environment Measures agreed	Climate/Environment Measures in the / logframe
Y / Climate and environmental impacts will be widely variable in a programme of this scale and design. The critical issue is to list all reasonably possible impacts, identify those of potential high impact and mitigate through implementation as well as build on climate and environmental opportunities. Most health and environmental risks arise out of poor infection control and insufficient environmental management practices. Reduction in maternal and neonatal mortality rates in Kenya depends on a number of direct and indirect factors. Some of these factors (mainly medical/clinical) are within the control of the health system; others are external determinants that affect maternal and neonatal health status. / Direct impact from health logistics and products. This includes the disposal of waste (i.e. safe needle disposal) and the maintenance of the cold chain. The first set of issues is associated with the impact of programme-supported interventions. These are both those of an explicitly adverse environmental impact in nature, and those where judicious intervention and appropriate sensitisation and education can prevent or mitigate problems. These issues are: (a) waste to air, water and land from health facilities and health machinery; (b) logistics of the health system e.g. the need for and use of transport; (c) health system basic infrastructure, energy needs, capital and operational costs; (d) use of medicines/treatment processes and environmental contamination that may ensue; and (e) human resources e.g. their sensitisation to climate and environmental concerns and their interaction with elements (a)-(d). In health care facilities these will also include treatment and disposal of bio-medical waste; disposal of syringe waste; providing water, sanitation and good hygiene conditions; design and construction related issues; and the need for widespread awareness and commitment at all levels to tackle these issues. / Indirect impact on climate and environment is associated with preventive health measures, such as improving water and sanitation and decreasing areas of swamp to prevent malaria. The second set of issues relate to the overall analysis of problems that prevent the achievement of the programme goal i.e. reduced maternal and neonatal mortality in Kenya. Health systems development plans should undertake a fundamental analysis of the causes of morbidity and mortality, particularly in mothers and infants. Where these are related to environmental factors such as the need for potable water, better indoor air quality, improved sanitation, reduction of mosquitoes and other disease vectors, then the programme design should explore multi-disciplinary and multi-institutional mechanisms by which the goal can best be achieved. Complex matters that are outside the control of the health sector, such as food and water safety, which are likely to have a bearing on health outcomes, should be addressed through other convergent mechanisms. / Opportunities in the health system could include innovative use of solar panels and water catchment; locating and constructing low carbon and energy efficient facilities in appropriate sites and asset maintenance costs include keeping equipment and supplies maintained. / Key health concerns and vulnerability to climate change: Approximately 13- 20 million Kenyans are at risk of malaria, with the percentage at risk potentially increasing as climate change facilitates the movement of malaria transmission up the highlands. Studies into the effect of climate change on health in Kenya also reported increases in acute respiratory infections for ASAL areas, re-emergence of Rift Valley fever, leishmaniasis, and malnutrition. Floods, occasional outbreaks of waterborne diseases e.g. cholera, dysentery and typhoid have been reported in lowland areas around water bodies.	Y / The log frame includes output indicators on plans for effective MNH services which will improve quality and coverage of skilled deliveries and Health Facility Management Committees. Health plans and facility committees need to develop a structured and systematic approach to help avoid, reduce and control health and environmental risks associated with health care facilities at different levels. This includes operational guidelines to prevent infection; surveillance systems; waste segregation, on-site storage, treatment, disposal and transportation of bio-medical waste; handling sharps; use and disposal of glass/auto-disable syringes; mercury waste disposal; site selection, design and construction management of new health care facilities; and drug expiry management. / Elements of disaster risk reduction and disaster preparedness relevant to health systems need to be integrated into sector and facility plans and guidelines and monitored. Related plans for training and capacity building should be prepared and periodic impact assessment carried out. / Recommendation: The programme should undertake further analysis on how to mitigate risk of climate and environmental impacts and identify opportunities for action. / General climate and environmental opportunities for green housekeeping in health sector facilities, and environmental impact reduction associated with health logistics should be identified and options recommended. With respect to infrastructure support, the costs and sources of materials, operational costs and opportunities for reduction of impacts and costs, and energy and fuel consumption reduction should be examined. Options include the use of solar panels as well as water conservation measures in all facilities and buildings. / The Health Facility Management Committees offer an entry point for integrating most of the climate, environment and disaster risk reduction issues. The health sector needs to assigns responsibilities at all levels and ensure that budgetary support is integrated within implementation plans. Training needs assessment and awareness building workshops should be conducted to provide information, change attitudes and build staff knowledge, skills and competencies.	Y / Indicator: Climate and environmental risks mitigated and opportunities maximised in the programme interventions / In addition, the Lead Adviser/Programme Officer will ensure that implementing partners report regularly on the mitigation of climate and environmental risks. / Joint meetings will be held with the health sector and implementing partners to identify priority areas to be addressed and to plan required actions.

Evidence
Relevant documents

SIGNED OFF BY:	Virinder Sharma
DATE:	July 2013