Annual Review

Title: Multi-Year Humanitarian Programme in Pakistan (MYHP)
Programme Value £ (full life): £100 million		Review Date: 30-11-2018
Programme Code: 204603	Start Date: 10-12-2014	End Date: 30-09-2020

Summary of Programme Performance
Year	2015	2016	2017	2018
Programme Score	B	A	A	A
Risk Rating	Low	Major	Major	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4811609.odt
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204603/documents

A. Summary and Overview

Description of programme
Pakistan is one of the most disaster prone countries in the world, with the poorest most at risk. Protracted crises in areas of the country have also displaced millions. The five year Multi-Year Humanitarian Programme (MYHP, 2014 - 2019) was approved by the Secretary of State in 2014 and received a 12 month no cost extension in June 2018[1] (more details can be found under Section F). It is a £100 million programme and aims to reach at least two million people with life-saving assistance and early recovery activities following both natural disasters and conflict-induced displacement. MYHP delivers these results through four main pillars as summarised below[2]:
[1] See AMP project number 204603 for all documentation. Vault ID for MYHP no cost extension: 32441091
[2] Pillar I - International Office for Migration (IOM) with Food and Agriculture Organisation (FAO), UN International Children’s Fund (UNICEF), and civil society organisations HANDS (local) and ACTED (international); Pillar II: International Rescue Committee (IRC)-managed IVAP is the IDP Vulnerability Assessment Profiling, used by all organizations working in FATA to identify people and communities most in need; UN Development Programme (UNDP) and World Food Programme (WFP); Pillar IV: UN Office for the Coordination of Humanitarian Affairs (OCHA) managed PHPF is the Pakistan Humanitarian Pooled Fund which provides funding to local and international organizations to respond to new emergencies.

Since 2015, MYHP has reached approximately 2.8 million people with emergency and recovery water and sanitation, livelihoods support, protection mechanisms and shelter.[3] In addition to responding to natural disasters, it has provided emergency support to internally displaced persons (IDPs) from the conflict in the Khyber Pakhtunkhwa Merged Districts (KPMD), formerly known as Federally Administered Tribal Areas (FATA)[4], and wider Khyber Pakhtunkhwa (KP) Province.
[3] Due to the nature of the integrated phased model of MYHP and the way that outputs are set up, this figure includes some double counting of those who have received separate interventions from both the emergency and early recovery phases.
[4] The Federally Administered Tribal Areas (FATA) were a  semi-autonomous tribal region in north-western Pakistan that existed from 1947 until being merged with neighbouring province Khyber Pakhtunkhwa (KP), in 2018. In May 2018, the National Assembly of Pakistan voted in favour of an amendment to the Constitution of Pakistan for the FATA-KP merger which was presented for approval in the Khyber Pakhtunkhwa Assembly, and passed with majority vote. The 25th Amendment received assent from the President of Pakistan, after which FATA was officially merged with Khyber Pakhtunkhwa.

Current programming aligns with the UK Humanitarian Reform policy and supports UK commitments to the World Humanitarian Summit and the Grand Bargain[5]. The programme complies with the UK International Development (Gender Equality 2014) Act and ensures inclusion of people with special needs. Data disaggregation takes place on the basis of sex, age and disability by all partners. For example, this year, the programme has reached over 16,500 persons living with disability (PWD) through recovery interventions.
[5] The Grand Bargain Commitments the MYHP focusses upon are: localisation of the response and; increasing the use of cash-based transfers.

For 2018/19, £9.6 million (47%) of the MYHP budget is classified International Climate Finance (ICF). Interventions such as livelihood activities, shelter and water, sanitation and hygiene help people become more resilient to disasters. Excepting conflict and earthquakes, many of the causes of these disasters are exacerbated by climate change. Resilience to future climate change is built into the design of these interventions.

The context has changed since the business case was written. Some of the assumptions underpinning the business case design have not held true:
1. There has not been a large-scale emergency in the past two years;
2. The situation in the KPMD and KP has changed with more focus on those who have returned (rather than those who are recently displaced);
3. The operating environment has become increasingly challenging for a number of partners;
4. The government of Pakistan has published guidelines[6] for when and how foreign assistance will be requested in the event of a disaster.
  [6] Host Nation Support Guidelines for Foreign Assistance to Pakistan During Disasters (HNG). These suggest a sense of greater self-reliance and capacity than was present in previous large-scale disasters.

The first two changes have resulted in a shift from emergency response to a greater focus on early recovery and rehabilitation work. The consequences of the second two changes are yet to fully materialise but are likely to require further reflection on how and if international actors intervene in Pakistan.

Summary supporting narrative for the overall score in this review
Despite the changes in the context and associated challenges for delivery, the programme has met expectations. The programme and its partners responded to smaller scale disasters where they had an added value within two weeks. A focus on recovery was also maintained ensuring interventions continued to reach over 480,000 beneficiaries. As humanitarian needs in border areas with Afghanistan have reduced and changed, the programme’s partners have adapted their approaches whilst keeping those affected as their principal beneficiaries.

In the continued absence of large scale natural disasters, it may seem appropriate to question the continued relevance of the programme and its reactive capacity which remains an important component and capacity of the programme. Nonetheless, the risk of natural disasters, often affecting and increasing the vulnerability of the same people, remains high. If this reactive capacity to scale up an emergency response did not exist we would reduce the ability to respond to smaller disasters that remain significant but for which others do not have a response capacity. The ability to rapidly scale up to respond to a large-scale disaster would be equally affected and result in greater human and financial costs.

No.	Recommendations for the year ahead	Owner	Deadline	Tracking
1.	Better understand implications of the recently finalised ‘Host Nation Support Guidelines for Foreign Assistance to Pakistan During Disasters’ (HNG) for the programme (See also Section E – below). This to include partners sharing their analysis of how the HNG affect their response.	Humanitarian Adviser / Partners	Ongoing/ February 2019	Programme Delivery Plan (PDP)
2.	Improve DFID Pakistan understanding of the reasons why displaced people remain or return to areas of displacement to inform wider policy and programming.	Team Leader	February 2019	PDP
3.	Review the theory of change, logframe and assumptions.	Humanitarian Adviser / DPM / Results Team	January 2019	PDP
4.	Partners to specifically focus VfM analysis on effectiveness at the outcome level	Deputy Programme Manager (DPM) / VfM Adviser	February 2019	PDP

Acronyms
AAP	Accountability to Affected Populations
ACTED	Agency for Technical Cooperation and Development
BC	Business Case
BDRP	(DFID Pakistan’s) Building Disaster Resilience Programme
BISP	Benazir Income Support Programme
CHASE	Conflict, Humanitarian and Security Department
CFU	Counter Fraud Unit
DDMC	District Disaster Management Centre
DFID	Department for International Development
DPM	Deputy Programme Manager
FAO	UN Food and Agriculture Organisation
FATA	Federally Administered Tribal Areas
GoP	Government of Pakistan
HANDS	Health and Nutrition Development Society
HH	Household
HNG	Host Nation Support Guidelines For Foreign Assistance to Pakistan During Disasters
ICF	International Climate Finance
IDP	Internally Displaced Person
(I)NGO	(International) Non-Governmental Organisation
IOM	International Organisation for Migration
IRC	International Rescue Committee
IVAP	IDP Vulnerability Assessment Profiling
KP	Khyber Pakhtunkhwa Province
KPMD	Khyber Pakhtunkhwa Merged Districts
MYHP	Multi Year Humanitarian Programme
NDC	Natural Disaster Consortium
NOC	No-Objection Certificate
OCHA	(UN) Office for Coordination of Humanitarian Affairs
PDMA	Provincial Disaster Management Authority
PDP	Programme Delivery Plan
PELP	Pakistan Evidence and Learning Platform
PHED	Public Health and Engineering Department
PHPF	Pakistan Humanitarian Pooled Fund
PPA	Partnership Principles Assessment
PSEA / PIP	Protection from Sexual Exploitation and Abuse / Programme Improvement Plan
PWD	Persons with Disabilities
RELIEF	Responding to the Evolving and Long-term IDP Emergencies in the Federally Administered Tribal Areas and Khyber Pakhtunkhwa
SDG	Sustainable Development Goals
SRO	Senior Responsible Owner
TPM / UN	Third Party Monitoring / United Nations
UNDP	United Nations Development Programme
UNICEF	United Nations International Children’s Emergency Fund
UNITAR	United Nations Institute of Training and Research
UNRCO	United Nations Resident Coordinator’s Office
VfM	Value for Money
WASH	Water, Sanitation and Hygiene
WFP	UN World Food Programme
WHS	World Humanitarian Summit

## B: DETAILED OUTPUT SCORING

Output Title	Timely delivery of appropriate relief in the immediate aftermath of disasters
Output number per LF		1	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s)	Progress
1.1. Time taken for DFID partners to deliver assistance	1 month	2 weeks
1.2. Percentage of people reached who receive cash-based transfers three months or less after a disaster	25%	2%[7]
[7] NDC reached 4,061 families with cash transfers out of a total of 22,879 Households (HH) (137,274 beneficiaries) for the Karachi flood response, and reached a total of 30,000 beneficiaries under the heatwave response. No cash transfers were required for a heat wave response which primarily provided individual emergency heat stroke first aid. .

Output 1 relates to speed of the humanitarian response following large scale natural disasters (likely at provincial level). The key assumption driving this output was that (on average) natural disasters displace 3 million people annually with a smaller number displaced by conflict. This has not held true and therefore poses problems for assessing progress with the current indicators. The indicators assume that timely use of cash based transfers is essential to an appropriate response and promote one of the key commitments made during the World Humanitarian Summit as part of the Grand Bargain.

Two main responses contributed to this output in 2017/18: the 2018 heatwave (26,618 beneficiaries) and 2017/18 urban flooding (137,274 beneficiaries) responses in Karachi by the Natural Disaster Consortium (NDC)[8].
[8] Urban flooding response occurred as the last Annual Review was being written in September/October and was insufficiently advanced to be captured. Results are therefore captured in this 2018 Annual Review.

Although emergency relief has been small scale (due to the absence of major new natural disasters), this output scores an A. This is because (a) both responses were within the maximum set timelines of the first indicator; and (b) although the second indicator milestone was significantly not met this is because cash based transfers were not the appropriate response for all or many beneficiaries. However, where relevant, cash transfer beneficiaries received them within the set three month milestone.

No.	Key lessons learnt
1.	The assumption of the likely frequency of major natural disasters has not held true.
2.	Drought response and other slow onset disasters are becoming more important than the programme design foresaw.
3.	Setting a minimum threshold for the use of cash based responses, whilst relevant to broader UK humanitarian policy objectives, assumes that cash responses are always the most appropriate (and therefore value for money) response. This assumption does not always hold true. For example, in the case of the Karachi heat wave response the most appropriate response was emergency first aid for heatstroke complications.
4.	The NDC capacity to respond to natural disasters quickly (within 2 weeks) remains good. In some areas it is reinforced by District Disaster Management Centres (DDMCs) constructed by local NGO HANDS since 2013, some with DFID support. These facilities are stocked with immediate relief response supplies and logistics capacity for local communities in the event of flooding or other disaster.

No.	Recommendations	Owner	Deadline	Tracking
1.	DFID to review logframe output 1 and indicators. Further details under Section C – Theory of change.	Senior Responsible Owner (SRO) / DPM	January 2019	PDP

Output Title	Integrated post disaster recovery supported that restores living conditions and reduces vulnerability to future shocks.
Output number per LF		2	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s)	Progress
2.1. Number of people living in rebuilt houses that are more resilient to disasters	24,570	18,659 / (Male 9,432; Female 9,214; PWD 284)
2.2. Number of people with access to water, sanitation and hygiene services (WASH)	77,688	244,651 / (Male 127,078; Female 117,553; PWD 3,638)
2.3. Percentage of people reached who receive cash based transfers for early recovery	30%	15%
2.4. Number of people receiving appropriate livelihoods and food security support that assists their recovery	167,703	332,071 / (Male 233,248; Female 166,907; PWD 3,990)

Output 2 has a focus on recovery and increasing the resilience of beneficiaries by ‘building back better’ where possible. It focuses on the key sectors of WASH, shelter, livelihoods and cash.

Key points informing the overall score include:
Partners have exceeded anticipated progress on WASH. In part this is because the Pakistan Humanitarian Pooled Fund (PHPF) focuses on providing potable water by for returnees to KPMD. WASH results have also increased because of better results achieved by the joint UN consortium. Based on lessons learnt, the joint UN consortium worked with the Public Health and Engineering Department (PHED) to rehabilitate drinking water supply schemes and in helping reduce non-activity costs were able to reach more people.

The increased number of people benefitting from livelihood interventions is due to a focus on cash for work rehabilitating key irrigation infrastructure. This has secondary benefits for many additional people (‘indirect’ beneficiaries) whose livelihoods are then improved.

The use of cash based transfers in the response is significantly less than the target set but this indicator has limited value tracking progress where cash transfers are not appropriate.

Support for recovery shelter (indicator 2.1.) has continued to deliver results. However important differences remain within the NDC on how beneficiaries are targeted. This is based on a difference in approach: concentrate resource in vulnerable villages or more exclusively target vulnerable households within a village (see also Value for Money section below).

No.	Key lessons learnt
1.	Focusing on a limited number of key indicators to track progress is necessary but limiting. When the PHPF focuses resources on results not included in the key indicators it can lead to the inaccurate perception of poor performance.
2.	Field trips and discussion with downstream partners show that lessons are insufficiently documented / shared by NDC.

No.	Recommendations				Owner	Deadline		Tracking
1.	Where MYHP output indicators do not capture all results ensure broader results and context are included in the narrative of the next AR.				Humanitarian Adviser	December 2019		PDP
2.	DFID to ensure NDC lead (IOM) documents and disseminates at a minimum through consortium discussion and progress reports.				DPM	Ongoing / April 2019		PDP
3.	DFID to review logframe output 2 and indicators. Further details under Section C – Theory of change.				SRO / DPM	January 2019		PDP
Output Title		Improved access to humanitarian assistance and protection services for disaster-affected people
Output number per LF			3	Output Score			A
Impact weighting (%):			25%	Impact weighting % revised since last AR?			No

Indicator(s)	Milestone(s)	Progress
3.1: Percentage of humanitarian actors in KP/FATA reporting improved planning, monitoring and delivery of humanitarian assistance due to Internally Displaced Person Vulnerability Assessment Project (IVAP) data	50%	34%
3.2: Number of people supported with preventative and responsive protection activities	97,650	120,791
3.3: Time taken for PHPF (UN Office for the Coordination of Humanitarian Affairs, OCHA) from submission of funds to initiation of high quality projects	2 months	2-3 weeks

Output 3 refers to the ability of people (principally displaced and host communities) affected by protracted conflict in KP and the KPMD to access humanitarian aid from the programme. Indicators track progress on the quality of the response by looking at how available resources are targeted through informed use of data and speed of the response.

The output scores an A, taking into account mixed progress across the indicators. Milestones for both the protection activities (Indicator 3.2) and time taken for the PHPF partners to initiate projects (Indicator 3.3) have been exceeded. The milestone for IVAP has not been met and is less than last year. This is because it was previously calculated on the basis of IVAP website ‘hits’. For this review a qualitative approach (including key informant interviews and focus group discussions) was used[9].
[9] Progress was determined by an external mid-term evaluation of IVAP conducted in March 2018.

No.	Key lessons learnt
1.	The ability of people to access support and the indicators and milestones used to measure progress cannot be separated from the external enabling operating environment. Continuing to monitor the operating environment is key to gauging the ability of partners to progress and deliver results. See also sections on ‘Theory of Change’ and ‘Risk’.

No.	Recommendations	Owner	Deadline	Tracking
1.	IDP Vulnerability Assessment Project (IVAP): / For this AR, IVAP progress assessment relied on third party monitoring. IVAP to propose additional ways to triangulate monitoring of progress (using both qualitative and quantitative data) documenting why this is a better way to track progress. / IVAP to present and share their key findings to date and discuss with the wider DFID team if and where it could provide further added value.	IVAP / DPM	January 2019 / February 2019	PDP / PDP
2.	DFID to review logframe output 3 and indicators. Further details under Section C – Theory of Change.	SRO / DPM	January 2019	PDP

Output Title	Improved coordination and technical design of humanitarian projects
Output number per LF		4	Output Score	B
Impact weighting (%):		15%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s)	Progress
4.1: Number of research and innovation projects undertaken through Pakistan Evidence and Learning Platform (PELP) and other partners	7	5
4.2: Percentage of partners who have thorough mechanisms for analysis of cash based interventions	90%	86%
4.3: Percentage of DFID partners with well-designed beneficiary feedback mechanisms in operation which inform programme adaptation.	100%	100%

Output 4 focusses on improving the quality of the response through better systems and use of evidence. Encouraging research and innovation; seeking to incentivise the use of cash based transfers and; adaptive programming linked to improved accountability to affected populations are identified as key to this improvement. The output scores a B (moderately did not meet expectations).

Following the 2017 AR, the Pakistan Evidence and Learning Platform (PELP) was placed on a Programme Improvement Plan (PIP). Ongoing challenges mean it has not established the momentum needed and this has led to a decision to close this component of the programme. The closure is further discussed below – see sections: Risk; Delivery, commercial and financial performance.

PELP was designed as key to programme research and innovation. What is apparent is that progress on research and innovation projects is now directly linked to operational components of the programme, with partners undertaking some research themselves[10]. Other projects funded through the PHPF may have elements of innovation and testing but are not standalone projects. As quantifying these requires a degree of subjectivity they have been excluded from progress.
[10] Research includes: How cash transfers can affect health outcomes; Agricultural adaptation to climate change; Low cost flood resistant shelter; https://www.gov.uk/dfid-research-outputs/flood-resilient-shelter-in-pakistan-phase-2-evidence-based-research; Evaluation of the impact of humanitarian aid on disaster prone households. Note: Two of the five research works (underlined) are not funded but made possible by the MYHP. The MYHP through funding to IVAP and OCHA has also contributed to the FATA Vulnerability Assessment influencing wider thinking.

Bilateral partners’ reports show some rigour when implementing cash based interventions but this is not uniform. The number of PHPF downstream partners means that they have the greater challenge but if they can improve this represents an opportunity for greater systemic change.

All partners have beneficiary feedback mechanisms. These are one element of ensuring Accountability to Affected Populations (AAP) and critical to informing programme/project adaptation. Mechanisms vary but include the use of individual and key informant interviews, focus group discussions, post distribution monitoring and feedback loops to take corrective action and inform those affected. Examples of how feedback has informed interventions include: changes to post earthquake shelter design; follow up and training on mitigating termite shelter damage; additional investments in seasonal livestock vaccination; reviewing agricultural inputs and selection criteria for beneficiaries to reduce probable failure.

No.	Key lessons learnt
1.	Partners initiate research and innovation projects irrespective of whether the PELP is present.

No.	Recommendations	Owner	Deadline	Tracking
1.	Partners continue research/innovation that contributes to a pre-determined agreed consortium objective.	DPM / Partners	Ongoing / April 2019	PDP
2.	Ensure standardised reporting on disability by using Washington Group Principles to better our programme. Encourage partners to recruit people with disabilities to conduct the Washington Group questions themselves.	DPM / Partners	Ongoing	PDP
3.	DFID to review logframe output 4 and indicators. Further details under Section C – Theory of Change.	SRO / DPM	January 2019	PDP

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year
The overall impact is "Reduced impact from humanitarian disasters in Pakistan".
The theory of change is that People affected by disasters have access to timely, appropriate and good value humanitarian assistance to recover which lead to reduced vulnerability to future shocks (outcome) and this can be achieved by the following outputs:
1. Timely delivery of appropriate relief in disaster aftermath;
2. Relief and recovery which is integrated, reducing vulnerability;
3. More effective systems which help people gain access to services;
4. Improved coordination and targeting of humanitarian projects.

The theory of change itself remains largely the same but key underlying assumptions have been tested this year:

Assumption 1: Natural disasters (floods) displace an average of 3 million people a year.
The programme design followed recurrent large scale disasters and assumed that this would continue in the coming years. This assumption has not held true. The last major natural disasters happened in 2015 with an earthquake in Chitral (KP Province) and flooding in Sindh. This has meant less need for large reactive responses. For some partners this has led to longer term presence and investment in the same geographic areas and increasing (conceptual and activity type if not geographical) overlap with DFID’s ‘Building Disaster Resilience Programme’ (BDRP).

Assumption 2: The Government of Pakistan grants access for delivery partners.
The review period has seen an overall closing of civil society space. In relation to this programme it is newly articulated through the need for International Non-Governmental Organisations (INGOs) to be re-registered. To date no MYHP partners have ceased operations but it does represent a risk to the programme diverting time and attention of partners as they seek to manage potential risk.

The publication of the HNG is welcomed. They provide greater clarity of expectations of national authorities in the event of large scale natural disasters, primarily at national level. The expectation is clear: any external assistance will only be requested once local capacity is overwhelmed. In the short term there is less certainty how this will affect large non-national level natural disasters overwhelming provincial level capacity. The programme is designed to address this second level of need.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead
The overall programme remains on track and in line with the outcome and impact foreseen (detailed above). Where the programme is not on track – progress on achieving results for emergency humanitarian response to disasters – this is context driven, does not require action at the level of implementing partners but rather a theory of change and logframe review.

Explain major changes to the logframe in the past year
No major changes made.

Describe any planned changes to the logframe as a result of this review
The review highlights a number of recommendations regarding the logframe. These are summarised below:
1. Review impact weighting in the light of disasters that occur during the course of the review period three months before the next Annual Review is due;
2. Review Indicators including:
1. Indicator 1.1. Assume national authorities may request the programme to respond to ‘slow onset’ disasters and determine the appropriate date for the ‘clock to start’;
2. Indicator 1.1. Where there is a rapid onset disaster and delays occur, factor in whether these are in the control of the response or an external entity when reviewing performance;
3. Indicator 1.2. The indicator should be amended to track progress on cash based responses are systematically included in all response options analysis and this is documented;
4. Indicator 2.2. Disaggregate WASH indicator results to better understand provision of clean water versus sanitation versus lower cost but equally important hygiene promotion;
5. Indicator 3.2. Unless the title is changed there is a need to review or add an indicator to capture improved access to ‘assistance’ in addition to ‘protection’;
6. Indicator 3.3. The PHPF now transfers funds once the identified partner has received the required No-Objection Certificates (NOC) and therefore does not sufficiently illustrate whether the output is met;
7. Indicators and milestones 4.2 and 4.3. Ensure these are measurable and objectively verifiable. For example, request that partners ensure they have followed and documented decision-making referencing DFID’s Humanitarian Guidance Note: Cash Transfer Programming[11].
  [11] http://www.cashlearning.org/resources/library/397-humanitarian-guidance-note-cash-transfer-programming

In light of the 12 month no cost extension to MYHP and based on the recommendations of this review, the theory of change, logframe and assumptions will be reviewed. We will work with the Evaluation and Results team to internally assess them and then work with partners to finalise the new logframe. The logframe amendment will also need to factor in the extra time provided by the extension. It will be amended during the first quarter of 2019, building on project proposal extensions from partners to revise milestones.

## D: VALUE FOR MONEY

The business case outlines the premise that improving analysis of Value for Money (VfM) requires looking beyond concepts of ‘economy’ and ‘efficiency’ with which most partners are comfortable. As the programme enters the final two years it becomes increasingly relevant and feasible to push partners for VfM analysis at the level of ‘effectiveness’ (outcome level) and ‘equity’ (arguably equivalent to ‘fairness’ or ‘impartiality/needs based’) where the focus has not been in part because ‘effectiveness’ in particular is more challenging to quantify during the initial stages of a project.

Partner level VfM frameworks remain project management tools requiring constant updating and improvement as interventions and the environment evolve. These partner frameworks include cost drivers and allow DFID to understand VfM both at the level of the individual partners and collectively.

Cost drivers have remained consistent. Collectively these cost drivers are at two broad levels: environment/external issues over which there is less control; and project intervention/internal issues over which there is greater control. Managing risk can also contribute to mitigating cost drivers and increasing VfM.

Examples of environment/external cost drivers include insecurity and delays in access in the absence of No Objection Certificates (NOCs) from the authorities. Delays and uncertainty of access have increased. However, these and insecurity can be mitigated by, for example, changing geographical focus to areas where needs remain high, changing downstream partners or working to improve perception and therefore acceptance of humanitarian actors by national authorities. Nonetheless, ultimately, these issues are controlled externally.

Examples of project intervention/internal cost drivers include the geographical location of targeted beneficiaries (if in remote and/or insecure locations) and logistic costs related to interventions (such as warehousing and procurement). The latter, at a basic level, can and are addressed by partners sharing facilities and infrastructure. For example, NDC continues to save at least £17 per day by storing emergency stocks in the HANDS and ACTED warehouses in Sindh. For the Responding to the Evolving and Long-term IDP Emergencies in the Federally Administered Tribal Areas and Khyber Pakhtunkhwa (RELIEF) consortium transport costs have been reduced from £340 to £84 per month. Instead of hiring vehicles for the full project duration they are hired according to specific needs for traveling to the field. Whilst remote location of beneficiaries can be a cost driver this does not mean it is poor VfM if the objective is to ensure that the approach is needs based and ensures that the most vulnerable and marginalised are not excluded.

The programme continues to push economy and efficiency in particular where this applies to the project intervention/internal level whether in terms of partners having negotiated better unit costs than initially anticipated or using technology and changing approach to make efficiency gains[12]. Nevertheless, ‘effectiveness’ and ‘equity’ remain concepts that require greater focus going beyond the anecdotal and systematically quantifying and assessing.
[12] The Natural Disaster Consortium switched payments to use of mobile transfer facilities for cash for work payments and reducing the number of days for payments to be made from 15 to 5 days. The RELIEF Consortium changed their approach from establishing separate centres for protection activities to one-roof centres providing the same services at 22% of the cost.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
The MYHP continues to deliver VfM in part because of its multi-year nature. Although it cannot and is not intended to address structural causes of vulnerability and poverty it provides much needed predictability to partners allowing for a potentially faster and more appropriate response[13].
[13] Draft findings of Thematic evaluation of Multi Year Humanitarian Financing in Pakistan (VALID Economics for DFID)

Longer term support to partners also allows relationship building with authorities. Partners can position themselves in relation to the wider natural disaster response in a way that short term unpredictable funding does not allow. For example, the NDC is now a partner of choice for the Sindh and Balochistan Provincial Disaster Management Authorities (PDMAs) – both of which have recently requested and provided access for drought assessments. The multi-year stand-by agreement with the World Food Programme (WFP) continues to enable a rapid and flexible response to natural disasters in part because of the sound relationship they have with government.

In an increasingly constrained operating environment such benefits of multi-year funding should not be overlooked if the UK is to remain at the forefront of humanitarian response[14]. Given the range and frequency of natural disasters that Pakistan is exposed to, an ability to support a humanitarian response in-country in a timely and appropriate manner remains relevant. The MYHP is essential to the wider portfolio because it provides a UK capacity for an immediate humanitarian response complementing our development investments. Put simply, without pre-existing in-country capacity it is possible that despite intent to support the UK could not do so in a timely/appropriate manner.
[14] Saving lives, building resilience, reforming the system: the UK Government’s Humanitarian Reform Policy

The MYHP also represents improved VfM because action has been taken to close PELP which was not delivering to expectations whilst nevertheless having given it sufficient time for it to succeed.

No.	Recommendations	Owner	Deadline	Tracking
1.	Partners to assess outcome level results / effectiveness contracting technical assistance if required.	DPM / Results and Evaluation Team / Partner	February 2019	PDP
2.	NDC to provide a return on investment analysis of their preparedness and resilience work. This should include (a) reference to the additional logistics capacity that HANDS managed DDMCs provide; (b) different flood-resilient housing approaches.	DPM / Results and Evaluation Team / Partner	April 2019	PDP
3.	NDC to ensure a sound documented evidence base for targeting demonstrating VfM.	DPM / Results and Evaluation Team / Partner	March 2019	PDP
4.	Consider whether partners could frame assessment of ‘equity’ through the lens of ‘Accountability to Affected Populations’ and vulnerability	DPM / Results and Evaluation Team / Partner	March 2019	PDP

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation
The programme risk rating is ‘Major’ with no change since the last annual review.

DFID works with partners to maintain individual risk management frameworks. These frameworks are reviewed and updated quarterly contributing to an assessment of the wider overall risk for the programme. Risks are escalated where required.

The principal risks have remained largely the same. Where there has arguably been the greatest movement is around access and this affects the programme in three principal ways:

1. Accessing targeted operating areas: No Objection Certificates (NOCs). The authorities require NOCs be obtained by partners. Separate NOCs are required for travel and project implementation in specific geographic areas. Obtaining NOCs has remained a constant challenge during the review period. This has been the case in particular for project implementation in KPMD. For some INGO partners this has resulted in significant access challenges and delays with the need to find new ways to mitigate the risk. One example would be working with alternative downstream partners that are perceived as more acceptable by authorities. Conversely improving security situation has meant greater access and reach for some UN partners into the same areas.
2. INGO registration. The ongoing registration and appeal process for INGOs is part of a broader issue of reduced civil society space. This goes beyond MYHP partners but represents a specific risk and uncertainty for the MYHP programme. Affected partners have begun to look at how a change in consortium make-up would be managed to mitigate impact on project progress.
3. United Nations Institute of Training and Research (UNITAR) accreditation. Output 4 foresaw the funding of PELP to generate and strengthen knowledge management, provide third party monitoring and be the locus of innovation grants. UNITAR was identified as the partner to work out of the UN Resident Coordinator’s Office (UNRCO). However, the previously identified risk that UNITAR would not receive accreditation from the Pakistani authorities has been realised which has essentially stopped activity. To mitigate further risks the decision has now been taken to close this project, engage an alternative third party monitoring supplier for the remainder of the programme and to do so as rapidly as possible.

Other areas of risk that merit continued and specific focus include:

1. Fraud and corruption. This remains a key risk. With challenges in accessing remote areas, DFID relies on third party monitoring (TPM) and independent auditing to monitor and mitigate risks. Delivery chain maps are maintained and regularly updated by partners allowing DFID to map flow of funds to downstream partners. These have helped the programme team in identifying, assessing and tracking risks of fraud within the programme. TPM and independent auditing also adds an additional layer of assurance in risk monitoring, management and assets;
2. Safeguarding. The nature of the operating environment means there are risks that women, minorities and other marginalised groups and vulnerable people are excluded from activities or, alternatively, are the victims of sexual exploitation and abuse. This risk continues to be mitigated by:
  1. Partners adopting an inclusive targeting approach that overtly considers the need of the most vulnerable and, in the case of the RELIEF consortium, is reinforced by the emphasised Protection element of the intervention.
  2. In August, partners were required to detail what process and procedures they had in place to manage and ensure the prevention of sexual exploitation and abuse (PSEA). Linked to the enhanced global focus on PSEA this represent both a top down and bottom up focus from DFID for MYHP partners. DFID also organised a technical workshop for the NDC and RELIEF consortia on the use and interpretation of the Washington Group questions.

Outstanding actions from risk assessment
There are no outstanding actions from the previous risk assessment. The due diligence assessments of lead partners of the NDC, RELIEF consortia, WFP and the PHPF are being renewed and revised in light of DFID’s new enhanced due diligence guidance on safeguarding standards. Assessments will be finalised by December 2018.

The findings will:
1. Inform both the specific partner and overall MYHP risk framework;
2. Ensure compliance with DFID rules;
3. Be the basis for an action plan to be followed up by the programme team.

DFID will continue to update the overall risk matrix and engage with partners early and pro-actively in looking at mitigating strategies regularly as risk evolves.

Update on partnership principles
The Partnership Principles Assessment (PPA) is regularly discussed with the Economic Affairs Division, Government of Pakistan at the federal level. The PPA was last discussed in March 2018 during our Bilateral Assistance Talks. The PPA sets out DFID’s assessment of the Government of Pakistan’s commitment to the four partnership principles, as demonstrated through its policies and action for reducing poverty and achieving the Sustainable Development Goals (SDGs). These principles cover issues relating to human rights; financial management and corruption; and strengthening domestic accountability.

MYHP is a humanitarian programme which provides emergency assistance based on humanitarian needs of people in crises in Pakistan. It is being implemented through a number of UN and other humanitarian non-government agencies. It does not contain any elements of budget support or financial aid. The programme is part of the wider aid relationship between the UK and Pakistan, which is based on an assessment of the Pakistan Government’s commitment to our partnership principles. Although the Partnership Principles do not need to play a role in management and monitoring the programme, the future sustainability of NGO operations depends on government buy-in, collaboration, policy and financial support, and to demonstrate greater commitment to the principles, the government will need to work more with non-state actors.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial and financial issues
The programme has spent 73.7% of its overall £100 million budget. In June 2018 a 12 month no cost extension to the MYHP was approved, extending its end date to September 2020[15]. It responds to an evolving context where: (i) other funding streams are now concentrating in KPMD supporting early recovery (ii) conflict related displacement has significantly reduced and (iii) where there has been a less than anticipated need for natural disaster related emergency response. This allows for alignment with the end date of DFID’s Building Disaster Resilience Programme (BDRP). The alignment provides space for DFID to consider how future programming can focus opportunities to align humanitarian and resilience activities where appropriate, focus on a trajectory from preparedness to response and recovery through a set of integrated programmes.
[15] MYHP No-cost Extension Vault ID: 32441091

In the past year the MYHP has had a continued focus on recovery related interventions and has also delivered an emergency heat wave response in Karachi.

The NDC, RELIEF and the Joint UN Consortia under the programme submit regular quarterly reports against templates which allow DFID to closely monitor all programme deliverables (progress against work plan indicators, updates on recommendations, budget utilisation, lessons learnt). The relationship with partners remains good and they are open to discuss and accept feedback and subsequently adjust or adapt implementation. Partners then capture improvements within their reporting as these specific interventions and the wider programme evolves.

Reporting from some partners (particularly the PHPF and WFP), remains limited in terms of information and budget breakdown. Both OCHA and WFP report being confined to their global reporting structures, but this will be further explored by DFID.

Financial audited statements of partner’s country programmes are received annually. External auditors provided unqualified audit opinions for partners with one exception. In the case of the United Nations Development Programme (UNDP), the audit qualified its opinion on project expenses for costs not relating to project and unsupported by documentation. This was investigated by the UN Office of Audit and Investigations and all the recommended actions were implemented by the UNDP Country Office and certified as completed by the UNDP Office of Audit & Investigations.  No further disbursements are foreseen.

As mentioned above, fraud and corruption remain key risks. The programme team and the Fraud Liaison Officer conducted an in-depth fraud and corruption workshop for all MYHP partners during the review period. In addition, the programme team has also developed a confidential fraud log tracking system and is monitoring all fraud / allegations of frauds received through partners or other sources. In the past year, the programme team has received eight allegations of fraud and has worked with the DFID Counter Fraud Unit (CFU) in successfully closing three; another three are subject to CFU’s approval for closure, and the other two allegations remain active.

Over the last year a number of challenges have resulted in slow utilisation of allocated funds affecting forecasts for some implementing partners. While the NDC, PHPF and IVAP remain on track for allocated fund utilisation for the year, the Joint UN Programme, RELIEF and PELP have particularly struggled. Reasons for these are summarized below:

1. A delay in the transfer of funds from UNDP headquarters to joint consortium members in December 2017 meant implementation of seasonal activities was delayed. To allow the consortium to complete the implementation of planned activities, a 4 month no cost extension to February 2019 has been approved by the Head of Office[16];
  [16] Approved No-Cost Extension to the Joint UN Programme Vault ID: 36674049
2. The PELP will be closed primarily due to absence of UNITAR accreditation from the Government of Pakistan (GoP) and therefore will no longer use all allocated funds. Remaining resources will be re-profiled under the contingency reserve pillar. Despite concerted efforts from the UN and DFID, UNITAR was not able to get GoP accreditation. With less than two years remaining under the programme a decision to close down the component was formalised in September 2018;
3. Access remains the biggest challenge for the RELIEF consortium. In the absence of approved project NOCs in KPMD and non-registration of partner NGOs, the consortium has struggled to implement its planned activities. Fund utilisation for the year has subsequently been slow and forecasts for the year have not been fully met. In order to address these challenges and remaining needs in areas to which people were displaced the consortium has repositioned its work to accessible areas of KP Province.

In the absence of emergencies during the past year the MYHP has not needed to fully utilise its contingency (reserve funds) under Pillar 3. It has instead continued to focus on supporting early recovery and rehabilitation work.

Asset Monitoring:
All partners follow DFID’s asset management policy. All partners’ record assets purchased using DFID funds in their asset registers and report on these quarterly. As the programme team has been unable to travel to all project sites in remote areas, asset spot checks were being undertaken through third party monitors. This year, the programme has conducted two asset spot checks and neither reported any discrepancies.

No.	Recommendations	Owner	Deadline	Tracking
1.	RELIEF project to provide high and low case financial projections enabling the DFID programme team to plan and monitor expenditure ensuring potential underspend is identified and flagged to finance teams in time.	DPM / RELIEF	November 2018	PDP
2.	Incoming TPM firm to undertake regular asset spot checks of all implementing partners for the duration of the programme.	DPM / TPM	November 2018	PDP
3.	WFP to provide detailed budgets under the Standby agreement to better understand and mitigate cost drivers improving VfM.	DPM / WFP	January 2019	PDP

Date of last narrative financial report(s)	22-Oct-2018 [NDC]; 14-Sept-2018 [Relief]; 28-Aug-2018 [IRC-IVAP];23-July 2018[Joint UN Programme]; 03-Aug-2017 [WFP Standby]; January-2017 [PELP]; 27-Jul-2018 [PHPF]
Date of last audited annual statement (s)	September-2017 [UNDP]; 30-Sept-2017 [IRC]; 21-Dec-2017 [IOM]; June-2018[WFP]; 31-Dec-2017[UN OCHA]

G: MONITORING, EVIDENCE & LEARNING

Monitoring
The programme delivery plan (PDP) is the primary monitoring tool to review performance. In addition to quarterly progress review meetings and reviewing formal quarterly reports on progress, finances and assets, DFID also carries out a 6-monthly more detailed technical progress review every six months. This provides an opportunity to assess progress and look into best practices as well as hold more in-depth discussions on risks, finances and future projections.

TPM was built into the programme design. In the past year, TPM has been delivered through VTT Global contracted under PELP, with monthly reports being shared with DFID. With the decision to now close PELP, an alternative third-party monitoring agent has been contracted via a local supplier to continue with third party monitoring. The first round of monitoring will commence in November 2018.

This AR was led by the MYHP Humanitarian Adviser/SRO and the Programme Manager, supported by DFID Conflict, Humanitarian and Security Department (CHASE) livelihoods and shelter advisers and the programme team. Meetings took place with all implementing partners as well as members of the wider humanitarian community; progress reports from partners were reviewed. A field visit to South Sindh also helped inform the review.

Evidence
The MYHP contributes to building evidence at three different levels: global, Pakistan sub-national and technical.

At a global level, the MYHP has been one of the case studies in the evaluation of multi-year humanitarian and resilience funding undertaken by the centrally managed team. This evaluation generates important evidence for the UK’s wider humanitarian programming. It will also shape and influence DFID Pakistan’s thinking on vulnerability and resilience. It is unlikely that a separate or further evaluation of the MYHP will generate sufficient significant additional evidence to justify the investment. Instead resource should be used to focus on ensuring partners assess project level outcomes.

At the Pakistan sub-national level, MYHP support to IVAP and OCHA contributed to the FATA (KPMD) vulnerability assessment. This was undertaken jointly with the World Bank. OCHA focussed on quantitative and qualitative data collection at the household and community level. The World Bank focussed on the institutional level. The assessment helped the wider humanitarian and development community in understanding the changing context, identifying the gaps, and in targeting assistance to those in need. It was also used to inform the design of the new DFID KPMD programme.

Technical level evidence has been generated by the MYHP through ongoing project implementation. Examples include published research on flood resilient housing[17] . This looked at specific typologies of construction that would withstand flooding focussing in particular on low-cost improvements to traditional/existing buildings. The research results have informed the NDC and their approach to ensuring best possible VfM in recovery housing design.
[17] Published in early 2018 with support from the DFID Research and Evidence Division/South Asia Research Hub: https://www.gov.uk/dfid-research-outputs/flood-resilient-shelter-in-pakistan-phase-2-evidence-based-research.

Future technical level evidence may be generated in other areas such as the Community Led Total Sanitation efforts undertaken within the NDC with the aim to better understand outcomes and impact of reduced prevalence of diarrhoea on morbidity and mortality in the target communities.

Learning
The TPM firm VTT Global worked for seven months (January – July 2018) in the field. Given challenges with regard to reporting and with the closure of PELP, DFID has asked PELP to develop a comprehensive summary TPM report highlighting key messages around what has worked and what has not, allowing the programme to adapt, learn and improve.

Even without PELP the MYHP continues to provide an opportunity to further push learning through operational research and further test what preparedness can provide in terms of a return on investment in the event of large scale natural disaster. This lesson learning and the further analysis that we will expect from partners on effectiveness and equity dimensions contributes to VfM of the current programme, will be relevant for future programming and has potential benefits for wider DFID programming.

The BDRP has been running since 2016 and the learning from both programmes has highlighted a number of complementarities between the two programmes including geographical focus and similar partner activities such as focus on shelter and food security. The teams have focused on trying to better identify and manage the areas of overlap and similarity. This process led to the decision to extend the MYHP so as to develop a new aligned programme going forward.

Progress on recommendations from previous reviews
Key recommendation 1. Cross-consortia learning: “DFID will consider clear mechanisms for cross-consortia learning, once the PELP is more established”.

This recommendation has not been fully met via PELP. Nonetheless, regular coordination between consortia has resulted in exchange of learning helping to improve implementation strategies, for example, between RELIEF and the Joint UN consortia who are working in the same geographical area. Further improvement is required to ensure more effective learning by BDRP and MYHP on complimentary areas. This will help inform programming beyond 2020.

Key recommendation 2. Market systems analysis: “DFID will request all partners to use a clear market analysis to inform recovery, based on needs and resources of the communities affected.  This will allow for livelihoods activities to be delivered at scale, and to ensure that the skills learnt are the most appropriate for the communities. By June 2018, DFID will hold a workshop for all partners to clarify the use of market analysis, with partners expected to use them more systematically and consistently by the end of 2018”.

Partners have made better use of market analysis to inform their recovery interventions, based on needs and resources of the communities affected. RELIEF conducted extensive studies in identifying market trends and associated livelihood opportunities in target areas. In addition, RELIEF relied closely on market systems analysis conducted by government stakeholders to inform food security and livelihood activities, where available. Pre-market analysis carried out by NDC for food security and livelihood interventions helped inform action in three districts of Sindh. Similarly, the Joint UN Consortium undertook market studies which helped identify employment opportunities for skilled-labour (inside the tribal districts and in adjacent settled districts) and therefore design of technical and vocational training packages for the youth.

Key recommendation 3. Scalable cash response: “DFID will consider whether humanitarian programmes can be harmonised with existing cash-based social safety net systems in order to use Government systems to deliver humanitarian cash in the longer-term.  The humanitarian team will work more closely with DFID Pakistan’s support to the government of Pakistan’s National Cash Transfers Programme to understand whether and how these can be linked”.

This was not specifically actioned as initially foreseen. However, a DFID-funded study on Shock-Responsive Social Protection Systems strengthens the evidence base as to when and how social protection systems can better scale up in response to shocks in low-income countries and fragile and conflict-affected states. It includes a Pakistan case study focussing on the Benazir Income Support Programme (BISP)[18] which has also generated a policy brief[19]. Both can inform our understanding of the possibility of working with existing social protection systems when responding to future humanitarian needs and therefore future programming.
[18] Under DFID’s Pakistan National Cash Transfers Programme (PNCTP), DFID is providing up to £279 million in non-budget support financial aid and £21 million in technical assistance to the Benazir Income Support Programme (BISP). BISP is a government programme, which provides basic income support to poor women and their families.
[19] Watson, C., Lone, T., and Barca, V. (2017) ’Building on social protection systems for effective disaster response: the Pakistan experience’. Policy Brief. Oxford Policy Management, Oxford, UK.

Key recommendation 4. Continue strengthening approaches to protection and gender-based programming: “DFID will revise protection indicator (3.2), after this Annual Review, so that all partners report regularly on their protection-related interventions.  This would allow DFID to track those engaged in protection mainstreaming rather than standalone programming”.

This recommendation was not actioned as discussion with partners suggested that existing protection related reporting from partners was increasingly adequate. It will however be reviewed as part of the recommendations made for the overall programme logframe and theory of change.

Key recommendation 5. OCHA in the longer-term: “DFID will consider how it can support OCHA in the longer-term.  Retaining a skeleton presence at a minimum of P4-level would allow for scale-up in the event of a crisis. Through advocacy and partnership, DFID will ensure that OCHA’s presence in country continues to reflect the extent of humanitarian needs across Pakistan”.

OCHA in country presence will continue to downsize due to decreasing humanitarian needs in the KPMD region. DFID Head of Office and Humanitarian Adviser discussed plans with the Emergency Relief Coordinator and OCHA Head, Mark Lowcock, in his recent visit. Current plans are for transition to a Humanitarian Advisor Team embedded in the UN Resident Coordinator’s office in 2021.

Key recommendation 6. Beneficiary feedback mechanisms need to take into account community engagement more systematically: “Consortia-wide mechanisms should be better developed so that learning is incorporated across each consortium.  This will also allow beneficiaries to give feedback on the performance of the consortium as a whole, rather than just the individual project interventions.  By June 2018, DFID will use research and evidence commissioned via PELP to support this process”.

Partners have beneficiary feedback mechanisms. Further work is required to determine how in the absence of the PELP we can ensure that we have measurable and objectively verifiable well-designed feedback mechanisms that can be used to provide an assessment of consortia as a whole (where relevant).

Key recommendation 7. Research and develop new Business Case: “Based on the Annual Review process, and the need to have a seamless transition once the MYHP is completed in mid-2019, the humanitarian team will begin research for a new Business Case in early 2018.  For this, DFID is commissioning an impact study to be completed by mid-2018.  The new BC will be premised on the need for links between humanitarian interventions and resilience (including interventions under the BDRP), and on the changing context in Pakistan.  By September 2018, the draft BC will be completed, and submitted for approval”.

Following a 12 month no-cost extension the MYHP will now come to an end in September 2020. The extension to MYHP in parallel to phase two of BDRP will maximise opportunities for lesson learning and strengthening relationships with key provincial governments. Both programmes are now aligned, and the team has started to address areas of overlap through joint monitoring visits, coordination between implementing partners (especially in common geographical areas) as well as joint needs assessments.

The substance of the recommendation remains valid. The primary objective is to inform the new business case, which will allow for the flexibility to provide emergency response whilst also responding to global commitments from the World Humanitarian Summit (WHS) and the SDGs. This approach will allow for going beyond just using humanitarian response i.e. it will further strengthen government and local systems to invest in disaster preparedness, response and resilience. The new business case is to be submitted for Ministerial approval in September 2019.