Type of Review: Annual Review

Project Title: Supporting Stability and Promoting Democracy in the Occupied Palestinian Territories

Date started: 09/2013	Date review undertaken: 04/2014

## Introduction and Context

What support is the UK providing?
The UK is providing £2m from 2012/13 to 2014/15 to help Palestinian civil society become more inclusive and effective at holding the Palestinian Authority (PA) to account. The programme uses a mix of training and grant funding to help Palestinians understand and influence those that are spending money and making decisions on their behalf. / Following a competitive procurement exercise, the British Council was chosen to lead a consortium of non-governmental organizations, called Tajaawob (“responsiveness” in Arabic) in implementing the programme. Tajaawob pilots new or improved mechanisms and spaces for dialogue, while also providing dynamic, transformational training to create a cadre of highly skilled advocacy activists, and whose voices are raised through media.

What are the expected results?
The overall impact of the programme is a negotiated outcome enabling a viable, contiguous and democratic Palestinian state, alongside a secure and prosperous Israel. / The expected outcome of the programme is that Palestinians are better able to hold their authorities to account through a more inclusive and effective civil society. While the individual outputs of the programme revolve around three main areas 1) Strengthened advocacy skills in Palestinian Civil Society through the delivery of advocacy cycle training with individuals and communities 2) Authorities able to understand and engage with communities and Civil Society Organizations through new and improved mechanisms 3) Strengthened capacity of Palestinian media to reflect community-led issues of marginalized voices, including women and youth.

What is the context in which UK support is provided?
UK policy (in line with international law and significant international consensus) is that the Occupied Palestinian Territories (West Bank, Gaza, East Jerusalem) or ‘OPTs’ constitute the land that should – as a result of negotiations between the parties – form the basis for a future Palestinian state. The UK’s ultimate goal is the creation of a sovereign, independent, democratic, contiguous and viable Palestinian State living in peace and security side by side with Israel. As part of this, the DFID programme is supporting the development of a peaceful, functioning Palestinian state and society. / The development context in the Occupied Palestinian Territories (OPTs) is characterised by conflict and fragility. There have been two violent Palestinian uprisings against the Occupation, and Israel has suffered periods of bombings and periodic rocket attacks against its population. An escalation of violence in 2009 led to significant numbers of deaths and destruction in Gaza. / The lack of a viable political horizon given the failure of the current round of the Middle East Peace Process (MEPP) negotiations to end Israel’s occupation and facilitate the establishment of a sovereign Palestinian state has only compounded popular disenchantment. CSOs once served as the organiational focus and expression of political, social and eceonomic life in the OPTs. However, these CSOs have been gradually weakened by the continuing impact of the occupation and movement nad access restrictions, which have resulted in a more fragmented and demobilized Palestinian society. / In addition, current negotiation between Palestinian factions over possible reconciliation still has unforeseen consequences over CSOs and communities in the West Bank and Gaza. Nevertheless, enhancing the advocacy capacity of CSO’s and marginalised Palestinian communities, and supporting public policy dialogue will be all the more important in this context.

## Section A: Detailed Output Scoring

Output 1: Strengthened advocacy skills in Palestinian Civil Society through the delivery of Tajaawob advocacy cycle with individuals and communities
Output 1 score and performance description: / Outputs met expectation - A
Progress against expected results: / Output Indicator 1.1 Baseline (2013) Milestone (2014) / No. of advocacy cycles which have reached: / Stage 1 (definition & capacity building) / Stage 2 (advocacy design and delivery) / Stage 3 (embedded) Planned 0 Stage 1 (3) / Achieved Stage 1 (3) / Stage 2 (3) / Output Indicator 1.2 Baseline (2013) Milestone (2014) / No. of people who have completed the six month Communications and Advocacy Leadership Programme (CALP) (of which women) Planned 0 15(6) / Achieved 13 (5) / Output Indicator 1.3 Baseline (2013) Milestone (2014) / % of participants who have completed CALP and report at least satisfied with the training (women) Planned 0 60% (60% women) / Achieved 77.5% (56% Women) / Output Indicator 1.4 Baseline (2013) Milestone (2014) / % of participants of advocacy training who report at least satisfied with the training Planned 0 60% (60% women) / Achieved 82% (80% Women) / Output Indicator 1.1: No. of advocacy cycles which have reached Stage 1 (definition & capacity building) / Advocacy cycles are advocacy skills training packages that are designed to follow trainees and accompany them through different stages during the programme to ensure continuity of skills learnt. The communities that were selected for this programme were a mixture of marginalized communities from Areas A B and C (namely Um Salamona, Frush Beit Dajan, Mograqa, Azzoun, Hableh and Qalqilya). In these 6 communities, Tajaawob worked on establishing representative community committees through a process that identified those who were the most dedicated to address the problems those communities faced, making sure that women and youth were represented. These committees then underwent training and were provided with assistance throughout the different stages of advocacy cycles: Stage 1 consisted of training and capacity building on strategic planning, codes of conduct, citizenship, gender, accountability and transparency, budgeting and planning. It also included an intense 10 day ‘Kumi’ (‘stand up’ in Arabic) training process for the whole committee to resolve conflicts within communities. Issues relating to the role of women in community decision making featured strongly in this training and there is evidence that attitudes to women’s engagement have shifted in many cases. / The target for this output was to train three community committees to stage 1 capacity. However, by the end of the year, all six committees completed stage 1, and three committees have already started on stage 2 – working on the design of advocacy campaigns towards authorities. / Output Indicator 1.2: No. of people who have completed the six month Communications and Advocacy Leadership Programme (CALP) (of which women). / The Communications and Advocacy Leadership Programme (CALP) is a component of the programme that focuses on training already existing activists and providing them with the tools to design and implement advocacy campaigns. Some of the persons selected for CALP are from the community committees that Tajaawob identified, whilst others were selected through an application process. The CALP graduates use the skills learnt to develop engagement tools for their communities. / The target for this output was for 15 individuals (of which six at least are women) to have completed six months of the CALP. The CALP programme is very intense and demanding involving 2 week-long residential training courses, as well as ongoing activities for the intervening 5 month period. Only 13 people (of whom five were women) have completed the six months of CALP and continued to engage in the ongoing mentoring, coaching and peer review sessions. These 13 are all engaged in innovative advocacy campaigns in the West Bank. Because of a relatively higher drop-out rate than anticipated, this output moderately did not meet expectations. / Output indicator 1.3: % of participants who have completed CALP and report that they are at least satisfied with the training (women) / This output indicator has been met. 77.5% of participants enrolled in the CALP have expressed their satisfaction compared to a target of 60%. However, only 56% of women were satisfied with the training. The programme’s assessment is that the course was more challenging for some women as they tended to have more domestic duties than men, in addition to their work requirements. / Output indicator 1.4: % of participants engaged in advocacy training who report they are at least satisfied with the training / The level of satisfaction of participants in the community advocacy training was very high with over 80% being highly satisfied or fairly satisfied. The extent of satisfaction among women participants was similarly high. Qualitative feedback on the impact of training is provided below in the “feedback from beneficiaries” section. / Recommendations: / Tajaawob to produce action plan for improving participation in the CALP training sessions to meet the 2015 target be end of July 2014. / Tajaawob to undertake a gender analysis of the CALP training to identify specific barriers to women’s engagement by July 2014. / Impact Weighting (%): 50% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: Authorities able to understand and engage with communities
Output 2 score and performance description: / Outputs met expectation - A
Progress against expected results: / Output Indicator 2.1 Baseline (2013) Milestone (2014) / No. of engagement mechanisms presented to authorities Planned 0 2 / Achieved 3 / Output Indicator 2.2 Baseline (2013) Milestone (2014) / No. of engagement mechanisms which are receiving feedback (being utilized) from public Planned 0 1 / Achieved 1 / Output indicator 2.1: No. of engagement mechanisms presented to authorities. / Under this output, Tajaawob is to approach government bodies responsible for the delivery of services to the people and present platforms where Civil Society and communities can engage with those authorities. / Tajaawob has been working with three Ministries: / Ministry of Education (MoE): the Ministry of Education is working with Tajaawob to substantially reform the Parent Councils mechanism as a means of engaging citizens with the ministry and school governance. This Ministry is looking at ways to improve social accountability as a guiding principle, and has agreed with research findings from Tajaawob concerning the presently very limited role of Parent Councils. MoE has agreed to a changed terms of reference for the councils and to build the capacity within the Ministry to handle feedback from them. / Ministry of Social Affairs (MoSA): The programme is working closely with Ministry of Social Affairs (MoSA) on a Beneficiary Forum for social protection issues. The Beneficiary Forum is a space in which social welfare beneficiaries are able to engage with the MoSA. Tajaawob helped the ministry agree a structure and geographical management for the Forums and is soon to establish the Beneficiary Forums formally at community level. / Ministry of Planning (MoPAD): Tajaawob engaged with MoPAD on improving engagement with citizens on the development of the national plan is underway but there has been less progress. / Meanwhile at community level, the committees in Qalqilya governorate have developed ‘Citizen Scorecards’ for services provided by the municipalities (Hableh, Azzoun and Qalqilya city) and also for the Qalqilya governorate itself. These scorecards were developed using a political economy analysis produced by Tajaawob for the lijnah and are starting to be used to obtain feedback from communities. / Output 2.2.: No. of engagement mechanisms which are receiving feedback (being utilized) from public / Local committees established by Tajaawob are starting to facilitate a new relationship between citizens and the Ministry of Social Affairs. For example the Hableh committee or lijnah facilitated an event where the Ministry took questions from citizens on the cash assistance programme among other social protection policy areas. In the committee at Um Salamona, Ministry officials were asked about the selection criteria for the cash assistance programme. This represents a culture shift in how the Ministry engages with local communities and bodes well for future involvement in the Beneficary Forums. Therefore this output has met expectation. / Recommendations: / Tajaawob to identify additional Authorities to approach concerning the creation of new engagement mechanisms by end of July. / Tajaawob to provide DFID with a clear strategy for ensuring the long-term sustainability of the engagement mechanisms; 1st draft by December 2014 and final draft by February 2015. / Impact Weighting (%):20 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Strengthen capacity of Palestinian media to reflect community-led issues of marginalized voices, including women and youth.
Output 3 score and performance description: / B- Outputs moderately did not meet expectation
Progress against expected results: / Output Indicator 3.1 Baseline (2013) Milestone (2014) / No, of training sessions on outreach to marginalized communities delivered to media houses Planned 0 2 / Achieved 5 / Output Indicator 3.2 Baseline (2013) Milestone (2014) / No. of discussions and debate shows between CS and authorities broadcast on radio and TV. Planned 0 5 radio debates broadcast by the trained radio stations / Achieved 2 broadcast radio shows / Output indicator 3.1: No. of training sessions on outreach to marginalized communities delivered to media houses. / This output aims to train local media to report effectively on issues affecting the most marginalised groups, while equipping the authorities to engage with an interactive media platform that acts as an interface with the public. Prior to the project, radio shows had not covered issues of community concern, with journalists focusing on national issues. Tajaawob worked with five radio stations (Raya FM radio; Nagham- Qalqilia; Radio Bethlehem; 2000-Bethlehem; Al-Wan) to build up their editorial capacity and help them identify community stories. Tajaawob provided training, coaching and ongoing mentoring of these stations in three areas: package making, social media training, editorial radio station training. Achievements under this output substantially exceeded expectation. / Output indicator 3.2: No. of discussions and debate shows between CS and authorities broadcast on radio and TV. / Tajaawob piloted the first radio debate show about communities in April 2014. The radio show, called ‘Tajaawob’, will be broadcast on Raya FM fortnightly on Tuesday afternoons. Each show will cover a number of issues facing marginalised communities in the Tajaawob programme and each of the trained radio stations will be responsible for helping produce sections of the show. Only two shows have been broadcast at the time of this Annual Review, however, more shows are going to be broadcast in June 2014. Therefore, as a result of the shows starting later than expected, this output moderately did not meet expectation. / Recommendations: / To receive a plan from Tajaawob by August 2014 detailing their TV targeted output for 2015; including what it will consist of and how local media houses will be involved in the production of the TV broadcast. / Impact Weighting (%):30 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? N / 1.2 Overall Output Score and Description: / A- Outputs met expectation / 1.3 Direct feedback from beneficiaries / Feedback from beneficiaries suggests that the community committees’ model is proving very successful in providing a focal point for the representation and articulation of community needs. As such it is filling a gap in hitherto unorganised communities, and establishing a strong foundation for improved relations with authorities. / The response of municipal authorities to the lijan mahallieh (community committees) is also positive – with mayors attending events and taking note of the legitimate authority the committees have in advocating for community improvements. / Beneficiary Feedback / Survey of Radio station training in editing Wood Rabaia, from Tareeq Al-Mahabeh FM said “The training was a success- it has opened my mind to many new ideas, the brain storm that we had with the trainer opened my mind to new concepts for new programmes.” / Azzoun lujnah We have come in contact with our potential – there is great opportunities and untapped potential, we can set a model. / Hableh lujnah My ideas about women changed – I learned she is allowed more than I thought. To go out, to work, to study. / Mograqa, Gaza City A male from Moghraqa Said "The Strategic Planning training (helped me) plan for my community and be able to prepare action plans for all our interests and issues . / Um Salamona capacity building training (KUMI)feedback A female said: “The training allowed us to study the reality of Um Salamona and prioritize our needs through preparing an executive plan for the community committee.” / Qalqilya capacity building training (KUMI)feedback A male said: “The workshop met my expectations, especially in terms of reaching a group of goals by the community committee; based on our strategic plan for Qalqilya, which aims at reaching an advanced and developed community.” / Hableh capacity building training (KUMI)feedback One female participant said: “These workshops have introduced to me the importance of women’s participation and role in society” / Azzoun capacity building training (KUMI)feedback A male participant said: “KUMI has enabled me to recognize the concept of social partnership and active participation.” / MoE project / [feedback from ministry officials on report] Ms. Ilham Sami, Director of Non-Academic Directorate at MoE, said: “There is a misunderstanding by parents of the role of parent councils. The concept of parent councils is connected in the social deep culture by the male/female roles in society.” “The Ministry of Education lacks the capacity in resources to cover all parent councils in the West Bank. We have more than 2000 schools, and the ministry’s central offices in the Palestinian cities cannot make sure of the accuracy of all reports from PCs due to the lack in human resources.”
1.4 Summary of overall progress / Overall, the programme has delivered well for the first year meeting expectation on most of the output indicators. Tajaawob has delivered successful training courses (output 1), it has established or improved three engagement mechanisms between communities and authorities (output 2) and has increased the capacity of local media houses while broadcasting locally produced radio shows by the trained media houses on community issues (output 3). However, there is a need to work on improving women’s engagement in the training sessions, and also ensuring that Tajaawob achieves its media targets for 2015.
1.5 Key challenges / One of the biggest challenges to the programme is in making sure that any intervention in strengthening civil society can be effective and sustainable given context of the occupation. The West Bank is currently divided into three administrative divisions: Area A with 18% of the land under the full control of the PA; Area B, with 21% of the land under Israeli security control and Palestinian administrative control; and Area C, with 61% of the land placed under full Israeli security and administrative control. This complex political context affects many of the marginalized communities that Tajaawob works with, as those under Area C (under Israeli military control), face significant challenges in access to services, and lack infrastructure and utilities. Tajaawob’s challenge is therefore in trying to help communities address these shortages and engaging stakeholders in a productive manner. / In terms of implementing the programme, Tajaawob relies on establishing and sustaining trusting relationships with communities and authorities. The projects have taken time to get started and the team reports that they are just now, after 8 full months of implementation, beginning to see impact and improvements in social accountability. The programme team feels that the time available for realising the full benefits of the early investments in capacity building and mobilisation needs to be further assessed and the possibility of an extension to the programme considered. / Further, the challenges emerging from working in a large consortium with six partners in the Palestinian context require sensitive handling. Tajaawob’s working methods, along with the output-based financial management system DFID has introduced, represent significant change for civil society organisations and in some cases this is very challenging to implement. The programme has simplified its management and reporting structures in response to local capacity concerns and also reduced the dependence on written feedback e.g. for field work in favour of creating spaces for the team to provide oral feedback.
1.6 Annual Outcome Assessment / # Indicator Baseline (2013) Milestone (2014) / 1 No. of case studies which demonstrate improved engagement of Palestinian Civil Society and which meet DFID quality assurance 0 1 / 2 % of people who have completed the Communications and Advocacy Leadership Programme (CALP) and report having used the training in a practical way 0 0 (however, the case study evidences that 8 participants are using the training actively in advocacy campaigns) / The assessment is that the Outcome is moderately exceeding expectation, as Tajaawob has produced a draft case study on the first cycle of the CALP programme, and already a good number of the first CALP programme participants are actively engaged in advocacy campaigns as a direct result of the CALP training (outcome indicator 2).

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: N / The project is currently underspending by over 25% of the estimated cost. This is attributable to a number of factors, including limited capacity of the partners during the inception period for estimating and budgeting spend. In addition, there was a time lag before the British Council identified this (due to the delay before quarterly invoices were received from partners). A new Operations Manager has been appointed to support the consortium to strengthen their financial management. / There is also a recognised tendency among Palestinian civil society to overestimate their budget needs, based on historical practices of generous grant funding by the international community. The degree of ‘slack’ in a budget takes several reporting cycles to identify and tackle comprehensively. / Further, as most of the work is community-led, community committees needed to identify their needs and priorities before scheduling advocacy training activities. This took longer than expected but did not prevent the project from performing to expectations. / 2.2 Key cost drivers / The funds for this programme are channelled through an implementing partner. As stated in the Business Case, the costs of staffing and running the programme has represented a significant cost driver, in addition to the Communications Advocacy and Leadership Programme (CALP) training, which is one of the most costly activities in the programme. This programme is about effecting change and as such requires building trusting relationships through mobilisation efforts, accompaniment and explicit capacity building and training. This is an intensive use of human resources. / Recommendations: / Tajaawob will work to continue building the capacity of the consortium to estimate, plan and forecast spending, and to rework the programme costs for the remaining months of the programme, within 6 weeks of the Annual Review. This has already begun with the recruitment of the Operations Manager. / Tajaawob will review the management structure of the programme in the light of capacity gaps and ensure it is fit for purpose, eliminating any duplication or areas that do not add value. / Pending the above actions, DFID to consider a no-cost extension after the end of the programme to support delivery of the outcome. / 2.3 Is the project on-track against original timescale: Y

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / As stated in the Business Case, the Theory of Change (ToC) for this programme is based on helping Palestinian civil society to be more inclusive and effective at holding the PA to account, including making progress on the PA’s anti-corruption agenda, a key priority for DFID. While there are no foreseeable major changes to our assumptions, there is a need to recognize that peace negotiations have stalled, and reconciliation negotiations are underway between Palestinian factions, these factors ensure, make the situation remains very fragile. As such, the evidence suggests that the difficulty lies in identifying where policy decisions take place, and where they can be influenced. / The majority of issues that were identified in the Business Case ToC have been identified by the programme. One area that could be taken forward is on improving oversight of the government budget, thereby tackling more directly issues of corruption and improving accountability as a whole. / 3.2 Where an evaluation is planned what progress has been made? / An evaluation is planned for the end of the programme. DFID has been working with Tajaawob on identifying the questions that will form the basis of the TORs. These will then be finalized in July 2014 so as to tender before the scheduled end of the programme in March 2015.

4. Risk
4.1 Output Risk Rating: the overall output risk rating of the project is Medium / 4.2 Assessment of the risk level / Assessment of risks as outlined in Business Case are set out below – Our assessment is that the risks in the Business Case have been mitigated in the contracting of the management of programme. The additional potential risks around the programme since its implementation has been the volatile political context, with stalled peace talks and reconciliation negotiations between Palestinian factions. However, it is the view that these risks only reinforce the importance and significance of this risk, and therefore is not seen as a threat to the programme’s implementation. / Risk Description Impact Probability Mitigating Actions Residual Risk / Contractor Managed Programme / Contractor unwilling to experiment with innovative ideas to deliver the programme outcomes. Medium Medium The Terms of Reference for the procurement of this programme included a criterion on innovative approaches which resulted in the formation of a consortium of NGOs. Low / Civil society organisations with a track record in working with international organisations and donors over those with stronger connections to community structures are favoured. Medium High DFID has specified the importance of a broad range of civil society organisations with close links to communities as part of the procurement criteria as evidenced by the selection of Palestinian organizations that have good ties and links with local communities at the grassroots levels such as Palvision, Aman and Mifrah. Low
Risk of funds not being used as intended / Low; A significant attribute of VFM management for Tajaawob is that it is managed and financed on the evidence of outputs of its partners. Therefore, the British Council, which manages the consortium of partners, reimburses consortium partners on the basis of demonstration of outputs or deliverables. / 4.4 Climate and Environment Risk / The Business Case sets out two potential entry points and opportunities to promote environmentally sustainable and climate smart development 1) Holding the PA to account for its climate strategy 2) Ensuring the working practices of CSO and NGO partners are environmentally sustainable and have a positive impact on climate. / Tajaawob has worked on two fronts: / Working with communities on environmental issues that affect them – including prioritizing problematic issues they face such as waste water management. / Embedding environmentally friendly working practices within the project while also sharing resources, such as ‘car-pooling’, office space, using recycled paper and sharing documents electronically rather than printing them, recycling materials, to fulfil their obligations to the environment. / There is a possibility that a third front will materialize: / Three trainees of the CALP are planning to launch environmental campaigns.

5. Value for Money
5.1 Performance on VfM measures / DFID Palestinian Programme’s Value for Money strategy contains commitments to appraise and monitor value for money throughout a project’s life through the use of unit costs for inputs (economy), outputs (efficiency) and outcomes (cost effectiveness). For this project, these unit costs translate into the following: / Economy: Cost of training activities compared to other training activities in OPTs. Admin costs below 15%. The target was to keep admin costs on all three outputs to a maximum of 15%. On the first output, admin costs were substantially below the 15% mark, however, on output 2 and 3 this threshold was crossed. This was the result of the difficulty by consortium partners of sharing financial management and overhead costs during the first year of the programme. Nevertheless, the average of admin costs over the three outputs only slightly exceeded at 15.17%. In addition, the British council is committed to improving Value for Money and will review the admin costs in the light of a review of the overall budget in order not to exceed the 15% limit over the remaining timeframe of the programme. / Efficiency: Cost of training per person compared to other training activities in OPTs: Overall, the cost per training per person ranged between 350 USD to 820 USD. In another programme currently being implemented by DFID Palestine programme, the total cost per day of training per person using local consultants was between 406 USD (excluding night boarding) and 634 USD per person per day. Therefore, overall, the costs of training are similar to other training costs in OPTs, but the high quality of the CALP training and the use of international consultants was the reason for the high costs of one the training elements. / Cost effectiveness: Cost per “case study” which demonstrates improved civil society engagement. The case study demonstrates that a number of the CALP graduates are already actively using their advocacy training skills. However, it is too early to demonstrate cost effectiveness of the case study. A revised case study for the CALP will be produced at the end of the programme after 2 further CALP cycles have been completed. / Economic return: Although it is not possible at this stage to estimate the Net Present Value of the project, this will be done in the evaluation using data gathered from the monitoring system. In particular, the economic impact of the PA policy changes resulting from the project will be estimated and compared with their cost. The extent to which further policy changes can be expected from the project after its end will also need to be estimated. / Because Tajaawob is managed and financed on the evidence of outputs, DFID has an the opportunity to challenge results. This marks a significant change for Palestinian NGOs that are used to receiving funds upfront on a grant-funding basis. / 5.3 Role of project partners / Partner organisations in Tajaawob are expected to contribute across all projects, so that the package of support provided to communities helps them bridge the gap with the authorities. This is working better with some partners than with others. Each partner also has a lead on one or two projects and on sectoral areas. The programme offers a package of support that goes well beyond the more usual capacity building projects in Palestine. Tajaawob is supporting the emergence and strengthening of an authentic voice from within civil society and then accompanying communities to advocate for change with authorities through the varied experiences and networks of our consortium. / AMAN  Leading on MOSA project on social accountability in the cash assistance. /  Leading on three community projects in Qalqilya and Mograqa projects /  Thematic lead on anti-corruption issues – working on a citizen scorecard approach in Qalqilya. / BBC Media Action  Leading on building capacity in media houses for amplifying the voice of marginalised /  Leading on media training and social media use within the consortium and with Tajaawob partners and beneficiaries /  Media production – Hur el Kalam TV programme and ‘Tajaawob’ radio show /  Responsible for Tajaawob website and FB page / British Council  Programme management. / Monitoring and Evaluation. /  Political economy analysis and advice / Financial management / MIFTAH  Leading on KUMI community change management and conflict management approach, supporting the lijnah mahallieh in working together, and developing consensus around community needs /  Leading on work with the Ministry of Education on improving Parent Councils /  Thematic lead on issues relating to women / Oxfam GB  Leading the CALP programme /  Providing policy advice /  Leading on service mapping work for East Jerusalem / Palvision  Lead for mobilising and supporting communities /  Thematic lead on issues relating to youth /  Leading on communications and innovation / 5.4 Does the project still represent Value for Money : Y / Efforts are made to ensure VFM in activity management and financing. These include working against the prevailing culture of hosting training and workshops in expensive hotels in favour of running events within communities and more modest venues outside Ramallah. Further work is anticipated to reduce duplication of effort resulting from the consortium partner structure, based on learning from the partnership that has operated in the past year. / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / This programme does not involve providing financial aid to government so no conditions apply. Nevertheless a country level assessment of the Partnership Principles was carried out in April 2014 and found that the PA is delivering on the partnership principles under difficult circumstances. Of particular importance to this programme is the fourth commitment on ‘strengthening domestic accountability’; the PA has produced a Palestinian National Development Plan that sets out commitments to Palestinians in areas of service delivery, and at the sector level line Ministries have produced strategies that commit to improving accountability. In addition, the planning process involved consultation by government with various civil society groups. / The last Parliamentary elections took place in 2006 with Hamas winning with a significant majority. However, since the Hamas takeover of Gaza and breakdown of political relations between Palestinian parties, there is currently no Palestinian Parliament. The PA governs the West Bank, while Hamas controls the Gaza Strip. The prospects of elections are deeply connected to the issue of reconciliation between Hamas and Fatah. There are currently efforts of reconciliation between the two parties that are aiming to set up an "independent government" of technocrats within the coming weeks, with a view to hold parliamentary and presidential elections shortly afterwards. This would signify a dramatic shift in domestic accountability. / As part of this programme DFID will monitor the fourth commitment in relation to this programme, in tandem with the country level assessment of the Partnership Principles, that is carried out every four months.

7. Conclusions and actions
The programme is performing well at both output and outcome levels. To ensure the successful implementation of the programme in the second year the following actions should be taken: / On the Management of the Programme: / Tajaawob will work to continue building the capacity of the consortium to estimate, plan and forecast spending, and to rework the programme costs for the remaining months of the programme, within 6 weeks of the Annual Review. This has already begun with the recruitment of the Operations Manager. / Tajaawob will review the management structure of the programme in the light of capacity gaps and ensure it is fit for purpose, eliminating any duplication or areas that do not add value. / Pending the above actions, DFID to consider a no-cost extension after the end of the programme to support delivery of the outcome. / On the output level: / Output 1: / Tajaawob to produce action plan for improving participation in the CALP training sessions to meet the 2015 target be end of July 2014. / Tajaawob to undertake a gender analysis of the CALP training to identify specific barriers to women’s engagement by July 2014. / Output 2: / Tajaawob to identify additional Authorities to approach concerning the creation of new engagement mechanisms by end of July. / Tajaawob to provide DFID with a clear strategy for ensuring the long-term sustainability of the engagement mechanisms; 1st draft by December 2014 and final draft by February 2015. / Output 3: / To receive a plan from Tajaawob by August 2014 detailing their TV targeted output for 2015; including what it will consist of and how local media houses will be involved in the production of the TV broadcast. / On Value for Money: Tajaawob will review the admin costs in the light of a review of the overall budget in order not to exceed the 15% limit over the remaining timeframe of the programme. / To ensure continuity of the successful implementation of the programme, and to put to good use the current underspend of the programme, it is also important to consider an extension to the end date of the programme by October 2014.

8. Review Process
The review was drafted based upon the following information sources: / • The original Business Case / • Tajaawob Quarterly reports / • Feedback from beneficiaries / Conducted by DFID Palestinian Programme State building team (Programme Officer and Governance Adviser) and quality assured by DFID deputy head and results adviser.