Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Africa Division funding to Africa Agricultural Development Company (AgDevCo)
Programme Value: £78.28m		Review Date: 21st April 2016
Programme Code: 204270	Start Date: 1 July 2013	End Date: 31st December 2020

Summary of Programme Performance
Year	2013	2014	2015
Programme Score	A+	A	A
Risk Rating	Medium/High	Medium/High	Major

Summary of progress and lessons learnt since last review

AgDevCo has again made good progress against annual targets as the portfolio further develops and matures. There continue to be differences between achievements and the challenges faced in each implementation country, with this reflected in country-level portfolios, strategies and results. No major concerns are raised in this annual review, with the overall risk rating moving to ‘major’ in the new 4-point risk rating scale.

Since the 2014 Annual Review, several changes have been made on how AgDevCo reports, monitors and conducts investments. In 2015, the organisation (i) completed a logframe update, including further granularity in results reporting and stronger monitoring of indicators such as full time equivalent (FTE) jobs created; (ii) adopted International Climate Fund financing (and associated monitoring) for part of the portfolio; (iii) recruited senior monitoring and evaluation (M&E) and environment, social and governance staff; (iv) worked with DFID to put in place a portfolio-wide gender policy; (v) strengthened its reporting policy across offices; and (vi) focused on large and/or greenfield investments in several countries.

AgDevCo has proactively addressed DFID’s April 2015 Annual Review recommendation to develop a gender strategy for implementation in 2016. During the year a new Gender Policy was developed and approved by the board in April 2016, accompanied by a gender action plan which is about to be rolled out. In January 2016 AgDevCo employed an Environment, Social and Governance (ESG) specialist who will lead on gender policy implementation, alongside a new M&E Specialist who will have a key role in monitoring gender progress and impact. The ESG specialist will also lead on capacity building for AgDevCo staff and investment partners to improve gender impact.

In the January 2016 Steering Committee it was agreed that 60% of the AgDevCo portfolio would be classified as International Climate Fund (ICF) financing. The Climate Finance justification was added as an additional requirement seizing the opportunities in AgDevCo’s investment pipeline, and thus was not designed into the programme from the start. As this review primarily focuses on first phase investment it would be unrealistic to hold these early projects to account against ICF criteria that were not agreed at the start. For the new portfolio of investments made in (November-December 2015), it is too early in the investment cycle to assess impacts. ICF comments are thus forward looking and focus on monitoring.

Through 2015, AgDevCo faced several exogenous challenges that affected their ability to make investments, as well as impacting the businesses that they supported. The uncertain, challenging environment was fuelled by extensive currency depreciation across the continent, making AgDevCo’s USD-denominated loans more expensive for those borrowing to generate revenue in domestic markets. Fiscal contraction as commodity prices tumbled affected several countries, with power cuts and other infrastructure-related issues further impacting businesses. Further, the onset of El Nino caused flooding in some parts of East Africa late in the year, with drought in parts of Southern Africa affecting yields.

In 2015 AgDevCo’s board approved a new ambitious strategy for expansion in the next 5 years. Based on that strategy AgDevCo has started negotiations with CDC on a possible investment of Development Capital and with DFID for a grant investment to allow expansion to 2 new countries and transition towards Development Capital Investment. As discussions are currently ongoing with CDC this review did not specifically address resourcing options for AgDevCo’s new strategy.

Summary of recommendations for the next year

A number of recommendations are made as part of this annual review. These have been grouped under the following headings:

Logframe and Development Impact Monitoring

Although the logframe was updated in 2015 to provide improved disaggregation of results, it is clear from discussions that further work should be done to address the challenges of evaluating the impact of AgDevCo. Initial discussions have taken place on this, which should continue:

Recommendation 1: DFID works with AgDevCo to both improve estimations of milestones, as well as ensure that the logframe captures as much as possible the benefits accruing from a diverse portfolio. AgDevCo’s suggestions to include a more structured assessment of development impact in the investment decision-making process while simplifying reporting should be further explored. Recommended areas of focus in further logframe review are (i) additionality, (ii) number of beneficiaries, (iii) income uplift, and (iv) economic transformation potential. The revised logframe will need to continue including agreed ICF indicators.

Gender Policy

Having completed the Gender Policy the emphasis should be on rolling out the action plan in the next year before an independent review of the policy and plan. Critical next steps are detailed in the Annex on gender policy:

Recommendation 2: DFID to ensure that the planned independent review of gender progress (2017) is appropriately prioritised and timed to inform AgDevCo’s annual corporate report and DFID’s next annual review in 2016, including responding the recommendations in the annex on gender and using it as a background document to inform the terms of reference. As part of this, DFID to ensure quarterly monitoring discussions on gender action plan implementation between DFID and AgDevCo, with a focus on completion of country studies as a priority area for action.

International Climate Fund Reporting

Going forward, AgDevCo will need to report on key KPIs as part of its classification as ICF financing. Recommendations have been made to ensure that this reporting is relevant, robust, in line with requirements of the ICF and useful for AgDevCo in managing climate risks.

Recommendation 3: AgDevCo ESG lead and portfolio leads should initiate resilience discussion amongst AgDevCo, business partners and farmers.

Recommendation 4: AgDevCo’s M&E systems and the new development impact framework should include climate and resilience considerations.

A. Introduction and Context

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5381171.odt
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204270/documents

Africa is recognized as the region with the most unexploited potential for agriculture production. Development of agribusiness and transformation of agriculture in Africa could create jobs, income and other opportunities for the African smallholder base.
Yet there is relatively little investment in commercial agriculture, even in countries where the policy environment is more supportive. A major reason is because investors face very high costs and risks associated with early-stage development, poor access to, and high cost of finance, lack of experienced workforce and absence of a supporting network of service companies.
AgDevCo is a non-profit sharing investment company that makes debt and equity investments in early stage or growing agricultural businesses in Africa. It aims to address many of the constraints these businesses face in accessing the capital and support they need to grow.
The UK currently provides up to a total of £105.46 million to AgDevCo. This is funded from the following departments:
- £50.0 million of re-deployable capital over 5 years channelled through 3 Catalytic Funds in Malawi (£10mln), Zambia (£10mln) and Ghana (£10mln) funded by DFID Country Offices and £20 million funded by Africa Regional Department;
- £15.58 million of additional re-deployable capital for specific investments in 3 projects in Tanzania, funded by DFID Tanzania;
- £11.0 million from Private Sector Department for mainly early-stage and greenfield large-scale agribusiness infrastructure, predominantly irrigation or irrigated large-scale production;
- £2.47 million from DFID Ghana prior to the joint Africa Division business case;
- £14.41 million from DFID Mozambique for the Beira Agricultural Growth Corridor; and
- £12 million from DFID Uganda through the Nu-Tec programme for an additional Catalytic Fund.

The programme also includes £1.7 million funding for an independent impact evaluation and research component in multiple countries to generate evidence and learning on stimulating private sector investment in agriculture. The contract for the impact evaluation was closed in 2015 and is discussed further in the Monitoring and Evaluation section.

The only increase in funding since the last annual review is the £12 million from DFID Uganda under the Northern Uganda: Transforming the Economy through Climate Smart Agribusiness (NU-TEC) programme. This annual review covers £78.28 million: £1.7 million monitoring and evaluation component and all funding to AgDevCo except the funding from DFID Mozambique, DFID Uganda and the early funding from DFID Ghana. Next year Annual Review will cover funding from DFID Uganda and from 2018 funding from DFID Mozambique will be also included in the central annual review.
As of Q2 2015, the funding has been disbursed through a direct agreement with AgDevCo.
Funding will result in an investment portfolio by 2018 that will have directly benefited over 900,000 people (ideally 50% women – actively monitored) and is expected to have had positive impact for many more through additional spill over investments and improvements in agriculture infrastructure. Expected Outputs by 2018 are:

- 57 agribusiness enterprises developed or expanded with an additional turnover of over £120 million;
- Over 900,000 individuals directly benefiting from the new investments by 2017, including: 190,000 smallholders’ households directly benefiting from additional income and 7,000 additional FTE jobs;
- Improved availability of agriculture supporting infrastructure – 34,000 additional hectares under irrigation (Ha) and 125,000 additional metric tonnes in processing throughput;
- Over $22million of additional regional trade directly generated by AgDevCo’s investments.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The outcome of the AgDevCo programme is to leverage private sector investment in agribusiness and agricultural infrastructure; increase agricultural cross border trade; and generate jobs and income in targeted countries. The performance of existing and new investments over the past 12 months has made a more pronounced impact on Outcome Indicators. It is worth noting that logframe targets have been amended to ‘annual’ figures, rather than ‘cumulative’ in previous reports.

Indicator(s)	Milestones 2015	Progress 2015
Value of capital leveraged and invested in agribusinesses (annual) ($m): a) Private, b) DFI	$5,000,000 / 0	$24,375,303 / $17,000,000
Incremental beneficiary household income: a) Outgrowers ($); b) employed ($)	$3,382,270 / $4,980,355 / TOTAL $8,362,625	$5,783,323 / $2,875,224 / TOTAL $8,658,546
Value (annual) of agricultural products exported by agribusinesses.	$3,776,000	$1,290,359
Percentage of private sector investment in DAC I, II countries	80%	84%
Value of capital repaid to AgDevCo ($)	0	$695,247

AgDevCo has leveraged over $41m of capital into agribusiness investees in 2015, giving a cumulative leveraged figure of just under $63 million by the end of 2015 – far exceeding targets set. Of the 2015 annual figure for DFIs, $14 million was leveraged from KfW for LAFCo (UK) and $3 million from IFC for Westfalia (Mozambique).

Overall targets for increases in household income have just been met; mainly driven by good results for outgrowers, rather than an increase in income for those employed. Tanzania and Malawi greatly exceeded household income targets for outgrowers; conversely Zambia and Mozambique were well below target for household income for those in employment. Total exports were below target, with only Malawi, Tanzania and Mozambique contributing to results this period. Although no target has been set for 2015, AgDevCo has had $695,247 repaid out of a total due of $737,905[1].
[1] This is repayment of the principle, rather than interest. Due to the early stage of the portfolio, this will increase in later years.

In coming years, AgDevCo is likely to continue to have strong figures on capital leveraged vs. plan until 2017, when logframe annual targets ramp up considerably. It is recommended that these annual figures post 2017 are reviewed. As the portfolio matures, figures for direct increases in household income will increase; although it is difficult to assess against current planned figures in future years as several major investments are high risk and in the early stages of development. The value of agricultural products exported is also likely to increase as AgDevCo focuses on ways to mitigate local currency risk.

Overall output score and description

The overall output score is an A.

Output 1 moderately did not meet expectations (B). AgDevCo exceeded targets for annual increase in EBITDA, however fell slightly short on other output indicators. This is not a cause for concern given challenges in the wider investment environment in 2015, and progress on larger deals that were not concluded in time for 2015 reporting.

Output 2 exceeded expectations (A++) with more farmers engaged than planned, for both male and female targets.

Output 3 moderately exceeded expectations (A+) as jobs created exceeded the annual target overall, however this was dominated by positions created for men, rather than women, with the latter falling below target.

Output 4 met expectations (A). AgDevCo exceeded targets for processing throughput but fell short on targets for irrigated land. As identified in the 2014 review, the current pipeline has meant that they will likely continue to struggle to meet irrigation targets.

Performance against logframe targets has marginally improved this year, however the logframe continues to under-represent AgDevCo’s impact, and have targets that do not match AgDevCo’s current and projected portfolio. Exogenous benefits of wider employment, systemic change and pioneering new agribusiness are also not captured in the logframe. By the end of 2015, AgDevCo had committed over $62.3m to 34 investments, with further pipeline being developed across the portfolio.

Key lessons

It was identified last year that as current projects are developed and pipeline is grown, it is likely that the assumptions used to develop the original logframe targets may no longer hold. Review and improvement of how the programme is assessed will ensure that both realistic targets are set, and that it is judged against valid metrics.

As per the 2014 annual review, it is evident that slower trajectories are required to achieve development results, particularly for greenfield site development and primary production. This is where most of the AgDevCo portfolio is focused – although the extent of this varies by country. As its portfolio expands, AgDevCo will need to ensure that they generate a balanced portfolio to (i) reduce portfolio risk and (ii) ensure a balance of impact across different investments.

Through 2015, DFID worked with AgDevCo to implement a new Gender Policy across the business. While further work still needs to be done to establish this within AgDevCo, it was clear from country visits that on the ground AgDevCo will have to work hard to change attitudes and implement across projects. Cultural and other factors often meant that beneficiaries were difficult to target based on gender.

AgDevCo has started a discussion on how to include a more structured assessment of development impact in the investment decision-making process, while simplifying reporting. A matrix on how to assess investment proposal is being developed and discussed with DFID with the following areas of focus (i) additionality, (ii) number of beneficiaries, (iii) income uplift, (iv) economic transformation potential.

It was evident from discussions (particularly in Zambia) that AgDevCo is in the process of increasing the size of SME investments, as well as their support to SMEs with repeat and larger investments to ensure they succeed. As the programme continues, it will be important that AgDevCo continues to target the investments – whether large or small – that have the widest development impact for the most poor. Formally incorporating development impact as part of the investment decision making process, (including using the right measures for additionality, poverty reduction for direct beneficiaries and wider economic transformation considerations) will be important to keep AgDevCo’s strong development focus and high risk appetite.

As the organisation moves to more greenfield, larger and platform investments, environment, social and governance due diligence and effective implementation of this will be of utmost importance to ensure that risks to DFID, AgDevCo and wider communities are minimised. This should be a key part of country level and annual reviews going forward.

It was evident in 2015 that wider business environment issues, such as depreciating currencies, climatic factors and poor fiscal environments were impacting on businesses as well as the ability for AgDevCo to invest. In most cases this created a more difficult operating environment, as investees avoid USD denominated debt and flooding and drought limited agricultural production. In some instances though – for example where AgDevCo had supported irrigation in drought-affected areas – AgDevCo’s interventions reduced losses and improved yields. Looking forward, AgDevCo will need to consider further ways to reduce exogenous risks such as currency, climatic and wider business environment in its portfolio. DFID should support this, as well as providing links to other programming that could assist.

Key actions

The following additional actions on policy should be taken:

- Continued discussion on the impact of AgDevCo’s investments, while the portfolio evolves and it potentially moves towards larger and even more early stage businesses;
- Discussion on how AgDevCo can minimise the burden and risk on non-export revenue earning businesses of dollar-denominated debt;
- Sharing of lessons learned as well as dialogue with DFID on wider business environment issues that other programmes could potentially impact.

Has the logframe been updated since the last review?

A revised logframe was put in place for the 2015 annual review, taking into account recommendations from the 2013 and 2014 reviews, where possible. Following advice from the independent evaluators not all recommendations were however adopted. It is worth noting that the new logframe scores against annual figures (opposed to cumulative); this is to allow easy reference to performance over a given reporting period and allow accurate scoring based on that period. Cumulative figures and targets are also reported in the logframe to allow monitoring progress on overall programme targets; Output scores are however based on annual and not cumulative figures.

Recommendation 1: Although the logframe has had some amendments made, targets and criteria do not necessarily accurately represent the way AgDevCo conducts investment, nor the portfolio and pipeline of projects and their estimated results. The major recommendation from this review is that DFID works with AgDevCo to both improve estimations of milestones, as well as ensure that the logframe captures as much as possible the benefits accruing from a diverse portfolio.

Specific areas to consider:

1. AgDevCo’s suggestions to include a more structured assessment of development impact in the investment decision-making process while simplifying reporting should be further explored. Recommended areas of focus in further logframe review are (i) additionality, (ii) number of beneficiaries, (iii) income uplift, and (iv) economic transformation potential. AgDevCo to include development impact in the decision making process, with indicators on (i) additionality, (ii) people benefiting, (iii) income uplift and (iv) economic transformation. Associated logframe indicators on the four areas and amendments are recommended, with additional logframe indicators providing background, but not assessment[2].
  [2] Data on irrigation, number of businesses and productive capacity is more relevant for learning purposes than to measure performance against arbitrary targets.
2. The revised logframe will need to continue including agreed ICF indicators.
3. Logframe milestones/targets are re-assessed based on current and planned portfolio, around SME, platform and greenfield investments.

## C: DETAILED OUTPUT SCORING

Output Title	Develop or expand agribusiness enterprises that are financed, owned or operated on a commercial basis by AgDevCo
Output number per LF		1	Output Score	B
Risk:		Major	Impact weighting (%):	30%
Risk revised since last AR?		Yes[3]	Impact weighting % revised since last AR?	No
[3] Risks have been reviewed against the revised DFID risk framework and updated to align with the new four point scale: minor, moderate, major, severe.

Indicator(s)	Milestones	Progress
1.1 Number of enterprises created or expanded (annual): a) SME businesses, b) Medium size financial investments, c) Large project development investments	SME 10 / Medium 4 / Large 1 / TOTAL 15	SME 12 / Medium 0 / Large 0 / TOTAL 12
1.2 Volume of investment committed to agribusinesses or agricultural development projects (annual) ($m)	$26,000,000	$24,561,777
1.3 Increase in EBITDA (annual) ($)	$1,813,000	$3,683,182
1.4 Volume of sales by agribusiness (quantity of goods sold or number of clients serviced at a fee)($)	$18,130,000	$12,986,636

Key Points

Achievement of targets for 2015 was overall moderately below expectation for output indicator 1. The number of enterprises created or expanded, volume of investment committed and volume of sales all fell marginally below annual targets. Increase in EBITDA for businesses was however above target for the year. When looking at cumulative figures to-date, both output indicators 1.1 and 1.4 remain behind target.

Reasons for this include:

- All countries apart from Mozambique are below target on cumulative enterprises created/expanded, with Ghana and Zambia also behind on their annual logframe targets. This reflects challenges of sourcing local staff and investible businesses in Ghana, and the difficult operating environment in 2015 in Zambia, with a depreciating local currency and taxing business environment. Overall a difficult operating year across the portfolio countries (due to macro, fiscal and climatic environment) has made investments and performance in agribusiness less certain, impacting the portfolio.
- Another reason for a lower number of enterprises created is because AgDevCo have found that SMEs require more investment than planned to succeed[4]. This has resulted in fewer new investments (output 1.1) but a roughly as-planned amount committed/invested in agribusiness (output 1.2).
  [4] Average SME investment size has gone from roughly $0.5m to $1.5m
- In several countries (Ghana, Malawi, Mozambique and Zambia), many investments took place in businesses that require more early stage support, or were made into new ventures (e.g. see NWK, NRZ and Babator in site visit reports). This often means results are delayed while the business is built, or there is a lag between investment and impact. While some work has been done to look at annual results and the AgDevCo portfolio, it is not possible to set perfect targets for such a portfolio that is reliant on early stage investment.
- The increase in EBITDA was mostly driven by GADCO (Ghana) and NWK (Zambia). EBITDA for NWK increased from $1.8m to $3m, due to an increased gross margin based on strict cost control of variable costs. The EBITDA for GADCO increased from -$2.2m to -$0.5m as the benefits of business restructuring were realised. KPL (Tanzania) also contributed $412k to the overall increase in EBITDA.

As per last year, it should be reiterated that the original logframe targets were based on an anticipated level of investment activity prior to funding being disbursed and any real development of the pipeline of investments taking place. Given the nature of the work that AgDevCo is undertaking, which is inherently iterative in nature with investments being explored, then developed or rejected once further due diligence work is undertaken, the logframe targets could only ever be an ‘estimation’ of what the portfolio would eventually look like. AgDevCo and DFID are now in a much better position to more accurately predict targets going forward as well as priorities for scoring, hence Recommendation 1.

Summary of responses to issues raised in previous annual review

Recommendations from 2014 Annual Review	Response
Recommendation 1: DFID should ensure the new logframe incorporates early lessons from the scale-up of likely impact from investments, including the longer time period needed to realise results from primary production and greenfield site development.	The logframe has been revised in light of previous recommendations. The present Annual review involved DFID statistics adviser in early discussion about a new more appropriate development impact framework and implications for the logframe. An assignment to externally review AgDevCo M&E system in comparison with relevant industry standards and best practices is ongoing which will make initial specific recommendations on development impact framework and revised logframe for DFID and AgDevCo to consider.

Recommendations

There are no specific recommendations for output indicator 1.

Output Title	Increase integration of smallholders into commercial agribusinesses through access to irrigation, processing infrastructure, modern inputs, etc.
Output number per LF		2	Output Score	A++
Risk:		Major	Impact weighting (%):	30%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
2.1 Number of smallholder farmers engaged in agribusinesses (annual): (a) male farmers; (b) female farmers; (c) total individuals benefitting (i.e. Total male and female farmers multiplied by household size)	Male farmers 8,652 / Female farmers 8,652 / Total individual 17,304	Male farmers 33,972 / Female farmers 18,590 / Total individual 52,563
2.2 Number of smallholder farmers selling to aggregating, storage, or processing services (annual): (a) male farmers; (b) female farmers	Male farmers 2,045 / Female farmers 2,045 / Total individual 4,090	Male farmers 5,327 / Female farmers 2,483 / Total individual 7,811
2.3 Number of smallholder farmers using agricultural extension services and improved management practices (annual): (a) male farmers; (b) female farmer	Male farmers 898 / Female farmers 898 / Total individual 1,796	Male farmers 32,048 / Female farmers 16,968 / Total individual 48,017

Key Points

Output 2 has been exceeded for all indicators with 52,563 farmers engaged or linked to markets, 35% of which are women. All countries contributed to results this year (including improvements in Mozambique compared to 2014), however the results were driven by investments in Tanzania (KPL, Suma Hydro and Rungwe Avocado), Zambia (Northern Zambia Agricultural Hub, NWK and NRZ), Malawi (Phata) and a significant contribution from working capital loans provided by LAFCo. Overall the sizeable increase is due to investments made during 2014 now reporting their impact. Cumulative figures are also well ahead of targets.

As per the 2014 annual review, it is worth indicating that ‘Farmers engaged in agribusiness’ often includes farmers engaged prior to the AgDevCo investment when such investment was instrumental to maintain those jobs, as well as those engaged in activities with no direct links to the investment. For example, investment in Gee’s Fresh Point in Ghana is for a new processing facility, which is currently under construction. Smallholders engaged include all of the company’s suppliers currently active, although all were engaged prior to AgDevCo investment.

Outputs 2.2 and 2.3 give further insight into the beneficiary engagement is taking place, and how benefits are accruing to smallholders. For output 2.2 most were from Malawi (mainly Tropha Chillies) and Zambia (NGHL). Again though, the numbers do not necessarily indicate direct beneficiaries of the AgDevCo funding; they indicate those benefiting from the business that AgDevCo has funded. This is often because it is difficult to disaggregate the components of the business directly funded by AgDevCo, and the results of the wider company.

Summary of responses to issues raised in previous annual reviews

Recommendations from 2014 Annual Review	Response
Recommendation 2: AgDevCo to agree a clear methodology with DFID on how they count and report on farmers engaged prior to AgDevCo funding being given.	AgDevCo has provided documented guidance to all team members on how to apply a consistent methodology for farmers that may have been engaged prior to AgDevCo’s funding. All investments will be reviewed to ensure that the approach has been consistent.

Recommendations

Recommendations are included in recommendation 1

Output Title	Increase employment through the development of agribusinesses.
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
3.1 Number of jobs created (FTE) (annual): a) men; and b) women.	Men 1075 / Women 684 / TOTAL 2,150	Men 2,030 / Women 677 / TOTAL 2,708

Key Points

Annual job creation figures for this year overall moderately exceeded logframe targets, however this was driven by jobs for men exceeding the target and those for women falling short of the target. The improvement from last year (where the output scored a ‘C’) came from investments in Tanzania, Zambia and Malawi. Specifically in Tanzania (increase from 282 to 1,130) results were driven by KPL and EFTA and in Malawi by Tropha Macadamias (427 jobs created/sustained). Cumulative job creation figures were marginally above target as of the review date[5]. Many of the businesses hired temporary or seasonal workers, with conversion of these workers to full time equivalents (FTEs) varying depending on the nature of the business, to give accurate (as possible) estimates. This is an improvement on the previous year’s reporting where the standard PIDG methodology of 2 seasonal jobs equating to 1 FTE was used. All businesses apart from EA Fruits, Gee’s and Zocoffams were considered to need AgDevCo’s funding for either establishment, continued operations or survival, thus no baseline of jobs was used and all employed workers were counted in the ‘annual’ figure.
[5] 3,577 achieved versus a cumulative target of 3,517

Looking forward, job creation will continue to be an integral part of AgDevCo’s added value to development impact. It was clear from discussions that larger, greenfield commercial investments such as Babator (Ghana) will need to create employment and source staff from local communities. Gender dynamics will be key: it was clear from site visits that men often dominated discussions on the business and the involvement of the project with communities. Involving women in discussions and specifically creating jobs that target women, as well as going further to reduce some of the exogenous barriers that limit participation by women in employment may help.

Summary of responses to issues raised in previous annual reviews

Recommendations from 2014 Annual Review	Response
Recommendation 3: AgDevCo to reassess the methodology for calculation of full-time equivalent jobs (FTE) with the independent evaluators. They should finalise a simple methodology to count seasonal/temporary workers.	The independent evaluation contract has been closed. / Initially AgDevCo made the simplifying assumption that each part-time or seasonal worker should count as 50% of a full time employee. However, this year’s report has looked at each investee on a case-by-case basis and made more business-specific assumptions about use of seasonal, temporary and part-time workers to convert to FTEs. / AgDevCo is also in the process be putting together a database providing an indication of the types of seasonal work associated with each crop, and the likely duration of employment for each of the seasonal workers.
Recommendation 4: DFID/AgDevCo to alter logframe indicator 3.1 to (a) new jobs created (b) jobs maintained.	Completed.
Recommendation 5: After the approval of an investment, AgDevCo should ensure that the company is not employing staff on temporary contracts to avoid payment of formal contributions/benefits to the detriment of employees, and aim for best practice in labour relations.	AgDevCo’s Head of Impact & ESG has a programme of work which a) reviews their investments (starting with the largest and working down) to ensure these, and other, matters are either in place or being addressed; he is also responsible for undertaking pre-investment ESG due diligence which includes labour contracts; and through the Gender Policy, taking forward ideas to improve women’s participation in the programme.

Recommendations

Recommendations are included in recommendation 1

Output Title	Increase agriculture-supporting infrastructure in targeted countries.
Output number per LF		4	Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
4.1 Hectares of irrigated land (cumulative) (Ha)	7,700 Ha	3,285 Ha
4.2 Processing throughput/capacity (annual) (Mt)	23,575 Mt	50,953 MT
4.3 Level of installed capacity of clean energy (cumulative) as a result of ICF support. (kW)	No target defined	700 kW

Key Points

As per 2014, output indicator 4.1 substantially did not meet expectations; however indicator 4.2 substantially exceeded expectations. An overall score of ‘A’ is awarded based on these two indicators. No target has yet been identified for output indicator 4.3. Compared to 2014, hectares of irrigated land has increased by almost 7-fold; however as this is a cumulative figure and results were behind target last year, results remain behind target this year. In addition, greenfield investments into primary production take considerably more time to reach financial close; this impacts results as most of the irrigation investments fall into this category. All countries though have seen increases in irrigated land. Processing throughput capacity increases have been driven in almost entirety by Tanzania[6] due to the mill-lines at KPL.
[6] increase of 50,714mt

Summary of responses to issues raised in previous annual reviews

Recommendations from 2014 Annual Review	Response
No recommendations made

Recommendations

There are no specific recommendations for output indicator 4.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The key cost drivers remain fund management costs and overheads. These compare favourably with fund management and overhead costs of similar institutions.

VfM performance compared to the original VfM proposition in the business case

VfM metrics, aligned to the three E’s – Economy, Efficiency and Effectiveness - were agreed in the 2015 business case.

Economy
1. Fund management cost ratio (the ratio of fund management costs to total investment funds).
2. Administrative cost ratio (the ratio of fund management and overheads to total investment funds).

These indicators are being reviewed in this annual review and compared the Africa Enterprise Challenge Fund (AECF) which also supports agri-businesses in Africa giving grant and non-recourse loans; and CDC, another Development Finance Institution (DFI) which has just had an additional £725m equity committed by DFID from 2015-2018, as recommended in the business case.

AgDevCo’s fund management and overhead costs in 2015 amounted to $6.8m on $88,703,636 of investment funds from the £77m to AgDevCo covered in this review. The total fund management cost ratio was 7.6%, and the administrative cost (£2.6m) ratio was 2.9%. These figures are taken from the investment funds committed by DFID, covered in this annual review. It should be noted that not all the committed funds are currently invested.

The CDC figures are not yet available for 2015 but in 2014 its operating costs were projected to be 1.2%[7]. The AECF portfolio total fund management in 2015 was 3.6% - $7m against a total commitment for grantees of $196.4m[8]. Both these comparators are lower than AgDevCo but they have been established for a lot longer; with much larger investment portfolios generating economies of scale; and have a different risk appetite and operational business model. Particularly in comparison with CDC, AgDevCo investees are often early stage businesses who they also provide business development support to which in turn increases their fund management costs with extensive due diligence requirements and business support throughout the investments. AgDevCo have committed to provide a more detailed analysis of the FM costs between those that are typically incurred in fund management roles and those that are additional, like the technical assistance that AgDevCo gives to the investees in order to develop viable and impactful businesses. This will enable clearer comparison with other investees.
[7] ‘CDC Programme of Support in Africa and South Asia 2015-2018’ business case https://devtracker.dfid.gov.uk/projects/GB-1-203444/documents
[8] AECF value for money metrics Q:5224043

Efficiency
Leverage ratio (The ratio of private and DFI finance committed to AgDevCo investment)

AgDevCo’s business model, private sector and DFI investment is not expected to be leveraged during the first years of new investments. This indicator can be meaningfully interpreted for investments over 5 years old which will be from 2017. Including projects in the existing portfolio (funded under previously approved Africa Division funding).

Effectiveness
1. Smallholder engagement rate, disaggregated by sex (Ratio of total committed investment to number of smallholders engaged)
2. Job creation rate, disaggregated by sex (Ratio of total committed investment to number of jobs created)
3. Business failure rate (Number of investees ceased trading as a proportion of enterprises financed)

Effectiveness was expected to be measured from 2016 in the 2017 annual review on the basis that all investments should have been committed by then. For this annual review the current results have been reported. For the first two indicators the total committed investment to date is $62.3m. For (iv) the cumulative number of smallholders engaged to date is 63,638 giving a ratio of $979 for each smallholder engaged (v) jobs created cumulative 3,577 giving a ratio of $17,417 for each job. Both the number of smallholders engaged and jobs created are above the logframe targets for 2015 and the rations are expected to fall as investment mature. For (vi) to date none of the businesses have failed. These results show that the programme is currently effective and will be explored in more detail in the next annual review.

Assessment of whether the programme continues to represent value for money

The programme still remains value for money. The VfM argument could be strengthened through additional support to generate economies of scale on the economy indicator. A decision on additional support should also ensure the effectiveness of the programme would be strengthened, including looking at the distribution of economic benefits and their poverty reduction implications.

Quality of financial management

Financial management in AgDevCo continues to be rated as good.  Annual audited financial statements are provided, which have been unqualified to date. In 2015 DFID moved to a direct funding relationship with AgDevCo with the first disbursement taking place in December 2015. Quarterly financial reports provided in the needs letters remain clear and detailed with accurate information.

Moving to quarterly disbursements after Board approval has reduced the risk of investments not proceeding and cash being held in the AgDevCo account for a long time before commitment.

Date of last narrative financial report	31/03/2016
Date of last audited annual statement	31/03/2016

E: RISK

Overall risk rating: Major

The overall risk rating has been revised under the new risk framework to ‘Major’. AgDevCo’s business model, investing in early stage companies who cannot access finance from other institutions, by nature, assumes major risk.

Overview of programme risk

AgDevCo maintain a comprehensive risk register of 23 key risks. Their risk register is updated and presented to their Audit and Risk committee quarterly. The following two risks have the highest rating, considered both highly likely and that they would have a significant impact on the programme:

- Regulatory compliance risk
- Currency risk

‘Regulatory compliance risk’ occurs because the countries in which investees' or AgDevCo's own projects operate can have regulations that cause delays and increase costs associated with doing business in the region. ‘Currency risk’ is also very high due to level of depreciation and macroeconomic uncertainty in the countries AgDevCo operates in.

Following the 2014 annual review the register is also discussed at the quarterly DFID wide steering committee as a standing agenda item. The risks above were highlighted by all offices as ones that were considered to be high risk. The weather, with the effects of El Nino being felt by most of the countries AgDevCo operate in, was also highlighted as a concern. AgDevCo agreed that it would be likely to increase in risk over the coming months.

The DFID risk register was updated in 2015 through the business case process and has been amended during this review to reflect the new DFID risk framework. Three new risks have been added:

Risk	Likelihood	Impact	Mitigation	Residual likelihood	Residual impact
DFID funds are misused	Unlikely	Severe	AgDevCo has a robust accounting, management and operational procedures. Extensive due diligence was conducted by DFID before the initial business case and additional due diligence will be conducted by CDC as part of their investment appraisal	Unlikely	Moderate
Negative UK public perception of DFID investing in AgDevCo while still being owned by a sole shareholder, because we stopped the transfer of shares to a Company Limited by Guarantee.	Likely	Severe	(i) DFID have established strong oversight structures of AgDevCo (ii) DFID must approve any company changes before they can take effect (iii) AgDevCo's statutes prescribe that no profit can be redistributed (iv) the shareholder has repeatedly asked to gift its shares to a non-profit entity which we have delayed (v) DFID has the right to terminate funding at any time (vi) a new governance structure will be finalized as part of negotiations with CDC and in consultation with DFID	Possible	Major
CDC not investing Development Capital in AgDevCo	Possible	Major	Although a negative outcome of negotiations with CDC could impact the future scale and sustainability of AgDevCo operations in future, grant funding on its own will deliver development benefits. CDC has agreed to provide an early investment indication in July 2016, which would also allow time for AgDevCo to pursue other investees in case of a negative outcome.	Possible	Moderate

Outstanding actions from risk assessment

Last year the annual review considered the actions log for the 2013 AgDevCo due diligence (EDRM reference 4951999). It recommended finalising the remaining issue around the governance of AgDevCo including under what legal form AgDevCo will be registered and how disbursements will be made in future to avoid payment in advance of need. The Disbursement arrangements have been revised and AgDevCo are now requesting investment funds quarterly after the Board has approved reducing the risk of AgDevCo holding uncommitted funds. On the governance a decision has been made and documented to delay agreed arrangements in the light of negotiations around Development Capital for agribusiness.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

AgDevCo committed $24.562m against a forecast of $25.499m – a 3.7% variance below target. Just over 50% of the new investments, $12.357m came from the Africa Regional funding following the slower than expected progress with the pipeline in 2014.

Disbursements requested from DFID were £3,490,005.40 against a forecast of £8,459,665 in the 2015 business case. AgDevCo reduced the disbursement request to ensure all pipeline funds were committed and that funds were only requested when there was a high probability of an investment being committed at the Board. Ultimately $18m of the year’s $24.562m was committed in December and AgDevCo received the additional funds from DFID for the December commitments in April 2016.

Looking forward to 2016, AgDevCo has reported a strong pipeline across all established countries. This, coupled with existing investments maturing, should see AgDevCo continue to deliver against overall logframe targets. As mentioned in Section B, revision of the logframe will assist in accurate monitoring of AgDevCo’s impact over the timeframe of DFID investment.

Performance of partnership (s)

As per last year, overall the partnership between DFID and AgDevCo has been performing well. Highlights on AgDevCo’s performance include the strong, professional management teams in-country, good country knowledge, excellent feedback from beneficiaries on the support received, and clear reporting.

At a country level, interviews with DFID and AgDevCo staff indicated several areas that could offer room for improvement:

- Expectations and speed of start-up in new countries. As per last year, some DFID country offices stated that their expectations of how fast AgDevCo could staff up and introduce an initial portfolio of projects were not met. Feelings were that this was due to both expectations on AgDevCo being over-optimistic in start-up, as well as AgDevCo setting over ambitious targets in the early stages of country establishment.
- Reporting. This was an issue for both DFID offices and AgDevCo, but for different reasons. Some DFID country offices would like further granularity of reporting by funding source and at alternative reporting times in order to meet requests from the centre to provide impact data (mostly requiring UK financial year figures). AgDevCo however have agreed centralised reporting to DFID on the whole portfolio on a calendar year basis. Quarterly reporting and overall reporting duties puts excess burden on the management team in-country and detracts from the investment making process. AgDevCo also highlighted that some DFID country offices were less concerned with projects that were not funded from their country-level budgets, instead focusing on only those investments that were allotted directly to their funds.

Several of the areas for improvement mentioned in the 2014 annual review have been addressed:
- Although it is still time consuming to recruit skilled local staff at a competitive wage, AgDevCo offices have succeeded in hiring local talented staff to manage investments and the investment process, including in Ghana and Zambia.
- Throughout 2015, AgDevCo has worked with DFID on improving its focus on gender (see annex)
- No DFID offices highlighted a lack of local indigenous business funding as an issue. Investments in Ghana highlighted some of the challenges of investing in indigenous businesses (see Gee’s), however an overview of AgDevCo’s country portfolios shows that investments are being made and supported with BDS funds.

Within DFID, country offices highlighted several areas that should be discussed at steering committee meetings and addressed in the future:
- As mentioned in the ‘reporting’ point above, discussion should take place on how AgDevCo should report results to DFID and clarity given to country offices of the agreements in place.
- DFID should continue to prioritise risk management, and the mitigating effects of sound ESG, especially as the investments in the portfolio increase in size. Several countries raised the issue of the possibility of negative exogenous impact of AgDevCo’s investments as they grow in size, especially on land ownership, employment and local supply chains.
- Country offices would like to understand how they can audit / have closer oversight over AgDevCo spend at a country level, especially in operating expenses.
- Clarity should be given to offices on how AgDevCo’s investment decisions are validated, especially how DFID ensures the correct level of scrutiny outside of the annual review process.

Overall, DFID country offices were positive on the central management of the programme by ARD and welcomed central oversight of the programme as this reduced the burden in-country and allowed for vfm and other economies of scale.

Asset monitoring and control

Through the provision of debt and equity AgDevCo will recoup a substantial proportion of the funds it invests. As a non-profit-sharing investment company, AgDevCo statutes confirm they will redeploy funds into future projects generating even greater employment, income and development outcomes. Assets are recorded on their financial statement and reviewed by the DFID Programme Manager.

G: CONDITIONALITY

Update on partnership principles (if relevant)

N/A.

H: MONITORING & EVALUATION

Evidence and evaluation

No new evidence has emerged which challenges the design of the programme.

Last year, DFID awarded a contract to conduct an independent evaluation to assess the results achieved by AgDevCo and to learn where, when, for whom, how and why the investment approaches work within different contexts and attain development goals. After the inception phase, the contract was terminated as the contractor was unable to deliver on its tender, with DFID informing AgDevCo in the latter half of 2015.

Subsequently it was agreed that AgDevCo would directly contract an independent assessment of their M&E system – based on a DFID-approved Terms of Reference – and involve DFID in the selection and work with the consultant. The review is assessing the extent to which the M&E systems that AgDevCo is putting in place will both enable good practice performance management, and produce high quality data to feed into any subsequent evaluation. It is envisaged that AgDevCo monitoring data will comprise the majority of information used in future internal and external evaluations of AgDevCo activities. In March 2016, Adam Smith International was appointed by AgDevCo to complete the review.

AgDevCo’s new M&E Lead will need to address how to effectively include ICF reporting as part of overall M&E systems and development impact framework.

2015 Monitoring Systems

In 2015, AgDevCo made several modifications to their monitoring systems. These included:

1. Working to meet recommendations on ESG and gender monitoring from the 2014 annual review, including working with DFID on implementing a gender policy framework (see below) and hiring an M&E Specialist and Head of ESG;
2. Providing guidance to country teams on assessing a variety of logframe indicators, as well as ensuring at central level that reporting is standardised and comparable between countries;
3. M&E workshops were conducted with all teams to review 2014 activities and capture lessons learned;
4. International Climate Fund (ICF) financing was included in the AgDevCo portfolio.

A number of observations were made during discussions of monitoring systems worth noting:

- Some investees continue to struggle with collecting robust data where ultimate beneficiaries are reached through 3rd party traders (e.g. Gee’s, NRZ) or where impact is much wider than the AgDevCo investment (e.g. NWK Agropreneurs).
- Where clear baselines cannot be established, or where the component of the business being funded by AgDevCo cannot be reasonably segmented from the rest of the organisation, AgDevCo reports all those impacted by the business as beneficiaries, when the business was at risk to collapse without AgDevCo’s investment.
- Counting of FTEs has been improved this year with methodologies varying per company based on assessments by the country office.
- Monitoring gender progress is facilitated through investor reports to AgDevCo country offices, onward reports to AgDevCo HQ and HQ Impact and Corporate reports.
- Reporting on sex disaggregated data is a work in progress
- Results are shown in the Development Impact Report with apparently exceptional results overall for men and women under outputs 2.1, 2.2 and 2.3 but targets for the number of jobs created for women continue to lag. The ESG and Impact leads should review these indicators and expected results in the coming year and consider why some results under these four outputs have been exceptional and others lagging, providing more in-depth narrative on results to explain what is happening and why in the 2016 Development Impact Report.
- On wider social impact, country reports show that AgDevCo is using farmer/small holder surveys in some programmes. There is an opportunity to consider how embedded this practice is, to consider expanding it and to ensure that such surveys incorporate gender and poverty relevant questions to produce more in-depth qualitative analysis on progress. This would also support analysis of beneficiary feedback by AgDevCo’s HQ and by DFID.
- Three KPIs have been included for monitoring ICF impact going forward, with AgDevCo to provide justification on each investment where a climate/resilience component exists. These are:
KPI 1: Number of People supported by ICF Programmes to cope with the effects of climate change.
KPI 5: Number of direct jobs created as a result of ICF
KPI 7: Level of installed capacity of clean energy as a result of ICF support.

- Reporting on the above KPIs need to comply with ICF schedule. As AgDevCo reports annually, if ICF requires more frequent reporting, DFID will have to find a solution that does not place additional burden on AgDevCo.
- There remains plenty of opportunity to demonstrate sustainable intensification of agriculture/ building climate resilience from many of the AgDevCo interventions as part of qualitative impact analysis.
As per last year, the logframe does not necessarily capture the many wider benefits of AgDevCo investments outside of income increases or employment, such as transparent pricing or prompt and reliable payments for crops. More qualitative case studies may help to tell this wider story.

Knowledge Management

A valuable outcome from this broad portfolio of agribusiness interventions would be to establish a knowledge base of what works and why, and for this information to be communicated across the programme and feed into DFID and other climate resilience networks.

Recommendation 2: DFID to ensure that the planned independent review of gender progress (2017) is appropriately prioritised and timed to inform AgDevCo’s annual corporate report and DFID’s next annual review in 2016, including responding the recommendations in the annex on gender and using it as a background document to inform the terms of reference. As part of this, DFID to ensure quarterly monitoring discussions on gender action plan implementation between DFID and AgDevCo, with a focus on completion of country studies as a priority area for action.

Recommendation 3: AgDevCo ESG lead and portfolio leads should initiate resilience discussion amongst AgDevCo, business partners and farmers.

Recommendation 4: AgDevCo’s M&E systems and the new development impact framework should include climate and resilience considerations.

Annual Review process

The review was undertaken by Tim McNeill (Private Sector Development Adviser, DFID Southern Africa), with support from Ben Davies (Senior Climate Change Adviser), Mary Thompson (Senior Social Development Adviser), Ed Smithson (Statistics Adviser) Marco Serena (Private Sector Development Adviser, Africa Regional Department) and Katie Wambui (Programme Manager, Africa Regional Department). The review took place between 18th April and 29th April 2016. Fieldwork was undertaken in Zambia from 18th to 22nd April and Ghana 26th to 28th April 2016. The following people were met / interviewed / consulted in AgDevCo and DFID:

Name	Position	Email
DFID
Marco Serena	DFID ARD Lead Adviser	m-serena@dfid.gov.uk
Martin Alsop	PSD Adviser, DFID Zambia	m-alsop@dfid.gov.uk
Vincent Langdon-Morris	Livelihoods Adviser, DFID Ghana	V-Langdon-Morris@dfid.gov.uk
Sarah Bloom	PSD Adviser, DFID Tanzania	s-bloom@dfid.gov.uk
Richard Sandall	PSD Adviser, DFID Uganda	r-sandall@dfid.gov.uk
Katie Wambui	Programme Manager, DFID ARD	k-wambui@dfid.gov.uk
Kerry Johnstone	PSD Adviser, DFID Malawi	k-johnstone@dfid.gov.uk
Teddie Nakhumwa	Economic Adviser, DFID Malawi	t-nakhumwa@dfid.gov.uk
Julia Kraetke	PSD Adviser, DFID Mozambique	j-kraetke@dfid.gov.uk
AgDevCo
Daniel Hulls	CEO, AgDevCo	dhulls@agdevco.com
Alex Simuyandi	Group Operations Director, AgDevCo	asimuyandi@agdevco.com
Rui Sant'ana Afonso	Director, Mozambique AgDevCo	rafonso@agdevco.com
Andrew Tillery	CIO, AgDevCo	artillery@agdevco.com
Peter MacSporran	Director, Commercial Agricultural , AgDevCo	pmacsporren@agdevo.com
Chris Isaac	Director, Investments & Business Development, AgDevCo	cisaac@agdevco.com
Yasser Toor	Director, West Africa, AgDevCo	ytoor@agdevco.com
Siobhan Franklin	Zambia Country Manager, AgDevCo	sfranklin@agdevco.com
Tom Phillips	Ghana Country Manager, AgDevCo	tphillips@agdevco.com
John Vercoe	Head of Impact and ESG	jvercoe@agdevco.com

In addition, the team met with representatives of

AgDevCo’s investees
- Gee’s Fresh Point and GADCO (Ghana),
- NRZ, NWK and Ilobezi (Zambia),
- managing partners of the new greenfield investments in Northern Zambia

Other stakeholders
- management of OLAM coffee operations in Kasama, Northern Zambia
- port and custom officials in Mpulungu Harbour on Lake Victoria (import/export lake gateway to Burundi Rwanda and Tanzania
- Zambia Ministry of Agriculture officials in Mbala (Northern Zambia).
Additional recommendations from 2014 reviews

A number of additional recommendations were made in the 2014 annual review; these are difficult to capture within the new annual review format. The table below includes commentary on how these have been addressed:

Recommendation	Update
Recommendation 6: A clear timeframe to be agreed to confirm the methodology for reporting on VfM metrics from 2015 onwards.	VFM metrics agreed and reviewed from the 2016 annual review.
Recommendation 7: DFID to be given the timetable for the ESG Specialist recruitment and to be thoroughly appraised of how this staff member will support and strengthen ESG due diligence across AgDevCo investees.	ESG recruitment completed. AgDevCo kept DFID updated throughout the process.
Recommendation 8: DFID country offices to ensure risks are discussed systematically at quarterly steering committee meetings. Country offices must understand all highly likely and significant impact risks and be satisfied with the measures taken to manage/mitigate impact.	Discussions have taken place at the quarterly steering committees and risk is now a standing agenda item. It has been agreed that the SC will focus on changes and Country offices also discuss risk in their own SC.
Recommendation 9: All remaining DFID due diligence actions to be completed by December 2015.	Outstanding action on the governance. Decision made and documented to delay agreed arrangements in the light of negotiations around Development Capital for agribusiness
Recommendation 10: Further sustained work required by AgDevCo to ensure an increasing number of partnerships (direct / indirect) with local/indigenous businesses in some countries	AgDevCo continues to engage both directly and indirectly with local entrepreneurs. The increased funding to the NWK Agropreneurs (Zambia) investment is designed to support farmers mechanism and professionalise; similarly the Litchi incubator investment (Mozambique) targets the creation of local farmers in very high value supply chains. Furthermore, AgDevCo continues to look for investments into platforms that can finance local entrepreneurs at a lower scale, which is difficult to access with its current model, through investments like EFTA.
Recommendation 11: AgDevCo to develop a gender strategy with support from DFID, to be implemented in 2016. DFID to monitor and provide support to its development, finalisation and roll-out.	Gender policy and action plan has been agreed with implementation now beginning. DFID have been heavily involved in the development of the policy.
Recommendation 12: AgDevCo to ensure consistent methodology applied for calculating ‘private capital leveraged’ that is accepted and clearly understood by all parties.	Guidance has been provided to the teams to record all capital leveraged by type; the greater degree of granularity should ensure that the approach is reported consistently across the portfolio.
Recommendation 13: DFID (ARD) to urgently check result reporting to ensure that the same results are not being reported twice to/within DFID via different programmes– i.e. through AECF and AgDevCo.	Portfolios of the AECF, FoodTrade and AgDevCo have been reviewed. There were six companies who have been invested in by two of these programmes. A review of the investments showed the majority were funding separate business units which would have no duplication of reporting. In one investment it was impossible to separate attribution at this stage but we are asking the AECF and AgDevCo to do further work on attribution.

Annex 1 – Country results

Ghana

Outcome: to leverage private sector investment in agribusiness and agricultural infrastructure; increase agricultural cross border trade; and generate jobs and income in targeted countries	Progress 2015
Value of capital leveraged and invested in agribusinesses (annual) ($): a) Private, b) DFI	1,500,000 / 0 / TOTAL: 1,500,000
Incremental beneficiary household income: a) Outgrowers ($); b) employed ($)	484,038 / b) 112,560 / TOTAL: 596,598
Value (annual) of agricultural products exported by agribusinesses.	0
Percentage of private sector investment in DAC I, II countries
Value of capital repaid to AgDevCo ($)	20,247
Output 1: Develop or expand agribusiness enterprises that are financed, owned or operated on a commercial basis by AgDevCo
1.1 Number of enterprises created or expanded (annual): a) SME businesses, b) Medium size financial investments, c) Large project development investments	a) 2 / b) 0 / c) 0 / TOTAL: 2
1.2 Volume of investment committed to agribusinesses or agricultural development projects (annual) ($)	7,300,000
1.3 Increase in EBITDA (annual) ($)	1,665,000
1.4 Volume of sales by agribusiness (quantity of goods sold or number of clients serviced at a fee)($)	962,414
Output 2: Increase integration of smallholders into commercial agribusinesses through access to irrigation, processing infrastructure, modern inputs, etc.
2.1 Number of smallholder farmers engaged in agribusinesses (annual): (a) male farmers; (b) female farmers; (c) total individuals benefitting (i.e. Total male and female farmers multiplied by household size)	956 Male farmers / 565 Female farmers / Total individual: 1,520
2.2 Number of smallholder farmers selling to aggregating, storage, or processing services (annual): (a) male farmers; (b) female farmers	716 Male farmers / 405 Female farmers / Total individual: 1,120
2.3 Number of smallholder farmers using agricultural extension services and improved management practices (annual): (a) male farmers; (b) female farmer	693 Male farmers / 302 Female farmers / Total individual: 995
Output 3: Increase employment through the development of agribusinesses.
Number of jobs created (FTE) (annual): a) men; and b) women.	a) 100 Men / b) 47 Women / TOTAL: 147
Output 4: Increase agriculture-supporting infrastructure in targeted countries.
4.1 Hectares of irrigated land (cumulative) (Ha)	503
4.2 Processing throughput/capacity (annual) (Mt)	57.5
4.3 Level of installed capacity of clean energy (cumulative) as a result of ICF support. (kW)	0

Malawi

Outcome: to leverage private sector investment in agribusiness and agricultural infrastructure; increase agricultural cross border trade; and generate jobs and income in targeted countries	Progress 2015
Value of capital leveraged and invested in agribusinesses (annual) ($): a) Private, b) DFI	0 / 0 / TOTAL: 0
Incremental beneficiary household income: a) Outgrowers ($); b) employed ($)	1,569,355 / b) 354,983 / TOTAL: 1,924,338
Value (annual) of agricultural products exported by agribusinesses.	852,359
Percentage of private sector investment in DAC I, II countries
Value of capital repaid to AgDevCo ($)	325,000
Output 1: Develop or expand agribusiness enterprises that are financed, owned or operated on a commercial basis by AgDevCo
1.1 Number of enterprises created or expanded (annual): a) SME businesses, b) Medium size financial investments, c) Large project development investments	a) 3 / b) 0 / c) 0 / TOTAL: 3
1.2 Volume of investment committed to agribusinesses or agricultural development projects (annual) ($)	3,941,410
1.3 Increase in EBITDA (annual) ($)	197,158
1.4 Volume of sales by agribusiness (quantity of goods sold or number of clients serviced at a fee)($)	2,221,889
Output 2: Increase integration of smallholders into commercial agribusinesses through access to irrigation, processing infrastructure, modern inputs, etc.
2.1 Number of smallholder farmers engaged in agribusinesses (annual): (a) male farmers; (b) female farmers; (c) total individuals benefitting (i.e. Total male and female farmers multiplied by household size)	4,395 Male farmers / 2,875 Female farmers / Total individual: 7,252
2.2 Number of smallholder farmers selling to aggregating, storage, or processing services (annual): (a) male farmers; (b) female farmers	1,413 Male farmers / 838 Female farmers / Total individual: 2,251
2.3 Number of smallholder farmers using agricultural extension services and improved management practices (annual): (a) male farmers; (b) female farmer	4,395 Male farmers / 2,875 Female farmers / Total individual: 7,252
Output 3: Increase employment through the development of agribusinesses.
Number of jobs created (FTE) (annual): a) men; and b) women.	a) 469 Men / b) 232 Women / TOTAL: 701
Output 4: Increase agriculture-supporting infrastructure in targeted countries.
4.1 Hectares of irrigated land (cumulative) (Ha)	717
4.2 Processing throughput/capacity (annual) (Mt)	182
4.3 Level of installed capacity of clean energy (cumulative) as a result of ICF support. (kW)	0

Mozambique

Outcome: to leverage private sector investment in agribusiness and agricultural infrastructure; increase agricultural cross border trade; and generate jobs and income in targeted countries	Progress 2015
Value of capital leveraged and invested in agribusinesses (annual) ($): a) Private, b) DFI	5,472,000 / 3,000,000 / TOTAL: 8,472,000
Incremental beneficiary household income: a) Outgrowers ($); b) employed ($)	142,500 / b) 174,677 / TOTAL: 317,177
Value (annual) of agricultural products exported by agribusinesses.	180,000
Percentage of private sector investment in DAC I, II countries	0
Value of capital repaid to AgDevCo ($)	0
Output 1: Develop or expand agribusiness enterprises that are financed, owned or operated on a commercial basis by AgDevCo
1.1 Number of enterprises created or expanded (annual): a) SME businesses, b) Medium size financial investments, c) Large project development investments	a) 1 / b) 0 / c) 0 / TOTAL: 1
1.2 Volume of investment committed to agribusinesses or agricultural development projects (annual) ($)	$5,089,667
1.3 Increase in EBITDA (annual) ($)	0
1.4 Volume of sales by agribusiness (quantity of goods sold or number of clients serviced at a fee)($)	0
Output 2: Increase integration of smallholders into commercial agribusinesses through access to irrigation, processing infrastructure, modern inputs, etc.
2.1 Number of smallholder farmers engaged in agribusinesses (annual): (a) male farmers; (b) female farmers; (c) total individuals benefitting (i.e. Total male and female farmers multiplied by household size)	232 Male farmers / 89 Female farmers / Total individual: 321
2.2 Number of smallholder farmers selling to aggregating, storage, or processing services (annual): (a) male farmers; (b) female farmers	6 Male farmers / 2 Female farmers / Total individual: 8
2.3 Number of smallholder farmers using agricultural extension services and improved management practices (annual): (a) male farmers; (b) female farmer	232 Male farmers / 89 Female farmers / Total individual: 321
Output 3: Increase employment through the development of agribusinesses.
Number of jobs created (FTE) (annual): a) men; and b) women.	a) 111 Men / b) 17 Women / TOTAL: 128
Output 4: Increase agriculture-supporting infrastructure in targeted countries.
4.1 Hectares of irrigated land (cumulative) (Ha)	473
4.2 Processing throughput/capacity (annual) (Mt)	0
4.3 Level of installed capacity of clean energy (cumulative) as a result of ICF support. (kW)	0

Tanzania

Outcome: to leverage private sector investment in agribusiness and agricultural infrastructure; increase agricultural cross border trade; and generate jobs and income in targeted countries	Progress 2015
Value of capital leveraged and invested in agribusinesses (annual) ($): a) Private, b) DFI	$8,258,319 / 0 / TOTAL $8,258,319
Incremental beneficiary household income: a) Outgrowers ($); b) employed ($)	1,413,416 / b) 1,726,026 / TOTAL: 3,139,542
Value (annual) of agricultural products exported by agribusinesses.	258,000
Percentage of private sector investment in DAC I, II countries
Value of capital repaid to AgDevCo ($)	0
Output 1: Develop or expand agribusiness enterprises that are financed, owned or operated on a commercial basis by AgDevCo
1.1 Number of enterprises created or expanded (annual): a) SME businesses, b) Medium size financial investments, c) Large project development investments	a) 1 / b) 0 / c) 0 / TOTAL: 1
1.2 Volume of investment committed to agribusinesses or agricultural development projects (annual) ($m)	$1,506,700
1.3 Increase in EBITDA (annual) ($)	$571,714
1.4 Volume of sales by agribusiness (quantity of goods sold or number of clients serviced at a fee)($)	$5,973,000
Output 2: Increase integration of smallholders into commercial agribusinesses through access to irrigation, processing infrastructure, modern inputs, etc.
2.1 Number of smallholder farmers engaged in agribusinesses (annual): (a) male farmers; (b) female farmers; (c) total individuals benefitting (i.e. Total male and female farmers multiplied by household size)	4,656 Male farmers / 3,907 Female farmers / Total individual: 8,563
2.2 Number of smallholder farmers selling to aggregating, storage, or processing services (annual): (a) male farmers; (b) female farmers	980 Male farmers / 645 Female farmers / Total individual: 1,625
2.3 Number of smallholder farmers using agricultural extension services and improved management practices (annual): (a) male farmers; (b) female farmer	4,656 Male farmers / 3,907 Female farmers / Total individual: 8,563
Output 3: Increase employment through the development of agribusinesses.
Number of jobs created (FTE) (annual): a) men; and b) women.	a) 825 Men / b) 325 Women / TOTAL: 1,130
Output 4: Increase agriculture-supporting infrastructure in targeted countries.
4.1 Hectares of irrigated land (cumulative) (Ha)	1,552
4.2 Processing throughput/capacity (annual) (Mt)	50,714.00
4.3 Level of installed capacity of clean energy (cumulative) as a result of ICF support. (kW)	700

Zambia

Outcome: to leverage private sector investment in agribusiness and agricultural infrastructure; increase agricultural cross border trade; and generate jobs and income in targeted countries	Progress 2015
Value of capital leveraged and invested in agribusinesses (annual) ($): a) Private, b) DFI	$24,375,304 / $17,000,000 / TOTAL:$41,375,304
Incremental beneficiary household income: a) Outgrowers ($); b) employed ($)	$5,783,323 / b) $2,875,224 / TOTAL: $8,658,546
Value (annual) of agricultural products exported by agribusinesses.	$1,290,359
Percentage of private sector investment in DAC I, II countries
Value of capital repaid to AgDevCo ($)	$350,000
Output 1: Develop or expand agribusiness enterprises that are financed, owned or operated on a commercial basis by AgDevCo
1.1 Number of enterprises created or expanded (annual): a) SME businesses, b) Medium size financial investments, c) Large project development investments	a) 5 / b) 0 / c) 0 / TOTAL: 5
1.2 Volume of investment committed to agribusinesses or agricultural development projects (annual) ($m)	$6,724,000
1.3 Increase in EBITDA (annual) ($)	$1,249,310
1.4 Volume of sales by agribusiness (quantity of goods sold or number of clients serviced at a fee)($)	$3,829,333
Output 2: Increase integration of smallholders into commercial agribusinesses through access to irrigation, processing infrastructure, modern inputs, etc.
2.1 Number of smallholder farmers engaged in agribusinesses (annual): (a) male farmers; (b) female farmers; (c) total individuals benefitting (i.e. Total male and female farmers multiplied by household size)	11,592 Male farmers / 1,475 Female farmers / Total individual: 13,067
2.2 Number of smallholder farmers selling to aggregating, storage, or processing services (annual): (a) male farmers; (b) female farmers	2,213 Male farmers / 594 Female farmers / Total individual: 2,807
2.3 Number of smallholder farmers using agricultural extension services and improved management practices (annual): (a) male farmers; (b) female farmer	11,452 Male farmers / 1,324 Female farmers / Total individual: 12,776
Output 3: Increase employment through the development of agribusinesses.
Number of jobs created (FTE) (annual): a) men; and b) women.	a) 506 Men / b) 17 Women / TOTAL: 523
Output 4: Increase agriculture-supporting infrastructure in targeted countries.
4.1 Hectares of irrigated land (cumulative) (Ha)	40
4.2 Processing throughput/capacity (annual) (Mt)	0
4.3 Level of installed capacity of clean energy (cumulative) as a result of ICF support. (kW)	0