Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: / Water, Sanitation and Hygiene Results Programme to support scale-up efforts
Programme Value: £81,000,000		Annual Review deadline - 14/08/14
Programme Code: 203572	Start Date: 14/08/13	End Date:31/03/18

Summary of Programme Performance
Year
Programme Score
Risk Rating

Summary of progress and lessons learnt since last review
This programme has been operational for four months – the main service delivery contracts were signed in April 2014, and this is the first annual review. Therefore this review focuses on the procurement and mobilisation stages of the programme as results delivery has not yet begun.

Key lessons are around the mechanisms of ensuring that not-for-profits can effectively enage with DFID commercial procurement processes including: entering into contract with DFID (by early market engagement, early sharing of contract documents, and anticipating the constraints that partners are under); and that Payment by Results programmes in WASH can be incorporated into contracts which parties can agree to.

Summary of recommendations for the next year
1. Incorporate a RAG rating for sustainability within the quarterly verification process
2. Continue to liaise with country offices following the Centrally Managed Programmes guidelines.
3. Agree to bring forward the next Annual Review from August 2015 to April 2015
4. Agree to amend the Logframe with a target range which permits a A++ to C scoring, in line with DFID PBR guideance.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203572/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203572/documents/

Outline of the programme

The UK Government is providing up to £81 million to three supplier consortia to deliver Water, Sanitation and Hygiene (WASH) services to at least 4.7 million people. The WASH services that will be supported by this project include improved latrines, improved water supplies and hygiene promotion along with the support to communities, local governments and the private sector to ensure that improvements are financially and operationally sustainable.

This programme was designed during the development of DFID’s payment by results strategy[1] and follows the main thrust of DFID’s approach to PBR, namely: giving suppliers discretion on how output and outcome results are achieved, linking payment to results, and independent verification of the results achieved. This programme transfers delivery risk from DFID to the suppliers contracted under this programme.
[1] https://www.gov.uk/government/publications/dfids-strategy-for-payment-by-results-sharpening-incentives-to-perform

The programme is operational in 13 countries. Under this programme: Plan International is leading a consortium with Unilever and WaterAid to deliver WASH results in Bangladesh and Pakistan; Oxfam is working with Tearfund, ODI and other partners in Liberia, DRC and Kenya; and SNV is delivering sanitation and hygiene in Ethiopia, Kenya, Ghana, Mozambique, Nepal, South Sudan, Tanzania, Uganda and Zambia. The district list has been entered into the DFID geocoding system.

The procurement process was managed by DFID’s Procurement and Commercial Department following “OJEU negotiated” provisions. This included greater flexibility for suppliers to propose to the client (DFID) the means to achieve programme objectives, and an additional negotiation stage before contracting to seek better value for money (VFM) in the contract terms.

In addition to the three main results contracts the programme budget includes provision for an independent monitoring, verification and evaluation (MVE) services provider. This was sourced via DFID’s evaluation framework agreement. Key services of the MVE contract are: third party verification of the results reported by suppliers, assistance in ensuring learning across the programme and evaluation of the approach to payment by results. The latter was included as it is a priority for DFID to learn from the implementation experience of payment by results programmes.

Results under this programme contribute directly to the DFID Results Framework target to reach 60 million people by December 2015. The programme has been designed to incentivise delivery by the required date (December 2015). In addition this programme forms part of a strategy to reduce risk across DFID’s WASH portfolio by working with a diverse range of suppliers with a global results programme which is additional to DFID’s country and multilateral programmes.

The original business case envisaged larger results numbers and a higher overall budget. The ambition for the programme was reduced in September 2013 following increased WASH results forecasts from country offices.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The annual outcome assessment is that while this project is early in the implementation stage the major blocks of the programme have been put in place – the suppliers are under contract and the Monitoring, Verificaiton and Evaluation team are operational. Output level results have not been reported, and were not expected, as the contracts have been operational for only three months.

Overall output score and description

A Procurement and mobilisation stages are now nearing completion. From the procurement we have four suppliers that meet the technical and commercial requirements, and the mobilisation and inception reports and systems are almost all in place. The MVE component scored a “B” because the contract was signed later than envisaged and the MVE inception phase is still underway - this is no negative comment of the MVE team’s early performance. The three results suppliers did not include an inception phase. This MVE inception phase is due to finish in early September.

Key lessons
International not-for-profit organisations (including large NGOs) are willing to engage with DFID procurement processes in open competition with private sector firms and operate under commercial contract terms.
In some cases, such as in this programme, DFID can manage Payment By Results contacts directly without engaging a management agent to operate on DFID’s behalf. Key factors include a limited number of suppliers (we have three), clear results achievement (we are able to use standard DFID methodologies) and a clearly defined independent verification role.
The procurement phase also provided experience of the application of programme management principles to that stage of the programme including: the importance of early market engagement, sharing DFID’s standard contract with partners early in the process, clear TORs, structured approach to negotiation, and ensuring management engagement with key procurement decisions.
Future DFID Payment by Results programmes that involve an independent MVE agent should consider tendering this contract first so that the MVE agent can work with DFID to set monitoring and verification perameters and develop an evaluation plan before implementors are appointed.

Key actions

1. Incorporate a Red-Amber-Green (RAG) rating for sustainability within the quarterly verification process
2. Continue to liaise with country offices following the Centrally Managed Programmes guidelines.
3. Agree to bring forward the next Annual Review from August 2015 to April 2015
4. Agree to amend the Logframe with a target range which permits a A++ to C scoring, in line with DFID PBR guideance.

Has the logframe been updated since the last review?
This is the first annual review. The logframe was updated when the outcome of the procurement process was known.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased access to clean drinking water
Output number per LF		1	Output Score	A
Risk:		Medium/High	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator	Milestone	Progress
Number of people with access to clean drinking water	0	As anticipated, no beneficiaries have been provided with clean drinking water at this stage

Key Points

As envisaged in the business case (EDRM 4116096), the WaSH results programme was tendered through a negotiated competitive procurement process of the Official Journal of the European Union (OJEU). A two stage selection process, led by DFID’s Procurement Group (PrG) with technical input from the WaSH team, took a period of 8 months (Aug 2013 – March 2014) and delivered 3 competitively sourced implementing partners (organised into consortia led by SNV, Oxfam and Plan International). Contracts were signed with each of the 3 impementing partners in April 2014.

In parallel, a Monitoring, Verification and Evaluation (MVE) contract was tendered through a mini competition under the DFID Evaluation and Wealth Creation Framework Agreement. The successful MVE agent was selected in March 2014 and their contract was signed in May 2014.

Given the length of time required to competitively select the partners for this programme we had anticipated that output level results would not begin to be delivered by this stage. To assess whether partners are adequately set up to deliver the results anticipated by December 2014 (the first results milestone in the DFID logframe) structured interviews were conducted with all partners using a standard set of questions (Annex A). Feedback from all 3 implementing partners suggests that they are on track to deliver the results anticipated for this output. As the implementers will only get paid for results that they deliver they all report a strong focus on building effective delivery systems. Oxfam and Plan also report that this programme has a high profile in their respective organisations.

As implementation has only begun in the last few weeks none of the implementing partners have yet sought any direct feedback from beneficiaries, but all 3 have beneficiary feedback loops built into their workplans. The MVE agent will use this information as part of the verification of results process.

Other evidence to justify an “A” rating includes that while output level results have not been reported, one supplier – Oxfam - has submitted a invoice based on early milestones (development of hygiene promotion materials and signing contracts with water supply borehole drilling companies). The evidence submitted has been reviewed by the MVE supplier which confirms that the Oxfam contract is on-track and that the mechanism for MVE is established and is working.

A workshop involving DFID, the MVE team and the 3 implementing partners was held on the 9 June where the process for monitoring and verification of results, at both output and outcome level, was discussed. The MVE agent is finalising the monitoring and verification framework which will conclude by the end of their inception phase by mid September 2014.

The DFID logframe contains annual milestones at aggregate level, but implementing partners have committed themselves to achieving specific sub-sets of deliverables at a number of payment milestones spread over the duration of their contracts (varying between 10 to 15 payment milestones in total). Suppliers will be paid within a month of providing the required evidence and invoice to DFID, and upon verification of the results by the MVE agent.

The overall programme logframe indicators represent aggregate progress from the three suppliers. Comparability is achieved by the use of standard indicators, and by requiring that each supplier adheres to the results methodologies outlined in DFID’s standard indicator methodology notes.

Recommendations
Bring forward the next Annual Review to April 2015 so that progress against the December 2014 milestone can be assessed at an earlier opportunity than the current August 2015 timeline. An Annual Review in April will allow the implementing partners to collate their results and evidence (in January) and submit to the MVE agent who will verify the results (in February) in time for the Annual Review to be prepared in March and submitted in April.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased access to improved sanitation
Output number per LF		2	Output Score	A
Risk:		Low/Medium	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator	Milestone	Progress
Number of people with access to an improved sanitation facility	0	As anticipated, no beneficiaries have been provided with access to an improved sanitation facility at this stage

Key Points
Please see Output 1. The score is on the basis that the programme is currently meeting expectations - suppliers have put in place mechanisms to deliver results. A numerical target was not set for this review so this is not a performance target against logframe milestones.

As with output 1 we had anticipated that results would not begin being delivered by this stage for output 2 as we are only three months into the contract delivery phase. The structured interviews indicate that implementing partners are on track to deliver the results anticipated for this output by the first milestone in December 2014.

Recommendations

As with output 1 the recommendation is to bring forward the next Annual Review to April 2015 so that progress against the December 2014 milestone can be assessed.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased provision of hygiene messaging.
Output number per LF		3	Output Score	A
Risk:		Low/Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator	Milestone	Progress
Number of people reached through hygiene promotion activities through DFID support	0	As anticipated, no beneficiaries have been reached through hygiene promotion activities at this stage

Key Points

As with outputs 1 and 2 we had anticipated that results would not begin being delivered by this stage for output 3 as the contracts were only signed in April 2014. The structured interviews indicate that implementing partners are on track to deliver the results anticipated for this output by the first milestone in December 2014.

Behaviour change is key to the hygiene output. While numerical output targets were not given for this early annual review there is some evidence that progess is on-track against this output. This includes the presentation of approaches to behaviour change given by each of the suppliers at a specific workshop on behaviour change in the WASH Results Programme held in DFID on July 30th, and a technical note on measuring behaviour change prepared by the MVE team.

Recommendations
- Bring forward the next Annual Review to April 2015 so that progress against the December 2014 milestone can be assessed. An Annual Review in April will allow the implementing partners to collate their results and evidence (in January) and submit to the MVE agent who will verify the results (in February).
- Update logframe to agree criteria for output achievement based on the A++ to C scale, to enable scoring of 2015 and subsequent Annual Reviews.
Note for all the output scores that the progress is effectively a “too early to tell” score. Process evidence gathered for this review shows that there is activity taking place in suppliers’ consortia under this programme, but output level results are not expected at this date. The first substantial annual review will take place in 2015, and for this output level results figures have been given in the programme logframe.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved knowledge and experience of delivering of WASH programmes at scale
Output number per LF		4	Output Score	B
Risk:		Low/Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Delivery of outputs of MVE Contract	- Lead verifiers in-place for each contract / - Monitoring and verification strategy in place and functional / - VFM and sustainability metrics established	- Lead verifier in place / - M&V strategy in development and to be agreed by end of August / - VFM and sustainability metrics in development, also to be agreed by end of August

Key Points

The delay in approving the MVE contract led to a delay in setting the monitoring and verification strategy and developing VFM and sustainability metrics which could have been addressed before the supplier contracts started. However following the June workshop the MVE agent has been working closely with implementing partners and DFID to develop these essential frameworks. A second workshop took place on 30 July to discuss the MVE agent’s initial proposals and the frameworks will be signed off and operational by the end of August.

When asked if they felt that the MVE agent had been effectively set up to deliver the expected verification and evaluation roles, the implementing partners said that the MVE agent was technically strong and that MVE structures – although still in development - are promising. Oxfam commented that they have had a lot of contact with the MVE agent who has helped them think through their approach to reporting results at both output and outcome level.

All three implementing partners felt it was unfortunate that the MVE contract was signed later than their contracts, as this has delayed the start of implementation and created some unpredictability over the reporting and measurement of results, and over the issue of payments. The MVE agent also felt that they could have added greater value if they had been appointed earlier – possibly even before the implementing partners were appointed.

There is some concern (from the implementing partners, not from the MVE agent itself) that the MVE agent has conflicting roles in being both the verifier of results, which requires a policeman-like role and the evaluator, which requires them to work collaboratively with the implementing partners. DFID has been clear with the MVE agent that roles and responsibilities should be definied clearly in this inception period.

This programme is medium to high risk given the context in which this programme will work. Already the feedback from Liberia is that WaSH results could be at risk due to the recent outbreak of Ebola. The monitoring and verification framework will be developed to be context sensitive. A more detailed discussion of risk is contained in the risk section of this review.

The implementing partners all feel that this programme will be good value for money for DFID, but it is too early to say at this stage whether this is the case as VFM metrics are not yet agreed and no measurements have taken place. It is hoped that there will be some early measurements available by the time of the next review in April 2015.

Recommendations

[Not directly relevant for this programme]

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The main cost elements of the delivery contracts centre on the administrative costs required for each organisation to deliver the selected activities and for any procurement of goods which may be required to support service delivery. This was assessed at the procurement stage, under commercial criteria, but will also be monitored throughout the programme by the VFM assessments undertaken by the M,V&E service provider (e-Pact consortium).

The administrative costs include staff time and travel costs associated with field work. SNV, Oxfam and Plan have set out clearly who will be involved in managing each project, their role, time, fees and amount of travel (including unit costs for flights and subsistence). DFID Project managers will control fees by applying full economic costing based on a 220 day working year and have liaised with appropriate DFID Departments to ensure the use of favourable rates which reflect current actual market prices.

The main cost elements for the M,V&E services contract will be staff time and travel costs associated with field work, although this element of work has not yet begun. DFID Project managers will monitor closely the involvement of senior staff to ensure they genuinely commit the time they charge for and do not use more junior staff to complete tasks identified as being led by them.

VfM performance compared to the original VfM proposition in the business case

This project utilised a comprehensive competitive tendering process, which included a significant focus on delivery methodology, costs and maximising results against costs within the selection criteria to deliver VFM for DFID. Bids were assessed on Technical and Commercial aspects against clearly weighted criteria; this stimulated financial competition between providers by assessing unit costs for comparable interventions. DFID held an open Early Market Engagement event which attracted over 70 interested parties from the private sector and not-for-profit entities, with a total of 21 Expressions of Interest being received. Seven suppliers (all consortia) submitted full tenders which represents a strong competitive field for this procurement process. The criteria for selection included a commercial criteria which involved a value for money assessment.

There were several clear VFM advantages in using a negotiated competitive process. It introduced a strong competitive element into the process, ensuring that each prospective supplier had to undertake a rigorous and transparent consideration of their approach and methodology, before submitting their bids. DFID were able to negotiate on unit costs, administrative fees and overheads with Bidders prior to awarding Contracts. The contracts awarded to successful bidders (Oxfam, SNV and Plan) offer a commercial advantage to DFID compared to accountable grants or memoranda of understanding arrangements, as DFID retains a stronger commercial leverage over supplier performance with formal contract mechanisms.

Assessment of whether the programme continues to represent value for money

Four key design decisions were taken to assure value for money for DFID:

1. Use of an open commercial competition to identify suppliers. This is a commercially stronger mechanism for holding providers to account for delivery (and therefore overall VFM) than Accountable Grants or Memorandums of Understanding. This approach put not-for-profit organisations in open commercial competition with private sector providers. Having strong competition, and selecting on the basis of providing the most economically advantageous proposal to DFID gives assurance that the selected suppliers represent value to DFID.
2. Direct procurement by DFID, rather than procuring a management agent to run the competition reduced overall procurement time and costs to DFID.
3. Undertaking the programme management function in-house, rather than contracting an external management agent, has resulted in significant cost savings to the department.
4. Using results based payments, which encourages VFM by linking payments from DFID directly to results achieved. The suppliers have agreed to a schedule of payment triggers which are designed to focus and incentivise performance and the supplier is only paid on actual results achieved.

The commercial benefits to DFID are clear – the bid evaluation team were able to select the proposals which represented the best value. The quality of the initial field was high and only experienced consortia were shortlisted. In cost terms, at the final stage strong bids which had weak commercial propositions were de-selected, giving confidence that the procurement process has resulted in proposed contracts which represent VFM for DFID. This programme used a competitive process to drive market competition to maximise the development of outputs of results achieved with the available resources. This £81m programme is estimated to have a positive Net Present Value of £400m and a benefit cost ratio of 4.6 to 1.

Sanitation and hygiene promotion are considered to be two of the most effective interventions for controlling endemic diarrhoea and are the most cost-effective public health interventions (approximately US$3 per DALY averted for hygiene promotion and US$11 for sanitation promotion) ranking higher on this basis than any other form of health intervention (e.g. combating malaria, tuberculosis and HIV Aids)

Hygiene improvements are critical for translating water and sanitation interventions into health outcomes. The adoption of good hygiene behaviours, particularly hand washing, has been shown to have a major impact of health, particularly by reducing diarrhoeal disease. The evidence for such impact is stronger than for water supply and sanitation and is also identified by the World Bank as the most cost-effective health intervention at $3.3 per Disability Adjusted Life Year (DALY).

As a Payment By Results (PBR) programme there is potentially a tension between PBR and measuring VFM. The contract price (the total contract budget for the given result) is set in the contract and so if the cost drivers change over the course of the project DFID does not have recourse to seek savings from the supplier as the contractual basis is results delivery rather than input payments. Ahead of this annual review this point was discussed with the DFID Value for Money Director who indicated that from a VFM perspective the use of competition and contracts to drive value for DFID in the procurement process outweigh the loss of post-contract negotiation space in the case of suppliers’ finding delivery efficiencies, reducing costs and benefiting from improved margins.

The next AR will be able to provide a detailed breakdown against Economy and Efficiency VFM metrics as the review will have taken place after results based payments have started.

Quality of financial management
The operating contexts for the proposed interventions, which includes fragile and conflict affected locations, places some upward pressure on overall costs. The required process for assuring that suppliers follow DFID Duty of Care procedures has been followed and these costs will be reflected in the overall price. There will also be an element of suppliers pricing risk into their overall cost. This is in line with DFID’s Payment By Results guidelines whereby risk is transferred but reflected in the costs. These upward pressures were managed in the procurement process through the commercial evaluation of the bids, and will be further reviewed during the contract delivery period by tracking unit costs of delivery.

Date of last narrative financial report	Not yet due.*
Date of last audited annual statement	Not yet due.*

*Financial audits are not required for Payment By Results contracts.

E: RISK (½ page)

Overall risk rating: Medium- High

Overview of programme risk
The headline programme risk of under-performance or delay has been transferred from DFID to the three suppliers. If any of the contracts under perform then payments will be proportionally reduced.
Each supplier manages risk within each supply contract (this is good practice as the risk-owner is therefore with the party best able to manage the risk).

Several programme countries are high risk fragile-state operating environments. The programme minimises risk to progress in these by operating in several countries, and has the ability to move resources between and within countries if the operating context is not permissive in certain countries. Since programme design, new risks include increased instability in South Sudan, and the West Africa Ebola outbreak.

Another key risk is poor sustainability with early system failure. This has been reduced by selecting providers based on the strength of the sustainability approach. This annual review recommends an additional step of a Red-Amber-Green (RAG) sustainability rating given by the MVE provider for early identification of particular sustainability concerns during the implementation phase.

DFID’s duty of care policy has been followed, with each supplier agreeing to the duty of care provsisions within the contracting mechanism.

Measures to mitigate risks of corruption and fraud are key. This has been a strong aspect of the commercial checks of suppliers undertaken by DFID’s Procurement and Commercial Department. All suppliers are bound by contract under this programme and the penalties are laid out in the contract documents.

Outstanding actions from risk assessment

Further monitor sustainability – specific action: MVE supplier to provide a RAG rating on suppliers’ approaches to sustainability (to provide early warning of process-failings which may contribute to poor sustainability).

Further clarification on force majeure risks – to be included in the design document / inception report of the MVE provider.
Update the overall programme risk register (DFID, MVE, and Suppliers, by end August 2014, incorporating views of programme stakeholders).

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
This programme involved a lengthy procurement exercise to ensure the successful identification and contracting of the most technically appropriate and cost-efficient delivery partners available. Once contracted, DFID worked closely with the 3 selected organisations/consortia to devise a detailed action plan for each, which clearly set out a roadmap of dates of specific deliverables. This roadmap is tied in to the payment by results focus of the programme through a milestone payments mechanism to ensure that progress is closely monitored and verified.

The milestone schedule covers the full range of deliverables from the beginning of the work, through to the hard deliverable target of 31 December 2015, and on through the subsequent sustainability targets up to the end of the programme in 2018. At this time, each of the 3 delivery partners are on-track against their respective agreed target schedules.

Performance of partnership (s)
This programme is actually a series of partnerships: between the DFID WASH team and each of the three delivery agents (each of which are actually consortia of a number of organisations, around 11 in total, in addition to many other local partners and sub-grantees); between DFID and the MV&E agent and; between the monitors and each delivery team. In addition the WASH team have worked hard to encourage collaboration, cross-team information sharing and joint lesson learning within the various partners, through a series of workshops and meetings which all parties attended.

The most recent of these involved a workshop with the MV&E team who set out their requirements and what they could provide to each contractor to further improve and develop their reporting processes. A workshop on Behaviour Change took place on 30th July with DFID Human Development Department’s behaviour change adviser and an expert from the London School of Hygiene, to discuss new or alternative methods of changing behaviours around WASH practices.

Asset monitoring and control
Due to the payment by results (PBR) nature of this programme, the issue of programme assets is not applicable as DFID are not directly involved in any procurement undertaken by partners. That said, the monitoring visits and spot checks undertaken by both the MV&E team and ourselves in the WASH team, will include an element of scrutiny into the programme management practices of the delivery agents and any sub-grantees they may employ, to ensure that due diligence is maintained and that any financial mis-management is discouraged.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable

H: MONITORING & EVALUATION (½ page)

Learning
This programme represents significant learning for DFID in three key areas: the application of Payment By Results in WASH; direct management of programmes rather than using management agents; and the use of OJEU Negotiated procurement to competitively source contracts where many suppliers are not-for-profit entitites. The programme has structured contracts around payments linked directly to output and outcome level results achievement, using an independent verifier to provide third-party assurance that results have been achieved. DFID is further investing in learning through a process evaluation of the payment by results mechanism. The second learning area on OJEU negotiated procurement has been communicated to relevant colleagues considering this route, and the WASH Team remains available to discuss with others any issues related to this procurement option. Finally the programme has had a positive experience with running a competition which has attracted not-for-profits including international NGOs to bid for DFID contracts. To encourage competition we held a large early-market engagement session, ensured early sharing of DFID standard contracts, and ensured that the TORs were clear and specific.

Evidence and evaluation
This programme has a structured approach to Monitoring and Evaluation involving strong results monitoring systems within the supplier contracts, and a resourced independent monitoring function. Results monitoring (and third-party assurance) are central to the payment mechanism and therefore at the heart of this programme. This represent good practice according to DFID’s payment by results strategy.

It is important that lessons from this PBR investment are captured and effectively disseminated, both as a feedback mechanism within the programme and as DFID and other donors require evidence from PBR implementation experiences for the design of future programmes. The evaluation investment under this programme, which includes a process-evaluation on the PBR approach, will contribute both to DFID knowledge on PBR (via close working with Evaluation Department) and also knowledge across development partners via a dedicated WASH PBR network that DFID co-convenes with the Gates Foundation.

Monitoring progress throughout the review period
The evidence gathering for this Annual Review was led by the current WASH Team Leader who was not involved in programme design. It involved structured interviews with programme stakeholders.

The monitoring strategy for the period between now and the next annual review will involve:
- Suppliers monitoring reports
- Monitoring undertaken by the MVE supplier
- Where possible, visits to programme countries by DFID staff.
- Direct beneficiary feedback: within suppliers’ delivery channels, directly to the MVE supplier, and to DFID during monitoring visits.
The WASH Team have worked closely with DFID country teams during the design and contracting of this WASH Results Programme. Advisers in-country will receive all monitoring reports regarding work in their country and will be able to provide additional evidence.

Annex A Questions for 2014 WASH Results Programme Annual Review

Methodology
Carol Anne to email questions to informants in advance.
WASH Team Leader to undertake scheduled phone interviews (max 30 min) with key informants during week of 14 July.
Respondents also to be invited to follow-up to questionnaire by email.

A: Introduction and Context
1. Has there been any significant change in context which affects the programme?
2. In the project design (either the DFID business case or the consortium bid) do you think that there are any weak assumptions which may threaten the delivery of project outcomes?

B: Performance and Lessons
1. Do you have any examples or evidence of weak performance, by any partner, in the WASH Results Programme? (or areas of concern where under-performance may arise)
2. Are there any key lessons that you or your partners have learned from the procurement and inception phases of the programme?
3. Is the log-frame fit for purpose (to track overall programme output and outcome progress)? Do you have any recommendations for log-frame improvements?

C: Risk
1. Are you on track to deliver the results in this programme? (yes/no, any comment)
2. In your opinion is the WASH Results Programme a High, Medium or Low risk project?
3. What are the key risks to the project?
4. Are there any additional actions (for any party: DFID, supplier, or the MVE team) that would reduce risk in the project?

D: Value for Money and Financial Performance
1. At this inception stage – what is your assessment of the key cost drivers in the project?
2. In your opinion, is this project likely to represent VFM for DFID? (yes/no, any comment)
3. Do you have any comment or recommendation for how DFID could further ensure value for money in the WASH Results Programme?

F: Commercial Considerations
1. Is the project on-track? If not are there any remedial actions that you would recommend?
2. Has the MVE supplier been effectively set up to deliver the expected verification and evaluation roles?
3. Could DFID be a more effective partner?

H: Monitoring and Evaluation
1. Is there any new evidence available which challenges the project design or rationale?
2. What monitoring activities (if any) have taken place since programme launch? Has there been any feedback from beneficiaries? If not, is this planned?

Leonard Tedd
7 July 2014

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process