Annual Review - Summary Sheet

Title: Ideas to Impact – Innovation challenges for climate & environment technologies for the poor / (Innovation prizes for climate, energy and water, Crowd Power and Frontier Technology Livestreaming)
Programme Value: Ideas to Impact programme’s total value is £13,754,350 (consisting of £10,909,350 for prizes, £845,000 for the Crowd Power research programme (started April 2015) and £2,000,000 for Frontier Technology Livestreaming (launched November 2016))		Review Date: April 2017
Programme Code: 201879	Start Date: April 2014	End Date: April 2019

Summary of Programme Performance
Year	2015	2016	2017	2018	2019
Programme Score	A	A	A
Risk Rating	High	High	Major

Summary of progress and lessons learnt since last review
The Ideas to Impact programme is performing well overall across the 3 components, and it is on track to meet the outputs and outcomes specified in the logframe, and achieve its aim of building the evidence base on innovation prizes and crowd funding platforms for development.

Over the past year, 4 prizes for water, sanitation and climate information have moved from Stage 1 into Stage 2, which is the implementation stage, during which impacts will be realised. A prize for refrigeration was launched in September 2016 with Global Lighting and Energy Access Partnership (GLEAP) and USAID. This includes field-testing products which has resulted in significant market attention. All of the prizes are particularly agile and adaptive (i.e. designed to be flexible and easily changed in response to lessons about running prizes), allowing for their redesign and/or relaunch (e.g.Dreampipe) and enabling them to perform across a variety of changing and challenging ecosystems. The consortium teams are working well together across the different prizes, and engage in extensive collaborative working and lesson learning with an increasingly broad range of stakeholders. An independent Mid-Term Review (MTR) has been undertaken to identify what is working well and the challenges facing the programme, and has also made recommendations for future resourcing and timeframes. The evaluation work (output 3) has also made good progress this year, with all Evaluation Methodology Notes completed and Phase 1 evaluations of all on-going prizes started, capturing robust evidence on whether innovation prizes work in development, and under what contexts. In February 2017 the Ideas to Impact programme hosted an innovation workshop with DFID, USAID and Rockefeller to share emerging lessons from the programme.

Key lessons identified by the MTR for the prizes component are:
- The main challenges in “prize ecosystems” identified across the programme tend to centre on gaps in the capacity of those attempting to solve the problems (e.g. applicants for the prizes/solvers), including their capacity to prepare applications, engage potential investors to leverage additional finance, and to network with others to enable collective problem solving.
- Some highly innovative solutions may be at risk of being ignored as I2I may have been too strongly incentivised to maximise direct beneficiary numbers to achieve the impact level indicators. For example, entry for Dreampipe II required the target population to be greater than 150,000; it is possible that innovative solutions may have come from the smaller locations which would have had significant indirect effects on wider populations through longer-term scale up.

Ideas to Impact Stage One Prize Winners

Pawa Farm won first prize in the Climate Information Prize for an innovative Virtual Agro-weather Advisory Platform to provide timely, relevant and usable weather and climate information to Kenyan farmers. The information will include agronomic advisories modelled in line with the projected weather/climate conditions to enable farmers to make informed decisions and improve farm management practices under conditions of climate risk.

In June 2016, three districts were awarded a total of 75,000 GBP for coming top of the first stage of the Urban Sanitation Challenge in Ghana with their liquid waste management strategies, including the Jasikan district which has a population of 25,000 people and an open defecation rate of 48.7%. The Jasikan district strategy included activities such as the delivery of community mobilisation and hygiene education campaigns, the construction of household and public latrines, the purchase of a vacuum truck and the construction of a wastewater treatment plant. Funding is being provided by reallocating assembly budget and also by leveraging private sector investment.

One of three winning entries within Dreampipe was from Wonderkid Multimedia (Kenya). The concept is a mobile-based system that improves metering and billing in water utilities, thus reducing commercial losses. Using the Mobile Field Assistant (MFA) software, meter readers use basic GPS-enabled smartphones to send readings directly to the utility’s billing system. A bill is then generated and the customer is alerted by SMS, thereby reducing opportunities for error and fraud as well as cutting billing-cycle times. Over 26 utilities in Kenya are looking to contract Wonderkid to provide this service.

Care Nepal, one of 15 winners of the Protsahan Prize of the Adaptation at Scale challenge, has successfully demonstrated the use of Payment for Ecosystem and Community Resilience in the Lamjung district of Nepal. It has introduced payment for sedimentation retention and conducted capacity building training in the same area to reduce landslides, river side cutting, siltation of water bottlenecks and drying up of springs. Care Nepal has also provided support in establishment of a basket fund for the following activities - water resource management, disaster risk reduction and biodiversity conservation in the targeted areas.

The crowdfunding for energy access (Crowd Power) component, managed by Energy4Impact, is working with 8 crowdfunding platform partners, focusing on donations (2), debt (3), equity (1), reward (1) and one hybrid of equity and debt. Four funding modalities are being tested; gift vouchers for redemption during specific campaigns, first loss protection for debt, matching contributions from the crowd and lump-sum payments. 23 campaigns have been launched since April 2015; 20 are complete and 3 are currently live. Completed campaigns have raised a total of £1.13 million utilising £263,200 in Crowd Power funding, at a ratio of approx. 4:1. Five campaigns in the reporting period (all debt raises) have each raised more than $100,000 (£75,000), with the largest reaching €150,000 (£123,200). The average DFID support for four of the biggest raises was £14,300 each, using first loss protection, lump-sum, vouchers and 1:1 matching.

Key lessons for the Crowd Power programme are:
- Debt-based platforms appear to be lower risk and have higher level of transparency than other platforms, with scope to absorb more funding. This is evidenced by some platforms now offering larger loans directly to social enterprises – a growth area in off-grid energy crowdfunding.
- One-to-one match funding for donation and reward campaigns, where 50% of a donation campaign target is offered, can create an incentive to “self-fund” through proxies (among other methods) to take advantage of the matching offer is created.

Frontier Technology Livestreaming (FTL) was launched by Minister Wharton in November 2016. The Frontier Technology Hub managing the programme has been quick to establish itself and has successfully launched its first call across DFID (Nov 1st – Dec 1st 2016). It received 14 applications, of which 6 have moved forward with design and development of pilots in Nepal (2), Tanzania (2), Zimbabwe and the Middle East and North Africa Department (MENAD). Technologies covered include drones, white space WiFi, Internet of Things (IoT) for road maintenance and Pay As You Go (PAYG) water taps. Overall, FTL has received a good response from DFID country offices, the private sector and technology providers. A second round will be launched in May 2017.

Summary of recommendations for the next year
A no-cost 12 month extension to the end of March 2020 is recommended in order to allow for the completion of the FTL component and a further prize in the energy space and replication of the sanitation prize, and to provide sufficient time for the evaluation outputs to be produced and the research uptake strategy to be implemented. No additional funding will be required for this; current funds will be reallocated (see below).

Key recommendations for the prizes component are:
- Building on the recommendations of the MTR the Ideas to Impact programme savings should be reallocated to areas that increase research uptake, focus on sharing lessons, capacity building of solvers, replication and scale up and crowding in additional finance for prizes, and to provide more support to the Evaluation team. The I2I team will provide DFID with a revised budget and associated work plan by end of April 2017 for approval.
- Communication needs to be strengthened by providing more resources to the Communication Manager and developing a research uptake strategy by June 2017. This will include continuing engagement with stakeholders bought together following the Feb 2017 Innovation Workshop.
- The programme should focus on leveraging inward finance to achieve the prize aims and to maximise results and impact. Engagement with potential investors (donors, impact investors, the private sector etc.) should be strengthened to draw in the necessary funds and technical support. The I2I team will develop an engagement framework for focusing on potential investors against each prize by end June 2017.
- The programme should plan additional capacity building activities, run by the implementing agents, in order to meet the needs of the prize applicant/solvers and to maximise the impact of the prizes. This will be incorporated in to all the prizes by end September 2017.
- Lessons learned from the prizes so far are likely to offer economies of scale for replication and scaling up; relevant opportunities should be actively pursued over the next year by identifying the prizes that are best suited for replication and contexts where replication could be successful. The prize plan for replication should feed into the work plan by end April 2017.

Key recommendations for the Crowd Power component are:
- Several advantages of using debt-based platforms have been identified; a larger proportion of the funding has been, and should continue to be, deployed to debt crowdfunding platforms in order to achieve the greatest impact.
- Crowdfunding (particularly of donations) is already a mechanism through which very early stage ventures and charities seek to formalise, and hopefully amplify, the amount of funding which they can raise from family and friends. It is recommended that the maximum amount available in matched funding is reduced to an amount proportional to existing average raises on the platforms, and that work with the platforms, including carrying out due diligence, is continued. Match funding should not be stopped completely to avoid this risk, however.
Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3954668.docx
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4456243.xls

Outline of the programme
Ideas to Impact[1] is a £13.75m programme supporting research and development (R&D) in energy, water and climate adaptation solutions for developing countries over a five year period, ending in April 2019. A key objective is to test various funding mechanisms for catalysing innovation on intractable environmental and developmental problems. The programme has 3 different components which focus on prizes, crowdfunding and frontier technology.
[1] More details are available on the programme website: http://ideastoimpact.net/. Previously known as Innovation Prizes for Environment and Development (IP4ED).

Overall, the Ideas to Impact programme aims to improve the lives of around 12 million people (directly and indirectly). It will achieve this by supporting:
1. At least 148 new, affordable and accessible technologies, solutions or processes developed for poor people
2. At least 22 affordable and accessible technologies, solutions or processes deployed to poor people
3. At least £35m of new private investment in technologies and business models attracted in
4. At least 50% of entrants applying for prizes are new teams/organisations to DFID’s existing portfolio of grantees in this area

The largest component, Innovation Prizes (£10.9m), is stimulating and incentivising the development and deployment of solutions for low-income consumers, focusing on improving poor people’s access to affordable clean energy services; safe drinking water and improved sanitation; and resilience to climate change. The programme was launched in April 2014 to test the application of innovation prizes as a funding mechanism to achieve development outcomes. An innovation prize is defined as “a financial incentive that induces change through competition”. More specifically, to win the prize, solvers need to compete against one another to meet a set of specified criteria, which if met, entitles them to some form of financial (and reputational) reward. Innovation prizes aim to stimulate or induce innovation rather than reward good performance ex-post, as a more standard recognition prize (also referred to as “award”) would do.

IMC Worldwide leads a consortium to manage and deliver the prizes programme. The programme is structured around thematic leads on water, sanitation and hygiene (led by Tremolet Consulting); low carbon energy (Energy for Impact (E4I), formerly Global Village Energy Partnership (GVEP)); and climate adaptation (Institute for Development Studies (IDS)). The consortium also includes experienced prize designers from InnoCentive, with research, evaluation and learning led by ITAD with support from IDS. Over the past year IMC has also worked with GLEAP/CLASP on a refrigeration prize and is looking to develop an additional prize on either cold chain or solar cooking with other partners.

Rather than looking for purely technical solutions, solutions to prizes under Ideas to Impact are involving combinations of systemic, social and technological change. Following the design phase, the programme has launched several innovation prizes to address five well-defined problem statements in the area of energy access, water and sanitation and climate adaptation:
1. Clean City fosters innovative approaches to integrated sanitation in small cities that are currently not receiving adequate investment (Ghana)
2. Dream Pipe stimulates the design and implementation of an innovative financing and contractual arrangement for reducing non-revenue water (water lost through leaky, unmaintained pipes) in DFID target countries (global). The applications submitted in Dreampipe stage 1 were of a disappointing quality and number. As a result, the planned trajectory was stopped and the prize was redesigned by the prize team, in close coordination with several stakeholders and DFID. Phase 1 of Dreampipe II was launched in October 2016; it has so far received positive feedback and the prize is on track to complete its three phases by the end of 2018.
3. Clean Cooking aimed to address challenges in both the supply and demand of LPG cooking solutions to enhance the market for clean cooking solutions (Ghana). The prize was closed a few months after awards were made in January 2016. It has since provided valuable learnings for the design of the other prizes.
4. Adaptation at Scale supports the replication and growth of successful local innovations for adaptation to climate change (Nepal).
5. Climate Information is making sophisticated climate information more useable for the poorest (Kenya).
6. A new Refrigeration Prize launched in September 2016 is focusing on the launch and field testing of off-grid refrigeration technologies in order to stimulate market interest and potential investment in the sector (global). Follow-up prizes on solar cook stoves and cold chains (temperature-controlled supply chains) are currently being assessed and designed (India and Global respectively).

The second component of the Ideas to Impact programme, Crowd Power, is researching the use of crowdfunding by donors to incentivise support for businesses focused on delivering energy solutions for the ‘bottom of the pyramid’. Crowd Power, which has a budget of £845,000, is being managed by Energy for Impact and will run from April 2015 to March 2018.

Crowdfunding could play an important and complementary role to traditional donors, banks and capital markets in providing finance for developing country entrepreneurs and SMEs. Developing country enterprises face particular challenges mobilising funds to test and develop business models, and to finance early stage growth. Crowdfunding could potentially help fill this gap, enabling ventures to grow to a point where they can attract more mainstream finance. Currently these early stage funding needs tend to go unmet, or are met through donor aid. Through Crowd Power DFID is playing a key role in enhancing the donor community’s understanding of how to facilitate the flow of funding to the best social impact ventures, by encouraging financial flows through a range of different platform types in support of social enterprises active in DFID priority countries.

To this end, Crowd Power will work with around 40 different campaigns using a number of types of interventions such as donation, debt and equity sites to mobilise finance for ventures in the energy access sector, and evaluate the impact of that funding on the businesses and the communities in which they are deploying their solutions. The programme will provide direct benefit to around 50-100 individual ventures through facilitating financial support, while also generating a rich body of learning about the characteristics and advantages of different types of platforms and interventions.

Finally, a new component called Frontier Technology Livestreaming (November 2016 to October 2019) will provide funding for the field testing, evidence and experience-generation of innovative “frontier technologies” such as 3D printing, the Internet of Things and drones in order to explore how they can positively impact development challenges like connectivity, health and education, humanitarian response and productivity. As with the prize funding component, FTL is being managed by IMC. The programme plans to deploy 15 technologies across DFID programmes, allowing for the building and sharing evidence of what does and does not work. The total budget for the programme is £2million over 3 years.

As an innovative research programme for DFID, Ideas to Impact as a whole has a strong emphasis on evaluation, lesson-learning and research uptake. The programme will launch a series of research papers, including papers on each thematic area, providing evidence of the problems and analysis of opportunities; evaluation papers on completion of each prize process; and an analytical guide providing a framework for using innovation prizes in a developing country context.

## B: PERFORMANCE AND CONCLUSIONS

Annual Impact and Outcome Assessment

Impact: Trajectory to number of beneficiaries
The target beneficiary numbers of 12 million by 2025; are likely to be achieved as they will now include not only prizes but also crowd power and frontier technology. Also the number of beneficiaries would increase significantly if both direct and indirect beneficiaries were counted and the effects of prizes such as changing people’s perceptions and replication were included. The current forecast is 8.7m (see Table 1) by the end of the programme, however these numbers are tentative and will be refined during Stage 2 of the prizes.

Impact Indicator 1: Number of people with access to water and sanitation (SDG6); and /or access to affordable, reliable, sustainable and modern energy services (SDG7); and/or strengthened adaptive capacity to climate related hazards (SDG13.1). The process for calculating these beneficiary numbers was most recently agreed between IMC and DFID in March 2016. The beneficiary numbers have also been disaggregated by gender and youth at an individual prize level (Table 1). IMC also look at maximising opportunities for gender and youth across the prizes this is covered in the monitoring section of the report.
Table 1: Forecast beneficiary numbers (estimated February 2016)
Prize name	Current forecast beneficiary numbers / (direct and indirect)
	Total	Female	Youth
Sanitation Challenge	5,727,922	2,932,696	2,193,794
Dreampipe	2,171,860	1,111,992	528,196
Adaptation at Scale	55,358	29,008	27,679
Climate Information	738,144	371,286	369,072
Clean Cooking	Prize closed
Global Leap Refrigerator Prize	28,500	14,582	6,921
Total	8,721,784	4,459,564	3,125,662

Crowd Power has thus far funded 23 campaigns; in total these are expected to reach over 125,000 beneficiaries (this number will continue to increase as more campaigns are supported). Additionally, the 23 campaigns have generated 117 jobs (of which 114 for local workers) and reduced CO2 emissions by at least 30,000 tonnes. Numbers are not yet available for FTL. However, beneficiary numbers are likely to be low prior to 2025 anyway, as the component focusses on early stage innovation.

### Progress on Outcomes
With the exception of Outcome Indicator 3, each of the four Outcome indicators is generally on track. Work within Indicators 3 and 4 will require a particular focus over the next year.

Outcome Indicator 1: New ideas, concepts, technologies, systems or processes developed that are judged to have award value. This indicator is largely on track (Table 2), and the programme is developing and supporting innovation (principally new concepts and plans). It was planned that in total 108 new ideas / technologies etc. would be launched by March 2017; 111 have been launched: the target has largely been exceeded due to Crowd Power, the Sanitation Challenge and Refrigerator prize.

Table 2: Progress against Outcome Indicator 1 (as of end December 2016)
Prize name	New ideas, concepts, technologies, systems or processes developed that are judged to have award value, as defined prior to launch of the prizes, expected by March 2017	Current Status
Sanitation Challenge	50 Liquid Waste Management Strategies expected; assume 14 will be award-worthy.	On track – 48 Strategies submitted; 21 judged to be award-worthy.
Dreampipe	Dreampipe I: 5 Concepts to be award worthy / Dreampipe II: Expect at least 10 good concepts submitted in Phase 1	Not achieved – 3 concepts awarded / On track – Expect to receive 10 by close of Phase 1 in June 2017
Global Leap Refrigerator Prize	20 nominations expected / 30 Products tested	Exceeded expectations – 32 nominations received / On track – 30 selected for testing
Adaptation at Scale	Estimated 45 applications; 15 to be awarded	Exceeded expectations – 59 applications received; 15 awarded
Climate Information	25 New technologies, partnerships, systems and processes developed in Stage 1	Not achieved – 13 prizes awarded
Crowd Power	15 campaigns launched by March 2017	Exceeded expectations – 23 campaigns launched
FTL	15 new technologies, split between 5 per call	On track – 6 selected for Call 1

Outcome Indicator 2: Prize driven activities delivering multiple innovations that benefit low income households. The focus of stage two for each of the prizes is on incentivising and rewarding deployment of innovation in its various forms. All of the prizes are on track (Table 3).

Table 3: Progress against Outcome Indicator 2 (as of end February 2017)
Prize name	Deployed innovation expected by March 2017	Status
Sanitation Challenge	15 Metropolitan and Municipal District Assemblies (MMDAs) undertaking Stage 2 activities	On track – 17 MMDAs progressing in Phase 2
Dreampipe	2 mechanisms scaling up	On track – Will know on conclusion of Phase 2 and launch of Phase 3 in summer (June) 2018.
Global Leap Refrigerator Prize	20 refrigeration products field tested for the first time with entrepreneurs in Uganda	On track – 20 fridges going for testing
Adaptation at Scale	2 partnership models scaling up adaptation services	On track – Will know upon conclusion of Stage 2 in January 2018.
Climate Information	2 new commercial businesses / otherwise-funded service operations actively delivering climate information services	On track – Will know upon conclusion of Stage 2 in August 2018.

Outcome Indicator 3 – Prizes stimulate new investment in technologies and business models. It is still very difficult to predict how much has been invested; however it looks unlikely that the programme will meet its target of £35m because the nature of the programme has changed since the design phase and most prizes do not aim at developing business models that work with commercial investors. A priority action for the year ahead will be to enhance the programme’s work with potential investors.

Outcome Indicator 4 – Discussions among key stakeholders around innovation prizes in development or for social outcomes. The programme is stimulating discussions across the scientific community and development sector, and interest in replicating specific prizes has shown encouraging signs. A concrete example of this is the Innovation Workshop held in Feb 2017. There are various lessons learnt which could be captured and shared more widely while the prizes are in progress, and not just through the evaluation reports. This will therefore be a focus for the year ahead.

Overall output score and description: A – on track
Progress against the three Outputs is largely on track. With the exception of the Sanitation Challenge, progress against Output 1 milestones is on track for every prize. Likewise, all milestones for Output 3 are on track. For Output 2, some milestones are on track, although some are delayed (e.g. energy access prize learning paper produced, and website updates).

Key Lessons
Key lessons from the prize component include:
- Across the prizes a need for capacity building support for solvers/applicants has been identified in order to fully meet the objectives of the programme and broaden the range of prize “effects”.
- As the prizes have moved into Stage 2 it has become clear that the results framework against which the programme reports does not give a full picture of what the prizes are achieving. While the full extent of the benefits and effects of the programme will emerge during Stage 2, there are clear signs that the programme is generating effects that go beyond the ones identified in the results framework. These range from sharing best practices to producing changes in the political landscape – these additional effects have been captured in the theory of change for each prize. Measuring the success of the programme only in terms of direct beneficiary numbers is therefore potentially limiting.
- The programme is currently looking into how to best integrate and report on these additional effects.
- While internal communication is strong, external communication work (particularly output 2) has been under-resourced and under-prioritised. This will be addressed in the coming year.
- Inward investment leveraged is currently predicted to fall short of the target £35 million, and focusing energy and resources in this area is a key priority for next year.
- Managing evaluation within the tight timeframes of the prizes has proved a challenge, as the length of time between close of phase 1 and launch of phase 2 does not always allow for final evaluation reports. While the final reports will be useful for wider programme evaluation, the prizes have been able to benefit from preliminary findings. To address this, meetings and feedback on a more informal and ad hoc basis are proposed to ensure the programme is continuously adapting and learning.

Key lessons from the Crowd Power component include:
- Debt is a particular area of growth for crowd funding. Debt-based platforms appear to be lower risk and have higher level of transparency than platforms using other modalities, with scope to absorb more funding. This is evidenced by some platforms now offering larger loans directly to social enterprises – a growth area in off-grid energy crowdfunding.
- Equity campaigns can raise significant funding, but are infrequent and transaction sizes are particularly variable. Large equity transaction sizes, relative to the off-grid energy crowdfunding market, must be viewed in context as they may distort perceptions of the sector. Despite a changing regulatory environment, the pattern in growth indicates that equity crowdfunding for off-grid companies is unlikely to scale in the near term.
- Donation campaigns tend to impact vulnerable groups and grassroots organisations. However the mechanism is inefficient with the slowest funding rates of all modalities and campaigns often do not reach their target.
- Reward crowdfunding is particularly good for ‘mobilising the crowd’; thereby gaining momentum and increasing coverage. It therefore particularly suits applications such as smaller campaigns by very early-stage companies raising funds from family and friends, and larger campaigns by companies offering the crowd a novel product. However these are relatively infrequent. It is unlikely to be a scalable solution in the energy space in the near term as few companies have a novel product valued by western consumers. For smaller raises (~£15,000) it is likely to continue being a useful tool to formalise and aggregate contributions from friends and family.
- One-to-one match funding for donation and reward campaigns, where 50% campaign target is offered, can provide an incentive to “self-fund” through proxies (among other methods) to take advantage of the offer that is created. The team has revised platform and campaign maker’s contracts to specifically outlaw gaming, and checks patterns of contributions against platform norms, and investigate anomalies, as pre-emptive action on potentially fraudulent campaigns. Where it is believed irregularities have occurred copies of bank accounts are requested, and matched funds are not disbursed until the team is satisfied the campaign maker is acting legitimately.
- Platforms sometimes carry out very light due diligence and controls on campaign partners. The team has terminated the partnership with one platform because of their lack of controls and responsiveness following an issue with one of their campaigns.

Key actions
The key challenge currently lies with Outcome Indicator 3 (investment leveraged), where the programme is in danger of not reaching the £35 million target. Promoting investment and leveraging inward finance towards the business ideas and innovations under the programme is a priority action for the year ahead.
There will be a strong focus on achieving maximum impact now that prizes are in implementation stage:
- Reallocation of funds and full review of work plans and budgets across the prizes
- Engaging with key stakeholders and focusing on disseminating learning, and strongly pushing the agenda in learning about innovation in development
- Building the capacity of applicants, through providing them support to fully implement, monitor and evaluate their ideas in order to achieve maximum programme impact.

Has the logframe been updated since the last review? Yes. The programme has been updated to include Frontier Technologies Livestreaming and Crowd Power (Annex 1).
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Five innovation prizes launched and three successfully awarded; and at least 20 crowdfunding campaigns for energy access successfully launched.
Output number per LF		1	Output Score	A
Risk:		Major	Impact weighting (%):	70
Risk revised since last AR?		N	Impact weighting % revised since last AR?	No

Indicators		Milestones	Progress
1.1	Prize implementation plans, resources and tools in place	Innovation prize design teams in place and operational in 2014/15 / Prize implementation and steering committees in place in 2015/16	Achieved – Team in place / Achieved – Prize teams in place and implementing
1.2	Prizes launched	Cumulative total of nine prizes launched by 2016/17	Achieved – Nine prizes have been launched thus far. One prize closed at stage 1; three are currently in stage 1 and three prizes are in stage 2.
1.3	Prizes awarded	Two prizes concluded and at least one awarded in 2015/16 / Three prizes concluded and at least two awarded in 2018/19	Achieved – Clean Energy prize concluded and awarded; Climate Information prize stage 1 concluded. / On track – Clean Energy prize concluded; 5 other prizes on track to be awarded by November 2018.
1.4	Crowdfunding platforms launched campaigns for energy access with match DFID funding.	At least 15 campaigns launched on different crowdfunding platforms by March 2017. / £1.14m raised in match financing by campaigns for energy access ventures by May 2017. / Progress towards direct benefit to at least 50 individual ventures focusing on the poorest segment (BoP) energy access by end of project.	Exceeded – 23 campaigns successfully launched to date. / Achieved – £1.13m catalysed using £263,500 from DFID. Total of £1.39m catalysed including Crowd power funding. / On track – Crowd power has directly benefited more than 37 individual ventures, with a recent campaign benefitting a currently-unknown additional number of ventures.

Key Points
All prizes have made good progress in 2016. Several prizes have progressed from Stage 1 to Stage 2 of the competition process. Some prizes have faced challenges, but have been redesigned to overcome these. For example, the Dreampipe Challenge was redesigned and relaunched, and the energy access prize has been refocused under Global LEAP awards. The programme has also had great success with the launch of Frontier Technologies Livestreaming, which is performing above expectations and provides another interesting research angle for the programme.

Output 1 work has particularly demonstrated how valuable internal learning is in helping the programme adapt to improve efficiency and effectiveness. The learning approach adopted includes building in reflection time post award of stage 1 to review the approach to Stage 2 to maintain focus on achieving the results wanted, and internal learning within the team on operational processes such as judging. Additionally the programme benefits from a centralised approach, with the majority of prize managers being full time IMC staff which allows for extensive internal and informal learning and lesson sharing.

The Crowd Power component has already delivered results and is largely on track. In the last year, four additional platforms partners were engaged, bringing the total partnerships to nine, although one was terminated after their failure to address concerns relating to a particular campaign on their platform.

Summary of responses to issues raised in previous annual reviews
- Energy access: The programme is investing in two new energy prizes, having considered a range of options. The first is the refrigeration prize run as part of the GLEAP awards in partnership with USAID, Power Africa and the US Dept. of Energy, whilst the second is a sister prize under design promoting innovation in cold chain storage for markets. This prize is due for launch in 2017. These two prizes offer a good balance to the programme as they are technology focussed. They have helped build relationships, share learning and influence others in the innovation prize community. A further prize on solar cooking in India is being explored with Kirk International.
- Support to National Implementing Agents (NIAs): Greater support has been provided to the NIAs managing each prize. Meetings are now bi-weekly for prizes in Kenya and Nepal, and monthly in Ghana. NIAs have reported feeling supported and that they have sufficient levels of follow up.
- Leveraging Inward Finance: The teams have put additional effort into leveraging additional finance, within the allocation of existing resources. This has had some success, notably leveraging finance for a sister prize to the Sanitation Challenge with Gates in Ghana, and attracting interest from the World Bank in further global and national prizes on urban sanitation. Working within existing resources alone however is not achieving the desired outcomes so additional resources specifically to undertaken targeted actions to lever additional finance have been proposed.
- Peer to Peer (P2P) Solar Lending Paper: The paper was agreed with DFID in early 2016, with a grant agreement signed between DFID and E4I signed in August 2016. A procurement exercise was organised and managed by E4I to identify a suitable platform partner. Ethex Lendahand is the appointed platform and a contract was issued in December 2016. The programme will offer crowd sourced loans to solar business and projects in Sub–Saharan Africa with an aim to increase sales of solar home systems from reputable businesses. DFID, in partnership with Virgin Unite, will provide support through funds for initial set up costs and match funding to attract investors.

Recommendations
Prize fund recommendations are as follows:
Reallocation of funds and review of work plans and budgets – based on the MTR findings and on the priorities put forward by the implementation and evaluation teams, programme savings will be reallocated across programme components which are most in-need and offer greatest VfM. A revised budget and work plan will be shared with DFID by end of April 2017.
- Capacity building activities should be increased for both national implementers and prize applicants/winners. The MTR reported that a key challenge across the programme centres on solver capacity gaps, including their capacity to prepare applications, engage potential investors to leverage additional finance, and to network with others to enable collective problem solving.
- Leveraging Inward Finance – Across the prizes the applicants need financing support, both to achieve the prize aims and to maximise impact. The programme will strengthen engagement with potential investors - donors, impact investors, the private sector etc. to draw funds towards the aims of the programme and support applicants. Follow up interest and partnerships with other stakeholders such as World Bank and Rockefeller/Gates on urban sanitation prizes.
- Scope and launch new prize(s) on cold chain and/or solar cooking in partnership with GLEAP, Shell Foundation and Kirk International – to leverage their support and branding for the prizes, as well as their ability to go to market with the technologies, building on the experience of the refrigeration prize.
- Feed in lessons on the field testing, market engagement and use of the prize modality from the prizes (in particular refrigeration) into the new Low Energy Appliances Business Case.

Crowd Power recommendations are:
The clear indication from the crowdfunding sector and the team’s learning so far is that debt funding is lower risk, more transparent and faster growing than the other platforms being researched. Focusing a greater share of the remaining funding on supporting debt platforms would therefore provide best value for money. The team should also research various incentive types to work out how to maximise the leverage effect of the Crowd Power funds.
Match funding for reward and donation platforms in developing countries presents some challenges. This is especially the case where match funds are significantly larger than the typical size of campaign seen on the platform. There is a tendency of organisations to overreach and temptation to game the system. Going forward, reducing the percentage match on donation platforms is proposed so that it is proportionate to the sums typically raised on these platforms.

Output Title	Learning on effective prize design and implementation of innovation prizes aiming to support low income households is made available
Output number per LF		2	Output Score	B
Risk:		Moderate	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicators		Milestones	Progress
2.1	Number of high quality papers published documenting the research into prize design process, for each topic, to coincide with the launch of a prize	Five papers disseminated by 2016/17	On track – 4 papers have been published and disseminated. The final paper, which had been planned / for March 2017, has been pushed back to 2018 to increase its value in terms of content and reporting on lessons learnt. Blogs will be produced to share learning in the meantime.
2.2	Number of key stakeholders accessing the programme learning on effective prize design and implementation of innovation prizes aiming to support low income households outputs and publications”	20,600 key stakeholders engaging with the research publications (via social media, participation at events, etc.) by 2016-17. Through: / I2I website and analytics / Videos, Blogs, Social Media incl. tweets / Events / Media Coverage / Direct Engagement with Donors	Exceeded – 23,220 key stakeholders (such as other donors, funders and implementers) engaging with the research publications (via social media, participation at events, By the end of December 2016, the I2I website and its associated Twitter page (823 followers) had received 20,326 unique page views. / The FTL project uses Medium as a way to share progress, information and projects. The Medium website works slightly differently from other websites, in that articles that have a high ‘read ratio’ are ranked higher and promoted to others. The FTL pages have a higher-than-average read ratio, of about 65%-98% across all articles, whereas the average on Medium is about 30% for shorter posts, up to 60% for posts that take 4 minutes and longer to read.
2.3	Number of high quality papers published documenting the research into campaigns on crowdfunding platforms for development outcomes such as energy access	Research scope and topics to be covered is agreed. 1 research report published by May 2016; 2 (cumulative) published by start of 2017 and 4 by May 2018. / 1,100 downloads and 100 attendees by end 2016; 3,300 downloads by 2017 and 4,400 downloads by 2018.	Slightly off track – The second paper was due for publication in Q3 of 2016 but will now be published in Spring 2017. / Not achieved – As of end of Feb 2017, the Initial report on “Mapping the market” (published May 2016) has been downloaded 100 times from the Energy 4 Impact website and the launch news story received 105 views. / E4I also contributed to a report published in February 2017 by The Cambridge Centre for Alternative Finance, which was downloaded 22 times from the E4I site in the first week, with the accompanying news story being viewed 57 times.

Summary Key Points
During the last year the programme has seen prize design turn into prize delivery, where learning has surfaced and fed-back into programming and prize implementation. The lessons from the prize implementation have started to be collated and communicated with external audiences through Newsletters, blogposts and videos.

A key achievement in sharing learning on prize implementation was the Innovating in Development Learning Event (held February 2017) – a two day workshop which aimed to bring together actors from the innovating in development sector, to share learning (including successes and challenges) of funding, designing, delivering and evaluating innovation programmes. The workshop very successfully shared lessons from the Ideas to Impact programme with others and also started to develop a community of practice on supporting innovation and prizes, which will not only improve the impact of the I2I programme but also facilitate learning with others.

The first of five research papers planned for disseminating Crowd Power learning was published in May 2016. The second was due for publication in Q3 of 2016 but will now be published in Spring 2017, whilst the final three are planned to be published in late 2017/early 2018. The main reasons for delay for the second report have been due to issues with securing data from various companies which ran campaigns, and the team’s workload with a busy period of campaigns.

Some early lessons have already been shared on FTL. For example the I2I team has spoken to USAID about the mechanism, while DFID have spoken to the digital team at the Swedish International Development Agency (SIDA) about FTL, as they are interested in approaches to mainstreaming.

Summary of responses to issues raised in previous annual reviews
Programme-level communications have been progressing, with significant resources supporting individual prizes – particularly Adaptation at Scale and Dreampipe, both of which have launched successfully and had a strong level of interest. Due to the focus on prize level communications less resources have been put into programme-level learning. Despite this, 14 different blogs and video blogs have been published over the year, thereby keeping the programme level audience engaged. The number of unique views of the website continues to increase quarterly. At the beginning of 2016, the programme management and communications role were combined. However, it was found that peak communications times coincided with peak management times – as this was not an effective approach the roles have now been separated again.

Recommendation:
- The key challenge for the prizes team in the last year around Output 2 has been around providing the right level of resourcing to optimise the value of the learning from the programme. In the early stages of the programme the focus was on Prize Design and then on the beginning of implementation – as the prizes have shifted into the implementation and delivery phase, practical action has started to generate valuable learning across the programme. This has led to a recognition and commitment to dedicating more time and resources to the Communication Manager, who will capture, share and make this learning accessible. This will be a priority for the year ahead.
- Similarly, the Crowd Power team should put more resources into ensuring uptake of any research published achieves satisfactory levels.

Output Title	Learning about cross cutting issues on the value and use of different innovation prizes tested by the programme is made available to key stakeholders.
Output number per LF		3	Output Score	A
Risk:		Minor	Impact weighting (%):	10
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator		Milestones	Progress
3.1	Number of high quality papers published on the value and use of prizes for development and environment published open access	Three papers disseminated in 2017/18	On track – The team is currently working on the second of three reports, on ethics and risks of innovation prizes in development.
3.2	Number of high quality evaluative research paper an analysis published following final evaluation of individual prizes- must include details of “failed” projects	One paper disseminated in 2017/18	On track – Planned for Cylinder Prize, will be reported on in next annual report
3.3	Examples of key stakeholders accessing programme learning outputs and publications	3 examples of key stakeholders (such as other donors, funders and implementers) engaging with the research publications (via social media, participation at events, etc.).	On track – There has been no planned action on this to date as evaluation and research outputs will be produced towards the end of the programme. However learnings so far have been published through blogs and video blogs on the I2I website, and an innovation workshop was held in February 2017 to bring together implementers, donors and evaluators to discuss innovation and share experiences

Summary of Key Points
The prizes component is on track to produce at least three peer-reviewed publications by the end of the programme. Additionally, the Evaluation Team has authored three blog posts on learning about practice of evaluating prizes (Learning Stream 3); two are online, and the third is due in 2017. The Evaluation Team Co-ordinator also presented Ideas to Impact’s approach to managing risks and ethical issues of prizes for development at the two day Innovation in Development learning event in February 2017.

The Evaluation Team is on track to deliver five Evaluation Papers, one for each of the five prizes that the team is responsible for evaluating; the first is due end of March 2017. Evaluation Methodology Notes have been submitted for Stage 1 of Climate Information Prize, Dreampipe, Adaptation At Scale and Sanitation Challenge for Ghana (Cylinder Prize Methods Note was submitted in March 2016); these have been peer-reviewed by a DFID Evaluation Advisor.

Workshops were held with Dreampipe and Sanitation Challenge for Ghana prize teams to review early findings from Stage 1 evaluations of these prizes, to feed into design of Dreampipe II and Stage 2 of Sanitation Challenge. Learning from all prizes was also fed into these workshops where relevant. A similar workshop was held in January 2017 for the Climate Information Prize in Kenya.

Summary of responses to issues raised in previous annual reviews
Evaluation and Learning: Strong collaborative relationships between the prize and evaluation teams have been in place throughout the year and have helped improve programme efficiency and effectiveness.

Recommendations
- Resources – It has become clear that the evaluation approach, distribution of resources, deliverables, and balance between academic rigour and being responsive all need to be reviewed and refocused, in light of the way the prizes have changed, the early evaluation findings and the research needs of DFID and other stakeholders. The team will produce an updated Evaluation and Learning Framework in Q2 of 2017 and a revised budget by end of April 2017. The Review Point meeting with DFID and the programme team in January 2017 and the Mid Term Review were two key steps in this process.
- Replication and Scaling Up – The experience of designing and running innovation prizes in a development context is likely to offer economies of scale for replication and scaling up. The programme should actively pursue concrete opportunities for replication and scaling up during the year ahead by identifying the prizes that are best suited for replication and contexts where replication could be successful. Potential partners to support the replication should be identified.
- Data collection challenges – There have been a number of challenges in this area e.g. whether one will be able to rely on applicants to provide usable data about themselves; how many solvers will be available for sampling for interviews; how much larger or smaller the datasets will be than anticipated, etc. Key informant interviews with prize stakeholders have gone well (although some are harder to reach than others), and are proving a rich source of learning about good practice in design of innovation prizes for development as well as themes that could warrant deeper investigation in Stage 2, such as solver incentives and barriers to participation.
- Time frame limitations – There has not always been a large enough gap between prize stages to allow for post-award data to be collected and analysed, before the following stage has been launched. To help compensate for this, the Lead Evaluators and Prize Teams for Sanitation Challenge and Dreampipe held workshops where preliminary findings from evaluation data collected to date, were reviewed in the light of the Prize Team’s proposed approaches to judging, post-award activity, capacity building, etc. These workshops should continue to feed into the development of the new prizes.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
Programme costs are broken down across the prizes programme. The prize purse value has been difficult to set and the programme has proactively engaged across the industry and various stakeholders to set each prize at the right level; as well as collecting data to learn if the values set were appropriate. To-date the prize purse values are typically lower than envisaged in the original business case as higher values have not been considered necessary or appropriate for the type of solvers targeted. The prize purse is 40% of the overall budget with 80% going to the prizes for design, implementation and prize purse.

Of the total cost of implementing the prizes, majority is attributable to human resources, including those of implementing agents, making fees the most important cost driver. The programme has effective mechanisms to continue to bring down this cost through the delegation of activities to national partners and more junior staff members where possible. This is evidenced by the decline in average fee rate over time, and the balance of time between international and national, and senior and junior, staff.

Currently, 75%, of the contract value is attributable to Output 1 and is closely monitored by dedicated prize managers and via financial and technical reporting. 4 shows the cost per prize. There is a high degree of diversity between the prizes: the difference in the cost of each prize reflects the complexity of each prize and its associated operating environment. Note that the table provides figures for the cold chain prize (“reproductive refrigeration”) which is still being designed.

VFM performance for the prize funding is as follows:

Table 4: Cost breakdown by prize

Economy
- Flexibility afforded by the contract allows adjustment of the team make-up to meet the need to deliver best VfM. There was a large decrease in average daily fee rates from the design phase and detailed design phase to the implementation phase. This is largely due to a greater use of junior staff to undertake tasks that do not require as much high level technical input.
- As shown in Table 4 Management and Admin costs account for 7% of the overall programme budget. This includes the costs of the Programme Manager, Financial Manager, all project reporting time and administration time, 15% of the Team Leader’s time and the financing fee applied to the cost of paying the implementing agents and prize purse.
- All fees are benchmarked against industry standards and work previously done by IMC and other consultants.

Efficiency
- Information across prizes is shared efficiently through both formal and informal methods; this is aided by housing the different prize managers within IMC and has enabled the team to learn and adapt as they progress. The programme has subsequently been highly adaptive, which has been an important VfM driver in such an innovative programme.
- There are very strong relationships across the multiple partners and implementing agencies within the programme team. The prize manager set up, which includes monthly reviews of work plans and expenditure, and close hand-holding of national implementing agencies to ensure they have the capacity to undertake the tasks required is seen as highly efficient.
- A new project management structure has set out clear roles and responsibilities across the team, avoiding duplication of effort and ensuring tasks are undertaken at the appropriate level. No further changes to this structure, which is working well, are anticipated.
- The programme operational procedures manual is regularly updated and shared with new team members.
- The DFID quarterly reporting on finances has been tailored to fit with IMC’s internal financial reporting in order to provide readily available information and reduce the admin costs.

Effectiveness
- The programme stage 1 evaluations indicated that the prizes are achieving their intended “effects” and the theory of change assumptions are holding true.
- The MTR completed in March 2017 has provided more detail and recommendations; overall findings were positive both in terms of effectiveness and value for money.

As a research programme the primary value of Ideas to Impact is in the knowledge being generated which will enable DFID to deploy funding in the area in future in a more efficient and effective way. To this end, Crowd Power is generating unique insights and gathering data to support learning that could not have been reached in any other way, such as the identification of the demand and potential for the use of crowdfunding in supporting energy access. Through £263K in DFID funding the programme has supported campaigns in raising over £1.13m, thereby catalysing total funding of over 4X the Crowd Power contribution and benefiting both individual organisations as well as the people they serve. Of the first 19 campaigns supported, 16 exceeded or met their target. Given the small size of the overall market in 2015, the allocation of funding to direct financial support of campaigns (£600,000) has allowed the team to access underlying campaign data and analyse different case studies.

The value for money of Crowd Power can also be assessed by examining DFID spend per beneficiary:
- With Crowd Power support of £17,000 Solar Now raised €150,000 (£128,000) which is able finance 250 solar home systems (benefiting ~1250 people).
- Crowd Power support of £8,500 in vouchers for a Sim Gas campaign (potential investors were issued with vouchers they could invest into the project to encourage them to also invest some of their own money) raised €100,000 (£85,000), which will enable 185 farmers, in Kenya to each own a biogas digester and thereby gain access to clean energy. For both examples, the funding is supporting a market based and sustainable solution, so that once the products are paid for the revenue can be redeployed to finance more systems.

VfM performance compared to the original VfM proposition in the business case
VfM indicators in the original business case have been translated into programme outcomes and are reported on in the Annual Report. The vfm performance is in line with the business case and opportunities for improvements have been made across the areas highlighted above.

Assessment of whether the programme continues to represent value for money
The programme continues to deliver strong value for money for DFID. It is highly adaptive, is sharing valuable learning and delivering results focussed on low income households. Greater value may be derived from further sharing of lessons by both the prize funding and Crowd Power teams, building the capacity of partners, and leveraging of additional finance; these are all priority areas for 2017.

Quality of financial management
This project uses a funding mechanism that is new to the DFID Climate research Team in the form of milestone payments underwritten by actual expenditure and agreed sign-off by DFID for each invoice submitted by IMC. IMC have provided a detailed and comprehensive financial plan which builds on the milestone payments proposal contained in the original contract. IMC have also provided payment forecasts on demand from DFID and have been very accurate, reliable and timely when submitting invoices.

IMC monitors expenditure throughout the programme. Detailed financial information is requested from partners and consultants in order to accurately track how funds are spent against prizes and deliverables. There have been no overruns this year and minor expenses such as flights and accommodation remain within budgets as set out in the Operations Manual and are lower than the DFID Subsistence Rates.

Due diligence is undertaken on all individual consultants and sub-consultants as per IMC best practice. This includes benchmarking of rates and taking up of references.

Date of last narrative financial report	March 2017
Date of last audited annual statement	September 2016

E: RISK (½ page)

Overall risk rating: Major
Under the business case risk framework the I2I risk is considered to be “major” with the following:
Management:	Moderate: given IMC is a new partner to the Climate team, and the consortium is a large mix of diverse organisations and implementing agents. IMC engagement and contracting documentation and processes clearly set out compliance requirements for our downstream partners, and our expectations. IMC also carry out various due diligence (DD) checks and research at the beginning of their relationships with these partners, and repeat these checks throughout the contractual relationship as part of their routine DD process. At any points of concern, or major change, IMC repeat their DD procedure. The assessment of risk (and adequacy of our standard procedures) is an ongoing activity for IMC Project Managers supported by the Business Improvement Leader.

Technical/intellectual:	Major: since innovation is inherently risky – as the programme is attempting to incentivise innovation, there is no guarantee that the prizes will result in high-impact solutions.
Output:	Major: as a new programme for DFID, there is no best practice that exists across the organisation (and very little outside DFID) on whether the programme might reach its intended outputs. If one prize does not work, it risks the programme as a whole not achieving its outputs.
Context:	Moderate: while the programme does not intend to operate in highly challenging contexts (e.g. fragile states), it is focusing on complex problems in DFID priority countries – problems that to this day remain unaddressed.

Overview of programme risk
The programme risk is major, in that it is trialling innovation prizes in new ways and new contexts. The programme takes a proactive and rigorous approach to risk management. Detailed risk assessments for each prize were included in the last Annual Report submitted to DFID, and are updated as the prizes evolved. Please see the 2017 I2I annual report for updated programme and prize level risks matrices.

Each prize has its own risk register managed by the prize manager, as well as the Programme Manager holding a programme-wide risks table. Each risk matrix is revisited at key points and any issues arising from these risks are logged and discussed at management meetings as required. Going forward, these risk matrices will be updated quarterly, in line with the findings from the Mid-Term Review.

The overall risk environment has not substantially changed since the last Annual Report. The current key risks for the prize funding component are:
- Scrutiny on DFID spending: the consortium is ensuring that it is very clear where programme funds are spent. Actual spend is submitted to DFID quarterly, and the consortium is able to provide any details of spend as required.
- Length of final stages for all prizes: the consortium is looking at the possibility of extending the prizes programme by 12 months to allow specific prizes to increase the length of Stage 2, and to allow time for the evaluation team to complete their learning research reports.

Key risks for Crowd Power include:
- Poor research uptake: the team is looking for additional opportunities to disseminate learning through a new connection at The Cambridge Centre for Alternative Finance, and is also seeking further collaborations with energy access and crowdfunding actors
- There is potential for manipulation of campaign totals in order to achieve high values of match funding. The team has now consequently changed their operating procedures. For example, they are now requesting bank statements and invoices to evidence spending stipulated in suspect campaigns, and have discontinued a partnership with one platform after they demonstrated poor controls after a campaign-maker went into liquidation. Another platform has been identified as being the most vulnerable site used, but it is also the only African-based site and the platform has thus far been extremely cooperative and have proactively addressed the problems. Crowd Power should continue to support them in their efforts to make the platform work whilst at the same time managing the risks appropriately.

The Frontier Tech Livestreaming risk matrix was developed in line with the format used for the other I2I components and was provided as an annex to the 2017 Annual Report. The main risk relates to the scope of projects selected – as these can be sensitive in nature, and will need to be carefully considered and mitigated by the team. This risk has occurred, and been successfully mitigated by the team.

In summary, all risks continue to be monitored, and many are mitigated for (where these are within the control of the Ideas to Impact team). All variations (from Design Report to Annual Report) relate to reduction in risk scores as a result of mitigation actions. IMC have also undertaken a mapping and due diligence of downstream partners – see Annex 3.

Outstanding actions from risk assessment
None.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Due to the innovative and adaptive nature of the programme, there have been some delays. Some of these have been entirely outside the control of the team and could not be anticipated, such as the earthquake in Nepal in April 2015. As prizes get delayed and run closer to the end of the overall programme, it will become a challenge to complete both the prizes and the evaluations by the end of March 2019. With the inclusion of the FTL component, and to ensure adequate evaluation work can be carried out (see Section H below). The independent Mid Term Review recommended the programme is extended to end March 2020, with the prizes closing in October 2019.

Performance of partnership(s)
The programme team has good relationships with all partners (both sub-consultant companies and individuals). The programme has an effective, open and collaborative nature, both with the PMU within IMC and with others involved. Implementing agents have reported feeling supported and provided with sufficient oversight; the independent Mid Term Review (MTR) described the leadership and management of the programme as being “very strong”. Please see the I2I 2017 Annual Report Annex 5 for the mapping of downstream partners.

Asset monitoring and control
The Asset Register has been updated and is included in the I2I 2017 Annual Report Annex 4.

G: CONDITIONALITY
Partnership Principles do not apply.

H: MONITORING & EVALUATION

Compliance with Gender Equality Act
The Ideas to Impact programme continues to strive to be compliant with the 2013 Gender Equality Act.  IMC are integrating gender analysis into the design of the prizes and proactively looking at opportunities to increase women applicants. For example, under Adaptation at Scale in Nepal women-only workshops were run during Stage 1 and the applications for Stage 2 were assessed in order to verify the number of women-led organisations that applied. As a result of this assessment, the prize team is currently specifically targeting women-led groups in Nepal. In addition, specific criteria on how solvers target women and youth are included in the judging criteria for most prizes and this is also a clear focus for the evaluation of the prizes. It can also be underlined that two out of three local implementing agents (in Kenya and Ghana) are women-led and that the entire programme management unit is made up of women.  The overall aim of the programme is to improve water, sanitation, climate information and energy services for poor households, and the integration of gender analysis into the programme will ensure that men and women benefit equally.

Evidence and evaluation
Good progress has been made by the evaluation team, and work on Monitoring, Evaluation and Verification is on track. The team’s focus in the first half of the year was on building strong foundations for the final evaluative research and learning publications, by developing detailed plans for evaluations (evaluation methodology notes) which are consistent with each other whilst also being tailored to the prizes. The notes have been peer-reviewed by a DFID Evaluation Advisor and are being used to develop a common approach to coding and analysing the data generated across the prizes. The process of agreeing and testing the team’s common approach to coding required a small sample of qualitative data from each of the first rounds of the Dreampipe, Cylinder, Urban Sanitation and Climate Information prizes. As these prizes awarded applications at different times, analysis of some prizes (e.g. Cylinder Prize) was paused until other prize timelines had reached the same stage.

In recent months, the team’s focus has shifted to data collection, analysis and reporting for the various prizes which have made awards so far. This has largely been targeted at prize processes because of the nature of the Stage 1 prizes (business cases, sanitation plans, etc.). However, interviews carried out with judges and participants included questions that will provide some insights into the value that prizes offer over other funding modalities, in their experience. These early findings were reported in the January 2017 Review Point meeting, at which a DFID Evaluation Advisor and programme management team provided feedback on the proposed evaluation methodologies.

As with other work carried out within the programme, it is necessary to increase engagement with I2I’s target audience and promotion of the learning agenda, including strengthened communication of insights produced by the evaluation team. In order to aid this, and to enable the sharing of learnings sooner, it is recommended that the outputs are labelled as ‘working papers’ or ‘learning notes’ i.e. the team would be sharing a “conversation”, not a peer-reviewed learning piece.

Other work carried out in the review period has included field visits, reviews and external engagements. A Monitoring Framework is in development by the programme (supported by ITAD), which will further assist the prize teams with monitoring and ensure data is collected in a systematic and consistent manner across the programme.

An independent Mid-Term Review (MTR) of the prizes component was completed in March 2017. The review was intended to guide the programme’s future strategic direction and resource allocation, as well as improve VfM where possible, it addressed six main questions which included investment in evaluation of the projects. The team has now started to consider how to incorporate recommendations, and other feedback from stakeholders, provided in the MTR into the programme. Key findings from the MTR were:

- I2I is effectively testing its core hypothesis that prizes can be used as a catalyst for innovation and problem solving;
- I2I is drawing in a range of solvers beyond the usual suspects but should continue to mitigate solver risk;
- I2I demonstrates that prizes can incentivise coalition building around “thorny” development problems, which is critical for sustainability of solutions;
- There needs to be a balance between research and application, clarity on the relationships between prize design/implementation, evaluation and wider knowledge sharing – there has perhaps been too much focus on beneficiary numbers at the expense of innovative solutions;
- Management and VfM: Leadership and management of the programme are very strong. The programme could do more to capture the lessons in working in an adaptive and agile way, which is critical for this sector. It would also be good to measure VfM of innovation prizes against other funding modalities;
- Risk Management: The programme team has a sound awareness of delivery risks and I2I is managed effectively at the prize level. It would be good to have a portfolio view of risk across the prizes.

Key strategic recommendations made by the MTR include:
- The overall programme duration should be extended by 12 months, to enable sufficient time for the development and deployment of solutions as well as the completion of evaluation outputs.
- Investment should be prioritised in two areas: i) research uptake - knowledge sharing and influencing and ii) scale up and replication of specific prizes with urban sanitation being the strongest contender, with interest from Gates, World Bank, the High Panel of Water and Oxfam. Considerable investment and learning has been made in the development of the prizes, which offer valuable lessons which need to be capitalised on for scale up and replication.
- A modest increase in evaluation budget would allow for a more flexible and responsive approach that could feed into stage 2 of prizes such as Dreampipe and Global LEAP; funding should also be provided to measure the effectiveness of capacity building measures.
- Building partnerships to leverage resources and networks, following the Innovation workshop held in Feb 2017, should be a focus for the programme.

The evaluation process, in addition to some of the prizes would benefit from a longer implementation period. It is therefore recommended that the project is extended to March 2020. The proposed evaluation timeline is presented below in Table 6.

Table 5: Proposed extended evaluation timeline
Period in Programme	Activity	Notes
June 2019	Prizes make final awards
August 2019	Field data collection e.g. interviews with winners	Data collection and analysis will be done beforehand as and when available.
September 2019	Evaluators draft final evaluation reports	ITAD will have access to early drafts
October 2019	Internal & external peer review of evaluation reports	Internal Quality Assurance, review by Prize Team and management, DFID and external peer review
Oct / Nov 2019	Evaluators carry out post-award follow-up (as updates for evaluation reports).	If this is a small number of interviews, possible in time-frame but otherwise (especially if extended to non-winners) will take longer and require more resources.
Nov – Jan 2019	Value & Use Paper drafted	Synthesises evaluation findings with reference to prize literature
Feb 2020	Internal & external peer review of Value & Use paper	Could be peer review through submission to journal (if there is time for this before end of programme)
March 2020	All final publications published online and disseminated.	Can do pre-publication activities e.g. roundtables.

For the monitoring and evaluation of Crowd Power, platforms conduct monitoring and evaluation (M&E) in a variety of ways, and the team has allowed their partners who already have M&E processes in place to continue their usual practices. For example, one platform conducts interviews and surveys the partners that received funding through the Crowd Power initiative to understand the number of beneficiaries reached by these organisations and the expenditure of funds. The team has found considerable variation in the number of beneficiaries reached proportionate to the funds raised; they believe this is caused by inefficiencies in this model (vs for-profit enterprises).

A second platform requires campaign-makers to fill a pre-campaign survey showing their funding history, revenues and sales, employees etc. Progress will be checked one year after each campaign so a progress update cannot be provided at this point other than anecdotally; it is recommended this data is made available for next year’s Annual Review. Many campaigns have been used by early-stage companies to refine their product and get to market, and the team has received reports from various entrepreneurs that their products are in production and will be launched in 2017.

Overall, the main metrics being collected from supported organisations for the prizes are 1) number of jobs created, 2) revenue/unit sales, 3) product updates/launch/development, and 4) beneficiaries reached. In addition data is being gathered on the campaigns including “crowd” demographics and trends in contributions. It is recommended that the team try to collect data disaggregated by gender as far as possible through the various platforms. Collected data in addition to broader research is being analysed to inform the 5 learning reports.

The M&E approach for FTL is under active development. Before Frontier Technology Livestreaming there was no comparable facility within DFID providing the funds, technical resources and agile management support to enable the piloting of frontier technologies within or alongside DFID mainstream programming.  Success over the course of the 3 year pilot will be measured in terms of the successful delivery of 15 country-based pilot projects and the quality of the live stream of insights, learning and evidence they produce.  The longer term impacts of the programme however will be more closely linked to the adoption of frontier technologies and practices into mainstream development practice both within DFID and other donor partners, as well as the potential use of Frontier Technology Livestreaming itself as a model for promoting organisational innovation and building capacity on new approaches.

Monitoring progress throughout the review period
DFID hold regular one day review meetings with the IMC project team (quarterly). The last meeting focused on evaluation and was an opportunity for the RED senior evaluation adviser to provide inputs. The frequency of communications and exchanges has intensified over the last six months due to the establishment of the Frontier Technology Livestreaming.. In addition, given our open relationship with the prize teams and grantees, we receive regular updates directly from them on their achievements (via meetings, email and telephone).

As part of this annual review process, IMC and Energy 4 Impact produced an annual report reviewing the progress of the Ideas to Impact and FTL over the last year against logframe outputs, targets and risks. A meeting with IMC and consortium partners was held to review each prize area. An independent Mid Term Review was undertaken by LDP consultants of the programme and this fed into the annual review process and this involved country visits (Nepal, Kenya and Ghana) and feedback from beneficiaries in each country. DFID staff (Infrastructure Adviser DESA, RED Evaluation Adviser and Senior Innovation Adviser) met with the consortium and MTR review team to better understand the status of activities and verify the findings in the annual report and MTR. Additional phone calls and emails have been exchanged with IMC and partners to obtain further details where necessary.

Annexes:
Annex 1: Revised Logical Framework
Annex 2: I2I Annual Report incl. asset register, mapping of downstream partners and updated risk matrix.
Annex 3: Mid Term Review report for the Ideas to Impact prizes programme