Poverty and Growth

## Business Case June 2013

Abbreviations and Acronyms

DFID:	Department for International Development
DFID-P:	Department for International Development, Pakistan
EGG:	Economic Growth Group
FTE:	Full Time Equivalent
GDP:	Gross Domestic Product
IFUSE:	Investment Facility for Utilising UK Specialist Expertise
IGC:	International Growth Centre
IMF:	International Monetary Fund
MSG:	Macroeconomic Stability and Growth
OJEU:	Official journal of the European Union
PIDE:	Pakistan Institute of Development Economics
PPP:	Purchasing Power Parity
PKR:	Pakistani rupees
PSLM:	Pakistan Social and Living Measurements
UK:	United Kingdom

Design team

Lead adviser/lead author:	Madiha Ahmed
Programme Manager:	Annette Babita
Private sector advisor:	Waqas-ul-Hassan

Quality assurance for final submission

MSG team leader:	Alan Whitworth
Programme Manager:	Sohail Wajid

Quality assurance for Programme Board version

EGG Group Head:	Alexis Ferrand
Results:	Muhammad Raza Khan

Additional inputs on current version:

Social Development:	Fatime Naqvi
Political Economy:	Shumaila Rifaqat
Programme design:	Nyda Mukhtar
Regional economy:	Ilyas Malek
Sub-national Governance:	Gareth Rannamets
Communications:	Ryan Gawn
Proof reading and editing:	Rachel Clayton

Key inputs to earlier draft:

Education:	Atif Rafique

Poverty and Growth - Business Case and Intervention Summary

Intervention Summary

What support will the UK provide?

The UK will provide £4.5 million over 8 years to communicate evidence on poverty and growth in simple language. This will enable decision makers and citizens of Pakistan to better understand how to promote economic growth and make it inclusive. This will seek to improve the prospects for economic reform, while protecting the interests of the poor.

What issue will this address?

With a tax to GDP ratio in single figures, a persistent federal fiscal deficit of 6-7% of GDP, huge subsidies and dwindling foreign exchange reserves, Pakistan is on the brink of a fiscal and balance of payments crisis. With investment of just 13% of GDP (compared to a regional average of 32%) and a major energy crisis, at 3% real economic growth barely exceeds population growth - and poverty appears to be increasing. Little progress on poverty is likely without fundamental structural reform.

Yet Pakistan is well endowed with (public and private) research institutes which produce international quality economic research and analysis. As a result, for some time there has been a good understanding among researchers, technocrats, and donors of the nature of Pakistan’s problems and the kind of reforms that are needed to accelerate growth and poverty reduction as was reflected in the economic manifestos presented by different political parties in the run up to the elections. With sensible policies Pakistan should be able to achieve the much higher growth rates seen elsewhere in the region, despite the security challenges facing the country.

Despite the availability of sound analysis, there has been little progress towards reform. This reflects a combination of poor public awareness and understanding of the issues, conflicts of interest / political economy and concern that reform will hurt the poor (for example higher prices). Policy research findings have not been effectively communicated to the public. As a result, politicians’ incentives have favoured the status quo.

This project seeks to take advantage of Pakistan’s research capability to change politicians’ incentives and improve the climate for reform by: (i) translating academic analysis into simple language and messages that make the case for reform in ways the public can understand; and (ii) designing reforms so as to minimise their impact on the poor.

Regional economic cooperation has been identified by DFID as a priority area. DFID-P will be a partner in the design and implementation of an advisory forum. Its purpose is to ensure that existing research on regional trade is understood by policy makers and to identify future policy direction.

Why is UK support required?
DFID’s primary interest in Pakistan is to reduce the incidence and severity of poverty. The DFID Pakistan (DFID-P) Operational Plan[1] recognises that this requires accelerated economic growth, while ensuring that the returns reach the poorest and most marginalised. Our ambition is to use policy and practice to achieve transformative change. DFID can change the way citizens and governments interact by promoting public debate on economic reform and strengthening the research on poverty.
[1] DFID Pakistan Operational Plan 2011-2015. http://www.dfid.gov.uk/Documents/publications1/op/pakistan-2011.pdf

With its focus on results and programmes such as the Transforming Education Programme, DFID has a strong reputation as an objective supporter of evidence based decision making. In the run up to the elections, DFID and other donors actively engaged with all major political parties to discuss the parameters for economic reform in their manifestos and are now well placed to take policy dialogue forward with the new government. With the macroeconomic challenges facing the country, which may require support from the IMF, the dialogue on reform must take into account how the poor will be affected during economic adjustment. Economic reform, with or without IMF support, needs to share the economic gains and incentives across the population, particularly the poorest and most vulnerable.

Who will be implementing this support we provide?
The knowledge development and economic advocacy components of the programme will be implemented by a management agent. For the knowledge development component, the management agent will sub-contract a range of local researchers that will use information and data to build constituencies for change.

For the economic advocacy component, the management agent will facilitate dialogue between private sector, academia and civil society with the appropriate federal and provincial authorities. Key messages, distilling complex analysis on reform into simple language will be communicated to the media and the public to build demand for and overcome resistance to economic reform.

Where possible the agenda will be driven by Pakistani stakeholders. The management agent will facilitate the development of a steering committee that will identify priority topics for the programme. The initial core themes for policy support will be energy, tax and regional trade. The steering committee will validate the core policy themes every two years to ensure the programme continues to be directly relevant to the needs of the Pakistan economy.

The World Bank is currently coordinating donor support to the Pakistan federal government and the private sector on policy engagement on regional economic cooperation. DFID Pakistan will contribute to support the establishment of an economic advisory group, with equal partnership from government, private sector and researchers. The focus will be on developing a regulatory and policy framework to govern Pakistan’s interaction with the regional energy market.

The monitoring and evaluation component will be implemented by an independent party.

What are the expected results?
The expected outputs will be
  1. Increased public and political support for economic reform as a result of better communicated evidence to target audiences on the constraints to growth.
  2. Economic reforms which are explicitly designed to minimise the impact on the poor.
  3. A regulatory and policy framework for Pakistan’s engagement in the regional energy market.

Over the long term, this will lead to better understanding across a diverse set of constituencies of key economic issues relating to poverty and growth. The obstacles to policy change will also be identified, increasing the prospects for reform and responsible inward investment. Better informed decision making should contribute to better poverty and growth outcomes and reduced need for aid inflows in subsequent years.

By the end of the programme (2021) the programme will have contributed to the improvement of income and deprivation measures of the bottom two quintiles of the population.

Business Case

Strategic Case

A. Context and need for a DFID intervention

What is the nature of the problem?
Since 2007 growth in Pakistan has averaged 3 to 3.5 percent of GDP, around 1 percent in GDP per capita[2]. To improve its performance, Pakistan needs to undertake politically difficult reforms. For instance, improving the reliability of power supply requires increasing electricity tariffs to at least cover generation, transmission and distribution costs. Another challenge is that, by any standard, the rate of tax collection is extremely low (less than 10% of GDP). A government which has to deliver services to over 180 million people but where only 1 million people pay direct taxes needs to overhaul its tax collection.
[2] Government of Pakistan. 2012. Economic Survey of Pakistan 2011-12. Ministry of Finance. Islamabad.

The absence of serious reform over recent years could be because of a combination of:
Insufficient understanding of the technical issues.
The public is unaware of how current policies are constraining growth, despite the availability of good analysis, and so does not push for reform. This may be because the analysis is poorly disseminated or is in a language (English instead of Urdu) or a format (dense jargon instead of plain language) that makes it difficult to absorb.

No agreement on the specifics of the reforms required.
Even where there is consensus on what needs to be done in broad terms, there may not be agreement on the specifics. For instance, while everyone agrees on the need for better management of public owned enterprises such as Pakistan International Airlines, proposed solutions range from bringing in managers from the private sector to privatisation.

The ‘New Framework for Economic Growth’[3] , approved by Cabinet in 2011, makes a strong case for reform. However, it is weak on implementation and engagement with provincial governments and other stakeholders on poverty and competitiveness. This business case supports the delivery of the New Framework by addressing the obstacles to policy consensus.
[3] Government of Pakistan. 2011. New Framework for Economic Growth. Planning Commission. Islamabad.

Impact on the Poor
A number of priority reforms (for example increasing electricity tariffs, removing subsidies) are likely to have a direct negative impact on the poor. The public may resist reform unless it is designed to minimise this impact.

Conflict of interest.
If those who are expected to design and implement reforms are benefiting in some way from the current arrangements, there will be no incentive for change.

Political economy of change.
Those constituencies who would lose income or patronage will block reform. Pakistan’s turbulent political history has encouraged the short-term economics of survival. The demand is weak for evidence based policy making[4] and poor economic governance has been identified as a binding constraint on growth[5].
[4] Akhtar S. 2012. Review of Technical Support for Pakistan Growth Policy Programme.
[5] Qayyum, A. et al. 2008. Growth Diagnostics in Pakistan. European Journal of Scientific Research. Vol 24. No.3. pp.433-450.

How is the problem going to be addressed?
The proposed development investment aims to increase the probability of policy reform being adopted by the Government of Pakistan by strengthening public understanding of the need for reform. The sectors we will work in will be determined by a steering committee comprising government, private sector and civil society. The initial core policy themes for the programme will be energy, tax and regional trade, which have been identified as the highest priority. The steering committee will review the core policy areas as appropriate every two years to ensure the focus of this work remains directly relevant to the needs of the Pakistan economy. The following interventions are proposed:

Assessing the impact of reform on the poor. Research will be conducted into the likely impact of various reforms on the poor, particularly in the short term. This analysis will be used to try and mitigate the impact in the design of the reforms, thereby reducing the risk of public opposition. A key focus will be increasing opportunities for women and girls to fully participate in the policy development process.

Measurement of the headcount ratio can be controversial and an assessment of how the incidence of poverty has changed over time is tricky in Pakistan. The first challenge is agreeing on how to define poverty and whom to categorise as poor. The second sensitivity is around the distribution of poverty, which is as much ethnic / linguistic as geographic[6]. There is strong evidence that addressing income inequality, not just the absolute level of poverty, is important for poverty reduction[7]. However, with a strong Islamabad centric bias of research capacity, there is little practical experience on how to grapple with the specific deprivations that different social groups have to face. Finally, a large proportion of the population is clustered around the poverty line where, vulnerable to shock, any small change in circumstances can pull them out of or into poverty[8]. This is why a better understanding of the dimensions and dynamics of poverty is needed to assess the likely impact of reforms on the poor, particularly women and girls.
[6] Naveed, A. and Ali, N. 2012. Clustered Deprivation: District Profile of Poverty in Pakistan. SDPI. Islamabad.
[7] Kalwij, A. and Verschoor, A. (2007) “Not by Growth Alone: The Distribution of Income in Regional Diversity in Poverty Reduction.” European Economic Review 51(4), 805–829; Ravallion, M. (2001). "Growth, Inequality and Poverty: Looking Beyond Averages," World Development, 29(11), 1803-1815.
[8] PIDE. 2012. Rural Poverty Dynamics in Pakistan. Islamabad.

Understanding why there is policy inertia. It is necessary to understand which constituencies benefit or lose from proposed changes. The analysis can also assess which particular options are more likely to succeed politically. As part of this, we will continue to engage with the IMF on the design on any potential new programme and work across other donor organisations so that we present a joint position.

Communicating policy analysis and evidence in format most appropriate to the target audience. The layman is unlikely to understand economic analysis and why reform is needed. The objective is to convey the case for reform in a simple way so as to change attitudes and behaviour. For instance, showing how higher electricity tariffs encourage investment in new generation, which then leads to less load shedding.

The objective is to have better informed decision making. The public should be better able to understand how federal and provincial policies impact on their lives, thereby improving their capacity to influence policy. We also want to improve quantity and quality of growth and poverty related coverage in the Urdu media so citizens as well as policy makers have better information to make choices.

Strengthening partnerships among champions for reform. To improve policy, consensus on necessary reforms must be built across the political spectrum. The programme will work to find common purpose amongst agents for change and transform the way citizens and governments interact.

DFID’s comparative advantage
DFID’s experience in implementing the innovative Transforming Education Programme[9] will inform how to reach non-traditional audiences. The Subnational Governance Programme focuses on improving transparency by strengthening information available at the local level. For instance budget information in the public domain is of value only if there is a network of different types of users (media, political agents) who can interpret it and then push this into the public consciousness. The Awaaz programme supports women’s rights through strengthening their political participation and improving indicators that track violence against women and their exclusion from the political process. The proposed programme can build on these outreach mechanisms to strengthen communication of poverty and economic policy evidence to the public.
[9] The programme uses different means of influencing political commitment to education and learning, by focusing on agents of change, from politicians to community leaders.

DFID has also experience with a research and advocacy fund for maternal and child health. The lessons and challenges in using research and evidence to influence policy change will be used to inform this programme’s operations.

Through our political economy initiatives over the past year, DFID has been testing how to engage with political parties on their economic manifesto in the year before elections. With a new government in place there is no better opportunity to push for ambitious reform. This programme will provide political economy perspectives on issues of fiscal and economic reform to the IMF for consideration in the design of the next IMF programme.

Linkages to DFID global strategy
DFID globally is funding programmes such as the ESRC-DFID Joint Fund for Poverty Alleviation Research,[10] the International Growth Centre (IGC)[11], and the Investment Facility for Utilising UK Specialist Expertise (IFUSE). The first two programmes provide high quality research that studies issues highly relevant to Pakistan such as growth, poverty and urbanisation. IFUSE provides access to UK expertise at short notice. The programme will draw heavily on these resources as it builds momentum and ownership for reform on specific issues such as energy and tax.
[10] http://www.esrc.ac.uk/funding-and-guidance/funding-opportunities/26497/esrc-dfid-poverty-alleviation-research-2013.aspx
[11] http://www.theigc.org/countries/pakistan

DFID’s Asia Regional team is investing in opening up trade and economic cooperation across Central and South Asia. This programme will complement the regional agenda by strengthening Pakistan’s policy engagement on trade and specifically the regional energy market.

B. Impact and Outcome that we expect to achieve
The expected outputs will be
1. Increased public and political support for economic reform on key policy themes as a result of better communicated evidence to target audiences on the constraints to growth.
2. Economic reforms which are explicitly designed to minimise the impact on the poor and increase opportunities for women to fully participate in the economy.
3. A regulatory and policy framework for Pakistan’s engagement in the regional energy market.

Over the long term, this will lead to better understanding across a diverse set of constituencies of key economic issues relating to poverty and growth, such as energy, tax and regional trade. The obstacles to policy change will also be identified. As a result, the prospects for key economic reforms will be improved – leading to the outcome ‘key economic reforms implemented and sustained’. Better economic policies should contribute to better poverty and growth outcomes.

By the end of the programme (2021) the expected impact is the improvement of income and welfare levels of the poor.

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case?

Theory of change

There has been paralysis regarding economic reform. Major barriers to growth, such as energy or tax, have not been addressed despite considerable public debate and research demonstrating the need for reform. On issues such as tax, the challenge is not just making changes on paper but changing the tax culture. The latter requires more than reform by the stroke of a pen, it needs to be supported by national movement so that reform is sustainable and citizens can hold politicians to account.

There is no formula that ensures good research leads to sound policy. Successful advocacy is characterised by the ability to adapt quickly, knowing what are the barriers to change, and being able to recognise entry points in a constantly shifting political environment[12].
[12] Teles, S. and Schmitt, M. 2011. The Elusive Craft of Evaluating Advocacy. The William and Flora Hewlett Foundation.

The debate on how to deliver economic reforms is a conversation amongst Pakistani stakeholders. However, DFID Pakistan can play an important policy brokerage role by improving awareness of research. By helping improve the use of research in public debate and decision making, DFID can improve the prospects of key reforms which are critical for faster growth and poverty reduction being adopted.

Summary of options

The objective of this programme is to improve the prospects for economic reform. The programme will translate the evidence (both pre-existing and newly generated) into an absorbable format, disseminate it effectively and track the policy uptake.

Option 1: Direct support to research and communication of policy analysis:	Cost £4.5 million

This option has four components:
1. Economic advocacy: translating policy analysis into simple language and disseminating it to target audiences (£2.2 million).
2. Knowledge development: Analysing the impact of proposed policy reforms on the poor and addressing gaps in evidence on poverty (£1 million)
3. Monitoring and evaluation (£0.3 million)
4. Co-financing World Bank coordinated support to Pakistan’s position on regional economic cooperation, specifically policy framework on regional energy markets (£1 million)

The total programme commitment over 8 years is £4.5 million. Where possible the research and discussion agenda will be driven by Pakistani stakeholders. The management agent will facilitate the establishment of a steering committee within the first year that will identify priorities for the programme. Until the steering committee is functional, DFID will identify the priority issues. In the first year, these will be energy, tax and regional trade.

Economic advocacy. How well research is used depends on its policy relevance, its quality and how well it is communicated. The management agent will subcontract a firm or individuals to communicate complex information simply to target audiences. For instance by converting existing research into simple diagrams, Urdu leaflets, media packages. Key messages developed by distilling complex analysis on reform into simple language will be communicated to the media and the public to try and build demand for economic reform. This could include mass media (radio, TV, newspapers, billboards), and networking events (conferences, community mobilisation). The management agent will facilitate dialogue between private sector, academia and civil society with the appropriate federal, provincial and local government authorities.

Knowledge Development. The management agent will sub-contract a range of local researchers to develop a broad network on research for the selected priority topics. To strengthen the supply of information, a web based portal will be set up where existing and new research will be provided. A non-web based mechanism for those target groups who do not have easy access to the internet will be tested and developed. Citizens can use information to make their choices and make it easier for decision makers to communicate the impetus for reform. For instance, a key step to transforming the tax culture in Pakistan is shifting to a principle that every sector (manufacturing as well as agriculture and services), and group (Punjab and Sindh, politicians and citizens) is contributing to tax revenue. Putting in place tools that allow citizens and decision makers to track how much each cross section is contributing to the tax net would reduce the ability for people to demand special concessions.

Any research commissioned will assess the likely impact of individual reforms on the poor so that policy design can be modified to mitigate the impact of (and reduce opposition to) proposed reforms, in particular on women and girls. The programme will also assess the political economy of reforms – to identify losers and opponents of reform (and inform strategies to neutralise opposition).

Monitoring and Evaluation. Monitoring and evaluation of the work undertaken by the management agent will be conducted by an independent party. This will ensure that baselines and follow up evaluations are implemented on time and that reporting is robust. Further detail is in the management case.

Regional Forum. The World Bank is currently coordinating donor support to the Pakistan federal government and the private sector on policy engagement on regional economic cooperation. DFID Pakistan has been supporting research on cross border engagement since 2011. The World Bank is helping establish an economic advisory forum on regional integration, with equal partnership from government and the private sector. This forum will use existing research and communicate it in plain language to stakeholders across government and the private sector. The forum will then recommend policy actions to maximise the gains for Pakistan from regional economic cooperation.

The objective of the World Bank programme is essentially the same as for components 1 and 2 above, though limited to a specific topic, regional economic cooperation, particularly on energy. It is proposed that DFID co-finances the World Bank initiative, which is ready for implementation, contributing £1 million.

Option 2: Finance a multilateral institution for policy support to pro poor growth: Cost £4.5 million

Globally there are instances where a multilateral institution undertakes research on a country or a topic and uses its convening power to disseminate the findings to the government and private sector. An example is the World Bank’s Operationalising Pro-Poor Growth[13] programme, partly funded by DFID, which produced a series of literature reviews and studies using cross country econometrics.
[13] http://web.worldbank.org/WBSITE/EXTERNAL/TOPICS/EXTPOVERTY/EXTPGI/0,,contentMDK:20264272~menuPK:524081~pagePK:148956~piPK:216618~theSitePK:342771~isCURL:Y,00.html

DFID has the option of funding such a research operation in Pakistan. The funding would either top up an existing global programme with a Pakistan specific focus, or directly fund a programme managed by the multilateral’s country office. The selected institution would then be responsible for contracting the appropriate research products as needed and developing a dissemination mechanism.

Option 3: Capacity building of government at federal and provincial level to implement pro-poor growth policy: Cost £2.9 million

One of the most critical audiences for policy research is the government. To improve the prospects for reform, one option is to try to transform the behaviour of government departments by increasing the discussion and usage of research evidence. This is necessary for the government departments to both develop credible policy options and defend their advice to decision makers.

Under this option technical assistance would be provided to key government departments, such as the Planning Commission or the Ministry of Finance at the federal level, or the Planning and Development Departments at the provincial level. The technical assistance would support targeted research and resources to assist officials to interpret and communicate information to decision makers.

Option 0: “Do nothing” counterfactual

DFID will continue to support the IMF’s policy engagement with Pakistan with in-house resources (for instance staff time).

B. Assessing the strength of the evidence base for each feasible option

In the table below the quality of evidence for each option is rated as Strong, Medium or Limited

Option	Evidence rating
1	Medium. We are building on the promising initial results from the Transforming Education Programme. Similar policy advocacy models have performed well in some countries such as Tanzania and Rwanda. We have good expectations given the complementarity and learning from other DFID programmes working with non-traditional partners.
2	Medium. In some countries there have been good results, such as the International Policy Centre for Inclusive Growth in Brazil[14]. However, performance is conditional on capacity in country
3	Weak. See Review of Growth Policy Programme (2012)[15]
[14] http://www.ipc-undp.org/About.do
[15] Akhtar S. 2012. Review of Technical Support for Pakistan Growth Policy Programme.

What is the likely impact (positive and negative) on climate change and environment for each feasible option?

The climate and environmental risks and opportunities of increasing the quantity, quality and dissemination of policy-related economic research are considered to be low. However, the project must take into consideration the effects that climate change may have on poverty and growth dynamics. There is growing evidence available to demonstrate the risk that poverty reduction and economic growth processes are destabilised by climate change is increasing.

The overall categorisation of the proposed support is category C.

It is also important to ensure that any policy prescriptions developed under the programme do not lead to inadvertent negative climate and environmental impacts and mal- adaptation. The programme will therefore be closely coordinated with the DFID humanitarian and resilience delivery teams. Researchers should be strongly encouraged to minimise the environmental and carbon footprint of their work.

C. What are the costs and benefits of each feasible option?

Costs Option 1
The cost of an independently managed research programme is estimated at £3,102,117 in present value terms (see Annex 1). This includes £1 million co-financing of the World Bank’s support for regional integration policy coordination.

Benefits option 1
Economic research can generate a wide array of benefits, including information, technological change (for instance web tools that improve transparency), and improved policy[16]. A small number of projects may account for most of the effects of a research programme. However, it will be virtually impossible to quantify the impact of this programme on the Pakistan economy. Not only are the benefits of policy reform difficult to measure, but so is attributing reform to research. The economic case for the programme is essentially that – while there are no guarantees - it is reasonable to expect that the programme will increase the probability of certain key reforms being adopted. The judgement is that the increased probability of reform multiplied by the considerable returns expected from reforms will comfortably exceed programme costs.
[16] Zilberman, D. and Heiman, A. 1999. The Value of Economic Research. Impact Discussion Paper No. 7. International Food Policy Research Institute. Washington D.C.

For illustrative purposes let us look at the energy sector. The federal government has provided over PKR 1.0 trillion (£6.7 billion)[17] in subsidies to the power sector during the last 4 years. Despite this, over 4 years the cumulative loss in GDP due to load shedding is estimated at PKR 5.2 trillion (£35 billion)[18]. If this programme improves the prospects for energy sector reform, the potential return is extremely high. For instance, if this intervention leads to a 0.0002 percent increase in GDP due to better power sector policy, the programme will have recovered its costs within a year.
[17] State Bank of Pakistan. Annual Report on the Economy
[18] Institute of Public Policy. 2012. Economic Costs of Power Outages. Lahore. Pakistan

To ensure that the programme is on track, from 2015, allowing sufficient time for research to have been disseminated, the quantifiable returns will be estimated in each annual review.

Costs Option 2
Using the World Bank (or other multilateral institution) model, the cost stream will differ slightly due to the difference in the timing of the disbursements. The present value of costs, assuming transfers of £1.5 million every two years, is £3,545,523 (details in Annex 1).

Benefits option 2
Delivery through a multilateral institution would lead to the development and dissemination of research products. Based on prior experience the research conducted through the multilateral will be high quality. Academics and donors would be the primary users for this research. Estimating the impact of this research on government policy is difficult as there is no clear linkage between the production of a report and the improvement in policy. Using the same approach as before, we would estimate benefits as increasing the probability of key reforms being undertaken.

Costs Option 3
In government systems, spend will not be consistent – experience shows individual government departments do not have the capacity to spend at the rate modelled in the other options. The present value of costs is estimated to be £1,869,508, with a total (undiscounted) spend of £2.9 million by the end of the programme (details in Annex 1).

Benefits Option 3
Delivery through government systems, if effective, will lead to high technical capacity within government departments. These benefits are hard to quantify. It is difficult to attribute how much higher technical expertise in a government department would lead to improvements in policy. It is also difficult to know in advance which policies will be improved and what would be their ultimate impact.

D. Which is the preferred option and why?

Option 0 means no DFID intervention and thus no challenge to the existing poverty and growth narrative. Currently the debate on growth does not extend to determining how the poor can share in the economic gains. There will continue to be contributions to the overall body of economic research, including on poverty, however there will be no cohesive theme. The International Growth Centre is expected to continue its work on linking policy to practice on specific entry points such as tax administration reform in Punjab. However it does not have an explicit poverty focus and its economic advocacy work is not as broad as proposed under this programme.

DFID will be unable to mobilise a stronger response to support economic reform without additional resources. Over the next half a decade, in the absence of a conversation around the necessity for reform driven by Pakistani stakeholders, we would not expect to see a challenge to the poverty narrative. Currently the major political parties look at poverty from a very narrow lens, viewing the poor as unwilling to work and regarding micro cash transfers as a sufficient intervention. However, our continued engagement has led to continuation of the cash transfer programme even after a change in government at the federal level.

Option 1 is the preferred option. Option 1 looks at the reasons why there is reform inertia and works to address those barriers to change. Option 1 proposes a non-traditional model, which focuses on communication through high level influencing, grass roots mobilisation and the tiers in between. Developing and testing such a model has inherent risks. However, the flexible experimental approach also has a higher probability of success. This is consistent with experience in other countries where DFID and other organisations have used this approach.

Option 2, has somewhat higher costs than option 1 in present value terms as the disbursements will be front loaded. Multilaterals have strong convening power at the federal level. However, this is less true at the provincial and particularly the local tiers. Multilaterals do not have the skill sets in house to reach a broader network of stakeholders. Even if quality research is produced, it is unlikely to be in a form and language that is accessible to the public and decision makers. As a result, there will be no more than incremental changes in policy development.

In option 3, structural change within government departments is difficult and slow. Gaining traction within departments, ensuring spend and then translating that into real change can be extremely challenging. We do not know as yet what the appetite for reform will be in specific departments. Also, staff changes that are required would take time. There is also limited opportunity to target multiple departments, as that would be administratively challenging and if some departments are faster to mobilise than others this could lead to friction about use of resources within departments.

E. What measures can be used to assess Value for Money for the intervention?

Cost efficiency: We will look closely at the cost and quality of outputs. We will encourage innovation in procurement to get competitive effort in production of output/research quality and ensuring peer review. There will also be benchmarks maintained for the costs of undertaking research and disseminating it, while ensuring that quality is maintained.

Effectiveness: We will track policy uptake. The success of the programme is not judged by only the outputs but rather how well those outputs translate into outcomes and impact. That is why the programme will innovate on tracking results of policy decisions. This will track a simple quantitative measure, such as number of policy notes produced and the number of times they are mentioned in the media. This will give a sense of how much the information we generate is circulating. The programme will also capture whether the exposure of audiences to the information we generate increases over time to see if there is a correlation between our advocacy work and the increase in awareness. The annual review will undertake a summary economic evaluation to assess the value generated by the programme based on the three criteria defined in the options appraisal above.

We will also track negative impacts, such as those decisions that negatively impact the incomes of the poor. This is to ensure that we learn from our mistakes.

F. Summary Value for Money Statement for the preferred option

The preferred option, Option 1, allows us to focus on the effectiveness of our intervention by focusing on improving the prospects for reform while protecting the interests of the poor. By supporting key policy development over the next few years, spreading our risk over multiple partners we are able to use a more flexible approach for transformational change.

DFID will ensure an open formal commissioning process for all procurement and commissioning of research to combat any potential bias. The programme will look to ensure research output is from across Pakistan to ensure diversity and inclusion. The priority will be those regions and topics with the highest potential impact on the poor.
Commercial Case

Direct Procurement

Clearly state the procurement/commercial requirements for intervention

DFID will undertake a direct commercial procurement process through the OJEU or a framework arrangement, to select a managing agent to manage both the evidence and influence and policy support components of this programme.

The management agent will be tasked to work with local research organisations and quality assure their work. It should have sufficient technical expertise to advise and closely monitor the implementation.

The contract will include key performance indicators and regular reporting requirements, which will closely be monitored by DFID Pakistan. The programme will be monitored annually and if performance is not consistent with agreed milestones DFID Pakistan reserves the right to re-issue the contract to another management agent.

World Bank’s regional trade and energy programme will compliment this programme. DFID-P will make a contribution of £1m for financial year 2013/14, possibly in two tranches.

Opportunities to collaborate with other donors and partners are being explored as part of the planning stage. This would reduce costs and would deliver better value for money for DFID.

How does the intervention design use competition to drive commercial advantage for DFID?

All procurement will be by competitive tendering using OJEU or through framework arrangements allowing direct comparison to be made to achieve the best balance of commercial and technical expertise.

Market Place Response

Recent experience indicates the existence of a responsive market to the needs of the programme. There are a number of research organisations and institutions in Pakistan that can be relied on produce high quality research. DFID will work with stakeholders to ensure that the market is made aware of the opportunity and due consideration will be given to pre-bid meetings, both to ensure the market is fully informed of the expectations of the programme, and to ensure the best possible technical and commercial responses.

Cost Drivers

The primary cost drivers will be the fees, expenses and overheads of service providers, including specialist technical support, associated and necessary goods, equipment, premises and related travel and accommodation. A number of recent competitions run by DFID Pakistan offer direct access to cost comparisons, and all service providers will be expected to demonstrate their competitiveness by illustrating how they benchmark their costs in a national and/or international context. In addition, service providers will be required to demonstrate how budgets and financing can be linked to DFID’s model for managing economy, efficiency and effectiveness.

Pakistan is generally perceived as a difficult working environment, with access to many areas circumscribed by security restrictions. Duty of Care will be the sole responsibility of appointed service providers, and security will attract a cost premium. DFID Pakistan will complete a Risk Assessment Matrix (RAM) for the project, which will be circulated to all bidders as part of tender packages. The technical evaluation team will assess responses qualitatively with regard to bidders’ understanding of the known and foreseeable risks, risk management and security procedures, as well as their knowledge, experience and resources to manage the demands of the programme.

F. How will the contract & supplier performance be managed through the life of the intervention?

DFID will maintain management and Due Diligence of the appointed Service Provider(s) but outsource management of the downstream supply base. All organisations that compete for high value DFID Pakistan work are subject to pre-qualification, a process that assesses their capability/capacity/resource to meet identified requirements and to supplier disclosure of convictions or proceedings against them including fraud, bribery and corruption.

The appointed Service Provider(s) will be managed through the identification of key high level outputs (including key performance indicators) over the duration of the contract. These will provide the comparators against which satisfactory performance will be measured. The Service Provider(s) will be expected to demonstrate work plans as to how successful delivery will be achieved – payment will be through achievement and results. The Service Provider(s) will be expected to manage downstream supply including Due Diligence in the same way, and to coordinate returns through financial reporting, accurate forecasting, work plan achievement, sub-contract management and demonstration of how continuous quality improvement and cost reduction will be achieved and maintained over the intervention duration. A risk management log will be maintained; proactively logging risks associated with successful project delivery and identifying risk mitigation measures that can keep the project on track.

DFID will make clear in terms of reference that funds may be scaled up or down, based on results achieved. Contracts will allow for DFID monies to be reduced at our discretion if we consider that programmes are not delivering the intended outputs, whether this is due to the performance of service provider, or to external factors.

The contract and supplier performance will be managed by the Deputy Programme Manager in Macroeconomic Stability and Growth (MSG) Team with support from the Lead Adviser and quality assurance from the Team Leader in MSG.

Financial Case

What are the costs, how are they profiled and how will you ensure accurate forecasting?

The total cost of the programme is £4.5m over 8 years. The budget will be split between four components; £2.2m for the economic advocacy component; £1m for the knowledge development component; and £0.3m for monitoring and evaluation and £1m for regional economic growth. DFID-P will rigorously monitor forecast/spend but will also put financial management as a Key Performance Indicator under the contract/agreements.

	2013/14	2014/15	2015/16	2016/17	2017/18	2018/19	2019/20	2020/21
	£ millions	£ millions	£ millions	£ millions	£ millions	£ millions	£ millions	£ millions
Economic Advocacy	0.05	0.2	0.25	0.3	0.3	0.4	0.4	0.3
Knowledge Development	0.05	0.1	0.1	0.1	0.2	0.2	0.15	0.1
Monitoring and Evaluation	0.025	0.025	0.05	0.05	0.05	0.05	0.05	0.0
Regional Economic Growth	1.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0
Total cost	1.125	0.325	0.4	0.45	0.55	0.65	0.600	0.4

B. How will it be funded: capital/programme/admin?

The programme will be funded from DFID Pakistan’s programme budget.

C. How will funds be paid out?

Payments will be made on monthly/quarterly basis in arrears subject to satisfactory performance. The management agent may receive a mobilisation payment in advance is there is a strong case. The World Bank will be paid in advance as per standard practice.

D. What is the assessment of financial risk and fraud?

The assessment of financial risk and fraud is judged to be minimal. Due diligence will be undertaken prior to issuing a contract/agreement. Invoices will be submitted with supporting documents to verify expenditure.

E. How will expenditure be monitored, reported, and accounted for?

DFID will monitor financial reports and evidence provided by the implementing partner to ensure funds are spent well. In addition the Deputy Programme Manager will undertake a spot check during the annual review to ensure that the implementing partner’s financial systems are adequate.

Management Case:

What are the Management Arrangements for implementing the intervention?

Accountability within DFID Pakistan:

Within DFID Pakistan, Economic Growth Group (EGG) will be responsible for implementing the programme. The Lead Adviser and Deputy Programme Manager will ensure that teams outside EGG are consulted on key issues and take part in high level meetings with the implementing partner and stakeholders.

Risk has been assessed against fraud and corruption in the office wide risk framework. It is assessed as low residual risk. Delivery risk has been assessed as medium given the challenges inherent in a new approach. Careful mitigation measures will be put in place to manage this risk.

Governance Group and Basic Services Group will also engage and contribute to the specific activities that have implications for their respective areas. Learning from the implementation of the Transforming Education Programme will be particularly useful in ensuring that the right partners and management systems are in place.

The contracts/agreement will be managed by the Deputy Programme Manager in the Macroeconomic Growth and Stability Team (MSG), with support and advice from the A2L/A2 Economist.

Management

The MSG Deputy Programme Manager will manage the project with support from the Lead Advisor. DFID-P has adequate staff resources to provide proportionate management and oversight of the programme. DFID-P will allocate the following to the engagement with the implementing partner.
1. 40% of the B1 Deputy Programme Manager and 10% of the C1 Programme Assistant
2. 60% Full Time Equivalent (FTE) of the Economic Advisors (senior economist, trade economist, lead advisor) and 10% FTE of the Governance Advisor, and 5% of the Group Head.

1. The Managing Agent will be the primary recipient of funds for the economic advocacy and knowledge management component (see Annex 2). It will be responsible for the following functions:
  1. A technical steering committee that comprises of private sector, government and civil society to provide input on the key priorities of reform. This will be the mechanism to ensure that there is direct communication with the government and their priorities for reform are being addressed.
  2. A strategy unit that will design tools (including mobile and web platforms) that allow people and governments to bring about change. For instance, increased transparency on how many individuals and organisations are paying their energy bills will increase the demand for accountability.
  3. A communications unit that will convert existing research into plain language (including Urdu) and use it to design message for how citizens can interact with their government on key issues such as energy or tax.

B. What are the risks and how will these be managed?

 Risk Assessment
Risk (RAG)	Likelihood	Impact	Mitigation
Lack of Political buy-in or not receptive to policy change	High	High	DFID will engage with all political parties not only at the leadership level but also the grassroots level to ensure the latter lobby for policy reform. The programme will target those areas where there is greater opportunity to create broad based support for reform. High level visits and support from the wider mission will be used to raise the profile of key messages.
The research is not used, resulting in the project not delivering the right outcomes	Low/Medium	High	DFID-P will use its influence to engage Pakistan stakeholders, multilateral institutions and other donors to support the reform agenda.
Research and data perceived too sensitive to be used	Low	Medium	DFID-P to ensure there is a communication strategy in place that will engage with diverse stakeholders.
Spending the forecasted budgets	Low	Low	DFID-P will rigorously monitor forecast/spend but will also put financial management as a Key Performance Indicator under the contract/agreement
Agents who oppose reform accuse DFID of interfering in political process	Medium	Medium	Research and debate is being undertaken by Pakistanis. The demand for change should be, and seen to be, from Pakistani stakeholders, rather than DFID. This will help inform policy makers and make agreement around delivery easier.
Change in government (federal/provincial) post elections	High	Low	This is an 8 year programme so government partners are likely to change during that period. The delivery is being undertaken by private sector so while elections (2018) will increase volatility it should not affect operations. DFID-P will monitor closely.

C. How will progress and results be monitored, measured and evaluated?

DFID-P will monitor progress on a yearly basis through Annual Review process where an assessment will be made against the milestones agreed in the logframe and the Business Case. The programme will conduct a baseline at the start of the programme to measure the degree of exposure of different audiences to debates on economic reform. Outcome indicators that track this degree of exposure will be designed at that stage, and the baseline will provide benchmarks. For instance, the transmission effectiveness index will track over time how much different audiences understand the issues in the same period as the economic advocacy campaign is run.

In addition, the managing agent will submit quarterly progress report and DFID-P will be holding regular meetings to discuss progress of the programme.

The programme will measure effectiveness by measuring rate of research uptake and using qualitative measures to assess economic and social impacts on the poor. To measure impact, the programme will look at the changes (disaggregated by region and gender) in income and deprivation levels of the poorest 40 percent of the population. If growth policies explicitly take into account the interests of the poor, then economic gains and benefits will be shared more widely. As a result the poor will benefit from both income and other opportunities to improve their lives.
Annex 1. Economic Appraisal – Discounting of cost stream

Discount Rate	10%
	2013/14	2014/15	2015/16	2016/17	2017/18	2018/19	2019/20	2020/2021	Total
Cost Option 01	1,125,000	325,000	400,000	450,000	550,000	650,000	600,000	400,000	4,500,000
Present Value	3,102,117

Cost Option 02	1,000,000		1,000,000		1,500,000		1,000,000		4,500,000
Present Value	3,545,523

Cost Option 03	200,000	300,000	400,000	400,000	400,000	400,000	400,000	400,000	2,900,000
Present Value	1,869,508

Annex 2. Management Structure

Identifying champions for reforms and mapping obstacles to change

Tracking impact of messages and communications on attitudes of key constituents

Policy brokerage – linking policy makers and citizens to evidence

Converting research into plain language (Urdu)

Communicating key messages on reform to different audiences

Mobile and web tools so citizens and government can share information on key economic issues

Research Networks
Government departments

IFUSE/IGC
Private sector
Civil society
Steering Committee
Technical advice, networking

Economic Advocacy
£3.2m
£0.3m
£1m
Knowledge Management
Monitoring and Evaluation
Managing Agent
DFID Pakistan

Regulatory framework for Pakistan’s engagement in regional energy market

Feasibility study Wagah border

World Bank