Evaluation Management Unit of the Making All Voices Count Programme
Final Evaluation Report

DFID
June 2018

In association with:

# Table of Contents

List of Annexes

List of Figures
Figure 1: The MAVC Theory of Change	19
Figure 2: MAVC grants by type	20
Figure 3: MAVC grants by country	21
Figure 4: The DFID VfM Framework	27
Figure 5: Grants reviewed at outcome level	41
Figure 6: Routes to Government Feedback	42

List of Tables AND BOXES

Table 1: Summary of Evaluation Questions, Evidence Sources and Methods of Analysis	30
Table 2: EIU Democracy Index value for tier 1 countries	44
Table 3: Estimating progress against impact indicator 2	44
Table 4: Estimating progress against outcome indicator 3	46
Table 5: Estimated indicative grant benefits relative to costs	60
Table 6: Black Sash grant – basis for estimating cost-effectiveness	63
Table 7: CBA data	67
Table 8: CBA results	68
Table 9: MAVC and SEATTI cost metrics	69

Box 1: DFID Business Case arguments for and against a multi-funder programme	88

# Acknowledgements
This report was written by Gil Yaron and Cecilia Luttrell with input from Catherine Renshaw, Jane Meme, Andrew Thornley, Lebogang Shilakoe, Helen Stevenson, Damien Faget and Sarah Goodwin. The MAVC Fund Management Consortium has cooperated fully with this evaluation and we recognise the effort made to facilitate our work. We are particularly grateful to the many interviewees who have given their time to help with this evaluation.

# Acronyms

AA / AM	Assurance Assessment / Amandla.mobi
BS	Black Sash
CBA	Cost-Benefit Analysis
CEA	Cost-Effectiveness Analysis
CED	Country Engagement Developer
CK / CLEP	Caritas Kitui / Country Learning Engagement Plan
CoP	Community of Practice
CSO / CW	Civil Society Organisation / Corruption Watch
DFID / ED	Department for International Development / IRC (Etoil Daang)
EMU	Evaluation Management Unit
EQ	Evaluation Question
FMC	MAVC’s Fund Management Consortium
FSH / GBP	Free State Housing Campaign / Great Britain Pound Sterling
GIC / GR	Global Innovation Competition / Grassroot
GYA / Hivos / IBP	GY Associates Ltd / Humanist Institute for Cooperation / International Budget Partnership
ICT	Information Communication Technology
ICW / IDS	Indonesia Corruption Watch / Institute for Development Studies
IMC	IMC Worldwide Ltd
IRC	International Rescue Committee
KPI	Key Performance Indicator
KYGC / LENGGO / M&E	Kwale Youth & Governance Consortium / Local Empowerment for Good Governance / Monitoring and Evaluation
MAVC	Making All Voices Count Programme
MEL	Monitoring, Evaluation and Learning
MODAC	Mobilising Data for Anti-Corruption Programme
MSC	Most Significant Change
NGO / OD	Non-Governmental Organisation / OD Labs
OGP	Open Government Partnership
ON	Omidyar Network
PRLG	Practitioner, Research and Learning Grant
QAS	Qualitative Assessment Scorecard
REL	Research, Evidence and Learning
ROT	Research Outreach Team
SA / SEND	South Africa / SEND Ghana
SASSA	South Africa Social Security Agency
SC	Steering Committee
SIDA / SSP	Swedish International Development Cooperation Agency / Southern African HIV Clinicians’ Society
ToC	Theory of Change
ToRs	Terms of Reference
USAID	United States Department for International Development
USD	United States Dollar
VfM	Value for Money
WB / WYDII	World Bank / Women and Youth Development Institute of Indonesia

# Executive Summary
Background to MAVC
Making All Voices Count: A Grand Challenge for Development (MAVC) brought together the Department for International Development (DFID), the US Agency for International Development (USAID), the Swedish International Development Cooperation Agency (Sida) and Omidyar Network (ON), to create a $45m fund to support innovation, scaling up and research in the use of technology and non-technology approaches to support open, responsive government and citizen engagement. MAVC has been implemented by the Fund Manager Consortium (FMC) consisting of Hivos (lead organisation), the Institute of Development Studies (the Research and Evidence manager) and Ushahidi (the innovation coordinator). MAVC ran from 2013-2017 and, from mid-2014, evolved into a two-tier approach: country strategies and extensive brokering in tier one countries (Kenya, South Africa, Indonesia, Philippines, Tanzania, Ghana) with lighter, strategic thematic targeting for tier two countries (Bangladesh, Pakistan, Mozambique, Nigeria, Uganda, Liberia).

The MAVC Theory of Change (ToC) is based on the view that there were: ‘Important new opportunities emerging to use mobile & internet technologies to close the gap between citizens and governments, through wider information availability, more opportunities to express citizen demands, and new ways to enable citizens to work together and with government. Mobile & internet therefore have potential to add value to wider work to improve transparency & accountability.’ DFID MAVC Business Case (2012).

The MAVC programme designed around the ToC has provided 178 small grants to NGOs, technology start-ups, and researchers to support innovative ideas, help scale existing initiatives, and finance research to understand what works. Numbers and category of grant are shown in the figure below.

Source: MAVC draft Final Narrative Report (2017)

MAVC has funded work in four areas:
- Backing innovative ideas and technology solutions (35-40% of available budget).
- Scaling up successful initiatives and responses (35-40% of available budget).
- Building an evidence base on what works and why (20-25% of available budget).
- Catalysing global attention and action around these issues (included in the 20-25%).
Policy Context
MAVC is aligned with a number of the policies of the funding organisations. Perhaps most significant is the commitment to the Open Government Partnership (OGP). This was launched in 2011 and now has 57 members committed to improving open government and citizen engagement, including using mobile and online technologies to do so. The UK became lead co-chair from Sep 2012-Sep 2013 (during the design and commencement of MAVC), and the priorities during this period were closely aligned with those of MAVC. MAVC also contributes to the Sustainable Development Goal (SDG) 16 to ‘Promote peaceful and inclusive societies for sustainable development, provide access to justice for all and build effective, accountable and inclusive institutions at all levels’.

Background to the evaluation
DFID engaged an independent Evaluation Management Unit (EMU) managed by consultants IMC Worldwide and GY Associates, who contributed to the annual reviews and this evaluation. The original ToR (Annex 1 to this report) state that: ‘The main purpose of the evaluation is to learn more about innovative approaches to amplifying the voices of citizens and enabling governments to respond effectively to what citizens are saying. The evaluation will aim to answer evaluation questions around which approaches (or parts of approaches) may best support the MAVC objective of supporting innovation, scaling up effective initiatives and commissioning research into the use of technology and non-technology approaches to support open, responsive government and citizen engagement, as well as recording the impact of these approaches. A secondary purpose of the evaluation will be to assess mechanisms (e.g. whether bringing together four funders for a common purpose, improves or hinders the success of initiatives in this area).’

Methodology and independence of the evaluation
The EMU is tasked with answering evaluation questions (EQs) and generating learning on which approaches best support the MAVC objectives. This independent evaluation of MAVC looks both at process and impact, using EQs derived from the programme Theory of Change (ToC). To answer these EQs we draw on:
- 11 representative grant case studies from the portfolio of innovation, scaling and Global Innovation Competition (GIC) grants in Kenya, Ghana, South Africa and Indonesia. We look at changes between project baseline and endline, often with treatment and control groups.
- Country case studies, based on 11 purposive ‘best-bet’ innovation, scaling and GIC grants selected by the FMC in South Africa (5), Kenya (3) and Indonesia (3).
- A review of the global MAVC Research Evidence and Learning (REL) component and its contribution to the wider MAVC programme. This draws on 10 randomly selected, representative REL grants and uses contribution analysis and process tracing.
- Other global perspectives, using stakeholder interviews and document review.

In addition to the grant case studies, this end of programme evaluation draws on more than 150 interviews and reviews of more than 300 documents.

Details of the grant-funded projects mentioned in this evaluation can be found in the separate report Annexes (5 – 8) but we also provide a brief summary of each of them in the attached and hyperlinked Appendix 2.

In order to promote learning within the programme, the EMU has attempted to be a ‘critical friend’ to grantees and the FMC more generally.  This has involved feeding back findings from the grant case studies to grantees, participating in MAVC learning events and working constructively with the FMC monitoring, evaluation and learning (MEL) team based at IDS.  In this context, our evaluation approach has helped to maintain independence. We have focused on outcome and impact levels of the logframe, whereas the large bulk of MEL data relates to logframe activities and outputs.  We have used some MEL data to assess progress against programme outcomes, with independent verification of major claims.  Likewise, claims made by grantees and FMC in the country case studies and the REL review have been verified by our independent researchers, who have been able to work freely.   The EMU grant case studies rely on independent evidence collected at baseline and endline by our researchers.  These case studies have required the cooperation of grantees but, in every instance, our researchers have been able to work freely and without interference.

We recognise that this evaluation will have a number of audiences, including MAVC donors, other donors, government policymakers and practitioners - and among these, grantees. While most recommendations are targeted to donors and policymakers, many of our findings will be of interest across these groups, with case study findings particularly relevant for practitioners.

Findings: achievement of outcomes and progress towards impact
Just one of the 11 representative grant case studies (Caritas Kitui) has delivered at the MAVC outcome level and has strong potential for scaling up (although it has not been). This is consistent with expected returns for early stage innovation, but this evaluation finds considerable evidence that problems in programme design and implementation have reduced success rates below those that could have been achieved.

FMC ‘best-bet’ grants should be much more successful than the MAVC portfolio as a whole. Two of these grants (Black Sash and KYGC) appear to have had very significant outcome-level results, the former after deliberate MAVC scaling. A number of other grants (LENGGO, IBP, Amandla.mobi, Corruption Watch, INFEST and CSK) have also contributed in varying degrees to citizen-government engagement for hundreds of thousands of people.

Progress against logframe outcome and impact indicators
There is evidence that two outcome indicator targets have been achieved (relating to number of citizens receiving a response from government agencies and number of changes in government policy). The third outcome indicator target (a 20% increase in the number of citizens in contact with MAVC who believe reporting deficiencies in public services is likely to lead to some improvement) has not been met. The target for impact indicator 1 has been achieved although there has been only very limited progress towards impact indicator 2.

Key findings, lessons and recommendations from evaluation questions on outcome and impact
MAVC has highlighted two critical policy gaps for ICT use in developing countries:
1. The problem of weakly regulated private companies selling personal data that is used to target vulnerable households, is well known in highly industrialised countries but is even more of a problem where a larger proportion of households are poorly educated.
2. There is a lack of regulation for NGO health sector interventions in Kenya (and possibly other countries).

We recommend (first priority):
Donors build on the experience of Black Sash to help governments, with CSO support, to strengthen protection of personal data in developing countries, and effectively scrutinise and regulate the contracting out of e-services.
We recommend (second priority):
The Government of Kenya and possibly others consider developing a registry for health sector, drug-related tracking innovations. It should be a requirement for any NGO or private business proposing a drug tracking or pricing innovation to show they have consulted this registry.
Fixing a one-year time horizon for tech4TA projects (as MAVC tended to) often leads to sub-optimal implementation (e.g. focusing on supportive elected leaders rather than building trust with administrators who will be in post for longer) or exiting when potentially successful investments are too immature to demonstrate success. Grants are also likely to have been more effective if based on project-level theories of change.

Our findings are consistent with the findings of De Lanerolle, Walker and Kinney (2016), based on MAVC-funded research in Kenya and South Africa, on developing tech tools for transparency and accountability. We found that only two of our 22 case studies actively developed tools with users, while our Indonesia country case illustrates why it is so important for non-government grantees developing tech tools to plan engagement with government tech tool users.

We therefore recommend (second priority):

Adding to the recommendations of De Lanerolle, Walker and Kinney (2016) for organisations choosing tech tools. Specifically, we recommend that non-government grantees developing tech tools should engage with government users of tech tools that aim to address similar issues.
Government is not as homogenous as it appears from the MAVC Business Case and this led to some unexpected results:
- Service delivery staff may not have the same incentives as performance monitoring or communications staff who want to engage with grantees. ICT can magnify these tensions.
- The on-going struggle between progressive and regressive factions within even sub-national government makes it difficult to work with one-year, one-off grants.

MAVC has valuable evidence on the success factors for tech-enabled collective action:
- Mobile phone technology (e.g. social media, digital mapping) lowers the cost to citizens of raising their voice but the technology itself generally only has a modest impact on their cost of collective action (the big cost is in the time required for offline activism or even repercussions from service providers).
- Strong assumptions on ICT access and use were made by virtually all grantees and were almost always flawed. This led to negative, unintended results.
- The experience of trying to support collective action on health facilities suggests that highly localised problems and localised governance arrangements raise transactions costs and hence the ability of government to respond.
We identify 6 cognitive biases driving tech-related optimism bias affecting MAVC. These are very likely to apply to public sector programme appraisal more generally. Given the evidence from MAVC and the documented tendency to overestimate what tech can deliver.
We therefore recommend (first priority) that:
- Tech4TA project appraisal guidance specifically considers likely sources of tech optimism bias; and
- HM Treasury add tech optimism bias into the next edition of The Green Book.
Key findings, lessons and recommendations on innovation and scaling
MAVC design made limited use of the literature on good innovation practice. Some elements of innovation support were added to MAVC through Ushahidi tech mentors and in-country tech hubs but these were not well integrated with the other programme activities and were often not effective. Likewise, there were some examples of agile and adaptive innovation but no systematic support for this. In practice, the open call for innovation and scaling proposals in year 1 produced far more grants than MAVC had capacity to nurture, exacerbated by the lack of joint working across the consortium, management weaknesses and by having numbers of grants made as a trigger for budget disbursal. It led to a fundamental mismatch between MAVC innovation objectives and MAVC innovation practice.
We therefore recommend (second priority):
Funders need to match the number and timing of innovation and scaling grants to the programme capacity for incubation and acceleration. This is especially important when considering the number of grants as a key performance indicator.
There was no consistent definition of innovation within MAVC, but it was often (mis)understood as new, tech-focused approaches. Where the focus was on tech (in the absence of user-focused design), MAVC innovation and scaling projects were typically not successful. The REL component took a much more tech-realist position but innovation and scaling grantees generally did not take these messages on board. Nonetheless, some of the more successful interventions involved getting organisations to use modest ICT when it had not been used in this way before.
Scaling within MAVC was constrained by: using scaling grants to test ideas that were no more proven than innovation grants; a lack of evidence on success to take to potential funders; absence of innovation pathways towards further investment where grants or elements of grants had proven successful; and too short a programme lifetime.
Key findings, lessons and recommendations on brokering
Relying on an Open Call in year 1 made it difficult for start-up local organisations without capacity or experience in bidding for international donor funding to bid. One-year grants, and the resource intensity required to support ‘unusual suspects’, also produced strong incentives to use established NGOs with existing relationships with government.

MAVC brokering was far more successful in South Africa than in Indonesia or Kenya, reflecting stronger CED experience and country team capacity, and creation of an effective community of practice for civic tech engagement. One aspect of brokering that worked well in Indonesia was the ‘HackJack’ hackathon events - credited by government as being the ‘first time that the wall was broken between the government and technologists’.
Given these findings, we recommend (second priority) that:
Future DFID-funded programmes involving brokering work, include a clear statement of what brokering is intended to achieve in a given country context, and require a supporting stakeholder analysis to identify who to work with.
Cross-cutting findings and lessons on Poverty and Gender
This evaluation identifies some key findings in terms of outcomes on poor and marginalised groups. Access to technology was a significant barrier. A key lesson is the need for interventions to consider both expected results and differential access to technology. The lack of recognition of the barrier of access to technology was rooted in a failure to consider the factors determining access to technology. Users were not involved in the design: only two of the 22 project case studies (Grassroot and KYCG projects) actively developed tools with users. In some instances, the failure to recognise the role of social norms in technology use led to women being excluded. On the other hand, the Yowzit project learned from the failure to address this issue in their original innovation grant with the help of a practitioner research grant, while the Caritas Kitui and OCOS projects adapted to using FM radio when access to mobile technologies did not work as expected. MAVC also highlighted an important policy gap around the way the use of technology is used to manipulate poorer less educated households (the Black Sash project).
Although grants took gender and poverty into account in the design and strategy stage, there was less evidence of a sophisticated analysis of exclusion (based on gender and other forms of differentiation) which would have allowed the challenging of social norms and power relations which underlay marginalisation.

Key findings and lessons on value for money (VfM)
We were able to develop cost-benefit analysis for two scaling grants (Black Sash, South Africa and MOPA in Mozambique). The MAVC grant enabled Black Sash to present evidence and secure repayment of unauthorised social security deductions. Their mid-point estimate is that it would have taken 18 months longer to achieve this without the grant. This translates to a discounted saving of £6.8 million and a benefit to cost ratio of 16.9. The MOPA benefits stem from participatory monitoring leading to clearance of informal waste dumps. Using values taken from the international literature, we estimate indicative benefits of at least £0.73 million and a benefit to cost ratio of 2.7.
If just two out of the 11 EMU case studies produced benefits like these and we assume that all the rest have zero benefits, the net benefit to cost ratio would be 3.3. Hence, even the small number of successful MAVC grants could plausibly have produced benefits that significantly exceed programme costs.

Comparing MAVC costs with the much smaller SEATTI programme (South East Asian Technology and Transparency Initiative) suggests that the ‘management, equipment, office and administration costs’ accounted for 29% in MAVC against 20% in SEATTI. The difference reflects the additional costs of the MAVC consortium model with three partners taking on management tasks. Problems with coordination across consortium partners and limited synergies over the programme life have led to lower than expected value for money.

Key findings and lessons on Research Evidence and Learning (REL) strategy implementation
The REL component was not well integrated with innovation, scaling and GIC grants. Grants funded by the REL component operated disjointedly from country programmes. A comprehensive Research and Evidence strategy was developed but rarely referred to by other components of MAVC or the donors. This lack of integration was difficult to address retrospectively due to working cultures of the different organisations and the fixed budget allocations, which were set at the start of the programme. REL would have been more effective if it had been led by better resourced country teams that included REL staff. Fewer grants with more strategic focus would have also helped delivery and communication of outputs.

Key findings and lessons on learning within MAVC
Within-programme learning has been limited despite significant efforts made by IDS on taking over the MEL function in 2015. The separation of ‘territory’ and related budgets between consortium partners has remained perhaps the most significant barrier to learning across the programme. Slow granting progress led to a focus on KPIs designed around granting which were divorced from the ToC. This made it difficult for Country Engagement Developers (CEDs) to prioritise learning and led to poor incentives at the project and country level to discuss and learn from failure. Comparison of grantee reporting and EMU case studies, suggest there was some ‘rosy reporting’.

The three International Learning Events were a successful method of bringing learning around research and practice together. In addition, the South Africa community of practice – although not a REL activity - provided very effective opportunities for grantee learning. Most grantees also believed that engagement with MAVC had strengthened their organisational capacity. Mentoring by Ushahidi and IDS played a part in this. Yet, ironically, as grantees had to request mentoring, the weakest often failed to do so. We also found very little evidence of tech hubs providing in-country learning.

Key findings and lessons on the contribution of the REL component to the field of technology and accountability
MAVC helped to highlight the importance of providing a political lens on issues of accountability in the technology space. Yet once findings were distilled into easily communicated ‘sound bites’, some global stakeholders at the IDS Dialogue suggested there was ‘little that was new’ in the conclusions from MAVC’s research. Nonetheless, our assessment is that value has been added through the addition of higher quality research, the depth of new evidence and the way this is presented.

Practitioner learning and research grants (PRLGs) attached to MAVC projects added substantial value to these projects but did not serve the original purpose of feeding back learning to the programme ToC. We also found that despite the number, and high quality, of written research products, their communication was limited by the MAVC website and lack of summarised, easily digestible content for different audiences. Global and country level stakeholders appear to want more targeted communication products. Delays to programme implementation and interruptions to funding have also led to very late findings with limited time for synthesis.

Key findings and lessons on efficiency, effectiveness and co-ordination from the multi-donor funding and management arrangements for MAVC
In answer to the question of whether bringing together four funders for a common purpose improved or hindered the success of MAVC, we found that the risks identified in the Business Case came to pass but the expected benefits were only partially realised. The reasons for this are that:

The international context at the time of MAVC programme development (following the Arab Spring) led to unrealistic expectations of what tech for governance could deliver. Although donors had developed a programme ToC, different organisational cultures, practices and priorities led to differing expectations of how to deliver it. These could not be resolved in a one-month inception period, and DFID allocation of staff time was insufficient given these complexities, combined with a high rate of DFID staff turnover and problems that emerged from FMC programme implementation. Moreover, the three FMC partners had different skills and organisational cultures – an advantage on paper – but presented substantial practical challenges that were not surfaced during procurement.

In practice, there was clearly mobilisation of funds from a range of donors. However, there is very little evidence that the combination of donors increased the ability of MAVC to influence developing country policy and practice. Donor country offices were not involved in supporting any of the five grants that the FMC MEL team identified as contributing to policy change, for example. It is also the case that while knowledge was shared among donors during the design phase, this benefit was outweighed by implementation with different organisational cultures, practices and priorities.

The principal recommendations of the 2015 Management Review, undertaken in response to donor concerns, were all implemented. This improved co-ordination within the FMC, but a number of serious limitations remained in that Hivos, Ushahidi and IDS retained their own budgets and had their own granting targets; incentives to work together were further weakened by short grant timeframes, overburdened country teams and conflicting organisational objectives. There were also unrealistic expectations of CEDs who were expected to combine a vast range of skills. Resource allocation and incentives skewed the programme to the centre rather than the country teams and engagement with the service delivery side of national and sub-national government remained weak.

In July 2016, DFID requested an assurance assessment of all MAVC grant spending, reflecting a lower appetite for risk under a new Secretary of State. This required Hivos to take some additional measures to mitigate risks of granting to inexperienced grantees that MAVC was asked to support. However, we found that putting donor funding on hold seriously impacted implementation and undermined credibility with government and CSO partners.

Under pressure to meet grant targets, CEDs were not able to provide support to grantees across the areas required and the other essential brokering and MEL functions. Given capacity constraints, the large number of grants together with KPI targets on grant disbursement, created a focus on quantity at the expense of quality. We also believe that a longer no-cost extension (1 year rather than 6 months) would likely have freed up more resources for learning, increased programme effectiveness and hence value for money.

A number of recommendations flow from this component of the evaluation.

Recommendations (first priority):
Programmes such as MAVC should do less (fewer countries, fewer grants) but do it better (properly resourced for incubation and acceleration, sufficient in-country capacity and joining up innovation, scaling and research components). This is likely to involve moving resources from headquarters to country teams and embedding monitoring, evidence, research and learning capacity at the country level.

Programme managers need to scenario test what they are asking country teams to deliver with the teams (if in place) or against realistic skill sets and time availability for proposed roles.
Recommendations (second priority):
With complex multi-donor programmes, donors need to leave enough time and put in place and resource a process to reach common expectations for implementation. Ideally, this would be done prior to implementation but, if not, a six month or even one-year inception period is likely to be required.

Multi-donor programmes should use independent review at the design stage to help identify conflicting objectives and independent facilitation to strengthen programme design.

Multi-donor agreement should be secured in advance of implementation to cover what is needed from the fund management consortium and how contact with the contract holder will be managed to deliver essential reporting metrics for all donors and limit transactions costs for the implementing consortium.

Donors should clarify the decision taking powers of programme steering committees with independent members at the outset. This should specifically cover the case where the programme is badly underperforming.

The DFID Business Case risk assessment should consider implications for DFID staffing.

DFID commissioners need to ensure they have a good understanding of governance arrangements in a contracted consortium (taking into account differing organisational cultures, systems and practices) and what donors will need to do to support effective consortium working. Arrangements need to be tested against likely practical challenges at tender and throughout the inception phase.

Funders should require consortium management arrangements that incentivise re-allocating funds between consortium partners to best deliver the ToC if the evidence supports this. It should be made clear before contracting how this will work in practice.

Funders should note that committing to a longer programme life (such as 2 x 3 or 2 x 4 years if success criteria are met) provides better incentives for consortium partners to invest in common systems, as they have more chance of recouping their investment.

Donors should involve their country offices in design and encourage formal linkages of programmes such as MAVC with country programmes. Programme designers should accept that busy country office staff are very unlikely to commit the necessary time to support without a link to their work plans.

# introduction
## Background to MAVC
Making All Voices Count (MAVC) aims to support innovative solutions and uses of technology to amplify the voices of citizens and enable governments to respond effectively to their concerns. Overall, it aims to support more effective governance and accountability in the spirit of the Open Government Partnership (OGP), which was launched in 2011 to promote transparency, empower citizens, fight corruption and harness new technologies to strengthen governance. MAVC is a partnership between the UK Department for International Development (DFID), Omidyar Network (ON), the Swedish International Development Agency (Sida) and the United States Agency for International Development (USAID). This partnership mobilised a $45million fund to support innovation, scaling-up and research in the use of technology and non-technology approaches to open, responsive government[1] and citizen engagement. This programme contributes to the first UK Aid Strategy objective - strengthening global peace, security and governance.
[1] This refers to government acting effectively to address issues raised by citizens. The essential components of a responsive government are discussed in detail in MAVC Learning Report “Addressing failure in ICT-enabled ‘citizen voice – government responsiveness’ interventions: unpacking core assumptions and essential components”, Herringshaw (2017). Available here

The DFID Business case set out the strategic case for MAVC by noting that ‘Democratic systems are inhibited by timescales and practices that provide only occasional opportunities for citizens to express their views formally about governments, such as during elections. Many ordinary people, including the poor and disadvantaged nevertheless have access to tools and data that can enable them to express their views and network with other people with similar problems on a more regular basis, through mobile phones and the internet. Increasingly, citizens expect to be able to use these data and tools in relation to government performance on specific policy issues, rather than waiting to use a single vote in a ballot box. In reality, there can be few opportunities to do so. Even where citizens’ voice is communicated regularly and effectively, it is often given inadequate consideration by governments. Governments may face constraints on their ability to release useful government data, or to consult and respond to citizens’ concerns, particularly at local levels. Such limited interaction translates into few opportunities for officials to understand public expectations and few incentives to meet them. This results in poor governance, citizen alienation, and discrimination. In short, open government depends on closing that feedback loop between citizens and the government’.

The MAVC Theory of Change (ToC) is based on the view that there were: ‘Important new opportunities emerging to use mobile & internet technologies to close the gap between citizens and governments, through wider information availability, more opportunities to express citizen demands, and new ways to enable citizens to work together and with government. Mobile & internet therefore have potential to add value to wider work to improve transparency & accountability.’ DFID MAVC Business Case (2012)[2] p13. The programme ToC was refined over time (e.g. adding intermediate outcomes and explicit linkages between levels) and is summarised in Figure 1 below.
[2] All published DFID documents relating to MAVC (including the Business Case) can be found at: https://devtracker.dfid.gov.uk/projects/GB-1-202628/documents

The DFID MAVC Business Case saw MAVC as a way of overcoming the following barriers that limit effective citizen engagement and government responsiveness:

Citizens lack incentives: Citizens may not have the necessary incentives to express their feedback on government performance—due to apathy, fear, a sense of powerlessness, little access to technology, or lack of reliable information.

Citizens lack meaningful opportunities: Citizens need greater access to better tools and know-how, to easily engage in a way that results in government action and citizen empowerment. In addition to technical capacity, people need to be knowledgeable about their rights and responsibilities. For many people, participating in a larger group or movement, or networking with other groups to collaborate together, facilitates and strengthens their engagement with the state or service providers.[3]
[3] Gaventa J. & G. Barrett ‘So What Difference Does It Make? Mapping the Outcomes of Citizen Engagement’ IDS working paper 347 (IDS, Sussex: 2010).

Governments lack incentives: At the same time, governments need incentives to respond to citizen input whenever possible and encourage citizen participation. The government’s response to citizens should be reinforced by proactive, public communication. This initiative will help create incentives for government to respond and, where government responds effectively, increase citizens’ confidence in and approval of government performance.

Governments lack ability to translate citizen feedback into action: Governments need better tools to effectively analyse and translate citizen input into information that will lead to solutions and shape resource allocation. Once captured, citizens’ feedback (on their experiences with government performance) must be publicly communicated to engage both the government and the broader public in finding a solution.

The MAVC programme designed around the ToC has provided 178 small grants to NGOs, technological start-ups and researchers (see Figure 2 below) to support innovative ideas, help scale existing initiatives, and finance research to understand what works. In order to exploit mobile and web technologies, and other innovations, MAVC has funded work in four areas:

- Backing innovative ideas and technology solutions (35-40% of available budget).
- Scaling up successful initiatives and responses (35-40% of available budget).
- Building an evidence base on what works and why (20-25% of available budget).
- Catalysing global attention and action around these issues (included in the 20-25%).

DFID implemented this by contracting a Fund Management Consortium (FMC) consisting of Hivos (lead organisation), IDS, (Research and Evidence manager), and Ushahidi (innovation coordinator).

The expected impact from these funded activities is: ‘All people, including the poor, are able to engage and call to account public and private institutions on policy issues that matter most to them.’ The outcome is: ‘Improved relationships and increased opportunities for constructive dialogue between citizens and governments (in MAVC countries).’ By November 2017, the programme aimed to enable 1.2 million citizens (50% female) to receive a response from relevant government agencies where MAVC operates, with 20 improvements in relevant government policy and a 20% increase in positive user/citizen satisfaction ratings for both men and women.

MAVC ran from 2013-2017, with some important changes to the programme in 2014 and 2015. In early 2014, the programme adopted a two-tier approach to concentrate resources more effectively. This involved developing country strategies and extensive brokering[4] in ‘tier 1 high priority’ countries (Kenya, South Africa, Indonesia, Philippines, Tanzania, Ghana) with lighter, strategic, thematic targeting for ‘tier 2 priority’ countries (Bangladesh, Pakistan, Mozambique, Nigeria, Uganda, Liberia). Numbers of grants by country are shown in Figure 3. A management review commissioned by the MAVC funders in 2015 led to changes. These included a new FMC senior management, creation of a cross-consortium leadership team, Hivos taking over management of all innovation and scaling grants, and IDS taking on grantee Monitoring, Evaluation and Learning (MEL).
[4] Extensive brokering refers to distilling and sharing targeted knowledge, facilitating new relationships between stakeholder groups to promote innovation, and bringing together a range of practitioners for focused learning events.

Figure 1: The MAVC Theory of Change

Figure 2: MAVC grants by type

 Source: MAVC draft Final Narrative Report (2017)
Figure 3: MAVC grants by country
 Source: MAVC draft Final Narrative Report (2017)

MAVC grant selection systematically took gender into account. Moreover, most innovation and scaling grantees were civil society organisations (CSOs) or NGOs with a commitment to working with poor and marginalised groups. Consequently, grant proposals to improve mechanisms for citizens to engage with government often highlighted benefits to the poor and marginalised but only a small minority of grants specifically focused on gender or poverty. Some research grants explicitly focused on marginalisation as ’exclusion and inclusion’ was one of five research themes and more than 1/3 of research grants were to support research and learning by practitioners (typically CSOs and NGOs).

## Policy Context and linkages with other programmes
### Policy Context
This section briefly discusses MAVC within the wider transparency and accountability policy context. In terms of individual government policy context, this sits at the heart of each country case study and is described in detail there.

MAVC sits within its donor policies in terms of promoting transparency and accountability in governance practices through innovation and technology. As noted in the MAVC business case, DFID supports the evidence that democracies based on inclusive political settlements, are more responsive to their citizens and generally make better progress towards the MDGs[5] than poorly governed, non-responsive ones. Further, that effective governance is a key factor underlying economic growth[6] and poverty reduction.[7] The substantial research component of MAVC responds to the findings of the ‘Review of Impact and Effectiveness of Transparency and Accountability Initiatives’, commissioned by DFID and the Transparency & Accountability Initiative in 2010. A number of findings pointed to the need for more outcomes-focused evidence of the use of technology and accountability, such as for service delivery in terms of access to information and community dynamics and the role and use of Freedom of Information by civil society.
[5] DFID (2009) Building the State and Securing the Peace, Emerging Policy Paper, p.2
[6] Kaufmaan D. and Kraat, A. (2002) Growth Without Governance, World Bank Policy Research Working Paper No 2928.
[7] Lakshman, N. (2003). Political Economy of Good Governance for Poverty Alleviation Policies. ADB Economics Working Papers.
The DFID policy paper[8] ‘2010 to 2015 government policy: governance in developing countries’, which was in place during programme design and through the first half of MAVC, sought to address the problem that ‘Up to 4 billion people in the world can’t access fair and functioning justice systems. Many are also deprived of democratic or accountable systems of government’. The action areas dovetail with the objectives and grant project focus areas of MAVC, including improving justice for poor people, improving effective democratic systems through better governance and fair elections, reducing corruption, improved public budget management, promoting citizen participation in feeding back to government services to improve accountability.
[8] Accessible here.
The UK and US are members of the Open Government Partnership, launched in 2011 which now has 57 members committed to improving open government and citizen engagement, and using mobile and online technologies to do so. The UK became lead co-chair from September 2012 to September 2013 (during the design and commencement of MAVC), and the priorities during this period were closely aligned with those of MAVC.
The tier one and tier two countries all sit within DFID’s focus regions, namely Africa, Asia and the Middle East.
MAVC is similarly well situated within the USAID policy context, as it links closely with the Promoting Transparency and Accountability policy. USAID’s objective in governance is to improve the relationship between civilians and state actors by directly linking those who are governed with those who are democratically elected to govern, and works to support the rule of law by promoting legal and regulatory frameworks that improve order and security, legitimacy, accountability, and equal application and enforcement of the law. MAVC tier one and two countries are well aligned with the USAID priority countries.
SIDA bases its governance policy and programming through a human rights perspective, and democracy, public administration and human rights including freedom of speech are areas where Sweden invests most of its development assistance budget (29% of SIDA’s total development cooperation). Since 2009, SIDA has a special grant for democracy and freedom of speech, targeting non-democratic countries, and with special focus on organisations and groups working for democracy and freedom of speech. The grant is governed by the Swedish Results Strategy for specific interventions on human rights and democratisation 2014-2017. MAVC tier one and two countries are well aligned with SIDA priority countries in Africa and Asia.
MAVC sits within two policy areas of Omidyar Network. As a donor, Omidyar Network invests in innovation and entrepreneurship towards open and stable societies and MAVC sits across two key funding focus areas: Emerging Tech, and Governance & Citizen Engagement.
In relation to the Sustainable Development Goals (SDGs), MAVC contributes to the SDG Goal 16: ‘Promote peaceful and inclusive societies for sustainable development, provide access to justice for all and build effective, accountable and inclusive institutions at all levels’, specifically:
- 16.3 Promote the rule of law at the national and international levels and ensure equal access to justice for all.
- 16.5 Substantially reduce corruption and bribery in all their forms.
- 16.6 Develop effective, accountable and transparent institutions at all levels.
- 16.7 Ensure responsive, inclusive, participatory and representative decision-making at all levels.
- 16.10 Ensure public access to information and protect fundamental freedoms, in accordance with national legislation and international agreements.
### Linkages with other programmes
The DFID MAVC Business Case[9] reviewed the literature in making the strategic case for DFID intervention. This framed the design of MAVC but in terms of operation, the primary linkage was with OGP (see Section 3.4.5, 5.1.2, 9.1.1, 9.1.5 and 9.2).
[9] See p.6 to 10 in DFID MAVC Business Case (2013).
## Background to the evaluation
DFID engaged an independent Evaluation Management Unit (EMU) managed by consultants IMC Worldwide and GY Associates, who contributed to the annual reviews and this evaluation. The original ToR (Annex 1 to this report) state that: ‘The main purpose of the evaluation is to learn more about innovative approaches to amplifying the voices of citizens and enabling governments to respond effectively to what citizens are saying. The evaluation will aim to answer evaluation questions around which approaches (or parts of approaches) may best support the MAVC objective of supporting innovation, scaling up effective initiatives and commissioning research into the use of technology and non-technology approaches to support open, responsive government and citizen engagement, as well as recording the impact of these approaches. A secondary purpose of the evaluation will be to assess mechanisms (e.g. whether bringing together four funders for a common purpose, improves or hinders the success of initiatives in this area).’ Reflecting these objectives, the primary purpose of this report is for learning.
Our evaluation approach is described in more detail in an externally reviewed Inception Report and a DFID-reviewed Approach Paper. Although there has been no departure from the scope of work in the original ToR, the evaluation questions which it sets out, have been slightly modified and rationalised in discussion with DFID. The aim has been to better reflect the programme Theory of Change. The Approach Paper (Annex 2) describes all the changes made (Approach Paper Table 1).
The original ToR placed the initial evaluation questions (EQs) against the OECD-DAC evaluation criteria and we have done the same for the revised EQs in Annex 3. However, we note that some evaluation questions address multiple OECD-DAC evaluation criteria. In this report, where it is practical, section headings have been chosen to cluster EQs around these evaluation criteria. Yet, process questions, in particular, address multiple OECD-DAC evaluation criteria and we have kept these together because, as our original ToR indicate, there is particular value in looking at process issues together. Different aspects of sustainability (one of the OECD-DAC criteria) are also reported under more than one EQ – with a particular focus on scaling and on MAVC’s approach to learning.
To answer the EQs we draw on:
- 11 representative grant case studies from the portfolio of innovation, scaling and Global Innovation Competition (GIC) grants in four tier 1 countries (Kenya, Ghana, South Africa and Indonesia). These have been undertaken over the life of MAVC, allowing us to look at changes between project baseline and endline, generally, with some post-project follow-up. Eight of these case studies follow quasi-experimental designs, with treatment and control groups.
- Country case studies, based on 11 ‘best-bet’ grants selected by the FMC in South Africa (5), Kenya (3) and Indonesia (3). Reviewing these grants provided an opportunity to assess the role of the country team, and the supporting MAVC ecosystem, in brokering and delivering against country strategies. This work was undertaken from September to November 2017[10].
  [10] Each country case study was written by an international and local researcher (identified in the relevant case study). All of the international researchers and one of the local researchers were closely involved with the grant case studies as well.
- A review of the global MAVC Research Evidence and Learning (REL) component and its contribution to the wider MAVC programme. This draws on 10 randomly selected representative REL grants, interviews with stakeholders involved in REL delivery and uptake, and a review of documents and REL communications (undertaken from September to December 2017).
- Other global perspectives - stakeholder interviews and document review to answer questions on process (undertaken from September to December 2017).
In addition to the grant case studies, the end of programme evaluation draws on more than 150 interviews and reviews of more than 300 documents. Summary details are given in section 10 of the report (which includes the bibliography). Details of the grant-funded projects mentioned in this evaluation can be found in the separate report Annexes (5 – 8) but we also provide a brief summary of each of them in the attached and hyperlinked Appendix 2.
## Independence of the evaluation
In order to promote learning within the programme, the EMU has attempted to be a ‘critical friend’ to grantees and the FMC more generally.  This has involved feeding back findings from the grant case studies to grantees, participating in MAVC learning events and working constructively with the FMC MEL team based at IDS.
In this context, our evaluation approach has helped to maintain independence. We have focused on outcome and impact levels of the logframe (whereas the large bulk of MEL data relates to logframe activities and outputs).  We have used some MEL data to assess progress against programme outcomes, with independent verification of major claims.  Likewise, claims made by grantees and FMC in the country case studies and the REL review have been verified by our independent researchers, who have been able to work freely.   The EMU grant case studies rely on independent evidence collected at baseline and endline by our researchers.  These case studies have required the cooperation of grantees but, in every instance, our researchers have been able to work freely and without interference.
## Purpose and structure of this report
We recognise that this evaluation will have a number of audiences, including MAVC donors, other donors, government policymakers and practitioners - and among these, grantees. While most recommendations are targeted to donors and policymakers, many of our findings will be of interest across these groups, with case study findings particularly relevant for practitioners. Discussion with users including DFID, suggested it would be more useful to present findings, lessons and recommendations in the relevant sections of the main report rather than as separate sections. However, these sections begin with findings, lessons are introduced with underlining, recommendations are introduced in bold and presented in italics. Recommendations are prioritised as first priority (the very highest priority) and second priority (high but not the very highest priority).
We have had the opportunity to present and discuss key findings and recommendations at the February 2018 Transparency and Accountability Initiative Learning event for donors held at the OECD and have contributed to the Hivos Global Learning Event in April 2018. A number of developing country government policymakers have expressed interest in reading the report and will receive copies. We also plan to present to a CAFOD-convened Community of Practice of NGOs working on governance and accountability.
The main body of this report covers our approach to, and results of, the evaluation, with signposting for readers to annexes for more information. This reflects DFID’s wishes and shortens the main body of the report. As MAVC is a complex and wide-ranging programme, many readers will find it useful to read these annexes, particularly the summary of EMU grant case studies in Annex 5 and country case studies in Annexes 6 - 8. The country case studies also provide a discussion of national and sub-national context that is specific to the selected projects but is important in understanding what has or hasn’t worked in these cases.
Section 2 of the report sets out the major elements of the methodology we have used[11]. In Section 3, we look at programme outcome and progress towards impact, both in terms of what has been achieved by this programme and also lessons for tech for transparency and accountability (Tech4TA) programmes more generally. Section 4 sets out findings on innovation and scaling, with issues of programme relevance and brokering covered in Section 5. Findings on cross-cutting issues of gender and poverty are summarised in Section 6. Value for Money (VfM) is addressed in Section 7, using data on programme cost-efficiency, an attempt at benchmarking, and the detailed cost and benefit evidence from two grants. The REL review can be found in Section 8, with findings against the relevant evaluation questions, and an appendix covering our review of MAVC communication products. Section 9 provides findings on process – on the multi-donor funding and management arrangements for MAVC. A summary of stakeholders interviewed, and a bibliography are given in Section 10.
[11] See also the Approach Paper in Annex 2.
## Note to the reader
This report is aimed at those interested in the use of technology and non-technology approaches to support open, responsive government and citizen engagement, as well as funders and commissioners of evaluations. We have attempted to explain technical concepts and results as clearly as possible but the inclusion of technical, statistical and evaluation terms is unavoidable. Therefore, the reader will find it helpful to have some familiarity with the field of governance transparency and accountability, and some understanding of research and evaluation methods.

# Methodology
## Evaluation Framework
### Overview
The approach and methodology we have used were specifically designed to account for biases through extensive triangulation using multiple data sources (see Section 2.3). This was carried out without interference, though there were clearly sensitivities dealing with government and accountability. No conflict of interests surfaced through the work, apart from the obvious dynamics experienced between citizens and service providers – the primary reason for the project. The core components of the impact evaluation design set out in the Inception Report continue to be relevant, providing both ‘country case’ and ‘global’ programme perspectives. These are:
Case evaluations (Kenya, South Africa and Indonesia)
Country level (‘top-down’)
- Assessment of progress against country plans, country learning and engagement plans (document review).
- Assessment of major country level results, based on the portfolio of grants and non-grant activities such as brokering[12], claimed by the programme. Contribution analysis with in-country stakeholder interviews, tests linkages to changes in practice and policy, and the role of MAVC brokering.
  [12] The aim is to consider clusters of activities around grants expected to have significant impact. Hence, a practitioner research grant, brokering or community of practice may be associated with a particular innovation, scaling or GIC grant.
Grant level (‘bottom-up’)
- Assessment of specific MAVC interventions to identify results, and exploring their contribution towards the programme’s overall objectives
- 11 grant case studies (drawn from innovation, scaling and global innovation competition components, in Kenya, Ghana, South Africa and Indonesia).
Global evaluation
- REL assessment based on a sample of REL grants and non-grant activities set out in the Research and Evidence Strategy[13]. The REL evaluation covers both the activities of REL component itself and its contribution to the wider MAVC programme. The review focused on strategy, results and outputs, uptake, outcomes and process.
  [13] http://www.makingallvoicescount.org/wp-content/uploads/2015/08/RE-strategy.pdf
- Document review and stakeholder interviews on Catalysing Action spend. Contribution analysis of claimed influence.
Synthesis and changes since our Inception Report
This draws together findings of an MAVC ‘family’ of interventions that are characterised by a common ToC, but are implemented across different domains - for example, case evaluations of countries. Our Inception Report states that we are influenced by a realist approach[14]: seeking to understand how and why MAVC interventions ‘work or do not work, for whom, to what extent, in what respects, in what circumstances and over what duration’. However, we decided against a fully-fledged realist synthesis, based on Context Mechanism Outcome (CMO)[15] combinations, as it would have required reallocating a significant proportion of researcher time from the field to the UK.
[14] Realist approaches to evaluation assume that nothing works everywhere or for everyone and that context makes a difference to programme outcomes. It uses the assumptions of realist philosophy. “A realist research question contains some or all of the elements of “how and why does this work and/ or not work, for whom, to what extent, in what respects, in what circumstances and over what duration?” Westhorpe, (2014). See the MAVC Evaluation Approach paper (p5-6) for detailed discussion of this approach.
[15] The “Context-mechanism-outcome” hypothesis is a type of programme theory within the Realist Evaluation approach. The analysis methodology involves generating a suite of hypotheses for patterns identified in a programme in which specific contexts, mechanisms and outcomes are linked. E.g. “In this context, that mechanism generates this outcome” - Westhorpe (2014).
## Evaluation Questions (EQs)
Feedback from DFID and FMC on our Approach Paper to this final evaluation, led to a reduction in the total number of EQs and some refinement to better reflect the ToC. The EQs we have used are set out in Table 1 below, together with evidence sources and methods of analysis. Despite revision, the EQs for the final evaluation are similar to those specified in the original ToR (see Annex 1). In Annex 3, we show which EQs relate to which principal OECD-DAC evaluation criteria, noting that some EQs contribute to multiple criteria.
## Value for Money (VfM)
DFID’s approach to VfM is set out in DFID (2011) and is summarised in Figure 44 below.
Figure 4: The DFID VfM Framework

Source: DFID (2011)
Many of the EQs that we address concern effectiveness, but the VfM analysis in Section 7 specifically focuses on 1) cost-effectiveness and 2) efficiency. This is because joint discussions with DFID and the FMC highlighted these two areas as particularly interesting.
The key cost-effectiveness question is whether intervention benefits justify the costs[16]. We use Cost-Effectiveness Analysis (CEA) and Cost Benefit analysis (CBA)[17] on a small sub-set of grants, to provide some evidence on this. On the question of efficiency, DFID was particularly interested in comparing MAVC with a programme undertaking similar interventions, and suggested we use the DFID SEATTI[18] programme managed by Hivos as a benchmark.
[16] HM Treasury Magenta Book (2011) Chapter 2.
[17] The Magenta Book (2011) Chapter 2 provides an overview of CEA and CBA. Technical discussion is provided in The Green Book (2018).
[18] Southeast Asia Technology and Transparency Initiative (SEATTI), https://hivos.org/news/hivos-and-omidyar-enhance-transparency-public-institutions-seatti
## Evidence Sources
### At the country level (‘top-down’)
We have selected three of the six tier 1 countries as country case studies: South Africa, Indonesia and Kenya. These provide a diversity of contexts for Tech4TA and country capacity, and allow us to draw on existing research networks developed for grant case studies.
Progress towards the programme outcome at the country level will inevitably rely on a sub-set of successful grants. The Approach Paper made the case to focus on a purposive sample, skewed towards these grants, and activities such as brokering and convening, to support them. Our resources allowed for a sample of between three and five innovation, scaling or GIC grants per country, together with the broader ecosystem of MAVC activities supporting grants that included brokering, research practitioner grants and Communities of Practice (CoP). The sample of 11 ultimately chosen[19], reflected grants the FMC thought most likely to produce impact (‘best-bet’ grants), drawing on Quarterly Assessment Scorecard (QAS) and evidence of Most Significant Change (MSC).
[19] For the countries concerned the sample of innovation, scaling and GIC grants was 22% in South Africa, 17% in Kenya and 21% in Indonesia.
Country level case assessments were undertaken by an international and locally based researcher, working together in the selected countries in September and October 2017. This draws on project reporting (secondary data) and stakeholder interviews (primary data).
### The REL review
Sampling for the REL review is complicated by the combination of REL grants and activities that are combined with innovation, scaling and GIC grants, in addition to research grants to research organisations. Our resources allowed a maximum of 10 REL grants and associated non-grant and capacity building activities, and our original aim was to provide some of this number from the country case studies. However, there was a risk that time-constrained country case researchers would not be able to undertake detailed research on PRLGs, and so we selected a separate, random sample of 10 REL grants from three categories (IDS Research, Third Party Research and PRLGs), proportionate to spend on each grant type. This represents a 14% sample of all REL grants.
The REL assessment was undertaken by an international researcher between September and November 2017. It drew on document review (secondary data) and stakeholder interviews (primary data).
### Grant case studies (‘bottom-up’)
The sampling of the 11 EMU grant case studies has been representative, covering innovation, scaling and GIC grants over the duration of the programme. This sample represents 10% of the grants of these types. The FMC did not permit innovation, scaling or GIC grant holders with practitioner research grants to be EMU case studies but this led to only two initial choices being substituted. Hence, the grant case studies give an indication of the distribution of successful projects as well as providing opportunities to learn from what went wrong as well as what went right. A summary of each case study and data sources is given in Annex 5.
Grant case studies involved primary data collection at baseline and endline of each selected grant, by a team of locally based researchers supported by an international researcher. Nine of the 11 case studies were also designed to include baseline and endline surveys, in addition to qualitative methods that included focus group discussions and stakeholder interviews[20]. Questionnaire design involved grantees and incorporated questions adapted for the project-specific context and a small module of programme-level questions. Survey sampling, enumerator training, piloting and data supervision was undertaken by qualified statisticians in all cases. We made a determined effort to form joint qualitative and quantitative research teams, with deliberate triangulation of findings but the one year or 18-month grant length made it largely impossible to sequence these components.
[20] One endline survey was cancelled due to evidently poor project performance that was picked up by endline qualitative work and in one case, the design suggested by the implementing grantee simply didn’t work for the nomadic pastoralist community.
All grant case study evaluations were designed with the implementing partners[21]. They involved qualitative researchers, with focus group and key informant interview guides structured around the programme ToC, but focused on issues derived from the grantee’s implicit project-level ToC[22]. Eight of the grant case studies had quasi-experimental designs and one had an experimental design. All these involved treatment and control groups (requiring some qualitative work in both control and treatment sites).
[21] They typically were under pressure to begin implementation very quickly, that also put pressure on the evaluation design.
[22] Understood from reading project documentation and discussion with grantees themselves.
### VfM data
We worked collaboratively with the FMC MEL team (at IDS) to identify grantees who had evidence of outcome-level results and had the types of evidence amenable to economic analysis. Starting with seven candidates, we were only able to undertake detailed CEA/CBA for two projects (MOPA in Mozambique and Black Sash in South Africa). For the comparison of MAVC and SEATTI costs, we were able to draw on published SEATTI accounts, but considerable work was needed to express MAVC costs in a comparable form to the SEATTI accounts. This work was commissioned from Cathy Shutt, an independent consultant, by the FMC MEL team. The VfM analysis was undertaken between September and November 2017.
## Additional evidence sources
### The FMC data inventory
The FMC MEL team provided a list of all MAVC-funded projects (scaling, innovation and research), with background data and some preliminary analysis of project activities, outputs and outcomes. The information in the data inventory relies on self-reporting by grantees. However, some of the performance measures received some peer review through the Qualitative Assessment Scorecard (QAS) process and from the FMC MEL team cross-checking against EMU case studies and CED reports. The data inventory has been used to support and cross-check against findings from country case evaluations.
Table 1: Summary of Evaluation Questions, Evidence Sources and Methods of Analysis
Evaluation Questions	Evidence Sources	Method of Analysis
What lessons on efficiency, effectiveness and co-ordination can be learned from the multi-donor funding and management arrangements for MAVC?	Steering committee discussions / Annual Review reports / FMC & MAVC donor interviews	Evaluator assessment based on document review (including the original DFID Business Case) and triangulation against stakeholder interviews.
How effective has the process for scaling been (involving innovation, scaling, GIC and Research grants, brokering, private sector finance and lessons from scaling up in this sector or country)? What lessons can be learned for other programmes?	MAVC data inventory (all innovation & scaling projects) / Country case studies (South Africa, Indonesia and Kenya – SA, I, Ke) / Grant case studies (11) / MAVC donor interviews	Analysis of any FMC data on the incidence and type of scaling and the value of external funding leveraged. / Assess against good practice for innovation programmes. / Identify mechanisms and contexts that have contributed to or constrained scaling. Review against Business Case and ToC. Evaluator synthesis based on Portfolio/REL, country case, grant case study reports and interview notes drawing on evidence tables.
How effective has the process for innovation been (involving innovation, scaling, GIC and Research grants, brokering, private sector finance and lessons from scaling up in this sector or country)? What lessons can be learned for other programmes?	MAVC data inventory (all innovation & scaling projects) / Country case studies (SA, I, Ke) / Grant case studies (11) / MAVC donor interviews	Assess against good practice for innovation programmes. / Identify mechanisms and contexts that have contributed to or constrained innovation. Review against Business Case and ToC. Evaluator synthesis based on Portfolio/REL, country case, grant case study reports and interview notes drawing on evidence tables.
How effective has the brokering approach been?	MAVC data inventory (all innovation & scaling projects) / Country case studies (SA, I, Ke) / Grant case studies (11) / MAVC donor interviews	Contribution analysis to assess changes claimed by brokering in country case studies. Review against ToC. Identify mechanisms and contexts that have contributed to or constrained brokering. Evaluator synthesis based on Portfolio/REL, country case, grant case study reports and interview notes drawing on evidence tables.
How effective were the management and governance arrangements for MAVC in supporting coherent and successful programme implementation?	Steering committee discussions / Annual Review reports / FMC & MAVC donor interviews	Evaluator assessment based on document review and triangulation against stakeholder interviews.
How effective was the REL strategy implementation process?	Steering committee discussions / Annual Review reports / FMC & MAVC donor interviews / Global learning event documentation / FMC Learning reviews, internal reviews	Evaluator assessment based on document review, surveys and triangulation against stakeholder interviews / Review against strategy and planning documents and ToC.
How effective has MAVC’s approach to learning been?	Lessons from the sample of REL grant/non-grant activities / Country case studies (SA, I, Ke) / MAVC data inventory (REL projects) / Logframe indicators	Evaluator assessment based on document review, surveys and triangulation against stakeholder interviews / Assessment against performance metrics derived from the data inventory.
Was there a bias in the types of intervention funded? Were any types of intervention excluded?	Review of investment committee criteria used / FMC & MAVC donor interviews	Evaluator assessment based on document review and triangulation against stakeholder interviews.
Were supported interventions coherent with MAVC country plans?	Country case studies (SA, I, Ke) / Grant case studies (11) / FMC & MAVC donor interviews	Review against MAVC Country Plans. / Review against MAVC Country Engagement and Learning Plans in South Africa and Indonesia. / Evaluator assessment based on document review and triangulation against stakeholder interviews.
To what extent has MAVC delivered improved relationships and increased opportunities for at least constructive dialogue and at best co-governance between citizens and governance in countries with an MAVC country plan?	Logframe indicators / MAVC data inventory / Country case studies (SA, I, Ke) / Grant case studies (11)	Performance metrics derived from the data inventory, cross-checked against grant case studies. / Difference-in-difference results from grant case study surveys checked against qualitative findings. / Contribution analysis to assess changes claimed in country case and grant case studies. / Identify mechanisms and contexts that have contributed to or constrained this outcome. Review against Business Case, logframe and ToC. Evaluator synthesis based on Portfolio/REL, country case, grant case study reports and interview notes drawing on evidence tables.
To what extent has MAVC improved citizen’s capabilities (individual and group incentives and opportunities) to express their feedback on government performance and engage with government? If so, how?	Logframe indicators / MAVC data inventory / Country case studies (SA, I, Ke) / Grant case studies (11)	Performance metrics derived from the data inventory, cross-checked against grant case studies. / Difference-in-difference results from grant case study surveys checked against qualitative findings. / Contribution analysis to assess changes claimed in country case and grant case studies. / Identify mechanisms and contexts that have contributed to or constrained this output. Review against Business Case, logframe and ToC. Evaluator synthesis based on Portfolio/REL, country case, grant case study reports and interview notes drawing on evidence tables.
To what extent has MAVC improved the quality and level of government responsiveness to citizen demands (at national and sub-national levels)? If so, given the capability of officials to respond reflects individual and institutional incentives and opportunities, how has MAVC improved these individual and institutional incentives and opportunities?	Logframe indicators / MAVC data inventory / Country case studies (SA, I, Ke) / Grant case studies (11)	Performance metrics derived from the data inventory, cross-checked against grant case studies. / Difference-in-difference results from grant case study surveys checked against qualitative findings. / Contribution analysis to assess changes claimed in country case and grant case studies. / Identify mechanisms and contexts that have contributed to or constrained this output. Review against Business Case, logframe and ToC. Evaluator synthesis based on Portfolio/REL, country case, grant case study reports and interview notes drawing on evidence tables.
To what extent can outcomes be attributed to the collective donor inputs?	From EQs 1, 2 and 10.	From EQs 1, 2 and 10.
What contribution to informing performance and practise (programme learning) in the field of voice, and accountability occurred?	Lessons from the sample of REL grant/non-grant activities / Country case studies (SA, I, Ke) / MAVC data inventory (REL projects)	Evaluator assessment based on document and survey review, review of output & uptake indicators and triangulation against stakeholder interviews, understanding of causal pathways. / Contribution analysis/process tracing and contextual analysis to assess changes claimed.
What evidence/theory-building and associated learning in the field of voice and accountability occurred?	Lessons from the sample of REL grant/non-grant activities / Country case studies (SA, I, Ke) / MAVC data inventory (REL projects)	Evaluator assessment based on document and survey review, review of output & uptake indicators and triangulation against stakeholder interviews, stories of change, understanding of causal pathways. / Contribution analysis/process tracing and contextual analysis to assess changes claimed.
What was the ‘added value’ of the REL component to the MAVC programme in contributing to reach, influence and catalysing action towards MAVC objectives?	Steering committee discussions / Annual Review reports / FMC & MAVC donor interviews	Evaluator assessment based on document review, triangulation against stakeholder interviews, contribution and contextual analysis.
Did the REL component deliver value for money?	Costs relative to similar programmes / Costs of achieving results of EQ 16	VfM metrics

### Stakeholder participation in the evaluation
The key stakeholders for the evaluation were the MAVC donors and their country offices, the MAVC FMC management and country teams, the REL and MEL teams, Usahidi, the Research Outreach Teams, Tech Hubs, project (grantee) staff, as well as government, civil society and private sector stakeholders directly involved with selected projects or involved in scaling, or as users of learning products at the global, national or subnational level.

There was a significant level of collaboration and participation by the stakeholders in the evaluation. The EMU played the role of ‘a critical friend’ to the FMC throughout the programme lifetime and there was frequent engagement. The final evaluation was designed in a participatory manner involving multiple meetings with the REL and MEL team. The EMU also held two structured meetings with DFID, to discuss VfM. Data collection involved a wider range of interviews with stakeholder at the international and national levels.

Although we have maintained a constructive relationship with the FMC, we recognise the FMC is made up of a diversity of institutions, and stakeholders within these institutions.  Not everyone will agree with all of our findings.  However, we have interviewed multiple stakeholders from each institution and given the FMC and DFID an opportunity to identify any factual inaccuracies in our findings.

A range of stakeholders have provided feedback on this evaluation.  Throughout the life of MAVC, projects evaluated by the EMU received early drafts of reports to comment on.  DFID and the FMC were given the chance to review the first draft of this report.  The FMC requested clarification on a number of points and we have taken more than 100 comments made by stakeholders on board.   Many stakeholders have requested (and will receive) copies of the evaluation report once DFID approves circulation.

Some challenges were faced in reviewing contributions as there were some timeline slippages in the production of written data. In the case of research results, this was predominantly the result of programme and funding delays. This slippage was particularly the case for the final research synthesis papers which were promised to us by the 7th December but were delivered on the 14th December (four working days before our final deadline).
### Data collection, taking into account cultural, ethical and security concerns
For the data collection, the evaluation team adopted a sound and rigorous ethical approach and established a set of ethical principles. We regarded those ethical principles as universal principles that informed the design and use of data collection tools. We followed the best practice for engagement and enquiry with all participants and took particular steps to ensure the confidentiality of sensitive information shared by and with vulnerable groups. We adopted the following fundamental ethical guidelines for data collection procedures: DFID’s (2011) ‘Ethics Principles for Research and Evaluation’[23], European Society for Opinion and Market Research (ESOMAR) code of ethical practice and ethical standards on research (2016)[24], and UN Evaluation Group’s (2008) ‘Ethical Guidelines for Evaluation’[25]. We also followed guidelines of national ethical bodies, when deemed appropriate.
[23] DFID (2011) Ethics Principles for Research and Evaluation.
[24] ICC/ESOMAR (2016) International Code on Market, Opinion and Social Research and Data Analytics.
[25] UNEG (2008) Ethical Guidelines for Evaluation.

All team members attended briefings on codes of conduct and ethics, and were required to demonstrate commitment to ethical procedures; all tools such as questionnaires, surveys, interviews, sample tools and processes, were developed in line with ethical research principles.
Standard principles that we followed included:
- Respect of rights – We respected the rights of those involved in any data collection process or activity. Participants were duly informed of the purpose and we monitored that they participated freely and equitably. This entailed respect of values (some of which were culturally specific), preservation of dignity and a commitment to respect autonomy.
- Mitigating security concerns – As successfully managing security and logistics was undoubtedly a concern, we built the requisite protocols and procedures to identify, manage, and adjust as needed, to effectively collect data. All logistical arrangements (accommodation and local transport) were carefully planned in close cooperation with our local consultants to ensure researchers’ safety.
- Conflict of interest – Exercising the commitment to avoid conflicts of interest in all aspects of our work, thereby upholding the principles of independence, impartiality, credibility, honesty, integrity and accountability.
- High reporting standards – Ensuring accuracy, completeness and reliability; inclusion and non-discrimination; transparency; and fair and balanced reporting, to acknowledge different perspectives.
- Inclusivity – We ensured that all voices were heard and ensured respect to privacy, confidentiality and dignity.
- Informed consent – Survey and focus group participants gave their consent to participate.
- Integrity – We undertook evaluations with integrity, ensuring that the most appropriate methods were adopted and data was honestly reported and used to the maximum benefit of the individuals and communities from which they were collected.
- Discovery of wrongdoing – Discreetly reporting the discovery of any apparent misconduct to a competent body when deemed appropriate.
- Interactions with participants – Engaging appropriately and respectfully with participants in evaluation processes, upholding the principles of confidentiality and anonymity and their limitations; dignity and diversity; human rights; gender equality; and the avoidance of harm.
Our standard practice required that:
- All members of the team underwent a screening process, which included a background check, as far as possible within the context of the work that they did and their level, type and scope of participation.
- The research preamble was clear and transparent.
- We set up reporting mechanisms and a process for dealing with the following situations:
a) If participants described/were suspected to be at risk of harm, we had the responsibility to ensure appropriate support and care could be given through reporting to a local social welfare officer or other equivalent officer.
b) Consultants/staff that were suspected of violating ethics/protection principles.
- All our staff and consultant contracts included a statement about working with vulnerable groups. We ensured that all team members were briefed on protocols when working with minors and vulnerable groups.
- For data collection activities that were likely to involve engagement with legal minors, researchers were working in accordance with guidelines set out by the Ethical Research Involving Children (ERIC) initiative[26].
  [26] Graham, A., Powell, M., Taylor, N., Anderson, D. & Fitzgerald, R. (2013). Ethical Research Involving Children. Florence: UNICEF Office of Research – Innocenti.
- We sought to maximise benefit and minimise harm to those directly or indirectly affected by the data collection activities.
- We worked with a professional approach, competence, integrity and accountability at all times.
- Consideration was given to whether the data collection team had suitable capacity, or whether access to further support may have been appropriate.
- All interactions were conducted in a sensitive manner. For instance, interviewers were trained to be aware of effects that their questions may have had on participants and how best to respond depending on distress level. All questionnaires were written in language that could not be considered judgmental/stigmatising.
- The safety of respondents and the research team was paramount and guided all project decisions.
In practice, the major challenge for ethical data collection has been for the in-depth primary evidence collection undertaken by the EMU case studies.  Experienced local researchers undertaking these studies secured participant permission to interview at both baseline and endline.  While we hope that DFID will make survey data sets available to external researchers, these will be fully anonymised.  Survey participants were typically not paid although if respondents were asked to be part of a panel (for baseline and endline) they received a small gift (such as a toothbrush and toothpaste).   Refreshments were typically provided for participants in focus group discussions.
### Programme documents and stakeholder interviews
Documents reviewed include the second round of Qualitative Assessment Scorecard (QAS) findings, Most Significant Change (MSC) case studies, Country Learning and Evidence Plans (CLEPs) and associated Research Outreach Team reports.
Stakeholder interviews played an important role in the final evaluation. They generated primary evidence and identified sources of secondary evidence that are not in the data inventory - for non-grant activities such as brokering and convening. The following types of stakeholder interviews were undertaken, and details of stakeholders consulted are given in Section 10:
- Government and private sector stakeholders directly involved with selected projects or involved in scaling.
- FMC management team.
- FMC country teams (CEDs in South Africa and Indonesia and Research Outreach Teams).
- Tech Hubs (Indonesia and South Africa).
- Project (grantee) staff.
- MAVC donors with country offices.
- Sector specialists/expected users of MAVC research[27].
  [27] We were able to establish some linkages with relevant programmes and donors during our Inception Phase (e.g. World Bank) and subsequently benefited from strong sector representation at the MAVC Learning Events. We have agreed to present evaluation findings to a network of NGO implementors as well as donors in this sector (through the Transparency and Accountability Initiative).
## Methods of Analysis
### Assessment against good practice for innovation programmes
No simple template can be used to assess innovation for development programmes, but there is considerable evidence on supporting innovation in general, for example by Nesta[28]. The 2017 DFID Innovating in Development workshop provided relevant background papers and discussion. We have also drawn evidence from venture capital funding of early stage tech projects. These evidence sources can be found in Annex 9.
[28] See www.Nesta.org.uk
### Contribution Analysis and Process Tracing
Contribution analysis[29] is an approach in which the steps from programme inputs to outcomes in the ToC are examined for a plausible association. As articulated by White and Phillips (2012: 42), ‘a plausible association can be said to have been made if the following criteria are met: (1) a reasoned theory of change is set out; (2) the activities of an intervention are shown to have been implemented as set out in the theory of change; (3) the chain of expected results can be shown to have occurred; and (4) other influencing factors have either been shown not to have made a difference, or their relative contribution has been recognised’.
[29] Mayne, J. (2001). Addressing attribution through contribution analysis: using performance measures sensibly. Canadian Journal of Program Evaluation 16: 1-24. Available at: http://www.oagbvg.gc.ca/domino/other.nsf/html/99dp1_e.html/$file/99dp1_e.pdf Mayne, J. (2008). Contribution analysis: An approach to exploring cause and effect. ILAC Brief 16. Available at: http://www.cgiar-ilac.org/files/ILAC_Brief16_Contribution_Analysis_0.pdf

Contribution analysis has been particularly important for the country case studies, as the FMC ‘best-bet’ projects are based on grantee self-reporting, albeit with some grantee and CED peer review. Hence, we have assessed claims using document reviews, interviews with stakeholders, and interviews with independent key informants.

To some extent, it has been possible to use process tracing in combination with contribution analysis (Befani and Mayne, 2014[30]) for case study work at the country level and around particular grants or activities under review. In cases where we have taken this approach, the absence of project-level ToCs has required our researchers to develop them based on discussion with grantees. It has been particularly useful in two cases where survey and qualitative results provided conflicting evidence on success that required further explanation.
[30] ] http://www.betterevaluation.org/sites/default/files/idsb12110.pdf [2] http://www.ids.ac.uk/publication/straws-in-the-wind-hoops-and-smoking-guns-what-can-process-tracing-offer-to-impact-evaluation
### Ensuring the quality of case study evidence collection and analysis
This evaluation relies extensively on case studies and we draw on the case study tactics proposed by Yin (2009)[31], below, to show how our research design addresses the four key tests commonly used to assess empirical social research.
[31] Yin, R.K. (2009), Case Study Research: Design and Methods, Volume 5 of Applied Social Research Methods.
### Case study approaches for quality assurance used in this evaluation
Tests of research quality	Case study tactic (Yin, 2009)	Approach to be used in this evaluation
Construct validity	Use multiple sources of evidence / Establish chain of evidence / Have key informants review draft case study report	Data collection / Interviews with a range of stakeholders and key informants. Systematic process for identifying independent key informants. / Establish chain of evidence. / Key informants review interview summaries and relevant draft case study reports where possible.
Internal validity	Do pattern matching / Do explanation building / Address rival explanations / Use logic models	Data analysis / Testing against predictions of global ToC and impact pathways (logic models). / Testing rival explanations using contribution analysis.
External validity	Use theory in single-case studies / Use replication logic in multiple-case studies	Research design / Testing global ToC in representative case study countries. / Synthesis of country case studies against EQs. / Process for identifying representative case studies & consistent use of EQs.
Reliability	Use case study protocol / Develop case study database	Data collection / Develop case study protocol. / Case study database (consistent documentation of evidence that is shared across the team).

Source: Adapted from Yin (2009) Figure 2.3
### Evidence Tables
We have used evidence tables to consistently record evidence from multiple sources such as document reviews and stakeholder interviews, against the evaluation questions.
### Synthesis
Two types of synthesis have been undertaken. The first involves bringing together different evidence sources within a case study. For example, evidence on a specific country case scaling grant would come from a variety of sources such as project documents, interviews, FMC MEL reporting, the REL review and potentially the QAS. This is uncontroversial but does require evidence to be consistently organised around EQs, likely threats to the reliability of sources to be made explicit and reasons for prioritising evidence sources to be made transparent.
The second type of synthesis involves bringing together evidence from different contexts, different country cases, for example. This presents a challenge from a realist evaluation perspective. Although it is not feasible for us to undertake a realist synthesis for this diverse and complex programme using ‘context, mechanism and outcome’ combinations, we are committed to the principle of identifying what works, for whom and in what context. To allow this to occur, the way in which we approach assembling evidence across cases is important. EQ sub-questions reflect local context and explicitly document the role it has played. As such, when we discuss the role of technology in enabling collective civic action, for example, we explicitly consider the role of the specific South African and Indonesian contexts. We do bring findings together at the EQ level, drawing lessons from across the programme, but highlight the role that context plays.

### Justification of methods and evidence sources chosen
The evaluation was designed to combine representative grant (‘bottom-up’) case studies, country (‘top-down’) cases and MAVC global evidence in response to the requirement of the ToR (Annex 1) to look at process, portfolio and intervention levels. This approach also provides a means of cross-checking (triangulating) findings from multiple sources. A combination of quantitative and qualitative methods has been used, particularly in grant case studies to strengthen reliability. Contribution analysis has been used to test claims in country cases and at the portfolio level. According to Stern et al. (2012), this approach is appropriate for evaluating a complex development programme (which MAVC is). Our evaluation methods were set out in our Inception Report that was externally reviewed and approved.
## Cross-cutting issues
The evaluation questions generated a breadth of evidence on cross cutting issues of poverty, marginalisation and socially differentiated outcomes. These include the evidence provided under Evaluation Question (EQ) 7 (who is excluded from or included in different types of interventions) EQs 9 to 12 (outcome and impact: differentiated impacts of the optimism around technology; assumptions made about access to technology); EQ3 (the effectiveness of interventions and the marginalising outcomes of the heavy focus on technology). EQs 9 to 12 deal specifically with gender. These include that data which looking at the impact and outcome, and the consideration of power dynamics within these differentiated outcomes. Issues of power, anti-corruption and capacity building run throughout the report and underlie much of the evidence.
The approach used to look at cross-cutting issues was to present evidence consistently for each case study around each evaluation question. Comparative methods were then used for analysis around cross cutting themes such as how wellbeing was distributed across different wealth, gender and age groups. Most of the results involved qualitative comparisons but a small selection of the case studies had more statistically robust quantitative data which allowed us to statistically analyse differentiated outcomes such as between genders.
## Limitations
We have faced some limitations implementing the methods above. The major ones are[32]:
[32] Less significant country case-specific limitations are noted within each country case study.

- Insufficient resources to undertake in-depth contribution analysis for all claims made in country case studies. For example, where grantee claims are based on a range of activities, we have only been able to look in depth at a few of these, as each will typically require locating multiple stakeholders that may have since moved jobs[33]. In some cases, grantees worked in diverse geographic locations and we had to focus our attention on only one region to interview sufficient independent stakeholders.
  [33] The earlier the grant in the MAVC lifetime, the more likely is it that government or NGO staff had moved on. In some cases, it was possible to locate and contact staff in new jobs and in others we had to identify alternative stakeholders with relevant experience from government or the NGO in question.
- The conflict around elections in Kenya meant that one of the proposed ‘best-bet’ case studies (ICJ) was unable to participate in the evaluation at the last minute, and a replacement (IBP) had to be found. More generally, there were some security constraints on travelling and interviewing at this time.
- Country case grantees gathered very little qualitative or quantitative evidence on project outcomes. Hence, it was much more difficult to investigate the claims made without undertaking primary data collection, which was not possible given the time and resources available for country case studies.
# Findings: Outcome and Impact
## Overview
The discussion below draws on both the 11 EMU case studies and the Kenya, South Africa and Indonesia country case studies and, to a lesser extent, the REL review. It begins by looking at progress made and then considers lessons to be learned, drawing together findings[34] on the following four evaluation questions:
[34] Our analysis considers ‘unexpected and unintended’ findings where results fall short of expected outcomes. Reasons for this are explored but we do not specifically use the terms ‘unexpected and unintended’.
- To what extent has MAVC improved citizens’ capabilities (individual and group incentives and opportunities) to express their feedback on government performance and engage with government? If so, how? (EQ 9)
- To what extent has MAVC delivered improved relationships and increased opportunities for, at least, constructive dialogue and, at best, co-governance between citizens, and governance in countries with an MAVC country plan? (EQ 10)
- To what extent has MAVC improved the quality and level of government responsiveness to citizen demands (at national and sub-national levels)? If so, given that the capability of officials to respond, reflects individual and institutional incentives and opportunities, how has MAVC improved these incentives and opportunities? (EQ 11)
- To what extent can outcomes be attributed to the collective donor inputs? (EQ 12)
The 11 independently (EMU) selected case studies are broadly representative of the MAVC innovation, scaling and GIC grant portfolio in four of the six tier 1 countries[35]. A summary of each case study is given in Annex 5. Each case study has been subject to independent review at baseline and endline, drawing on evidence from citizens and government. Our evidence suggests that just one of these (Caritas Kitui) has delivered at the MAVC outcome level and has strong potential for scaling up, although it has not taken place. Two grants (ICW and WYDII) have demonstrated some contribution at the MAVC outcome level, but limited CSO capacity for essential offline work (ICW) or the specific project context (WYDII), makes it unlikely that scaling would lead to broader impact. Three grants (OCOS, SEND and SSP) have made very limited outcome level contributions but grantees are likely to take some lessons forward. The IRC Etoil Daang grant has generated extremely limited, localised gains. To date, Yowzit has not enabled citizens to gain effective responses from municipal government, although uptake by additional municipalities seems possible. Three grants (MDTS, DPI, BSID) have clearly failed to deliver.
[35] These were randomly chosen from the target country portfolio in each year. One of the selections originally made was vetoed by IDS as they feared that the grantee would not have the capacity to participate as a case study and implement a practitioner research grant at the same time. This grantee was replaced by another in the same country with the same type of grant.
The above distribution is consistent with expected returns for early stage innovation. Kasper and Marcoux (2014) report 51/850 (6%) of projects across Grand Challenges, prior to MAVC, went on to receive follow-on support. De Ferranti and Skeels (2017)[36] argue that the venture capital ‘1 in 5 or less’ success rate applies to innovation in development. Nonetheless, as explained in the following sub-sections, this evaluation finds considerable evidence that problems in programme design and implementation, have reduced success rates below those that could have been achieved and prevented the programme potential from being realised.
[36] See - Vogel, I., Minkley, G., and Chowdhury, S. (2017) Innovating in development: Sharing learning, improving impact. Workshop report. Ideas to Impact. Available at: https://www.theengineroom.org/alidade-interactive-guide-for-finding-technology-tools/
The IDS response to the draft of this evaluation claimed that the 11 EMU case studies were ‘in effect, a biased sample in the light of the ruptures and drastic redesign of the programme in 2015’. This is an interesting conjecture but is totally rejected by the evidence. Just by observation, we know that the most successful case study (Caritas Kitui) dates from 2014, the least successful (BSID) from 2016 and four of the case studies date from late 2015 or 2016. We also test this statistically and there is no significant variation in grant success over the time covered by the 11 case studies - either measured pre/post management review, or as months from the start of the first grant[37].
[37] ANOVA and regression results based on the categorization in Figure 5 with highly successful scoring 4, upper intermediate 3, lower intermediate 2 and did not work 1.
The country case study grants, as summarised in Annexes 6 - 8, have been selected by FMC as the ‘best-bets’ to illustrate progress at the MAVC outcome level. We have used contribution analysis to assess major claims made, using key informant interviews at the end of the programme but have not been able to systematically obtain the views of citizens targeted by project interventions. As FMC has selected ‘best-bet’ grants, we would expect them to be much more successful than the MAVC portfolio as a whole. Two grants (Black Sash and KYGC) appear to have had very significant outcome-level results, the former after deliberate MAVC scaling. A number of other grants (LENGGO, IBP, Amandla.mobi, Corruption Watch, INFEST and CSK) have also contributed to citizen-government engagement for 100s of 1000s of people, but the external context, or relatively early stage of innovation, makes us less confident of the precise role of MAVC. It is too early to know whether some country case grants will deliver outcome-level change (Grassroot and FSHC) but the former has potential to do this without significant external funding while the latter does not. We were only able to evaluate one of the three Open Data Lab Jakarta initiatives (Project DARU) but we could not find evidence that this had led to improved citizen-government engagement, despite claims to the contrary.

Figure 5: Grants reviewed at outcome level

Extent of citizen-gov’t engagement resulting from grant
KYGC
BS

CK

AM, CW, INFEST

CSK, IBP, LENGGO, ICW
WYDII

GR

SEND, SSP, YOWZIT
OCOS

FSHC

ED

OD, MDTS, DPI, BSID

Evidence of MAVC contribution

Key:	A basic description of each project can be found in Appendix 2
BS	Black Sash, national level, country case study – see Annex 6 for more detail
KYGC	Kwale Youth & Governance Consortium, county level+, country case study (CS) – see Annex 7
CK	Caritas Kitui, county level, EMU CS – see Annex 5
WYDII	Women and Youth Development Institute of Indonesia, village level, EMU CS – see Annex 5
AM	Amandla.mobi, national level, country CS – see Annex 6
CW	Corruption Watch, national level, country CS – see Annex 8
INFEST	INFEST, district level x 3, country CS – see Annex 8
CSK	TI Indonesia, provincial level, country CS – see Annex 8
IBP	International Budget Partnership, county level+, country CS – see Annex 7
LENGGO	Local Empowerment for Good Governance, county level, country CS – see Annex 7
ICW	Indonesia Corruption Watch, city level x 3, EMU CS – see Annex 5
YOWZIT	Yowzit, city level (metropolitan municipality), EMU CS – see Annex 5
OCOS	Global Communities, city level (metropolitan authority), EMU CS – see Annex 5
SEND	SEND Ghana, provincial (4 administrative regions), EMU CS – see Annex 5
ED	IRC (Etoil Daang), Kenya, county, EMU CS – see Annex 5
SSP	Southern African HIV Clinician's Society, provincial level x 2, EMU CS – see Annex 5
GR	Grassroot, national level, country CS – see Annex 6
FSHC	Free State Housing Campaign, provincial level, country CS – see Annex 6
OD	OD Labs (project Daru only), city level, country CS – see Annex 8
MDTS	TI Kenya, county level x 2, EMU CS – see Annex 5
DPI	TI Kenya, county level, EMU CS – see Annex 5
BSID	Perkumpulan YPBB, city level, EMU CS – see Annex 5

There are many ways to cluster the case studies in the Figure 5 above but, in terms of learning, there is value in considering the five approximate groupings above:
1.	The high achievers – Only one of these has received support to move from early innovation towards scaling.
2.	The upper intermediates – The organisations that received MAVC grant funding will continue post-project and the challenge will be to take on board lessons from MAVC. A number will take forward projects or elements of MAVC-funded projects.
3.	Lower intermediates – Again, the organisations that received MAVC grant funding will continue post-project but there is less chance of donors picking up these projects. There is still value in taking on board lessons from MAVC.
4.	Projects that clearly did not work.
5.	Too early to talk about outcome – However, there is an opportunity to contribute to and draw on programme learning.
Another way to cluster these case study projects is to use the categories of Peixoto and Fox (2016). Specifically, whether projects rely on ‘collective civic action’[38], with groups of citizens applying pressure on service providers – so called ‘downwards accountability’, in contrast to individual user feedback to service providers, who are motivated to respond (‘upwards accountability’)[39]. An overlapping area is defined where individual feedback to service providers gives rise to personalised responses.
[38] The Grassroot (GR) app that makes it much easier for citizens in South African townships to organise group action on local public services illustrates this kind of project.
[39] Illustrated by the Cek Sekolah Ku (CSK) project in Indonesia providing an on-line platform for schools or the local education department to respond to complaints sent in by parents.

Figure 6: Routes to Government Feedback

WYDII
CK
BS

KYGC

YOWZIT
INFEST
SEND

OCOS
DPI
CSK
ED

CW

GR
MDTS
IBP
AM
SSP

FSHC
BSID
LENGGO

OD
ICW

Primarily collective
Source: adapted from Peixoto and Fox (2016)

Primarily individual
The underlying assumption in the MAVC Business Case, and original ToC, was that closing the feedback loop would involve ICT enabling individuals to report more effectively, and service providers to respond more effectively in return. As the programme evolved, there was a growing realisation that the reality was more complex, and IDS pushed for a revision of the ToC (see REL review)[40].
[40] The FMC inception report raised concerns with the initial ToC inherited from the DFID Business Case. As part of the subsequent EMU Inception Report preparation, we ran sessions on developing the ToC at our October 2013 learning workshop (attended by FMC members); and produced suggested revisions to the ToC.
The large proportion of case studies that are collective civic action projects reflects this change. However, we recognise that this representation is an oversimplification, as grants often had offline and online components, and sometimes supported both civic action and individual feedback[41]— hence, it is more accurate to say ‘primarily collective’ or ‘primarily individual’. We also argue, in the following Section, that the Peixoto and Fox (2016) categorisation, while useful, runs the risk of underplaying the critical role of country context and the dynamic nature of bargaining between civil society and competing interests within service providers. For example, it is true that the most successful interventions relied primarily on collective action, but it was the combination of country context and the intervention that was critical: devolution in Kenya (CK and KYGC), and the culture of collective action and a powerful independent judiciary in South Africa (BS).
[41] Black Sash’s community based monitoring at local social security offices supported by local and national advocacy, would seem to fall into an intermediate category that Peixoto and Fox describe as ‘citizen engagement’. However, what drives responsiveness is clearly national advocacy, media and judicial engagement – downwards accountability – that draws on case studies of individuals for evidence.
## Progress against logframe impact indicators

The choice of impact indicator 1 reflects the extremely high level of ambition for MAVC at the outset. Some key informants involved at the time, thought this reflected the aftermath of the Arab Spring uprisings in which social media had played an important role. In practice, we do not believe it is possible to claim a plausible contribution between modest outcomes from the largely sub-national MAVC focus and very limited scaling over the programme life, and changes in impact indicator 1 – even for MAVC tier 1 countries. However, for completeness, we report that at the end of 2017 the target (a 0.2 increase) has been achieved as shown below. Note that in December 2017, the latest EIU (Economist Intelligence Unit) democracy index was for 2016.
Table 2: EIU Democracy Index value for tier 1 countries
Country	2012 (reported 2013)	2016 (reported 2017)	Difference
Ghana	6.02	6.75	0.73
Kenya	4.71	5.33	0.62
Tanzania	5.88	5.76	-0.12
South Africa	7.79	7.41	-0.38
Philippines	6.30	6.94	0.64
Indonesia	6.76	6.97	0.21
Average	6.24	6.53	0.28

Source: Derived from https://www.eiu.com/topic/democracy-index
Impact indicator 2 can be calculated from EMU case studies where we have survey data[42]. The surveys include a question that relates to whether individuals ‘believe they are able to engage and call to account public and private institutions on policy issues that matter to them’. Details are given in Annex 4. The target is for a 10% increase over the baseline for both women and men.
[42] For the MDTS and DPI case studies, extensive qualitative evidence and project reporting strongly suggests there has been no project impact and hence we do not use this survey data for impact or outcome indicators. In the case of IRC, pastoralist groups in treatment areas migrated to control sites hundreds of kilometres away, invalidating the survey design. The quantitative BSID endline survey was cancelled as the qualitative component indicated that delayed project implementation meant there was no possibility of impact.
At the impact level, the indicator would seem to apply to all citizens in the surveys – whether or not they were MAVC beneficiaries. However, in Table 3 below, we also note any evidence of significant differences between citizens targeted by project interventions (treatment groups) and control groups, in the same part of the country.
Table 3: Estimating progress against impact indicator 2
Source of evidence	% change in impact indicator (baseline to endline)	Treatment vs control evidence
Caritas Kitui, Kenya	+ 21% (female only sample)	Increase in impact indicator 10.3% for treatment group.
OCOS, Ghana	Female: -1%, Male: +3%	Suggests a decline for both women and men.
SEND, Ghana	Female: -3%, Male: – 5%	Impact indicator has increased significantly for women and men in the treatment group.
Yowzit, South Africa	Female: -12%, Male: -9%	Decrease (but not statistically significant) for the treatment group.
SSP, South Africa	Female: -3%, Male: +8%	Not estimated
Average	Female: 0.4%, Male: -0.8%	More positive for the treatment group than citizens as a whole but < 10% increase on average.

This impact indicator target has not been achieved. If we look more narrowly at programme beneficiaries, there have been gains on average, but these are less than the 10% increase set by the indicator target.
## Logframe outcome indicators
Evaluation question (EQ) 10 is very similar to the MAVC outcome statement: improved relationships and increased opportunities for constructive dialogue between citizens and governments (in MAVC countries). This also includes elites who retain power within the private sector. In terms of outcome indicator 1 below, there is convincing evidence from a combination of EMU and country case studies, as well as the MOPA cost-benefit case study, that the 2017 target has been comfortably exceeded.

We have seen that the South Africa Social Security Agency (SASSA) estimated 1 million ‘first-wave’ claimants will be able to address unauthorised deductions, following the MAVC-funded work of Black Sash. Black Sash survey data from a sample of sites suggests it may be 2.5m. In either case, MAVC funding has enabled this to happen a year or two faster than it would have otherwise (South Africa country case study).
The KYGC, Caritas Kitui, Amandla.mobi, INFEST, CSK, IBP, LENGGO and ICW grants have all contributed to sub-national government responses that cumulatively have affected millions of people. For example, KYGC has led to a new coalition of mining companies and citizens, demanding implementation of the 2016 Mining Act, undercutting national and some county government officials and politicians, who had been extorting money from them for ‘protection’ (Kenya country case study). The reallocation of funds to county spending with increased civil society oversight, would seem to qualify as a contribution to programme outcome and Kwale has a population of approximately 650,000. The Caritas Kitui grant has helped women in Kitui influence the county integrated development plan affecting approximately 1 million people. At a more modest level, WYDII grant funding has led to village-level plans taking on board some proposals put forward by women, who had previously been excluded (EMU case study). The population of Tunjungtirto covered by the WYDII project is approximately 65,000.

Outcome indicator 2 (above) can be interpreted in various ways. Starting with the narrowest definition, evidence from the FMC MEL team indicates that five projects directly contributed to policy change. Our case study work allowed us to verify this for three projects. This definition is too narrow, as one project can influence more than one policy – particularly if it is working at different levels of government or with separate sub-national governments. On this basis, these five projects contributed to 32 policy changes, with the INFEST support for appreciative village-level planning and open data use in different districts in Indonesia, accounting for 27 of them[43].
[43] Appreciative village planning led to 18 new village regulations and Open Data for village development led to 9 new village regulations.
Both FMC MEL reporting and our case studies suggest that there are more examples of MAVC contributing to changes in government practice than changes in policy[44]. Hence, if practice is taken as the measure of improved policy, the logframe target for outcome indicator 2 is easily exceeded (as there are more than 30 examples). However, ’change in government practice’ covers a huge range: from an improvement in just one area of municipal service delivery (e.g. OCOS) to the way national social assistance is delivered to the poor (e.g. Black Sash).
[44] In part because the legislative process takes much longer than the typical one year MAVC grant life.

Survey evidence from the Caritas Kitui and OCOS EMU case studies can be used to estimate progress against outcome indicator 3 (above), in the same way it was used for impact indicator 1. However, in this case, the change in the outcome variable we consider is the response to the survey question “Do you believe that reporting deficiencies in local/national public services is likely to lead to some improvement?”. The results show that Table 4 (below), the second column reports the change in the outcome indicator from the survey, measured across both treatment and control groups, while the third column looks at the programme effect on those targeted by the project (treatment group) – explained in more detail in Annex 4, Box 1.
Table 4: Estimating progress against outcome indicator 3
Source of evidence	% change in outcome indicator (baseline to endline)	Mean difference in the indicator variable between the treatment and control groups after the intervention
Caritas Kitui, Kenya	+ 21% (female only sample)	+10% for the all-female sample
OCOS, Ghana	Female +22%, Male +22%	Female 0%, Male +26%
SEND, Ghana	Female -1%, Male -2%	Female +14%, Male +10%
Yowzit, South Africa	Female -11%, Male -10%	Female 0%, Male +4%
SSP, South Africa	Female -3%, Male +8%	Female +5%, Male +15%
Average	Female +6%, Male +5%	Female +6%, Male +14%

### A lesson from reporting on logframe outcome indicators
A lesson for those designing logical frameworks is that the numerical logframe indicator for outcome 2 (number of policy changes), is not able to capture the qualitative dimensions of policy change that determine what difference these policy changes make to people’s lives. The grant and country case studies (see annexes to this report) are more effective ways of identifying outcome level change but this approach is only feasible for a sample of grants. If funders want to judge programme success on the basis of policy change, this should be designed into the MEL system at the outset, for example by prioritising and resourcing independent verification of grantee claims. This approach was used by DFID in the periodic verification of implementing partner reporting in the End Child Marriage Programme[45].
[45] https://devtracker.dfid.gov.uk/projects/GB-1-202347
## Key findings and lessons from evaluation questions on outcome and impact (EQs 9 – 12)
### Grants would have been more effective if based on project-level ToCs
Context has proven critical to grant success, but opportunities were not captured in country strategies (e.g. devolution in Kenya or E-government in Indonesia). A lesson for those designing and implementing programmes is that country and project-level ToCs would have helped adapt interventions to local contexts. This would have required more in-country capacity, longer project lifetimes and fewer projects.
### MAVC has highlighted two critical policy gaps for ICT use in developing countries
Firstly, there can be a strong efficiency case to contract out e-services to private providers, particularly if the private banking sector already has the demonstrated capacity to manage payments. However, effective regulation is essential. The problem of weakly regulated private companies selling personal data that is used to target vulnerable households is well known in highly industrialised countries but is even more of a problem where a larger proportion of households are poorly educated. The experience of Black Sash (South Africa) provides a lesson to developing country governments on the danger of contracting out both social assistance and banking in a poorly regulated environment, as unauthorised deductions can easily be made from individuals misled into accepting ‘free gifts or services’. This is very likely to be replicated in other developing countries.
We recommend (first priority): Donors build on the experience of Black Sash to help governments, with CSO support, to strengthen protection of personal data in developing countries, and to effectively scrutinise and regulate the contracting out of e-services.
Secondly, MAVC’s experience of funding poorly researched and designed NGO health sector interventions in Kenya (MDTS and DPI), has illustrated the lack of any regulation in this area. The lesson for developing country governments and donor partners is that the current unregulated system needs to change. The challenge is to encourage innovation while avoiding costly and damaging duplication of existing systems. It might be possible to address this issue by following better project design protocols.
However, we recommend (second priority):
The Government of Kenya and possibly others consider developing a registry for health sector, drug-related tracking innovations. It should be a requirement for any NGO or private business proposing a drug tracking or pricing innovation, to show they have consulted this registry.
### There is a need to expand MAVC guidance on tech tools when government are the users to work with
Our findings are consistent with the findings of De Lanerolle, Walker and Kinney (2016), based on MAVC-funded research[46] in Kenya and South Africa, on developing tech tools for transparency and accountability. Only two of the 22 case studies in Figure 5 actively developed tools with users, for example. We would also strongly support the six recommendations they provide for organisations choosing such tools. The checklist process for tool selection should, perhaps, be mandatory given the demonstrated tendency for grantees to skip these steps. However, in addition, the Indonesia country case also provides a lesson for all those developing tech tools for transparency and accountability. It highlights the importance of engaging with government users of tech tools that are likely to draw on or compete with a grantee’s. For example, MAVC-funded CSK inspired the national Corruption Eradication Commission’s public service monitoring platform (JAGA) but this did not take on board the need to provide feedback to people making a complaint. Working with government needs to incorporate more than what De Lanerolle et al. (2016) recommend, i.e. trialling with individuals who will use the tool, and could require a significant investment of time to build the necessary relationships. As Yowzit in South Africa found, this investment can be lost following a change in administration, making a one-year project time horizon highly unrealistic.
[46] A REL 3rd party research grant. See: http://www.makingallvoicescount.org/publication/six-rules-thumb-select-tools-transparency-accountability-projects/
We recommend (second priority):

Adding to the recommendations of De Lanerolle, Walker and Kinney (2016) for organisations choosing tech tools. Specifically, we recommend that non-government grantees developing tech tools should engage with government users of tech tools that aim to address similar issues.
### Effectiveness would be increased by considering grants as an investment portfolio
The MAVC Business Case envisaged testing innovative ideas and scaling successful ones. This is a venture capital model for early stage investment. We have already seen how some interventions require relationship building with government partners, and complex external environments also play a part when projects start producing returns. A lesson for funders is that fixing a one-year time horizon for tech4TA projects often leads to sub-optimal implementation (e.g. focusing only on supportive elected leaders rather than administrators) or exiting when potentially successful investments are too immature to demonstrate success. Across an entire portfolio, this reduces effectiveness and value for money.
To some extent, flexible grant management can deal with this, although it will make quarterly spend forecasts significantly less accurate. Investing in organisations rather than projects – as recommended by a number of speakers at the final MAVC learning event at the University of Sussex – is more likely to be a solution for later stage rather than early stage investments. For example, the innovation and venture capital literature makes it quite clear that early stage innovation is best funded through grants rather than equity[47].
[47] https://www.nesta.org.uk/sites/default/files/innovation_flow_chart.pdf , and 350IP (2016).
### Government is not as homogenous as it appears from the MAVC Business Case
Service delivery staff may not have the same incentives as performance monitoring or communications staff, who want to engage with grantees (Yowzit and OCOS case studies). There are three related issues associated with this:
1. A more sophisticated engagement strategy is needed to create an enabling environment that improves incentives for service delivery staff to respond to user feedback. This may be the case even where the political leadership is committed to providing a response to users reporting problems, but it takes time to build trust with administrative staff, who will stay in post after the elected political leadership has gone (Indonesia country case study). A lesson for funders is that projects that need to do this cannot generally be completed in a year.
2. Attitudes to, and capability to use, tech are not uniform across local government. ICT can introduce new ways to highlight differences between government communications staff happy to receive feedback on social media and service delivery teams that say they cannot respond because social media is not an official communications channel (LENGGO in Kenya country case). A lesson for governments and donor partners is that a committed political leadership can change this (Eleyo Marakwet county, Kenya) which has also signed up to be an OGP sub-national pilot).
3. A lesson for funders is that, sometimes, the context means that a grant-funded intervention needs to support collective citizen action and user feedback to progressive allies in government – being in both sides of the Venn diagram (Figure 6). This can be sequential; LENGGO in Kenya had to take the Mombasa county government to court to make the government realise the danger of public anger if they didn’t start engaging on public participation, which they then did. At other times, a grantee may have responsive feedback at a local level, while needing collective citizen action to push for a response at the national level or in other locations (Black Sash work with social security offices in the Western Cape and nationally in South Africa).
### Unintended and unexpected findings related to institutions
The successful Caritas Kitui innovation grant led to many examples where women held county government to account but provoked a backlash with ’difficult’ women being prevented from asking questions at high-profile meetings. In this case tech (radio) combined with offline collective action, took local government actors by surprise and created new ways of holding them to account. However, a one-year project cannot be expected to change social norms or power relationships. Donors need to think both about scaling (which MAVC failed to do in this case[48]) and how to sustain gains in the face of active resistance by regressive factions within local government. The DFID Business Case did not differentiate government in this way and described apparently homogeneous ‘government’ as lacking the incentives or ability to close the feedback loop. The more complex, dynamic institutional context for project interventions was therefore unexpected.
[48] We specifically asked this question to FMC but have not had a response.
This complexity did not always mitigate against closing the feedback loop with citizens. The OCOS project in a large Ghanaian municipality increased citizen feedback on a large range of local public services via radio. While very few departments were willing to change their behaviour, there were isolated service providers who did make changes. However, it was unclear whether these voices would grow or subside over time.
A lesson for funders and implementers is that the presence of progressive and regressive factions within even sub-national government, make it even more difficult to work with one-year, one-off grants. This supports the recommendation elsewhere to have fewer projects but stick with them and work towards scaling over a number of years.
### MAVC has valuable evidence on how to determine when tech-enabled collective action is likely to work
Moving from the initial Business Case focus on ICT-enabled ’willing government feedback’ to supporting tech-enabled collective action, has generated evidence in less well-researched areas. The case studies in this evaluation, provide some useful perspectives.
Mobile phone technology (e.g. social media, digital mapping) lowers the cost to citizens of raising their voice (ED, GR, AM and KYGC examples) but the technology itself generally only has a modest impact on their cost of collective action. In the ED, GR and KYGC examples above, the big cost is in the time required for offline activism or even repercussions from service providers. The Amandla.mobi (AM) example may suggest a big reduction in cost – and joining online campaigns has sometimes been derided as online activism or ‘clicktivism’[49] - but the South African context is vital as AM often joins existing campaigns that involve offline activism as well. However, there is at least one example where an online campaign alone (with a credible threat of subsequent action) has had a rapid impact (see AM in the South Africa country case).
[49] Gladwell (2010), https://www.newyorker.com/magazine/2010/10/04/small-change-malcolm-gladwell
We have argued that the expected value of collective action is a function of what is at stake and the likely response from service providers. We have found that changes in the external context, such as devolution and the 2016 Mining Act in Kenya, can have a huge impact on the expected results of collective action. In this example, the context created a meaningful prize to engage youth in Kwale, one of Kenya’s poorest but mineral rich counties. This made it worthwhile for poor youth, who were the targeted users of the Kwale Youth & Governance Consortium (KYGC) project app, to club together to buy airtime for data access to try and influence planning.
In terms of likely response, much has been written on the importance of willingness of government to respond (Fox, 2014, Peixoto and Fox, 2016). However, the experience of Black Sash (first scaling grant) and IRC trying to support collective action on health facilities, provides a lesson for funders and implementers. Specifically, it suggests that highly localised problems and localised governance arrangements also affect the ability of government to respond. The transactions costs for sub-national governments getting involved at this level are high and have probably been underestimated. So, for example, CSK in Indonesia found that local government was happy to see problems resolved at school level rather than having to do it themselves. Black Sash also realised they would have a lot more impact trying to influence government on social security, which was managed locally within a common national regulatory structure, than working with district level health facilities that had multiple individual governance arrangements.
It is no great novelty to say that grant interventions need to consider both expected results and access to tech and to look for ’contextual levers’. We have noted the importance of involving users in design at the outset, to get the right tech and address constraints to access to technology, but a lesson for implementers is that it can also help to identify when issues are just not a priority for citizens. MAVC funded platforms specifically to enable communities to address waste management in Mozambique (MOPA) and Indonesia (BSID). In the former case, a scaling grant took forward a World Bank-funded pilot and our cost-benefit analysis (see Section 7) suggests it was successful. In the BSID case, the GIC grant has focused on building an app for an issue that people simply do not see as a priority. This should have been identified in advance.
### Unintended and unexpected findings related to technology
Uptake of ICT4TA by citizens depends on the expected results (or value) of doing so as well as the environment determining access to tech (social norms, poverty and power). MAVC innovation and scaling grantees very rarely considered factors determining access to technology, despite this being a well-researched area prior to MAVC[50]. Of the 11 EMU case studies, Yowzit learned from the failure to address this issue in their original innovation grant with the help of a PRLG, while Caritas Kitui and OCOS adapted to using FM radio when access to mobile technologies did not work as expected. Lack of access to tech has proved to be a barrier to uptake – but not the only barrier – in all EMU case studies. More generally, there seems to have been an assumption that either access to tech would not be a constraint or that the benefits from using it were so high that users would pay to do so. Grassroot was extremely unusual even among ’best-bet’ country case studies in undertaking user-centred design that surfaced the issues around access to tech at the outset[51]. A lesson for funders and implementers is that taking this approach is important and it was not enough to assume that problems of tech access can be solved by giving people phones; in some cases, women did not want to be identified as poor (WYDII) and in others receiving SMS from male strangers was socially unacceptable (ED). Across the 22 case studies, there seems to be only one example where the expectations of collective action were so high, this led poor people to club together to buy airtime for data access to try and influence planning (KYGC).
[50] The EMU inception report discussed pre-MAVC work published on technological competencies.
[51] The KYGC project ran into problems with the tech they assumed would work and then adapted, bringing in users to test solutions. However, lengthy redesigns led to delays in project delivery and it would have been more efficient to do research with users at the outset.
### Tech-related optimism bias and implications for programme design
Tech-related optimism bias can also be considered, as expected. It is certainly worth considering why virtually all MAVC innovation and scaling grantees assumed tech solutions would be more accessible or effective than they were. Greenhalgh (2013)[52] argues that technology in medicine has been influenced by five cognitive biases. The lesson for funders is that the problems of ’rosy reporting’ discussed in the REL review (see Section 8), suggest these apply to tech4TA as well. The biases Greenhalgh discusses are:
[52] Greenhalgh, T. et al. (2013). Five biases of new technologies. The British Journal of General Practice, 63(613), 425. http://doi.org/10.3399/bjgp13X670741
- Pro-innovation bias - anything new is inherently better than anything already in use (Rogers et al (1962).
- Subjunctivisation bias - ‘Much of the policy rhetoric on new technologies rests not on what they have been shown to achieve in practice but on optimistic guesses about what they would, could, or may achieve if their ongoing development goes as planned; if the technologies are implemented as intended; and in the absence of technical, regulatory or operational barriers.’ (Greenhalgh, 2013)
- Bells and whistles bias - the more functions a technology offers, the better it will work.
- Connectivity bias -the more technologies and systems to which a new technology can connect, the more useful it will be.
- Human substitution bias - whatever the task, a technology is as good as - or better than - a human.
We would argue that, in addition to these, MAVC assumptions around technology are likely to be affected by the Availability Heuristic[53], as we are so accustomed to hearing about tech solutions to everyday issues[54].
[53] Tversky and Kanneman (1973)
[54] https://www.wired.com/2010/10/app-for-that/
The official guidance for UK economists working on public sector programme appraisal and evaluation – The Green Book (2011)[55] – explicitly warns against ‘optimism bias’ and recommends that appraisals address the tendency to overestimate project benefits.
[55] https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/220541/green_book_complete.pdf
Given the evidence from MAVC and the documented tendency to overestimate what tech can deliver, we recommend (first priority) that:
- Tech4TA project appraisal guidance specifically considers likely sources of tech optimism bias; and
- HM Treasury add tech optimism bias into the next edition of The Green Book.
# Findings and Lessons: Innovation and Scaling
## Overview
The discussion below draws together findings on the following two evaluation questions:
- How effective has the process for innovation been (involving innovation, scaling, GIC and Research grants, brokering, private sector finance and lessons from scaling up in this sector or country)? What lessons can be learned for other programmes? (EQ 3)
- How effective has the process for scaling been (involving innovation, scaling, GIC and Research grants, brokering, private sector finance and lessons from scaling up in this sector or country)? What lessons can be learned for other programmes? (EQ 2)
There is an established literature on good innovation practice that includes both innovation and scaling. In trying to assess MAVC practice, we have drawn on the experience of Nesta.org, the DFID-funded Innovation in Development workshop findings and a UK early stage venture capital tech fund. There is considerable overlap across these three in terms of staging of funding and the kind of support required at each stage (see Annex 9).
The MAVC Business Case clearly states its intention for MAVC to be ‘backing innovation and new ideas, taking successful initiatives to scale, and building an evidence base’. However, while the subsequent Strategic Case section is built on the literature around transparency and accountability, and highlights the role of mobile and internet technology, innovation and scaling is not defined and there is no reference to the literature on good innovation practice[56]. The MAVC Inception Report used more innovation language, stating that such components ‘are set up to accelerate the number of new ideas, approaches and mobile- and web-based solutions that engage citizens and incentivise greater government responsiveness…to transform initiatives from valuable ideas via proven concepts to solutions at scale’. The Inception Report also highlighted its three core design principles as ‘co-creation, nurturing and scouting, and [being] user-centred’, however, as has been discussed in Section 3.4.3, user-centred design has been extremely rare.
[56] In part, this is because DFID did not have a specific innovation team at the time and the UK government Digital Service was UK focused and did not engage (Lu Ecclestone).

Scaling was only mentioned in terms of scaling up in the DFID Business Case. The MAVC Inception Report broadened this to three types of scaling: scaling up, scaling down or scaling out. However, the MAVC Inception Report made clear that scaling grants would be “Assessed on their potential for achieving demonstrable impact out of concepts. If it is indeed a proven concept, it will be assessed on the potential for implementation at scale and attainment of extensive reach” (p.13). Hence scaling grants were primarily intended to achieve scaling up and scaling out.
After the management review in 2015, elements of innovation support were added to MAVC in the form of Ushahidi tech mentors and in-country tech hubs. However, key informant interviews with grantees and MAVC country staff for the country case studies, suggest these were not well integrated with the other programme activities and were often not effective. In practice, the open call for innovation and scaling proposals in Year 1 produced far more grants than MAVC had capacity to nurture[57]. This problem was exacerbated by the lack of joined-up working across the consortium and management weaknesses subsequently identified by the Management Review. However, a lesson for funders is that submerging the FMC with a big open call for proposals that could not realistically be provided with incubation or acceleration support, was a serious mistake and contributed to a fundamental mismatch between MAVC innovation objectives and MAVC innovation practice. This effect was magnified by having numbers of grants made as a Key Performance Indicator (KPI) trigger for budget disbursal to the FMC (see Section 9.1.7). This was an unintended consequence of combining the KPI trigger and the call for more proposals than could be incubated or accelerated.
[57] This reflected USAID’s desire to have a high-profile launch.
Recommendation (second priority):
Funders need to match the number and timing of innovation and scaling grants to the programme capacity for incubation and acceleration. This is especially important when considering the number of grants as a key performance indicator.
### There was no consistent definition of innovation[58], but it was often (mis)understood as new, tech-focused approaches
[58] DFID Business Case does not define innovation but provides some examples of the types of interventions that the programme would support (under Expected Results p2).
Even relatively late in the programme, April 2016, the tender document soliciting applications for the MAVC Indonesia Joint Initiative to Support Civil Society Groups stated: ‘MAVC is a global initiative that supports innovative and tech-focused approaches to addressing governance issues’. This matters because where the focus was on tech (particularly in the absence of user-focused design), MAVC innovation and scaling projects were generally not successful (BSID, ED, MDTS and DPI case studies). The REL component took a much more tech-realist position (2015 Learning Event, Manila; 2016 Learning Event, South Africa) but innovation and scaling grantees generally did not take these messages on board. A lesson for funders and implementers is that the absence of targeted communication products in a language that NGO practitioners can relate to, makes it even more difficult for them to overcome widely held tech-optimism biases (see Section 3.4.9).
Some of the more successful interventions involved introducing modest ICT to organisations that had not used ICT in this way before i.e. the innovation was in getting organisational change. Examples include Black Sash in South Africa, INFEST and WYDII in Indonesia.
### There were some examples of agile and adaptive innovation but no systematic support for this
A number of grantees started implementing grants and found that their ideas for ICT use were not working out. Some rapidly adapted, switching from relying on mobile phones to existing FM radio, or making other simplifications to match user tech capacity and needs (e.g. OCOS, KYGC and CK). However, programme support to do this was patchy.
Although there are examples of MAVC supporting the learning and adaption of approaches originally that were originally taken - through PRLGs (Yowzit), the Community of Practice in South Africa (AbFP), Tech Hubs (Code4SA support to Black Sash) and Tech Mentors (AM) - these only occurred in some instances. The South Africa country case finds as many examples where this support did not work out as where it did. Grantees in South Africa said that before the management review, Ushahidi provided effective and intensive incubation support but afterwards, the support received from Nairobi or from local tech hubs was far less useful. In Indonesia no grantees we spoke to reported could identify support from Ushahidi or the tech hub.
The South Africa country team made a strong case that an incubation approach – with much more hands-on support and small grant funding released in tranches – would have provided better support for innovation, but this would have only been possible with far fewer grants.
### Innovation pathways were never set out for grants
The innovation literature identifies multiple stages, from defining the problem to innovation at scale and changing the market. Nesta.org has 7 stages (in which scaling occurs at 6), while NASA has 9 Technology Readiness Levels (in which proof of scalability is 7-8). While progress is often non-linear, there is general agreement on the kind of evidence and financing needed at different stages (see Annex 9). This is reflected in donor development programmes that take an explicitly innovation approach, such as USAID’s Development Innovations Ventures (DIV) programme or DFID’s Humanitarian Innovation Development Fund (HIDF).
MAVC used innovation programme terminology (innovation grants and scaling grants, for example) but these did not relate to innovation pathways that were intended to track and support grantees in this process. This was pointed out by the EMU at each DFID annual review[59]. The implications of MAVC not requiring grantees to have an innovation pathway have been serious and provide lessons for innovation programme funders:
[59] This was contested by the FMC. In response to our draft the MAVC REL component director wrote that they ‘disagree that one particular innovation pathway should have been adopted or that the FMC had in any way committed itself to any one innovation pathway, but I entirely take the point that the conceptual vagueness over what innovation was or should be, leading to operational vagueness in this respect, was a serious weakness’.
- The case study examples indicate that scaling grants have typically been used to test early stage ideas, with more funding than innovation grants but no stronger evidence of what works or does not, to take to funders. Hence, MAVC scaling grants have been targeted at proving concepts rather than the subsequent ’missing middle’ or ’valley of death’ that has to be crossed for scaling to be a possibility; and
- MAVC often failed to provide a pathway towards further investment where grants or elements of grants have proven successful. This threatens the viability of small organisations as well as undermining programme investments.
### The programme lifetime was too short for effective scaling
According to those running venture capital funds, the time taken to get to scaling depends on the technology involved and can be as little as three years for software but as much as 15 years for clean energy[60]. USAID DIV specify up to three years for Stage 1 (seed financing), up to three years for Stage 2 (start-up and testing) and up to five years for Stage 3 (transitioning to scale)[61]. This adds weight to the views of MAVC grantees and the implementing partners that effective scaling takes more time than MAVC envisaged. The lesson for funders is that, in this context, the MAVC timeframe was far too short given an aspiration to achieve scaling.
[60] Interview with Jonathan Bryers, Managing Partner, 350ip.
[61] https://www.usaid.gov/div/model
### Other factors impeding scaling
Even the strongest country teams (e.g. South Africa) struggled with the demands of implementing the large number of grants, leaving limited time to focus on scaling. In Kenya, where there was no CED for much of the implementation period, MAVC failed to capitalise on successful county-level projects with potential in other counties (e.g. KYGC).
The original intention was for donors and donor country offices to act as a conduit to programmes that would take successful grantees towards scaling[62]. This has not happened, firstly due to the lack of evidence on successful grants throughout most of the programme, and secondly as donor country offices never felt ownership of the programme, and were unwilling to commit their limited time to it (see also Section 9.1.2).
[62] The importance of country offices for uptake was mentioned in SC meetings.
# Findings and Lessons: Relevance and Brokering
## Overview
The discussion below draws together findings and lessons on the following three evaluation questions:
- Was there a bias in the types of intervention funded? Were any types of intervention excluded? (EQ 7)
- Were supported interventions aligned with overarching programme objectives as expressed in the MAVC ToC, country plans, synthesis strategy and REL strategy? (EQ 8)
- How effective has the brokering approach been? (EQ 4)
### Types of intervention funded
We have noted elsewhere that the initial ToC tended towards being technology-led and innovation was generally (mis)understood as meaning new, tech-focused approaches (Section 4.1.1). Some donor key informants thought the excessive tech focus reflected the powerful role that tech had played in the Arab Spring. We also find evidence for a number of pro-tech cognitive biases (Section 3.4.9). Whatever the cause, this led to MAVC granting that was more tech-focused, in particular mobile and internet focused, than required by the programme objectives. By 2016, some country programmes (e.g. South Africa) had developed a broader understanding of innovation, but this was not generalised. For example, at the final MAVC Learning Event in Jakarta in October 2017, the Hivos Country Engagement Developer frequently referred to technology as being at the heart of the MAVC programme (Indonesia country case study).
Programme relevance was reduced by the failure to involve users in design and the assumption of much greater access to mobile and internet tech than was actually the case. There are a number of case studies we have considered in which initial assumptions on costs or technological competence proved highly optimistic (BSID, OCOS, WYDII, MDTS, DPI). In practice, the poor and marginalised had less access to technology than assumed in (funded) grant proposals. In some instances, the failure to recognise the role of social norms in technology use, led to women being excluded (IRC, ED). A lesson for programme implementers is that it is very important for grantees to take assumptions around accessibility, competence and inclusivity of technology into account, but they are unlikely to do so if left to their own devices.
There were a number of factors that led to established actors rather than ‘unusual suspects’ being funded for much of the programme. Relying on an Open Call in Year 1 made it difficult for local start-up organisations, without capacity or experience in bidding for international donor funding, to bid. This was overcome to some extent by the move to brokering (discussed below). However, given a one-year or 18 month grant period, there was a strong incentive to use established NGOs with existing relationships with government (particularly evident in the Indonesia country case). This incentive would have been reduced if the programme itself had better capacity to help ‘start-up’ grantees link with government effectively. This contributed to the under-representation of government-led grants (discussed further in the South Africa country case). The lesson for funders and implementers is the need to consider potential trade-offs in working with ‘unusual suspects’, such as early resourcing to support smaller and less well-established organisations in advance.
### Alignment of interventions with overarching programme objectives
It is never easy to get the balance right between producing strategies and focusing on programme implementation (execution) and much has been written on this[63]. In the case of MAVC, we would make the following observations.
[63] For a just a flavor see McNulty (2008), https://hbr.org/2008/02/talking-with-robert-sutton-1 and Slevin and Pinto (1987)
- The MAVC steering committee (SC) perceived the early years of the programme, before the management review in 2105, as strategy heavy but light on implementation, which was one of the reasons for the management review. Following this review, the emphasis went in the other direction, and the FMC focus was very much on KPIs. The SC was intended to take a strategic role and should therefore have considered alignment of interventions against overarching programme objectives. In practice, the donors - facing both far slower implementation than expected and no overall picture of grant performance - saw the SC as an essential problem-solving forum, and there was a move away from strategic oversight. The difficulty of bringing all the donors and consortium partners together for the SC also meant that in-person meetings only happened once a year, and the nature of large audio conferences made it easier to focus on operational details than less tightly defined strategic conversations.
- We have noted elsewhere in this report that the MAVC country strategies varied in quality, only identified broad areas of opportunity and inevitably became outdated. In practice, country strategies influenced rather than guided interventions[64]. However, we would argue that having relatively weak country strategies that served as a starting point for country engagement (e.g. emphasising partnership with OGP), did not prevent interventions aligning with programme objectives. A lesson for implementers is that, as McNulty (2008) puts it, ‘…strategy doesn’t have to be a work of art, it just needs to get you moving in the right direction—with the emphasis on getting moving’. Any strategy or plan, he says, ‘needs to be adjusted or possibly abandoned, as events change and new information comes in’. Based on the evidence of the country case studies, the capacity of CEDs and the supporting MAVC ecosystem in country were much more important in terms of alignment or non-alignment with the programme ToC, than how good a country strategy was. In practice, alignment of country grant portfolios with the ToC was rather stronger in South Africa than in Indonesia and Kenya.
  [64] In Kenya, for example, only seven out of 25 grants were made in counties identified as priorities for MAVC investment.
- REL interventions were aligned with the Research and Evidence Strategy (RES) that was, in turn, designed around the programme ToC. Unfortunately, the programme as a whole failed to gain from the significant investment in the RES due to the lack of integration of the REL component with components managed by Hivos and Ushahidi.
### How effective has the brokering approach been?
Brokering is not formally defined in MAVC, but four areas frequently mentioned in interviews are:
- bringing ‘unusual suspect’ grantees into MAVC
- facilitating Communities of Practice (CoP) between grantees in country
- facilitating links between grantees and the tech or wider innovation ecosystem
- bringing government together with civil society grantees.
Communities of Practice are potentially important ways of contributing to the latter two elements. Brokering can also mean creating links to the users of research and this is covered in Section 8.
In Indonesia a decision was made early in the programme not to formalise a CoP because it was argued that vibrant networks around technology and accountability already existed in Indonesia. Instead, MAVC aimed to ‘jump on a moving train’. The Hivos MAVC country manager had established connections in this area and played an important role. The series of HackJack hackathon events in 2014, 2015 and 2016 were credited by government as being the ‘first time that the wall was broken between the government and technologists’. The head of the National Secretariat for Open Government Indonesia also saw this series of events as promoting the national government’s open data agenda. The Jakarta government subsequently provided funding to support the event.
The Indonesia country programme struggled to grant to unusual suspects[65]. This reflected short timeframes and the pressure to get grants out, combined with limited CED experience in this area. Hivos drew on extensive networks with civil society but failed to engage with large innovation incubators already working with private sector start-ups and government on promoting public services through innovative use of technology.
[65] The most ‘unusual’ suspect the CED could identify among her roster of program partners was that of SLOKA-the citizen journalist association. In Indonesia, journalist associations frequently collaborate with civil society organizations and would not broadly be considered unusual partners.
The Kenya country case study found very little evidence of brokered partnerships between grantees, tech outfits and duty bearers. None of the three Kenyan ‘best-bet’ grants, nor the four EMU case study grants, were the result of brokering to find unusual suspects. The absence of a CED for most of the programme made brokering much more difficult, and having Ushahidi and the MAVC programme headquarters in Nairobi did not make up for this absence.
MAVC brokering in South Africa has been successful in terms of:
- Granting to ‘unusual suspects’ such as the Amadla.mobi, Grassroot and Freedom Park Housing grants.
- Drawing on the CED’s experience, network and country team efforts to bring partners together.
- Creation of an effective and (what looks to be) sustainable community of practice (CoP) for civic tech engagement, making connections that would not have been made simply by CED brokering (GrassRoot and AbFP) and enabling some grantees to get practical help (including on tech issues) from group members, as well as providing space to reflect on their own work and learning from the experience of others.
Looking across the country cases, we draw the following lessons on brokering:
- Effective brokering of ‘unusual suspects’ with very little initial capacity (Freedom Park Housing Campaign in South Africa) is very resource intensive. It is only possible to do this for relatively few grants and, where this investment starts to pay off, it makes sense to grow returns over a number of years by enabling the organisation to grow rather than ‘cash-out’ at the end of a one-year project. If funders such as DFID can only do short-term project funding, it makes sense to partner with others who can systematically build on early stage funding, rather than leave it to the fledgling grantee to find the partners or solutions to take them to the next stage on the innovation pathway.
- Establishing a CoP requires significant investment of time by the country team, but the payoff is not only grantee learning, but having grantees in the same place makes it possible for the highly time-constrained CED to engage with them, helping to build trust and strengthen MEL.
- Establishing a CoP requires a significant investment of time by grantees and there has to be enough on offer for them to attend. It was worthwhile for MAVC SA grantees to do so as most grantees were CSOs with little experience of using digital technologies, and they were keen to learn how others had solved similar problems or find tech partners. There were also genuine networking opportunities – in part created by having user-focused tech made suitable for similar purposes by different users (GR, Amandla.mobi). The Indonesia team probably made the right judgement that grantees were attending CoPs if they were already interested.
Context for a CoP matters: South Africa has a tradition of civil society organisations working together to hold government to account, and building a successful CoP without this tradition and a shared purpose will be more difficult.
We recommend (second priority):
That future DFID-funded programmes involving brokering work, include a clear statement of what brokering is intended to achieve in a given country context, and require a supporting stakeholder analysis to identify who to work with.
# Cross-cutting findings on Poverty and Gender
This evaluation identifies some key findings in terms of outcomes on poor and marginalised groups. Within some MAVC projects there was the consideration and specific targeting of different social and wealth groups. For example, KYGC carried out targeted training sessions with a variety of groups and specifically targeted youth; LENGGO also targeted different gender groups and farmers using different tailored communication methods, and IPB carried out participatory budgeting meetings with special interest groups such as women and the disabled (see the Kenya Country Case Annex 7). Examples of methods to enhance targeting included the role of ’offline’ coordinators as intermediaries to encourage confidence in the use of the SMS system (see the WYDII case study in Annex 8).
Access to technology proved to be a barrier to uptake in all the EMU case studies (Section 3.4.7) and was a particular barrier for marginalised groups. Virtually all MAVC innovation and scaling project design assumed technology solutions would be more accessible than they were (Section 3.4) and assumptions on costs or technological competence proved highly optimistic (BSID, OCOS, WYDII, MDTS, DPI) (Section 3.4). In the case of Free State Housing Campaign, women were excluded from the WhatsApp groups developed (Annex 6). As noted in section 4.1.1, where the focus was on technology (BSID, ED, MDTS and DPI), innovation and scaling projects were generally not successful.
A key lesson is the need for interventions to consider both expected results and differential access to technology (Section 3.4.7). This lack of recognition of the barrier of access to technology was rooted in a failure to consider the factors determining access to technology (Section 5.1.1). Users were not involved in the design (Section, 3.4.3 and 3.4.7): only two of the 22 EMU case studies (Grassroot and KYCG in Section 3.4.7) actively developed tools with users. In some instances, the failure to recognise the role of social norms in technology use led to women being excluded (IRC, ED). On the other hand, Yowzit learned from the failure to address this issue in their original innovation grant with the help of a PRLG, while Caritas Kitui and OCOS adapted to using FM radio when access to mobile technologies did not work as expected. MAVC also highlighted an important policy gap around the way the use of technology is used to manipulate poorer less educated households (Black Sash in Annex 6).
MAVC grant selection clearly took gender into account and in some cases there was specific targeting, as seen in the case of WYDII (Annex 8) and amamdla.mobli’s mobile-phone platform to engage low-income black women (Annex 6). In some projects, women’s voices were enhanced but the greater challenge was getting a response to women’s voices. Quantitative survey data from four EMU cases showed that in only one of these (OCOS) was there a greater increase of women claiming that they believed they are able to call to account institutions on policy issues (Sections 3.2 and 3.3). Three out of four of the projects (SEND, Yowzit and SSP) (Table 3 Section 3.2) showed a fall in those answering positively, suggesting less progress for women.
In the WYDII project, there was an increase in levels of women’s confidence to engage in planning issues. This was particularly the case for the project’s community ‘coordinators’ who were predominantly middle-class. The village elite also became more aware of the exclusion of women and led to village level plans taking on board some specific proposals of women (Section 3.3 above). In the case of Caritas Kitui (Annex 5), the project was very gender focused and contributed to women influencing the county integrated development plan, and more involvement in government processes at various county administrative levels (Section 3.4.6. and Annex 5).
So, although grants took gender and poverty into account in the design and strategy stage, there was less evidence of a sophisticated analysis of exclusion (based on gender and or other forms of differentiation) which would have allowed the challenging of social norms, and power relations which underlay marginalisation. Both WYDII and Caritas Kitui show how a one-year project cannot be expected to change these norms (Annex 5). For example, in the case of Caritas Kitui, government officials started to exclude women with dissenting views from attending or participating in meetings (Section 3.4.6). In the case of WYDII, increased confidence was limited mostly to middle-class women who required the endorsement of the elite to engage, and many poorer respondents remained unable to attend or speak up in meetings (Annex 5). This shows the way in which wealth status secures a differentiated result from government. These examples also show the hazards of working through elite channels which necessitate the use of pre-existing power structures and thus avoid addressing the underlying reasons for exclusion.
# Findings and Lessons: VfM
## Cost-benefit analysis (CBA) and cost-effectiveness analysis (CEA)
### Overview
Following discussion with EMU on the type of evidence needed for CBA, the FMC REL team commissioned local consultants to try and identify quantifiable changes in project outcomes for two projects. It proved possible to use findings on one of these projects: MOPA (participatory monitoring leading to clearance of informal waste dumps in Mozambique). In addition, as part of our South Africa country case study, we looked carefully at evidence produced by Black Sash, and developed a CEA for this case study. We also gathered evidence on the impact of ICW on the re-tender of solar street lighting, but this was not sufficient for CBA or CEA.
As we have very little quantitative evidence from the FMC grantee monitoring and evaluation system that can be used as the basis for CBA, it is very difficult to make an assessment of programme benefits relative to costs. Nonetheless, if the Black Sash example is taken as representative of the small group of innovation, scaling and GIC ‘high achievers’, and if MOPA is considered representative of ‘upper intermediates’, we can use this to give a broadly indicative sense of net returns across these types of grants[66]. Effectively, we are making four strong (possibly heroic) assumptions:
[66] This does not attempt to estimate the returns to the approximately 22% of grant spend on research.
1. The distribution of EMU case studies into four achievement categories is reflected across the MAVC portfolio for innovation, scaling and GIC grants.
2. Black Sash (which is not an EMU case study) produces benefits equivalent to Caritas Kitui (which is in the same achievement category).
3. MOPA (which is not an EMU case study) produces benefits equivalent to ICW (which is in the same achievement category).
4. The large majority (9/11 or 82%) of innovation, scaling and GIC grants produce benefits lower than costs. To make this test as challenging as possible we assume zero benefits.
In this case, the question we ask is: How do the very high returns achieved by one project and more modest returns achieved by one further project, compare to the total grant and non-grant costs of the remaining nine projects?
Table 5: Estimated indicative grant benefits relative to costs
Total disbursed funds 11 EMU grant case studies	£1,080,779
Non-grant mark-up (113%)[67]	£1,221,281
Total cost	£2,302,060

Estimated benefit of one high achieving project (equivalent to Black Sash)	£6,770,472
Estimated benefit of one upper intermediate project (equivalent to MOPA)	£731,235
Total benefit	£7,501,707

Benefit : Cost ratio	3.3
[67] Ratio of total MAVC non-grant to grant expenditure. See Section 7.2 for discussion of cost data comparability over time.

The lesson for funders suggested by the results in Table 5 is that, as predicted by the venture capital model for innovation projects in development[68], it only takes a small number of big wins to easily cover the costs of investing in the MAVC innovation, scaling and GIC portfolio. It is quite likely that MAVC has achieved this. There are two caveats to bear in mind. Firstly, the assumptions made in this analysis (II and IV, in particular) are very strong. Secondly, the findings set out in the process section of this report (Section 9) make it clear that MAVC implementation has been sub-optimal and value for money could have been significantly improved if these problems had been avoided.
[68] Kasper and Marcoux (2014).
### Black Sash CEA
There is clear documentation, confirmed by interviews with multiple stakeholders, of how community-based monitoring evidence was generated following grant funding, and how this was used for national advocacy by BS, resulting in changes in South Africa Social Security Agency (SASSA) policy and practice. Table 6 below provides details.
For this evaluation, we have worked with BS to identify the numbers of beneficiaries affected. SASSA have estimated they will need to provide support to 1 million beneficiaries facing unauthorised deductions[69]. BS and CSO partners contest this, based on sample survey evidence, estimating that 2.5 million beneficiaries are affected. This provides lower and upper bounds for our analysis. Our base case scenario takes the mid-point of these two estimates.
[69] Presentation to Minister Dlamini re Unlawful and/or immoral debit deductions SASSA bank accounts, August 2014
We have drawn on work-in-progress reports submitted to the Ministerial Task Team (MTT) for Social Development for 2016 for evidence of:
1. Disputes lodged with SASSA between May and September 2016.
2. Refunds obtained by beneficiaries for these five months.
Using this information, we derive a monthly ‘average successful refund per claimant/month’ of 33 Rand or R395 per year (GBP 20.4). Beneficiary case study data presented by BS to Minister Dlamini in August 2014 indicates an average successful refund/claimant of R451, which is a useful cross-check on the (SASSA) R395 refund/claimant figure we use. We use this to estimate lower, upper and mid-point estimates for the annual value of beneficiary refunds in Table 6 below.
It is important to note that the figures on unauthorised deductions in the table below only relate to the first wave of deductions from payments under the control of SASSA. Black Sash has run a campaign against a second wave of deductions from payments managed by Grindrod Bank. If the Supreme Court of Appeal finds in their favour, unauthorised deductions from up to 25% of 2 million beneficiaries could be reclaimed – but this potential benefit is not included in our analysis.
Black Sash argues that the MAVC grant enabled them to make an evidence-based case on unauthorised deductions to government at least one year, and quite possibly two years, faster than would have been possible using their previous CBM system. As benefits in this case are a redistribution of income to the poor - as social security spending will ultimately be funded by taxpayers - they are technically a ‘transfer payment’[70] and CEA rather than CBA should be used to assess interventions[71]. However, this is a rather unusual CEA, as the outcome in this case is expressed in monetary terms.
[70] See the Glossary to HM Treasury The Green Book (2018). https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/220541/green_book_complete.pdf.
[71] http://www.betterevaluation.org/en/evaluation-options/CostEffectivenessAnalysis (accessed November 2017)
In this CEA, we are asking whether it was cost-effective to spend grant money on the MAVC Black Sash intervention rather than waiting a year or two to get the same results using the previous CBM system. The value of providing beneficiaries with refunds a year faster than otherwise is the lower bound benefit estimate. The value of doing this two years quicker is the upper bound benefit. The estimated value of getting a refund now rather than in a year’s time is calculated as the difference between the discounted and undiscounted benefit values. For low-income households, the value of not waiting is likely to be very high but as we are considering the use of donor funds (the MAVC grant), the appropriate discount rate is arguably a discount rate for donor finance, and we use a figure of 12%.
The additional costs involved in getting the faster refund are taken to be the full MAVC grant costs. These are the grants disbursed, plus the overhead or management cost paid by the donors. It is important to note that we recognise the many costs incurred in national advocacy by Black Sash, that were not covered by the MAVC grants, but these would have still been incurred if the previous, slower, CBM process was in place.
As Table 6 shows, the ratio of estimated benefits to costs ranges from 5.5 to 28.4, with the mid-point (our base case) being 16.9. Hence, we estimate that MAVC grant support to Black Sash has been highly cost-effective.

Table 6: Black Sash grant – basis for estimating cost-effectiveness
	Number	Rand	GBP	Source
Disputes lodged with SASSA May - Sept 2016	36,904			3rd MTT report 2016 p 19
Refunds obtained for these 5 months		1,216,197		3rd MTT report 2016 p 19
Average successful refund per claimant/month		32.96		Derived
Implied average successful refund per claimant/year		395.47
Cross check: average value of refunds claimed from 10 cases presented to Minister		450.95		Presentation to Minister Dlamini Aug 2014
SASSA estimate of affected bank accounts (lower bound - first wave of deductions only)	1,000,000			Presentation to Minister Dlamini Aug 2014
Civil society estimate of total affected bank accounts	10,000,000			Presentation to Minister Dlamini Aug 2014
Civil society estimate based on 25% of total affected bank accounts suffering deductions (upper bound - first wave of deductions only)	2,750,000			Based on Black Sash work with beneficiaries
Lower bound estimate of refunds due/month (first wave only)		32,955,696	1,697,218
Lower bound estimate of refunds due/year (A)		395,468,350	20,366,620
Upper bound estimate of refunds due/month (first wave only)		90,628,164	4,667,350
Upper bound estimate of refunds due/year (C)		1,087,537,963	56,008,205
GBP:Rand (2016)	0.0515			https://uk.investing.com/currencies/zar-gbp-historical-data
Discount rate	12%

Table continued		Rand	GBP	Source
NPV of getting lower bound annual refund a year later (B)		353,096,741	£18,184,482	Derived
Value of not delaying repayments by a year - lower bound (A - B)		42,371,609	£2,182,138	Derived

NPV of getting upper bound annual refund two years later (D)		866,978,606	£44,649,398	Derived
Value of not delaying repayments by a year - upper bound (C - D)		220,559,357	£11,358,807	Derived

Mid-point estimate of not delaying repayments (proxy for grant value) (F)		131,465,483	£6,770,472	Derived

Costs:
Scaling grant 2014/16			£100,000	MAVC
Scaling grant 2016/17			£100,000	MAVC
Mark-up for MAVC non-grant costs			100%	Estimated[72]
Total costs (G)			£400,000	Derived

B:C ratio - lower bound (A-B)/G			5.5	Derived
B:C ratio - upper bound (C-D)/G			28.4	Derived
B:C ratio - mid point (base case) ((A-B)+(C-D))*0.5/G			16.9	Derived
[72] Data provided by FMC after this CEA was carried out suggests that the MAVC non-grant markup is 113%. Our analysis will therefore slightly overstate the benefit:cost ratio.

### Cost-benefit analysis: Participatory Monitoring platform Maputo (MOPA)
MOPA is the acronym given to the participatory monitoring of the solid waste management process (PGRS) in Maputo. This enables the Maputo Municipal Council (MMC) to supervise their many small waste management contractors, and citizens to report solid waste collection and disposal problems. Following a World Bankfunded pilot in four neighborhoods in 2015, an MAVC Global Innovation Competition grant (£85,749) has funded the roll-out across most of Maputo from June 2016 to May 2017. Evidence for this analysis has been taken from the evaluation report of Ascenção Machel (2017), responses to our follow-up questions provided by MMC and our review of international literature on solid waste disposal in developing countries.

MAVC grant outcomes
Machel (2017) finds that:
‘Improvement in PGRS could be noted arising from funding from MAVC. For instance, based on the latest report produced on 01/11/17, there were around 6,698 cases reported and from these reported cases, 6,230 were solved, corresponding to 93% of compliance. It should be noted that the cases are reported by different users, but in the event the cases are reported by the same users, the type of issue reported is different. It is worth considering that the 93% of satisfaction from municipal citizens is in relation to the total number of cases reported by them (6,698) and not to the overall number of municipal citizens of Maputo city.

One of the major gains from the introduction of this platform was the removal of over 200 informal waste dumps with greater emphasis on the one of Maxaquene ‘A’, which had 06 waste dumps, Polana Caniço ‘B’, with 04 waste dumps, Inhagoia ‘B’, with 02 waste dumps and Magoanine ‘C’ with 08 waste dumps adding up to 20 big waste dumps which would need greater intervention with Bulldozer, big trucks and lasted days while others ranged from between medium and small intervention.’

We have tried to test whether this major gain was, in fact, the result of the MAVC grant rather than improvements implemented as part of the MCC waste master plan. Two sources of evidence suggest that the grant is likely to have played a major role: firstly, a range of stakeholders[73] identify MAVC funding as extremely important and secondly, the graph of citizen-reported waste problems shows a significant increase following MAVC funding.
[73] The World Bank, the existing platform implementer (UX) and the Municipality.

Cost-benefit analysis
In order to produce an indicative estimate of grant benefits, we rely on the following:
The number of households affected by removal of the 200 informal waste dumps.
- Based on the location of the dumps, Machel, in discussion with MCC, identified the 568.567 citizens of Kamaxaquene and Kamubukwna municipal districts (National Statistics Institute, 2013) as the principal beneficiaries.
- Average household size in Mozambique is 4.5 (derived from 2016 World Bank data). Hence, there are 126,348 beneficiary households.
The Willingness to Pay of citizens for improved solid waste management.
Wang et al. (2011) report four contingent valuation study findings that estimate the willingness of citizens to pay for improvements in solid waste management in terms of % of household income. These range from 0.1% - 0.75%, with a mean of 0.34%.
Household income of affected citizens.
We estimate household income of the affected citizens based on World Bank 2016 final consumption expenditure for all households in Mozambique. This is likely to understate income (and hence benefits) for two reasons: i) Residents of Maputo have higher incomes than the country average and ii) final consumption expenditure/household excludes savings and so will be less than income on average.

Evidence on intervention costs, is based on the following:
1. GIC grant cost = £85,749 (expressed in US$ using HMRC monthly exchange rates).
2. Share of programme management costs. FMC were still working on this at the time of writing, and so we used a figure of 100% of grant costs.
3. The informal waste dump tonnage cleared due to the MAVC grant was 9,700 tons.
4. The unit cost of waste dump clearance is estimated from data reported by Hoornweg and Bhada-Tata (2012) Annex E as US$5/ton (the mid-point of the $2-$8 range). This is updated to US$ 2017 figures using the US GDP deflator series (https://fred.stlouisfed.org).
5. ICT platform costs post MAVC grant will cost MMC US$ 600/month.

As Machel (2017) notes a number of reported benefits in addition to the clearance of waste dumps, just focusing on this one, albeit major benefit, will tend to understate net benefits. In contrast, we are likely to be overstating the net benefit by failing to account for the pilot investment previously undertaken in four districts funded by the World Bank.

Given the various uncertainties, we are only aiming to provide indicative estimates of benefits relative to costs. We consider two scenarios: firstly, assuming the benefits of the MAVC grant are only seen in the year of the grant. This is very likely to understate net benefits as we know that the MCC is continuing to use the platform funded by the grant, supervising waste disposal contractors and responding to problems reported by citizens. However, it provides a lower bound for our analysis. Secondly, we assume the benefits of waste dump removal are repeated in each of the next nine years. This is likely to overstate net benefits as informal dump clearance is a relatively easy problem to fix (‘low-hanging fruit’) relative to systemic municipal solid waste problems. Future benefits will be harder to achieve.

Detailed figures are presented in the table below, but the headline findings are that benefits are nearly three times the costs, even in the lower bound scenario. In the multi-year scenario, discounted benefits (using a discount rate of 12%) are nearly seven times discounted costs.
Table 7: CBA data
	2016
Average household size (Mozambique)	4.5	www.arcgis.com/home/item.html?id=1a85d81f75044c1b8cf0abf5e69fc0f2
Population	28,829,476	https://data.worldbank.org/country/mozambique
N households	6,406,550	Derived

Final consumption expenditure, etc. (current US$)	10,985,963,353	https://data.worldbank.org/country/mozambique
Final consumption expenditure/household (current US$)	1,715	Derived (understates income as excludes savings)
Citizens estimated to benefit from removal of waste dumps	568,567	Consultant study
Households estimated to benefit from removal of waste dumps	126,348	Derived
Average WtP for improved waste disposal as % of HH income - mid range	0.34%	Based on four studies of WtP for improved solid waste management – / Wang et al. (2011) - mid-range

Estimated WtP value of improvement (US$) mid-range	731,235	Derived
Grant cost (GBP)	85,749	MAVC
Grant cost (US$)	108,725	Using official monthly exchange rates
Estimated non-grant markup	100%	Estimate
Total grant cost (US$)	217,450	Derived
Informal waste dump tonnage cleared due to grant (tons)	9,700
ICT platform costs going forward (US$ 600/month)	7,200
Estimated clearance cost/ton (midpoint of literature review findings) US$ 2012	5.0	Annex E, Low income country mid-range for solid waste management cost of / collection and disposal for open dumping, Daniel Hoornweg and Perinaz Bhada-Tata (2012)
Inflation-adjusted estimated clearance cost/ton US$ 2017	5.4	Derived from https://fred.stlouisfed.org
Estimated additional clearance cost as a result of grant (US$)	52,476	Derived
Discount rate	12%

Table 8: CBA results
Based on grant period only
Total grant cost including programme markup (US$)	217,450
Total additional solid waste clearance costs (US$)	52,476
Total costs	269,926
Estimated WtP value of improvement (US$) mid-range	731,235
Net benefit (WtP - total costs)	461,309
B:C	2.7

Based on continued platform use	NPV	2017	2018	2019	2020	2021	2022	2023	2024	2025	2026

Total grant cost including programme markup (US$)		217,450
Total additional solid waste clearance costs (US$)		52,476	52,476	52,476	52,476	52,476	52,476	52,476	52,476	52,476	52,476
ICT platform costs			7,200	7,200	7,200	7,200	7,200	7,200	7,200	7,200	7,200
Total costs	524,903	269,926	59,676	59,676	59,676	59,676	59,676	59,676	59,676	59,676	59,676
Estimated WtP value of improvement (US$) mid-range		731,235	731,235	731,235	731,235	731,235	731,235	731,235	731,235	731,235	731,235
Net benefit (WtP - total costs)	3,606,736	461,309	671,559	671,559	671,559	671,559	671,559	671,559	671,559	671,559	671,559
B:C	6.9

## Cost-efficiency
We have tried to compare MAVC costs to those of the South East Asian Technology and Transparency Initiative (SEATTI) programme, funded by Omidyar Network. Both MAVC and SEATTI work in the tech4TA space, have ON as a funder, are managed by Hivos and undertake brokering, mentoring and learning activities alongside granting - although SEATTI is much smaller and has a narrower geographic focus and operational remit.
In practice, it has proved challenging to make this comparison for three reasons: firstly, MAVC definitions of spending by budget category changed over the life of the programme, making it difficult to construct consistent expenditure figures by category. Secondly, definitions of what constitutes management expenditure vary by consortium partner. Thirdly, IDS research spend on their own research staff includes a markup of 65% - 100%. At the time of writing, an FMC consultant (Cathy Shutt) had just produced some tentative estimates that go some way to overcoming these obstacles, and we calculate MAVC management and administration costs, including an average IDS markup of 70% on their own research staff costs.
With these caveats in mind we note the following in Table 9:
Table 9: MAVC and SEATTI cost metrics
	MAVC (2013 - 2017) in GBP	SEATTI (2014 – 2016) in USD
Total	24,862,212	2,026,074
Grant	11,670,558	1,547,702
% Grant : Total	47%	76%

Management, equipment, office and administration	7,174,833	407,914
% of Total	29%	20%

We have not been able to establish the relative importance of all of the drivers of non-grant costs but the most significant component of this spend is management, equipment, office and administration. As the table above shows, this component is almost 1/3rd higher for MAVC than for SEATTI and is likely to reflect the different management models for the two programmes.
The lesson for funders from this is that a consortium model, with three partners taking on management tasks, is very likely to be a more expensive approach than the single contract model. Whether this provides value for money will depend on the added value from taking this approach. In Section 7, we identified a number of problems with coordination across consortium partners and limited synergies over the programme life that suggest the additional cost has not provided good value for money, in this instance.

# Findings: Research Evidence and Learning
## Overview
Sources of information for the analysis and discussion below included:
- Direct interviews and skype calls with key individuals including MAVC staff (CEDs, REL staff, ROTs, Ushahidi), grantees, donors, global stakeholders and attendees at the IDS Dialogue.
- Document review of key programme, country and project data, including strategy and planning documents, Country Learning and Engagement plans (CLEPs), global learning event documentation, EMU case studies, FMC learning reviews, QAS and internal reports, research uptake plans, narrative reports and annual reviews.
- Review of outputs including publications, blogs, websites, tweets, and newsletters.
- Information collected during field work for country case studies.

A particular focus was placed on a sample of 10 randomly selected REL projects (Appendix I), non-grant and capacity building activities, as well as information generated from country level evaluation work.
## How effective was the REL strategy implementation process? (EQ 5)
### The Research and Evidence strategy
The Research and Evidence strategy[74] was first developed in July 2013 and shared with the donors within the first few months of the programme. It was revised and made publicly available in Year 2. It is a comprehensive and relevant document which outlines the ToC, audiences, different kinds of research and the purpose and rationale for each. Despite being used as a working document by the REL component, prior to February 2016, it was rarely referred to by donors or taken up by other components of MAVC[75]. This was partly related to the insufficient clarity from donors about the degree to which REL funding was intended to be used to engage around the innovation elements of the programme, and the proportion of funding that should be spent on ‘purer’ forms of research[76]. There was never a common position on this and it remained an area of contention until the end.
[74] http://www.makingallvoicescount.org/wp-content/uploads/2015/08/RE-strategy.pdf
[75] At the February 2016 Steering Committee meeting the REL component made a presentation which elicited some positive discussion and response from the donors.

### Engagement around the Theory of Change
The initial programme ToC, provided by the DFID business case in 2012, tended towards being technology led, with little consideration of political dynamics and theories about governance processes and outcomes. During programme implementation, there was little engagement by the non-REL consortium partners around the ToC, which meant that programme implementation was not informed by the intellectual drive embedded in it. This gap persisted after the Management Review, as the focus of consortium (and the donors) was on resources and KPIs. This further encouraged the separation of the REL component from other consortium partners. Thus, there remained a clear separation between the REL component, the innovation and scaling grants managed by HIVOS, and the activities of Ushahidi, which resulted in a significant disconnection between incubation, learning and communication of learning to stakeholders. A lesson for implementers and funders is that it is undesirable to allow a consortium of implementing partners to separate responsibility for ToC development and programme implementation.

IDS also recommended that ToCs were also needed at project level, however donor requests were not to do so in order to concentrate on granting[77]. Because of this, communicating the subtlety of the programme ToC proved difficult at project level and, for many projects, implicit project ToC and MEL systems were focused around the objective of rolling out technology.
[77] Interview with REL component director.

### 7.2.3 Integration at country level
The REL component allocated research grants primarily in line with research themes rather than with the primary consideration of country context. This was for a number of reasons. Firstly, the scope of work of the REL component, as set out in the tender document, has a thematic approach to granting rather than a country focus. Secondly, the research themes and questions had been informed by the programme ToC and were set out in the Research and Evidence Strategy. Thirdly, there were no country plans until the end of 2014 and those that were developed were of low quality.[78]
The ROT (Research Outreach Team) function was intended to increase the reach of the REL component at the country level, to mentor the REL grantees, and to provide contextual research and evidence (as laid out in the R & E Strategy). CLEPs were developed in late 2016. These helped to make the role of the REL component at the county level more tangible. They also helped start embed learning in the grantees’ portfolio and develop a clearer understanding of who the target audience were.

However, the time allocated to the ROTs was limited and some struggled with a lack of familiarity with MAVC’s projects and project documentation. There also was some ambiguity over who was ultimately responsible for uptake: the ROT function relied heavily on the capacity of the CED, and in South Africa and Tanzania the ROTs worked closely with the CED. However, in some cases facilitation of the ROT’s role was complicated by the separation of CED and ROT lines of reporting. Thus, the separation between the REL component and the country programme can be seen both as a function of limited resources for the REL component to operate at that level, but also as a reflection of the R & E strategy not being adapted to support country strategies, when the CLEPs were introduced.

The research grantees were directly managed by IDS, and CEDs had little interaction with most of the REL grantees, resulting in some disconnect between the implementation projects and the REL projects. Some CEDs expressed frustrations at feeling they were not perceived as stakeholders in the vision of how the REL component would operate at country level. However, effective country programmes were only in place for the REL component to engage with, late in 2015 and then CEDs’ time was ‘ringfenced’ until July 2016, to enable them to catch up on addressing granting delays. Thus, apart from the learning events, the REL component had very few opportunities to engage across the programme in the early stages of the project. In July 2016, the Research, Outreach, Use and Learning (ROUL) workshop held in Sussex explicitly drew attention to the integration of country relevant research into CEDs’ work with innovation and scaling grants, and their grant-accompanying activities. However, in practice, a lack of integration was difficult to address retrospectively, due to working cultures of the different organisations and the fixed budget allocations, which were set at the start of the programme. The REL component was not perceived by some country staff as having a clear benefit for the country programme, and there was a feeling that theory and analytical frameworks were being centrally produced, outside the implementation context. This, combined with what was perceived by some as a large spend allocated to the REL team in Brighton, had the effect of creating some resentment. The suggestion that IDS is ‘too academic’ and upward facing, was a common response from country and project respondents in our evaluation interviews, reflecting a clash of objectives between upwards and downwards flow of learning. IDS was aware of this, as well as the need to tread a narrow line with their interventions in country and with partners. Shutt’s (2015) learning review also discusses the issue of the ‘critical friend’ dilemma where bottom-up approaches can be undermined by too heavy an intervention in country.

Our review suggests that the centralisation of the REL component at IDS in Brighton brought challenges (both physically and intellectually) for mainstreaming REL across the programme, but it is not clear how this might have been improved without a significant change in funding allocation. The lack of strategic partners who could have led on research and technology in country, with a greater presence than the ROT function was able to achieve, was problematic for REL engagement at a country level. One of MAVC’s original objectives was the intention to support broad-reaching relationships and collaborations, including with ‘unusual suspects’. Many of the grantees therefore did not have a track record of engaging in research. This brought some tension between the objective of producing quality research and that of the inclusion of unusual ‘research’ suspects. Some grantees felt push back from IDS in terms of the quality requirements. This emphasises the challenge that global programmes, such as MAVC, face in encouraging the emergence (and ownership) of theory which is relevant to place and context, to avoid the inevitable trend towards the central production of theory. Within this, the challenges of ensuring quality research whilst working with a range of partners and analytical capacities cannot be underestimated.

### Project delays and funding restrictions

Delays and complications in project administration were said by many REL projects to have caused delays and significant problems for the research. Staff from all sampled projects reported frustrations at cuts and delays in funding, or the way in which they were affected by poor sterling exchange rate. PRLG recipients attached to innovation or scaling projects, were particularly affected by the funding delays. Many projects reported having to use funds from other sources to keep project timelines and delivery realistic. Some also stressed the cumbersome nature of financial reporting requirements, heavy project bureaucracy and the additional burden of auditing requirements. Given that most of the learning activities were scheduled for the final year, the assurance audit requirements and funding delays were particularly challenging for county-level learning. Momentum developed during the ROUL workshop and the development of the CLEPs was affected by demands for assurance assessment in December 2016, and the suspension or cutting of donor funding between December 2016 and June 2017.
Lessons we draw for REL funders are that:
- There could be benefit in someone responsible for MEL and REL, based at the country programme level, to increase engagement and integration of the component. This would also reduce unrealistic expectations on the country director to have capacity in technology, innovation, research, governance as well as programme management.
- Locating representatives of all consortium partners in one geographic location at the country level and providing more resources in country teams could have led to more joined-up work with project implementers. The challenge would then be for the MEL team to extract learning from across a global programme. A QAS-type exercise at country level could be one way to do this.
- It would be very difficult to combine the clustering of resources in country described above, with the diverse and wide-reaching research portfolio that MAVC actually had. On balance, we believe it is likely that the advantages of a more tightly focused research programme, with researchers concentrated in selected areas with a few larger grants around selected issues, would have outweighed the narrower range of research outputs. This approach would have allowed more resources to support interaction between country staff and the research component, and tighter more targeted communication outputs.
## How effective has MAVC’s approach to learning within the programme been? (EQ 6)
This section discusses the internal learning that took place within MAVC.
Overall, there was a significant time gap between learning and its uptake across the programme. The reasons for this are: i) there were few functioning linkages between the three components at any level, ii) the original MEL systems were ineffectual, and iii) results from the REL grants did not become available until late in the programme cycle.
To address these constraints, various mechanisms were introduced to document and enhance internal programme learning. However, a lack of overall attention to the ToC, and the mainstreaming of engagement around this by the consortium, remained an underlying barrier to learning. In addition, the RE strategy did not include learning[79] and there remained a lack of clarity as to how research would feed back into the overall programme.
[79] A Learning Strategy was produced separately and later.
### Strategic issues
The clear separation of ‘territory’ and related budgets between consortium partners, has been perhaps the most significant barrier to learning across the programme, with REL being the domain of IDS, implementation that of Hivos and ‘innovation’ that of Usahidi. A lesson for funders and implementers is that treating management of research as a separate component, acted as a barrier to wider programme learning and restricted learning from innovation.
Learning evidence on user-centred and participatory design, including knowledge such as the importance of considering the technical competences of users, existed long before MAVC, but was not clearly taken on board in the design and implementation of the innovation and scaling projects (Sections 3.4.3 and 4.1). The failure to make space for this learning prior to granting was partly due to the very short inception period and the pressure to grant so early on. It was also related to a difference in approach between consortium partners – innovation and scaling consortium partners were significantly more ‘tech-optimistic’ and had less interest in evidence that might challenge their assumptions.
Prior to the management review, MEL requirements by Hivos were minimal, leaving a vacuum of project data and inadequate MEL plans, which were hard to address retrospectively. In April 2015, IDS took over the management of MEL, and new appraisal and reporting tools were developed to encourage project level monitoring, to improve a learning focus around the ToC. These included new attention to MEL plans, new project reporting templates, exit interviews, the QAS and the setting up of the Champions Learning group. However, due to their lack of management authority over the CEDs it was hard for IDS to monitor the implementation of the new MEL requirements and thus implementation varied across the CEDs.
At this stage, IDS was also able to input suggestions into changes being made to the criteria for granting which hitherto had not been based on the ToC. However, the delay of the PRLGs, and the lack of real time learning, meant that the direct feeding of project results back into grant decisions did not occur.
### Accountability versus learning
The slow granting progress led to a focus on KPIs designed around granting which were divorced from the ToC. The donors’ main concern with granting KPIs, in order to catch up on delays in granting, made it difficult to prioritise learning. IDS attempted to strengthen the learning aspect in the review of the logframe. Tensions developed over issues such as the requirements for gender disaggregated data and notching up large reach figures[80].
[80] Discussed in the REL synthesis (draft December 2017).
As grant-focused KPIs remained the main concern of Hivos country staff, and project level ToCs were not well developed, the ‘learning ‘agenda was not being clearly communicated to the project level through the MEL system. This has resulted in over-rosy reporting, which in turn means that much of the MEL data is hard to use for learning. The lesson for implementers and funders is that the focus on management KPIs (and inappropriate KPIs), resulted in a lack of incentives, at the project and country level, to discuss and learn from failure, an activity which should be a key feature of an innovation project.
### Effectiveness of methods/tools developed
The QAS was a mechanism to increase ‘learning by doing’ and involved a process of analysis requiring country staff to think about outcomes and the evidence to show outcomes. The QAS Methodology was an attractive tool as it allowed a lesson sharing and learning process. However, in some cases, country level staff themselves did not have access to the evidence needed and the analysis was thin. Much of the MEL data remained of minimal use for learning purposes and could not be used by the synthesis process to fill the gap of engagement around ToC. In some cases, CEDs could not verify project reports and some claims made by CEDs in the QAS contradicted EMU reports. From this evaluation’s more in-depth exploration of some of the claims made in the case of Indonesia, this is a particular problem in terms of reporting influence in government.
The introduction of exit interviews was a good opportunity for reflective and crucial discussion, and provided a way of capturing outcomes which had not been captured in the grantees’ own reports. However, overall there was a lack of attention to feeding back from these new MEL processes into their programmes. The QAS had an action plan but there is no evidence that further discussion (outside of the QAS workshops) was facilitated around it.
Throughout the programme, there has been a tension between learning for MEL and learning for REL (accountability versus learning) with a focus on the former. IDS was primarily concerned with using MEL data to fulfil DFID reporting requirements, while the MEL system was only used to a lesser degree, to have discussions (with projects and CEDs) on the ToC and uptake pathways.
A new narrative, reporting template forms, was developed as part of increased attention to MEL to help grantees think about how outcomes fitted around the ToC. However, many of the grantees struggled with the format, which was difficult for those with language barriers and lack of experience with analytical reporting. In some cases, the new report format was not being used, which led to a backlog of closing projects, as people were not keeping up with reporting.
The International Learning Events were successful in bringing learning around research and practice together in a space where REL projects could interact directly with the innovation and scaling grantees part of the programme. The three events (in Tanzania - May 2014, Manila - February 2016 and South Africa - February 2017) achieved their objectives of shared learning, capacity building and providing opportunities for networking. Theoretical discussions and learning were vibrant and relevant, with an appropriate balance between peer-to-peer learning and a more theoretical focus. The latter two, in particular, provided an ideal opportunity to discuss the theoretical and practical challenges, and were marked by an air of realism, learning and questioning of assumptions around the role of technology.
Discussion at the South Africa learning event suggested some frustration rooted in the tension between academic and partner learning. Feedback from participants suggests that some grantees and country staff felt that ‘they were being squeezed into frameworks which were not discussed in plenary and …. that IDS had a hypothesis that they wanted to test’. This reflected some resistance to bringing in concepts and expectations that practitioners should engage with them.
Overall, however, participants benefitted from the learning events and they were well organised and facilitated (Manila, in particular). They played a vital role in helping overcome a key challenge of MAVC: how to apply learning to its activities as well as ensuring direct learning from the ground. However, the cost of these events was high, not every grantee was able to attend, and they involved very high levels of preparation.
In all countries, the CLEPs included the objective of synthesising, distilling and disseminating ideas of relevance to grantees and their stakeholders. Every country had a different approach to networking and their learning approach depended on the context. The Philippines and South Africa also held many learning and sharing events organised by the CED, to encourage brokering between the grantees (including REL grantees[81]). The drive of the CED was crucial in these cases. In Indonesia and Kenya there was no systematic feeding of lessons from the wider MAVC programme implementation or research results, into the projects at country level or into national learning processes.
The country learning process could have benefitted from increased resourcing, in addition to that which was provided for the ROT and CLEP process. The budget from IDS for country learning (allocated to the ROT and CLEPs) was constrained by earlier budget commitments and pressure to deliver on KPIs, which prevented them from transferring more budget to the ROT or CLEP process.
One of the most successful country level learning processes was the South Africa CoP. This facilitated learning through bringing together grantees around the theme of civic tech engagement. The South Africa CoP was not directly related to the REL component but connected grantees across the portfolio. It was facilitated by the CED in 2014, when the first round of grantees and some applicants were convened. However, this went beyond what could have been provided by CED brokering alone, and enabled some grantees to get practical help, as well as providing space to reflect on their own work and learning from the experience of others (South Africa case study). At all 12 CoP events, a conscious effort was made to make space for REL. Some of the CoP members were subsequently allocated PRLGs.
Interviews with grantees, almost across the board, reported positive outcomes on organisational capacity. The provision of mentors and reviewing assistance to REL projects by IDS and Usahidi appears to have made significant difference to the individual learning and capacity building of the projects.
### Whose learning?
A tension between the need for learning from country level and this being perceived as extraction, was a common theme expressed by some country staff and exacerbated by the way in which learning was not clearly flowing back down to country level. In this respect, the QAS was also perceived as quite an extractive process. It was not always clear (to the CEDs) how the country programmes were benefitting from the exercise.
There was some tension between the flow of learning upwards and downward in the implementation of the CLEP. At country level, some of the REL products and frameworks were reported to be not useful for targeting messages for practitioners on how they should use the knowledge.
In general, the reporting tools did not help to bring engagement around the learning objectives of MAVC, but in some cases fuelled the perception of the REL component as being extractive. From July 2016 onwards, despite the recruitment of the ROT, expectations of the CEDs increased greatly, with discussions about the ToC, increased requirements for reporting and MEL processes such as the QAS. Overall, the design of new mechanisms by IDS to address the lack of learning at and from the country level, did not match with the existing management, cultural and ‘capacity’ context. A key lesson is that it was unrealistic to expect the country programmes to adapt without substantial support (such as that given by the Adaptive Learning methodology under the GI project).
It does seem that IDS was over ambitious in trying to encourage a learning approach from grantees and CEDs, and making requests to which, in some cases, they found it hard to respond[82]. Many of the country staff did not have previous experience in this and the programme management context was such that demands were constantly changing. Overall, the CEDs did not get as many learning opportunities as they needed.
[82] IDS were the only partner familiar with theories of civic tech and T & A.
### Role of Ushahidi
Ushahidi’s role in learning was to provide two types of learning: i) capacity development on a range of issues directly to grantees through the South to South lab, provision of mentoring and hosting webinars ii) provision of support to grantees via the tech hubs which Ushahidi was responsible for facilitating. There is more detailed discussion of Ushahidi’s role in other sections of the evaluation report. However, evidence of Ushahidi playing a significant role in learning for MAVC grantees and processes is limited.
In the case of South Africa and Indonesia, we were told that no technical support was provided on innovation or methods to grantees, and there is little evidence of interaction with grantees in Kenya. End of programme reports from Ushahidi do not list details on country level interactionthat would allow further verification. Ushahidi did facilitate some valuable mentoring support in the Philippines, where the CED reported that this was well managed, responsive and provided good support in the form of MEL, ToC, open data and stakeholder engagement
The role of tech hubs in country learning is not evident. In the case of the Philippines and Indonesia, the expected model - where tech hubs provide support to grantees - did not happen. Some CEDs were alienated from the process: ‘I honestly did not understand what a tech hub was… even they [the tech hub] did not know what they were meant to do as a tech hub and begged to be able to send the grant back.’ (Interview with CED)
### Key lessons are:
- The high costs of research and brokering, and sufficient resources for MEL and support outreach, should have been reflected in the initial proposal and budgets.
- Clarity and agreement about how learning will be incorporated into the programme strategy, design and operation needs to be developed early in the programme.
- Systems to ensure research and the collection of evidence support implementation and innovation pathways and are not working in isolation, can help ensure that research conclusions are embedded in the learning framework.
- The benefits of mentoring are clear and increase with intensity and attention to adaptive learning.
- Reflection and learning from failure needs to be incentivised in any learning or innovation programme.
- A results framework that can measure activities and results for both learning and accountability purposes, as well as account for the time delays associated with research, would help overcome tensions that can arise.
- If research and practice are running in parallel there is an advantage in creating opportunities for physical meetings between consortium partners, such as annual strategy meetings or chances to work together as a team, to recognise common differences, and discuss how to learn as the programme progresses.
## The contribution of the REL component to the field of technology and accountability (EQ 13 and 14)
### Overview
We start with a discussion of the contribution of outputs of the REL component activities and we then consider separately the contribution to i) evidence and theory building ii) to immediate performance and practise (real time learning).
Overall, the REL component has produced a number of written outputs, coupled with involvement in global networking, including events and interaction on social media. In the last month of the programme, the production and communication of products has been particularly voluminous. The written outputs are, for the most part, high quality but many are not accessible for all of their target audiences[83]. This is a result of there not being enough time for synthesis and the development of more accessible research communication products.
[83] Each type of publication was aimed at different audiences with different implications for ‘accessibility’.
A clear assessment of outcomes, at this stage of the programme, is challenging for various reasons:
1. Changing practices takes a lot longer than the duration of the programme. There is both a time lag in the way that REL component was designed (with an intentional back loading of learning and some research uptake activities), as well as a well-documented time lag of the outcomes from any research process. Indeed, much of MAVC’s own research shows that it is naïve to assume that levels of accountability and citizen’s relationships with the state can change over a short period of time.
2. Many the written outputs have come out only in the last months of the programme and by the time of the evaluation (in October and November 2017) there had not been a substantial synthesis across the body of learning. This limits the assessments that could be made[84].
  [84] This review was not able to cover outputs which were finalised after mid-December. Some early conclusions from the final synthesis were presented at the IDS Dialogue in October 2017 so these presentations (and the reaction to them) were used as a proxy for the final synthesis (which was delivered in January 2017) .
3. Outcomes and influence from the research outcomes were not measured systematically by the programme (see Appendix 1). Data on uptake and learning influence was not collected by the programme and there has been no systematic attempt to capture impact stories or to record feedback received[85]. This was in addition to the way in which there were no suitable indicators which attempted to capture the complexity and pathways of how learning occurs.
  [85] It would have been useful to have an MTR as this would have allowed this point to be fed back earlier.
### Research outputs and uptake
At the project level, each of the 60 individual research projects has a range of different outputs associated with it. There is a variation in the quality of written project outputs, reflecting the wide range of grantees, different objectives of the grants and different levels of capacity. A rigorous peer review processes was used on all the publications released on the MAVC website and many of the publications needed heavy editing to reach the required quality standard. In some instances, they were not accepted to be published as MAVC publications.
At the programme level, the REL component outputs included:
- Open access journal articles[86], comparative or multi-project reports, synthesis products (some associated with specific grants), and programme level synthesis, as well as a number of blogs. Overall, there was a high level of quality assurance for these written products.
  [86] The IDS bulletin issue 47.1 entitled Open Governance produced in January 2016 had clear and relevant lessons that bridged the space between policy and practise. The Bulletin achieved the highest download figures out of all the MAVC publications which may be related partly to the way which it brought together many of the ‘big’ names in the field.
- Learning events such as webinars, specialist seminars and most recently the final Dialogue event held at IDS. Videos of many of these are available on YouTube or the GPSA website but are not available on the MAVC website.
- Country learning events were held in tier 1 countries at the end of the programme, as part of the CLEP process.
- IDS REL staff were active in presenting and networking at the key influencing events and at most international events around technology, accountability and governance.
- They also took frequent opportunities to interact with donors such as SIDA, USAID, WB, DFID to try to integrate learning from MAVC[87].
  [87] There is a lack of rigorous data on donor impact but some of the donors interviewed for this evaluation reported they had been positively influenced by interaction with the REL component’s events and/or their products.
### Contribution of thematic content
The interviews conducted for this evaluation show the value of MAVC outputs in providing quality research. There was a clear demand and niche for the MAVC work, with relevant questions being answered. There are two main themes to the content of the outputs:
1. content which adds to evidence and theory, and
2. content which adds to a knowledge base of practice and what to do about it. We now discuss these in turn:

The evidence/theory building and associated learning in the field of voice and accountability [EQ 13 and EQ 14]
In terms of contribution to theory and evidence, the added value of the REL component’s outputs lies in two main areas:
1. outputs answering new questions, describing new issues or phenomena emerging and providing novel approaches,
2. outputs strengthening the evidence base around phenomena which have already been described but were not previously supported by robust evidence.
Novelty
Many of the interviews we carried out suggested that MAVC is valued for producing research in new areas, for stimulating novel ideas and approaches, and in highlighting the areas where more work needs to be done. Indeed, looking across the project portfolio there are a number of areas of innovation in terms of research. In our sample of only 10 projects we find the bringing together of different theoretical debates not always seen in the same arena (see, for example, Francesca Feruglio’s project which brought in concepts from the human rights sector), the use of innovative methodologies for understanding motivations of the ‘less connected’ (Network Society), and the application of new theory around technology and accountability to new sectors (Hrynick and Waldman’s review of health projects). Above all, MAVC helped to highlight the importance of providing a political lens on issues of technology in the accountability space, where there is some disinclination to do this.
On the other hand, as the results began to emerge and become distilled into ‘sound bites’ of more practical advice, there were some suggestions that there was ‘little that was new’ in the conclusions from MAVC’s research. These perceptions reflect the challenge that the REL component faced in finding a balance between developing accessible messages and presenting stimulating, novel ideas.
This also raises questions about what is meant by ‘new learning’. In interviews with participants and donors following the Dialogue Event, some of the lessons which the donors claimed to be new for them are indeed discussions which have been in the theoretical debate for many years. So, although these ideas may not be new from an academic point of view (i.e. they have been described before), they may be new for that audience. The time lag for research innovation to filter into the field of practice and policy narrative is a challenge for a programme like MAVC, which is juggling different audiences who assimilate and deal with research lessons in different ways and at a different pace.
Evidence
As well as the niche that MAVC fills in terms of providing a new lens on the technology and accountability debate, the main value of MAVC lies in the depth of the evidence base that it has created. Indeed, there were a number of (predominantly case) studies on social accountability involving technology prior to the programme, but the evidence was often of poor quality. There was therefore a clear need for triangulation around the claims. Above all, there was an urgent need for an evidence base to highlight the political aspects of the technology and accountability space, and it was in this area that some of the specific IDS Research project grants were most valuably used for. MAVC has helped to strengthen this space through the production of higher quality research.
MAVC did face some challenges in terms of extracting general lessons from case studies in a systematic and robust manner. The microsite review[88] relied heavily on syntheses works by Hrynick and Waldman (2017) and Martin (2016), which are based primarily on self-reported data from the grantee and project reports. However, as discussed elsewhere, there is a problem of data credibility associated with relying on reported data from the MEL system and projects self-reporting - EMU country and projects evaluations have found a mismatch between what is being reported and what could be verified. Both of these synthesis reviews overcame this problem by augmenting their data with further interviews with grantees.
[88] https://researchfindings.tech/
The value of programmes such as MAVC in promoting the benefits of conducting research and the critical questioning that this involves, is clear. This is especially the case in the field of technology and accountability where a lot of funding has been allocated with little research on the practical aspects: ‘We cannot just drop tools/technologies on communities and expect that everything is going to be fine.’[89] Thus, a key niche which MAVC filled was the honest analysis of the evidence around the use of technology, a type of analysis which is not easily found elsewhere in the practitioner orientated literature. The strong demand for this type of analysis was shown by the Engine Room research[90] (one of the first Third Party Research grants), which collected a rich data set of responses from technology users thus highlighting the demand for work in this area.
[89] Interview with global stakeholder
[90] https://www.theengineroom.org/alidade-interactive-guide-for-finding-technology-tools/
One of MAVC’s key contributions MAVC has been to challenge the tendency for ‘rosy reporting’ which is inherent in the arena of tech and accountability. As one IDS Research project grantee explained: ‘When you stand up and present an unrosy picture you get a backlash … this is part of the bell curve of innovation and it takes courage to stand up - particularly when your funding system relies on it. ‘
Contribution to informing performance and practice in the field of voice and accountability [EQ 13]
There are two main channels for real-time learning, which were intended to provide feedback into the direct performance and practice of MAVC projects (and in so doing provide wider learning for practice management and implementation in this field). These were i) the PRLGs and ii) the Adaptive Learning project which focused around learning for the OGP process.
PRLGs
The PRLGs were intended to result in real-time learning and feedback into the project implementation and in so doing represented a crucial pathway for implementing the programme’s ToC. Beyond the benefit for the actual project to which the grant was attached, the R&E strategy emphasised the role of PLRGs in contributing to the wider evidence base and practise through reflective experiential learning. The original vision of the PRLGs was that these would run alongside all innovation or scaling grants and feed back into the grantees’ own learning. The PRLGs were therefore deliberately designed to be back-loaded[91]. Delays in allocating innovation and scaling grants inevitably mean delays in PRLGs. As a result, IDS changed strategy and provided nine (out of a total of 25) non-MAVC practitioners receiving PRLGs. This compromised their original real-time learning objective though it did help to produce evidence and lessons from a wider variety of projects. By the end of the programme, there were only a few instances of results from the PRLGs that could have been utilised by the innovation and scaling grants.
[91] Interview with REL component director.
By the end of the first year it was clear that the delays in PRLGs would affect the real-time learning that would be available from the PRLGs. At this stage, there would have been benefit in focusing on other ways in which the REL programme could have fed back into the practice, and particularly back into the innovation pathways. In addition, apart from the PRLGs, much of the rest of the REL grant portfolio is characterised by a lack of action learning which is surprising given the nature of the programme’s ToC and intended pathways.
The PRLGs which were attached to existing MAVC projects provided useful input to those projects (e.g. TGCI and Prakarsa, in the case of our sample) as this additional grant enabled them to put additional, separate resources into learning. Each of the PRLGs we looked at had produced relevant outputs, more often in the form of process than written products. This attention to process was encouraged by IDS. For example, TI-Kenya and TGCI projects did not produce quality written research products from their PRLGs but have had impact on the government processes they were engaged with and a high level of uptake. In the case of TGCI, despite a sophisticated statistical evaluation methodology, it was the qualitative processes associated with doing their assessment, which had the more valuable influence.
The individual PRLGs in our sample all reported significant contribution to their own project learning but capturing and disseminating that learning for wider learning was less successful. Some of the project reports were not of high enough quality to be published by MAVC and for many of the PRLGs there is no written product (blog or report) available on the MAVC website. In some cases, this lack of output was overcome by the writing of practice papers, which were facilitated by the IDS team and took the form of a conversation with the project implementer. These presented a valuable opportunity for IDS to push for some self-reflection and capture relevant practical lessons that were not always referred to in the partner’s research reports.
However, apart from the PRLGs attached to MAVC projects who did feed lessons into the wider synthesis process, few lessons were captured systematically from innovation and scaling grants across the programme and there is little evidence of discussions around the evidence/learning that would be needed for scaling at the project level. Overall, (as discussed in the country section above) due to the limited interaction in most countries (other than South Africa) between the REL component and the country programme, there was little interface between the PRLGs and wider practitioners in country. Perhaps related to this, some REL grantees (e.g. CIPG, TI-Kenya) emphasised the dilemmas they faced about the lack of follow-up to the research, and the regrets they had about not being able to maintain momentum around their positive engagement with government actors. An exception to this was the Philippines where there was a workshop facilitated by the ROT on lessons learned and an attempt was made to learn from the INCITE project[92].
[92] A £190,000 scaling project entitled “Strengthening meaningful civil society and local government partnerships in the Open Government Partnership (OGP)”
Under a different design, the research element need not be managed separately, thus encouraging consortium partners to work in a more integrated manner and avoid silos. This might ensure research matched more closely with the support needed for innovation, and learning is more closely structured into the programmatic design. In practice, this is a significant challenge. IDS’s value in the research and conceptual role is clear and not often found in organisations with the capacity to manage implementation at country level. Without a consortium, funders would need to specify the required qualities carefully and ensure the implementing organisation recruits programme managers to reflect these qualities.

Contribution to the OGP
MAVC was intended by donors as a key enabling mechanism for providing support to the OGP. However, MAVC’s ToC had not been clear on how it should engage around OGP and it was not until the final year of the programme that it received attention. Government was increasingly associating OGP with technology and it was, therefore, not appropriate for MAVC to throw innovation finance at this space without a critical angle[93]. The only realistic way of funding projects related to OGP was via a ‘learning niche’ which meant that the REL component had to lead on it. The REL component did not have the in-house capacity to take on the scale of the work required. Hence, Global Integrity was asked to help design and then lead a learning trajectory initiative involving six projects, which had all had either scaling or innovation funding and a PRLG. The aim was to support grantees to come together four times a year in a reflective learning process, to provide analysis to feed into the OGP process.
[93] Interview with REL component director.
It was a risky endeavour and IDS was worried about the standard of output that they would get near the end of the programme. There was some tension between the priorities of the two objectives i) to make a difference in OGP ii) to test an adaptive learning approach. IDS was keen to avoid a focus on adaptive learning alone and they did need to work to keep GI focused on the key issues facing OGP. Despite these concerns, the final publication does appear to have reached an appropriate balance and it resulted in useful real-time learning which was crucial for MAVC’s results and learning, particularly around the clear added benefits of a more engaged method. All the projects involved reported benefits from engagement in this approach and five out of six reported enhanced outcomes, making progress towards supporting the OGP process and communities in various ways[94][95]. This decision on how to engage around OGP is an example of MAVC providing targeted input into an international and national process based on a careful assessment of the specific niche of MAVC.
[94] Interview with Global Initiative.
[95] For example, both projects in the Philippines (JRIG and INCITE) are said to have resulted in influence on content of the OGP sub/national action plans as a result of the process by which they were developed (Interview with REL component director).
### Common issues affecting the contribution of the REL component to the field of technology and accountability [EQ 13 and 14:]

Uptake strategies
No research uptake strategy was produced for the programme level[96], rather it was intended that uptake plans would be produced at the individual project level, with the justification that each project had a different specific audience[97]. However, IDS did not pay great attention to ensuring the implementation of the project uptake plans - they were not always referred to and quite a few of the grants (both of the IDS research projects in our sample) had not prepared an uptake plan. Where significant attention was put into uptake, it was often due to the motivation of the grantees themselves, though IDS were supportive (see for example the Alidade toolkit).
[96] The R & E strategy states that the findings from a number of research uptake and communication activities ‘will inform the development of a research dissemination and uptake strategy targeted to the different stakeholder groups’.
[97] The CLEPs played a role as uptake plans at the country level.
Research communication at the programme level
A number of online methods were used for programme level communication including the website, webinars, e-discussions, e-newsletters and social media (see Appendix II – Communications Review). Twitter was a key means of engaging and provided some interpretation and succinct messaging. By the end of the programme, tweeting had reached the high levels achieved at the start of the programme and was particularly active around the final Dialogue event. However, it is not a medium that is utilised by all audiences.
Despite the number, and generally high quality, of written research products, the communication of research and knowledge management was less strong. General communication was the responsibility of Hivos and responsibility for research communications lay with IDS, thus the two were inextricably linked[98]. The poorly designed and maintained website was a barrier to effective research communication throughout most of the programme. Only towards the end of the programme did project pages begin to include information on project details and outputs.
[98] Late in the programme IDS took over the creation of a searchable repository for publications and the twitter feed.
Challenges facing research communication were not only related to the design and management of the website itself but also to the lack of easily digestible summaries and synthesis material. The website is not able to provide a clear overview of the programme’s ToC or clearly identify and discuss the key thematic issues. A number of blogs were produced over the programme’s lifetime, some of which do contain useful overview material which could have been used as synthesis and summary products. However, the way they were displayed on the website meant it is hard to separate those overview blogs from those on project level ‘micro’ results.
By the final months of the programme, apart from the microsite which was released in mid-October, there was no other accessible summary communication product. Much of the research produced had not been summarised or extracted into more practical learning messages. To overcome this, a number of strategic and targeted syntheses products were prepared by communication consultants in the last weeks, to highlight key areas of the programme[99].
[99] Various synthesis processes were embarked on in the last month of the programme (Engine Room’s micro site; a review of governance lessons by Herringshaw (2017) and a blog review of adaptive learning by Miller, 2017). These were in addition to earlier syntheses of project results by IDS Research projects such as that by Martin et al. (2016) that reviewed 24 projects of which 18 were MAVC funded and that by Hrynick and Waldman (2017) (who reviewed 26 MAVC projects in the health sector).
This lack of accessible communications products presenting evidence on outcomes, has been a source of tension with the donors throughout the programme. Donors have put pressure on the REL component to produce evidence on outcomes and provide accessible information and the succinct communication products they needed. Related to this, the perception by donors that IDS wanted to publish its own research for their academic purposes, beyond the immediate focus on MAVC, has been a hard perception to shift. This suggests a deficiency in communication of the clear linkages and relevance of case study or country specific work to the overall questions of interest to MAVC.
The challenge of multiple, segmented audiences
One of the most significant challenges that the REL component faced in term of uptake was the wide range of target audiences segmented in many ways (sector, type, country, level). The need for different strategies was recognised in both the R&E and the communication strategies[100] but we do not see a corresponding segmentation in outputs clearly targeted at different audiences. As a result of the multiple audiences and the narrow balancing act between theory and practise, the REL outputs faced contradictory judgements, which ranged from being too academic to not theoretically novel enough, and a range of opinions in between. This is expected for a programme with multiple audiences and further highlights the need for more attention to be paid to segmented communication products. Without this segmentation, MAVC’s written outputs (the synthesis products in particular) risk ‘falling through the gap’ by not quite being tailored to any specific audience.
From our survey of global and country level stakeholders, there was a range of responses on this issue - some felt that more could have been done to engage practitioner organisations and reduce focus on the analytical ‘Western academics’. At the same time, it is recognised that the added value of IDS lies specifically in its ability to engage in, and influence, the theoretical debate and to bring this to bear on a sector of development which is in need of theoretical rigour. To reduce the theoretical input of the REL component’s engagement would be to reduce its added value. Thus, as discussed above, the solution seems to lie in more time and resources being allocated to the creation of more targeted communication products, rather than the reduction of the theoretical content of the products.
The implications of delays
The wider programmatic delays and additional tasks, such as taking on the lead of MEL in Year 2, meant that the REL component was always striving to keep up with timelines. Although there was an emphasis on process and real-time research uptake activities, the requirement for ‘written products’ meant that many of the outputs would be backloaded. In addition, some of the IDS Research projects were specifically intended to produce synthesis and learning products, which relied on the outputs of other projects as their inputs. The PRLGs were intended to be attached to innovation and scaling grants and therefore had to wait for these grants to be allocated. A result of these features many of the research results only emerged at the very end of the programme.
Thus, there was already some contradiction in the design of the REL component between the objectives for double loop learning and the backloaded nature of the design. The overriding challenge for the real-time learning that was intended by the design (i.e. via the PRLGs) was that, for this to operate, a well sequenced programme machinery was required. Once the programme was underway, opportunities to adjust to programme delays (such as a reduced number of questions or reducing the number of grants in favour of country engagement and brokering or research communication) was limited given the pressures they were under for grant disbursement and inflexible budgets that were set well ahead of time.
The resources required for mentoring, capacity building, and quality control, as part of research, were underestimated. These requirements and timelines will be exacerbated where unusual suspects are involved in the research or where extra attention is put on process, as was intended. For many of the projects, the time taken for research was underestimated, added to which each of the sample projects had faced some delay in fund disbursement, resulting in delivery delays. Delays in delivery were a particular problem for some of the IDS Research projects.
Making research products more accessible requires time. Not all research projects had been required to do shorter outputs which would be relevant to a wider audience and to do so would have required extra time written into the projects. The benefits of making extra time available were clear, as in the case of the Engine Room research which produced a sophisticated communication product (the Alidade framework for choosing technology tools). A lot more can still be done with the wealth of data and evidence that exists and given the delays faced there would have been benefits to the REL component having had more time allocated in the no-cost extension (as suggested in the draft Hivos final reports) to allow them to get more value out of the synthesis work.
Due to the challenges faced in time delays and in synthesising across a wealth of different research outputs, there is an argument to be made that a smaller number of larger comparative studies focusing more strongly around selective issues, would have been more effective.
Synthesis
The lack of synthesis products from MAVC has been a challenge for the easy communication of MAVC’s messages. A lot of research, published over the final two months of programme, has not yet been adequately communicated or incorporated into the final messages that MAVC was proposing at the Dialogue event. One challenge was that many of the project results did not materialise until the end of the programme[101] which raised problems for the synthesis process and for the production of accessible outreach products. In addition, a number of the research projects had no publications associated with them even by the end of the programme (see for example TGCI and CIPG). This might be understandable in the case of the PRLGs, where the emphasis was put on process and direct learning but in the case of Third Party grants and IDS Research projects, some form of written output should be a minimum expectation.
[101] For example, the MIT work was the only experimental work done under the REL component so it was vital that results could be incorporated into the syntheses, but it was delayed (due to country political reasons) and only able to complete an internal report for MAVC in time to allow data to be incorporated in to the systems. A large amount of work remained at the end of the programme to finalise products and translate them for partner audiences.
The challenge of extracting policy messages
Some of the analysts working on the synthesis products found it hard to pull evidence out of the research results as many of the results were not ‘easily digestible’ and the research not written to allow an easy synthesis. This echoes some of the feedback around the Dialogue event that the synthesis messages presented were not strong or memorable. Overall, the Dialogue event was valued more as a ‘dialogue’ and networking event than as a chance to access clear evidence from MAVC.. The messages from MAVC that were presented were judged to be clear but the evidence was not fully consolidated. Some participants were disappointed that there was not enough discussion of the details of MAVC’s projects and that grantees had no chance to share project experiences. Some were disappointed by the negative results presented and felt that, had their own projects been presented, they could have balanced this with more positive and exciting results[102]. There were also some suggestions that the overall emphasis on technology threatened to detract attention from the work on non-technology related MAVC projects.
[102] The Final synthesis report (December 2017 draft) does however seem to have addressed it with the inclusion of lessons and reference to a range of innovation and scaling projects as well as those from the REL portfolio.
One of the challenges which compromised opportunities for learning across the programme was that it was not possible to use much of the MEL data from non-REL grants in the synthesis analysis, as common indicators were not used across the grants, making it hard to compare across the database. Where they could include MEL data in the synthesis analysis (from narrative reports, QAS and exit interviews) there were concerns about quality. The tension between the use of reported/perception data and that emanating from the experimental work, is a theme running throughout the synthesis process.
### Key lessons to highlight in this area are:
- There was not enough focus on research uptake planning and implementation at the programme or project level, which led to a gap in transfer of knowledge to the relevant stakeholders.
- There is value in matching research more closely with the support needed for innovation.
- The resources required for mentoring, capacity building, and quality control as part of research can easily be underestimated.
- Extra budget and time is needed to allow iteration and user testing of communication products.
- Attention to theoretical content of the research needs matching with time and resources for the creation of more targeted communication products.
- The effort and activity focused on delivering learning products from the programme took place at the very end of the programme, which meant there was little time for synthesis for the wide and diverse audiences of MAVC, and also left little time to filter out into the wider fields of Tech4T&A. Knowledge flow takes time and occurs through complex diffusion methods. It is not realistic to expect that simply by making lessons available, people will engage and use them.
## What was the ‘added value’ of the REL component to the MAVC programme in contributing to reach, influence and catalysing action towards MAVC objectives? (EQ 15)
The REL component’s RE and Learning strategies and Hivos’s communication strategy are the main route through which reach, influence and catalysing global action was expected to occur in the programme’s ToC. At the global level, the REL component had a far more significant effect on reach and influence than the other consortium partners. At individual country level, however, the REL component did not have significant influence directly or clear direct added value in all cases.
The inclusion of a research component working alongside practice represents an exciting programme design. Where the consortium partners came together the outcome was impressive – namely the international learning events and the CoP in South Africa. However, this did not happen frequently. Most of the documented learning has come from the REL component as very little has been produced on the innovation and scaling grants that can be referenced or incorporated into the synthesis pieces[103].
However, as discussed above, the lesson for implementers is that catalysing action takes time; it is unrealistic to assume that a programme involving the feedback of high level research into the county level effectively and in a way which navigates power dynamics, can produce significant outcomes in five years.
One of the main ironies that emerged was that, although the REL component’s higher-level analysis managed to problematise, and advance theoretical trends away from a ‘rosy one-dimensional story’ around technology, the implications of these advances did not filter down to implementation at the level of innovation and scaling grantees.
## Considering the proportion of budget allocation, did the REL component deliver VfM? (EQ 16)
In addition to the general VfM questions addressed in Section 7, there is a specific question on whether spending 25% of the programme budget on research represents a good use of money? In terms of producing grants, the REL component was relatively efficient - spending 25% of the total budget produced significantly more than 25% of total programme grants. However, a more important determinant of VfM is the effectiveness of REL spend in delivering REL-specific objectives and the added value to the other components of the programme. The latter is critical in justifying spending 25% rather than a more usual (anecdotal) 10% – 15% on REL. Taking a broad definition of REL, this component accounts for 18% of SEATTI total spend[104].
[104] SEATTI audited accounts 2016. Linking & learning, exchanges, research and portal components of spend.
The evidence from preceding sections of this report suggests that while REL spend has generally been efficient, it has been less effective than hoped in terms of adding value to the wider programme. There are a number of examples of PRLGs (Yowzit) and other applied REL spend (Amandla.mobi, FSHC) that have added value as intended but the evidence of this section, as well as the country cases, illustrates this was not widespread and systematic. It proved impossible to achieve the joining up of programme activities at country level over a sustained period that would have enabled REL spend to add value as intended. It seems likely that VfM would have been improved by a more targeted, lower REL spend on research grants and greater investment by the FMC in country on joining up components and uptake.
We have argued elsewhere in this report that the additional benefits of the consortium management arrangements are very unlikely to have justified the additional cost. This does not mean there were no additional benefits from bringing in a research organisation for overall programme management. IDS played a valuable role in developing (and in many cases leading on) strategies, engaging discussions around the ToC and the logframe, and providing intellectual input. Any successful management team should certainly include these functions. However, the lesson to be drawn is that the MAVC consortium arrangements led to paying a high price (in resources spent and conflict between IDS, Ushahidi and Hivos objectives) as well as inefficient use of these intellectual resources by the consortium.
# Findings and Lessons: Process
## What lessons on efficiency, effectiveness and co-ordination can be learned from the multi-donor funding and management arrangements for MAVC? (EQ 1)
This section addresses the issue raised in the original ToR of whether bringing together four funders for a common purpose improved or hindered the success of MAVC. The DFID MAVC Business Case presented the following arguments for and against the multi-funder option that was subsequently selected (see Box 1 below):

Box 1: DFID Business Case arguments for and against a multi-funder programme

Why?
- Helps mobilise funds from a range of donors (e.g. the US, Sweden and Omidyar Network already committed in principle, and other donors could join in future).
- Influence policy and practice with other donors.
- Leverage expertise & know-how from funders already active in this field (Omidyar) for better programmes.
Why not?
- Risk of not fully sharing programme and policy objectives.
- Potentially higher transaction costs associated with design and implementation than bilateral effort.

Source: DFID MAVC Business Case Option 2 p. 13
In practice, there was clearly mobilisation of funds from a range of donors. However, there is very little evidence that the combination of donors increased the ability of MAVC to influence developing country policy and practice. Donor country offices were not involved in supporting any of the five grants that the FMC MEL team identified as contributing to policy change, for example (discussed in Section 3.3). It is also the case that while knowledge was shared among donors during the design phase, this benefit was outweighed by implementation with different organisational cultures, practices and priorities. Factors that drove this are discussed in the following sub-sections. However, the net result is that the potential disadvantages identified in the Business Case - of not fully sharing objectives and higher transactions costs – came to pass.
### Design issues around objectives
The international context at the time of MAVC programme development (following the Arab Spring) led to unrealistic expectations of what tech for governance could deliver. Pressure on USAID to have MAVC ready to be launched by President Obama as a Grand Challenge also encouraged an accelerated programme launch[105]. Prior to this, the donors had spent a year developing a shared ToC that was subsequently refined but not radically changed, and a shared understanding of context, seeing MAVC as a way of supporting OGP at a critical time by bringing together civil society and government.
[105] Sources: David Sasaki, Hewlett Foundation, Bruce Kay, USAID.
However, a lesson for funders is that different organisational cultures, practices and priorities meant that donors had different expectations of how to deliver the ToC. For example, under Output 1 – Reach – the initial ToC activity set states: ‘Larger numbers of tested ideas that utilise mobile and online applications are available. Support and test new ideas. Increase the scale of those showing potential for success.’[106] USAID, DFID and ON had quite different understandings of how best to do this but these were not sufficiently discussed prior to programme implementation[107]. A second lesson is that this increased the risk of the programme but was not mitigated by an extended inception period and a process for reaching a common understanding.
[106] DFID MAVC Business Case p12
[107] Interviews with donor staff involved at the outset.
Unresolved differences in approaches led to combinations of objectives that were not always consistent:
- A large number of competitive one-year grants.
- Funding ‘unusual suspects’ – highly innovative small organisations that would not be funded by mainstream donor programmes.
- Managing reputational risk by funding projects but not organisations and requiring auditing of all grantees[108].
  [108] Until year 4, all donors accepted that external audit was not required for grants below £40,000. DFID changed its view following the appointment of a new Secretary of State.
The South Africa country case study (Annex 6) provides evidence that these objectives were not compatible even for the most experienced and best-resourced country team in our three country studies. The tension between objectives was certainly magnified by weaknesses of the fund management consortium implementing MAVC (discussed below) but it was there from the outset.
Recommendation (second priority):
With complex multi-donor programmes, donors need to leave enough time and put in place and resource a process to reach common expectations for implementation. Ideally, this would be done prior to implementation but, if not, a six month or even one-year inception period is likely to be required.
### Number of countries and grants
As a result of differing donor focus countries, MAVC ended up with a larger portfolio of countries than any one donor would have chosen. Two factors amplified the effects of this decision. Firstly, the limited in-country capacity of the implementing consortium, even in the six tier 1 countries, and secondly, a large number of relatively small grants that had a high administrative burden per USD spent.
A lesson for funders is that the process of multiple funders developing a programme naturally leads to accommodation of multiple organisational objectives and focus countries. As each donor has legitimate objectives accompanying their funding, it can be difficult for the group to critically highlight likely negative implications.
For this reason, we recommend (second priority) that:
Multi-donor programmes use independent review at the design stage to help identify conflicting objectives and independent facilitation to strengthen programme design.
### Management issues
MAVC was the first Grand Challenge for Development that USAID had co-funded but not implemented. Despite agreeing to DFID contracting on behalf of all the donors, the USAID manager at the time felt that their reporting requirements and opportunities to facilitate country office to MAVC country teams meant they, as well as DFID, should be in direct contact with Hivos. This created multiple demands on Hivos and increased transaction costs. This was ultimately resolved by the Steering Committee (SC) removing the requirement for time-consuming donor no-objection to each grant. We recommend (second priority) that:
Multi-donor agreement is secured in advance of implementation to cover what is needed from the fund management consortium, and to decide how contact with the contract holder will be managed to deliver essential reporting metrics for all donors and limit transactions costs for the implementing consortium.
The role of the SC was another area in which different donors held different expectations that were not resolved prior to implementation. USAID expected SC engagement on operational issues, whereas the other donors thought it would have a more strategic role. The lesson for funders is to ensure these issues are surfaced prior to implementation or at least during piloting. The fact that the MAVC SC had independent members helped to mediate disagreements between funders and the implementing consortium. It was a good idea in principle. However, when serious difficulties in hitting KPIs emerged, funders had to take responsibility for their own spend and marginalised the independent SC members, causing them to leave[109]. There were no independent SC members from the second year of MAVC onwards.
[109] Interview with Martin Tisne, ON
With this in mind, we recommend (second priority) that:
Donors clarify the decision-taking powers of programme steering committees with independent members at the outset. This should specifically cover the case where the programme is badly underperforming.
There are a number of features of MAVC that required a significant amount of DFID programme management time: a multi-donor partnership (with limited opportunities for face-to-face meetings), an untried consortium for implementation and a complex, innovative multi-country programme. The DFID allocation of staff time underestimated the programme complexity. Moreover, a high level of staff turnover resulted in six DFID staff leading engagement over the life of the programme – requiring new staff to get up to speed on a complex programme as well as manage it. As noted in DFID annual reviews, the demands of programme management exceeded allocated staff time[110].
[110] Recognised in the 2014 and 2015 AR.
Recommendation (second priority):
The DFID Business Case risk assessment should consider implications for DFID staffing.
### Contracting process for consortia
The 2015 Management Review identified significant problems of silo working by the three consortium members. Yet a lesson for both funders and implementers is that many of the problems around information flows and the process for decision taking could have been identified at the outset if consortium partners had been required to set out how arrangements would work in some detail, and then demonstrate operation in an extended inception phase. Hivos and IDS interviewees have also highlighted that the consortium members had different skills and organisational cultures – an advantage on paper – but presented substantial practical challenges that were not surfaced during procurement and took time to solve.
DFID’s procurement rules meant that MAVC had to be funded as a competitive contract rather than an accountable grant. At the time, with this form of contract, only a limited check on consortium arrangements was done. This has changed, and due diligence checks are much stronger now. However, procurement department staff may not have the contextual knowledge to pick up the difficulty of bridging ‘tech’ and ‘social accountability’ worlds and may need to bring in sector specialists to help.
Recommendation (second priority):
DFID commissioners need to ensure they have a good understanding of governance arrangements in a contracted consortium (taking into account differing organisational cultures, systems and practices) and what donors will need to do to support effective consortium working. Arrangements need to be tested against likely practical challenges at tender and throughout the inception phase.
### Consortia arrangements and the management review
The principal recommendations of the 2015 Management Review[111], undertaken in response to donor concerns, were all implemented, leading to important changes across seven thematic areas[112] including:
[111] A., Bacchetta and C. Beer (2015), MAVC Management Review, Sandstone Consulting, March.
[112] 1. Engagement & Brokering; 2. Configuration of the MAVC Consortium; 3. Leadership & Role of Management Team; 4. Geographic Distribution; 5. Grant Portfolio Management; 6. Accounting & Financial Management; 7. Donor & Consortium Interface.
- Eventual appointment of a Nairobi-based Director and Country Programme Manager with regular monthly consortium management meetings.
- Creation of a cross-consortium leadership team with joint consortium investment committee decision taking on scaling and innovation grants (the largest component of grant spend).
- Replacing country programme teams with six Country Engagement Developers (CEDs) based in tier 1 countries, responsible for networking, engagement, brokering, innovation and scaling partnerships.
- Hivos taking over management of all innovation and scaling grants.
- Strengthening financial management by separating grant and programme management costs, getting each FMC accounting system coded according to the revised budget structure and adopting new financial management processes.
- IDS started to independently manage research grants and was allocated additional resource capacity. This led to an investment in grantee MEL by IDS, although Hivos employed the Grants Manager for innovation and scaling.
While both consortium partner and donor interviewees agree this improved coordination, evidence from these stakeholders and the country case studies indicate that a number of serious limitations remained:
- Hivos, Ushahidi and IDS retained their own budgets and had their own granting targets, generating an institutional incentive to spend their own budgets rather than managing a flexible, pooled budget – under the control of the programme director – to deliver the Theory of Change. This was particularly problematic given that MAVC was deliberately experimental and it was not possible to predict in advance which areas would be most successful.
- Incentives to work together were further weakened by short grant timeframes, overburdened country teams and conflicting organisational objectives. For example, few Hivos grantees were willing to take on the risk of slowing implementation by adding a Practitioner, Research and Learning Grant (PRLG)[113]. A second example is that IDS allocated REL grants against research themes from the Research and Evidence Strategy. As discussed above, this was rarely referred to by other components of MAVC or the donors, and was not mainstreamed throughout the programme. CEDs and non-IDS grantees, who were more likely to be aware of country strategies than the R&E Strategy, found it difficult to see the link between REL and their own work.
  [113] Although the primary reason why IDS could not find sufficient PRGLs within MAVC was the very slow rate of contracting innovation and scaling grants in year 1.
- Financial reporting by Hivos still did not meet DFID’s expectations. Problems arising from the loss of financial management personnel when relocating to Nairobi[114] were eventually solved. More fundamentally, DFID as a whole was starting to ask for much more due diligence on grants. Where Hivos managed large regional funds for donors (e.g. The Global Fund), they re-granted to organisations with strong financial reporting systems. In MAVC, Hivos found themselves unable to draw on strong financial reporting by grantees and did not have systems or capacity to track spending by small, inexperienced organisations without financial management systems. The implications for financial reporting of granting to small organisations were not picked up by Hivos or DFID during procurement.
  [114] A., Bacchetta and C. Beer (2015), MAVC Management Progress Assessment, Sandstone Consulting, September
- Unrealistic expectations of Country Engagement Developers (CEDs) who were expected to combine an unrealistic range of skills (identifying and supporting grantees, navigating tech and governance spaces, enabling grantee M&E and facilitating learning[115]). The large number of grants[116] and focus on meeting granting targets, meant that CED time/grantee was extremely limited – even for a development programme with experienced grantees - and particularly so where incubation of early stage innovation was required. The individual CED hired in Kenya also soon left and Hivos was unable to find a suitably qualified replacement.
  [115] South Africa and Indonesia country case studies and REL review evidence.
  [116] The Annual Narrative Report Year 4 and extension Figure 4, indicates 155 grants across tier 1 countries.
- Resource allocation and incentives skewed the programme to the centre rather than the country teams, even after the shift to tier 1 countries and associated strategies. IDS-supported research and Ushahidi-supported tech activities largely operated in parallel to CEDs, reporting to their own organisations, according to QAS, REL review and country case study evidence. CEDs and programme officers we interviewed felt that the lack of these skills within the country team significantly weakened programme effectiveness. Evidence from other multi-country programmes also suggests that country team capacity is a critical success factor for getting knowledge into practice[117].
  [117] The CDKN evaluation identified this as one of the key success factors – see Yaron et al. (2015).
- Weak in-country coordination and weak collaboration incentives disempowered CEDs and undermined collective impact of all programme strands. Adding Research Outreach Team members in all tier 1 countries by May 2015 and the Country Learning and Engagement Plans produced in late 2016, did help join up research outreach team and CED activities[118], but this only came into being for Year 4 of the programme. Even at this stage, IDS retained management responsibility of ROTs and Hivos for CEDs, and effective coordination depended on the individuals involved, working well in some countries and not at all in others[119].
  [118] South Africa case study and REL review.
  [119] See REL review.
- Engagement with the service delivery side of national and sub-national government remained weak. The proposed use of VNG to bring in local government experience did not work out and FMC experience was primarily with civil society. Government contacts were typically those with a civil society connection (South Africa) or relied on grantee networks (Indonesia and Kenya). This is not to dismiss the linkage with OGP, and the value of the South African community of practice (CoP) combined with CED initiative and hard work, but the lack of capacity to engage service providers identified in early Steering Committee meetings persisted. It would have helped if the programme could have drawn on networks formed by donor country offices, but busy country offices felt no ownership of MAVC and did not engage.
Recommendations (first priority):
Do less (fewer countries, fewer grants) but do it better (properly resourced for incubation and acceleration, sufficient in-country capacity and joining up innovation, scaling and research components). This is likely to involve moving resources from headquarters to country teams and embedding monitoring, evidence, research and learning capacity at the country level.

Programme managers need to scenario test what they are asking country teams to deliver with the teams (if in place) or against realistic skill sets and time availability for proposed roles.
Recommendations (second priority):
Funders should require consortium management arrangements that incentivise re-allocating funds between consortium partners to best deliver the ToC if the evidence supports this. It should be made clear before contracting how this will work in practice.

Funders should note that committing to a longer programme life (such as 2 x 3 or 2 x 4 years if success criteria are met) provides better incentives for consortium partners to invest in common systems, as they have more chance of recouping their investment.

Donors should involve their country offices in design and encourage formal linkages of programmes such as MAVC with country programmes. Programme designers should accept that busy country office staff are very unlikely to commit the necessary time to support without a link to their work plans.
### The assurance assessment
Following the management review, Hivos worked to meet DFID’s grant management and financial reporting requirements. Some DFID concerns remained (noted above) and were increased by ‘a couple of issues’ reported in the March 2016 Hivos external audit[120]. The UK political context was also changing, and a new DFID Secretary of State was appointed in July 2016. The DFID appetite for risk taking by granting to inexperienced civil society grantees working with social media was decidedly lower under the new Secretary of State. In this context, the head of GOSAC requested an assurance assessment (AA) of MAVC grant spending in July 2016, although it took four months to be contracted[121].
[120] Interview with Alan Pettigrew, DFID.
[121] DFID initially hoped that DFID auditors could do the assurance assessment, but this was not possible. It then had to go through the tender process for external consultants and be signed off by the GOSAC head of department.
Prior to the AA, the donors had agreed that grants under £40,000 would not be subject to audit but Hivos was now required to audit all spending. The findings of the AA were that Hivos would need to take some additional measures to ensure its mixture of enhanced financial reviews and grantee audits was ‘sufficient to mitigate the risks of ineligible expenditure inherent to the inexperienced grantees that the MAVC programme has been asked to support’[122]. Hivos was able to implement the additional measures by hiring additional grantee auditors and providing additional financial guidance and reporting. However, putting donor funding on hold (DFID withheld funds to Hivos from September 2016 to the beginning of June 2017[123]) while the AA was contracted, and additional measures implemented, has had some serious consequences.
[122] Moore Stephens (2017), Assessment of Hivos’ grants management systems In the Making all voices count programme.
[123] Other donors released funds from Nov 2016.
For example, evidence from the SA case study indicates that:
- Scaling opportunities were lost (Amandla.mobi).
- Uptake opportunities with government were lost, for example a project brokered with considerable effort by the CED with the SA Treasury.
- Implementation by small grantees such as Grassroot was delayed and growth of the organisation was undermined.
- Programme credibility with government and CSO stakeholders was seriously damaged.
There was also a serious negative impact on the REL component, as so many learning activities were scheduled for the last year of programme implementation.
### Use of the Logframe and management KPIs
The logical framework (logframe) is a required accountability tool for funders and is part of the MAVC management arrangements. The limitations of logframes in complex programmes have been well documented[124] and we have already discussed measuring policy change in Section 3.3.1. Here we identify some lessons to be drawn on logframe use from MAVC for future programming in this area:
[124] For example: Bakewell, O., and A. Garbutt (2005) ‘The Use and Abuse of the Logical Framework Approach: A Review of International Development NGOs’ Experiences’, INTRAC report for SIDA, Critical Study of the Logical Framework Approach in the Basque Country (2011) http://www.betterevaluation.org/sites/default/files/english.pdf
Having an innovation focus makes it particularly difficult to set meaningful output and outcome indicator targets in a complex and changing environment. MAVC followed the recommended approach of revising the logframe mid programme but neither donors nor the FMC felt that the logframe did an effective job of capturing programme performance. We would suggest this, in part, reflects an inherent weakness in the logframe for this kind of programme. For example, it is straightforward to specify the number of citizens reached by interventions but the quality of reach by radio or WhatsApp is not directly comparable. Hence, management reports such as the Annual Review need to be able to draw on a number of evidence sources. Likewise, it is difficult to motivate reflective learning when future funding is contingent on whether numerical targets have been hit. Separate tools such as the QAS are better suited for this purpose – even if logframe indicator targets are set at modest levels in the early years.

The logframe would have been more useful if the Hivos grant tracking and IDS MEL system developed by the end of the programme had been in place by the end of the inception period. Funders were rightly concerned that they could not track performance of the grant portfolio until Year 4. The weakness of the system proposed at the outset and the massive investment in capacity needed should have been identified by the FMC and DFID due diligence. The Hivos assumption that grantees’ own systems would provide all the required information may have been appropriate for some INGOs but was entirely unrealistic for MAVC as a whole.

A separate set of management KPIs across the four logframe outputs was used to monitor delivery with disbursement of funds contingent on achieving a sub-set of KPIs. The interim Programme Director brought in following the management review on 2015 brought a much greater focus on these KPIs and increased the pace of programme implementation. This produced an increase in programme efficiency in terms of declining management costs relative to grant spend. However, we would argue that the combination of relatively small annual grants (median of £48,000[125]), with many grantees needing considerable support across areas in which no CED could have extensive experience, led to a trade-off between efficiency and effectiveness. This can be considered an unintended consequence of KPI use.
[125] Calculated from MAVC MEL data inventory 24 November.

The Indonesia and South Africa country case studies indicate that under pressure to meet grant targets, CEDs were not able to provide support to grantees across the areas required and the other essential brokering and MEL functions. KPI targets on grant disbursement in particular, created a focus on quantity at the expense of quality. Our REL review also found that the focus on hitting operational KPIs late in the programme made it extremely difficult to focus on learning.
In summary, a shift in resources from centre to country team, and fewer but larger grants (with successful small innovation grants being supported, in stages, towards scaling) is likely to have improved effectiveness. This, rather than management KPIs per se, was the problem. Nonetheless, given competing demands on country staff time, a longer no cost extension (one year rather than six months) is likely to have freed up more resources for learning, increased programme effectiveness and so value for money.
## To what extent has MAVC been managed and delivered against the Paris Declaration principles?
The 2005 Paris Declaration[126] outlines the following five fundamental principles for making aid more effective:
[126] http://www.oecd.org/dac/effectiveness/parisdeclarationandaccraagendaforaction.htm
- Ownership: Developing countries set their own strategies for poverty reduction, improve their institutions and tackle corruption.
- Alignment: Donor countries align behind these objectives and use local systems.
- Harmonisation: Donor countries coordinate, simplify procedures and share information to avoid duplication.
- Results: Developing countries and donors shift focus to development results and results get measured.
- Mutual accountability: Donors and partners are accountable for development results.
In many respects, MAVC was well aligned with these principles:
- MAVC work via the Open Government Partnership (OGP) provided a means of building on existing developing country agreements.
- MAVC country plans explicitly noted the relevant government plans and informed granting in most tier 1 countries.
- MAVC coordinated donors and funding on transparency and accountability.
- The objective of supporting sub-national government to close the feedback loop with citizens meant that the focus was very largely on using local planning systems, even where grants were for civil society to improve citizen participation in these systems.
Nonetheless, this evaluation has found that better alignment with the Paris Declaration principles could have been achieved if the following issues had been addressed:
- The FMC was much more experienced in working with civil society than local government and this relative lack of capacity constrained granting to local government (discussed in Section 9.1 above).
- It is important to engage with government users of tech tools that are likely to draw on or compete with grantee tech tools (discussed in Section 3.4.3).
- Securing better engagement of donor country offices in the programme (discussed in Sections 4.1.5 and 9.1.5).
# Sources of Evidence
## People interviewed
List of Informants for Final Evaluation
- Regional Coordinator - TI-Kenya
- Deputy Programme Officer - TI-Kenya
- Executive Director & Co-Founder - Kota Kita
- Knowledge Management Officer - Kota Kita
- MIT- RCT
- MEL manager - IDS
- Senior Fellow, Strategy and Learning - International Budget Partnership
- Senior Anticorruption Advisor - USAID
- MAVC MEL consultant
- Programme Officer - Hewlett Foundation
- Founder Executive Director - TGCI
- Co Founder and Secretary - TGCI
- Director of Programmes - Ushahidi
- Senior Research Associate - IT 4 Change
- REL component manager
- CEO - Hivos
- CIPG
- Programme Director MAVC
- MAVC programme officer and grantee
- M&E Officer - Ushahidi
- Accountability Lab
- Director - Network Society & ROT South Africa
- REL communication officer MAVC
- grantee
- SROs -DFID
- Research Manager - Prakarsa
- Researcher - Prakarsa
- Investment Partner - Omidyar Network
- Tactical Tech
- Regional Research Manager - WWW Foundation
- Director Programme & Learning - Global Initiative
- Research Outreach Team, Lead for Tanzania & Kenya - MAVC
- Director - Ford Foundation
- Head of Research - MySociety
- Research Outreach Team, Lead for Indonesia - MAVC
- Indonesia CED
- REL component director
- Research Manager - Engine Room
- Sr. Anti-corruption and Good Governance Advisor - USAID
- Country Engagement Developer Philippines - MAVC
- Head of Programmes – Hivos

Short conversations were also held with:
- Professor - Boise State University
- Director - Ground Truth Initiative
- South to South Lab Manager - Ushahidi
- WYDII
- Sinergantara
- Innovation Engagement Officer - South to South Lab - Ushahidi

List of Informants for South Africa Case Study
- Project Manager - Grassroot
- Innovation Engagement Officer - Ushahidi
- CEO - YOWZIT
- ROT - Wits University School of Journalism (Network Society)
- Project Manager - Corruption Watch
- Director - Corruption Watch
- Executive Director - Open Democracy Advice Centre
- Manager - Open Up (former Code for South Africa)
- Country Engagement Developer - MAVC
- Programme and Knowledge Coordinator - MAVC
- Director - Black Sash
- Project Manager -Black Sash
- Project Manager - Black Sash
- Director of Community Based Monitoring - DPME
- General Manager - SASSA
- Senior Researcher - Rhodes University
- Platform user - Abahlali baseFreedom Park
- Operations Manager - Amandla.Mobi
- Director - Afesis Corplan
- Advocacy Coordinator AmaBhungane - CSO
- Director - Marikana Support Campaign
- Executive Secretary - CASAC
- Omidyar – Analyst - Omidyar Network
- Coordinator - Action Research Learning
- Coordinator - Action Research Learning
- Staff member - Maokeng Advice office
- Executive Director - Oxfam South Africa
- Director - Qholaqhwe Advice Office (Grant Conduit Community Advice Office)
- Coordinator -Gun Free South Africa
- Faculty member - University of the Free State (Centre for Development Support E&MS Dept)
- Paralegal - Fickburg Advice Office
- Manager - USAASA
- Manager -Media 24 - Slide the City
- Communications Officer - National Department of Communications

List of Informants for Kenya Case Study
- KYGC Community leader - Kwale
- KYGC Community leader - Kwale
- KYGC Programme officer
- KYGC County Government – CBEF Chair person
- KYGC Administrator – County Government
- KYGC Programmes Coordinator - CSO
- KYGC Digital Mapping Expert and Youth Leader
- KYGC Environmentalist and GIS expert
- KYGC Program Coordinator
- LENGGO Coordinator of Programs
- LENGGO Community Representative
- LENGGO Community Representative
- LENGGO Programme officer - CSO
- LENGGO Project Officer - CSO
- LENGGO Programme Officer - CSO
- IBPK Chief, Ketut Location (Nat. Govt)
- IBPK Mercy Kurgut Teacher and CSO
- IBPK Community Member – Elgeyo Marakwet County
- IBPK Uasin Gishu County – Agricultural Stakeholder’s Forum
- IBPK Freedom of Information Network, Nandi County Youth Bunge – Nandi county,
- IBPK Chief Executive officer	Institute for Public Finance Kenya (IPFK)
- IBPK Director, Economic planning, EM County
- IBPK Head of Research and Tech Advisor, IBP Kenya
- IBPK CFI- Program Director, Centre for Innovations
- IBPK Governor, Elgeyo County
- FMC donor Innovations Coordinator
- FMC donor Programme Officer, Africa
- FMC donor Programme Officer - iHUB
- FMC donor Programme Manager, Transparency and Accountability
- FMC donor Partnerships Development Officer – ICT Authority
- FMC donor MAVC - Global

List of Informants for Indonesia Case Study
- Project Implementer – INFEST
- REL component manager
- Indonesia CED
- REL component director
- MEL manager MAVC
- MAVC REL programme officer
- Wonosobo District Administration (government partner/Stakeholder)
- Village Head of Kapencar Village (Government partner/Stakeholder)
- Project Implementer – INFEST
- Wonosobo District Administration (Government partner/Stakeholder)
- Village Head of Kapencar Village (Government Partner/Stakeholder)
- CIPG REL grantee
- Prakarsa REL grantee
- ROT Indonesia
- Open Government Indonesia Secretaria (National level Stakeholder)
- Kota Kita REL grantee
- Executive Office of the President (National level Stakeholder)
- OGI (National level Stakeholder)
- World Bank (International Stakeholder)
- Transparency International Indonesia, (project implementer)
- OD Labs (project implementer)
- Radya Labs (project Implementer)
- Head of District Education Department (regional government partner/Stakeholder
- Head of Junior High School 41 (school partner/Stakeholder)
- Pattiro Semarang (project implementer)
- Sinergantara
- HIVOS (MAVC Country Manager)
- Global Initiative
- BSID – Various team members as part of the endline evaluation
- Corruption Eradication Commission (National level Stakeholder)
- MAVC MEL consultant and mentor
- REL grantee
- WWW Foundation
- WYDII
## Documents reviewed
Final Evaluation
Programme documents
DFID. 2017. Volume 2 Terms of Reference, Evaluation Manager for MAVC: A Grand Challenge for Development (EMU Torso DFID Annex 1). Internal Document.
EMU. December 2013. Inception Report – Evaluation Manager for Making All Voices Count: A Grand Challenge for Development. Internal Document.
MAVC. 10 June 2014. Learning Strategy Version 2.3 Submitted to Steering Committee. Internal Document.
MAVC. October 2014. MAVC Theory of Change. Internal Document.
Chris Underwood. 28 November 2014. Making All Voices Count – Indonesia Country Plan 2014 – 2017. Internal Document.
MAVC. 29 June 2016. MAVC Revised Log-Frame_Completed by FMC_29 June 2016. Internal Document.
MAVC. 15 August 2016. MAVC Year 3 Annual Narative Report (June 2015 – May 2016). Internal Document.
MAVC. June-November 2016. MAVC Semi-Annual Report: Year 4. Internal Document.
MAVC November 2016. Output #1 QAS Scorecard Philippines. Internal Document.
MAVC November 2016. Output #1 QAS Scorecard Indonesia. Internal Document.
MAVC. March 2017. Learning Event Pretoria and Johannesburg, South Africa – More accountable and responsive governance: How do technologies help make it happen? Internal Document.
MAVC. 8 May 2017. CELP Indonesia: Indonesia’s Country-Level Learning Plan for Making	All Voices Count. Internal Document.
MAVC. August 2017. MAVC Organogram. Internal Document.
MAVC. September 2017. DFID MAVC Business Case and Intervention Summary (Making All Voices Count: A Grand Challenge for Development 2012-2016). Internal Document.
MAVC. October 2017. Annex VI Progress traffic lights for MAVC portfolio as at March 2017-1. Internal Document.
MAVC. September 2017. Theory of Change (ToC) Diagram v4-5_final – Document number 3. Internal Document.
MAVC. 2017. Making All Voices Count Website. http://www.makingallvoicescount.org/
Rosie McGee with Duncan Edwards, Gabrielle Minkley and Ciana-Marie Pegus. 2015. MAVC Research and Evidence Strategy. Internal Document.

MAVC publications
Arnold AK. May 2010. ICT for Accountability: Transparency ‘Bottom-Up’. https://blogs.worldbank.org/publicsphere/ict-accountability-transparency-bottom
Brock K. with McGee R. March 2017. More accountable and responsive governance: How do technologies help make it happen? A Learning Event Pretoria And Johannesburg, South Africa. https://opendocs.ids.ac.uk/opendocs/bitstream/handle/123456789/12975/mavc_learning_event_FINAL.pdf
Civic Tech Innovation Network. 2017. Making technologies work for governance, accountability, and civic participation. https://medium.com/civictech
Department of Budget and Management – Republic of the Philippines. 30 October 2017. Budget chief Diokno leads PH delegation at UK dialogue on tech & govt accountability. http://www.dbm.gov.ph/?page_id=22254
Edwards E. December 2016. Open governance – the complexity of scale. http://www.makingallvoicescount.org/blog/open-governance-complexity-scale/
Gurumurthy A, Bharthur D, Chami N. September 2017. Voice or chatter? Making ICTs work for transformative citizen engagement. http://www.makingallvoicescount.org/publication/voice-chatter-making-icts-work-transformative-citizen-engagement/
Hernandez K. September 2017. Why development needs innovation scouts. http://www.makingallvoicescount.org/blog/development-needs-innovation-scouts/
Herringshaw V. December 2017. Addressing failure in ICT-enabled ‘citizen voice – government responsiveness’ interventions: unpacking core assumptions and essential components. http://www.makingallvoicescount.org/publication/addressing-failure-ict-enabled-citizen-voice-government-responsiveness-interventions-unpacking-core-assumptions-essential-components/
Herringshaw V. December 2017. Addressing failure in ICT-enabled ‘citizen voice – government responsiveness’ interventions: unpacking core assumptions and essential components. https://opendocs.ids.ac.uk/opendocs/bitstream/handle/123456789/13442/PLReport_ICTenabled_Online_final.pdf
Ismael Peña-López. 2017. Appropriating Technology for Accountability (XII). So what? - Notes from the Appropriating Technology for Accountability, part of the Making All Voices Count program, organised by Institute of Development Studies and held in Brighton, UK, on 25-26 October 2017. http://ictlogy.net/tag/allvoicescount/
Martin PP. November 2017. Adaptiveness through ‘simplest tools and practices’. http://www.makingallvoicescount.org/blog/adaptiveness-simplest-tools-practices/
McGee R and Gaventa J. November 2011. Shifting Power? Assessing the Impact of Transparency and Accountability Initiatives. https://www.ids.ac.uk/files/dmfile/Wp383.pdf
McGee R and Gaventa J. October 2010. Synthesis Report: Review of Impact and Effectiveness of Transparency and Accountability Initiatives. http://www.ids.ac.uk/files/dmfile/IETASynthesisReportMcGeeGaventaFinal28Oct2010.pdf
McGee R, Edwards D, Minkley G, Pegus CM and Brock K. 2015. Making All Voices Count Research and Evidence Strategy. http://www.makingallvoicescount.org/wp-content/uploads/2015/08/RE-strategy.pdf
McGee R. January 2014. From ‘feedback loops’ to ‘responsive governance’. http://www.makingallvoicescount.org/blog/feedback-loops/
McGee R. January 2014. Something’s stopping all voices from counting…. http://www.makingallvoicescount.org/blog/somethings-stopping-voices-counting/
McGee R. June 2014. Government Responsiveness: A think piece for the Making All Voices Count programme. https://opendocs.ids.ac.uk/opendocs/bitstream/handle/123456789/11582/Think_Piece_on_Government_Responsiveness.pdf?sequence=2
McGee R. June 2014. So there’s a ‘short-code route of accountability’? Really?. Tanzania Learning Event. http://www.makingallvoicescount.org/blog/so-theres-a-short-code-route-of-accountability-really/
McGee R. May 2015. Accountable governance inside out and outside in. http://www.makingallvoicescount.org/blog/accountability-inside-out-outside-in/
McGee R. May 2016. Research, evidence and ethics in ‘civic tech’ – a call to action. http://www.makingallvoicescount.org/blog/research-evidence-ethics-civic-tech-call-action/
Moses M and Shoal S. March 2017. Learning to Make All Voices Count: Pursuing openness through iterative adaptation. http://www.makingallvoicescount.org/blog/learning-make-voices-count-pursuing-openness-iterative-adaptation/
Open Government Partnership. 15 December 2015. Calling All Subnational Reformers! https://www.opengovpartnership.org/stories/calling-all-subnational-reformers
Prieto-Martin P, Faith B, Hernandez K, Ramalingam B. October 2017. Doing Digital Development Differently: lessons in adaptive management from technology for governance initiatives in Kenya. https://opendocs.ids.ac.uk/opendocs/bitstream/handle/123456789/13285/MAVC_DDD_RR_%28Pr4%29Final_WEB.pdf
Roberts T. May 2017. Digital technologies exclude. http://www.makingallvoicescount.org/blog/digital-technologies-exclude/
Siregar F, Usmani ML, Kumaralalita L, Nufaisa H and Putri DA. July 2017. Complaining to improve governance: four stories of complaint-handling systems in Indonesia. http://www.makingallvoicescount.org/publication/complaining-improve-governance-four-stories-complaint-handling-systems-indonesia/
Tech Hubs Week. December. Draft Concept Note 5 – 9 December Nairobi. https://docs.google.com/document/d/15CaThAYuTq9MB6GBYqQNfZrFi-iwzdjZvu24diY7ZmA/edit?ts=57d01aaf
The Engine Room on behalf of MAVC. November 2017. A lot of civil society organisations have a secret. Their tech projects are failing. What does the research tell us? https://researchfindings.tech/
Tshimologong Digital Innovation Precinct, Johannesburg. September 2017. Civic Tech Innovation Network Meeting in South Africa. http://www.makingallvoicescount.org/event/civic-tech-innovation-network-meeting-south-africa/
Walker T. November 2017. What does it take to make research used and useful? We’ve been experimenting. http://www.makingallvoicescount.org/blog/take-make-research-used-useful-weve-experimenting/

Sample Project documents
Transparency International Kenya
TI Kenya. May 2017. MAVC – Practitioner Research and Learning Grant - End of project narrative report template: Transparency International Kenya. Internal Document.
MAVC. August 2017. Final Grant Assessment Report TI Kenya. Internal Document.
Kibukho K, Hiribae S and Amenya D. November 2016. Action Research Report On Improving Complaints Referral Mechanisms For Greater Accountability And Transparency In Kenya. Internal document.
Kibukho K, Hiribae S and Amenya D . April 2016. Inception Report: For Action Research On Improving Complaints Referral Mechanisms For Greater Accountability And Transparency In Kenya. Internal document.
TI Kenya. September 2015. Practitioner Research Grant Concept Note: Focused Call Phase 2 TI Kenya. Internal Document.

Yayasan Kota Kita (YKK)
YKK. April 2016. Research grant Interim Narrative Report: Yayasan Kota Kita. Internal Document.
MAVC. April 2016. Interim Grant Assessment: Yayasan Kota Kita. Internal Document.
Rifai A, Asterina N and Hidayani R. October 2016. Making all Voices Count - Improving the Transparency, Inclusivity and Impact of Participatory Budgeting in Indonesian Cities: Solo, Yogyakarta, Surabaya, Makassar, Bandung and Kebumen. Internal report.
Rifai A. November 2016. Revitalising ‘The Musrenbang’ for Inclusive and Transparent Participatory Budgeting in Indonesian Cities. Event Report National Dissemination Workshop. http://www.kotakita.org/publications-docs/MAVC_%20National_Dissemination_Workshop_Event_Report.pdf
MAVC. December 2016. Final Grant Assessment: Yayasan Kota Kita. Internal Document.
Yayasan Kota Kita. 2016. Practitioner Research and Learning Grant - End of project narrative report: Yayasan Kota Kita. Internal Document.
Yayasan Kota Kita. September 2015. Kota Kita Practitioner Research Learning Grant Proposal: Improving the transparency, inclusivity and impact of participatory budgeting in Indonesian cities. Internal Document.
Rifai A, Asterina N and Hidayani R. December 2016. Making all Voices Count - Improving the Transparency, Inclusivity and Impact of Participatory Budgeting in Indonesian Cities: Solo, Yogyakarta, Surabaya, Makassar, Bandung and Kebumen. http://www.kotakita.org/publications-docs/MAVC__Improving_the_Transparency,_Inclusivity,_and_Impact_of_Participatory_Budgeting_in_Indonesian_Cities.pdf
Nina Asterina. Short reflection. Internal Document.
Feruglio F and Rifai A. January 2017. Participatory budgeting in Indonesia: past, present and future. http://www.makingallvoicescount.org/publication/participatory-budgeting-indonesida-past-present-future/
Yayasan Kota Kita. October 2016. Terms of Reference (ToR) National Workshop: Revitalising ‘The Musrenbang’ for Inclusive and Transparent Participatory Budgeting in Indonesian Cities. Internal Document.

TGCI
MAVC. Summary of Liberia Global Citizens Initiative Project. Internal Document.
TGCI Liberia. Practitioner Research and Learning Grant Concept Note: The Global Citizens’ Initiative. Internal Document.
TGCI Liberia. 2017. End of project narrative report: The Global Citizens’ Initiative (TGCI). Internal Document.
TGCI Liberia. December 2016. Research Uptake Plan. Internal Document.
Hartwell A. June 2017. More accountable systems for tackling sexual abuse and rape in Liberia. http://www.makingallvoicescount.org/blog/accountable-systems-tackling-sexual-abuse-rape-liberia/
Efetobore D and Israel R. January 2017. Liberia Citizen-Government Engagement Project (CGEP): Narrative Progress Report (June 1- December 31, 2016). http://endingsexualabuse.org/wp-content/uploads/2017/01/Final-TGCI-MAVC-Narrative-Porgress-Report-June-1-December-31-2016-1-2.pdf
Efetobore D and Israel R. September 2015. Project Report. http://endingsexualabuse.org/wp-content/uploads/2017/01/TGCI-Project-Report.pdf
Heaner G and Bettencourt G with Hartwell A, Israel R and Efetobore D. September 2017. Making All Voices Count Research Grant Report Using A Developmental Evaluation Approach to Support Citizen Engagement & Reduction Of Child Sexual Abuse (CSA). Internal Report.
TGCI. August 2016. TGCI Memo to MAVC: TGCI Practitioner Research and Learning Grant Application. Internal Document.

Francesca Feruglio
LE (Legal Empowerment). IDS Research Grant Concept Note: LE. Internal Document.
Feruglio F. August 2017. Do more empowered citizens make more accountable states? Power and legitimacy in legal empowerment initiatives in Kenya and South Africa. Research Report. Internal Report.

Global Initiative OGP
Global Integrity. 2016. Interim Narrative Report: Global Integrity. Internal Document.
Gobal Integrity. 2016. Global Integrity Proposal - Making All Voices Count project of support to civil society OGP-related processes: Action research & action learning sub-project. Internal Document.
Global Integrity. 2017. 2nd Interim Narrative Report: Global Integrity. Internal Document.
Global Integrity. September 2016. Learning to Make All Voices Count: First Reflective Learning Workshop - Narrative Report. Internal Report.
Global Integrity. January 2017. Learning to Make All Voices Count: Second Reflective Learning Workshop - Narrative Report. Internal Report.
GI OGP Project Details. Internal Document.
MAVC. 2017. Summary of OGP Third Party Research Grant Project. Internal Document.

Linda Waldman
Waldman L and Hrynick T. Interview Guide - MAVC Research: ICT and Accountability for Health. Internal Document.
Waldman L. March 2016. IDS Research Grant Concept Note – Revised. Internal Document.
Hrynick T and Waldman L. July 2017. ICT-facilitated accountability and engagement in health systems: a review of Making All Voices Count mHealth for accountability projects. http://www.makingallvoicescount.org/publication/ict-facilitated-accountability-engagement-health-systems-review-making-voices-count-mhealth-accountability-projects/
Waldman L, Reed P and Hrynick T. July 2017. Accountability in health systems and the potential of mHealth. http://www.makingallvoicescount.org/publication/accountability-health-systems-potential-mhealth/

Tactical Tech
Ganesh M and Deutch J. November 2014. Risks And Barriers Marginalised Communities In Kenya And South Africa Perceive In Engaging With T4TA Platforms: Design For Research. Internal Document.
Tactical Technology Collective. December 2014. Interim Narrative Report To Making All Voices Count. Internal Report.
Tactical Technology Collective. February 2013. Making All Voices Count: Research Design, Kenya. Internal Report.
Edwards D. Mentoring Plan. Internal Document.
Ganesh M and Deutch J. October 2014. Risks and barriers for marginalised communities in Kenya & South Africa in using T4TA platforms: Proposal For Research. Internal Document.
Ganesh M and Deutch J. September 2014. Researching the flip side of technology for transparency and accountability. Internal Document.
Tessa. August 2015. Review from Tessa for paper: From 'Dirty Toilets' to Thembelihle: Risks and barriers perceived by marginalised housing and urban development rights activists in South Africa in using technology for transparency and accountability. Internal Document.
Ganesh M, Deutch J and Schulte J. July 2016. Privacy, anonymity, visibility: dilemmas in tech use by marginalised communities. https://opendocs.ids.ac.uk/opendocs/ds2/stream/?#/documents/52731/page/1
Ganesh M, Deutch J and Schulte J. July 2016. Privacy, anonymity, visibility: dilemmas in tech use by marginalised communities. Summary, findings and reflections. https://opendocs.ids.ac.uk/opendocs/handle/123456789/12109
Ganesh M and Deutch J. October 2015. The Möbius Strip: How LGBTQ Kenyans use technology to negotiate visibility and anonymity. https://tacticaltech.org/media/files/KenyaSummary_Oct19_0.pdf
Deutch J and Ganesh M. 2015. Being LGBTQ Online and Offline in Kenya. http://giswatch.org/en/country-report/sexual-rights/kenya

MIT Philippines
MIT GOV/LAB. August 2017. Research Grant Amendment Request. Internal Document.
MAVC. September 2015. REL Research Proposals for Donor Group No-objection. Internal Document.
MIT GOV/LAB. July 2016. MIT GOV/LAB Interim Narrative Report. Internal Document.
MIT GOV/LAB. April 2017. MIT GOV/LAB Interim Narrative Report. Internal Document.
MIT GOV/LAB. January 2017. Research Uptake Plan: Better together? Examining the effect of civic education for local officials and citizens on local government responsiveness and citizen engagement. Internal Document.
Notes on MIT. Internal Document.
MAVC Revised Plan - memo Jan 2017 (ZIP Document). Internal Document.
MIT GOV/LAB. July 2016. Research Uptake Plan: Representation or Cooptation? Examining the Effects of Community Leadership Training in the Philippines (MAVC grant 15/327). Internal Document.
MIT GOV/LAB. January 2017. MIT GOV/LAB Interim Narrative Report. Internal Document.
MIT GOV/LAB. March 2016. Research Grant MIT – amended (PA 12035). Internal Document.
MIT GOV/LAB. Email exchange: MAVC interim report. Internal Document.
January 2017. Revised plan for MIT MAVC grant, Study of SA Councillors. Internal Document.
Jamie Goldberg. February 2016. Research Proposal entitled ‘Representation or Cooptation? Examining the Effects of Community Leadership Training in the Philippines (under the direction of Prof. L. Tsai). Internal Document.
MIT GOV/LAB. August 2016. MIT GOV/LAB: Response Clarifications to MAVC Interim Report. Internal Document.

Perkumpulan Prakarsa
Prakarsa. June 2017. Documenting the Adaptive Learning Journey: Perkumpulan Prakarsa. Internal Document.
MAVC. June 2017. Interim Grant Assessment: Perkumpulan Prakarsa. Internal Document.
Prakarsa. August 2016. PRL Grant Proposal: Perkumpulan Prakarsa. Internal Document.
Prakarsa. 2017. Reflection Journal: Bojonegoro Research Team. Internal Document.
Prakarsa. 2017. Reflection Journal: Open Government Research Process in DKI Jakarta. Internal Document.
Prakarsa. 2017. Reflection Journal: Makassar Research Team. Internal Document.
Prakarsa. August 2017. Documenting the Adaptive Learning Journey: Perkumpulan Prakarsa. Internal Document.
Prakarsa. April 2017. Documenting the Adaptive Learning Journey: Perkumpulan Prakarsa. Internal Document.
Prakarsa. 2017. Qualitative Evidence Collected. Internal Document.

Network Society
de Lanerolle I, Walton M and Schoon A. November 2015. Revised Research Proposal ‘Yesterday’: daily mobile-centric communications practices in South Africa. Internal Document.
Wits University. December 2016. IDS Interim Narrative Report: Network Society Lab, University of Witwatersrand (Grant ref 15306). Internal Report.
MAVC. January 2017. Interim Grant Assessment: Network Society Lab, University of Witwatersrand. Internal Document.
January 2017. Planned outputs. Internal Document.
 ‘Yesterday’. 31 March 2016. 1st report – draft – idl. Internal Document.
‘Yesterday’. ‘Yesterday’ Research Output. Internal Document.
de Lanerolle I, Schoon A and Walton M. 20 August 2017. IZOLO - Mobile diaries of the less connected (IDS report draft v3). Internal document.
Tony Roberts. August 2017. Izolo: Mobile Diaries of the Less Connected – Peer Review Feedback. Internal Document.

South Africa Case Study
South-Africa specific
MAVC. 2014. MAVC South-Africa Country Plan – Supporting innovations that promote citizen voice
and government responsiveness for improved service provision at local level.
MAVC. 2016. Learning Plan South-Africa.

Amanla.mobi
AM. Proposal Documents. Internal document.
AM. Campaigns trackers. Internal document.
AM. How We Work Poster. Internal document.
AM. 2015. Final Narrative Report. Internal document.
AM. 2017. Concept Note Research Grant. Internal document.
AM. 2017. MAVC Narrative Report Assessment (Interim). Internal document.
AM. 2017 Research Grant Interim Narrative Report. Internal document.
Byrne, D. 2016. Narrative Report: MAVC Partner Name. Internal document.
MAVC. 2015. Grant Assessment Form. Internal document.
MAVC. 2015. Contracts with Hivos. Internal document.
MAVC. 2015. Monitoring Visits Reports. Internal document.
MAVC. 2017. Terms of Reference for Amanla.mobi. Internal document.

Black Sash Trust
BST. Proposal Documents. Internal document.
BST. 2016. Partner Visits in Johannesburg, Cape Town (South Africa) and Maputo (Mozambique). Internal document.
BST. 2016. Community-Based Monitoring Report.
BST. 2017. Report on three citizen-based monitoring meetings. Internal document.
BST. 2017. Final Narrative Report. Internal document.
BST. 2017. MAVC Narrative Report Assessment (Interim). Internal document.
MAVC. 2014. Due Diligence Assessment Form. Internal document.
MAVC. 2014. Black Sash Site Visit Report. Internal document.
MAVC. 2015. Monitoring Visits. Internal document.
MAVC. 2017. Monitoring Visits. Internal document.
MAVC. 2016. Assessment Form – Investment Committee. Internal document.
MAVC. 2016. Contracts with Hivos. Internal document.

Corruption Watch
CW. Proposal Documents. Internal document.
CW. Stakeholder Analysis Documents. Internal document.
CW. LogFrame. Internal document.
CW. 2017. Final Narrative Report. Internal document.
CW. 2017. Evaluation of the Bua Mzansi Campaign. Internal document.
CW. 2017. MAVC Narrative Report Assessment (Final). Internal document.
MAVC. 2016. Assessment Form – Investment Committee. Internal document.

Free State Housing Campaign
FSHC. Proposal Documents. Internal document.
FSHC. Baseline Report for the Free State Housing Campaign. Internal document.
FSH. Policy brief. Internal document.
FSH. Working Ideas and Budget. Internal document.
FSH. Ushahidi Tech Assessment. Internal document.
FSH. Introductory Guide to Participatory Action Research. Internal document.
FSH. Findings Reports from Participatory Action Research. Internal document.
FSH. Outcome, activity and output matrix. Internal document.
FSH. DUE DILIGENCE REPORT FOR THE QHOLAQHWE ADVICE CENTRE and THE FREE STATE HUB OF ACAOSA. Internal document.
FSH. Monitoring Visits Reports. Internal document.
FSH. Milestone achievements. Internal document.
FSH. 2017 MAVC Narrative Report Assessment. Internal document.
FSH. 2017. Triangulation Focus Group. Internal document.
FSH. 2017. Interim Narrative Report. Internal document.
FSH. 2016. Free State Community Advice Offices Housing Campaign Inception Workshop.
FSH. 2016. Notes from the Campaign Reflection. Internal document.
MAVC. Grant Agreement for Free State Housing Campaign. Internal document.
MAVC. 2017. Terms of Reference for Free State Housing Campaign. Internal document.

Grassroot
Grassroot. Proposal Documents. Internal document.
Grassroot. ANNEX B: CASE STUDY OF ABAHLALI BASE-FREEDOM PARK. Internal document.
Grassroot. Gender balance spreadsheet. Internal document.
Grassroot. 2017. Monitoring Visits. Internal document.
Grassroot. 2017. MAVC Narrative Report Assessment (Final). Internal document.
Grassroot. 2017.Tringulation Interviews. Internal document.
Grassroot. 2016. Partnership Agreement between Grassroot and Abahlali baseMjondolo. Internal document.
Grassroot. 2014. Due Diligence Assessment Form. Internal document.
MAVC. 2015. Contracts with Hivos. Internal document.

Kenya Case Study
Kenya specific
Country Government of Elgeyo Marakwet. 2013. Country Integrated Development Plan 2013-2015 (CIDP). http://www.google.co.uk/url?sa=t&rct=j&q=&esrc=s&source=web&cd=2&ved=0ahUKEwjkptX0ibLZAhVLDcAKHSGTCi8QFgguMAE&url=http%3A%2F%2Fcog.go.ke%2Fbest-practices%2Freportss%2Fcategory%2F82-county-integrated-development-plans-2013-2017%3Fdownload%3D147%3Aelgeyo-marakwet-county-integrated-development-plan-2013-2017%26start%3D25&usg=AOvVaw1XCQQjwisFRcHL5AV08CB1
DFID Kenya. June 2012. Operational Plan 2011-2015. Internal Document.
MAVC. November 2014. Kenya Country Plan 2014-2017. Internal Document.
MAVC. 2017. Kenya Closeout Event Programme. Internal Document.
Republic of Kenya. 2013. Kilifi County - First County Integrated Development Plan 2013-2017. http://www.google.co.uk/url?sa=t&rct=j&q=&esrc=s&source=web&cd=1&ved=0ahUKEwi4896zi7LZAhWoDMAKHcsmAckQFggpMAA&url=http%3A%2F%2Fwww.kilifi.go.ke%2Flib.php%3Fcom%3D6%26res_id%3D62&usg=AOvVaw03Jjtz4O94y4NMlNg72pHs
Prieto-Martin, P., Faith, B., Hernandez, K. and Ramalingam, B., 2017. Doing Digital Development Differently: lessons in adaptive management from technology for governance initiatives in Kenya.
Republic of Kenya. 2013. County Government of Kwale – First County Integrated Development Plan 2013. http://www.google.co.uk/url?sa=t&rct=j&q=&esrc=s&source=web&cd=1&ved=0ahUKEwjS8azCjrLZAhULDcAKHd4dDpcQFggpMAA&url=http%3A%2F%2Fwww.kwalecountygov.com%2Fapps%2Findex.php%3Foption%3Dcom_phocadownload%26view%3Dcategory%26download%3D327%3Acidp2013-2017%26id%3D9%3Abudgets&usg=AOvVaw1vcPfGnPJ5QOv9HgBqGkgP

International Budget Partnership Kenya
IBP. 2016. Concept Paper on Promoting Open Government in Kenya for Making All Voices Count. Internal Document.
IBP. 2017. Report of Factual Findings to the Directors of International Budget Partnership in Respect of the Expenditure Verification of the Grant for Making all Voices Count: A Grand Challenge for Development.
IBP. 2016. PAM Assessment. Internal Document.
IBP. Full Budget. Internal Document.
IBP. Financial Plan. Internal Document.
MAVC. 2017. End of Project Narrative Report (IBP). Internal Document.

Kwale Youth and Govenance Consortium
KYGC. 2016. PAM Assessment. Internal Document.
KYGC. Exit Interview Notes. Internal Document.
KYGC. Budget. Internal Document.
KYGC. Financial Report. Internal Document.
KYGC. Interim Financial Report. Internal Document.
KYGC 2016. Interim Narrative Report Assessment. Internal Document.
KYGC. Narrative Report. Internal Document.
KYGC. Interim Report Resubmission Assessment. Internal Document.
KYGC. M&E Plan. Internal Document.

Locals Empowerment for Good Governance
LONGGO. 2016. PAM Assessment. Internal Document.
LONGGO. 2016. Annual Report. Internal Document.
LONGGO. 2016. Narrative Report. Internal Document.
MAVC. 2017. Notes for LENGGO Exit Interview. Internal Document

Indonesia Case Study
Indonesia specific
Anggriani N. 17 February 2017. Indonesia’s Village Law: A Step Toward Inclusive Governance. https://asiafoundation.org/2016/02/17/indonesias-village-law-a-step-toward-inclusive-governance/
Bojonegoro Institute. 2016. Endorsement letter to OGP Steering Committee. https://www.opengovpartnership.org/sites/default/files/BI%20Eng.pdf
Bojonegoro Regency Government. 2016. Open Government Sub-National Action Plan Bojonegoro Regency Government Year 2016-2017. https://www.opengovpartnership.org/sites/default/files/Bojonegoro_Subnational_Action-Plan_2016-17_ENG_0.pdf
Chris Underwood. 28 November 2014. Making All Voices Count – Indonesia Country Plan 2014 – 2017. Internal Document.
Coca N. 8 February 2016. Indonesia’s Anti-Corruption Fight. https://thediplomat.com/2016/02/indonesias-anti-corruption-fight/
Dinas Komunikasi, Informatika dan Statistik Provinsi DKI Jakarta. 2017. Jakarta Open Data. http://data.jakarta.go.id/
Karen Brock, Rosemary McGee and Marjan Besuijen. November 2014. MAVC Strategy synthesis: Enabling Citizen Engagement and Accountable, Responsive Government. Internal Document.
Hrynick T and Waldman L. July 2017. ICT-facilitated accountability and engagement in health systems: a review of Making All Voices Count mHealth for accountability projects. http://www.makingallvoicescount.org/publication/ict-facilitated-accountability-engagement-health-systems-review-making-voices-count-mhealth-accountability-projects/
Kedesa website. 2017. http://kedesa.id/id_ID/
MAVC. 10 May 2017. MAVC Data Inventory. Internal Document.
MAVC. 2017. Indonesia MAVC – Country Learning. Internal Document.
MAVC. 2017. OGP Initiatives in CSO. Internal Document.
MAVC. 2017. QAS 3 Scorecards Indonesia – commented by AA. Internal Document.
MAVC. 2017. QAS Scorecards Indonesia – commented by RE. Internal Document.
MAVC. 28 April 2017. Learning Agenda Indonesia: Indonesia’s Country-Level Learning Plan for Making All Voices Count (MAVC). Internal Document.
MAVC. 6 December 2017. Learning to Make All Voices Count: Lessons for OGP, donors, and practitioners. http://www.makingallvoicescount.org/publication/learning-make-voices-count-lessons-ogp-donors-practitioners/
MAVC. 6 October 2017. Identifying Criteria for Assessing Innovation in Project and Portfolio. Internal Document.
MAVC. 8 May 2017. CELP Indonesia: Indonesia’s Country-Level Learning Plan for Making	All Voices Count. Internal Document.
MAVC. November 2016. QAS Scorecards Indonesia – commented by CS. Internal Document.
Nurhayati Y. 2017 in Luttrell et al 2016. Background stats on ICT: Annex J The increased use of ICT nationwide. Internal Document.
Nurjanah S and Saputro M. 10 October 2017. WYDII Learning Paper Final: The Dynamic of the ICT Citizen Users in Generating the Government Response. Internal Document.
Nurjanah S and Saputro M. 12 October 2017. Summary MAVC Learning Paper Final: Dinamika Masyarakat Pengguna TIK dalam Mendorong Response Pemerintah. Internal Document.
OGI. 2017. Open Government Indonesia Website. http://www.opengovindonesia.org/
Open Government Partnership. 15 December 2015. Calling All Subnational Reformers! https://www.opengovpartnership.org/stories/calling-all-subnational-reformers
Panto MA. 17 December 2014. Participatory Village Development Planning: Towards Self Reliant Communities. https://www.changemakers.com/makersofmore/competition/nominations/participatory-village-development-planning-towards-self
Pattiro platform http://kedesa.id/id_ID/
Rifai A and Muhajir A. 12 October 2017. MAVC Workshop Presentation: Peran Organisasi Masyarakat Sipil – Mengenal Ruang Kapabilitas dalam Upaya Mendorong Akuntabilitas dan Transparansi. Internal Document.
Saenong IB. 11 November 2015. Linida Story, When Villagers Open Up Local Government. https://www.opengovpartnership.org/stories/linida-story-when-villagers-open-local-government
Satriyo HA. 7 March 2012. Without a Say in Indonesia’s Budget Decisions, Women’s Needs are Left Out. https://asiafoundation.org/2012/03/07/without-a-say-in-indonesias-budget-decisions-womens-needs-are-left-out/
Sinergantara. 2017. Sinergentara Learning Seminar Presentation: Efektifitas Pemanfaatan Teknologi Informasi dan Komunikasi (TIK) untuk Memperkuat Transparansi, Akuntabilitas dan Partisipasi (TAP) serta Bagaimana Keserasian Interaksi Antara Platform Online dan Platform Offline. Internal Document.
Siregar F, Usmani ML, Kumaralalita L, Nufaisa H and Putri DA. July 2017. Complaining to improve governance: four stories of complaint-handling systems in Indonesia. http://www.makingallvoicescount.org/publication/complaining-improve-governance-four-stories-complaint-handling-systems-indonesia/

Transparency International Indonesia
Cek Sekolah-Ku 2017. Cek Sekolah-Ku Website. http://ceksekolahku.or.id/
AirPutih. 2017. Cek Sekolahku. http://www.airputih.or.id/portofolio/cek-sekolahku
Cek Sekolah-Ku App. 2017. Applikasi Cek Sekolah-Ku. https://play.google.com/store/apps/details?id=id.or.ceksekolahku&hl=en
KPK. 2016. Cegah Korupsi Sektor Strategis, KPK Siapkan Aplikasi JAGA. https://www.kpk.go.id/id/berita/siaran-pers/3579-cegah-korupsi-sektor-strategis-kpk-siapkan-aplikasi-jaga
KPK. 2017. JAGA App. https://play.google.com/store/apps/details?id=id.or.checkmy&hl=in
MAVC. 2015. Assessment CSK Semester 1. Internal Document.
MAVC. 2017. Check My School – Transparency International. Internal Document.
MAVC. 2017. Check My School – Exit interview notes DC. Internal Document.
MAVC. 16 February 2017. Exit Interview note taking. Internal Document.
MAVC. 6 January 2017. Final Report MAVC – CSK. Internal Document.
MAVC. 2017. Final Summary Notes for CSK. Internal Document.
MAVC. 1 November 2016. Monitoring Visit Skhola. Internal Document.
MAVC. 2017. MSC Indonesia TI School Final Commented. Internal Document.
MAVC. 2017. MSC Indonesia TI School Final. Internal Document.
MAVC. 2017. Project Summary TI Indonesia Cek Sekolah-Ku. Internal Document.
Pemerintah Kota Semarang. 2016. Lapor Hendi. http://laporhendi.semarangkota.go.id/
TII. 2014. Proposal Cek Sekolah-Ku: Improving School Condition and Governance through Participatory Monitoring of School Performance. Internal Document.
TII. 2017. CSK PAR report layout. Internal Document.

INFEST
17 January 2016. Budget untuk HIVOS MAVC Final. Internal Document.
Afif A. 21 July 2017. Open Data Keuangan Desa. https://www.youtube.com/watch?v=EaB8BIHJvB4
Ibad. December 2016. New Activity. Internal Document.
INFEST Yogyakarta. 2017. Final General Report compiled – RE feedback. Internal Document.
INFEST Yogyakarta. 23 October 2017. Testimoni KPK Tentang Aplikasi MitraDesa dan Inisiasi Open Data Keuangan Desa di Wonosobo. https://www.youtube.com/watch?v=2v6b6d93U_E
INFEST Yogyakarta. 13 July 2017. Inisiatif Open Data Keuangan Desa di Wonosobo. https://www.youtube.com/watch?v=XBIE-Mwr0fA
INFEST. 2016. Proposal INFEST for MAVC final. Internal Document.
INFEST. 2015. Monitoring, Evaluation and Learning Plan INFEST Yogyakarta. Internal Document.
INFEST App. 2017. Applikasi Mitra Desa. https://play.google.com/store/apps/details?id=com.infest.mitradesa&hl=in
INFEST. 2017. Wonosobo Jadi Daerah Model Percontohan ‘Open Data Keuangan Desa’. https://sekolahdesa.or.id/wonosobo-jadi-daerah-model-percontohan-open-data-keuangan-desa/
Innovation Fund. August 2015. MAMPU Innovation Fund: Exploring New Ways of Problem Solving, Mid Term Update. Internal Document.
MAVC. 2016. Appreciative Village Planning Module. Internal Document.
MAVC. October 2016. Assessment Midterm INFEST. Internal Document.
MAVC. 27 October 2016. INFEST Monitoring Visit. Internal Document.
MAVC. 2016. MAVC Core Learning and ME RE. Internal Document.
Mitra Desa. 2017. Tentang Mitra Desa. https://www.mitradesa.id/tentang-mitra-desa/
Open Data Desa. 2017. Open Data Desa Kabupaten Wonosobo website. https://datadesa.wonosobokab.go.id/
Pattiro. December 2016. Pattiro Notes for report. Internal Document.
Pattiro. August 2016. Best Practices in Village Law Implementation. Internal Document.
Pattiro. 2016. Village Research Design: A Study on Village. Internal Document.

WWW Foundation’s Open Data Lab Jakarta
2017. Annex 01 – Summary of 3 innovation projects. Internal Document.
MAVC. 4 October 2017. Antya Widita: The social innovator using open data for positive social change. http://www.makingallvoicescount.org/blog/antya-widita-social-innovator-using-open-data-positive-social-change/
Open Data Lab. 2017. Tech Hub Proposal. Internal Document.
Open Data Lab. 2017. Revised and Final MAVC OD Hive Budget. Internal Document.
Open Data Lab. 2017. Final Interim Report: Innovationg for Open Cities (Innocities). Internal Document.
Open Data Lab. 30 March 2017. DARU: Firefighting at your fingertips. http://labs.webfoundation.org/daru-firefighting-at-your-fingertips/
RadyaLabs. 2017. Radya Labs Website. http://radyalabs.com/

Yayasan Kota Kita (YKK)
Feruglio F and Rifai A. January 2017. Participatory budgeting in Indonesia: past, present and future. http://www.makingallvoicescount.org/publication/participatory-budgeting-indonesida-past-present-future/
Nina Asterina. Short reflection. Internal Document.
Rifai A, Asterina N and Hidayani R. October 2016. Making all Voices Count - Improving the Transparency, Inclusivity and Impact of Participatory Budgeting in Indonesian Cities: Solo, Yogyakarta, Surabaya, Makassar, Bandung and Kebumen. Internal report.
Rifai A. November 2016. Revitalising ‘The Musrenbang’ for Inclusive and Transparent Participatory Budgeting in Indonesian Cities. Event Report National Dissemination Workshop. http://www.kotakita.org/publications-docs/MAVC_%20National_Dissemination_Workshop_Event_Report.pdf
Rifai A, Asterina N and Hidayani R. December 2016. Making all Voices Count - Improving the Transparency, Inclusivity and Impact of Participatory Budgeting in Indonesian Cities: Solo, Yogyakarta, Surabaya, Makassar, Bandung and Kebumen. http://www.kotakita.org/publications-docs/MAVC__Improving_the_Transparency,_Inclusivity,_and_Impact_of_Participatory_Budgeting_in_Indonesian_Cities.pdf
Yayasan Kota Kita. April 2016. Research grant Interim Narrative Report: Yayasan Kota Kita. Internal Document.
Yayasan Kota Kita. 2016. Practitioner Research and Learning Grant - End of project narrative report: Yayasan Kota Kita. Internal Document.
Yayasan Kota Kita. Budget estimation National Dissemination Workshop: Yayasan Kota Kita. Internal Document.
Yayasan Kota Kita. September 2015. Kota Kita Practitioner Research Learning Grant Proposal: Improving the transparency, inclusivity and impact of participatory budgeting in Indonesian cities. Internal Document.
Yayasan Kota Kita. August 2016. Update call. Internal Document.
Yayasan Kota Kita. October 2016. Terms of Reference (ToR) National Workshop: Revitalising ‘The Musrenbang’ for Inclusive and Transparent Participatory Budgeting in Indonesian Cities. Internal Document.
Yayasan Kota Kita Twitter account. 2017. https://twitter.com/kotakitaorg?lang=en
Yayasan Kota Kita Facebook account. 2017. https://www.facebook.com/solo.kota.kita/

Perkumpulan Prakarsa
Lauranti M, Afrina E, Mawesti D, et.al. 2017. Assessment of the Use of e-government by the sub-national Government in Indonesia. http://theprakarsa.org/new/ck_uploads/files/Open%20Government%20Report%20Perkumpulan%20Prakarsa(2).pdf
MAVC and Global Integrity. 2017. Testing the claims of e-government through engagement: A case study from Indonesia. http://www.globalintegrity.org/wp-content/uploads/2017/11/Indonesia_Prakarsa.pdf
Prakarsa. June 2017. Documenting the Adaptive Learning Journey: Perkumpulan Prakarsa. Internal Document.
Prakarsa. June 2017. IDS Budget Former and Revised. Internal Document.
Prakarsa. August 2016. PRL Grant Proposal: Perkumpulan Prakarsa. Internal Document.
Prakarsa. 2017. Reflection Journal: Bojonegoro Research Team. Internal Document.
Prakarsa. 2017. Reflection Journal: Open Government Research Process in DKI Jakarta. Internal Document.
Prakarsa. 2017. Reflection Journal: Makassar Research Team. Internal Document.
Prakarsa. August 2017. Documenting the Adaptive Learning Journey: Perkumpulan Prakarsa. Internal Document.
Prakarsa. April 2017. Documenting the Adaptive Learning Journey: Perkumpulan Prakarsa. Internal Document.
Prakarsa. 2017. Qualitative Evidence Collected. Internal Document.
## Documents referenced in the main report
Bacchetta, A. and Beer, C. (2015). MAVC Management Review, Sandstone Consulting, March.
Bakewell, O., and A. Garbutt (2005) ‘The Use and Abuse of the Logical Framework Approach: A Review of International Development NGOs’ Experiences’.
Befani, B. and Mayne, J. (2014). Process tracing and contribution analysis: A combined approach to generative causal inference for impact evaluation. IDS bulletin, 45(6), pp.17-36.
Chen, B. (2010). Apple Registers Trademark for 'There's an App for That'. Wired. [online] Available at: https://www.wired.com/2010/10/app-for-that/ [Accessed 20 Feb. 2018].
DFID (2009). Building the State and Securing the Peace. Emerging Policy Paper. [online] Available at: http://www.gsdrc.org/docs/open/con64.pdf [Accessed 20 Feb. 2018].
DFID (2011). DFID’s Approach to Value for Money (VfM). Policy Paper. [online] Available at: https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/49551/DFID-approach-value-money.pdf [Accessed 20 Feb. 2018].
DFID (2011) Ethics Principles for Research and Evaluation. [online] Available at: https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/67483/dfid-ethics-prcpls-rsrch-eval.pdf [Accessed 20 Feb. 2018].
DFID (2015). 2010 to 2015 Government Policy: Governance in Developing Countries. Policy Paper. [online] Available at: https://www.gov.uk/government/publications/2010-to-2015-government-policy-governance-in-developing-countries/2010-to-2015-government-policy-governance-in-developing-countries [Accessed 20 Feb. 2018].
Innovating in development: Sharing learning, improving impact Workshop report
de Lanerolle, I., Walker, T. and Kinney, S. (2016). Sometimes it is about the tech: choosing tools in South African and Kenyan transparency and accountability initiatives. [online] Available at: http://www.makingallvoicescount.org/publication/six-rules-thumb-select-tools-transparency-accountability-projects/ [Accessed 20 Feb. 2018].
ECODE (2011). Critical Study of the Logical Framework Approach in the Basque Country. [online] Available at: http://www.betterevaluation.org/sites/default/files/english.pdf [Accessed 20 Feb. 2018].
Eiu.com. (2018). Democracy Index 2017. [online] Available at: https://www.eiu.com/topic/democracy-index [Accessed 20 Feb. 2018].
Edwards, D. and McGee, R. (2015). Opening Governance. IDS Bulletin.
Edwards, D. and McGee, R. (2016). Opening Governance: Glossary. IDS Bulletin
Gaventa J. & Barrett, G. (2010). So What Difference Does It Make? Mapping the Outcomes of Citizen Engagement. IDS working paper 347.
Gladwell, M. (2010). Small Change. The New Yorker. [online] Available at: https://www.newyorker.com/magazine/2010/10/04/small-change-malcolm-gladwell [Accessed 20 Feb. 2018].
Graham, A., Powell, M., Taylor, N., Anderson, D. & Fitzgerald, R. (2013). Ethical Research Involving Children. Florence: UNICEF Office of Research – Innocenti. [online] Available at: https://childethics.com/wp-content/uploads/2013/10/ERIC-compendium-approved-digital-web.pdf [Accessed 20 Feb. 2018].
Greenhalgh, T. (2013). Five biases of new technologies. British Journal of General Practice, 63(613), pp.425-425.
Herringshaw, V. (2017). Addressing failure in ICT-enabled ‘citizen voice – government responsiveness’ interventions: unpacking core assumptions and essential components, Making All Voices Count Programme Learning Report, Brighton: IDS.
Hivos (2013). Hivos and Omidyar to enhance transparency in public institutions with SEATTI. [online] Available at: https://hivos.org/news/hivos-and-omidyar-enhance-transparency-public-institutions-seatti [Accessed 20 Feb. 2018].
HM Treasury (2011). The Green Book: Appraisal and Evaluation in Central Government. London.
HM Treasury (2018). The Green Book: Central Government Guidance on Appraisal and Evaluation. London.
HM Treasury (2011). The Magenta Book: Guidance for Evaluation. London.
ICC/ESOMAR (2016) International Code on Market, Opinion and Social Research and Data Analytics. [online] Available at:https://www.esomar.org/uploads/public/knowledge-and-standards/codes-and-guidelines/ICCESOMAR_Code_English_.pdf [Accessed 20 Feb. 2018].
Kane, R., Levine, C., Orians, C. and Reinelt, C. (2017). Contribution Analysis in Policy Work: Assessing Advocacy's Influence. [online] Available at: http://orsimpact.com/wp-content/uploads/2017/12/Contribution-Analysis.pdf [Accessed 20 Feb. 2018].
Kasper, G. and Marcoux, J. (2014). The re-emerging art of funding innovation. Stanford Social Innovation Review, 12(2), pp.28-35.
Kaufmaan D. and Kraat, A. (2002) Growth Without Governance, World Bank Policy Research Working Paper No 2928.
Lakshman, N. (2003). Political Economy of Good Governance for Poverty Alleviation Policies. ADB Economics Working Papers. [online] Available at: https://www.adb.org/publications/political-economy-good-governance-poverty-alleviation-policies [Accessed 20 Feb. 2018].
Mayne, J. (2001). Addressing Attribution Through Contribution Analysis: Using Performance Measures Sensibly. The Canadian Journal of Program Evaluation, [online] 16(1), pp.1-24. Available at: https://pdfs.semanticscholar.org/7501/501b7fb4ee9f31985540f3e1ca661f262ec6.pdf [Accessed 20 Feb. 2018].
Mayne, J. (2008). Contribution analysis: An approach to exploring cause and effect. The Institutional Learning and Change Initiative. [online] Available at: http://www.betterevaluation.org/sites/default/files/ILAC_Brief16_Contribution_Analysis.pdf. [Accessed 20 Feb. 2018].
McNulty, E. (2008). How to Balance Strategy Development and Execution. Harvard Management Update. [online] Available at: https://hbr.org/2008/02/talking-with-robert-sutton-1 [Accessed 20 Feb. 2018].
McGee, R., Edwards, D., Minkley, G., Pegus, C. and Brock, K. (2014). Making All Voices Count: Research and Evidence Strategy. Institute of Development Studies.
Moore, S. (2017), Assessment of Hivos’ grants management systems In the Making all voices count programme.
Nesta.org.uk. (2018). Nesta - the innovation foundation. [online] Available at: https://www.nesta.org.uk/ [Accessed 20 Feb. 2018].
Nesta.org.uk. (n.d.). Innovation Flow Chart. [online] Available at: https://www.nesta.org.uk/sites/default/files/innovation_flow_chart.pdf [Accessed 20 Feb. 2018].
OECD (2005). The Paris Declaration on Aid Effectiveness and the Accra Agenda for Action. online] Available at: http://www.oecd.org/dac/effectiveness/34428351.pdf [Accessed 20 Feb. 2018].
Peixoto, T. and Fox, J. (2016). When does ICT-enabled citizen voice lead to government responsiveness?.
Pinto, J.K. and Slevin, D.P. (1987). Critical factors in successful project implementation. IEEE transactions on engineering management, (1), pp.22-27.
Punton, M. and Welle, K. (2015). Straws-in-the-wind, Hoops and Smoking Guns: What Can Causal Process Tracing Offer to Policy Studies?. Centre for Development Impact, [online] (10), pp.1-8. Available at: https://opendocs.ids.ac.uk/opendocs/bitstream/handle/123456789/5997/CDIPracticePaper_10.pdf;jsessionid=AA39E39F8196A5B4C85B0D8B6CEB3474?sequence=1.
Researchfindings.tech. (2018). Tech for transparency and accountability - what does the research say?. [online] Available at: https://researchfindings.tech/ [Accessed 20 Feb. 2018].
Stern, E., Stame, N., Mayne, J., Forss, K., Davies R., Befani, B. (2012). Broadening the Range of Designs and Methods for Impact Evaluations: A Report of a Study Commissioned by the Department for International Development. Working Paper 38. [online] Available at: https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/67427/design-method-impact-eval.pdf [Accessed 20 Feb. 2018].
The Harvard Business Review. (2008). Talking with Robert Sutton. [online] Available at: https://hbr.org/2008/02/talking-with-robert-sutton [Accessed 20 Feb. 2018].
The Economist (2017). Democracy Index 2017. Intelligence Unit. [online] Available at: https://www.eiu.com/topic/democracy-index [Accessed 20 Feb. 2018].
The Engine Room. (2006). Alidade interactive guide for finding technology tools. [online] Available at: https://www.theengineroom.org/alidade-interactive-guide-for-finding-technology-tools/ [Accessed 20 Feb. 2018].
Tversky, A. and Kahneman, D. (1973). Availability: A heuristic for judging frequency and probability. Cognitive Psychology, 5(2), pp.207-232.
UNEG (2008) Ethical Guidelines for Evaluation. UNEG Guidance Documents. [online] Available at: http://www.unevaluation.org/document/detail/100 [Accessed 20 Feb. 2018].
Usaid.gov. (2018). DIV's Model in Detail. [online] Available at: https://www.usaid.gov/div/model [Accessed 20 Feb. 2018].
Vogel, I., Minkley, G., and Chowdhury, S. (2017) Innovating in development: Sharing learning, improving impact. Workshop report. Ideas to Impact. [online] Available at: http://www.imcworldwide.com/wp-content/uploads/2017/05/Innovating-in-development-report.pdf [Accessed 20 Feb. 2018].
Walker, T. (2018). Alidade: an interactive tool to help you bring technology strategically into your project. [online] The Engine Room. Available at: https://www.theengineroom.org/alidade-interactive-guide-for-finding-technology-tools/ [Accessed 20 Feb. 2018].
Wang, H., He, J., Kim, Y. and Kamata, T., (2011). Municipal solid waste management in small towns: An economic analysis conducted in Yunnan, China.
Westhorp, G. (2014). Realist impact evaluation: an introduction. London: Overseas Development Institute, pp.1-12.
White, H. and Phillips, D. (2012). Addressing attribution of cause and effect in small n impact evaluations: towards an integrated framework. New Delhi: International Initiative for Impact Evaluation.
Yin, R. (2009). Case Study Research: Design and Methods. Applied Social Research Methods, 5.

# Appendix I: Communications Review
MAVC website analytics reports
The evaluation team has received basic monthly Google Analytics reports in .csv spreadsheet format relating to the MAVC website from August 2016 to October 2017. More comprehensive reports are available for August-October 2017. Reports from earlier in the programme timeline are unavailable, as had Google Analytics tracking was not embedded. Online tools such as Google Analytics and Twitter analytics offer real-time visualised data, from which user behavior insights can be incorporated in real time. However, as Google Analytics code was not embedded on the MAVC website until later in the programme, much user activity on the MAVC site cannot be analysed in detail. Based on available data, we can see that:
- The site has roughly 3,000-4,000 ‘sessions’ per month. March 2016 had the highest number of sessions, at 7,166.
- From August-October 2017 data, the top countries by numbers of visitors are the UK, US, Philippines, Kenya, South Africa, and Indonesia.
- Twitter creates roughly 300-400 referrals to the MAVC website per month, followed by Facebook at 50-100. Other notable sources of referrals are usaid.gov, sida.se, ngopulse.org, and ids.ac.uk, likely due to a combination of job ads, links, and communications materials published on those sites mentioning the MAVC programme.
- While the site is visually appealing, it arguably suffers some accessibility-related issues. Navigation can be more clearly supported, text messages can be simplified and clarified, and the aims and activities of the MAVC programme can be more explicit. Concepts such as scaling grants and innovation competitions can be defined, particularly as the site is catering to countries where English may not be a first language.
- Note: programme teams can save PDF versions of visualised monthly Google Analytics reports and provide these monthly reports directly to donors and evaluation teams, rather than providing raw data sets in .csv spreadsheet format. These visualised reports are free and can be exported and shared easily. Similar analytics reports are available with Twitter and email management application MailChimp, which was used for MAVC e-newsletters. These can similarly be shared, along with brief synthesis reports from a programme communications team to offer a concise analysis of performance of each online account and how they relate to one another.
MAVC publications on IDS OpenDocs database
MAVC research documents are published to the IDS OpenDocs e-repository of development research. Within the OpenDocs e-repository, 117 documents are tagged within the ‘Making All Voices Count’ category. Data relating to these documents, such as number of downloads and citations, is available with online application Google Scholar, which enables users to search for scholarly literature. Based on data updated October 2017, some summarising points are below:
- The 20 most-downloaded articles each have 1,100-5,600 downloads, mostly from the UK and US.
- The 2 most-downloaded articles, The Dark Side of Digital Politics and When Does ICT-Enabled Citizen Voice Lead to Government Responsiveness?, are also the most-cited among other online documents tracked by Google Scholar. These were both published in the January 2016 IDS Bulletin issue 47.1 entitled Open Governance. The relatively high number of downloads and citations of these documents may have resulted from coverage on Twitter and Facebook or from additional traffic on other sites where those documents are published, including Eldis, Mendeley, and the World Bank Open Knowledge Repository, though more detailed analysis is not possible with this data.
- Some additional basic data relating to number of Twitter mentions and views on Mendeley of MAVC research documents is available using the free version of online application Altmetric. These show relatively high numbers of Twitter mentions of the two most-downloaded documents, with mentions appearing particularly on IDS-related Twitter accounts.
Twitter analytics
The evaluation team received free Twitter analytics reports dating back to May 2016. Based on these analytics, some summarising points are below:
- As mentioned earlier, according to MAVC website Google Analytics reports, Twitter creates 300-400 referrals to the MAVC website per month, the most effective social referral channel.
- Some keywords used in the top tweets in this period include technology, citizens, marginalised, participatory, accountability, disaster (risk reduction), digital and innovation.
- There has been a notable recent increase in tweets and retweets from the MAVC account since August 2017, resulting in higher numbers of new followers and total impressions of tweets. However, conclusions are difficult to draw from available analytics reports.
MailChimp analytics
The evaluation team has received a .csv file with topline data relating to emails sent by the MAVC team to its newsletter community through the email management application MailChimp. From late 2013 to present, the newsletter community has grown from roughly 1,000 to 3,000+ members, with emails sent intermittently one to three times per month. The open rate of these emails is roughly 20-30%. Not mentioned in this data is the extent to which these newsletters created any more in-depth engagement (beyond numbers such as emails opened and links clicked) with audiences, such as follow-up replies, or questions from audience members.
As mentioned in a December 2017 newsletter, two more newsletter issues will be released in January 2018 to share our last publications, including synthesis of key programme messages and report of lessons learned about how to support work in this field. These could also be good opportunities to announce a possible closing audience survey of MAVC’s online communication. As MAVC has been conceptualised by nature to have an active online communication component, the conclusion of the programme is a good opportunity to seek summary reflections from audience members, particularly from those who have been part of the MAVC community of practice since programme launch.
Implementation teams should maintain analytics reports and syntheses/analyses of those reports as standard for all their online channels, and the Comms person/team should handle this. If the analytics/synthesis reports have not been maintained and assessed by the programme team throughout, then the job of an evaluation team is quite challenging.
# Appendix 2: Summary Descriptions of Grants
This Appendix provides summary descriptions of the grants that were selected for the EMU case studies, country case studies and the REL component.
## Grants for EMU Case studies
Grant name	CK - Caritas Kitui
Project name	Including women in rural governance processes
Country	Kenya
Grant type	Innovation grant
Description	Caritas-Kitui was using a combination of approaches- some reliant on technology, others not - to take women’s voices out of the home and into the public sphere. / Working with rural women’s groups, the project used a range of communications tools such as poetry, songs and competitions to include women’s voices in discussion on public issues and to support women’s participation in government decision-making processes. / The project also trained leaders of women’s groups to take part in interactive sessions at partner radio stations, where they meet with elected members of the County Assembly. / This combination of radio and face to face work aimed to challenge perceptions about women's inclusion in public debate, and provide real opportunities for women to stand up together.

Grant name	WYDII - Women and Youth Development Institute of Indonesia
Project name	A voice to deepen Indonesian Women's democracy
Country	Indonesia
Grant type	Global innovation competition grant
Description	“Suara Kita” (Our Voice) aimed to empower ordinary women to play a role in the shaping of policies and programmes and promotes transparent and accountable relations between village leaders and ordinary citizens. / The project focussed on Tunjungtirto Village and through SMS surveys, and consultative meetings, aimed to increase the participation of women in Tunjungtirto Village's annual planning meeting known as "MosDes." / Through aggregating and reporting on this feedback, the project was meant to provide leaders with greater insight into the issues and concerns of women within the village, and new ideas on how to address these.

Grant name	ICW - Indonesia Corruption Watch
Project name	Confronting e-procurement corruption through open data
Country	Indonesia
Grant type	Scaling grant
Description	Indonesia Corruption Watch (ICW) was expanding its e-Procurement Potential Fraud Analysis Programme to address this challenge. ICW analysed national procurement data and posts its findings on a public website, which was proving to be a powerful tool for tracking irregularities and ensuring that publicly accessible data translates into public understanding of government spending. / The scale up of the programme included supporting Civil Society Organisations, media, government inspectors and procurement officers to make use of the website for investigations of potential fraud in procurement processes. / The project was a unique example of how opening up data could involve multiple actors in monitoring and motivating for more effective governance.

Grant name	YOWZIT
Project name	Connect-Tech: Connecting citizens and government through technology
Country	South Africa
Grant type	Scaling grant
Description	Yowzit aimed to partner with local civil society organisations to act as intermediaries to encourage disenfranchised groups to raise their concerns about public services offline and online. Yowzit had also plans to work with senior management of the municipality to integrate its e-governance platform with Ekurhuleni’s complaints management system, and to train staff frontline staff to use the Yowzit platform.

Grant name	OCOS - Global Communities
Project name	Our City, Our Say: Including women’s voices in local governance
Country	Ghana
Grant type	Scaling grant
Description	Global Communities was working with the Sekondi-Takoradi Metropolitan Assembly (STMA) to ensure the poorest residents of the city, and particularly women, had a voice in prioritising and improving the city’s service delivery. / The project built on a long-term partnership between Global Communities and the STMA, which was the local government of the twin cities of Sekondi and Takoradi. / Our City: Our Say’ used information from phone in guests and the toll-free hotline to publicise where government was failing to deliver services. The programme also featured city employees, service providers and elected officials answering questions about how Sekondi-Tekoradi district could improve its services.

Grant name	SEND - Ghana
Project name	SEND Ghana: Supporting open budget processes
Country	Ghana
Grant type	Scaling grant
Description	With this project, SEND wanted to make budget information easy-to-understand and available for everybody. / Working through community radio stations, newsletters, workshops and community meetings, the team conducted a mass-education campaign to help people understand how they can access information about government spending, and help them to read and understand it. / SEND will also worked with local and national advocacy groups to help them use the data in their work, campaigning for better budgeting, and inclusion of citizens in the budgeting process.

Grant name	ED - IRC (Etoil Daang)
Project name	Every Voice: SMS to monitor gaps in public health services
Country	Kenya
Grant type	Scaling grant
Description	To help provide the government with actionable data, and improve decision-making on health services, the International Rescue Committee (IRC) was using SMS to monitor and improve the health and nutrition services provided by 12 health facilities and 37 outreach posts in Turkana West. Working with citizen-led health management committees, the project team were supporting the introduction of community scorecards to identify gaps in health services and prioritize healthcare needs in the county.

Grant name	SSP - Southern African HIV Clinician's Society
Project name	From Apps to Accountability: Information for better health services
Country	South Africa
Grant type	Scaling grant
Description	This project was systematically linking information from the local HIV/AIDS War Rooms with planning and budget management systems. Through an integrated reporting system within the government, citizens' reports were brought into the government's own monitoring processes to ensure those in charge of delivering health services had direct access to information about how ordinary people experienced them.

Grant name	MDTS -TI Kenya
Project name	Mobile Drug Tracking System
Country	Kenya
Grant type	Scaling grant
Description	MAVC partnered with Transparency International – Kenya (TI-Kenya) to increase efficiency in the procurement and distribution of essential drugs to Kenya’s public health system. TI-Kenya expanded a pilot mobile drug tracking system from an initial three facilities to an additional five. This system allowed patients to query availability of essential medicines through mobile phones. It also allowed health providers to query stock status from the national supply agency and it served as a complaints response mechanism.

Grant name	DPI - TI Kenya
Project name	Pharmaceutical Guide: Supporting fair prices for essential medicines
Country	Kenya
Grant type	Innovation grant
Description	TI-Kenya constructed a pharmaceutical pricing reference guide to achieve a transparent and accountable pricing process for medicines in Kenya. This guide contributed to formulating a long-term pricing policy by providing a baseline of costs and monitoring pricing trends. / Combined with increased transparency, the project aimed to contribute to greater price predictability, limit consumer exploitation and ease access to medication for the most vulnerable members of society.

Grant name	BSID - Perkumpulan
Project name	Strengthening waste management system accountability using BebasSampah.ID platform in Indonesia.
Country	Indonesia
Grant type	Global innovation competition grant
Description	A previous Ford Foundation funded collaboration developed an application based waste information map providing information on the location of temporary waste collection sites (TPSs), waste banks and collectors. The MAVC project aimed to build on this by developing interactive elements in the ICT platform (TPSRS) and collaboration with the local government (PD Kebersihan).

## Grants for Country Case Studies
Grant name	BS - Black Sash
Project name	Black Sash: Improving local health services with community-based monitoring
Country	South Africa
Grant type	Scaling grant
Description	By putting citizen's priorities for government front and centre, the Black Sash Trust was aiming to shift how, and to whom, government service providers were accountable, re-framing the government-citizen relationship. / Working in partnership with the South African government, the project team was bringing citizen feedback into the government’s system for monitoring of its health service provision. / Through an open-source web-based feedback tool (Keystone’s Feedback Commons) the project collected data that was being used to produce government performance reports, providing real-time comparative information across districts, regions and provinces for use by the government and the general public.

Grant name	KYGC - Kwale Youth & Governance Consortium
Project name	Digital mapping & social accountability in extractive sector / mining
Country	Kenya
Grant type	Scaling grant
Description	Kwale County is one of the mineral rich counties in Kenya with a presence of more than 20 different kinds of extractive mineral resources. / KYGC was involved in advocacy work for the mining act, and this project enabled KYGC to: / • bring the community members together to give their views and to conduct advocacy initiatives / • work closely with the national committee that was undertaking consultative forums with local leaders and communities / The purpose of this project was to map projects in Kwale county that were related to extractive industries. Using GPS devices and an application to collect information, digital maps were created and distributed and discussed at community forums in mining regions across Kwale County.

Grant name	AM - Amandla.mobi
Project name	Amandla.mobi
Country	South Africa
Grant type	Innovation grant
Description	This consisted of a mobile and multilingual campaign to provide tools to citizen with which to organise their communities in numbers that incentivise government accountability. Amandla.mobi worked collaboratively with CSOs in the lobbying and advocacy space, who were the ones that held relationships with decision makers – connecting these organisations with citizens, particularly low-income women – that they would not have been able to reach by themselves.

Grant name	CW - Corruption Watch
Project name	The Public Protector Campaign
Country	South Africa
Grant type	Innovation grant
Description	This campaign delivered against the following objectives: / • To educate the public through online and broadcast media about the role and appointment of the Public Protector / • To encourage the public to nominate suitable candidates for the position, thereby increasing levels of public participation / • To demonstrate the power of public participation in the appointment of the Public Protector using innovative technologies coupled with face-to-face interventions with the aim of reaching diverse audience / • To stimulate public debate around the appropriate process for the appointment of the leadership of other Chapter 9 institutions (of which the Public Protector is one example).

Grant name	INFEST
Project name	Supporting Open Village Financial Data in Wonosobo, Central Java
Country	Indonesia
Grant type	Scaling grant
Description	This project aimed to increase the awareness of the public to monitor and evaluate village planning and development processes at the village level as well as to improve the quality of public services at the village level, especially for vulnerable and marginalised people

Grant name	CSK - TI Indonesia
Project name	Cek Sekolah Ku
Country	Indonesia
Grant type	Scaling grant
Description	The overall stated goal of this project was to improve transparency and accountability in public education through participatory monitoring of school performance via an online platform, Cek Sekolah Ku (CSK, or Check My School) and promote a scale-up strategy built upon sustainability of this initiative. Cek Sekolah Ku was an initiative that was pioneered in the Philippines. Drawing on this Philippine model, TII supported the design and implementation of Cek Sekolah Ku in Indonesia since October 2013, with initial support from the Southeast Asia Transparency and Technology Initiative (SEATTI).

Grant name	IBP - International Budget Partnership
Project name	Promoting open government in Kenya
Country	Kenya
Grant type	Scaling grant
Description	This project sought to increase access to timely and reliable budget information throughout the budget cycle and build and strengthen structures allowing citizens to use budget information as a means of engaging with certain county governments.

Grant name	LENGGO - Local Empowerment for Good Governance
Project name	Tracking County Budgets
Country	Kenya
Grant type	Scaling grant
Description	LENGGO implemented the County Budget Tracking Project to support better, more accountable budgeting in three counties - Kwale, Mombasa and Kilifi. Working in conjunction with the county governments and civil society groups, the team aimed to support public education on the right to participate in budgeting processes, and expand a government-run citizen complaint system.

Grant name	GR - Grassroot
Project name	Grassroot community action platform
Country	South Africa
Grant type	Innovation grant
Description	This consisted of an alternative platform for dialogue between citizens and government and tools with which citizens can more efficiently organize their civic actions. Grassroot received a one-year innovation grant to develop a mobile phone-based tool that was meant to reduce the cost, time and skill required for the marginalised to organise meetings. Critically, the tool was designed with users from the outset who focused on SMS, given the lack of smartphone access.

Grant name	FSHC - Free State Housing Campaign
Project name	Free State Housing Campaign
Country	South Africa
Grant type	Innovation and action research grants
Description	The Free State Housing Campaign (FSHC) is an ambitious and complex partnership, combining innovation and action research grants. It involved working with 22 separate community advice offices and officers on the issue of corruption in the allocation of housing, with a focus on amplifying the voice of people with inadequate housing by using technology.

Grant name	OD - OD Labs
Project name	OD Labs: Project DARU
Country	Indonesia
Grant type	Innovation grant
Description	The overall objective of this ‘Open Data for High Impact Ventures’ (OD HIVE) project was to act as a data innovation intermediary by providing activists, entrepreneurs and researchers, as well as champions from government, with the infrastructure, knowledge and network to develop, prototype and test their ideas for data driven solutions for positive social impact. Specific objectives included seeding and scaling innovation, gathering evidence and sharing lessons with the global tech and governance community.

## REL grants
Grant name	TI - Kenya
Project name	Improving complaints referral mechanisms for greater transparency and accountability
Country	Kenya
Grant type	Research
Description	‘Accountability Together’ – Uwajibikaji Pamoja in Kiswahili – an automated mobile and web-based complaint referral mechanism that aimed to monitor and improve the quality and accountability of humanitarian aid and public services provided to citizens in Wajir, West Pokot and Turkana. It also facilitated the referral of complaints from one aid agency or public service provider to another. / This research aimed to: / •look at Uwajibikaji Pamoja’s fist year of operation, gathering evidence on how technology could be used to set up, implement and sustain an effective complaints referral and management system / •document lessons from similar systems

Grant name	Yayasan Kota Kita (YKK)
Project name	Improving the transparency, inclusivity and impact of participatory budgeting in Indonesia
Country	Indonesia
Grant type	Research grant
Description	Kota Kita’s work on participatory budgeting in Solo City had identified problems including lack of information for project planning and prioritisation, local elites dominating the Musrenbang, and non-implementation of projects selected by citizens. It developed solutions to these problems that included neighbourhood profiles and a tracker tool which shared information about the implementation of selected projects. / This research aimed to learn how to apply different combinations of solutions to improve the Musrenbang in six Indonesian cities.

Grant name	TGCI
Project name	Using a developmental evaluation approach to support citizen engagement and reduction of child sexual abuse
Country	Liberia
Grant type	Research grant
Description	Developmental evaluation of this initiative involved three sets of learners: / •project staff to learn about the impact the project was having on stakeholder perceptions, attitudes, practices and relationships, and use these insights to make adjustments as appropriate in the project design / •community-based stakeholder participants to learn how a development project could have been improved by listening to those involved / •county and national level government officials to gain insights into how voices at the community level could have contributed to the improvement of national level policies, and how they themselves could have worked more effectively across ministries.

Grant name	Francesca Feruglio
Project name	How do empowered citizens make a more accountable state?
Country	Kenya & South Africa
Grant type	Research grant
Description	Examining two legal empowerment initiatives in Southern Africa, this project analysed how marginalised individuals and groups used legal provisions to improve access to health services and address rights violations. It looked at the added value of legal empowerment initiatives and their use of a legal discourse to obtain social change, contributing to explorations of the relationship between the law and development.

Grant name	Global Integrity OGP
Project name	Learning to make all voices count
Country	Indonesia, Kenya, South Africa, Tanzania & The Philippines
Grant type	Research grant
Description	This project supported an action learning and research process which aims to strengthen the impact and effectiveness of the MAVC grantees working on the six Open Government Partnership (OGP) projects. It was informed by the fact that open governance reform was political and complex, so there were no blueprint approaches to making progress.

Grant name	Linda Waldman
Project name	ICT-facilitated accountability and engagement in health systems
Country	Indonesia, Kenya & South Africa
Grant type	Research grant
Description	This study reviewed health-related projects funded under Making All Voices Count to better understand how ICTs can support citizen accountability and engagement in relation to health systems. The study aimed to explore the extent to which ICT innovations have facilitated behaviour change, and to understand which forms of citizen engagement were emerging in health systems.

Grant name	Tactical Tech
Project name	Investigating the role of anonymity in online governance
Country	Kenya & South Africa
Grant type	Research grant
Description	Technology for Transparency and Accountability (T4T&A) projects aimed to leverage technology to illuminate decision-making processes and support new and broader forms of political participation. / Tactical Tech conducted research with partners in South Africa and Kenya exploring: / • the political and legal context in which T4T&A projects function / • how NGOs/activists running citizen-led T4T&A initiatives understand data privacy, security and risk, and how they integrate this into their practice / • how marginalised communities negotiated visibility and anonymity online and offline.

Grant name	MIT Philippines
Project name	Better together? Examining the effect of civic education on local government responsiveness and citizen engagement
Country	Philippines
Grant type	Research grant
Description	Through a field experiment in the northern Philippines, this research tested whether providing civic education to citizens and officials together was more effective at improving local government performance and increasing citizen engagement than providing it to citizens alone.

Grant name	Perkumpulan Prakarsa
Project name	Open government: assessing the utilisation of e-planning and e-budgeting of sub-national governments in Indonesia
Country	Indonesia
Grant type	Research grant
Description	This project examined the implementation of e-budgeting and e-planning in four subnational governments that were championing these efforts. These case studies aimed to contribute thinking to the national government’s plan to implement e-budgeting and e-planning at the national level by 2018, particularly regarding whether the online approach is suitable in Indonesia context.

Grant name	Network Society
Project name	‘Yesterday’: daily mobile-centric communications practices in South Africa
Country	South Africa
Grant type	Research grant
Description	This project focused on ‘hard to reach’ mobile users (phone and Internet) in South Africa. / Using an interview diary ‘day reconstruction’ methodology, the researchers aimed to better understand the motivations of less-connected mobile users, the constraints they face, and the significance of mobiles in their daily lives.

Evaluation Management Unit (EMU) of the Making all Voices Count (MAVC) Programme
Final Evaluation Report - Annexes

DFID
June 2018

In association with:

# Table of Contents

# Annex 1: DFID Evaluation Manager ToR
To access the ToRs, please double-click on the front page in the page below.

This annex contains the original DFID terms of reference for the evaluation manager that all bidders responded to.

# Annex 2: Evaluation Approach Paper
To access the Evaluation Approach Paper, please select and double click on the icon below.
This annex sets out the evaluation management unit approach to the final evaluation. It was reviewed and accepted by DFID.

# Annex 3: Evaluation Questions and OECD-DAC Evaluation Criteria
There are five OECD-DAC evaluation criteria: Efficiency, Effectiveness, Relevance, Impact and Sustainability. This annex shows which evaluation questions are most closely mapped to which evaluation criteria. It closely follows the allocation used by DFID in Annex 1.
Efficiency
EQ1. What lessons on efficiency, effectiveness and co-ordination can be learned from the multi-donor funding and management arrangements for MAVC?
EQ16. Did the REL component deliver value for money? [REL]
Effectiveness
EQ2. How effective has the process for scaling been (involving innovation, scaling, GIC and Research grants, brokering, private sector finance and lessons from scaling up in this sector or country)? What lessons can be learned for other programmes?
EQ3. How effective has the process for innovation been (involving innovation, scaling, GIC and Research grants, brokering, private sector finance and lessons from scaling up in this sector or country)? What lessons can be learned for other programmes?
EQ4. How effective has the brokering approach been?
EQ5. How effective was the REL strategy implementation process? [REL]
EQ6. How effective has MAVC’s approach to learning been? [REL]
Relevance
EQ7. Was there a bias in the types of intervention funded? Were any types of intervention excluded?
EQ8. Were supported interventions aligned with overarching programme objectives as expressed in the MAVC ToC, country plans, synthesis strategy and REL strategy?
Impact
EQ9. To what extent has MAVC delivered improved relationships and increased opportunities for at least constructive dialogue and at best co-governance between citizens and governance in countries with an MAVC country plan?
EQ10. To what extent has MAVC improved citizen’s capabilities (individual and group incentives and opportunities) to express their feedback on government performance and engage with government? If so, how?
EQ11. To what extent has MAVC improved the quality and level of government responsiveness to citizen demands (at national and sub-national levels)? If so, given the capability of officials to respond reflects individual and institutional incentives and opportunities, how has MAVC improved these individual and institutional incentives and opportunities?
EQ12. To what extent can outcomes be attributed to the collective donor inputs?
EQ13. What contribution to informing performance and practice (programme learning) in the field of voice, and accountability occurred? [REL]
EQ14. What evidence/theory-building and associated learning in the field of voice and accountability occurred? [REL]
EQ15. What was the ‘added value’ of the REL component to the MAVC programme in contributing to reach, influence and catalysing action towards MAVC objectives? [REL]
Sustainability
EQ2. How effective has the process for scaling been (involving innovation, scaling, GIC and Research grants, brokering, private sector finance and lessons from scaling up in this sector or country)? What lessons can be learned for other programmes?
EQ3. How effective has the process for innovation been (involving innovation, scaling, GIC and Research grants, brokering, private sector finance and lessons from scaling up in this sector or country)? What lessons can be learned for other programmes?
EQ6. How effective has MAVC’s approach to learning been? [REL]
EQ10. To what extent has MAVC improved citizen’s capabilities (individual and group incentives and opportunities) to express their feedback on government performance and engage with government? If so, how?

# Annex 4: Estimation of Progress Against Outcome and Impact Targets from Survey Data
This annex shows how survey data from the EMU grant case studies was used to estimate progress against logframe indicator targets at the Impact and Outcome level.
Impact indicator 2
Caritas Kitui, Kenya (women only sample):
Based on the question: If you do contact them, how hard do you think they will work to help you?
Asked in respect of the following:
Local school
Local health clinic
Local revenue office
Chief's office
Ward representative
Local MP/Senator
Governor's office
Simple comparison of those saying 'Very hard' from any of the govt agencies:
Baseline 604 observations (71.9%)
Endline 604 observations (92.4%)
Difference = 20.5%
The impact level of the logframe describes a change to which the programme contributes. That is to say, there may be many other factors unrelated to the programme involved in any observed change. Hence for any particular project (such as Caritas Kitui), there is an argument to say that the simple comparison above is the appropriate measure for the impact level indicator.
It is important to note though that the difference of 20.5% does not take into account whether those in treatment groups have gained more than those in control groups.
In principle, the quasi-experimental design means that we can compare responses for this outcome variable for treated and control groups at baseline and endline – as explained in Box 1 below.

For a continuous outcome variable, estimates are obtained by linear regression for person i as follows:
Outcome vari = β0 + β1.periodi + β2.treatedi + β3.treatedi.periodi + ei
where period = 0 or 1 (baseline or endline) and treated = 0 or 1 (treatment or control group).
The standard literature (World Bank, 2011), focusses on the estimated value of β3. - the difference-in-difference measure of impact. However, the logframe indicator asks for the estimated mean difference in the indicator variable between the treatment and control groups after the intervention. Villa (2012) notes that:
The mean outcome for the control group at endline = estimate of β0 + β1 and
The mean outcome for the intervention group at endline = estimate of β0 + β1+ β2+ β3
 Hence, we need to look at β2+ β3
Box 1 – Using Difference-in-Difference estimates for logframe indicator targets
In the Table below, β2+ β3 is given as “Follow-up Diff (T-C)”. Hence, if we only consider targeted project beneficiaries (treatment group), there has been a 10.3% increase in this variable from baseline to endline.

OCOS, Ghana
Based on the question: If you do contact them, how hard do you think they will work to help you?
Asked in respect of the following local service providers/local government representatives:
STMA	GES	GHS	Local MP	ECG	GWCC	Assembly Member	Traditional Authorities

A simple comparison of those saying 'Very hard' from any of these service providers/representatives shows the following:

	Endline	Baseline	Difference
All	70%	67%	2%
Female	31%	32%	-1%
Male	38%	35%	3%

Note: Difference shows rounding to nearest percentage point
Overall, there has been virtually no change and women may have seen a marginal decline.
The results of the generalized linear mixed effect model (below) suggest a that men and women in the treatment group have gained relative to the control group over the project life (odds ratio on Endline*Treatment is above 1). However, this effect is not statistically significant.
OCOS model
Term	Odds Ratio	Standard Error	T-statistic	P-value
(Intercept)	8.5000000	0.7474345	2.8632156	0.004193651
Baseline	ref	ref	Ref	ref
Endline	0.4411765	0.9355329	-0.8746997	0.381737329
Control	ref	ref	Ref	ref
Treatment	0.1612903	0.7658614	-2.3823492	0.017202574
Endline*Treatment	5.0977778	0.9694762	1.6800873	0.092940331

SEND, Ghana
Based on the question: If you do contact them, how hard do you think they will work to help you?
Asked in respect of the following local service providers/local government representatives:
Local school	Local health clinic	Local revenue office	Chief’s office	Assemblyman	Local MP	District/Municipal chief executive

Both men and women have seen a decline in the proportion responding that the service providers/local government representatives will work very hard to help.
	Baseline	Endline	Difference
Female	28%	25%	-3%
Male	41%	36%	-5%

However, if we restrict our attention only to the treatment group (targeted project beneficiaries) we find that the proportion of respondents who believe that these representatives will work very hard to resolve problems has increased (14% for women and 10% for men). This is shown below as “Follow-up Diff (T-C)” in the Table below.
SEND Estimates for women:

SEND Estimates for men:

Yowzit, South Africa
Based on the question: If you do contact them, how hard do you think they will work to help you?
Asked in respect of the following local service providers/local government representatives:
The staff delivering the local service e.g. your local health clinic or school	Municipal Administration	Local ward councillor

A simple comparison of those saying 'Very hard' from any of these service providers/representatives shows the following:

	Baseline	Endline	Difference
All	49%	38%	-10%
Female	50%	38%	-12%
Male	47%	38%	-9%

There is a clear decline between baseline and endline and the decline is greater for women than men. This is very likely to reflect the broader political environment in South Africa, with increasing dissatisfaction for the Zuma administration.
The generalized linear mixed effect model results (below) were estimated for Townships and Suburbs separately and there were insufficient observations to disaggregate by gender. The statisticians at DMSA, Wits University, used a slightly different approach to the one used for Caritas Kitui, OCOS and SEND – looking across all possible responses for expected effort by service providers - but the key result is that there has been a decrease for treatment relative to control groups between baseline and endline although this was not statistically significant.

SSP, South Africa
Based on the question: If you do contact them, how hard do you think they will work to help you?
Asked in respect of the following local service providers/local government representatives:
Local health clinic
Municipal administration
Local ward councillor
Provincial Administration
Local MP/MPL
A simple comparison of those saying 'Very hard or Absolutely' from any of these service providers/representatives shows the following:

	Endline	Baseline	Difference
All	55%	54%	1%
Female	52%	55%	-3%
Male	60%	52%	8%

Note: 68% of the sample were women
Overall, there has been a marginal increase, with a small decrease for women and a larger increase for men. The incidence of stockouts had improved substantially and the impact level finding combines improvements in this outcome measure with dissatisfaction with the Zuma Administration.
Outcome indicator 3
The MAVC logframe indicator is “the % of citizens that have been in contact with MAVC who believe that reporting deficiencies in local/national public services is likely to lead to some improvement”.
Caritas Kitui, Kenya (women only sample):
Based on the question: If you do contact them, how hard do you think they will work to help you?
Asked in respect of the following:
Local school
Local health clinic
Local revenue office
Chief's office
Ward representative
Local MP/Senator
Governor's office
For both treatment and control samples combined we have:
	Endline	Baseline	Difference
Female	92.4%	71.9%	20.5%

At the outcome level, it makes sense to distinguish the difference made by the MAVC intervention on the treatment group relative to the control group between baseline and endline. The impact of the project (Diff-in-Diff) is statistically significant and the contribution for the treatment group to the indicator target for the treatment group is 10.3%

We also have some evidence from responses to the question: If you make a complaint about services, how confident are you that any action will be taken as a result?
The analysis[127] for a combined male and female sample below indicates that the percentage who were very confident of action increased more for project participants (treatment group) than those in the control group between baseline and endline. This is shown by the odds ratio on the Time*Treatment variable.
[127] Generalized linear mixed effect model (GLMM) where the time variable (baseline/endline) was used as a random effect to account for clustering.
Q32 Model
Predictor	Term	Odds Ratio	Standard Error	T-statistic	P-value
	(Intercept)	0.3636364	0.4129104	-2.449928e+00	0.01428847*
Time	Baseline
	Endline	1.0000000	0.5839573	1.466133e-13	1.00000000
Treatment	Control
	Treatment	0.5647321	0.4435137	-1.288356e+00	0.19762195
Time*Treatment	Endline*Treatment	3.1770944	0.6185991	1.868685e+00	0.04166661*

A * On the Pvalue denotes a statistical significance

OCOS, Ghana
For this project we have responses (strongly agree, agree, neutral, disagree, strongly disagree) to the following statement.
“If I report an issue to STMA it is likely to lead to an improvement in service delivery”
To get a change in % response we simply score “agree or strongly agree” as 1 and zero otherwise. We then look at the % with a positive response for the treatment group (294 people who received the MAVC intervention). This has increased by 22% for both women and men between baseline and endline - exceeding the logframe target of +20% between baseline and endline.
	Endline	Baseline	Difference
Female	58%	36%	22%
Male	57%	35%	22%

The simple difference between baseline and endline (above) does not take into account project-specific effects that can be identified by comparing the change for treatment and control groups separately. Using the method explained in Box 1 above we estimate the following from the difference-in-difference regression model with the average propensity to report across all of the institutions as the outcome variable. This is shown below. The key statistic for the logframe outcome indicator 3 is “Diff (T-C) for Follow-up” as this corresponds to “β2+ β3“ in Box 1. These results indicate:
- A 26% increase for men; but
- A statistically insignificant negative result for women. This result may possibly be explained by only having 12 control group observations. However, it does suggest that increases for women benefiting from the project was no greater than the increase experienced by women in the control group.
OCOS Estimates for women:

OCOS Estimates for men:

SEND, Ghana
For this project, the closest question we have is “Have you thought about contacting any of the providers about a problem in the last one-and-a-half years?”
Asked in respect of the following local service providers/local government representatives:
Local school	Local health clinic	Local revenue office	Chief’s office	Assemblyman	Local MP	District/Municipal chief executive

We look at the average propensity to report across all of these institutions for the treatment group (those who received the MAVC intervention). This has marginally decreased between baseline and endline. This simple difference appears, if anything, to have moved in the opposite direction to the logframe target of +20% between baseline and endline.
	Endline	Baseline	Difference
Female	29%	30%	-1%
Male	39%	41%	-2%

However, the simple difference between baseline and endline does not take into account project-specific effects that can be identified by comparing the change for treatment and control groups separately. Using the method explained in Box 1 above we estimate the following from the difference-in-difference regression model with the average propensity to report across all of the institutions as the outcome variable. This is shown below. The key statistic for the logframe outcome indicator 3 is “Diff (T-C) for Follow-up” as this corresponds to “β2+ β3“ in Box 1. The results immediately below indicate that:
- Female project beneficiaries gained 13.6% between baseline and endline.
- Male project beneficiaries gained 10.3%.
So, while the logframe target of a 20% increase has not been achieved, project beneficiaries have made some gains, more so for women.
SEND Estimates for women:

SEND Estimates for men:

Yowzit, South Africa
For this project, the closest question we have is:
“If you were not satisfied with any of the services provided by Ekurhuleni municipality, how likely are you to contact any of the following”
Asked in respect of the following local service providers/local government representatives:
The staff delivering the local service e.g. your local health clinic or school	Municipal Administration	Local ward councillor

We compare the % very likely to contact one of these institutions at endline and baseline. Project participation is proxied by those who say they have undertaken a public service rating exercise in the past year. This suggest that those who had rated a public service were either as likely (female) or slightly more likely (male) to be very likely to contact public service institutions at endline than at baseline. In contrast, those who had not participated, were significantly less likely to contact a service provider at endline than at baseline.
Project participants at endline:
	Baseline	Endline	Difference
Female	61%	62%	0%
Male	62%	67%	4%

All at endline
	Baseline	Endline	Difference
Female	61%	50%	-11%
Male	62%	53%	-10%

The statistical analysis carried out by the local research team (DMSA at Wits University) compared the % very likely to contact one of these institutions by area of the metropolitan municipality in which the project was active (treatment) with a matched control area. They did not produce results by gender, but their analysis suggests there were no significant differences for the change in this outcome variable between treatment and control sites over time. Their results are shown for each institution below.

SSP, South Africa
The survey question that is most likely to give us an indication of whether MAVC beneficiaries believe that reporting deficiencies in local/national public services is likely to lead to some improvement is:
If you do contact them, how hard do you think they will work to help you?
Asked to randomly assigned treatment and control sites in respect of the following local service providers/local government representatives:
Local health clinic
Municipal administration
Local ward councillor
Provincial Administration
Local MP/MPL

A comparison of those saying 'Very hard or Absolutely' from any of these service providers/representatives shows the following:

Treatment + Control
	Endline	Baseline	Difference
All	55%	54%	1%
Female	52%	55%	-3%
Male	60%	52%	8%

Note: 68% of the sample were women

Control group
	Baseline	Endline	Difference
Female	61%	52%	-8%
Male	60%	62%	2%

Treatment group
	Baseline	Endline	Difference
Female	47%	52%	5%
Male	43%	57%	15%

A crude difference-in-difference estimate would therefore be an increase of 13% among project beneficiaries relative to those in control groups. This is indicative but not a statistically robust measure as it does not account for differences in characteristics within both groups.

# Annex 5: Evidence from EMU Case Studies

Caritas Kitui, Kenya, £38,161 innovation grant, Aug 2014 – July 2015
Involvement of	Gil Yaron (Team Leader), Patrick Osodo (Baseline, Governance Adviser), Michael Otieno (Governance Adviser, Endline) Jane Meme (Focus Group Discussion Coordinator), Daniel Mwero (Data Manager)
Outcome-level results		FMC summary against objectives
The end of project evaluation (difference-in-difference survey with control groups and qualitative evidence), found that the project has led to improvement of rural women’s participation in county government processes through previously marginalised women attending public participation consultative meetings and making their views known. At the same time, there was increased knowledge and understanding of devolved governance structures and the role of citizens in governance, resulting in enhanced engagement and demand for improved public services. / Post project monitoring in Sept 17 found an increased respect for the role of women in decision making at the lower echelons leading to more female representation in community level development committees, school management committees and health management committees. The project had led to a ‘surge’ in female candidates applying for the jobs of village administrator, chief and sub chiefs (with some success). Women reached by the project continue to utilize radio call-in programmes with limited use of SMS. / Women continue to be more involved in government processes through public participation forums originally organised by the project at various county administrative levels. However, sub-county and ward government officials in the face of increased scrutiny have started to exclude women with dissenting views from attending or participating in meetings. Project activities contributed to the frustration with transparency and accountability that was an important factor in the voting out of virtually all incumbents (Governor, MP and members of the County Assembly) in the elections in August 2017. / The project built on strong existing Caritas work with local women’s groups. The ICT was not developed with users but when problems with the planned SMS focus emerged, the team adapted to using existing FM radio.		The project met all of its objectives, while the additional advocacy work and networking which occurred and was supported as a result of the project exceeds the initial expectations of the reach and impact on change and participation in this project. There are lessons incorporated within this project as to the degree to which women's voice needs to be listened to as well- the women were strongly empowered and engaged more than expected, but still encountered some resistance from government responsiveness at points.

ICW, Indonesia, £81,000, Scaling grant, Jun 14 – May 16
Involvement of	Gil Yaron (Team Leader), Kerry Brennan (Baseline Evaluation Lead), Carrie Oppenheimer (Endline Evaluation Lead), Yunie Nurhayati (Research Consultant), Ari Setiawan (Baseline National Research Expert),
Outcome-level results		FMC summary against objectives
ICW trained three local CSOs (in 3 cities in Sulawesi, Indonesia) in the use of its Open Tender website and Potential Fraud Analysis (PFA) tool for e-procurement, and supporting them to undertake off-line investigations into identified cases of potential procurement fraud. In practice, limited CSO capacity to do the off-line evidence gathering in the face of government obstruction has been a major constraint. Post project it emerged that following media uptake, one of the four cases being investigated by the police has led to repayments by the contractor and re-tendering of the contract (originally approximately £150,000) for solar street lighting in Manado (a city of more than 400,000 people). This case went to trial in the corruption court of Manado in 2017. The MAVC project contributed to this process but very much depends on external factors for success (media uptake and help being available to the local CSO to do the off-line investigation). Our post-project monitoring confirms that, local CSO activists and journalists continue to be trained to use the tools developed in the three cities but any new cases will require major investments to do the off-line investigation and there is little certainty that these will be forthcoming. / Despite being a scaling grant, this project piloted ICT tool use with off-line support and found that the off-line component has presented by far the major challenge.		Project clearly tracked and aligned implementation to the proposal, and successfully accomplished all activities and objectives as outlined. The two areas where the project fell slightly short (but still counted as overall achieving objectives), was in: Engaging 60% women, and creating a more specific feedback loop into the online system. It is also not clear how many cases were put forward by region for investigation, a process also ongoing. The latter two areas are understandable due to the delays of the hacked and crashed system during the course of the grant.

WYDII Indonesia, £65,457, Global Innovation Competition grant, Oct 15 – Aug 16
Involvement of	Gil Yaron (Team Leader), Cecilia Luttrell (Evaluation Lead), Yunie Nurhayati (Research Consultant), Ibrahim Ukrin (Research Consultant)
Outcome-level results		FMC summary against objectives
There was a significant increase in levels of confidence to raise planning issues particularly amongst the project’s community ‘coordinators’ (predominantly middle class women). However, confidence tended to be limited to interaction at the level of their own sub-village level or to reporting anonymously by SMS, and not speaking out at village level and many poorer respondents said that they were afraid to attend or speak up in meetings. / By the end of the project, the village government and the BPD had placed much more attention on the voice of women and their role in development and planning processes, and seems to be taking pride in being seen to be more inclusive. The village elite were much more aware of the exclusion of women and the issue of confidence amongst women to speak out. / The village government became more open about the budget although full budget details were not shared publicly. Some issues raised by the project were subsequently reflected in the village budget. / When WYDII first entered the village, people were suspicious, and the project was resisted by certain sub-village leaders. Many people refused to take part in the SMS survey fearing that it was only for WYDII’s benefit or that it had some political agenda. The project director already knew the village leader and convinced her to endorse the survey as a way of proving her capability and raising her profile to spend the larger budget under the 2014 Village Law. / The role of ‘off-line’ coordinators as intermediaries was crucial to give people confidence to answer survey questions and to facilitate the use of the ICT (SMS) system. Provision of phone credit as an incentive was also critical. Regional government saw the results and in 2017 have begun to roll out their own SMS survey programme (contribution of project unknown) but uptake is reportedly limited as it has no off-line facilitation and is not anonymous. / The project piloted the ICT only as part of implementation, finding resistance to the survey idea rather than the tech itself and adapting as noted above.		Objectives partially achieved. The achievements are too bold but they underestimated in the report the political space that they navigated

Yowzit, South Africa, £240,000, Scaling grant, Apr 16 – Aug 17
Involvement of	Gil Yaron (Team Leader & Evaluation Lead), Mark Paiker (Director DMSA) & Team from Data Management & Statistical Analysis (DMSA)
Outcome-level results		FMC summary against objectives
Yowzit is South Africa’s leading private rating website. This project builds on an earlier innovation project and an associated practitioner research grant that led to a new off-line focus by the project. / We have focussed on the two principal outcomes of the project: 1: Improve local government officials’ ability to understand the priorities of citizens and respond to their needs; and 2: Build the willingness of people to participate in the political life of their communities as active citizens. / Project outcomes have been evaluated by local researchers (DMSA at Wits University) using a panel survey (for treatment and control sites in 2 Townships and 2 Suburbs), focus group discussions and key informant interviews. These results suggest that despite considerable effort by the project team, there has not been widespread engagement of citizens. Citizens in both treatment and control groups felt significantly less inclined to contact service providers at endline than baseline and were less confident those contacted would work hard to address reported problems. It seems likely that citizen dissatisfaction with corruption in service provision in general has overwhelmed any localised project activities. This presents a problem for the Yowzit model, as it relies on citizens having confidence that their service rating will get a response from service providers (rather than eliciting a media or some other off-line campaign). / A significant investment of time and effort was made by the project team to build partnerships with municipal governments at an operational as well as political level but post-election changes in personnel meant that this had to begin all over again. A distinction has emerged between ‘progressive, performance-focussed’ elements of municipal government, that are keen to champion responsiveness to citizen concerns and service delivery departments that see additional costs and time pressures imposed by responding to these complaints. Yowzit are in negotiations with 3 municipalities to contract citizen feedback and problem resolution services but a contract may take a further year to materialise. Once a municipality has invested in this service it will signal greater probability that government engagement will produce improved service delivery. / This scaling grant builds on an earlier innovation with PRL grant that led to developing the off-line component in this scaling grant. It would be more accurate to describe it as moving to the next phase of innovation than scaling.		Objectives partially met. Project successful in engaging citizens, particularly including marginalised citizens, as well as integrating with some government officials/departments. However, despite some degree of responsiveness’ being achieved, there are no indications of these responses resulting in improved service delivery.

Send Ghana, £182,033, Scaling grant, Oct 15 – Apr 17
Involvement of	Gil Yaron (Team Leader), Kate Conroy (Baseline Evaluation Lead), Felix Wood (Endline Evaluation Lead), Adobea Owusu (National Lead Researcher), Daniel Mwero (Data Manager), Rosario Leon (Casestudy report support)
Outcome-level results		FMC summary against objectives
The objectives of the project were to: i) Increase citizens’ knowledge on the administration of the District Development Fund (DDF); ii) Strengthen the capacity of citizens to track and monitor the DDF resources for local development; and iii) Increase citizens’ involvement in the utilisation of the DDF. The end of project evaluation (difference-in-difference survey with panel data & control groups plus qualitative evidence), found that the project had not increased citizens’ knowledge of the DDF. Knowledge of SEND Ghana’s District Citizens’ Monitoring Committees (DCMC) that were ICT enabled by this project increased primarily in one project sub-area in northern Ghana (Bolga municipality). More widely, most duty-bearers (including the Regional Coordinating Council members) were unaware of this project although there was some increasing awareness of DCMCs in half the municipalities (based on interviews of 65 key informants across four project districts). And the small group of duty bearers who were familiar with the work of DCMCs felt this had made it easier for them to engage with citizens. Radio was the most useful ICT. / Survey data suggests an increase an increase in citizens’ awareness of their rights and responsibilities regarding service provision and inclusion of their needs in funded projects of the Metropolitan, Municipal and District Assemblies (MMDAs), although this was attributed to projects previously implemented by SEND and other NGOs in northern Ghana as well as the current project. Nonetheless, survey results are better in project areas. / Citizens’ participation in the planning, implementation and monitoring of projects funded by the DDF remains very low. While MMDAs said they involve citizens in interactive processes regarding the management of the DDF, virtually all citizens said they were not even informed. Citizens also said they did not know how much DDF their districts were awarded in the current year. Hence, the evidence suggests that project objectives have been, at best, partially met. / SEND had existing experience of developing DCMCs. However, despite being a scaling grant, the ICT was not previously developed or piloted with users.		Objectives met. Project appears to have demonstrated significant results in obtaining a 72% commitment rate from duty-bearers with regards to DDF projects, as well as incorporated a platform to assist in collecting citizen input. The degree to which tech affected this outcome and the results achieved were particularly new is unclear.

Global Communities, Ghana, £100,492 Scaling grant, Jun 14 – Jan 16
Involvement of	Gil Yaron (Team Leader), Kate Conroy (Baseline Evaluation Lead), Felix Wood (Endline Evaluation Lead), Adobea Owusu (National Lead Researcher), Daniel Mwero (Data Manager),
Outcome-level results		FMC summary against objectives
The ‘Our City, Our Say’ (OCOS) project has twin goals of increasing the capacity of the Citizens Report Card (CRC) team to sustainably support mechanisms for frequent feedback from citizens on service quality; and to improve the ability of the Sekondi-Takoradi Metropolitan Assembly (STMA) to track, analyse and promptly resolve service delivery complaints (in a city of more than 500,000). The project is implemented by Global Communities, in conjunction with STMA. Key project activities include using Smartsol software for interactive SMS messaging. Websites and monthly call-in radio programmes are also used to gather citizens’ feedback. The end of project evaluation (difference-in-difference survey with panel data & control groups plus qualitative evidence), found was very little use of Smartsol interactive messaging but much greater use of the monthly radio call in programme that had service providers as interviewees. Local radio is a popular medium, particularly among the poor, and by the end of the project, 67% of the respondents who listened to this radio programme, and had service delivery problems within the last 12 months, made a follow up call/reported such issues to STMA or other service providers. This reflects a statistically significant increase in citizens interacting with local government and its representatives over the project lifetime, but feedback from 16 FGDs suggests that this has primarily been driven by factors outside the project. In addition, face to face contact with service providers and members of local government remains by far the most common means of citizen engagement and although the project has had some success in getting improved citizen awareness of and engagement with governance issues, it has been much harder to get service providers to respond to issues raised – particularly by women. / An unexpected benefit has been that the OCOS Project equipped the STMA with the necessary skills to bid for and win funding from the IBM Smarter Cities Project to improve revenue management. STMA was the only city in Africa to win funding. / Nearly all interviewees across the range of stakeholder groups felt that changes the Project had put in place were sustainable, contingent on funding – particularly from STMA. Early indications are encouraging as STMA have paid for continued use of the toll-free numbers and additional attempts to use radio to reach out to citizens. RoK FM radio station who mentioned that in in the aftermath of the OCOS project, they run similar programmes and Global Communities mentioned that their success with the OCOS project had prompted three more radio stations in the STMA to contact them for partnerships. / GC have considerable experience of working in STMA. However, despite being a scaling project, the intended SMS/Smartsol technology had not been developed or piloted with users. The project made more use of existing FM radio.		Objectives partially met. Basic outreach and implementation occurred, the change hoped for is less certain.

IRC, Kenya, £97,049, Scaling, May 14 – Mar 16
Involvement of	Gil Yaron (Team Leader), Patrick Osodo (Baseline, Governance Adviser), Michael Otieno (Governance Adviser, Endline) Jane Meme (Focus Group Discussion Coordinator), Daniel Mwero (Data Manager)
Outcome-level results		FMC summary against objectives
The IRC’s Etoil Daang’ (Every Voice) Project aimed to address the challenges of poor health service delivery as well as poor consultations with citizens in the management of local government affairs in Turkana County using a mobile-phone enabled Citizens Score Card (CSC) approach. It complemented an existing IRC integrated health and nutrition outreach programme in 12 health facilities and 37 health posts in remote and conflict affected Turkana West Sub-County. Evaluation using a panel survey with treatment and control sites proved very difficult as pastoralist health facility users moved vast distances and we rely mainly on focus group and key informant interviews. / It proved impossible to establish a mobile phone platform to support on-going CSCs due to low levels of mobile ownership, patchy network coverage, low levels of literacy and the conservative cultural context. This could and should have been established before starting a scaling project. / There are examples where CSCs and action plans put in place by the project contributed to increased county government investment in specific health facilities. However, we did not find widespread or sustained use of CSCs and action plans in the 12 project intervention facilities. / IRC expected to piggy back on funding for community health outreach but when this ended they found this scaling project to be significantly under-resourced. / Rather than the project, the process of devolution has made health facility staff more accountable to county rather than very distant national officials. This, together with improved resourcing, has improved service delivery at health facility level. Yet, public participation in decision making remains a challenge for residents of Turkana west and the aims of the project CSC remain relevant. / IRC built on existing relationships with focus communities from the nutritional support programme and have international experience with CSCs. However, despite being a scaling project, no attempt was previously made to develop and pilot ICT with users or CSC action plans with communities and service providers in the challenging Turkana West context.		Objectives partially met. Increased interaction between citizens and government and progress towards community identified change plans; however the ICT platform did not take off and was underutilised. The degree to which the specific health issues (measles immunisation, iron-folate supplementation, malnutrition recovery and nutrition activities were specifically affected is unclear.

Southern African HIV Clinician's Society, South Africa, £97,907, Scaling, Dec 15 – Dec 16
Involvement of	Gil Yaron (Team Leader & Evaluation Lead), Temesgen Zewotir (Senior Quantitative Expert), Partson Tinarwo (Quantitative Expert)
Outcome-level results		FMC summary against objectives
This MAVC 12-month scaling grant for the Stop Stock outs Project (SSP) involved interventions at provincial, district and facility level with four pilot districts and 11 facilities per district receiving community monitoring (sentinel surveyors and patient information sessions) in addition to the general reporting from patients and healthcare workers at any public health facility through the existing Stop Stock outs system. / Our evaluation has been based on a randomised allocation of paired facility areas into treatment and control sites. Respondents at baseline have been matched with (different) respondents at endline. Survey findings indicate that this MAVC grant increased households’ awareness of how to report complaints on not having a prescribed drug or specialist drug from the health facility. There were also a substantial number of households reporting complaints to the advocacy groups in treatment areas. Nonetheless, there is no evidence that respondents in treatment areas experienced bigger reductions in stockouts than those in control sites. Both saw significant drops in stockouts that reflect government action on health care at a higher level – that is not consistent with the MAVC grant driving this change. / SSP builds on existing institutional arrangements with health care facilities and communities but despite being a scaling project, the innovative use of ICT had not previously been piloted.		This project in some ways met its aim of rewarding behaviour and engaging citizenry in improving the standard of living of society (to a limited degree of service). However, there are no indications of government/citizen interaction, and the initial premise of the reward system as a feedback loop is flawed. Additionally, there is no indication that the specific campaigns identified as congruent with government initiatives (even though these still are questionably a means of direct citizen/government engagement) were accomplished. This project is not considered a failure, but has only minimally met objectives and the alignment of stated objectives with the principles of MAVC are questionable

TI-Kenya, MDTS, £80,000, Scaling, Jun 14 – Jul 16
Involvement of	Gil Yaron (Team Leader), Patrick Osodo (Baseline, Governance Adviser), Michael Otieno (Governance Adviser, Endline) Jane Meme (Focus Group Discussion Coordinator), Daniel Mwero (Data Manager)
Outcome-level results		FMC summary against objectives
The mobile drug tracking system (MDTS) aimed to give the public, community health workers and health facility management committees access to data on medicine supplies health facilities and enable them to query and receive feedback on specific medicines from a mobile platform. / We found that there very limited knowledge of this project by citizens and no use by targeted health facilities we visited. This makes it very likely that recorded improvements in health care reflect significant county investments to more progressive clinics willing to sign up to the MDTS, rather than the project itself. The project was not implemented as intended due to numerous challenges including the slow pace of uptake by county governments and health facilities, and delayed disbursement and communication from the grants managers. The short project period of one year was not feasible. It did not take into account the fact that relationship building with county governments (that were key partners in the project) takes a much longer time. Indeed, because of these delays and slow response from county governments, TI- Kenya was forced to not only in one case shift the target counties but also in many other cases shift health facilities in cases where the county governments had agreed to partner with TI, but the individual health facilities were either slow or unwilling to partner. / Although this was a scaling project, the institutional relationships had not previously been developed with government and technology had not been piloted with users.		Failed to meet objectives. While training and initial implementation of the system occurred in some facilities, there was a sufficient lack of usage/data entry which prohibited the more significant aims of engaging citizens in monitoring to occur. No sensitisation or citizen engagement occurred.

TI-Kenya, DPI, £35,000, Innovation, Sep 14 – Oct 16
Involvement of	Gil Yaron (Team Leader), Patrick Osodo (Baseline, Governance Adviser), Michael Otieno (Governance Adviser, Endline) Jane Meme (Focus Group Discussion Coordinator), Daniel Mwero (Data Manager)
Outcome-level results		FMC summary against objectives
This innovation grant supported development of a pharmaceutical pricing reference guide (DPI) for mobile phone users in Homabay and Kwale counties to provide baseline costs of medicines to the public. In our visits to intervention sites we found that apart from staff and community members that directly interacted with the project; there was no wider knowledge about the project. This was the case in all the focus group discussions. The participants noted that if the DPI project had had any effect on the behaviour of the various service providers and county level officials, the persistent drug shortages in the facilities would have eased since the project was specific to drugs (but they had not). The few that had interacted with the DPI indicated that in fact the prices of drugs at the health facilities were cheaper than the prices on the price indicator, a fact that was confirmed by health workers and key informants. This was because the county government subsidises the costs of drugs to make them affordable to a majority of citizens. In addition, the county staff also noted that the drugs list was not complete and was not harmonised with the official KEMSA list, in some cases the drug codes were not matching. / There does not appear to have been an attempt to develop the project itself with health facility or county health providers or the ICT with end users.		Exit interview team determined that project did not meet its objective; project was not adequately familiar with context to provide a suitable project to meet objectives and problem identification was not clear or necessarily appropriate.

Perkumpulan YPBB (BSID), £63,690, GIC, May 16 – May 17
Involvement of	Gil Yaron (Team Leader), Cecilia Luttrell (Evaluation Lead), Yunie Nurhayati (National Research Expert), Dhimas Anindito (National Research Expert)
Outcome-level results		FMC summary against objectives
A previous Ford Foundation funded collaboration developed an application based waste information map providing information on the location of temporary waste collection sites (TPSs), waste banks and collectors. The MAVC project aimed to build on this by developing interactive elements in the ICT platform (TPSRS) and collaboration with the local government (PD Kebersihan). / In practice, the development of the platform was severely delayed, and no attention was given to the associated offline (community organising) activities. Our endline qualitative research found very little evidence that the app was being used as intended. In part, as highlighted at the baseline, waste was not seen as a priority issue by the public and just having an app to report problems was not going to change citizen behaviour. This also reflects very low levels of confidence among citizens that government would respond to any complaint made. We found some resistance to using the app as only 48% (at baseline) had access to a smart phone and only 12% used social media. More generally, people felt that the app consumed phones memory and internet quota, while an SMS rating requires phone credit. Most people prefer paper-based form as it is easy and quick. From total 1561 number of ratings, only 441 ratings coming from apps, and 120 coming from SMS. / The app itself was also limited by not enabling discussion of waste or allowing the government to respond to the request/inputs/comments from public users through the system. This is in contrast to new government platforms such as LAPOR! or social media channels that are currently being used by government.		Failed to meet objectives. Project experienced significant delays in launching the app, only successfully doing so as the MAVC-funded project was drawing to a close. While a few offline activities were facilitated, they were primarily around app development and testing, as well as baseline studies, with little meaningful influence on the overall project intended outcomes.

Notes:
Longer summaries and the full case study reports have been provided to DFID. The FMC summary is included as it draws on the QAS and reflective exit interviews with project staff for some more recent projects. For most, but not the most recent, grants above our case study findings have been reviewed by FMC and we cannot know how different their conclusions would have been without our findings.

# Annex 6: South Africa Case Study
To access the Annex, please select and double-click on the front page in the page below.

# Annex 7: Kenya Case Study
To access the Annex, please select and double-click on the front page in the page below.

# Annex 8: Indonesia Case Study
To access the Annex, please select and double-click on the front page in the page below.

# Annex 9: Innovation Pathways and Stages
Innovation programmes typically promote innovation by establishing targets and criteria for funding that require innovation; enable innovation by applying and/or supporting innovation processes, such as the application of lean methods, adaptive programming and trial and test approaches with failure (Fail fast and learn fast) an accepted component of the process.; and apply good innovation practice, by recognising and working with current learning about innovation in the sector.

Innovation pathways and stages
The innovation literature identifies multiple stages from defining the problem to innovation at scale and changing the market. Nesta.org Innovation Flow Chart has 7 stages (in which scaling occurs at 6). While progress is often non-linear, there is general agreement on the kind of evidence and financing needed at different stages (see the Figure below).

Figure Nesta.org Innovation Flow Chart

The following Figure consists of another innovation process involving different stages from concept to commercialization.

Figure 2 VC Innovation Infographic (Jonathan Bryers, 350ip)

Criteria for innovation
The assessment of innovation fitted within the wider final evaluation for the programme, which involved a performance, process and impact (outcome level) evaluation. It was based on bottom up (grant level) and top down (country level) assessments, and overall synthesis of data using theory based approaches.
The criteria were used during key informant interviews and analysis to assess the extent to which innovation was supported at project and programme levels.
To assess MAVC we looked across the programme at the extent to which innovation was promoted, enable and good practice applied.
In doing this we recognise that different projects and programmes have different aims and contexts so not all criteria are relevant for all MAVC projects.

Criteria for assessment may include:
- Promotion:
  - Was a clear definition of Innovation given in the call for funding?
  - Did scoring criteria include marks for innovation?
  - Did the grant submissions and those initiatives that received funding, achieve high scores for innovation in the grant evaluation process?
- Enabling:
  - Did the programme promote principles of fail fast learn fast, or trial and testing approaches to innovation?
- Best Practice:
Did the programme (and projects within the programme) consider best practice, including considering the route to scale, the wider innovation ecosystems and the impacts this may have of success and scale up, and effectively consider risk.