## Master Log Frame
NOTE: Additions associated with the addendum are added in RED
PROJECT NAME | Ideas to Impact 201879
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025
Number of people with new or improved access to improved technologies across a range of sectors | Number of people with access to water and sanitation (SDG6); and /or access to affordable, reliable, sustainable and modern energy services (SDG7); and/or strengthened adaptive capacity to climate related hazards (SDG13.1), people with access to Assistive Technology | Planned | 1.3bn with no access to electricity and 2.7bn without clean cooking facilities (2011) 780m with no access to clean drinking water (2012) 2.5bn with no access to sanitation (2012) X million disabled people living in developing countries | Prizes launched (5 by 2016/17) must atriculate and provide strong evidence on contribution to impact trajectory to target. 1 million people by 2016/17 | 12m (2025) 12 million people with access to energy/water by 2025 as a result of the technologies developed and deployed under this programme | [6 empty] | 22.5 million people people positively impacted through the use of affordable and accessible techs, including people with access to water and sanitation; and /or access to affordable, reliable, sustainable and modern energy services Develop scalable ideas and solutions that can be integrated into broader DFID programmes people with access to energy/water, or improved adaptive capacity by 2025 as a result of the programme 3 million people with improved access to Assistive Technologies | Further sectors addressed by the wider range of technologies supported by I2I will be included over time.
Achieved
IEA's World Energy Outlook WHO/Unicef Joint Monitoring Program report Programme and sub-project M&E reports, Annual Reviews, Project Completion Report, final independent evaluation (2018/19)
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025
Affordable and accessible technologies, innovations and policies are accelerated in their uptake, adoption and development in international development. | Number of technologies, new processes and services, and new business models being developed/adopted/scaled-up directly or indirectly | Planned | 0 | a) 4 b) 1 | a) 12 b) 2 | a) 18 b) | a) 2 b) | a) b) | a) b) | a) b) | a) b) | a) 148 developed b) 22 deployed
|  | Achieved |  |  |  |  | a) 87
Source
Routine Results Reporting by M&E team Individual prize M&E reports published post-prize
| Outcome Indicator 2 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025 | Assumptions
| Additional a) private investment and b) public finance leveraged to support technological innovations and business models | Planned | 0 | £8m | [7 empty] | £35m | Other key areas to tackle poverty are successfully addressed including: - policies and regulations - institutional requirements - corruption International and local investors are willing to invest in the deployment of solutions in countries. appropriate partner programmes are willing to collaborate willing target countries with appropriate enabling environments can be identified and are able to effectively respond Winning projects are able to be replicated, scaled up and costs reduced. Successful ventures raise public and investor awareness of opportunities.
|  | Achieved |  |  |  |  | a) £1,937,993 b) £6,028,000 |  |  |  |  | £35m
Source
Routine Results Reporting by M&E team Individual prize M&E reports published post-prize
| Outcome Indicator 3 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025
| Number of services (inc. technological innovations and business models) supported by the programme that show indication of replication | Planned
Achieved
Source
Routine Results Reporting by M&E team
| Outcome Indicator 4 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025
| Number of a) changes in policy (internal or external) as a result of programme activities, or cases where the programme supports the creation of a more enabling policy environment b) % partners who are new external partners | Planned | 0 (2014) | a) x b) 20 | a) x b) 25 | a) x b) 30 | a) x b) 35 | a) x b) 40 | a) x b) 50 | a) x b) 50 | a) x b) 50 | 50% of partners or grantees new to DFID
Achieved
Source
Programme Media Log
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | [6 empty] | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
0.5
OUTPUT 1 | Output Indicator 1.1 a |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025 | Assumption
Innovation Prizes | Prize implementation plans, resources and tools in place | Planned | No platform or teams (2012) | Innovation prize Design Teams in place and operational (2014/15) | Prize implemenation teams and steering committees in place (2015/16) | [7 empty] | Problem statements are identified and articulated clearly and solutions are realisable. challenge design is appropriate within 5 year time frame Prize purse is attractive enough to incentivise organisations to take part. Other funders (public and private) recognise opportunity and join the UK in establishing the platform. Research and analysis contributes to the limited evidence base on opportunities to support innovation in environment & development. Evidence on failures is easy to acquire and is treated as a global public good. Failures provide valuable lessons learnt for the sector.
|  | Achieved |  | achieved | achieved
Source
Programme Annual Review
| Output Indicator 1.1 b |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025
| Number of a)Prizes launched b) prizes stimulating the expected response from launch to award | Planned | 0 (2014) | a) 4 b) 1 | a) 4 b) 4 | a) 4 b) 2 | a) 1 b) 3 | a) 0 b) 4 |  |  |  | a) 13 b) 13
|  | Achieved |  | achieved | achieved |  | a) 3 b) 5
Source
Programme Annual Review
| Output Indicator 1.2 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025
| Number of a) open access peer-reviewed publications documenting the research into innovation prizes b) key stakeholders accessing programme learning outputs and publications | Planned | 0 (2014) | a) 0 b) 14000 | a) 4 b) 6600 | a) 1 b) 2080 | b) 540 | b) 108
|  | Achieved |  | a) 0 b) 31000 | a) 4 b) 31000 | a) 1 b) 2080
Source
Programme Annual Review Individual prize M&E reports published post-prize Programme Media Log of downloads, tweets and other social media
| Output Indicator 1.3 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025
| Number of a) final evaluation reports of individual prizes, including details of failed prizes, published as open access b) key stakeholders accessing programme evaluation outputs | Planned | 0 (2014) | a) 0 b) 2 | a) 0 b) 3 | a) 0 b) 2 | a) 1 b ) 2 | a) 5 b) 3 |  |  |  | a) 6 b) 12
|  | Achieved |  | Yes | On track | a) 1 |  | a) 6
Source
Programme Annual Review (Programme Media Log of downloads, tweets and other social media) TBC based on updated dissemination plan objectives and activities
IMPACT WEIGHTING (%)
30%
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£) |  |  |  |  | DFID SHARE (%)
| 10.35m | [5 empty] | 10.35m | [5 empty] | RISK RATING
INPUTS (HR) | DFID (FTEs) | [11 empty] | H
0.2
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025 | Assumptions
Frontier Technologies | No. of Frontier Technology Grant: a) applications received b) Awarded, and then c) Scoping and Design completed and implementation contracted, d) completed, e) with extra sprints/pivots | Planned | 0 | N/A | a) 10 b) 5 awarded c) 0 contracted d) 0 completed e) 0 | a) 20 apps b) 10 awarded c) 8 contracted d) 0 completed e) 0 | a) 15 b) 8 awarded c) 7 contracted d) 5 completed e) 2 pivots/extra | a) 15 b) 8 awarded c) 7 contracted d) 5 completed e) 2 pivots/extra | a) 15 b) 8 awarded c)7 contracted d)6 completed e)2 pivots/extra | a) 0 b) 0 awarded c) 7 contracted d) 6 completed e) 2 pivots/extra | a) 0 b) 0 awarded c) 0 contracted d) 6 completed e) 2 pivots/extra | 30 + 45 Applications 15 + 24 awarded 13 + 21 contracted 10 + 18 completed 2 + 8 pivots/extra sprints | Call frequency will be annual as opposed to the 6 monthly in the pilot to better allocate resources and manage quality pipeline, allowing for an acceptance rate of around 50%. Assumes a 10-20% rate of projects approved but not going past the scoping phase to contracting, and then a 10-20% rate of started projects not completing, and a 10-20% rate of projects justifying pivots/extra sprints from that fund and reallocations from discontinued projects
|  | Achieved |  |  | a) 12 b) 6 awarded c) 0 contracted d) 0 completed e) | a) 30 b) 13 awarded c)6 contracted d) 0 completed e) 0 | a) 24 b) 8 c) 9 d) 2 e) 2
Source
Annual and Quarterly reports / Challenge Fund Round Reports
| Output Indicator 2.2 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025 | Assumptions
| FTL Futures number of DFID country offices or teams supported | Planned | 0 | N/A | N/A | N/A | 1 | 3 | 3 | 3 | 3 | 1 + 12 countries | Assumes that demand is there from countries and advisors to engage, which will also be stimulated by the various communications and engagement strategies.
|  | Achieved |  |  | N/A | N/A | 1
Source
Annual and Quarterly reports
| Output Indicator 2.3 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025 | Assumptions
| FT Foresighting: number of innovation scoping/prep studies delivered | Planned | 0 | N/A | N/A | N/A | 1 | 1 | 2 | 2 | 2 | 1 + 7 Scoping/prep studies | Assumes that demand is there from countries and advisors to engage, which will also be stimulated by the various communications and engagement strategies.
|  | Achieved |  |  | N/A | N/A | 2
Source
Annual and Quarterly reports
| Output Indicator 2.4 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025 | Assumptions
| Reports, learning, and engagement: number of a) Sprint Reports b) Medium posts c) Case study/closure reports d) Learning events e) Research publications f) Followers of the live stream | Planned | 0 | N/A | N/A | a) No target b) 60 c) 0 d) 1 e) 1 f) No target | a) 13 b) 69 c) 5 d) 1 e) 1 f) 150 | a) 13 + 6 b) 24 + 60 c) 5 + 4 d) 1 e) 1 f) 250 | a) 12 b) 60 c) 4 d) 1 e) 1 f) 500 | a) 12 b) 60 c) 5 d) 1 e) 1 f) 750 | a) 12 b) 60 c) 5 d) 1 e) 1 f) 1000 | a) 26 + 42 Sprint Reports b) 154 + 240 Medium posts c) 10 + 18 Case Studies d) 2 + 4 Learning Events e) 2 + 4 Research Publications f) 150 + 850 followers | Assumes 2 Sprint Reports per contracted project, and one Case study per contracted project (even if it closes early, a case study of why has value)
|  | Achieved |  |  |  | b) 41 | a) 15 b) 69 c) 0 d) 1 e) 1 f) 277
Source
Annual and Quarterly reports / Medium channel analytics
IMPACT WEIGHTING (%)
25%
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | [6 empty] | DFID SHARE (%)
| £2.5m + £6.55m |  | 0 | £1.8m + £2.4m | £14.7m | [6 empty] | 70% | RISK RATING
INPUTS (HR) | DFID (FTEs) | [11 empty] | M
0.2FTE + 0.2FTE
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025 | Assumptions
Innovative Partnerships | Number of a) active partnerships b) innovations supported under total partnerships | Planned |  |  |  |  | a)1 b) 5 | a) 2 b) 10 | a) 2 b) 10 | a) 1 b) 5 |  | a) 4 b) 20 | Assuming an average partnership length of 12 months to maintain between 1-3 partnerships at any point in time (and flexible FTE availability).
|  | Achieved |  |  |  |  | a)2 b)12
Source
Annual Review
| Output Indicator 3.2 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025 | Assumptions
| DSTL ALMRS: Number of technology applications and delivery models for development/humanitarian developed/demonstrated or supported in Phase 2 | Planned | 0 | - |  |  | 0 | 6 |  |  |  |  | Correct incentives exist for existing suppliers to engage meaningfully with humanitarian stakeholders, and thse relationships will last beyond Phase 2
|  | Achieved |  |  |  |  | 3
Source
Demonstration events throughout Phase
| Output Indicator 3.3 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025 | Assumptions
| IDIA: Number of innovation learning resources accessed through / co-created / shared with IDIA Members | Planned | 0 | - |  |  | 4 | 8 | 8 | 8 | 8 | 20
|  | Achieved |  |  |  |  | 4
Source
IDIA Quartetly Meetings, Working Group Attendance
| Output Indicator 3.4 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025 | Assumptions
| Crowdpower: programme is successfully closed under Ideas 2 Impact and learnings used elsewhere | Planned | 0 | - | - | - | Crowd power final report delivered and shared in the energy sector but also more broadly.
|  | Achieved |  | - | - | - | Report was delivered in June 2018. Evidence from the Crowd Power programme formed the basis for the Energise Africa initiative under TEA, which was launched in October 2017.
Source
IMPACT WEIGHTING (%)
25% | [12 empty] | Risk Rating
INPUTS (£) | DFID (£) | Govt (£) |  | Other (£) |  | Total (£) |  | DFID SHARE (%)
£3.2m + 845,000
INPUTS (HR) | DFID (FTEs)
0.1
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025 | Assumptions
Assistive Technology
| Coordinating research, evidence, and impact: (a) number of papers on critical AT topics, (b) number of methodologies for Market Shaping and Return on Investment, (c) number of research conducted on stigma, mobile access, and innovation, | Planned |  |  |  |  | (a) 1 (b) 0 (c) 0 | (a) 4 (b) 1 (c) | (a) 4 (b) (c) 1 | (a) 1 (b) 1 (c) 2 |  | (a) 10 (b) 2 (c) 3 | This refers to academic publications, resaerch conducted by partners, strategy documents and the two new methodologies
|  | Achieved |  |  |  |  | (a) 2 (b) 0 (c) 0 | (a) (b) (c) | (a) (b) (c) | (a) (b) (c) |  | (a) 2 (b) (c)
Source
| Output Indicator 4.2 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025 | Assumptions
| Sparking innovation: (a) number of start-ups supported and (number of disruptive technologies developed), (b) number of innovative finance and business models tested, (c) number of innovative service delivery models tested in LICs, | Planned |  |  |  |  | (a) 1 (0) (b) 0 (c) 0 | (a) 10 (3) (b) 1 (c) 2 | (a) 10 (3) (b) 1 (c) 2 | (a) 9 (4) (b) (c) 2 |  | (a) 30 (10) (b) 2 (c) 6 | Assume 'start ups' will be supported mainly throught the Keyna ecosystem, and that this will include the proposed 10 new technologes
|  | Achieved |  |  |  |  | (a) 2 (0) (b) 0 (c) 0 | (a) (b) (c) | (a) (b) (c) | (a) (b) (c) |  | (a) 2 (0) (b) (c)
Source
| Output Indicator 4.3 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025 | Assumptions
| Opening-up market access: (a) number of APL procurement specifications developed, (b) number of procurement manuals developed, (c) number of country pilots, | Planned |  |  |  |  | (a) 0 (b) 0 (c) 0 | (a) 15 (b) 1 (c) 1 | (a) 14 (b) (c) | (a) 1 (b) (c) |  | (a) 30 (b) 1 (c) 1 | This incorporates the 6 innovative service delivery models
|  | Achieved |  |  |  |  | (a) 0 (b) 0 (c) 0 | (a) (b) (c) | (a) (b) (c) | (a) (b) (c) |  | (a) (b) (c)
IMPACT WEIGHTING |  | Source
25%
Inputs(£) | DFID (£) | Govt (£) |  | Other (£) |  | Total (£) |  | DFID SHARE (%) |  |  |  |  | Risk Rating
£10m
INPUTS (HR) | DFID (FTEs)
0.4FTE + 0.2FTE
OUTPUT 5 | Outcome 5.1 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025 | Assumptions
Project-level research, Learning and Knowledge Sharing (CCMEL)
| Number of cross-I2I learning events and workshops delivered (outreach) | Planned |  |  |  |  | 0 | 1 | 1 | 1 | 1 | 4 | There is budget for one learning event per year where different strands of I2I will come together, as well as stakeholders in the innovation community
|  | Achieved |  |  |  |  | 1
Source
| Output Indicator 5.2 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total Target Date 2025 | Assumptions
| Number of cross-I2I research studies completed (review and research) | Planned |  |  |  |  | 0 | 2 | 2 | 2 | 2 | 8 | Formal studies, reviews and learning documents (such as case studies, blogs and lectures) created for the I2I programme as a whole, involving all strands
IMPACT WEIGHTING |  | Achieved |  |  |  |  | 0
Source
10
INPUTS (£) | DFID (£) | Govt (£) |  | Other (£) |  | Total (£) |  | DFID SHARE (%) |  |  |  |  | Risk Rating
2m
INPUTS (HR) | DFID (FTEs)
0.2

## Outcomes
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total (2025)
Affordable and accessible technologies and innovations are developed and deployed | Number of technologies, new processes and services, and new business models being developed/adopted/scaled-up directly or indirectly | Planned |  | 0 | 12 | 18 | 2 | 0 | 0 | 0 | 0 | 170 (148 developed, 22 deployed)
Achieved
Source
Routine Results Reporting by M&E team Individual prize M&E reports published post-prize
| Outcome Indicator 2 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total (2025) | Assumptions
| Additional a) private investment and b) public finance leveraged to support technological innovations and business models | Planned | [9 empty] | 1:1 on pilot investments overall (£35m) | Other key areas to tackle poverty are successfully addressed including: - policies and regulations - institutional requirements - corruption International and local investors are willing to invest in the deployment of solutions in countries. appropriate partner programmes are willing to collaborate willing target countries with appropriate enabling environments can be identified and are able to effectively respond Winning projects are able to be replicated, scaled up and costs reduced. Successful ventures raise public and investor awareness of opportunities.
Achieved
Source
Routine Results Reporting by M&E team Individual prize M&E reports published post-prize
| Outcome Indicator 3 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total (2025)
| Number of services (inc. technological innovations and business models) supported by the programme that show indication of replication | Planned
Achieved
Source
Routine Results Reporting by M&E team
| Outcome Indicator 4 |  | Baseline | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | Milestone 6 2020/2021 | Milestone 7 2021/2022 | Milestone 8 2022/2023 | Cumulative Total (2025)
| Number of changes in policy (internal or external) as a result of programme activities, or cases where the programme supports the creation of a more enabling policy environment | Planned | 0 (2014)
Achieved
Source
Programme Media Log
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | [6 empty] | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
0.5

## Output 1.3 (hidden)
INDICATORS OF:
#REF!
work in progress - to be completed by end of March (to go in Annual Report)
Geographical and sectoral reach of the prize launch activities (broken down by [communications] channel)
Number of visits made to the Prize webpage
Ratio of solutions submitted, to number registering interest
Ratio of solutions submitted by eligible solvers, to solutions submitted
Ratio of solutions meeting all criteria compared to total submitted.
% of applicants still working towards the prize
Regional distribution of solvers and winners
Sectoral distribution of solvers and winners
Number of winners who are new to the field of endeavour, DFID or other donor funding
|  |  | #REF! | #REF! | #REF! | #REF! | Milestone 5 2019/20 | #REF! | Total
Urban Sanitation
|  | Description -effects intended (from ToC) |  | Ratio of solutions submitted, to number registering interest | % of applicants still working towards the prize | Ratio of solutions submitted by eligible solvers, to solutions submitted | Ratio of solutions submitted by eligible solvers, to solutions submitted
|  |  |  | Ratio of solutions submitted by eligible solvers, to solutions submitted |  | Ratio of solutions meeting all criteria compared to total submitted. | Ratio of solutions submitted by eligible solvers, to solutions submitted
Dreampipe
|  | Description -effects intended (from ToC) |  | Ratio of solutions submitted, to number registering interest | Ratio of solutions submitted, to number registering interest
|  |  |  | Number of visits made to the Prize webpage | Ratio of solutions submitted by eligible solvers, to solutions submitted
Regional distribution of solvers and winners
Sectoral distribution of solvers and winners
Number of winners who are new to the field of endeavour, DFID or other donor funding
|  |  |  | Geographical and sectoral reach of the prize launch activities (broken down by [communications] channel) | Ratio of solutions meeting all criteria compared to total submitted.
Cylinder
Description -effects intended (from ToC)
Adaptation at Scale
Description -effects intended (from ToC)
Climate Information
Description -effects intended (from ToC)
Other EA?
Description -effects intended (from ToC)
| Total |  | 0 | 0% | 0% | 0% |  | 0% | 0%

## Output 2.2 (hidden)
INDICATORS OF:
No. of Frontier Technology Grants Awarded
|  |  | Milestone 1 2015/16 | Milestone 2 2016/17 | Milestone 3 2017/18 | Milestone 4 2018/19 | Milestone 5 2019/20 | #REF!
| Call 1 |  | 0 | 0 | 5 | 0 | 0 | 5
| Call 2 |  | 0 | 0 | 5 | 0 | 0 | 5
| Call 3 |  | 0 | 0 | 0 | 8 | 0 | 8
[5 empty] | 10 | 8 |  | 18
Grants as part of Call 1 expected be formally awarded in March / April, 2017. For the purposes of this framework, it is considered to be ending after April 1st, 2017, and therefore falls under the year 2017/2018.
Call 2 to be launched in April, 2017 and be completed in October, 2017.
Grants as part of Call 3 expected be formally awarded in March / April, 2018. For the purposes of this framework, it is considered to be ending after April 1st, 2018, and therefore falls under the year 2018/2019.
Assumed that five grants will be awarded per call, but we have committed to being flexible to awarding greater or fewer numbers depending on the strength of applications during a particular period.