Type of Review: Annual Review

Project Title: Sudan Free of Female Genital Cutting

Date started: 01/10/2013[1]	Date review undertaken: 21/03/2014
[1] The start date as per ARIES is March 2013; however the actual start date of implementation was October 2013.

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK will provide £12 million over 5 years, 2013/14 to 2017/18; this is the first 5 year phase of a potential 10 year programme to support national efforts to end the practice of Female Genital Cutting (FGC) in Sudan. / This DFID Sudan country led programme will complement a planned programme for up to £30 million over 5 years led by DFID Africa Regional Department and the AIDS and Reproductive Health Team, Policy Division. This will further increase the reach and impact of DFID’s overall support to efforts to end FGC globally and in Sudan. / This programme will deliver DFID Sudan’s commitment in its Operational Plan to support DFID’s Strategic Vision for Girls and Women: Stopping Poverty Before It Starts by contributing to three of its four pillars: Delaying first pregnancy and support safe childbirth; Getting girls through secondary school; and, Preventing violence against girls and women. The programme will also deliver results against Pillar 1, Empower women and girls to make healthy reproductive choices, of the UK’s Framework for results for improving reproductive, maternal and new-born health in the developing world.

What are the expected results?
The main project outcome is: To decrease the prevalence of Female Genital Cutting in Sudan thereby promoting gender equality and empowerment of women (MDG3) / The planned outputs attributable to UK support are; / 1. Legislation is in place to support FGC abandonment, including specific bans in all States; / 2. Policies, standards and codes of conduct are in place to prevent and address FGC; / 3. Evidence and data systems on FGC strengthened to inform policy; / 4. Strengthened national capacities to achieve abandonment; / 5. Mechanisms to coordinate FGC activities strengthened; / 6. Shift in social norms through evidence based behaviour change communication. / Specific results will include: / Reduction in prevalence rate, for all girls and women, of 3% (from 2010 to 2016); / Reduction in women who believe the practice should continue by 10% (from 2010 to 2016); / 1400 communities declaring public commitment to abandonment by 2017 / Reducing the prevalence of FGC will deliver both individual and social returns including economic, social and intergenerational health benefits. The intended direct beneficiaries of this programme will be the girls and women who will no longer undergo FGC. The indirect beneficiaries of this programme will be the families, households and communities who will no longer bear the full health, economic and social costs of FGC.

What is the context in which UK support is provided?
Female genital cutting, also known as female genital mutilation or female ‘circumcision’, is one form of gender based violence. It refers to a set of practices involving the partial or complete removal of the external female genitalia or other injury to the female genital organs for non-medical reasons. It is mostly carried out on young girls sometime from birth up to pre-adolescence, and invariably before first menstruation and marriage. Between 100 and 140 million women and girls in the world have undergone some form of FGC. A further 3 million girls are at risk of being cut annually. FGC is recognised internationally as a violation of the human rights of girls and women. It reflects deep seated inequality between the sexes. / There is a clear case for a long term programme supporting the abandonment of Female Genital Cutting in Sudan: / FGC poses serious physical and mental health risks for girls and women, especially for women who have undergone extreme forms of the procedure as in Sudan; / FGC hinders the full empowerment and involvement of girls and women in many areas of society; / The UK government condemns FGC as a serious human rights abuse against girls and women; / At 89% Sudan has one of the highest rates of FGC (for girls and women aged 15-49) in the world (after Somalia 98%, Guinea 96%, Sierra Leone 94%, Djibouti 93%, and Egypt 91%); / Without comprehensive and coordinated support to the National Strategy its ambitious goal of ending FGC within a generation (2008-2018) is unlikely to be achieved. / There is increasing interest in FGC in the UK in Parliament; a new All Party Parliamentary Group focussing on the issue was established in December 2011. The African Union agreed on 1st July 2011 to support a resolution at the United Nations General Assembly (UNGA) to ban the practice. On 20th December 2012, the UN General Assembly adopted a resolution calling for an end to the practice.

## Section A: Detailed Output Scoring

Output 1: Legislation is in place to support FGC abandonment, including specific bans in all States
Output 1 score and performance description: B: Outputs moderately did not meet expectation
Progress against expected results: / Due to delays in start-up actual project activities only started in October 2013 when DFID signed the agreement with the implementing partners. Although we are making good progress, it is unlikely that we will meet agreed milestones due to this delay in start-up. / Indicator 1.1: Number of States with a ban on FGC / Planned Annual Milestone (Oct 2014): Legislative review completed in 3 States. / Completed Activities: / An agreement with the Society Studies Centre (SSC) has been signed to draft recommendations for enforcement of existing FGC. Law banning FGC in South Kordofan, South Darfur and Gedaref states. / The Centre for Violence Against Women (CVAW) received funds to support the established ‘National Committee on Law Reform’ regarding FGC and child marriage. / Discussions initiated with the WHO East and Mediterranean Regional Office (EMRO) for timely recruitment of Azhar scholars as required by the three agencies. / Preliminary coordination and consultation activities of relevant stakeholders, such as National Council for Child Welfare (NCCW), State Council of Child Welfare (SCCW) in South Kordofan, South Darfur and Gedaref states, Women’s Centre for Human Rights, National Women’s Parliamentarian Caucus, Parliamentary Commission for Social Welfare and Health and civil society organizations, on the enforcement of laws to ban FGC at the state level will be conducted in February and March 2014. / A desk review of existing laws in the selected states and comparative analysis with the drafted national law will be conducted in March and April 2014. / Analysis on law enforcement in each state, based on case studies analysis and assessment on challenges and opportunities will be conducted on April and May 2014. / An agreement has been signed with SSC as an implementing partner. The cooperation with SSC provides a valuable network of connections useful 1) to advocate for the enforcement of the FGC law and 2) to support the process to increase the number of states with a law to ban FGC. / The existing cooperation between WHO regional office and Azhar, as a renowned and esteemed institute, offers successful experiences on which Sudan can build their FGC abandonment efforts as Islamic scholars are well respected by government officials. / Indicator 1.2: Number of States with action plan for enforcement of legislation established & implemented. / Planned Annual Milestone (Oct 2014): Recommendations for action plans shared with States / Completed Activities: / A National Action Plan for Combating Violence Strategy was created. / One monthly forum with NGOs to discuss the issues of GBV including reviewing national laws and state policies and develop strategy/plans where applicable at state level. / Workshop on referral pathway at state level (one state) / Recommendations: / Continuously engage with civil society and women group and construct activities in a way which will ensure the programme can easily accommodate changes in government officials and/or positions. / Jointly with partners hold a milestone review in October 2014 to assess progress / On the next annual review, we need to be more specific about the quality of the processes we are supporting, the extent to which they are collectively adding up to a critical mass of activities that is beginning to translate in impact on the ground / Impact Weighting (%): 05 / Revised since last Annual Review? NO / Risk: Medium / Revised since last Annual Review? NO

Output 2: Relevant policies, standards, and codes of conduct are in place to support abandonment of FGC and address its impacts
Output 2 score and performance description: B: Outputs moderately did not meet expectation
Progress against expected results: / Due to delays in start-up actual project activities only started in October 2013 when DFID signed the agreement with the implementing partners. Although we are making good progress, it is unlikely that we will meet agreed milestones due to this delay in start-up. / Indicator 2.1: Number of nationally endorsed health sector standards on FGC priority health areas (counselling, management of clinical complications, reconstruction) / Planned Annual Milestone (Oct 2014): Research findings available to inform protocol development. / Completed Activities: / Preliminary consultation meetings with NCCW and Federal Ministry of Health (FMoH) conducted to coordinate responsibilities and Standard Operating Procedure (SOP) objectives. / Selected a consultant to draft SOPs in consultation with NCCW, FMoH, SCCW and SMoH. / Discussions initiated with WHO regional offices and Khartoum office and sharing of all available material. / Plans to work with FMoH on reviewing national guidelines and identify gaps in curricula initiated. / Monitoring tour in 18 ‘Born Saleema’ health care facilities to assess needs, procedures and Saleema activities in order to draft SOPs. / A number of leading obstetricians have expressed their readiness to support the area of FGC reconstructive surgery and one of them is currently very active in delivering the service to volunteering women. The upcoming fora present an opportunity for engaging target health professionals. / Indicator 2.2: Number of nationally endorsed sectoral policies & strategies for 2017-2021 aligned to national strategy for FGC abandonment / Planned Annual Milestone (Oct 2014): Participation of 7 relevant Ministries in FGC coordination mechanism / Completed Activities: / Coordination meetings with NCCW, FMoH, SCCW and State Ministry of Health (SMoH), UNFPA and WHO were conducted in February 2014. / The functional national FGC task force was formed with representatives from; departments/units of the Ministry of Welfare and Social Security (Combating Violence against Women Unit - Child and Family Protection Units; General Directorate of Women; Women Centre for Human Rights and NCCW), Ministry of Health, Ministry of Education, National Population Council, Central Bureau of Statics, national television and radio, Ahfad University for Women (AUW), Midwifery Association, Obstetrics & Gynaecology Association; Ministry of Guidance and Endowment, UNFPA, UNICEF, WHO, Care International and Plan Sudan. / Indicator 2.3: Number of medical schools and institutes incorporating FGC in pre-service curricula. / Planned Annual Milestone (Oct 2014): Research findings available to inform curriculum development / Completed Activities: / SOPs drafted and will be shared with partners in April/ May 2014. Once the Born Saleema SOPs are endorsed by the major counterparts, it will generate an opportunity to scale up the Born Saleema initiative - potentially as standard operating procedures in all the health care facilities reporting to SMoH and FMoH. / Manuals/protocols shared by WHO regional office and headquarters with the Ministry of Health. / Identify gaps in medical curricula, including those relating to reconstructive surgery. / Recommendations: / Continuously engage with civil society and women group, and construct activities in a way which will ensure the programme can easily accommodate changes in government officials and/or positions. / Jointly with partners hold a milestone review in October 2014 to assess progress / On the next annual review, we need to be more specific about the quality of the processes we are supporting, the extent to which they are collectively adding up to a critical mass of activities that is beginning to translate in impact on the ground / Impact Weighting (%): 10 / Revised since last Annual Review? NO / Risk: Medium / Revised since last Annual Review? NO

Output 3: Evidence and data systems on FGC strengthened
Output 3 score and performance description: B: Outputs moderately did not meet expectation
Progress against expected results: / Due to delays in start-up actual project activities only started in October 2013 when DFID signed the agreement with the implementing partners. Although we are making good progress, it is unlikely that we will meet agreed milestones due to this delay in start-up. / Indicator 3.1: Status of baseline assessment and monitoring system on prevalence of re-infibulation / Planned Annual Milestone (Oct 2014): Baseline established / Completed Activities: / The study concept note has been drafted and discussed with partner and Request for Proposal was issued in October 2013. The selection process identified a suitable consultancy firm to undertake the study. / The first phase of the rapid assessment has been finalized in Kassala, Gedaref, Northern State, South Darfur, North Darfur and West Darfur states. The results were received in November 2013. / Research areas for Year 1 were selected based on information gaps, while ensuring consistency and complementarity of the proposed research areas in Sudan with those on the global agenda. / WHO study in Nigeria on psycho-sexual research on perceptions regarding sexuality, reproductive health and FGC was reviewed to determine how it will inform the study in Sudan. / Discussions initiated with Ministry of Health and the Central Bureau of Statistic to generate baseline information on re-infibulation through the upcoming Multiple Indicator Cluster Survey (MICS) 2014 survey. / The first phase of the Baseline study on impact and behavioural change: acceptance of Saleema terminology and understanding of connotation of Saleema will be completed in March. The study is coordinated with NCCW. / A rapid assessment of social marketing tools in 6 states has been completed and the results presented at the NCCW Social Norms Working Group in February 2014. Follow up Rapid Assessment in the six tested states to be completed by August 2014. / The Sudan Household Health Survey Steering Committee, led by Central Statistics Bureau, agreed to include a question related to the use of the word ‘Saleema’ to describe an uncut girl in the 2014 Sudan Household Health Survey/MICS survey questionnaire. / Indicator 3.2: Number of sentinel sites established. / Planned Annual Milestone (Oct 2014): Surveillance system developed / Completed Activities: / Terms of References have been developed, experts (international + national consultant) have been identified, and concept paper designed with the purpose of conducting a desk review and identifying existing research. / The identification of a national consultant to carry out the surveillance assessment is ongoing. The panel is conducting the review and selection of the applicants. / Indicator 3.3: Status of research strategy / Planned Annual Milestone (Oct 2014): Adoption of research strategy by steering committee / Completed Activities: / Two meetings were conducted (6 February and 23 July) at the WHO premises to brainstorm and identify priority research areas that need to be addressed by the three agencies. National FGC experts were invited to share their views and give their inputs on the research framework in its entirety, including the needed implementation arrangements. / Sudan FGC research strategy was drafted; an international consultant was hired and started the desk review, identification of key information gaps, and development of a research framework for tendering. Consultations are ongoing to streamline with the global research strategy. / Recommendations: / Continuously engage with civil society and women group, and construct activities in a way which will ensure the programme can easily accommodate changes in government officials and/or positions. / Jointly with partners hold a milestone review in October 2014 to assess progress / On the next annual review, we need to be more specific about the quality of the processes we are supporting, the extent to which they are collectively adding up to a critical mass of activities that is beginning to translate in impact on the ground / Impact Weighting (%): 20 / Revised since last Annual Review? NO / Risk: Medium / Revised since last Annual Review? NO

Output 4: Mechanisms to coordinate FGC activities strengthened
Output 4 score and performance description: B: Outputs moderately dod not meet expectation
Progress against expected results: / Due to delays in start-up actual project activities only started in October 2013 when DFID signed the agreement with the implementing partners. Although we are making good progress, it is unlikely that we will meet agreed milestones due to this delay in start-up. / Indicator 4.1: The status of the National Task Force coordinating FGC abandonment activities. / Planned Annual Milestone (Oct 2014): Partners capacities assessed; reporting lines at key levels identified / Completed Activities: / An agreement on the planned activities to be implemented under this output has been created through a consultative process with four partners. The agreement with NCCW was finalized and signed. The agreements have been drafted and finalized but not yet signed by the other three partners: Federal Ministry of Health, State Ministry of Health & Ministry of Welfare and Social Services. / A coordination meeting to plan 2014-2015 activities and to strengthen reporting mechanisms was organized in December 2013 with representatives from SCCW in Khartoum, Sennar, White Nile, River Nile and Gezira states. / Methodology agreed with NCCW for community level mapping of interventions and partners in all states. / An advocacy and visibility event has been organized by NCCW, with the financial support of UNICEF, to celebrate the International Day against FGC on the 6th of February. Stakeholders, media and Sufara’a Saleema attended the event. / The needs assessment is completed in the process to identify the best way to establish national coordination mechanisms that will monitor the implementation of national policies and strategies nationwide. / The existing government Women Empowerment Policy, National Plan on Gender Based Violence, Maternal Child Health Acceleration Plan and Reproductive Health Policy are being used to strengthen the national efforts on abandonment of FGC. / Support to the FMoH for the abandonment of FGC through this joint program is providing an excellent opportunity for the program to make use of the existing human resources and systems at national and state levels as well as strengthening the capacity of health personnel on FGC related issues. / Identification of capacity gaps of potential partners through a capacity assessment exercise to guide the planning for capacity building interventions. Implementation of planned capacity building activities within the proposed integrated training packages for the existing Government Primary Health Care (PHC) expansion project. / Indicator 4.2: Regular monitoring meetings/events at national and state levels organized and reports disseminated / Planned Annual Milestone (Oct 2014): Monitoring mechanisms and frequencies identified. / Completed Activities: / To establish a more effective national system for better coordination, the following activities have started in the first and will continue in the second quarter of 2014; / Supporting the draft of FGC law at the national level. / Developing scientific papers about Muslim Personal Law and Criminal Law 1991. / Supporting the establishment and coordination of intervention activities on FGC at the state level. / Supporting monitoring and evaluation and capacity building activities. / Integrating educational dialogue on FGC in the education sector. / FGC regular coordination meetings are supported and in June 2014, the FGC monitoring system will start covering all states (e.g., communities reached, number of public declarations, counselling and commitments in Born Saleema hospital settings). / Recommendations: / Continuously engage with civil society and women group, and construct activities in a way which will ensure the programme can easily accommodate changes in government officials and/or positions. / Jointly with partners hold a milestone review in October 2014 to assess progress / On the next annual review, we need to be more specific about the quality of the processes we are supporting, the extent to which they are collectively adding up to a critical mass of activities that is beginning to translate in impact on the ground / Limited access for international consultants to some project sites needs to be taken in consideration as a potential constraint. In order to overcome this problem the monitoring and evaluation framework is being developed in close collaboration with NCCW and with a national research institution which has been identified as an implementing partner and contracted to visit & finalize the M&E framework from April to June 2014. / Impact Weighting (%): 10 / Revised since last Annual Review? NO / Risk: Medium / Revised since last Annual Review? NO

Output 5: Strengthened national capacities (Government, Non-Government Organisations, and Community Based Organisations) to achieve abandonment
Output 5 score and performance description: B: Outputs moderately did not meet expectation
Progress against expected results: / Due to delays in start-up actual project activities only started in October 2013 when DFID signed the agreement with the implementing partners. Although we are making good progress, it is unlikely that we will meet agreed milestones due to this delay in start-up / Indicator 5.1: Percentage of health facilities providing a comprehensive package of FGC abandonment services (actual number of existing health facilities currently being compiled). / Planned Annual Milestone (Oct 2014): Research findings available to inform protocol development / Completed Activities: / The Saleema toolkit concept note has been developed. Consultation are ongoing with NCCW and CSOs to receive comments on the drafted concept note for Toolkit this month March 2014 and the English & Arabic contents will be finalized in May 2014. / An international consultant to finalize concept note and toolkit contents has been selected. / The Saleema national Convention tentatively planned for Aug/Sep 2014. / A Long Term Agreement with the communication company tasked to produce the toolkit has been signed. / AUW and its constituencies at the national and state levels have planned support and capacity building interventions (advocacy and awareness promotion). / An agreement is in place for AUW to conduct capacity building and training of Four Community Based Organizations (CBO) in Gedarif State on issues of 'FGC and Child Marriage.' / An agreement is in place with AUW for the following activities: / Train cadre in dissemination of knowledge and communication initiatives. / Conduct studies on the sociocultural and gender related factors influencing FGC and child marriage. / Conduct training workshops in Policy Communication for researchers and CSOs and in advanced Research Methods for researchers & NGOs. / Conduct TOT in gender and reproductive health for implementing partners. / A rapid assessment of Social Marketing tools in 6 states has been completed and the results presented at the NCCW Social Norms Working Group in February 2014. Follow up Rapid Assessment in the six tested states to be conducted by August 2014. / Indicator 5.2: Status of midwifery curriculum to include abandonment of FGC and training programme / Planned Annual Milestone (Oct 2014): Consensus and agreement with MoH reached and consultant recruited. / Completed Activities: / Discussions initiated with the ministry to implement training for doctors, medical assistants, midwives, and community health workers as part of the training packages proposed for the Primary Health Care Expansion Project. / Plans to liaise with OB/GYN Society and Midwifery Association to enhance their role in abandonment efforts. Discussions will include technical support for surgical management of FGC. / Indicator 5.3: Number of communities with leaders (religious, tribal) and community health promoters actively involved in FGC abandonment / Planned Annual Milestone (Oct 2014): 530 communities / Completed Activities: / An agreement is in place for AUW, NCCW, MoGE and FMoH to support the development of a Communication Plan for ‘Al-Mawada and Al-Rahma’ campaign and align it to partners’ strategy. In addition, the training of politicians, religious and community leaders on FGC and gender issues in reproductive health will be contained within this campaign. / NCCW organized a zero tolerance day ceremony on the 6th of February in collaboration with Ministry of Guidance and Endowment (MoGE) under this campaign / Recommendations: / Continuously engage with civil society and women group, and construct activities in a way which will ensure the programme can easily accommodate changes in government officials and/or positions. / Jointly with partners hold a milestone review in October 2014 to assess progress / On the next annual review, we need to be more specific about the quality of the processes we are supporting, the extent to which they are collectively adding up to a critical mass of activities that is beginning to translate in impact on the ground / Impact Weighting (%): 15 / Revised since last Annual Review? NO / Risk: Medium / Revised since last Annual Review? NO

Output 6: Shift in social norms through evidence based behaviour change communication
Output 6 score and performance description: B: Outputs moderately did not meet expectation
Progress against expected results: / Due to delays in start-up actual project activities only started in October 2013 when DFID signed the agreement with the implementing partners. Although we are making good progress, it is unlikely that we will meet agreed milestones due to this delay in start-up / Indicator 6.1: Percentage of women who believe the practice of FGC should continue / Planned Annual Milestone (Oct 2014): 38%. / Completed Activities: / A briefing note has been developed and a long term agreement with the communication company to produce the radio drama has been signed. / Lack of common understanding among the government institutions of Saleema guidelines which has been identified as a constraint to strength the Saleema movement impact, and to address that Saleema toolkit is developed and potentially increase the number of institutional partners, NGOs and civil society organisations supporting the Saleema movement. / Within the reporting period, the Saleema Ambassadors TV public service announcement (PSA) has been broadcasted nationwide more than 500 times and the Saleema Ambassadors Radio PSA more than 1,000 times, reaching a potential audience of 80% of the total population. / A Long Term Agreement has just been signed with marketing / Communications Company to facilitate speed and agility in scaling up coverage of behavioural change communications tools. / To strengthen the implementation and synergize the impact of the activities, a cooperation between the SMoH as a governmental body and AUW as an academic institute and its constituencies has been developed. / The involvement of the Ministry of Guidance and Endowment (MoGE) in developing media messages on FGC abandonment is an added value and will strengthen the messages. MoGE will produce CDs and theater plays. / Production of Saleema cloths, Saleema stickers, Saleema posters and Saleema leaflets has been completed. / The Saleema branding was refreshed in nine health care facilities in Khartoum State and a Born Saleema focal point was established in each of the nine facilities to support counselling and public awareness activities. / States Ministries of Health and AUW, through other sub-contractors, have agreed to be involved in behaviour change communication (BCC) activities at the community level in the three targeted states. / Agreements are in place for the design of appropriate media messages and the training of journalists. / Sudan is being included in the regional Social Change Communication Campaign for which the contracted consultancy firm will be visiting Sudan in this month March 2014. / Indicator 6.2: Number of communities (each average 2,000 population) declaring public commitment to abandonment / Planned Annual Milestone (Oct 2014): 800 communities / Completed Activities: / Saleema community dialogue activities reached 80 new communities during the reporting period and 15 community public declarations of FGC abandonment were declared. / Radio drama script on FGC developed and under approved by NCCW to be broadcasted initially in River Nile State by April 2014. / Ongoing Saleema community dialogue activities, / Maintenance of Born Saleema Programme, including indoor/outdoor visibility and counselling training for health care providers targeting; / Ongoing preparations to; produce Saleema notebooks in April 2014 & Saleema tool kit in June 2014; conduct the counselling training in June and to start a Billboard campaign in September 2014. / The ongoing maintenance of Born Saleema branding in six states will be completed by June 2014. / Indicator 6.3: Percentage of women who intend or not intend to undergo re-infibulation. / Planned Annual Milestone (Oct 2014): Baseline and monitoring mechanism established / Completed Activities: / Radio drama script on FGC developed and under approved by NCCW to be broadcasted initially in River Nile State by April 2014. / Ongoing Saleema community dialogue activities, / Maintenance of Born Saleema Programme, including indoor/outdoor visibility and counselling training for health care providers targeting; / Ongoing preparations to; produce Saleema notebooks in April 2014 & Saleema tool kit in June 2014; conduct the counselling training in June and to start a Billboard campaign in September 2014. / The ongoing maintenance of Born Saleema branding in six states will be completed by June 2014. / Within the reporting period, the Sufara’a Saleema TV public service announcement (PSA) has been broadcasted nationwide more than 500 times and the Sufara’a Saleema Radio PSA more than 1,000 times, reaching a potential audience of 80% of the total population. / The involvement of the Ministry of Guidance and Endowment (MoGE) in developing media messages on FGC abandonment is an added value and will strengthen the messages. MoGE will produce CDs and theater plays. / Saleema community dialogue activities reached 80 new communities during the reporting period and 15 community public declarations of FGC abandonment were declared. / Production of Saleema cloths, Saleema stickers, Saleema posters and Saleema leaflets has been completed. / Recommendations: / Continuously engage with civil society and women group, and construct activities in a way which will ensure the programme can easily accommodate changes in government officials and/or positions. / Jointly with partners hold a milestone review in October 2014 to assess progress / On the next annual review, we need to be more specific about the quality of the processes we are supporting, the extent to which they are collectively adding up to a critical mass of activities that is beginning to translate in impact on the ground / Impact Weighting (%): 40 / Revised since last Annual Review? NO / Risk: Medium / Revised since last Annual Review? NO

## Section B: Results and Value for Money.

1. Progress and results

Has the logframe been updated since last review? NO / 1.2 Overall Output Score and Description: B: Outputs moderately did not meet expectation / Recommendation: / DFID needs to be clear on internal processes and adjust project timelines accordingly. In doing so, it needs to consider realistic project deliverables during the implementation period. / Direct feedback from beneficiaries / 1. DFID Social Development Adviser and Senior Deputy Programme Manager joined UNICEF on a mission to Dongola, Northern State in February 2013. The visit provided an opportunity to understand better some of the political, institutional and social challenges of ending the practice in Northern State. During the visit the team met and develop relationships with local counterparts, visited the obstetric section of Dongola Public Hospital (meeting with the hospital administrator and Saleema nurse midwives), El’Imtidad Health Centre, with AlBourgeg community Saleema advocacy groups (school children, community midwives, mothers and grandmothers). The main findings were: / There is a high level of commitment within the State Government to end the practice; / There is high potential for progress on FGC in the State and the knock-on impacts of this in other parts of Sudan due to the extensive familial networks among the Nubian communities in the country. The Nubian diaspora will have an important role to play in ending the practice; / health professionals, including midwives, have an important contribution to make in ending the practice / the Legislative Council recognises the importance of legislation in contributing to banning the practice but it nervous about criminalising a practice that is so strongly rooted in social practice; / In conclusion, the visit reinforced the need to work at multiple levels of governance (national, state, locality and sub-locality) and across several coordinated outputs as noted in the business case. Scaling up existing efforts in Northern State is certainly necessary but this will not be straightforward given the high percentage of rural/nomadic communities (at 83%). The potential importance of familial networks is underestimated in current efforts to end the practice. / 2. UNICEF website included a report published on the 7th of February 2014 from Kassala. The report is from the Saudi Hospital, one of the facilities supporting the Saleema Campaign. Saleema means whole, intact in a God-given conditions. Fatima who had a new born girl ‘Imtenan’ said “My daughter will not be cut”. She continued “FGC creates so many problems. It affects a woman during her period. It causes infections. It is a problem early in the marriage, and during pregnancy and delivery. And the child is also affected.” / The report reflected on the positive message the Saleema campaign is delivering, a message which is advocating parents to let their girls remain ‘Saleema’. The campaign is communicated widely through radio and television, and also in many health facilities. The Saleema is part of the National Strategy to abolish FGC in Sudan, which is supervised by the NCCW. For the full report, please refer to: / http://www.unicef.org/infobycountry/sudan_71891.html
Summary of overall progress / The project has only been implemented for four months. The project was internally approved in February 2013 and DFID only signed the agreement with UNICEF (lead partner) in October 2013. The main reason for the delays was that DFID need to complete a due diligence of the three implementing partners UNICEF, UNFPA and WHO and it took longer than originally planned to complete it. Despite the delays, the program is on track for the following reasons: / The intervention is building on what was achieved by the DFID supported UN Joint program (2008 – 2012); / All the necessary processes towards achieving the October 2014 milestones targets are in place. / We have continuously engaged with implementing partners thought the steering committee meetings to address project bottlenecks and challenges. This has been very useful forum to ensure that project keeps on track to achieve the outcome. / Implementing partners already started procurement processes with either consultants or downstream partners. This will allow a smooth implementation of programme activies. / Coordination mechanisms between partners and relevant institutional counterparts initiated. / UNICEF and UNFPA dedicated staff for the programme implementation identified and are in the process to be recruited.
1.5 Key challenges / The main key challenges were and are the following: / Delay in the starting the implementation was not originally foreseen by DFID and partners. / Administrative processes are different for each implementing partners. This can cause some delays, i.e. it was not possible for UNFPA to release the funds to the implementing partners earlier than the beginning of this year 2014 given that they received funds from UNICEF in the quarter 4 of 2013. / The late involvement of the FMoH, due to their reluctance, has delayed the implementation of the WHO activities specially the research component. To ensure ownership and subsequent utilization of the products in future trainings this required a close involvement of the ministry. / The ongoing government reshuffle at the federal and the state (may affect ministers, director generals, etc). This change might bring into power some new personnel and hence might delay and/or derail the course of implementation. / The un-clarity in the position of the Federal Ministry of Health which could be a tactic but it is presenting a serious challenge to the flow of the planned interventions. / The introduction of two initiatives at the DFID headquarters level; the Regional Social Change Communication campaign and the global research strategy, although an opportunity, but in the context of Sudan it is a challenge as well. / Limited access for international consultants to some project sites needs to be taken in consideration as a constraint / It is very difficult to identify national consultants/consultancy firms with required expertise. / The lack of coordination between national and state level is a risk that might potentially result in less effective government support to the Saleema movement.
1.6 Annual Outcome Assessment / As described above in the section 1.4 the project was only implemented for four months. Therefore it’s very difficult to assess at this stage if the project is on track to meet the outcome.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: NO / In October 2013, a 1.5 million was allocated to cover two quarters. The implementing partners were behind schedule in term of recruitment and this had an implication on the level of spending. Thus the allocated 1.5 million is now covering a nine months period instead of six months. / 2.2 Key cost drivers / The main cost drivers identified in the BC were: i) the cost of transport of goods and people, particularly to the more remote parts of the country, and ii) the deployment of private sector expertise for mass marketing. / We are not able to review this cost drivers given the short implementation period. / 2.3 Is the project on-track against original timescale: NO / As outlined through this review, the project experience delays in starting implementation. We may need to consider a no cost extension in the next years to ensure project outcome is met.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There is no change in the theory of change or assumptions. / 3.2 Where an evaluation is planned what progress has been made? / The BC planned a theory of change based and impact evaluation for this programme. We have started the procurement process as outlined below: / The Terms of Reference (ToR) for the evaluation have been developed and screened through the Specialist Evaluation & Quality Assurance Service (SEQAS) service. The review concluded that the ToR were very good and made few recommendations which have been incorporated. / The ToR was submitted to the Global Evaluation Framework. We expect the contract to be signed in June 2014.

4. Risk
4.1 Output Risk Rating: HIGH / 4.2 Assessment of the risk level / There is no change in the risk matrix. / 4.3 Risk of funds not being used as intended / We have not received a financial report. According with our agreement with UNICEF, they will provide six monthly financial reports. The first one is due in April 2014. Once we receive the report we will review and we will take into consideration before the next disbursement.to ensure that funds are spent as originally intended and we are not making payment in advance of need. / Furthermore, we have completed the due diligence of the 3 implementing partners and there is no major financial risks identified. We have been following up with partners on implementation of recommendations from the due diligence. / 4.4 Climate and Environment Risk / According with the BC, the environment and climate change risk is low. There is no change in the risk given the short implementation period.

5. Value for Money
5.1 Performance on VfM measures / The BC identified the VFM measures below. However, we are not able to assess the performance of these measures given the short implementation timeframe. / Cost per case averted and/or the cost to achieve a community pledge. / Medicalization could include the proportion of cuts performed by trained nurses, midwives and doctors; number of health care professionals taking oaths not to perform FGC; number of midwives trained in the abandonment of FGC during their 1, 2 and 4 years education; integration of FGC into the current curriculum of midwifery; number of midwives recruited by government and get salaried; number of midwives organizing and involved in the public declarations; establishment of strong midwives association for midwives’ empowerment and commitment; and the number sanctioned for performing FGC. / During the field visit undertaken by DFID staff, the hospital director, suggested that the estimated additional cost for each child delivery associated with complications arising from FGC is US$20 (including training costs, sutures, pain killers, bandages). / Recommendation: / DFID should work with partners to monitor the additional costs of delivering a child with complications arising from FGC. / 5.2 Commercial Improvement and Value for Money / The Multilateral Aid Review (MAR) assessment of February 2011 provided the following; / Agency Overall VfM Category Comments / UNICEF Very Good Provides services which drive down procurement costs across the UN system / WHO Adequate There is evidence that procurement decisions are driven by value for money. Working to build the evidence base on cost-effective interventions. / UNFPA Adequate A good track record on procurement. Provides services which drive down procurement costs across the UN system. / Furthermore, we have completed the due diligence of the 3 implementing partners and there were no major risks identified. We have been following up with partners on implementation of recommendations from the due diligence. / 5.3 Role of project partners / The main project partners are UNICEF (lead), UNFPA and WHO. To date, the performance of the partners has been satisfactory. There have been some challenges in ensuring coordination between partners and government authorities; however these have been addressed through the steering committee meetings. / 5.4 Does the project still represent Value for Money : YES / Despite the short implementation period, it’s fair to say that this project still represents value for money. In fact, the government has in the last two months raised the profile of FGC. / 5.5 If not, what action will you take? / NOT APPLICABLE

6. Conditionality
6.1 Update on specific conditions / NOT APPLICABLE / NB: The UK’s conditionality only applies to Financial Aid directly given to a partner government

7. Conclusions and actions
Due to delays in start up, the project is currently behind schedule to meeting the October 2014 milestones. However it is important to note that very good progress has been made in the first four months creating a solid foundation for the project to build on and we would anticipate there is good potential for the next Annual Review to improve its score. . / A milestone reviews will be held with partners in 2014 to assess progress and the need for any adjustments. This will include a review process in selected states. / A key objective of the next annual review will be to assess the quality of the processes we are supporting, the extent to which they are collectively adding up to a critical mass of activities that is beginning to translate in impact on the ground. To inform this team will significantly increase the number of field visits it makes over the next year (at least 3 visits). / The main lesson learnt to date is data, DFID needs to be realistic about timescale to completed internal processes and impact that will have in achieving project outcome. For this project, the due diligence process delayed the project start-up by eight months. / Given the sensitivity of this work and to achieve of the project outcomes there is a need to work at multiple levels of governance (national, state, locality and sub-locality) and across several coordinated outputs. Thus, requiring partners to continue to work with key stakeholders at government level and re-build relationships when changes occur. It’s also key to understand the importance of familial networks is underestimated in current efforts to end the practice

8. Review Process
This desk review has been carried out by DFID Sudan with inputs from the implementing partners, UNICEF, WHO and UNFPA and all recommendations and actions are therefore shared. Various documents were used to complete this review, mainly steering committee meeting minutes and one partners’ progress report compiled by UNICEF the lead agency.