Annual Review - Summary Sheet

Title: Humanitarian Assistance and Resilience Building in South Sudan (HARISS)
Programme Value: up to £443 million (£110m in 2015)		Review Date: February 2016
Programme Code: 204019	Start Date: 1 April 2015	End Date: 31 March 2020

Summary of Programme Performance
Year	2015
Programme Score	A+[1]
Risk Rating	High
[1] The score is based on a review of the results of Outcome 1 of the HARISS log frame only as Outcome 2 and 3 are yet to go live.

Summary of progress and lessons learnt since last review
This is the first Annual Review (AR) of Department for International Development’s (DFID) HARISS programme which has been developed to address the shortcomings of annual funding cycles and short-term humanitarian horizons. During its 5-year timeframe the programme will deliver multi-year funding which balances the need for life-saving assistance and resilience building. 2015 is a ‘bridging’ year during which the life-saving humanitarian response has been prioritised while laying the foundations for resilience programming underpinned by stronger evidence of results and impact. A focus on Value for Money (VfM) and community engagement will strengthen the effectiveness of the funding and will be scaled-up in the second year of the programme.

Summary of recommendations for the next year
- There has been significant over-achievement on output 1.1. DFID should reassess milestones to ensure they remain realistic and sufficiently ambitious.
- There would be value in DFID estimating annual output targets by partner to allow greater scope to monitor progress and to frame discussions about performance throughout the year.
- Partner reporting requirements should be harmonised with the calendar year for reporting against outputs to be possible for ARs in the future.
- A focus on achieving outputs (against the HARISS logframe) must be matched by a greater understanding of impact. DFID’s Evidence and Learning Facility (ELF) should have the mandate to make a significant contribution to this.
- It will be important to continue to have protection actors join the Rapid Response Mechanism in order to analyse local dynamics with a view to understanding what the protection threats people are facing are and whether the provision of assistance could be doing more harm than good.
- It will be necessary for DFID to construct a detailed Accountability to Affected People (AAP) baseline which provides details of partners’ corporate commitments and country strategies as well as providing guidance to its partners on expectations for AAP in programme implementation. This will be important for progress against this output to be accurately measured (this activity forms part of the ToR for the Evidence and Learning Facility).
- While the main recipient of the Evidence and Learning Facility of HARISS will be DFID and their partners, there is significant need for high quality evidence to drive a change agenda at the collective level. It will be extremely important for senior DFID South Sudan staff (who have links to the Humanitarian Country Team [HCT] and clusters) to champion the use of evidence in order to close the gap between policy analysis and changed practice.
- During 2016, DFID should discuss with each of its partners the progress that has been made against each of the recommendations of the due diligence assessments.
- As the Common Humanitarian Fund (CHF) risk management framework approaches the end of its first year, DFID should work with the Secretariat to ensure that a ‘substantial review and updating’ occurs as outlined in the framework.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5207793.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5208922.xlsx

Background to the humanitarian crisis in South Sudan: In 2015, the conflict that broke out in South Sudan in December 2013 was still affecting millions of people across the country with widespread displacement, high rates of death, disease and injuries, severe food insecurity, disrupted livelihoods and a major malnutrition crisis. By April 2015, it was estimated that more than 2 million people had been displaced (1.55m people displaced internally with a further 521,660 refugees sheltering in neighbouring countries[2]). Humanitarian activities were ongoing across many parts of the country although access was hampered by violence against aid workers and looting of assets. In the same month, the Integrated Food Security Phase Classification (IPC), registered parts of two states (Upper Nile and Jonglei) at emergency levels (Phase 4) and parts of a further 6 states in crisis (Phase 3)[3], with an estimated 3.8 million people classified as severely food insecure and unable to meet their food needs.[4] While humanitarian need has been significant, the ability of humanitarian organisations to reach people in need of assistance has been precarious with 64 incidents that affected humanitarian access[5] reported in March 2015. This figure rose to 73 in April and 134 in May 2015.[6]
[2] United Nations, Office for the Coordination of Humanitarian Affairs (UNOCHA), South Sudan Crisis: Humanitarian Snapshot (as of 13 April 2015).
[3] Integrated Food Security Phase Classification, Republic of South Sudan, April 2015.
[4] IPC, May 2015 Food Security and Nutrition Analysis, Key messages.
[5] Access incidents include restrictions on movement, interference in implementation, violence against personnel or assets and conflict.
[6] UNOCHA, South Sudan Humanitarian Access Snapshot (March, April & May 2015).

Introduction to HARRIS: It is in this context of protracted conflict and intermittent access to the most vulnerable that DFID’s multi-year HARISS programme was launched which seeks to address the humanitarian consequences of war and hunger (outcome 1), in addition to strengthening the resilience of communities where continuity of access permits longer-term support to be provided (outcome 2). Underpinning programme delivery is a commitment to bolstering the evidence-base for interventions (outcome 3).

Figure 1: Overview of HARISS
The HARISS business case argues for a new approach to supporting the most vulnerable citizens of South Sudan. It proposes a significant change in the delivery of humanitarian aid. This programme will enable DFID to move away from short-term assistance which meets only immediate needs to a flexible, multi-year approach which will work to increase the resilience of affected populations, including to climate variability, and improve the efficiency of the overall humanitarian response. The programme will also be scaled up or down according to needs and according to commitments from other donors and the Government. This approach will not only save lives, but also build the capacity of people to recover and cope better with shocks. This will ultimately contribute towards greater resilience, with the express aim of contributing to move South Sudan out of the vicious cycle of aid dependency.

In its first year, the focus of HARISS was on the first outcome, provision of life-saving assistance, while foundations were put in place for outcomes 2 and 3 to be launched in 2016 (year 2 of the programme). For this reason, this AR will focus and score the programme on the first outcome and will only comment on relevant aspects of outcome 2 and 3 and associated outputs.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
Analysis: The humanitarian situation in South Sudan remains extremely precarious despite the signing of a peace agreement mid-way through 2015. While inter-communal violence has played a part in the crisis, the most significant factor in the loss of lives and destruction of livelihoods has been the continuing conflict. During 2015 the displacement of civilians continued in the conflict-affected states (2.34 million people have now (January 2016) been displaced; 1.69 million internally and 648,100 seeking refuge in neighboring countries)[7] and the situation of those that have chosen to remain in situ has been compromised by the destruction of civilian infrastructure including health facilities, water points, markets and roads. South Sudan’s humanitarian crisis has been exacerbated by an increasing economic crisis driven by corruption, the depreciation of the South Sudanese Pound, shortages of foreign currency and the global decline in oil prices. Conflict, displacement, insecurity, the affects of climate change, market disruption, economic downturn and localised crop failures have caused a surge in food prices and have exacerbated the spread of hunger into previously stable locations. Poor access to food has been compounded by a lack of access to safe water and sanitation and the poor state of health facilities which led to the continuation of alarming rates of malnutrition, with food security declining year on year.
[7] OCHA South Sudan, Humanitarian Needs Overview 2016, South Sudan.

Figure 2: Summary of impact and outcome indicators against the baseline
Analysis level	Indicator	Milestone 1 / (Dec 2015)	Actual / (Dec 2015)
Impact / Save lives, avert suffering, maintain dignity and reinforce coping capacities of those affected by shocks	1. Number of counties in target states in South Sudan in which there is a declaration of famine	No more than 4 counties	None declared however, 40,000 individuals in ‘catastrophe’ in Unity State[8]
	2. Malnutrition rates in target states in affected populations in South Sudan & in refugee populations in neighbouring countries below 15% Global Acute Malnutrition (GAM), 2% Severe Acute Malnutrition (SAM)	Not applicable as the Resilience component of HARRIS will not commence until 2016	In Unity, Upper Nile, Jonglei, Warrap, NBeG and some parts of Eastern Equatoria states, the prevalence of GAM is above Emergency thresholds (GAM >15%).[9][10]
Outcome 1: / Lifesaving / The vulnerability of people in need in conflict-affected states has reduced	1. %of people classified in Phase 3 (crisis) and Phase 4 (emergency) by the IPC in target areas	40% of people or less including 29% or less in Phase 3 and 12% or less in Phase 4	2.8 million people or 23% of the population are classified in Phase 3, 4 or 5.57% of this caseload, or 1.6m people are in Greater Upper Nile[11]
	2. Number of counties in target states in South Sudan where crude mortality rates (CMR) exceed SPHERE standards (CMR = 1.07/10,000/day , Under-5 mortality rates = 2.1/10,000/day)	Mortality levels have remained below SPHERE standards except in the 4 inaccessible counties in Unity state.	Mortality rates have remained below SPHERE standards except in Unity state where between April and December 2015 Crude Death Rates surpassed the emergency threshold in a number of the counties.[12][13]
[8] IPC South Sudan, December 2015 update, Communication summary, January 2016.
[9] Ibid.
[10] This figure is for information only – the impact indicator will go live in 2016 when the resilience-building component of HARISS has commenced.
[11] IPC South Sudan, December 2015 update, Communication summary, January 2016.
[12] Ibid.
[13] See also Office of the Deputy Humanitarian Coordinator for South Sudan (2016) Crisis impacts on households in Unity State, South Sudan, 2014 – 2015.Initial results of a survey, January 2016.

Assessment: DFID has met its year 1 milestone for the HARISS programme although indicators of humanitarian need including for food insecurity and crude mortality rates continue to be at or above emergency levels and hence there is little room for a further deterioration. Given the nature of DFID’s humanitarian support and the areas targeted by its partners’ interventions, there can be little doubt that UK Aid has made a contribution to ensuring that food security and mortality indicators in Greater Upper Nile and Unity have not tipped beyond crisis levels. It is also likely that DFID’s support has ensured that other states have not fallen into crisis.

While indicators of humanitarian need have remained precarious throughout the year, there have been some improvements in access which has enabled agencies to strengthen their presence in some conflict-affected areas and has offered a level of continuity that had been difficult to achieve in 2014. The consequent mix of short-term need and longer-term presence is well-timed as it potentially offers a conducive environment for DFID’s HARISS programme which has the flexibility to be responsive to the alarming situation in conflict-affected states while also supporting agency interventions where continuity of presence and the protracted nature of the crisis requires a more coherent longer-term approach.

Overall output score and description
At an output level, DFID’s partners have performed well in delivering humanitarian services that have met the basic needs of many vulnerable South Sudanese. In 2015, DFID was the second largest donor in South Sudan, contributing 14.4% of the total funding[14] against the Humanitarian Response Plan which outlined the humanitarian requirements for 6.4 million people and which was ultimately 64.6% funded.[15] At the most basic level of analysis, this suggests a DFID-attributable beneficiary figure of 595,353 people although estimates of progress against output indicators suggest that the figure may be well in excess of this. While there is some possibility of double-counting within sectors and a far greater likelihood of double-counting between different sectors as a consequence of DFID’s funding portfolio, there can be little doubt that UK Aid has had significant reach across South Sudan.
[14] See https://ftsbeta.unocha.org/countries/898/summary/2015
[15] Ibid.

Figure 3: Detailed output score
OUTPUT: Multisectoral humanitarian assistance is provided.	Year 1 milestone	Year 1 progress
1.1.1 Number of people reached with food assistance (cumulative)	120,000	441,500
1.1.2 Number of people reached with non-food assistance including (i) Water, Sanitation and Hygiene, (ii) Health, (iii) Shelter and Non-Food Items, and (iv) Camp Management assistance and services (cumulative)	(i) 57,600 / (ii) 280,000 / (iii) 130,000 / (iv) 180,000	499,748 / 664,660 / 130,602 / 550,630
1.1.3 Number of children treated against severe acute malnutrition	48,000	637,968

DFID’s cross-sectoral support delivered through its humanitarian partners has played an important role in meeting the most immediate needs to sustain life, and DFID’s support for pipelines and air services has also played an important role in permitting the broader humanitarian community to respond to needs in a timely way. The timeliness of the funding that DFID has provided to its partners and to Common Humanitarian Services has allowed humanitarian goods to be prepositioned in advance of the wet season and has permitted under-funded humanitarian priorities to maintain momentum.

Key lessons
- The assumptions that are outlined in the business case remain valid;
- The logic behind maintaining humanitarian services while at the same time supporting longer-term resilience initiatives is sound and the theory of change articulated in the business case continues to be justified;
- The multi-year approach potentially offers significant benefits to beneficiaries through continuity of services and more contextually-relevant responses but also has the potential to offer significant VfM;
- While output reporting is generally good, impact reporting lacks rigour and there needs to be renewed emphasis on seeking to understand the impact that assistance has had on recipients.
- As the HARISS programme progresses, it will be important to collect evidence of these benefits as well as unanticipated outcomes. The Evidence and Learning Facility will have the capacity to do this which will permit HARISS to inform policy and practice both in South Sudan but also globally.

The logical framework was updated in December 2015.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Multisectoral humanitarian assistance is provided in food, non-food items, health, Water, Sanitation and Hygiene (WASH), nutrition, protection, GBV in conflict-affected states
Output number per LF		1.1	Output Score	A+
Risk:		High	Impact weighting (%):	35%
Risk revised since last AR?		N	Impact weighting % revised	N

Indicator(s)	Milestones	Progress
1.1.1 Number of people reached with food assistance (cumulative)	120,000	441,500
1.1.2 No. of people reached with non-food assistance including (i) WASH, (ii) Health, (iii) Shelter and Non-Food Items, and (iv) Camp Management assistance	57,600	499,748
	280,000	664,660
	130,000	130,602
	180,000	550,630
1.1.3 Number of children treated against severe acute malnutrition	48,000	368,366

Key Points: DFID South Sudan have successfully exceeded the beneficiary targets in the first output by a considerable amount. While there is margin for error due to both under-reporting and the potential for double-counting, this should not detract from the impressive achievement. It is noteworthy that the investment made by DFID in the CHF of $52m[16] which represents 53.1% of the total CHF budget accounted for 72.9% of the cumulative beneficiaries.[17]
[16] The figure of $52m comprises the contribution of £21m that DFID made in 2015 in addition to funds which were rolled over from 2014.
[17] The CHF accounts for 2,148,391 beneficiaries from a cumulative total across all sectors of 2,943,108.

While the operating environment in South Sudan continues to be extremely hazardous, discussions held during the review revealed that DFID’s partners have been broadly successful in navigating some of the challenges posed by seasonality and insecurity. Their responses have been informed by a greater understanding of the context and there was evidence that conflict sensitive approaches were being more routinely identified and employed. That is not to say that those in need of humanitarian assistance have been consistently provided with humanitarian services that are of the requisite standards, these have been compromised by the challenging context. What is far more difficult to determine is the impact of the assistance and a better understanding of the totality of assistance that has been received by those in need; while there is now a distribution mechanism in place that can access much of the country, the challenge lies in being able to achieve consistent access, in proving that the assistance is effective and in accurately identifying gaps in service provision so they can be addressed. The fragility of the humanitarian situation in South Sudan is evidenced by the fact that despite large numbers of people receiving some assistance, humanitarian indicators (such as food security) are still deteriorating. Filling in some of the knowledge gaps should be considered a priority for 2016.

Output Title	DFID contributes to a more accountable, effective and evidence-based humanitarian coordination system
Output number per LF		1.2	Output Score	n/a
Risk:		High	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised	N

Indicator(s)	Milestones	Progress
DFID regularly shares evidence with humanitarian actors using lessons learned generated by HARISS	n/a (component not live in 2015)	n/a (component not live in 2015)

Recommendations:
- There has been significant over-achievement on output 1.1. DFID should reassess milestones to ensure they remain realistic and sufficiently ambitious.
- There would be value in DFID estimating annual output targets by partner to allow greater scope to monitor progress and to frame discussions about performance throughout the year.
- Partner reporting requirements should be harmonised with the calendar year for accurate reporting against outputs to be possible for ARs in the future.
- A focus on achieving outputs (against the HARISS logframe) must be matched by a greater understanding of impact. DFID’s Evidence and Learning Facility should have the mandate to make a significant contribution to this.

Output Title	Targeted vulnerable people (severely food insecure people including IDPs, host communities, including female-headed households and disabled households)* have increased access to food security and livelihood opportunities
Output number per LF		2.1	Output Score	n/a
Risk:		High	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised	N

Indicator(s)	Milestones	Progress
2.1 Number of people reached with food security and livelihood opportunity creation projects (peak indicator)	n/a (component not live in 2015)	n/a (component not live in 2015)

Output Title	Targeted vulnerable people (women and girls, boys and men at risk of protection abuses including sexual violence) have increased opportunities to strengthen their protection strategies
Output number per LF		2.2	Output Score	n/a
Risk:		High	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised	N

Indicator(s)	Milestones	Progress
2.2 Number of women, girls, boys and men reached with GBV prevention and response services (cumulative and peak indicator)	n/a (component not live in 2015)	n/a (component not live in 2015)

Output Title	Targeted vulnerable people and partner organisations are better prepared to answer emergencies in a timely manner
Output number per LF		2.3	Output Score	n/a
Risk:		High	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised	N

Indicator(s)	Milestones	Progress
2.3.1 Emergency preparedness and response partners have contingency plans, preparedness measures and rapid teams in target areas	n/a (component not live in 2015)	n/a (component not live in 2015)
2.3.2 Number of children, women and men reached with preventative activities including messages on Infant and Young Child Feeding Practices (manifesto commitment)	n/a (component not live in 2015)	n/a (component not live in 2015)

Indicator 2.3.1 Emergency preparedness and response partners have contingency plans, preparedness measures and rapid teams in target areas: While there is significant evidence of interagency humanitarian coordination via the Humanitarian Country Team (HCT), clusters and pooled financing (particularly the CHF) and while there are tools to support collective assessment of needs (such as the Initial Rapid Needs Assessment IRNA)[18] and some evidence of interagency assessment[19], rapid response is an area that has proved difficult to find a workable model for. One of the most frequently-deployed approaches has been the joint WFP-UNICEF Inter-agency Rapid Response Mechanism (IRRM). WFP reporting shows that between August and December 2015, 16 RRM missions were conducted in over 14 locations which permitted cross-sectoral assessment and response.[20] When supplemented by broader NGO support, particularly in the area of protection, it is possible to have significant impact on some of the most urgent humanitarian needs, however, it is important to recognise that this is relevant only as a last resort as there is also a risk associated with such short-term interventions that there is limited possibility for post-distribution-monitoring and follow-up. Where the situation stabilizes, it continues to be important to seek to support longer-term agency presence.
[18] See https://www.humanitarianresponse.info/en/system/files/documents/files/strengtheningassessments_final.pdf
[19] See, for example, interagency assessment report for conflict displaced population in Tonj East and North Counties, Warrap State, 27-31 October 2015.
[20] WFP/UNICEF, South Sudan, Joint UNICEF/WFP Nutrition Response Plan, November/December 2015 progress report

Recommendations:
It will be important to continue to have protection actors join the Rapid Response Mechanism in order to analyse local dynamics with a view to understanding what the protection threats people are facing are and whether the provision of assistance could be doing more harm than good.

Output Title	DFID partners are good value-for-money
Output number per LF		3.1	Output Score	n/a
Risk:		High	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Percentage of partners that have improved value-for-money compared to project start	n/a (component not live in 2015)	n/a (component not live in 2015)

Output 3.1 DFID partners are good value-for-money is not yet live. While discussions with DFID’s partners highlighted a level of knowledge and analysis of cost drivers and issues of value for money, levels of familiarity with the concepts and the approach were patchy. A minority of partners were relatively systematic in their analysis but many tended to view VfM through a cost-efficiency lens and for some, examples of VfM only came to light when the reviewer pointed them out during discussions about programme interventions. DFID has started to engage with partners both to provide information but also to outline reporting requirements for the future which should be considered good practice.

Output Title	Accountability to affected populations (AAP) mechanisms are implemented for each project and partner
Output number per LF		3.2	Output Score	n/a
Risk:		High	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised	N

Indicator(s)	Milestones	Progress
3.2 % of partners collecting feedback from affected populations (beneficiaries and non-beneficiaries)	n/a (component not live in 2015)	n/a (component not live in 2015)

Output 3.2 Accountability to affected populations (AAP) mechanisms are implemented for each project and partner - while the AAP component of the HARISS programme is yet to go live, it will be important for DFID to calibrate their logframe outputs against an accurate baseline in order to accurately capture progress.

At an operational level, each of DFID’s partners was able to provide programmatic examples of how they engaged with communities throughout the different stages of the project cycle from initial assessment, project implementation and monitoring. Putting community at the heart of humanitarian preparedness and response is an important foundation for AAP and as such constitutes good practice.

Output Title	Lessons learned are shared with the decision-makers and practitioners (donors, UN agencies, NGOs, Clusters, HCT) in South Sudan and globally (through DFID Humanitarian Advisers' network)
Output number per LF		3.3	Output Score	n/a
Risk:		High	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised	N

Indicator(s)	Milestones	Progress
3.3.1 Number of HARISS MEAL Publications shared nationally and globally (cumulative)	n/a (component not live in 2015)	n/a (component not live in 2015)
3.3.2 Number of lessons learned shared through publications and events	n/a (component not live in 2015)	n/a (component not live in 2015)

Indicator 3.3.2 Number of lessons learned shared through publications and events: It is important to acknowledge that some progress has been made in the systematic collection of humanitarian evidence and analysis. During the review, several organisations spoke of efforts that had been made to strengthen internal programme monitoring; a good example of this is the CHF that has now developed standardised indicators linked to an online reporting and monitoring mechanism. In addition to easing the process of project reporting, it is now possible for the CHF Secretariat to manipulate and analyse the data in a range of different ways to meet the needs of its clients.

There is also some evidence that DFID’s partners are collecting and analysing lessons from their responses via annual reports, review reports and evaluations. In 2015 IOM[21] released a real-time evaluation of its humanitarian response to the South Sudan crisis. The annual report for the CHF similarly captures and analyses lessons learned[22] and this is further strengthened by the evaluation of the South Sudan CHF which was a contribution to the Global CHF evaluation.[23] The report contains a number of recommendations which have been reviewed by the HCT.
[21] Caldwell, A. and Oliver-Burgess, A (2015) Real-time evaluation of IOM’s humanitarian response to the South Sudan crisis, CMS consultants.
[22] OCHA South Sudan (2015) South Sudan Common Humanitarian Fund, 2014 Annual Report, April 2015
[23] Hidalgo, S. et al (2015) Evaluation of the Common Humanitarian Fund, Country Report – South Sudan, May 2015, OCHA.

Recommendations:
- It will be necessary for DFID to construct a detailed AAP baseline which provides details of partners’ corporate commitments and country strategies as well as providing guidance to its partners on expectations for AAP in programme implementation. This will be important for progress against this output to be accurately measured (this activity forms part of the ToR for the Evidence and Learning Facility).
- While the main recipient of the Evidence and Learning Facility of HARISS will be DFID and their partners, there is significant need for high quality evidence to drive a change agenda at the collective level. It will be extremely important for senior DFID South Sudan staff (who have links to the HCT and clusters) to champion the use of evidence in order to close the gap between policy analysis and changed practice.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

The HARISS business case correctly identifies South Sudan as one of the most fragile, high risk operating environments in the world, which also makes it one of the most expensive.

Key cost drivers and performance
- Procurement: Procurement continued to be largely international although there has been an increase in local procurement of seeds and shelter materials.
- Security: Although the frequency of security incidents has reduced during the year, there continues to be an important need for security of assets both in situ and in transit. Partners have sound strategies in place to manage security.
- Transport: Throughout much of the country, DFID’s partners were successful in pre-positioning relief items which significantly reduced costs. The likelihood of assets being looted during conflict has led to agencies having to balance the risk of loss against the additional cost required to move food commodities and non-food items during the rains when such items must be air-lifted – practice differs between agencies although there is evidence that all partners compare the costs and benefits.
- Capacity of local staff: Experienced local staff continue to be comparatively expensive and relatively few in number although capacity building initiatives are helping to address the skills gap.
- Inflation: Annual inflation as of December 2015 in South Sudan was 109.9% following a 73.6% growth in the previous month. It was the highest inflation rate recorded so far, as cost of food increased sharply by 130%.[24]
  [24] www.tradingeconomics.com, National Bureau of statistics, South Sudan.

VfM performance compared to the original VfM proposition in the business case
VFM is a key driver of the new approach and DFID partners have a clear expectation that multi-year grants will offer significant benefits, however these will not be realised (or be able to be measured) until the end of 2016 at the earliest (and in-depth analysis won’t be possible until the end of 2017 when two-years results can be compared). In the context of a single year of funding, DFID’s partners have sought to achieve VfM through a combination of the following strategies:

- Economy: Pre-positioning of food commodities (WFP and ICRC) and non-food items to reduce transport costs (Logs cluster, WASH cluster) and preventative targeting of cholera hotspots in advance of the season to reduce the likelihood of an outbreak (UNICEF).
- Efficiency and cost-effectiveness: An increase in the use of local procurement (such as the use by FAO of local seed stocks or the distribution by IOM of locally-available shelter materials) and greater use of community managed interventions which offer efficiencies and greater effectiveness (such as the use by UNICEF of community-based psychosocial support). Use by the logs cluster of a Buffalo fixed-wing aircraft over helicopter which achieves considerable cost-savings per ton of cargo.
- Effectiveness: While the context is challenging, there is evidence that partners are providing ‘smarter’ assistance that takes into account the potential for aid to exacerbate conflict (see section E below). For hard-to-access areas, technological advances now allow WFP to air drop oil and other commodities thus ensuring the provision of a full basket of commodities. Where longer-term assistance is possible, agencies are beginning to re-calibrate their ways of working.

Assessment of whether the programme continues to represent value for money
Yes, while South Sudan is a complex and expensive country to operate in, the life-saving nature of DFID’s support linked to the strategies that its partners have adopted to strengthen the economy, efficiency and effectiveness of their responses continues to represent VfM.

Quality of financial management
Date of last narrative financial report	Umbrella business case, several partners
Date of last audited annual statement	Umbrella business case, several partners

£110 million of funding to partners was approved in three allocations and tranche payments to partners have progressed as planned during the year. Partners have utilised the funding provided in a timely manner and there have been no material issues related to financial management.
E: RISK (½ page)

Overall risk rating: High

Overview of programme risk
The risk mitigation and management strategy in the business case has been translated by DFID South Sudan into a risk register which identifies risks, their associated impact and likelihood for each partner and outlines mitigation measures. During the AR, all partners demonstrated a sound understanding of the key operational risks and were able to outline key mitigation measures to reduce the likelihood of occurrence and to minimise the potential impact. Key strategies included the following:

- Humanitarian negotiation: ICRC have maintained unprecedented access throughout South Sudan as a consequence of continued negotiation with parties to the conflict.
- Addressing conflict pull-factors: In some areas particularly prone to conflict, ICRC and WFP have undertaken coordinated distributions in neighbouring areas to minimise the likelihood of conflict.
- Strengthening conflict analysis and protection: The deployment by several of DFID’s partners of protection-related staff during distributions to support conflict analysis has strengthened their ability to understand and analyse conflicts. It has also reduced protection-related incidents.

DFID South Sudan has also sought to reduce risk through the following strategies; preparation of comprehensive proposals which have included articulation of risks and mitigation measures, regular partner meetings, receipt and review of reports and financial statements, field monitoring visits and liaison with other donors for the purposes of partner assessment.

Outstanding actions from risk assessment
Due diligence assessments were undertaken early in 2015 and a comprehensive report outlining actions was prepared for each of DFID’s current partners. A follow-up meeting has been held with partners.

Recommendation:
- During 2016, DFID should discuss the progress that has been made against each of the recommendations of the due diligence assessments.
- As the CHF risk management framework approaches the end of its first year, DFID should work with the Secretariat to ensure that a ‘substantial review and updating’ occurs as outlined in the framework.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The delivery of the HARISS programme is in line with the planned timeframe. The procurement for the contract awards for both the resilience and monitoring, evaluation and learning (MEAL) components are also running to schedule.

Performance of partnership(s)
The first year of the HARISS programme focuses on emergency response and utilises existing memorandum of understanding (MOUs) and agreements with the CHF, the ICRC and UN agencies. The partnerships are well-established and the programme has been successful in building on DFID’s prior knowledge and relationships with each of the partners. As HARISS moves into its multi-year phase it is anticipated that some aspects of these partnerships will need to be renegotiated and it will be important that there is clarity about the reporting requirements and how these relate to pre-existing global agreements.

Asset monitoring and control
Each partner has corporate policies on asset management in addition to country-level procedures which include monitoring and spot-checks. DFID South Sudan has engaged all of their partners in discussion about the importance of timely reporting of any losses or fraud and there is now a good understanding of expectations in this regard.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
Not applicable.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
To a large extent, the theory of change remains untested as the resilience and MEAL components of the business case are yet to be implemented. However, there continues to be a compelling justification for the delivery of assistance which seeks to go beyond purely humanitarian objectives and with agencies, particularly Non-Governmental Organisations, beginning to establish a longer-term presence in previously insecure parts of the country, delivery mechanisms for the proposed resilience programme are now available. While there have been signs of improvement over the course of the year, the evidence-base to prove (and improve) the contribution made to saving lives and securing livelihoods continues to be weak. This supports DFID’s investment in monitoring and impact measurement.

Monitoring progress throughout the review period
The progress of the programme has been monitored by DFID staff throughout the year. Regular field visits (to every partner) are undertaken by humanitarian advisors and reports with details of partner performance are written and archived. There is evidence that recommendations that are made are followed up. Progress reports from partners have been submitted according to the schedule and on time.

Annual review process
The annual review was conducted over a period of 2-weeks with one week spent in South Sudan. A total of 213 documents were reviewed and interviews were conducted with 41 people which included DFID staff, partners staff, donor representatives, humanitarian leaders and coordination staff.