Business Case

Summary Sheet

Title: Somalia Security and Justice Programme (SSJP)
Project Purpose: Building the foundations for sustainable security and justice Institutions
Programme Value: GBP 36.3m		Country/ Region: Somalia
Project Code: XXX	Start Date: August 2016	End Date: July 2020
Overall programme risk rating:	Major
Quest Number:	5479626

Somalia’s Emerging Federal Map (as of September 2015)

Intervention Summary

What support will the UK provide?
Under this programme, the UK will provide a total of £36.3m million over four years (2016-2020) to support security and rule of law programmes across Somalia. This is composed of:

- £30 million of new funding requested under this business case;
- £2.3m represents the balance of approved funds from the Re-establishing basic Policing Programme (which is now being merged into the SSJP); and
- £4 million will be drawn from Conflict, Security and Stability Fund finances (CSSF) delivered through this programme.

Earlier DFID investments in the areas of security and justice have resulted in improved access to justice for citizens in Somaliland, Puntland and Mogadishu. This programme will continue to support these successful access to justice and basic policing activities while introducing two new elements aimed at: (a) deepening support to stabilisation in southern and central Somalia by focusing on urban areas recovered from Al Shabaab, and (b) establishing the political and financial foundations for the sustainable development of state security and justice institutions.

The programme is an expansion of existing support to basic police and justice functions combined with support to political dialogue and negotiation on Somalia’s federal security arrangements and public financial management and accountability within state security and justice institutions. This will improve the overall sustainability of basic security and justice functions across Somalia.

The programme will work across Somalia, including in Somaliland, at several levels of government: federal level; state level; and district level. This will be the first programme from the international community with a dedicated and substantial component of support for the establishment of security and justice structures in the emerging Federal States. The programme will provide support primarily through training, technical assistance, infrastructure and equipment support.

What are the main programme activities?
The programme has 4 outputs:
- Output 1 –Development of Political, Legal &Financial Frameworks GBP 4.3m
- Output 2 – Expand, train, equip and provide infrastructure for police GBP 17.3m
- Output 3 – Expand, train, equip and provide infrastructure to justice agencies in targeted areas GBP 13m
- Output 4 – Monitoring and Risk management GBP 1.7m

The programme will use a variety of multilateral and bilateral delivery mechanisms. The choice of components and delivery mechanisms has been informed by detailed design, but also in many cases represents the UK meeting commitments it has already made, to international and Somali partners, in particular through the New Deal.

The SSJP is one of two successor programmes to the Core States Functions Programme, with its sister programme focussing on public resource management. Some components continue support already being provided through the Re-establishing Basic Policing (RBPP) which will now be absorbed into the new SSJP.

Why is UK support required?
This programme responds to core security and justice priorities identified under Peacebuilding and Statebuilding Goals (PSGs) 2 and 3 of Somalia’s New Deal Compact. The programme will: provide a critical mass of resource needed to implement multilateral policing and justice state-building programmes help consolidate AMISOM’s military gains and pave the way for AMISOM’s exit and hand over of security responsibilities to Somali authorities. Within DFID-Somalia and the BAR offer the programme serves as a critical foundation for progress and sustainability for the rest of the portfolio.

What are the expected results?
The programme will:
- Re-establish basic policing and justice functions in key urban areas recovered from Al-Shabaab;
- Cover additional 30 districts in south-central Somalia and consolidating the provision of legal assistance and mobile courts in Somaliland (25 districts) and Puntland (16 districts). The support will in particular target women and girls and ensure they have equal access to legal services.
- Establish counter- explosive ordinance policing capacity in key urban areas
- Strengthen financial management and accountability within the security sector at both federal and sub-national levels;
- Support the development of federal and sub-national policing and justice policy and legislation;
- Establish a common score-card for assessing policing and justice provision at district level;
How does the project fit with wider strategic objectives?
All of HMG’s activities in Somalia are guided by the UK National Security Council Strategy on Somalia. The SSJP is the primary vehicle for delivering Pillars 2.3 and 2.5. The programme is also key to delivering the UK aid strategy.

What are the key risks to the success of the programme?
Stabilising Somalia remains a huge challenge and consequently a programme such as this will face many risks. The programme’s risk assessment divides these into four categories:
- Political: the risk that domestic political dynamics prevent enabling decisions being taken
- Security/access: the risk of limited access to project sites or partners
- Commercial/delivery: the risk that implementing partners are unable to deliver effectively
- Fiduciary: the risk of fraud or non-compliance with DFID fiduciary standards

Each component has been designed to try and mitigate these risks. Ultimately the programme’s main strategy for risk management will be based on portfolio diversity combined with flexibility and use of multiple delivery partners.
## Strategic Case
Context and need for a DFID intervention

Somalia continues to present both a global and regional threat to peace and stability and therefore remains a UK National Security Council priority country. It has the lowest governance scores of any African nation[1], the second lowest world ranking for state fragility[2], the lowest ranking for corruption (equal last with North Korea)[3], and occupies 157th place out of 162 nations ranked on the Global Terrorism Index[4]. Somalia is also ranked amongst the 10 poorest performers in the world for intensity of conflict, incidence of displaced persons, political instability and internal conflicts[5].
[1] Mo Ibrahim Foundation, Ibrahim Index of African Governance (2015) http://www.moibrahimfoundation.org/iiag/
[2] US Fund for Peace, Fragile states Index 2015, http://fsi.fundforpeace.org/
[3] Transparency International, Corruption Perception Index 2014, http://www.transparency.org/cpi2014
[4] Institute of Economics and Peace, Global Terrorism Index 2014, http://www.visionofhumanity.org/#/page/indexes/terrorism-index
[5] Institute of Economics and Peace, Global Peace Index 2015, http://www.visionofhumanity.org/#/page/indexes/global-peace-index

The situation is not uniform across all of Somalia and some areas of the country have experienced relative peace and stability for many years whilst others have been far more unstable with higher levels of violence. In simple terms Somalia can currently be seen as consisting seven regions. Northern Somalia covers two key regions:

Somaliland and Puntland which have been accessible for much of the conflict period with relatively permissive security environments that have allowed DFID to support development in major urban areas.

In Southern and Central Somalia the rise in terrorism led to the deployment of an African Union mission in Somalia (AMISOM) in 2007 with a robust peace enforcement mandate. Its mandate is to work alongside the Federal Government of Somalia’s (FGS) security forces to degrade Al Shabaab’s capability. The combination of all these factors has had devastating humanitarian consequences and impacted strongly on the most vulnerable members of the population, especially girls and women. There are five key regions in this area:

Mogadishu and the surrounding Benadir region which has become increasingly accessible, albeit at high threat levels, since 2011 allowing basic development support; and

The emerging states of Jubaland, South West Somalia, Hiraan and Middle Shabelle, and Galmudug[6] which have previously seen only limited development attention and remain active military zones with AMISOM challenging Al Shabaab for control of the heavily populated “food basket” districts along the Jubba and Shabelle Rivers.
[6] Mosley J. (2015) Somalia’s Federal Future: Layered Agendas, Risks and Opportunities, Chatham House, Royal Institute of International Affairs, London.

 These geographic and contextual variations have informed our three main objectives:
- The first is focused on political economy and accountability and aims to (i) assist federal and state governments reach political agreements on federal security arrangements. The lack of clarity around command and control arrangements, mandates between federal and state level security and justice institutions is a continued source of tension . (ii) to improve public financial management within the security and justice sector at federal and state levels in order to address affordability and sustainability issues.
- The second is continuing consolidation of previous security and justice efforts in Somaliland, Puntland and Mogadishu to preserve gains made as a result of earlier development investments.
- The third proposes deepening and extending our work in the emerging states, especially in the South, to build local capacity as part of AMISOM’s exit strategy.

Security Context
The scars of civil war still run deep, with politics and security provision deeply divided along both clan and politico-religious lines. Intense factional competition over the distribution of even small amounts of power and resources constantly threatens to undermine efforts to establish a rules-based system of governance. The latter is also true of the more stable parts of northern Somalia.

State security and justice institutions are weak across all regions of Somalia with services largely delivered through non-state community institutions or militia. This irregular service provision results from the vacuum left by the collapse of the state in 1991, and the concurrent resurgence in clannism alongside the influence of business, religious and civic groups. Al Shabaab is still able to operate in large parts of the rural areas south of Puntland, while general insecurity limits freedom of movement, livelihoods and investment.

In 2012, AMISOM, working with Somali National Security Forces (police and military), took control of various strategic towns and supply routes from Al Shabaab, including the key port of Kismayo. But given the weak Somali security capacity, this has left AMISOM over-stretched, preventing further advances and any effective consolidation. In response, Al Shabaab has shifted to asymmetric tactics, including targeting the Somali Federal Government, AMISOM, international organisations and local authorities in areas recovered from Al Shabaab.

A June 2015, a Joint United Nations (UN) and Africa Union (AU) Review of AMISOM noted that, while degraded, Al Shabaab remains an active force capable of disrupting peace and security. The mission concluded that if unaddressed, the remaining threat is likely toderailthe peace process. It also highlighted the increasing Al Shabaab threat to wider regional security, particularly in Kenya and the security implications for the Horn of Africa posed by the conflict in Yemen.

Penetration of recovered urban areas in southern Somalia by police and courts is very limited at this point due to both restricted capabilities to deploy and the many rural areas which remain militarily contested with the insurgents cutting urban centres off from their immediate hinterlands. Importantly however, perception surveys indicate awareness and increasing degrees of credibility of state police and justice providers.

Political and Legal Context
Somalia’s Provisional Constitution provides for a plural legal system. Sharia, customary and state law are all permissible. This is not unusual and is indeed the norm for most African and Gulf countries. While quality may be variable and there are issues regarding human rights and equality within state and non-state systems, under a plural system citizens have a broader range of service provision options. In this context, donor efforts should be focused on improving the quality of available security and justice service provision options thereby enhancing citizen choice. Our comparative advantage is in strengthening state led service delivery. Our intervention is therefore aimed at expanding the range of viable options for Somali citizens by increasing access to, and improving the quality of, state police and justice functions- i.e. making basic state security and justice provision a viable option for Somali citizens.

Situating global security and justice doctrine within a legal pluralism context
The generally accepted global policy doctrine is that security and justice are essential for states if they are to govern their territories and operate at the most basic level. States in turn, need to be seen to meet public expectations in the provision of security and justice in order to establish legitimacy and create stability. They need a minimum level of administrative capacity to deliver these functions and accountability is critical to ensure they are responsive rather than repressive. Support to security and justice should include working with both state and non-state actors as appropriate.

We have explicitly taken local context as our starting point and will therefore be working on the basis of more than one theory of change based on the different sub-national contexts. Nonetheless some characteristics are common across the country:

- Similar to many other fragile states and developing countries, Somali citizens rely primarily on non-state service provision[1].
  [1] Research in many fragile states suggests that non-state systems are the main providers of justice and security for up to 80-90% of the population.6 Non-state systems may often be more effective, accessible, fairer, quicker, cheaper and in tune with people’s values.
- A variety of legal systems coexist in Somalia[2] and this will continue to be the case.
  [2] Not unique to Somalia and as follows: (a) the customary, clan-based system (xeer); (b) the state judiciary structures in regional administrations and central governments; (c) the growing number of shari’a courts in urban areas, particularly in Mogadishu; and (d) civil society and private initiatives, as well as ad hoc mechanisms established by militia factions. Several or all of these systems are often found in the same location.
- Customary, religious, and secular systems, functioning in parallel, regulate a wide range of affairs, to the enforcement of business contracts and the settlement of family disputes.

The politics of security
The Provisional Constitution provides limited clarity on federal security and justice arrangements- mandates, roles and responsibilities on policing and justice are highly contested and will require political negotiation and agreement.

The processes for developing the detailed constitutional and legislative frameworks for these new federal security and justice arrangements have not been agreed. With few exceptions everything, at least from the regional states’ perspective, is seen as up for negotiation. At this stage the emerging states are still extremely limited in their ability to deliver any sort of service and jurisdictional disputes, on which level of government is supposed to deliver what frequently arise

Evidence of Need
 The justification for DFID’s continued policing and justice support in Somalia is based on three empirical considerations:

Somalia’s Safety and Rule of Law History 2000-2014
Between 2000 to 2014, according to the Ibrahim African Governance Sub Index for Safety and Rule of law, Somalia has consistently had the lowest scores on this indicator compared to any other country. Indeed Somalia’s scores fell after 2005 setting new record low points for the entire African continent and its offshore entities. Whilst these low points are only indicative given the technical limits of the data, they show that security and justice have been in a downward spiral for over a decade.

Benchmarking Somalia’s Position Relative to Other African States 2014
Research undertaken in preparation for this business case compared the Ibrahim Index of African Governance 2014 found that:

- Somalia is at the very bottom of Africa on the Safety and Rule of Law Measure but on all four measures by a large margin
- No nation in Africa with a low Safety and Rule of Law Score performs well on any of the other three measures of performance (i.e. sustainable economic opportunity, participation and human rights and human development);

No nation in Africa with a high Safety and Rule of Law score performs badly on any of the other three measures of performance; and

Improvements in Safety and Rule of Law are associated with strong improvements in each of the other three key performance measures.

Detailed Police and Justice Diagnostics
Police and justice agencies have been the subject of both sector wide and agency specific reviews over the past three years. These have been undertaken by DFID and other partners to determine capacity and need amongst the main sectoral actors. Elements of these processes were brought together most comprehensively in 2014 through the work of:

- The Peace and State building Goal (PSG) Working Groups on Security (including police) and Justice which have identified the critical short and medium-term policing and justice support objectives;
- The 2013 and 2015 AU/UN Benchmarking reviews which identified the short term policing milestones for areas recovered from Al Shabaab and
- UN agencies establishing a Joint Rule of Law Programme setting out the detailed policing and justice support across Somalia.

The PSG Action Plans for security and justice set out the political and institutional context in both sectors. This can be summarised as follows: An almost complete absence of fundamental legal and policy frameworks as the basis for future development, the existence of only rudimentary field capability to deliver actual services, dysfunctional management practices, weak or nonexistent backroom (finance and human resource) capabilities, nonexistent national security architecture, weak levels of accountability at all levels, extreme difficulty in enforcing court decisions, lack of connection between local and federal institutions, and yet to be drafted legislation mandated as necessary to give effect to government decisions. At the big picture level it is reasonable to conclude that the identified weaknesses are so serious that the poor performance documented by the Ibrahim sub-indices reflects a state overwhelmed by its own deficiencies as much as by the catastrophic problems it faces.

The most important observation from the Joint Rule of Law Programme developed by UN agencies relates to the sheer volume of tasks identified to ‘stand-up’ rudimentary police and justice services within Somalia. These extend to several hundred interventions covering the full spectrum from detailed activities to big picture strategy. In policing this covers basic items such just as procedures, equipment and logistics. In the justice sector this includes fundamentals such as equipment, case management and filing.
#### What are others doing in this area?
The aid context (as well as the political context) in which this programme has been designed is very different from that of 2012. The New Deal architecture has changed the way aid is being programmed and coordinated. Secondly, the World Bank ,IMF have now re-engaged with Somalia anda new UN Multipartner Fund through which a critical mass of rule of law programming is delivered.

Nonetheless there remain some critical gaps in international community support. The UN programmes mentioned above are only partially funded; and the overall funds available to both the Bank and UN are limited, so their programmes have had to be focussed very tightly on certain priorities. See table 1 below:

Table 1 - Gaps in international support
Functional Area	Federal Level	State Level	Puntland[7]	Somaliland
Policy, legislation and financial management and accountability	Only partial EU and DFID support	N/A	N/A	N/A
Police training, equipment and infrastructure	Partial EU Japanese and US support	Only DFID training and infrastructure support (AMISOM training lead and UNOPS infrastructure lead)	UNDP lead, only partial EU support	UNDP lead, only partial EU support
Justice training, equipment and infrastructure	Only partial EU support	Only DFID support	UNDP lead, only partial EU support	UNDP lead, only partial EU support
Improving integration across the entire justice chain	Only DFID support	Only DFID support	Only DFID support	Only DFID support
[7] Puntland is a federal state, but is usually referred to separately from the other federal states/interim regional administrations as it has been in existence for several years and so has quite different needs

Priority Needs
Based on the above diagnostics and the gap analysis DFID interventions have been structured around four main areas:

(1) Expanding, training, equipping and providing infrastructure support to public police forces in the various regions of Somalia with as much emphasis as possible on partnerships which capitalise on the work of other donors. DFID support will remain focused on the basic recruit training, the payment of stipends to police and equipment in newly recovered areas (main urban areas) of 6 regions. This will be supplemented by annual refresher training and middle-management training..

(2) Extending the reach of courts and legal assistance . The project will continue to support the expanded outreach for mobile courts and legal assistance now operating through all states in Somalia. In parallel the project will start to engage with state institutions through upgrading both physical infrastructure and human capacity (e.g. middle management in the courts)

(3) Support to political agreements, legal frameworks and financial accountability necessary to set out agreed divisions of function and responsibility which are binding on all parties with financial structures in place which manage the resources necessary for these agencies to operate at both federal and state levels.

(4) Improving integration across the entire justice chain through increased joint assistance to police and justice agencies with initiatives such as joint management training, joint performance assessments and the introduction of inventive rating systems to stress the interdependent nature of the broader sector and prevent imbalances which may see some areas left behind.

Why DFID?
The SSJP has been designed on the basis of a careful assessment of comparative advantage with other international agencies. Where we consider that another agency has comparative advantage; that agency is willing and able to fill one of the gaps identified above; and/or the UK and international community has already agreed a particular agency should lead, our preferred choice is to support that agency. This we consider to be the case with:

- A UNDP lead on legal assistance and support to mobile courts (a well-established multi-donor programme and international consensus that they should lead in this area)
- A UNOPS lead on the delivery of stipend support to security personnel at Federal and sub-national levels (UN comparative advantage, and the UK has helped secure international consensus that they should lead in this area)

Where no other agency has obvious comparative advantage, and/or where there is clearly a gap in international support, we have considered a bilateral DFID lead. This is particularly the case with regards:
- Political negotiations on security arrangements
- Sub-national security sector payroll development
- Score card development

The Consequences of Not Intervening
The consequences and costs for Somalia, the region, and the UK of not intervening are high. The risks of political settlements failing to improve security and justice are significant. The high relative financial costs to the international community of humanitarian aid, migration of displaced populations, and peacekeeping will continue. Risks to the UK from terrorism would remain a particular concern, significantly constraining the ability of HMG and others to operate in Somalia, particularly in areas recently recovered from Al Shabaab control.

Without UK support, current efforts to improve basic security and justice in Somalia will remain under-resourced and restricted to the capital city of Mogadishu which is a source of tension between the centre and the regions. Improved security is critical for development and humanitarian efforts to deliver results.

Working in Partnership with Others
In addition to DFID the two most active partners in policing and justice have been the European Union and Japan with the UN also contributing funds. The US has recently entered this field with criminal investigative training conducted by the Bureau of International Narcotics and law Enforcement Affairs and this is a welcome support to DFID efforts. Turkey and Qatar along with multilateral organisations including the Arab League also offer support but this tends to be less visible.

The PSG Working Group structure is the main vehicle for coordination. Beyond and in addition to the PSG structure the UK is playing an active role to ensure support is coordinated and mutually reinforcing. Looking ahead, links with the AMISOM Police Contingent will become increasingly important over the period 2016-2020. The ability to leverage AMISOM police training and mentoring capabilities for Somali counterparts is a significant part of our existing delivery strategy as they are the only implementing partner able to undertake police training and support in areas recovered from Al Shabaab.
## C Gender Considerations
Lack of basic security tends to affect women and girls disproportionately both through breakdown of basic services as well as being more vulnerable to discrimination and violence. The use of sexual and gender based violence during periods of conflict can have devastating long term impacts on families and communities. Where sexual and gender based violence persist, women and girls are disproportionately affected. The long term civil conflict in Somalia has led in many areas to high degrees of sexual and gender based violence. Ensuring recognition of equal and fair property rights (particularly with regards to land in fragile and conflict affected countries) is also important from an economic development perspective. Too often women are legally and/or culturally excluded from being able to hold and dispose of property and as such are not able to realise their full economic potential .

Ensuring fair and impartial fora to which women and girls have access is a vital part in enabling individuals and the society as a whole start to redress some of these types of injustice. Where institutions have been physically destroyed or are overly remote and inaccessible, innovative mechanisms, e.g. mobile courts can be deployed to overcome those barriers. Access can be enhanced through the subsidised provision of legal services so that those without financial means can access justice systems.

It is important that the composition of the state institutions designed to deliver fair and impartial justice be representative of the society which it serves. Ensuring that women are adequately represented in both the judiciary and prosecutors office is also a general public good that all countries attempt to strive for – although even in the most developed countries, there can often be numerous societal barriers to ensuring such representation occurs.

Recognising these issues, this programme will therefore act in full compliance with the provisions of the Gender Act by directly seeking to address gender equality concerns through:

- Continuing to support and expand the provision of legal aid and mobile court services throughout Somalia;
- Support gender neutral hiring practices in the judiciary and for prosecutors;
- Support the development of a gender neutral political settlement across Somalia around the police and the judiciary to ensure that women are treated with equal respect and that they have equal access to all such institutions; and
- Through the work with our partners under the project, and with other DFID Somalia programmes e.g. the UK’s Plan of Action on SCR1325 for Somalia and the SNaP programme - attempt to deepen our understanding of the key social barriers that prohibit women (or actively exclude them) from accessing security and justice services, and work to resolve and mitigate them over time.

Impact and Outcome that we expect to achieve

Overall state security and justice provision in Somalia is seriously degraded. The weaknesses amongst police and justice agencies at all levels of government are profound and represent one of the major obstacles to stability and recovery. This intervention recognises at the outset that desirable and achievable objectives differ and that in this case the balance lies in supporting the foundational development of public policing and justice agencies for the duration of the 2016-2020 programme

The three pronged strategy proposed for 2016-2020 seeks to target the main needs for security and justice, and offers scope to engage at federal and emergent state levels in respect of all police and justice agencies while working towards implementation of the broad enabling frameworks necessary for sustainability.

Expected Outcome: The foundations for sustainable security and justice institutions are in place.

The impact of this project is heavily reliant on the work of partners, political stability within the different levels of Somali government and a unified desire on behalf of Somali leaders to build trust with citizens to the point where expectations for better governance marginalises violent or otherwise illegitimate behaviour.

Impact: Improved public safety and rule of law in Somalia.
This is a measureable impact which will assist in creating awareness within Somalia of successes and failures on an annual basis and guide partners on the extent and nature of support required to achieve the desired objective.

## Appraisal Case
#### Feasible Options
DFID has been supporting security and justice work in Somalia since 2005. We have built up a significant amount of experience, knowledge, understanding of the operating environment and evidence of what works best, through annual reviews and project evaluations.

The consideration of feasible options for this programme is therefore not focused on ‘what’ we should be funding but is rather an assessment of feasible options in terms of ‘scale’, ‘scope’ and ‘delivery’.

In this section we will: (a) set out our proposed approach (the ‘what’) and the evidence underpinning this and (b) consider the issues of scale, scope and delivery structured according to the 4 major functional areas highlighted as high priority in the strategic case:

- Expanding, training, equipping and providing infrastructure support to public police forces;
- Extending the reach of public justice institutions and continuing to ensure access to justice;
- Support to political agreements, legal frameworks and financial accountability, and
- Improving integration across the entire justice chain.

I. Proposed Approach
Discounting the ‘do nothing’ counterfactual
The consequences of not intervening (the ‘do nothing’ option) have been set out in the Strategic Case. In reality, the ‘do nothing’ option is actually ‘doing nothing more’ because, as highlighted earlier: (a) work in this area is a core UK National Security priority, and (b) there is already a significant level of support being provided by the UK to support security and justice in Somalia. In the absence of the proposed programme key New Deal PSG 2 and 3 priorities would not be delivered, specifically, there would be:

- No comprehensive support to establishing basic policing and justice support in new federal states;
- No contribution to the UN Security Council’s proposed Police Support Package and therefore limited support to re-establishing basic policing as part of the wider stabilisation process and AMISOM exit strategy; Limited work on improving the political and financial sustainability of current international security and justice assistance.
- Limited contribution to HMG objectives in Somalia.

Preferred approach
Despite ongoing volatility in the political and security contexts, there are now clear opportunities to carefully expand the existing portfolio of policing and justice interventions and to increase the sustainability and impact of our investments by focusing on supporting the emergence of political agreements on federal security arrangements and financial accountability.

Our new approach will combine interventions currently delivered under two programmes (Core State Functions and Re-establishing Basic Policing) into one overall Somalia Security and Justice Programme. While, a single programme framework will ensure greater coherence and efficiency, this remains a multi-faceted package of high risk interventions working across varied, extremely fragile, highly complex and insecure contexts.

At present, the UK supports a number of interventions in the broad area of security and justice. Activities vary by region (based on feasibility, access and political will); the focus has mainly been on police training, access to justice and infrastructure. Our existing portfolio has delivered clear results particularly around mobile courts (now operating in 59/90 districts across Somalia with an expectation this will increase to 68/90 districts by the end March 2016) and legal assistance (15,000 citizens across Somalia receive legal assistance annually), We have delivered police training and stipend support to 400 new police officers in areas recovered from Al Shabaab (this will increase to 1200 by October 2016). The construction of four new Regional Police Headquarters in key towns is on-going.

Somalia’s political shift towards a federal system of government and the emergence of interim regional administrations presents us with an opportunity to address some key political, financing and institutional gaps, which will improve the overall sustainability of our current support to the development of basic security and justice functions.

The proposed new programme approach can therefore be summarised as: a careful expansion of existing support to basic police and justice functions combined with support to political dialogue and negotiation on Somalia’s federal security arrangements and public financial management and accountability within security and justice institutions.

II.	Scale, scope and delivery: Feasible Options
The 2015 ICAI report on UK Development Assistance for Security & Justice programming has informed the design of the SSJP. Three key ICAI recommendations have informed our consideration of feasible options:
Avoid spreading programmes too thinly in order to achieve sustainable results;
Strengthen supervision of delivery partners to ensure technical assistance does not end up being largely input rather than output focused;
Less is more- the most convincing designs are relatively modest in their objectives and focus on finding solutions to specific problems rather than system wide reform.

The above along with the assessment of current gaps in international support set out in Table 2 has informed our assessment of feasible options as follows:

1. Support Development of Political, Legal and Financial Frameworks
	Continue with current programme	Scale back	Expanded programme
Scope (Geography and Administrative level)	Focus only on the Federal Government of Somalia’s Ministries of Finance, Security and Defence only. / Pros: See below. No discernible benefits to maintaining the status quo. / Cons: Limited to federal level institutions which has historically proved to be the most difficult to reform and have the most entrenched networks and interests. Misses the opportunity to test openings around e.g. negotiations around policing models and legislation that have emerged through our Re-establishing basic Policing Programme.	Discounted as an option given the clear sustainability benefits this work provides for all international assistance in Somalia. Guiding principle is that we should do as much as we can as long as the political conditions exist for meaningful progress to be made.	Work at both Federal and sub-national levels. Rationale: / Pros: Directly addresses absence of political, legal and financial foundations for sustainable security and justice institutional development. Country-wide and federal and sub-national approach enables us to spread risk more evenly and incentivise federal level reform by demonstrating progress at the state levels. / Cons: Risk of overstretch in terms of geography and level of ambition. Mitigated by delivery approach set out below and the fact that if successful this component will (at a relatively low cost) leverage the most significant strategic returns.
Scale	Limited to planned start-up TA support to the Federal Government on security sector (SS) payroll reform. / Pros: Ability to test political will incrementally without committing full resources. Only limited resources required. / Cons:	N/A	Support modest deployment of targeted TA and support where enabling political conditions exist. / Pros: Better value for money based on ability to maintain control of TA- and scale up/down depending on political will and context. Opportunity to test this out across Somalia at different levels. / Cons: No discernible disadvantages to this approach given the incremental approach that will be implemented.
Delivery	Continue with proposed private contractor approach of current work. / Pros: Existing relationships relatively simple to manage. Ability to retain direct control of scope and scale of TA deployments / Cons: Current project has not begun yet so Contractor Performance in this area untested. Will have a clearer idea mid-2016	N/A	Mixed delivery approach: A combination of Private Contractor delivery to support targeted TA deployments and Grant Agreements. / Pros: Ability to retain direct control of scope and scale of TA deployments under a private contractor arrangement along with the opportunity to finance credible NGO conceived projects / Cons: Does not prioritise multilateral delivery options. UNSOM are currently active in the support to political negotiations around a policing model. Financing the UN carries some significant risks given their current preference for limited donor engagement in this key area. Our preferred option will ensure that bilateral support is well co-ordinated with on-going activities.

2. Expand, train, equip and provide infrastructure to police in targeted areas
	Continue with current programme	Scale back	Expanded Programme
Scope (Geography and Administrative level)	Benadir, Jubaland, Puntland, the South West State and Somaliland / Pros: Continuity in programming and limited additional risk exposure. / Cons: Misses available opportunities to consolidate and improve the sustainability of previous support.	Focus exclusively newly emerging Federal States only: Jubaland, South West State, Galmudug and Hiraan Middle Shabelle. / Pros: Avoids geographic overstretch / Cons: Proposes two new geographic areas where access is extremely limited and delivery capacity is untested. Misses opportunities to consolidate results in areas of existing support	Work at Federal level to set training, equipment and infrastructure standards. We will also work in 5 sub-national entities as follows:(a) A continuation and consolidation of existing activities in Benadir, Puntland, Jubaland, and the South West State, (b) an incremental expansion into one additional state- Hiraan Middle Shabelle and (c) deliver support to Somaliland police through the CSSF Somaliland Strategy and Programme. / Pros: Maintains equitable geographic scope of the current portfolio. Delivers support to policing in Somaliland through the CSSF programme. / Cons: Somaliland policing results will be captured under the CSSF results framework.
Scale	Continue with existing portfolio of interventions / Pros: Simple to manage / Cons: Does not reflect the developments in Somalia or the needs since 2013. A huge amount of policing needs and wider stabilisation objectives would go unmet and existing investments could be imperilled	Pros: DFID support is wholly focused on supporting the immediate stabilisation agenda and AMISOM’s exit strategy / Cons: Al Shabaab threat is likely to be displaced and policing needs will emerge in new areas, e.g. Puntland. To avoid major security reversals it is important to ensure stable areas such as Puntland and Somaliland are maintained.	Scale up our bilateral contribution to the justice sector / Pros: A greater proportion of the New Deal justice priorities in Somalia can be met with increased resources. Support will be calibrated to absorption capacity. / Cons: Even with the scale up, there will still be significant needs in Somalia. Important to ensure that areas in which we scale up are carefully chosen to ensure the broader conditions are in place for successful scale up.
Delivery	Continue with existing delivery partners as long as delivery standards and performance are maintained / Pros: Existing relationships relatively simple to manage. / Cons: Unlikely that current partner performance will remain stable. Experience shows that regular staff turnover will inevitably lead to dips in performance which will need to be managed. We expect to make delivery adjustments even under this steady state scenario.	Along with the reduced geographic scope, prioritise private sector delivery options in new geographic areas. / Pros: Enables us to test multilateral vs private sector vfm options in different geographic regions / Cons: Likely to attract high private sector delivery costs in the two new geographic areas where access is extremely limited and delivery capacity is untested. Limited opportunities for joint programming with the EU and Japan	A mixed delivery approach: AMISOM training lead combined with limited additional private sector TA to deliver middle management training[8]. MPF contributions to UNOPS for infrastructure and equipment support / Pros: Maintains existing tried and test partnerships and provides more scope for co-ordination through joint programming under the MPF
[8] Specialist training delivery options to be assessed based on on-going threat analysis and capability baseline assessment

3. Expand, train, equip and provide infrastructure to justice agencies in targeted areas
	Continue with current programme	Scale back	Expanded programme
Scope (Geography and Administrative level)	Benadir, Jubaland, Puntland, the South West State and Somaliland / Pros: Consolidating activities in these areas would allow for simple project management. / Cons: Some key parts of Somalia would continue to receive no justice services.	Reduce support to legal assistance in Somaliland and Puntland on the basis that such activities have been on-going for a number of years. / Pros: Would allow increased focus on newly emerging federal member states. / Cons: Would entail major and rapid wind down of activities in Somaliland and Puntland and represent dramatic shift in HMG approach in Somalia.	No work at Federal level. Support work in 5 sub-national entities as follows:(a) A continuation and consolidation of existing activities in Benadir, Puntland, Jubaland, and the South West State and (b) an incremental expansion into one additional state- Hiraan Middle Shabelle.
Scale	Continue with existing portfolio of interventions / Pros: Simple to manage / Cons: Does not reflect the developments in Somalia or the needs since 2013. A huge amount of need/demand in the justice sector would go unmet and existing investments could be imperilled	Reduce financial support for legal infrastructure / Pros: Allows for more targeted interventions / Cons: Demand and need for better infrastructure in Somalia is massive. Even current anticipated support will only meet a limited need. No other donor has resources to invest in this area on any significant scale.	Scale up our bilateral contribution to the justice sector / Pros: A greater proportion of the New Deal justice priorities in Somalia can be met with increased provision of resources. Support will be calibrated to absorption capacity. / Cons: Even with the scale up, there will still be significant needs in Somalia. Important to ensure that areas in which we scale up are carefully chosen to ensure the broader conditions are in place for successful scale up.
Delivery	Continue with existing delivery partners as long as delivery standards and performance are maintained / Pros: Existing relationships relatively simple to manage / Cons: Unlikely that current partner performance will remain stable. Experience shows that regular staff turnover will inevitably lead to dips in performance which will need to be managed. We expect to make delivery adjustments even under this steady state scenario.	Only use one delivery partner either UN or private contractor / Pros: Easier to manage and reduces burden on staff / Cons: Neither UN nor private sector has demonstrable comparative advantage across all the areas we are seeking to work in.	A mixed delivery approach: UNDP and Private Contractor. / Pros: Ensures that partners with particular comparative advantages are working in their area / Cons: Increases programme management time.

4. Improving integration across the justice chain
	Continue with current programme	Scale back	Expanded programme
Scope (Geography and Administrative level)	This would entail essentially “doing nothing” as no significant work is going on this area / Pro: Entails no increase in management time / Con: Not engaging means that key issues in ensuring a sustainable justice system are not met	This section is discounted as it is not possible to “do less” than the current “nothing”.	Work at all sub-national entities – / Pros: Working at all levels is required in order to ensure that the cohesion of the justice system chain in Somalia can be ensured (including appeal mechanisms). / Cons: Sub-national states are at various states of development so handling the variable trajectories will be relatively management intensive
Scale	N/A	N/A	Provide the first direct financing for this work. / Pros: Increasing financial support in this area will increase the probability of better human rights compliance within the justice chain / Cons: As the only visible financier there is a certain reputational risk associated with this work – this can, however, be well mitigated.
Delivery	N/A	N/A	Draw in new delivery partners to take forward this work / Pros: Drawing in specialist skills will help consolidate existing investments in functional capacity building and improve overall performance and effectiveness across the justice chain. Ensuring effective partner coordination will improve the cohesion of the justice chain / Cons: New entrants will lead to lengthy start-up phases and will require increase management time.

Conclusion:
An expanded programme is the recommended option

IV:	Theory of Change
 The theory underpinning this programme is that, if we continue to support training and hardware required to deliver services, and if those services can be complemented by the development of political, legal and financial frameworks, then we will build the foundations for sustainable security and justice institutions in Somalia (the outcome), which in turn plays a part in improved rule of law and public safety (the impact). As previously mentioned, the focus on policy frameworks and standards is intended to deliver the sustainable institutions mentioned in the outcome, but those institutions and frameworks need to be credible in order to stimulate demand for security and justice services. A high level Theory of Change is set out in figure 1, below:
police in recovered areas

Delivers the tools and foundations for sustainable S&J institutions that improve state-led service delivery
Delivers the tools and foundations for better service delivery
OUTCOME: The Foundations for Sustainable Security and Justice Institutions are in Place
Output 2: Support Development of Political, Legal and Financial Frameworks:
Political agreements on federal policing and justice arrangements are in place
Credible security sector payroll established
Medium-term security and justice sector expenditure frameworks in place at federal and regional levels
Output 1: Expand, Train, Equip and Provide Infrastructure for Police in Targeted Areas:
Pay stipends to 600 additional Provide police infrastructure and equipment in recovered areas
Train and equip IED/EOD teams
Support basic training and mentoring
Output 3: Expand Reach, Train, Equip and Provide Infrastructure to Justice Agencies:
Deliver justice infrastructure and equipment
Provide training and mentoring to justice personnel
Provide support to Mobile Court Units
UK funding is sufficient to improve S&J in Somalia
Sufficient political will for S&J reform
Adequate political effectiveness (foundation of rule of law)
Institutional reforms support more sustainable, quality S&J services
Justice effectiveness is a foundation of rule of law
Figure 1: Theory of Change for the Preferred Option
Joint Activities (Outputs 1 and 2):
Conduct third party monitoring of project delivery
Train executives and middle management within police command and justice bodies
IMPACT: Improved Rule of Law and Public Safety in Somalia

IV: Value for Money
A detailed VFM analysis has been undertaken and documented. A summary of the suggested economy, efficiency and effectiveness indicators is provided below. A final set of indicators will be chosen during the inception period.

Economy Indicators

- Annual cost of security attributed to DFID security [police] and justice activities through partner delivery agencies.
- Annual cost of activities conducted outside of Mogadishu, Hargeisa and Garowe attributed to DFID security [police] and justice activities by partner delivery agencies.
- Annual cost of equipment packages provided to police and the judiciary in each region.
- Annual overheads arising from the payment of police stipends.
- .

Efficiency Indicators
- Annual staff turnover rates for all direct security [police] and justice positions in partner delivery agencies.
- Annual percentage of security [police] and justice staff based within Somalia for partner delivery agencies.
- Construction costs for police and justice facilities constructed by partner delivery agencies on behalf of the DFID Security [police] and Justice Project compared to costs of locally constructed facilities.
- Annual percentage overhead costs attributed to the payment of police stipends.
- Percentage difference in invoiced costs for a sample of selected items of equipment provided by partner delivery agencies under the police and judicial equipment package activity against market costs for identical or similar items.
- Percentage of sample equipment from previous year equipment packages delivered to police and judicial agencies which can be produced by recipients and validated by serial number or other unique identifier.

Effectiveness Indicators
- Annual differences in the aggregate score from the Somali Security [police] and Justice Scorecard attributed to the UK intervention.
- Annual differences in the aggregate Somalia score from the Ibrahim African Governance Sub-index for Safety and Rule of Law attributed to the UK intervention.
- Annual reviews show that political, legal and financial frameworks are being implemented
- An exit strategy for stipend support through greater government contributions to recurrent costs (police salaries).

## Commercial Case

Since 2013, the range of implementing partners available has increased partly as a result of efforts from DFID Somalia, (including scoping exercises and early market engagement) and partly in response to increased development spending by donors. In addition to UN agencies, the World Bank is now an important channel for the delivery of development assistance. A number of private sector contractors experienced at delivering development assistance in fragile states have also now demonstrated an ability to work effectively in Somaliland, Puntland and Southern Somalia, including cities such as Baidoa and Kismayo that were entirely out of reach just 3 years ago. The Somalia Stability Fund and the Somaliland Development Fund, both managed by private contractors, are good examples of how the private sector is able to deliver a range of complex projects across Somalia.

Nonetheless, as in many fragile states, the options open to DFID are still relatively limited. Between 2005 and 2012, DFID mainly worked with the United Nations Development Programme on support to policing and justice in Somalia. Since 2013, in response to the changing market dynamics outlined above and an explicit decision to pilot alternative delivery options, to drive up partner performance, we have tested other UN agencies, NGO and private sector delivery partnerships.

The private sector delivery options, while significantly improved, are still relatively limited. Our experience has shown that, the costs of delivery are broadly similar, and there are significant challenges in squaring the circle between value for money, inputs and results for larger contracts. We found that the private contractor route for large projects has been less effective for donor co-ordination- the majority of other donors continued to fund UN rule of law programmes and the challenges of ensuring both operational and policy level co-ordination were significant.

The experience and lessons learned from DFID’s support to security and justice programming across Somalia since 2005, has led us to pursue a commercial strategy based on the following broad principles:

- Given the high risk nature of this programme, funding modalities that maximise the potential for enhancing donor co-ordination and greater risk burden share will explicitly be pursued.
- Each component’s procurement strategy will place an emphasis on the use of implementing partners with proven experience, clear comparative advantage and an understanding of the Somalia political context.
- We will avoid large and long-term tenders for technical assistance related to institutional strengthening work. Experience has shown that we need a more incremental and adaptive means of supporting institutional reform. We will therefore preference the use of adaptive payment agreements (e.g. output based contracts, delivery by results) whether contracts, MoUs or accountable grants. This approach will enable us to (a) flexibly deploy technical assistance (b) test political will in key institutions, and (c) expand and contract our support based on performance.

Based on these considerations, we envisage channelling approximately 67% of this programme through earmarked contributions to the United Nations Multi-Partner Trust Fund (UNMPTF). The two UN implementing partners will be the United Nations Office for Project Services (UNOPS). UNOPS will be responsible for 50% of the total UNMPTF contribution, all of which represents an uplift to on-going activity that we judge to be progressing well. The United Nations Development Programme (UNDP) will deliver the remaining 50%. We have focused this contribution on areas where we believe UNDP has a comparative advantage that would be difficult and too costly to replicate- mobile courts and legal assistance. The untested area is that of judicial training. Here our investment logic is driven by the fact that UNDP has an established footprint and operational platform in all of the target areas identified under our programme and has a historical track record of delivering judicial training.

The UN MPTF was set up as a New Deal funding instrument. A signing ceremony was held for the first six priority UN programmes under the MPTF on 17 June 2015 Capacity Development, Rule of Law, Constitutional Review, Elections, State Formation and Youth Employment. DFID is currently financing four of these programmes through a one year £5.3m contribution. This is set to increase by an additional £12m contribution in the next few months.

The MPTF itself is managed from New York. For our current support, given the amount of DFID funding, we have negotiated with the fund management team to ensure: (a) DFID funds are only used for the earmarked programmes; (b) DFID receives direct quarterly narrative and financial reporting against the programme documents’ results frameworks and budgets, in addition to the overall consolidated reporting against the MPTF; and (c) DFID can pay tranches based on progress against outputs. We propose to extend this agreement to cover this programme.

The use of the MPTF incurs an additional 1% fee on top of the 7% overhead charged by each programme. This brings total management costs to 20-30% for each of the programmes. This is comparable with costs that DFID has been paying for UN programmes in Somalia to date, and includes delivery costs such as UN staff advising government.

The remainder of the programme (33%) will be contracted through an Accountable Grant, the Professional Evidence and Applied Knowledge Services (PEAKS) - Governance, Social Development, Conflict & Humanitarian (GSDCH) framework and a Memorandum of Understanding with the World Bank.

#### Commercial approach by component
#### Table 3 - Sub-Component Delivery Partner & Contract Route
#	Purpose	Value	Imp. Partner	DFID Funding %	CSSF / %
Component 1 – Support Development of Political, Legal and Financial Frameworks GBP 4.3m
1.1	Public expenditure review and payroll reform	GBP 2m	World Bank	50%
1.2	Security sector financing strategies	GBP 800k	Private sector	100%
1.3	Score card/baselines	GBP 1m	Private sector	100%
1.4	Federal policy and legislation development	GBP 500k	Grant Agreement	50%
Component 2 – Expand, train, equip and provide infrastructure for police in targeted areas GBP 17.3m
2.1	Police Support Package	GBP 3m	UNOPS	45%
2.2	Middle Management and refresher training	GBP 1m	UN/AMISOM	100%
2.3	Specialist Counter-Improvised Explosive Device training	GBP 4m	UNMAS/other	60%	100%
2.4	Stipend support	GBP 5.0m	UNOPS	100%
2.5	Stipend support from RBPP	GBP / 2.3m	UNOPS	100%
2.6	Infrastructure	GBP 2m	UNOPS	70%
Component 3 – Expand, train, equip and provide infrastructure to justice agencies in targeted areas GBP 13m
3.1	Middle management and refresher training	GBP 4m	Private sector	100%
3.2	Mobile courts	GBP 3m	UNDP	30%
3.3	Legal Assistance	GBP 3m	UNDP	30%
3.4	Infrastructure	GBP 3m	UNOPS	30%
Component 4 – Monitoring and Risk management GBP 1.7m
4.1	Third party monitoring	GBP 1.2m	Grant Agreement	100%
4.2	M&E	GBP 500k	Private Sector	100%
	TOTALS	GBP 36.3m		GBP / 32.3m	GBP / 4m

Component 1- Support Development of Political, Legal and Financial Frameworks (GBP 4.3m)

The public expenditure review and payroll reform elements of this component will be delivered by the World Bank, in line with its objective to provide some limited additional support for Bank-executed operations that enable the Bank to work more flexibly and politically; and address potential delivery bottlenecks. The agreement would be through two Externally Financed Outputs (one for 2016/17 and one 2017/18). Each EFO would spell out specific priorities, and would be underpinned by a regular dialogue between DFID and the Bank on delivery, alongside regular reporting.

The support to political negotiations on federal security arrangements will be delivered through a suitable organisation with a track record in facilitating sensitive political and security negotiations through an Accountable Grant agreement. The rationale for choosing an Accountable Grant over a contract is based on a market assessment. Non-profits working in this sector have a comparative advantage in terms of quality, knowledge and access to key political decision makers that a private contractors do not appear to be able to bring to bear as a recent review of justice sector work in Somaliland noted.

The scorecard and baseline assessment work will be delivered through the PEAKS Governance, Social Development, Conflict & Humanitarian (GSDCH) framework. The terms of reference for this work will be developed by DFID. A small team of 2 -3 consultants with relevant technical expertise and knowledge of security and justice programming in Somalia will be selected for this assignment.

Component 2 - Expand, Train, Equip and Provide Infrastructure for Police in targeted areas (GBP 17.3m)

The infrastructure, procurement, stipend support and police support package elements of this component will largely be delivered by the United Nations Office for Project Services (UNOPS). This represents a continuation of on-going support to UNOPS £11m of new financing + £2.3 million incorporated from the RBPP) which is progressing well (Annual Review Score A, Re-establishing Basic Policing Programme and Output Score A under Core State Functions Programme). UNOPS has a proven track record in procuring and delivering, infrastructure, training related materials, and delivering police stipend support in the target areas identified. They have an established project implementation structure in Somalia and are likely to be identified as the UN organisation tasked with the management of the United Nations Security Council authorised Police Support Package. Our support to UNOPS would be through earmarked support to the UN Multi-partner Trust Fund (UNMPTF).

During the first quarter of 2016 we initiated a baseline assessment of on-going Counter-Improvised Explosive Device (C-IED) training and equipment capacity in four urban areas. Conclusions from this assessment will guide the commercial strategy for this element of this component. This component of the programme will be CSSF financed (£4 million). We have previously financed UN Mine Action Service to support this work. As part of this programme we will tack stock of market options in this specialist field. An IED threat assessment and delivery partner capability assessment is currently underway and will inform final decisions around delivery.

Component 3 - Expand, Train, Equip and Provide Infrastructure to Justice Agencies in targeted areas (GBP 13m)

The training, mobile courts and legal assistance elements of this component will be delivered by UNDP, as part of its on-going project funded by several donors through the UN’s Multi-Partner Trust Fund. This would be a continuation of current DFID funding (we earmarked GBP 1.85m for this project in our first contribution agreement to support the UN MPTF in June 2015). We continue to monitor UNDP performance closely, in response to lessons learned on operational delivery across our wider portfolio. We will also link tranche releases to assessments of achievement against the annual milestones set out in the project document in order to encourage a strong performance focus.

Infrastructure and procurement elements will be delivered through UNOPS as part of our earmarked UN MPTF contribution.

All DFID funding through the UN MPTF will be earmarked for specific projects, reducing the risk of DFID funding going to areas we do not consider a priority. We have and will continue to work closely with the EU (the other major donor partner) on UNDP performance issues to ensure a coherent donor position.

Component 4 - Third party monitoring (GBP 1.7m)

This component will be delivered by an Accountable Grant A call for proposals will be issued in 2017 for the second phase.

International Not for Profit organisations have been very effective in delivering 3rd party monitoring for DFID funded projects in Somalia and are showing interest in continuing to undertake these activities. For example, DFID’s policing programme is currently using Sahan Foundation to do 3rd party monitoring. They have demonstrated a good abilty to deploy strong technical expertise and operate effectively in the target areas.

#### Key Cost Drivers
We expect the key cost drivers in this programme will be security, staff costs and travel.

Security

For the foreseeable future, Somalia will remain a highly insecure environment. Levels of insecurity differ from location to location, but almost all locations require physical premises reinforced with security infrastructure, the use of armoured vehicles and full-time security expertise and Close Protection Teams for international staff.

We will seek to manage security costs by encouraging co-location where possible (for example among UN agencies) and by close monitoring of costs across contracts to establish benchmark averages.

Staff costs

Staff costs are considered to be somewhat higher in Somalia than in other more stable or longer-established markets due to insecurity and the resulting impact on supply. High quality international consultants are generally less willing to work in such environments, and therefore expect a premium to do so. Capable local consultants are in short supply with many educated Somalis still overseas, and those remaining in Somalia inexperienced in modern public administration. This restricted supply of both international and local staff, combined with increasing demand as donors spend more, drives costs up. We believe the best way to counter this is to ensure the most competitive environment for consulting services possible, by encouraging as many service providers as possible to consider entering the market.

Travel

This programme envisages work in a wide variety of locations. Most implementing agencies are expected to retain some operations in Nairobi (as does DFID). Under the various components, operations will then be needed from Hargeisa and Garowe in the North, to Baidoa, Beledweyne, Mogadishu and Kismayo in the South.

## Financial Case

The total budget (approved, bilateral and CSSF) for this programme is £36.3 million. This is made up of:
- £2.3m representing the balance of the approved Re-establishing Basic Policing Programme which is now being merged into the new SSJP
- £30m from the bilateral aid budget, and
- £4m from the CSSF over four years.

We are only requesting approval for the £30m outlined above. These funds will be disbursed through four implementing partner agreements covering the different streams of work. All the figures are reflected in the table below.

Table 4 – Estimated break down of costs over programme years.
	2016/17 (millions)	2017/18 / (millions)	2018/19 / (millions)	2019/20 / (millions)	Totals / (millions)
Component 1: Support Development of Political, legal and Financial Frameworks	0.5	1.3	1.5	1	4.3
Component 2: Expand, Train, Equip and Provide Infrastructure for Police in targeted areas	1.0	3.5	3.4	3.1	11.0
Component 3: Expand, Train, Equip and Provide Infrastructure for Justice Agencies in targeted areas	1.5	3.5	4.0	4.0	13.0
Component 4: Third party monitoring	0.3	0.5	0.5	0.4	1.7
Total New Financing	3.3	8.8	9.4	8.5	30
RBPP (supports component 2 outputs)	1.3	1	-	-	2.3
CSSF (supports component 2 outputs)	1.0	1.0	1.0	1.0	4.0
Grand total - bilateral + CSSF	5.6	10.8	10.4	9.5	36.3

Costing analysis
The cost estimates for this programme were developed based on experience from existing work in the security and justice sectors in Somalia under the Core States Functions Programme e.g., legal aid costs, police reform work with the private sector (Adam Smith International) and non-profit (Horizon).

The allocation to the programme is based on design team estimates. Funds will be re-allocated by the programme team between components, over the years, to reflect implementation requirements and performance.

The costs for two programme funded post to provide technical assistance will total 1.6% of the total programme budget. As is explained in more detail in the management case, these posts are critical in order to be able to maximise the effectiveness of our investments in Somaliland and Puntland by ensuring a more robust and consistent dialogue with partners (including government) on the ground. This will deliver an enhanced set of results and has been a key lesson learned from the last four years of working in Somalia. The current preference is for a post in Somaliland to be supported through a service provider arrangement. A post in Puntland would be created on a cost-sharing basis with the European Union.

This programme will be monitored through a third party mechanism at a cost of approximately £1.8M translating to 4.6% of the programme budget. An additional 1.3% of the total programme budget has been set aside for M&E costs, including annual reviews and project completion report.

Co-financing with other donors
EU contributed EUR 11M to the Justice work under the UN Multi Partner Trust Fund (UNMPTF) although their financing was un-preferenced. The EU continues to be in discussions with the UN and the FGS about how best to programme their funds. The EU and Japan provided intermittent stipend support to the Federal Police in Mogadishu through UNOPS. US supported programmes are delivered outside the UN Rule of Law programme and are narrowly focused on specialised criminal investigations capacity building. The most likely prospect for co-financing remains the EU.

Method of disbursement
At least four types of financial instrument will be required to deliver this project. These instruments reflect our experience of comparative advantages of viable partners already working in the sector and in this context who are also able to demonstrate value for money.

Multilateral MoU: The United Nations Office for Project Support (UNOPS) will deliver the Rule of Law component of the programme. A memorandum of understanding will be signed with UNOPS clearly stipulating a disbursement profile agreed at the start-up phase of the project. Payments will be disbursed against agreed milestones.

Accountable Grant: We will continue to use this modality for the third party monitoring component. Grantee/s will be paid quarterly after the review of quarterly narrative and financial reports. A forecast of spend will be provided at the beginning of every financial year and reviewed at the end of each quarter, where necessary.

Commercial Contract: Commercial partners will be contracted through the PEAKS framework to fill the programme funded post and deliver the scorecard/baseline component of the programme. The programme funded post will be paid monthly in arrears against agreed deliverables, while the scorecard/baseline aspect will be paid quarterly in arrears against set milestones.

Memorandum of Understanding: This will be signed with the World Bank disbursements will be made on quarterly basis.

Accounting and audit
Accountable Grant/commercial contracts
To monitor spend each financial year, partners with Accountable Grants and Commercial contracts will submit quarterly financial reports, with an annual report at the end of the year. In addition, annual institution audit reports will be submitted. Quarterly meetings will be held with each partner to monitor budgets, forecasts and spend.

Commercial/Accountable Grant partners, will be contractuallyrequired to submit project specific audit reports at the end of each calendar year.

Multilateral partners
UNOPS is audited at country level on an annual basis and will share the reports with DFID. Annual Headquarters-level audit reports are also posted in their website for easy access for their partners.

The DFID Programme Manager and Finance Manager will work closely with partners and give guidance on budgets, forecasts and spend.

Fiduciary risk management and due diligence
This programme is rated high risk as it proposes to work across complex, fragile and often insecure contexts. The partnerships selected for this project have been chosen on the basis of comparative advantage in the specific areas that they will work, and their ability to manage the particular operating risks effectively. For example, UNOPS has a comparative advantage of delivery of infrastructure and equipment through the ongoing Re-establishment of Basic Policing in Somalia project.

In addition to the SMP, the programme will be monitored through a third party monitoring mechanism already established by Sahan Foundation who are currently conducting third party monitoring of the Police Stipends Project to ensure effective fiduciary oversight.

A comprehensive risk assessment and management framework will be developed with each partner and monitored on a quarterly basis. Due Diligence Assessments on UNOPS and Sahan were carried out in 2014. Both partners are on track to implement the recommendations provided. Due diligence will need to be undertaken on UNDP since the current due diligence has lapsed. However, this work is being undertaken more broadly by the Governance and Security team as a number of programmes rely on UNDP.

For the commercial partners, due diligence has been completed under the requirements of the PEAKS framework agreement. However, all partners are expected to carry out Due Diligence assessments of sub-contracted partners.

Use of Financial Aid
Funding will be paid directly to the UNOPS, UNDP, Sahan Foundation, and the World Bank. Funds will not be paid directly to government systems.

Additional Financial management requirements
Asset management
Major assets may be procured through this programme. We will ensure (as part of our due diligence), that all partners have internal processes in place to register, monitor and account for assets worth £1,000 and above, procured during the programme. Annual reports will include details of any assets acquired through an asset register for each component. At project closure, DFID will decide on transfer of ownership of assets to agencies (including local partners or sub-contractors) if necessary.

Return of Funds
Any unspent funds remaining at the scheduled end of a project (including from exchange rate fluctuations); will be returned to DFID unless specifically agreed between DFID and the implementing partners in writing.

## Management Case

DFID Management/delivery
The SSJP is the principal delivery mechanism for key elements of Pillar 2 of the NSC Strategy for Somalia and the UK aid strategy. Close cross-government working and joint programming is envisaged, particularly in Somaliland. The CSSF Local Strategy Board provides a critical forum for regular co-ordination.

The Somalia Security and Justice business case is one of a number of programmes in the Governance and Security portfolio of DFID Somalia. The overall management of this portfolio is the responsibility of the Governance & Security Team Leader. The SRO for Security and Justice will be the A1 Conflict Advisor supported by a B1 programme officer.

Given the complexity, risk and geographic scope of the programme as a whole, in addition to the A1 Conflict Advisor, some management time will be drawn from an A2 Governance Advisor within the Governance and Security team. The A2 Governance Advisor will lead on overseeing the work related to the “justice” components, while the A1 will take the lead on the “police” components.

A B1 Programme Officer (expected FTE 75%) from the DFID Somalia Governance Team will be part of the management team to support programme delivery. The SRO and Programme Officer will together provide programme management oversight, co-ordination, quality assurance and peer review.

Contracted technical assistance
Due to geographical spread of the programme and the widely different set of needs between Somaliland and Puntland as opposed to the emerging Federal Member States, the programme will look to support specific positions focusing both on Somaliland and Puntland. Experience since 2012 suggests these positions are important to deliver high performing projects since: (i) the nature of much of the work that is anticipated under this programme is political and therefore requires a high and consistent level of engagement with partners; (ii) the nature of the political dialogues – particularly in Somaliland – are very different from the rest of Somalia and therefore requires a specific focus; (iii) Duty of care has significantly restricted the ability of DFID advisors to travel to Puntland in any meaningful way for the last 1.5 years; and (iv) Unlike in Mogadishu, there are no other donors who can lead on this dialogue.

There are three potential mechanisms for management support: (1) Joint financing of individual positions through a private contractor model with the EU with the individuals based in Hargeisa and Garowe; (2) Joint financing with the EU for the same two positions but through the UN; and (3) DFID directly financing the individuals as private contractors with locations to be determined. The choice of management mechanism is subject to ongoing discussions, however, it will be expected that whatever mechanism is chosen, the individuals will have specific reporting lines back to DFID Somalia in Nairobi and will also feed into conflict and security programmatic and policy discussions out of Addis Ababa.
#### Timeframe – start-up and implementation phases
The programme is expected to become operational in August/September 2016 (contingent on receiving Ministerial approval). No significant delays are expected between approval and start up since nearly 90% of programme funds will be channelled through MoU with multilaterals in support of existing programmes. The remaining components will be programmed using the most efficient mechanism available (e.g. framework contracts rather than full “OJEU” processes).
#### Results, monitoring and evaluation
The DFID Annual review process will ensure regular monitoring of the overall programme. The logical framework in (QUEST 5479543) will be used as the basis to assess performance. Each component and subsequent implementing partner will be accountable to a further set of results and will provide regular reporting (at least quarterly) against agreed milestones/targets. For example:

- UN projects each have results frameworks linked to budgets included in their project proposals, against which they will report; and
- The commercial partner contracted will be asked to agree a detailed results framework to underpin dialogue on progress between the implementing partner, government counterpart and DFID Somalia

Since not all project results are likely to be captured in the overall programme logical framework, Annual Review teams will also be asked to comment generally on progress against these component-level results frameworks.

Having a dedicated resource focusing on Somaliland and Puntland will provide additional inputs into the monitoring of how project activities in Somaliland are progressing. In addition to this, the programme will also recruit – through a private contractor – two experts who, on a semi-annual basis (including around the Annual Reviews) – will provide advice as to how the overall programme is progressing and suggest any remedial actions.

Monitoring (including third party monitoring)
In addition to the DFID Annual Review processes, the programme team will monitor implementation and performance through quarterly meetings with partners to review progress (following submission of quarterly reports). Internally, the programme team will continually update the Programme Delivery Plan to ensure programme issues are dealt with in real time.

As much of Somalia is not accessible to DFID staff for field visits due to insecurity, DFID Somalia has, through the Somalia Monitoring Programme, established a system of third party monitoring that enables us to maintain oversight of project activities and outputs, independent of implementing partner reports. A new Business Case supporting a second iteration of this project was approved in November 2015 and it will run until October 2020.

This approach of the Monitoring programme continues to develop but currently involves:

- The agreement of a monitoring strategy for the coming year, based on requirements across the portfolio and within each programme
- Agreement for the scope, purpose and timing of each monitoring visit (for example, whether to verify an activity, or assess the quality of an output, or canvas beneficiary views on either activity or output)
- Conduct of the review by the implementing partner contracted through the Somalia Monitoring Programme
- Submission of review report, with an assessment, including positive or negative ‘flags’
- Lesson learning at the programmatic level by DFID and the implementing partner
- Meta-assessment of all 3rd party monitoring reviews, to extract lessons that might apply across the DFID-S portfolio

These reviews have proved highly useful at providing insights into project effectiveness under CSFP to-date. More detail on the Somalia Monitoring Programme is available here: http://devtracker.dfid.gov.uk/projects/GB-1-202984/

In addition to this, due to the high risk nature of the work involving police stipend payments, a separate monitoring agent will be engaged to monitor the delivery of this element of the programme. This will be a continuation of work already started under the existing Police Stipends business case. This monitoring agent has proved extremely effective at providing in field granular information about the stipend payment process that has ensured the programme is able to sufficiently mitigate much of the risk associated with that programme. Continuing the arrangement into this business case will provide similar levels of management, oversight and risk mitigation. This specific monitoring agent will also monitor the new areas of work under this business case related to the police support package.

Evaluation
An evaluation of the CSFP programme was undertaken in early 2016. The emerging lessons have been integrated into the design and delivery of individual components of the SSJP.

The programme will undertake at least two reviews of its work – at the mid and end point of the programme. A full-fledged “evaluation” is unlikely given that much of the work envisaged under the current programme is neither novel nor contentious. Since the programme will be following an “adaptive/flexible” approach to programme, establishing rigorous evaluation parameters from the outset will be difficult. The programme methodology and the context instead lends itself to a “review” approach to monitoring. Additionally, experience around the CSFP programme has demonstrated how difficult it is to conduct rigorous evaluations in the Somali context due to the security risks which limit the market and raise the overall costs of conducting them. So, reviews and real time operational research, combined with active remote management will be used as they have provided more useful and relevant real time information for programmes to reflect on lessons and adapt their programmes to achieve the best possible results.
#### Component-level governance arrangements
The majority of this programme is expected to be delivered through multilaterals. In all cases the work undertaken through the Security and Justice Programme will be aligned with New Deal coordination structures and both DFID and Implementing Partners are expected to report to the relevant PSG working group (either PSG 2 on Security, or PSG 3 on Rule of Law). Design work to-date has been based on a range of consultations with government counterparts and implementing partners, which will stand the programme in good stead during implementation.

Components (including sub-components)	Management Arrangements
Support Development of Political, Legal and Financial Frameworks	Not yet established, but expected to be a Steering Committee comprising DFID + HMG, FGS and Federal Member State (FMS) representatives, meeting either quarterly or 6-monthly. Other relevant donors may also be invited.
Expand, Train, Equip and Provide Infrastructure for Police in targeted areas	Common project steering committees under the PSG 2 structure – meetings once a month. Regular meetings between DFID-S Conflict advisor and AMISOM and UN teams.
Expand, Train, Equip and Provide Infrastructure to Justice Agencies in targeted areas	Common project steering committees under the PSG 3 structure – meetings once a month. Regular meetings between DFID-S Conflict + Governance Advisor and UN rule of law team.
Third party monitoring	Directly managed by DFID – results will be fed into the three structures above

#### Risk management
The overall gross risk rating for the programme is judged as [ major (score of 6.1)][9]. The net risk rating for the programme (after mitigation) is judged as [moderate (score of 4.5)]. Carefully designed risk mitigation is expected to reduce gross risk, but some risks will remain beyond the control of the programme (for example, an unexpected weakening of the AMISOM offensive). Additionally, the nature of operating in this sector in an environment like Somalia means it is unlikely that the risks could be reduced to “low”. Any heightened risk will be escalated from the SRO through the management chain to the Team Leader and Head of Office.
[9] For ARIES purposes recorded as ‘High’

The risk profile for Somalia is extreme by comparison to most other nations which are the subject of HMG development assistance (see Strategic Case). The risk management challenges are often underestimated in such settings with the effect that project outcomes, milestones and targets are not achieved on schedule and sometimes not at all. The development choices under these circumstances are stark by comparison to those of more nuanced situations and, in the first instance, evolve from fundamental judgements on whether to engage or not. Final decision of this type are more likely to reflect broader policy considerations with subsequent development decisions being less determined by the conventional return on investment model than mission survivability due to the level and type of risks to be managed.

In this context even the most aggressive risk mitigation measures can prove ineffective as treatments for possible threats to programmed activities with the magnitude of the problem often raising questions of increased tolerance to risk of loss. Somalia’s recent history demonstrates that non-engagement or light engagement policies are difficult to sustain in the face of negative externalities in the localised region with scope for various forms of contagion such as piracy and terrorism to affect the international community.

The individual risks associated with the Somalia Security and Justice Project are, as expected, disproportionally high with the political and operational risks reinforcing one another. At the most serious end of the scale the first five political risks fuse into one theme which incorporates the major dimensions of Somali state dysfunction from a security and justice perspective. These revolve around security and justice challenges which may be non-responsive to HMG’s interventions combined with potential for some or all agencies to become instruments of authoritarianism in the near absence of legal and other frameworks to formally describe responsibilities, controls, and functions at federal and state level. This situation is compounded by other risks including the underlying influences of broadly based institutional corruption and the risk that police at federal or state levels may cumulatively exhibit conduct and behaviours which are contrary DFID values.

The major risks (ordered according to risk category) are analysed and detailed in Quest No 579559, along with proposed mitigating measures and their expected effect on the gross risk. This matrix will be reviewed regularly during programme implementation with our delivery partners. Key risks will be incorporated into the delivery plan and will be updated regularly, especially at Annual Review stages. Overseas Security and Justice Assessments for this programme have been undertaken and are available on request.