Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Robert Carr Civil Society Network Fund (RC-NF)
Programme Value: Up to £4 Million		Review Date: December 2014
Programme Code: 203325	Start Date:17/12/2012	End Date: 31/03/2015

Summary of Programme Performance
Year	2013	2014
Programme Score	A	A
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review
Overall conclusions of the recent external Mid Term Review (MTR) were that the RC-NF has made significant and impressive progress. It has: completed two rounds of funding; allocated 38 grants worth $18,217,092; provided a lifeline to some of the most important civil society actors in the response to HIV; identified a unique and strategic niche within the global architecture; developed effective grant-management policies and processes; and established appropriate and highly committed governance bodies. The RC-NF’s grantees are achieving impressive work across the RC-NF’s four outputs– with strong indications that, in combination, these are ensuring stronger support to inadequately served populations and more effective responses to HIV at the country, regional and global levels.
While there remain a number of areas for clarification and improvement, some of which are urgent, progress is good given this is a complex, multi-lateral and collaborative initiative that is just two years old.

Summary of recommendations
The MTR recommended that the International Steering Committee (ISC), Programme Advisory Panel (PAP) and Fund Managing Agent (FMA) work together to:
- develop and start to implement a significantly more strategic, systematic and coordinated resource mobilisation strategy for the RC-NF;
- significantly step-up the profile and communications of the RC-NF to showcase its actual and predicted results and to sell its unique value-added to the civil society and funding architecture of the global response to HIV;
- ensure a strong and strategic niche for the RC-NF’s future – by re-confirming and ensuring consensus on the basics of its identity and purpose;
- consolidate the many good practice aspects of the RC-NF’s processes and policies – making adjustments only where vital;
- strengthen the assessment and articulation of the RC-NF’s results by: producing simpler, more practical versions of the Results Framework and Theory of Change; and building understanding across the Fund of why the tools matter and how they can be used;
- strengthen the RC-NF’s governance by re-clarifying the respective roles and responsibilities of the ISC and PAP – to reduce current tensions and maximise the bodies’ complementarity in ensuring the technical quality and strategic relevance of the Fund’s work;
- strengthen the RC-NF’s management by developing a formal process, led by the ISC, to appraise the performance of the FMA;
- develop a knowledge management strategy for the RC-NF to foster learning among grantees, share key lessons (especially about the Fund’s areas of value-added) and contribute to the global knowledge bank of the civil society response to HIV.

The UK will be particularly concerned to ensure the third recommendation above is taken forward in a way that reinforces the added value of the Fund as pro-poor.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3717358.docx
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/3647522.xls

Outline of the programme
The Robert Carr Civil Society Network Fund (RC-NF) has been designed in collaboration with donors and civil society organisations (CSOs) as a pooled funding mechanism to ensure that through global and regional action, civil society networks support improved HIV responses that reach inadequately served populations at the local level. The Fund Management Agent for the RC-NF is Aids Fonds. Other founding contributing donors to the fund are USAID, Norway, and the Bill & Melinda Gates Foundation (BMGF).

UK support is required in response to three critical issues:
1) the inadequate attention paid in national responses to the populations at highest risk of HIV and therefore most in need of effective HIV prevention, treatment, care and support services;
2) the need to address the disproportionate stigma and discrimination directed towards high-risk populations;
3) the reduction in adequate and reliable funds for regional and global civil society networks to respond to the HIV epidemic.

The definition of inadequately served populations includes the standard internationally agreed term ‘key populations’ (defined as those that face a higher HIV risk, mortality and/or morbidity when compared to the general population, principally gay men and other men who have sex with men, women and men who inject drugs, sex workers and transgender people), but the definition also includes more broadly those with less access to information and services in a number of localities including women and girls, youth, migrants and people living in rural areas.

Although the UK is principally concerned with key populations in relation to this fund given its strong commitment and good track record of support to these specific groups, the broader definition of inadequately served populations enables the fund to be more flexible and engage a broader range of donors in committing resources. Membership of the CSO networks who will benefit from the support include communities and people living with HIV. However a strong focus on key populations is essential for our continued support.

Expected Results
Civil society networks, working at global and regional levels, have sufficient and predictable resources to enhance the quality, effectiveness and gender equity of the HIV response [universal access to prevention, treatment, care and support without stigma or discrimination], especially in reaching inadequately served populations at local level.

Context
The RC-NF has issued two Requests for Proposals and allocated a total of $18,217,092. Round 1, recipients were announced in December 2012 providing 24 grants in early 2013, valued at $ 5,519,016 (for 1 year) to 7 global networks and 17 regional networks. In Round 2, it provided 14 grants in early 2014, valued at $ 12,698,076 (for 2 years), to 8 global/regional consortia, 1 global network and 4 regional networks.
This is the second Annual Review and the last before the current funding commitment finishes in March 2015. An external Mid Term Review was published in October 2014 which significantly informs this Annual Review.
DFID sees the RC-NF as an important channel for its response, and will consider options to support this kind of work in the future, subject to continual review of results, value for money and ability to retain and attract new donors.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Through core and programmatic funding, in year two the RC-NF is making concrete progress towards its goal and objectives – with strong actual results from Round 1 and planned ones for Round 2. It is making a critical difference to the structure, capacity and coordination of global and regional networks and their unique role in advocacy for the rights of key populations within effective responses to HIV. Further clarification of the niche should assist with other challenges the Fund faces – notably resource mobilisation.

In scoring this annual review we have made use of the thorough and independent Mid Term Review undertaken this year for the RC-NF.

Overall output score and description: A Outputs met expectation

Key lessons

The goal of the RC-NF has been the right one. It has been evidence based and filled a niche, responding to both: a critical need within civil society architecture (global/regional networks focused on the rights of ISPs); and a major gap in the global response to HIV (a targeted fund for such organisations). The objectives have also been right – adding up to a logical and comprehensive approach.

From its start in December 2012 the RC-NF has allocated two Rounds of funding (with 38 grants, totalling $18,217,092) towards the achievement of its goal and objectives. Its portfolio of grantees includes major, respected players within the global and regional civil society response to HIV– which support inadequately served populations that are vital to ‘know your epidemic’ and investment approaches. In both Rounds, the largest proportion of funding was allocated to grants that include attention to PLHIV and MSM.

In the Grantees’ Survey from the MTR, equal proportions of respondents (45%) felt that the RC-NF has made ‘some progress’ or ‘strong progress’ on achieving its goal. They also considered that at least ‘partial progress’ has been made on all of the objectives. Some grantees have carried out activities
across the four outcome areas. However, generally, in both Rounds 1 and 2, the RC-NF’s grantees have prioritised action under Output 1 – with all grantees reporting on at least one indicator for this area. The lowest level of results is seen for Output 4 – although action in this area is planned to increase in Round 2.

RC-NF’s resources have made a critical difference to grantees – in some cases preventing them from closure, in many others enabling them to achieve a step change in their functionality and effectiveness.
The emphasis on Outcome 1 partly reflects the nature of the RC-NF, including its provision of core
funding. However, the MTR found that it also reflects an economic reality – that, where grantees
have been forced to cut budgets, allocations to network capacity are more likely to be maintained (due to be essential for their survival, compared to programmes). Furthermore, a fundamental limitation to the results of the RC-NF has been the short duration of its grants (1 year for Round 1 and 2 years for Round 2). In reality, many of the type of results expected for Outputs 2, 3 and 4 require longer timeframes. In addition, attribution remains a challenge – as many of the results (such as in advocacy) cannot be solely or linearly traced to one organisation and/or RC-NF funding.

Key actions

Take forward the recommendations of the MTR that the International Steering Committee (ISC), Programme Advisory Panel (PAP) and Fund Managing Agent (FMA) work together to:

- develop and start to implement a significantly more strategic, systematic and coordinated resource mobilisation strategy for the RC-NF;
- significantly step-up the profile and communications of the RC-NF to showcase its actual and predicted results and to sell its unique value-added to the civil society and funding architecture of the global response to HIV;
- ensure a strong and strategic niche for the RC-NF’s future – by re-confirming and ensuring consensus on the basics of its identity and purpose;
- consolidate the many good practice aspects of the RC-NF’s processes and policies – making adjustments only where vital;
- strengthen the assessment and articulation of the RC-NF’s results by: producing simpler, more practical versions of the Results Framework and Theory of Change; and building understanding across the Fund of why the tools matter and how they can be used;
- strengthen the RC-NF’s governance by re-clarifying the respective roles and responsibilities of the ISC and PAP – to reduce current tensions and maximise the bodies’ complementarity in ensuring the technical quality and strategic relevance of the Fund’s work;
- strengthen the RC-NF’s management by developing a formal process, led by the ISC, to appraise the performance of the FMA;
- develop a knowledge management strategy for the RC-NF to foster learning among grantees, share key lessons (especially about the Fund’s areas of value-added) and contribute to the global knowledge bank of the civil society response to HIV.

From a DFID perspective, the third recommendation above is particularly vital. It is essential that the Fund sharpen its focus on its strategic niche. For DFID the added value of the fund is reaching key populations marginalised in the response rather than a more general HIV civil society strengthening mechanism. It is also essential for DFID that the focus of the Fund remains pro-poor.

Finally, the International Steering Committee (ISC) of the Fund should consider its relationship to Global Fund to fight HIV, TB and Malaria, in the light of the latter’s funding of the RC-NF, to ensure the RC-NF contains to add distinct value and there is no duplication.

Future reviews should also look in more detail at the end impact of grantees’ work on the ground and the ISC should consider ways to facilitate this.

Has the logframe been updated since the last review?
This is a pooled funding mechanism and the expected results for the RC-NF are articulated in a shared Results Framework http://www.robertcarrfund.org/wp-content/uploads/2013/09/20130701-RCNF-Results-Framework-final.pdf?c866de,
supported by a Theory of Change http://www.robertcarrfund.org/wp-content/uploads/2014/08/20130731-RCNF-TOC-visual-V2.jpg?c866de
As already indicated it is recommended that these are simplified in order that reporting against key indicators on impact by grantees can be made clearer.

The RC-NF’s International Steering Committee has discussed the need to improve capture of impact, recognising the challenges of aggregating results in a Network fund such as this. DFID will wish the process of refreshing the framework, coming out of the Mid Term Review, to include refinement of milestones and progress indicators in the shared results framework.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	GLOBAL AND REGIONAL NETWORK CAPACITY / The capacity of global and regional networks and their membership is improved, such that networks enable well-capacitated, representative and accountable civil society to influence the delivery of effective responses to HIV.
Output number per LF		1	Output Score	A+
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Output moderately exceeded expectation. Improve the capacity of global and regional networks to support meaningful participation of inadequately served populations, in influencing policy at global, regional, and national levels such as: meeting universal access targets, ensuring high quality and equitable care, treatment and prevention support.
Progress
For both Rounds 1 and 2 100% of the grantees – 38 grants in all addressed this output. Continues to be a significant component of the expected results as building capacity of networks has been a priority for the RC-NF but Round 2 has improved spread across the four outputs.
Specific examples reported by grantees against output 1: Grants from the RC-NF:
- contributed to a stronger, more coordinated structure for the sex worker movement. Enabling the Network of Sex Workers Programmes to better understand the issues of its regional/country members and, in turn, improve the messaging of its advocacy in global policy forums. Examples of the latter are with the UNAIDS Key Populations Inter-Agency Working Group and the Global Fund (where it advocates for the rights of sex workers within the New Funding Model and policies to promote human rights and community systems strengthening).
- enabled the Men who have Sex with Men Global Forum (MSMGF) to establish a more far-reaching, stable and sustainable infrastructure for the MSM movement that, in turn, strengthens the impact of its work, such as in advocacy. This was demonstrated by developing a global strategy and led to a formal Consortium of MSM Networks. The work was backed-up through capacity building and tool development. Examples included regional Speak Out advocacy trainings and a LAC adaption of a Sexual Health and Prevention Guide for MSM. It also included the MSMGF: increasing its media outreach (resulting in 115 new stories on the health/rights of MSM in widely-read outlets); and building a multi-lingual, on-line knowledge hub (with thousands of resources on MSM-related issues).
- strengthened the ability of Youth LEAD and its partners to engage in critical regional and national processes affecting their constituents. enabled Youth LEAD to play a stronger leadership role in Asia Pacific, such as co-chairing the Inter-Agency Task Team on Young Key Populations and, within PACT (a global alliance of 25 youth networks), advocating for action on legal barriers. In parallel, Youth LEAD increased the number of its national focal points from 27 to 57, with the addition of countries such as Mongolia and Bangladesh.

All of the above successfully received grants in Round 2 as consortia (Global and Regional Networks of Sex Worker Projects Consortium, the Consortium of MSM Networks and the Consortium of Networks
Youth LEAD and HIV Young Leaders Fund) itself proof of improved capability but which has also to some part corrected the unwanted effects of Round 1 whereby there was competition for limited resources between global and regional networks.

Recommendations
It is difficult to quantify impact across 38 grants in a systematic way. As already indicated the remedy is to strengthen the assessment and articulation of the RC-NF’s results by: producing simpler, more practical versions of the Results Framework and Theory of Change; and building understanding across the Fund of why the tools matter and how they can be used in order that reporting against key indicators on impact by grantees can be made clearer and easier. The ISC should also look at site visits in the coming year to track ultimate beneficiary impact.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	ENHANCING HIV RESPONSE IMPLEMENTATION: / Inadequately served populations influence HIV responses for greater relevance, equity, accessibility and delivery across the full spectrum of prevention, treatment, care and support services.
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Output met expectation. Advocacy interventions to improve progress and implementation of the HIV response.

Progress:

71% of the grantees addressed this output in Round 1 and 85% in Round 2. Interventions adopted by networks under this output included; ISP input provided into the content/language of specific global/regional/national policies for ISPs; Processes strengthened for ISPs to input into government and other decision-making bodies, such as Country Coordinating Mechanisms; targeted services, such as HIV rapid testing, provided to highly marginalised, ‘hard-to reach’ ISPs; focus and quality of service delivery to ISPs improved, such as through the training of health workers.
Specific examples reported by grantees against output 1:
Grants from the RC-NF:
- enabled the Global Network of People Living with HIV (GNP+) to support national, regional and global responses to HIV by providing evidence-based tools, positions and messages that specifically focus on the needs of PLHIV. For example through its HIV Leadership Through Accountability programme, the network supplied five tools to 10 country partners to measure and address HIV-related stigma, restrictive laws and policies, human rights violations, the greater involvement of people living with HIV (GIPA) and the SRHR of PLHIV. It also informed national and regional responses by developing a series of papers on treatment policy, such as on treatment as prevention and PLHIV-led decentralization of treatment services.
- enabled REDLACTRANS, a regional network that represents the transgender community, to continue to raise the profile of transgender people in the Latin-American and Caribbean region and to influence national and regional responses to HIV that meet their needs. It used RC-NF resources for targeted programmatic activities to reach highly marginalized transgender people who might otherwise not access HIV services. For example, it provided free HIV tests to 138 transgender women and started rapid HIV testing (an appropriate approach for marginalised community members who often do not return for results).
- Supported the International Network of People who Use Drugs (INPUD) to raise critical issues relating to PWUD within major global policy-making forums – shaping frameworks and policies that, in turn, shape regional and national responses to HIV. For example it used the UNAIDS Programme Coordinating Board to highlight the inadequate role of the United Nations Office on Drugs and Crime (UNODC) – which led to dialogue with the agency and their increased understanding of the need for the use of proven interventions (harm reduction and opiate substitution therapy (OST)) and action on the rights and involvement of PWUD. INPUD advocated on the specific challenges posed to PWUD by the Global Fund’s New Funding Model and, among other measures, secured the establishment of a Harm Reduction Working Group (co-chaired by INPUD and UNAIDS) to advise the HIV Disease Committee.

Recommendations

See above

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	HUMAN RIGHTS ADVOCACY: / Fulfilment of basic human rights that support an equitable, effective HIV response is achieved for inadequately served populations.
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Output met expectation. Improve organizational capacity and technical expertise within inadequately served populations to reduce policy and regulatory barriers, combat human rights abuses, stigma and discrimination and support access to legal services to meet community needs.

Progress

79% of the grantees addressed this output in Round 1 and 85% in Round 2. A wide range of interventions were covered by networks under this output including: mapping of ISP engagement in national decision-making processes; advocacy implemented to parliamentarians and policy-makers on discriminatory bills and laws for ISPs; media work carried out to raise understanding/ coverage of ISP human rights; communications resources, such as films and case studies, produced on ISP rights; rights-based policies and programmes for ISPs promoted among national/ regional/global institutions

Specific examples reported by grantees against output 3
Grants from the RC-NF:

- enabled AIDS and Rights Alliance for Southern Africa (ARASA) to act as a ‘watchdog’ and fight for the fundamental rights of PLHIV and key populations within a negative political environment in the East and Southern African region. Used RC-NF resources to implement (directly and indirectly – through country partners and programmes) a comprehensive package of initiatives related to human rights advocacy. The work included strategic litigation, such as: in Zambia, supporting partners to advocate against the prosecution of Paul Kasonkomona (an activist for LGBT rights); and, in Botswana, supporting the Botswana Network on Ethics, Law and HIV/AIDS to advocate against the enactment of a Public Health Bill (that would, among other measures, make it compulsory for sexual partners to disclose their HIV status).
- enabled The International Drug Policy Consortium (IDPC) to support its partners to begin to create a more supportive environment for programmes and policies for PWUD and to open doors to dialogue with national, regional and global decision-makers. Examples of national-level results included that: in Thailand, the Office of the Narcotics Control Board called for a meeting with civil society to discuss drug policy and harm reduction; and, in Kenya, over 20 civil society organisations formed a Policy Advocacy Forum to champion the health needs and rights of PWUD.
- enabled Inclusive and Affirming Ministries (IAM) to support its partners to build a more tolerant environment for the LGBTI community and build understanding and capacity among current and future faith leaders in relation to the human rights of sexual minorities in the East and Southern African region – in view of the critical role of faith leaders in promoting and protecting their human rights. Examples of its initiatives include: providing a workshop about ignorance, intolerance and stigma against LGBTI and PLHIV for 70 theological students and lecturers at the Seth Mokitimi Methodist Seminary; providing a workshop on sexual diversity and rights for 180 students from the Anglican Student Federation; and facilitating an open dialogue on sexual orientation and PLHIV for 65 clergy leaders in Namibia, Kenya, Lesotho, Ghana, Zimbabwe and South Africa.

Recommendations
See above. Important that there needs to be a way to reflect high level impact from human rights advocacy but recognise the difficulty of attributing to specific actions of networks.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	RESOURCE ACCOUNTABILITY FOR THE HIV RESPONSE: / Local level responses to HIV have sufficient, strategically targeted investments to deliver results, both through donor government commitments and domestic governments accountability for appropriate resource allocation.
Output number per LF		4	Output Score	A
Risk:		High	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Output met expectation. Building resource accountability for the HIV response means enabling community organizations to play a central part in ensuring that at local level responses to HIV have sufficient, strategically targeted investments to deliver results. This means being able to hold government accountable for commitments and have the capacity to mobilise domestic resources.
Progress

29% of the grantees addressed this output in Round 1 and 54% in Round 2. Significant improvement on Round 1 (it being one of the most difficult outputs to achieve, progress against). Interventions covered by networks under this output included: national/regional/global HIV budget processes engaged in and influenced by ISPs; collaborations implemented with other sectors to develop national systems to monitor budgets related to health and HIV; ISP organisations mobilised to be watchdogs of national expenditure on HIV; ISP organisations trained in the structures and processes of key donor agencies, in particular the Global Fund; Good practice programmes for ISPs documented to assess and promote their cost-effectiveness; Funding mechanisms (such as the New Funding Model of the Global Fund) influenced to ensure appropriate allocation to ISPs.

Specific examples of impact reported by grantees against output 4
Grants from the RC-NF:

provided the Eurasian Harm Reduction Network a springboard for more and better advocacy on
sustainable funding – a theme that has now been adopted as the advocacy focus for EHRN’s Regional Global Fund Project. Used RC-NF resources to launch ‘Harm Reduction Works– Fund It!’ – a regional campaign to increase resources for harm reduction in Eastern Europe and Central Asia and developed a regional online platform to share the campaign’s results and lessons.
- enabled partners of the African Men for Sexual Health and Rights to be better placed to tackle and influence future funding patterns – including within a scenario of reduced external resources and increased pressure for domestic financing. For example, with the Global Fund, members received training in the mechanism’s new priorities and processes – in order to understand when and how to influence the programming and budgeting decisions that affect key populations.
- Enabled the International Community of Women Living with HIV (ICW) to contribute to the development of the Global Fund’s New Funding Model, emphasising priority issues for Women Living with HIV. In Uganda, ICW-East Africa participated in the national budget review process – advocating for increased financing for health, especially to motivate health workers. This included work with the government’s Health Committee to sensitise Members of Parliament to the needs of Women Living with HIV and draw up priorities for funding in the health budget.

Recommendations

It would be helpful if data could be collected in the future on how many Global Fund programmes targeted inadequately served populations and in which countries to assess success and to make the link between the work of the networks addressing this important output and the GF NFM. We would expect that this will be easier to track now that the RC-NF will be receiving additional funding from the Global Fund. In the light of this, the ISC should urgently review the implications of its engagement with the Global Fund to ensure no double funding or duplication.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers for RC-NF are the re-granting via Aids Fonds - the FMA - and their overheads for grant management and evaluation. Overhead percentages are kept at 7%. This is comparable to programmes of similar sizes. This is used by Aids Fond to: manage relationships with grantees, manage donor funds and grant making, coordinate bi-annual ISC meetings, including an annual ‘face to face’ meeting. Aids Fonds attempt to limit flight travel, using teleconferences and bolt-on visits to grantees onto other meetings as well as using Skype interviews with grantees in place of site visits where appropriate. Every second meeting of the ISC is via teleconference.

VfM performance compared to the original VfM proposition in the business case

On reduced transaction/management costs of the FMA compared to direct DFID management/funding processes:

Contracting a competitively tendered FMA to manage a pooled donor fund for global and regional HIV civil society networks to improve the HIV response for inadequately served populations was designed to increase efficiency by developing collaboration and coordination among networks, as well as aiding transparency through joint oversight and governance structures for the Fund.

This arrangement improves economy by reducing transaction costs for both donors and recipients. The RC-NF is fulfilling important aspects of its intended added value, such as being a ‘bridge from donors to ISPs’ and a ‘unique inventory of the demand from civil society’ while cutting management costs and time for DFID. Some aspects (such as a ‘way to compare and encourage quality’) will be achieved over time.

Additional results achieved through leveraging other donor funding and supporting a more diverse range of networks than currently funded through DFID.

The RC-NF has been particularly effective in supporting a more diverse range of networks, and their end beneficiaries. Previously to RC-NF DFID was funding just two consortia focusing on people who use drugs and men who have sex with men. For approximately the same funding per annum in Round 1, 7 grants were awarded to global networks and 17 to regional networks. In Round 2, 8 grants were awarded to global/ regional consortia, 1 to a global network and 5 to regional networks covering the full range of key populations.
Besides the original founding donors, the RC-NF has been less successful so far in attracting new donors except for M.A.C. AIDS and encouragingly, the recent announcement of additional funding from the Global Fund.

As a result there is still a significant funding gap; for example the demand (amount requested) by the eligible applicants was significantly higher – by about 8 times in Round 1 and 5 times in Round 2 – than the resources supplied. In the future, it must significantly step-up its work on resource mobilisation to ensure a predictable flow of funds to achieve sustainability over the long term. Greater clarity on the niche of the Fund will assist this.

Assessment of whether the programme continues to represent value for money

As of 2014, the rationale for the existence of the RC-NF remains sound. This includes that: ISPs continue to be disproportionately affected by HIV and lack access to decision-making; global and regional networks play a unique and critical role in shaping responses to HIV; and funding for HIV as a whole – and the work of regional and global ISP networks in particular – continues to diminish.

There are a number of existing processes and funding channels to support civil society action at the country level. Making maximum use of these – and securing the resources, services and political environment that ISPs need – requires the analysis, expertise and action that regional and global networks are uniquely placed to mobilise and provide. It is understood that the RC-NF’s longer-term impact is not yet possible to fully document or assess. However, greater attention to the existing and emerging ‘policy change achieved’ would significantly help the process of articulating the Fund’s overall worth and its specific value-added.

Quality of financial management

Over the course of the programme Aids Fonds –the FMA - has provided requests for quarterly contributions/tranches on time as specified by the Memorandum of Understanding with detailed statements of expenditure and forecasts for the remaining financial year as requested. Annual Audited Statements have been received for both 2012 and 2013. We are on track to spend the remaining commitment by 31 March 2015 with two further tranches being paid out in December 2014 and March 2015. Feedback from the MTR on financial management of grantees has also been positive. Aids Fonds are considered a ‘safe pair of hands’ and demonstrated rigour in their grant regulations and due diligence procedures.

Spending profile and commitment illustrated in the table below.

Yr	Approved Budget	Committed	Spend	Balance	Forecast Outturn	Outturn Variance
2012	450,000	0	450,000	0	450,000	0
2013	1,775,000	0	1,775,000	0	1,775,000	0
2014	1,775,000	887,500	887,500	0	1,775,000	0
	4,000,000	887,500	3,112,500	0	4,000,000

Date of last narrative financial report	December 2014
Date of last audited annual statement	December 2013

E: RISK (½ page)

Overall risk rating: Medium

Original Risk Description	Original Risk / Rating	Revised Risk 2014
FMA Management model is overly complex and expensive.	Medium	Low: RC-NF has benefitted from Aids Fonds’ extensive and established policies for grant management, including in risk management and due diligence. Aids Fonds’ has also developed a comprehensive policy on conflict of interest. All policies available on RC-NF website.
Focus of the fund contested.	Medium	Medium-high: three-bodied governance and management structure (ISC, PAP and FMA) is widely seen as good practice providing a strong and appropriate backbone to the Fund. But there still remains a tension on overall identity and / purpose. E.g. the extent to which the Fund is intended to be: a ‘donor’; solely for key populations; and a mechanism to fill specific gaps in funding for civil society.
Limited engagement by national governments to prioritise inadequately served populations in the national response. This is a particularly high risk in countries which criminalise particular key populations.	Medium-high	Medium This is one of the key challenges the Fund is designed to address through effective policy dialogue and influence by regional and global networks.
US, BMGF and Norway have all committed US $2 million in 2012 with the intention to secure sufficient funds for 3 years. However this is not guaranteed and a political change could present a risk to this longer-term commitment and thus the sustainability of the Fund. Ongoing financial crisis, changing donor priorities and deprioritisation of HIV could also threaten funding prospects.	Medium	High to ensure sustainability it is of major concern that the RC-NF has not broadened and deepened its donor pool over the long-term. This should be addressed urgently to both maintain (hopefully increase) the commitment of existing donors and get new ones on board – overall, ensuring a healthy and viable Fund to fully achieve its value-added. / Encouragingly, the RC-NF’s additional funding from the Global Fund provides a vital opportunity to support existing grantees and strengthen civil society’s input into Concept Notes for the New Funding Model. It also demonstrates the Fund’s role as a proven channel to reach ISP networks and support country-level responses to HIV.
Difficulty in tracking and measuring results	Medium	Medium Results Framework and Theory of Change are in place but need to be further simplified in order that reporting against key indicators on impact by grantees can be made clearer.
Added 2014 / Fraud and misuse of resources	Medium	Aids Fonds continues to make regular site visits and ensures all grantees have whistle blowing procedures in place. Any suspected or alleged misuse of funds is reported immediately to RC-NF donors and thoroughly investigated by the fund management staff and/or an independent forensic audit team. / All grantees receiving funding continue to be subjected to due diligence to ensure the risk of fraud is low.

Outstanding actions from risk assessment
At the face-to-face meeting in December take forward recommendations from the MTR particularly with regard to those areas we have highlighted in the risk assessment i.e.:

- on clarification of the focus of the fund
- future funding for the RC-NF
- simplified reporting on key indicators and on
- risk of fraud.
F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

In year one there was a slow start up to the programme due to delays in donor funding decisions and subsequent disbursements had impacts on proposals. Round 1 grantees were announced in December 2012 and disbursed during 2013. Round 2 Grants were announced early in 2014 and are being disbursed over 2014/15.
The RC-NF has issued two Requests for Proposals and allocated a total of $ 18,217,092. In Round 1, it provided 24 grants, valued at $ 5,519,016 (for 1 year) to 7 global networks and 17 regional networks. In Round 2, it provided 14 grants, valued at $ 12,698,076 (for 2 years), to 8 global/regional consortia, 1 global network and 4 regional networks. The 8 consortia (a model prioritised in 2013) received 71% of the Round’s funding. In both Rounds, a large proportion of the resources (74% in Round 1, 50% in Round 2) were used for core funding. Also, a notable proportion (some 24%) is used for onward-granting (the provision of small grants to partners).

Performance of partnership

The RC-NF’s three-bodied governance and management structure - International Steering Committee (ISC), Programme Advisory Panel (PAP) and Fund Management Agent (FMA) - is widely seen as good practice. It provides a strong and appropriate backbone to the Fund that benefits from: joint donor/civil society leadership (through the ISC); and the technical expertise of civil society (through the PAP). The complementary roles of the ISC and PAP are articulated in the Governance Charter. However, they have been more challenging in practice – with tension around the PAP’s role in ‘advising’, ‘guiding’ or ‘instructing’ the Fund’s strategy.

The RC-NF has benefitted from Aids Fonds’ as the FMA with its extensive and established policies for grant-management, including in risk management and due diligence. . Aids Fonds’ has also developed a comprehensive policy on conflict of interest and all these policies are available on the RC-NF website. Our relationship with Aids Fonds has been very positive and constructive. Queries and requests for information are always provided promptly whether on financial or general matters.

The RC-NF has laid the foundations for an effective grant-making mechanism. In the future, it must significantly step-up its work on resource mobilisation. It must also continue to build on its communications work - to raise the profile of the RN-CF and ‘sell’ its results.

Asset monitoring and control
N/A no programme assets owned by DFID through this programme.

G: CONDITIONALITY (½ page)

In view of the encouraging progress of the RC-NF evidenced by the external mid-term review and attracting further funding from M.A.C.AIDS and the Global Fund to fight AIDS TB and Malaria DFID increased the contribution to the full £4 million commitment up to 31 March 2015.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

An external Mid Term Review was undertaken between May and July 2014. This aimed to engage relevant stakeholders in assessing the strengths, weaknesses, results and lessons of the Fund to date and to make recommendations for its development and strengthening in the future. The Review was carried out by an independent consultant and used five methods: a survey of grantees (31 responses); in-depth interviews (28 completed); focus group discussions (3 completed); data analysis; and literature review (over 60 resources). The MTR was a ‘360º process’, involving all key
stakeholder groups: civil society networks that are past/present/potential grantees; existing/potential donors; the governance and management bodies (International Steering Committee (ISC),
Program Advisory Panel (PAP) and Fund Management Agent (FMA)); and external stakeholders.

The Mid Term Review was the key document for informing this review in view of the wealth of data and case- studies it incorporated.

Monitoring progress throughout the review period

Regular telephone conferences of the International Steering Committee are held throughout the year and face to face meetings at least once a year. The DFID programme officer for the RC-NF communicates regularly with Aids Fonds on financial reports and forecasting.

This Annual review was completed by Will Niblett, SRO and Sally Chakawhata, Programme Manager for the RC-NF programme in the AIDS and Reproductive Health team in coordination with Aids Fonds – the FMA – and members of the ISC along with reference to this year’s external Mid- Term Review. All scoring, using this evidence, was undertaken by DFID AIDS and Reproductive Health team.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process