Type of Review: Annual Review

Project Title: Global SME Finance Initiative

Date started:	28 February 2012 Date review undertaken: April/May 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
DFID is contributing £75 million over 7 years (2012 -2019) to the Global SME (Small and Medium Enterprise) Finance Initiative set up by the International Finance Corporation (IFC) through two Trust Fund Administrative Arrangements. The existing Business Case is approved for a DFID contribution of up to £100 million. We have provision to bid for an additional £25 million in the next Spending Review Period (SRP) if the mid-term review of the programme in end-March 2015 indicates that the Initiative is delivering strong results and value for money. DFID’s support is as anchor donor to the Initiative. / Of the £75m, £60 million will come from the Private Sector Department’s (PSD) aid framework over the current Spending Review Period (SRP 2011-15). The remaining £15 million will be provided through co-funding from DFID Country Offices. / DFID Mozambique had initially agreed to provide up to £5m and DFID Nigeria £10m. DFID Mozambique has subsequently halved its projected contribution and DFID Nigeria intends to disburse only £8 million during the current SRP. Therefore, we could have an overall funding shortage of £4.5 million if DFID were to disburse all of its £75 million contribution in this SRP as per the current plan. We are in discussion with DFID Pakistan and DFID Ethiopia who may be interested to provide co-funding. We are also exploring the possibility of additional funding from PSD’s aid framework (2011-15), which will raise PSD’s contribution from original £60 million to £64.5 million.

What are the expected results?
The SME Initiative, when fully funded, is forecast to deliver the following results: / Over 700,000 additional SME loan accounts over the baseline (with at least 25% of these loans for women headed enterprises) / 2.8 million new jobs. / Of these results those attributable to DFID funding of £75m are: / At least 200,000 additional SME loan accounts over the baseline (with at least 25% of these loans for women headed enterprises). / One million new jobs generated by those SMEs. / At least £600 million of DFI and commercial funding catalysed through the programme. / At least £5 billion of additional lending from financial institutions to SMEs over the programme period. / At least 25% of the headline results above will come from fragile and conflict affected countries. / Additional results are being finalised by IFC in consultation with DFID at the time of this review. Seven new target countries have been added to the original list of 16 countries supported by DFID funding under the Initiative.

What is the context in which UK support is provided?
SMEs can drive economic development by providing jobs and income, expanding the middle class, and broadening the tax base to support public expenditure on health, education and other social services in low-income countries (LICs). SMEs can also play an important role in building a dynamic and flourishing private sector in LICs over a period of time. / However, access to finance remains a priority constraint on SME growth. In LICs, 43% of small enterprises and 38% of medium-sized enterprises report access to finance as a major obstacle to their operations and growth. / A 2010 study by IFC and McKinsey to assess and measure the credit gap of micro, small and medium enterprises (MSMEs) revealed that over 300 million formal and informal businesses in the developing world suffer from credit constraints and/or have no access to credit. Of the 25 to 30 million formal SMEs, 70% have insufficient or no access to finance. There is an estimated $700-850 million financing gap for SMEs in emerging economies, with the biggest shortfall in Africa, where SMEs require 300% more funding than is currently available in the market. / SME financing is constrained because of high transaction costs and high perceived risk. There are viable opportunities that banks and financial institutions are not able to pursue with their available capital, standard investment instruments and risk tolerances. Key risks for financial institutions include the credit quality of SMEs, lack of data on underlying SME risks in the context of frontier markets or innovative products, and macroeconomic instability in fragile states. / The G-20 called for greater support to small businesses to harness their contribution to wealth creation and employment generation. In recognition of the vital role played by SMEs in economic development; scaling up SME financing in poorer countries through a global programme, is a key deliverable of the DFID Business Plan 2011-15 and the Private Sector Department’s (PSD) Operational Plan 2011-15. / The Global SME Finance Initiative implemented by the IFC brings together the combined resources of donors, Development Finance Institutions (DFIs), commercial banks and financial institutions to catalyse significant funding for bridging the global SME financing gap. / The Initiative combines funding from donors and Development Finance Institutions (DFIs) to share risk with, and make investment in, commercial banks and local financial institutions –“Partner Financial Institutions (PFIs)” in order to increase their risk appetite for scaling up lending to SMEs. / The Global SME Finance Initiative has three components; / 1. Risk sharing and investment component: combines donor grants and DFI investments to provide; (i) risk sharing to cover of up to 50% the commercial risk in the SME lending portfolio of PFIs and (ii) direct funding lines to PFIs especially in markets with liquidity constraints. This is designed to enhance risk-taking by PFIs and provide capital relief by requiring lower risk weighting for SME lending in bank balance sheets. Grant financing combined with DFI investments is expected to reduce the pricing and conditionality of products offered to PFIs. / It is intended that IFC and other DFIs will invest a combined US$ 600 million in the initial phase of SME finance projects targeting 35 PFIs. DFID is providing £40 million (US$ 60 million) in grant funding as the Initiative’s anchor donor. When fully funded the Initiative aims to mobilise $1.8 billion - $1.4 billion of funding from DFI and $0.4 billion from donors to support an expansion of its geographic focus. / 2. Advisory Services component: a complimentary Technical Assistance pool to (i) support PFIs to establish and strengthen skills, systems, products and processes (e.g. credit risk appraisal and management) to scale up their SME financing portfolio and; (ii) support development and improvement in financial market infrastructure (e.g. credit bureaus and asset registries) to improve information on the creditworthiness of SMEs which can in turn reduce risks and transaction costs associated with SME lending. DFID will provide £32 million (US$ 51 million) grant funds to this technical assistance pool. / 3. Financing for G20 SME Finance challenge winners: provides £3 million of funding to three of the fourteen G-20 SME Finance Challenge Winners to scale up technologies to alleviate systemic constraints faced by SMEs. Additional funding will be provided to support the development and operations of the SME Finance Forum, housed at IFC. The Forum will be a virtual platform for knowledge sharing on SME finance to identify and promote best practices across countries and institutions and establish baselines.

## Section A: Detailed Output Scoring

Output 1: Risk sharing mechanism (s) to catalyse investments from DFIs in the selected PFIs for scaling up SME financing on commercially sustainable basis in the 15 target countries, including in the high risk environments of fragile/conflict affected countries.
Output 1 score and performance description: / This output relates specifically to the Investment Services element of this Initiative. The Initiative completed its first year of operations in March 2013. The review assesses that progress against this output has been slower over the review period than the expectation as reflected in the milestone targets for year 4 (March 2015) of the programme. Recommended score: B.
Output Indicators: / 1a: Cumulative number of Partner Financial Institutions (PFIs) supported with risk sharing and funding mechanisms. Target: 15 PFIs by end-March 2015. / 1b: Volume of additional funding mobilized for SMEs through PFIs under the investment facility component (concessional funding). Target: £800 million by end-March 2015. / 1c: Investment leveraged from DFIs and PFIs as a multiple of the size of risk-sharing funding from DFID. Target: £323 million by end- March 2015. / 1d: Share of fragile countries and frontier markets in (a) and (b). Target: £200 million by end-March 2015. / Progress against expected results: / Progress against this output has been slower than expected, and implementation needs to accelerate over the next 18 months to ensure that targets set for the first milestone in March 2015 are delivered. / The Initiative has supported one PFI; Access Bank in Nigeria, with a risk-sharing facility (RSF) of US$ 22 million and a credit line of US$ 50 million. Another five investment projects are awaiting approval from the IFC Board. These projects are: (1) US$ 5 million loan to Advans in Democratic Republic of Congo, (2) US$ 55 million loan to KCB for supporting SMEs in the healthcare sector (3) US$ 60 million RSF and loan to the Diamond Trust Bank in Kenya, (4) US$ 5 million RSF and loan to the Diamond Trust Bank in Uganda, and (5) US$ 5 million RSF and loan to the Diamond Trust Bank in Tanzania. / Three additional projects were at the appraisal stage at the time of this review: (1) a $40 million RSF and loan for SIB Cote D’Ivoire, (2) a $5 million RSF for BICIGUI Guinea and (3) a $40 million loan for CRDB Tanzania. All eight projects will involve DFID support through blended finance. Once approved by the IFC Board, this will take the number of PFIs supported with DFID funding under the Initiative to nine against the target of 15 by end-March 2015. / Targets for the investment projects in the appraisal stage were not determined at the time of the annual review. The remaining investment projects already approved or going to be approved are forecast by IFC to deliver additional commercial lending of £470 million to 22,000 new SME loan accounts, used as a proxy for outreach to SMEs, by end-March 2015 against the log frame target of £800 million. The review assesses the loan mobilisation target of £800 million by end-March 2015 to be at potential risk. / Progress in mobilising funding from other Development Finance Institutions (DFIs) has been slower than expected. To date, IFC has mobilised investments worth US$ 300 million or £188 million. This includes US$ 200 million investment from IFC and another US$ 100 million from the European Investment Bank, although it is not clear at this stage how much of the investment approved by EIB will fund projects in DFID approved countries leveraging our concessional funding. KfW has agreed in principle to invest US$ 75 million in projects in Tanzania and Kenya supported through the Initiative. KfW has also indicated that it is willing to consider additional investments on a project-by-project basis in future. If all of EIB’s approved investment is channelled to DFID-approved countries and the two projects identified by KfW for investments are approved, total investment mobilised from DFIs will stand at US$ 375 million or £235 million, compared to a target of £323 million by end-March 2015. / The slow progress in mobilising and committing investment capital is attributable to the longer-than-anticipated time for programme inception. The first 6-8 months since the approval of the Initiative was devoted to inception during which the IFC established relevant procedures, processes and structures to manage investments. The IFC Board also introduced a new strategy on blended finance shortly after DFID’s approval of the Initiative imposing more stringent norms on the use of donor-funded subsidy for investment projects. IFC’s operational team has taken time to adjust to these changes. / The application of more stringent standards in use of donor-funded subsidy has prompted IFC to take more risks with its own capital. Several projects which had previously been earmarked by IFC for concessional funding will now be funded through mainstream IFC financing. This meets the Initiative’s long-term objective that IFC and other DFIs take more risk onto their own balance sheet and wherever possible do deals on a commercial basis. / The IFC’s Independent Blended Finance Committee has been effective in managing possible conflict of interest in IFC managing the donor-funded concessional funds in the investment component of the Initiative. It is recognised that unnecessary under-pricing of donor-funded concessional investment projects could distort pricing of and possible undermine IFC’s non-concessional investments in many markets. / The original aim was to structure the investment component as a SICAV – or open-ended collective investment vehicle - registered in Luxembourg with a tiered investment structure. IFC in consultation with DFID determined that such a structure would not be feasible because of regulatory and other liability issues. An in-house structure with project level approvals by investors was assessed as more appropriate and effective. / There are multiple benefits to the current structure. First, the IFC does not need to outsource management, and is able to leverage its extensive network of banks to build deal flow and identify the leading PFIs to engage. Second, the IFC is able to be more targeted in the use of concessional funding, resulting in greater leverage. Third the IFC has more flexibility to incorporate new funders as they are identified rather than through rigid funding rounds. Fourth, it grants IFC greater flexibility in managing different pools of funds for different regions, and the varying usage requirements of different funders. / Recommendations: / The programme’s trajectory of progress over next six months is good and on an improving trend. IFC has developed a strong pipeline of investment projects identifying 11 more PFIs. / The terms of the Initiative need further adjustment to reflect and address the implications of IFC’s new strategy on Blended Finance. The geographical focus should be broadened further to address the needs of more Fragile and Conflict Affected Countries (FCAS). The Initiative could have a stronger focus in certain sectors considered too risky by DFIs and commercials banks to finance and increase its focus on gender and sustainable energy. / Following a request from IFC, DFID has recently agreed to expand the geographical coverage of the SME Initiative to include seven additional FCAS countries. These include five countries in sub-Saharan Africa (Burundi, Chad, Cote d’Ivoire, Guinea, Guinea-Bissau,) and two in other regions (Haiti and Myanmar). / IFC has reiterated its commitment to deliver the set of high level results of 200,000 SMEs, £5 billion additional commercial lending and one million jobs in the original list of countries. In addition, IFC believes it will be able to reach an additional 5-10,000 SMEs in the seven additional countries, delivering greater value for DFID money. We will develop results for loan and job indicators, and increase headline indicator targets commensurately with the expansion of the geographic focus. IFC has also agreed that funding channelled to the seven additional countries will not exceed 15% of the total DFID funds allocated to the Initiative. / Impact Weighting (%): 50% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: Capacity of partner banks and Non-Banking Financial Institutions (NBFIs) strengthened through well-targeted technical assistance to partner financial institutions in risk management, product development, and improvement in of business processes, and support for development of financial market infrastructure such as credit bureau and collateral registry in the identified.

Output 2 score and performance description: / Overall, progress against this output moderately fell short of expectation. / Recommended score: B
Output Indicators. / 2.1a: Cumulative number of PFIs and financial infrastructure projects covered with advisory services and activities. Target: 20 PFIs by end-March 2015. / 2.1b: Cumulative number of PFIs and financial infrastructure projects supported with advisory services in the fragile countries and frontier markets. Target: 5 PFIs by end-March 2015. . / 2.2a: Volume of SME loans generated by PFIs / financial infrastructure covered by advisory services plus IFC's non-concessional financing. Target: £1,700 million by end-March 2015. / 2.3a: Percentage of SME loans per loan officer. Target: to be confirmed. / 2.3b: Processing time per small and medium size loan. Target: to be confirmed. / 2.4a: Number of Credit Bureaus (CBs) and Collateral Registries (CRs) created or significantly strengthened. Target: to be confirmed. / 2.4b; Number of banks and financial institutions participating in the CBs. Target: To be confirmed. / 2.4c: Number of SMEs reached by the CRs. Target: to be confirmed. / 2.4d: Number of SME credit history information sold/supplied by CBs to banks and NBFIs. Target: to be confirmed. / 2.5: Number of PFIs provided with technical support for strengthening capacity to identify, screen and support SMEs that either contribute to low carbon and climate resilient outcomes or have neutral impact. Target: 4 PFIs by end-March 2015. / Progress against expected results: / IFC has identified and committed Advisory Services (AS) support to 17 projects at a total cost of nearly £11 million, 48% of which is funded by DFID and the remaining 52% met by other donors and clients in line with the conditions set by DFID. Projects include 13 PFIs in Pakistan, Nepal, Bangladesh, Nigeria, Sierra Leone, and Ghana. / The Initiative is also supporting 4 financial market infrastructure development projects including development of collateral registries in Liberia, Bangladesh and India and the development of a credit bureau and collateral registry in Nigeria. All 17 projects, with the exception of a Collateral Registry, in India and UT Bank Ghana, qualify as fragile countries and frontier markets. / On average, AS projects take more than a year to undertake diagnostics and implement system improvements before yielding results. Most of the AS projects are at various stages of development and will take at least another six months to realise results. Of the 17 AS projects, only two have been in implementation long enough to demonstrate results. According to latest IFC data, the two projects have helped deliver £157 million of commercial lending to almost 3,000 SMEs in Pakistan and Nigeria. / The outlook for progress against headline indicators for this output is positive. IFC has developed a strong pipeline of AS projects including 13 additional PFIs in Liberia, Rwanda, Tanzania, Kenya and DRC. One project with EcoBank is being developed on a regional basis to cover 17 countries in Africa. / The 17 projects already committed are forecast to help unblock over £2.1 billion of commercial lending to over 200,000 SMEs by end- March 2015. Incorporating expected loans from pipeline, the Initiative appears well on track to deliver the target for additional loan volumes by the mid-term review. However, the target for the number of additional loans to women-headed SMEs may be at risk by the time of this milestone. / Recommendations: / Targets for several of the output indicators were not determined at the project documentation stage. PFIs were not identified and sufficient data was not available to determine the targets. Now that IFC has identified several PFIs for advisory as well investment support, DFID will develop targets for the indicators in consultation with IFC as a priority over the next three months. / Impact Weighting (%): 45% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Development of technology based approaches and solutions to drive SME financing and development in the identified developing countries.
Output 3 score and performance description: Overall, progress against this output has been good, with some indicators exceeding the expectation. / Recommended score: A. / Output Indicators: / 3.1a: Number of banks and NBFIs adopting and scaling up the use of psychometric credit scoring tools. Target: 6 banks and NBFIs by end-March 2015. / 3.1b: Number of SME loan applications processed and approved using psychometric tools. Target: to be confirmed / 3.2a: Number of SMEs in fragile countries successful in winning large procurement contracts. Target: 250 SMEs by end-March 2015. / 3.2b: Volume of financing SMEs is provided in support of bid and delivery for large contracts. Target: £9 million by end-March 2015. / 3.2c: Total value of procurement contracts SMEs supported to bid and deliver. Target: £44 million by end-March 2015. / 3.2d: Value of operating LOCs guaranteed jointly by PDT and partner local banks. Target: £9 million by end-March 2015. / 3.2e: Number of SMEs provided with credit guarantee. Target: 75 SMEs by end-March 2015. / 3.2f: Number of SMEs reached through credit counselling/facilitation: Target: 175 SMEs by end- March 2015. / 3.2g: Number of women-owned SMEs reached through contracts facilitated. Target: 25 women headed SMEs by end-March 2015. / 3.3a: Number of SMEs accessing the technology driven platform to reach investors and mentors. Target: 20,000 SMEs by end-March 2015. / 3.3b: Volume of investments in SMEs made possible through the technology-driven platform. Target: £14 million by end-March 2015. / Progress against expected results: / Good progress has been made on this output with some targets set for March 2015 already achieved. IFC has signed grant agreements with the three G-20 SME Finance Challenge winners selected by DFID to support under the Initiative; Entrepreneur Finance Lab (EFL), Bid Networks and Peace Dividend Trust (now known as Building Markets). / The EFL’s psychometric tool has been piloted by three banks, including HBL in Pakistan, BBVA Bancomer in Mexico and Banco G&T in Guatemala. EFL is considering partnership with other banks, including Grameen Bank and BRAC, to pilot the psychometric tool in Bangladesh. The three pilots have rolled out nearly 300 loans worth over £3 million. These institutions are able to generate a psychometric credit score in less than 30 minutes against the target of under five hours. / So far 45,451 SMEs have accessed the Bid Network’s technology driven platform to reach investors and mentors. The volume of investments in SMEs made possible through the technology-driven platform was valued at close to £9 million at the time of this review. Although not part of the originally agreed milestones, the IFC also expect that 100,000 SMEs will access on-line mentoring support and over £14 million investment will be mobilised through this platform by end-March 2015.
Grant support to the Building Markets has taken time to implement. Results are yet to be reported. / Recommendations: / Under Output Indicator 3.1 suitable Years 1 & 2 milestones should be developed as well as targets relating to the number of SME loan applications processed and approved using the EFL psychometric tool. We shall work closely with IFC to develop these and update the log frame accordingly. / Impact Weighting (%): 5% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

## Section B: Results and Value for Money.
1. Progress and results

1.1 Has the logframe been updated since last review? No / This is the first Annual Review of the Initiative. The log frame will be updated in consultation with IFC to determine milestone targets that have not yet been confirmed for several output indicators. / 1.2 Overall Output Score and Description: / The overall composite score across the three programme outputs is assessed at B, indicating the programme outputs moderately fell short of expectation. / 1.3 Direct feedback from beneficiaries / This is a desk based review of various reports and material provided by programme implementers IFC. The 2nd donor Steering Group meeting held in Washington in February 2013 also contributed content to the review. The review incorporates feedback from DFID Country Offices covered by the Initiative.
Summary of overall progress / The overall progress in the first year of implementation of the Initiative has been slower than expected, against (i) headline results expected to be delivered by end-March 2015, including provision of finance to 100,000 SMEs, generation of additional £2.5 billion of SME lending and creation of 500,000 jobs and; (ii) the constricted disbursement schedule, which aims to deploy all of DFID’s initial contribution of £75 million by end-March 2015. / The logical framework sets targets for result indicators, including headline indicators, at three different milestones FY 2015, 2017 and 2019. On a pro-rated basis, the Initiative should have delivered roughly a third of the targets in the first year in order that it is able to meet the first Milestone in three years up to end-March 2015. However, two of the three headline results are well short of one-third of their respective Milestone 1 targets while no meaningful information about the jobs targets has been generated (see below). / The Initiative had a slower-than-expected start in mobilising and committing investment capital with only two investment projects reaching implementation in the first year, and only one DFI investment commitment secured of US$200 million from IFC itself. Slow progress in commitment of investment capital was largely attributable to the change in the IFC’s new Blended Finance strategy and operational guidelines in May-July last year which introduced more stringent norms for use of subsidy in investment projects. Although this has slowed down the pace of deal generation under the Initiative, the new norms have had a positive impact in enhancing IFC’s risk appetite. Some of the relatively less risky projects developed through the Initiative will now be funded through the IFC’s mainstream project financing. This meets DFID’s long-term objective to encourage IFC and other DFIs to take more risks on their balance sheet. / The deal generation on the AS side has also been slower-than-expected. IFC is now exploring how best to cut back on some of the process without compromising on the quality of due diligence and diagnostic work. Time taken in mobilising matching contributions of DFID grants to AS projects may also have caused delay to the generation of AS projects. Securing matching contributions was not included in the original design but was introduced as a condition of SoS approval of the project. / Following adjustments to the terms of the Initiative, including the expansion of the geographical focus of the country to more ODA eligible countries in Africa and other region agreed by DFID in May 2013, the programme outlook is good and on an improving trend. / As of April 2013, 27 AS and IS projects totalling approximately US$ 302 million are at different stages of development. In addition, the pipeline contains an equal number of projects that the IFC is confident will materialise over the next six months. Momentum is also gathering on DFI investments. The European Investment Bank has obtained approval from its board to invest US$100 million in the Initiative. KfW has provided in principle agreement to invest US$ 75 million in two investment projects in Kenya and Tanzania, and has expressed interest in future investments on a project-by-project basis. / A full list of AS and IS Projects currently contributing to the Initiative is at Annex 1.
1.5 Key challenges / Advisory Services: The primary challenge is ensuring that key cost drivers, particularly consultant costs, are managed and contained within a certain range, while also accounting for variables that affect such costs, including the market and political context of individual projects, degree of specialization, availability of consultants and local security issues, given the strong focus of the Initiative on fragile and conflict affected states. / Investment Services: Forecasting exact drawdown timelines for the pipeline of investment projects is complex. Commitment timeframes vary for each project and are subject to client negotiations, local market volatility, and PFI planning. In some cases projects may be expedited or delayed significantly due to unpredictable changes in local markets or clients’ needs to balance their own cash flows. This issue is being addressed by amending the definition of project commitment under the Facility from “Board Approval” to “Mandate Letter” signing stage. DFID has approved this adjustment. / Results Attribution: Attribution of results at both programme and output level is challenging. Project-level results are assessed using IFC’s corporate attribution guidelines used for the IFC’s Development Goals (IDGs), which acknowledge that attribution of results to advisory services, concessional and non-concessional investments is difficult to disaggregate in projects with multiple components.
1.6 Annual Outcome Assessment / The expected outcome for this programme is to scale up SME financing on a commercially sustainable basis in target countries by catalysing investments from DFIs, IFIs and the private sector to support the development of: / Enabling financial market infrastructure; / Adoption of technology to address wider systemic constraints including effective information systems. / Progress in the first year has lagged against outcome level indicators, reflecting challenges of early stage implementation of a 7-year programme. It remains too early to judge whether or not the full outcome expectations will be achieved. / Progress towards achievement of several output indicators is on track. Two of the three headline results are at relatively low risk and on track to be delivered by the time of the mid-term review. The 27 AS and IS projects under development and approaching implementation are forecast to generate £2.6 billion of lending to over 220,000 SMEs by end-March 2015. Close to 85% of SMEs and over 55% of additional loans are expected to come from fragile and conflict affected and frontier markets, according to the IFC’s April 2013 supplementary progress report. / At least a quarter of the headline results, are expected to benefit women-headed businesses and women employees. According to latest available data, progress against gender targets has been laggard. The number of loans going to women-headed businesses is expected to reach 2,800 by end-March 2015. Gender specific data is currently being tracked only in Mozambique. Similar data for loans in other AS and IS projects will require improvements in the management information systems of the PFIs to allow them to track and report data periodically. A comprehensive M&E system is being developed to help the PFIs collect information for gender-related targets. / Data for the job indicator is in the process of being collected. Given that there is a long gestation period before higher loans to SMEs under the Initiative translate in to higher output and jobs, it is unlikely that we will have any meaningful job data before the next Annual Review. IFC is exploring three ways of data collection to provide information for this indicator: (i) country surveys and deep dives with SME clients; (ii) integration of job measurement methodology in the World Bank’s Enterprise Survey (ES), and (iii) tracking employment through selected PFIs.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: N / The programme is off-track in terms of financial disbursements against original forecasts. DFID is committed to disbursing all of the funds in the current Spending Review Period (SRP), which finishes in March 2015. Of the £75m currently committed to the Initiative, incorporating £35m for Advisory Services and £40m for Investment Services, DFID has disbursed £25m in total as of May 2013. / Although disbursements for Advisory Services have more or less met our forecasts, those for Investment Services have fallen significantly short of expectation. In 2012/13, no funding was released by DFID for Investment Service activities. It has taken longer than anticipated for IFC to identify relevant investment opportunities that meet the criteria for the SME Initiative, including investment standards required by IFC. / The IFC’s latest report does indicate a relatively strong pipeline of projects, with a good trajectory over the next two years. However, it remains uncertain, especially given the long lead in time to develop projects under Investment Services, whether disbursals can be brought back on track. / DFID remains in constant communication with IFC to assess progress of spend against target. To date, IFC has remained confident that they can meet disbursement targets following adjustments to the terms of the Initiative recently agreed with DFID. / DFID’s contribution of £75 million comprises £60 million from PSD with the remaining £15 million contributed by Country Offices in Nigeria (£10 million) and Mozambique (£5 million). We are anticipating a potential shortfall of £4.5 million in the contribution expected from the Country Offices. We are exploring options for meeting this shortfall from PSD budget while DFID Ethiopia and DFID Pakistan have expressed interest in the Initiative. / 2.2 Key cost drivers / The review did not identify any new cost drivers from those outlined in the business case. Cost drivers differ between Advisory and Investment Services: / Advisory Services: IFC's delivery model for Advisory Services is hands-on and expert-based, relying on external and internal consultants, as well as a mix of in-house IFC experts at global and local level. The AS projects with PFIs require consultants and/or consulting firms with expertise in relevant fields of SME banking advisory, including credit risk management, information technology, product development, marketing, customer management and strategy. IFC staff plays an important role in the selection process of consultants evaluating technical proposals, expertise, experience and financial proposals to achieve highest value for money through procurement. Project oversight is managed by IFC staff. AS projects involving the development of market infrastructure require a high level of technical expertise, which is in limited supply. In these projects, IFC uses a combination of local consultants and in-house IFC experts in order to achieve greater value for money. IFC also works with local consultants with deeper expertise in specific areas for discreet pieces of work. Project components are provided by external providers and typically paid for directly by the client. / Investment Services: IFC's delivery model for the Investment Services component consists of regional IFC staff working with the Initiative team to develop process and supervise investments on behalf of IFC, donors and IFI investors. This model has the following key cost drivers: (i) pipeline development and supervision, (ii) cost of establishing and administering the investment vehicle and trust funds, (iii) governance and approval mechanisms, and (iv) reporting and M&E. Across all of these elements scale is important since management and administration can be leveraged across a larger pool of funds. Operational costs will gradually decline with increased utilisation of funds and mobilisation of additional funds from other donors, and DFIs. / 2.3 Is the project on-track against original timescale: N / Some slippage of activities has occurred as a result of aforementioned lagged operationalization of Investment Service activities. We are working closely with IFC to ensure they develop a robust portfolio of projects. The planned geographical expansion of target countries discussed in Section A in the ‘recommendations’ section under Output Indicator 1 will help to provide greater opportunities to support SMEs in additional countries.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The evidence base that supported the identification and design of the interventions in 2012 remains broadly unchanged. Evidence continues to support the of the Initiative’s central theory of change that small firms are an important channel for job creation and poverty reduction in developing countries. / A 2011 World Bank paper based on cross-country databases concludes that small firms (firms with less than 100 employees) and mature small firms (small firms older than 10 years) have the largest share in job creation. Moreover small firms, in particular those less than 10 years old, have higher job creation rates than large firms. / However, the paper also acknowledges the risk of potential adverse consequences on productivity and growth, if the focus is on smaller SMEs. Evidence indicates that small firms are not good for productivity. Indefinite support to SMEs can involve possible trade-offs with productivity and growth. We recognise the risk of inflating the number of SMEs in an economy, given the lack of evidence on what is an optimal distribution of firms by size in any given economy to assess adverse growth effects. The governance arrangement rightly gives IFC the flexibility to relax the definition of SMEs based on country level diagnostics to include larger SMEs, as evidence suggests larger firms (100-250 employees) have better productivity. / Evidence on the current risk appetite of DFIs and their lending strategies and willingness to target frontier markets is embedded in their operational strategies and is well known to us through DFID’s shareholder positions. The DFIs develop their strategy on return expectations. The initial problems encountered by the Initiative in catalysing investments from DFIs, even on the basis of donor funded subsidy, highlight the risk averseness of some DFIs. / Evidence on the leverage effect of the risk capital on actual SME lending is based in part on IFC’s current portfolio analysis and experience although there is a limit to the evidence base for lending into some of the riskier markets. We will attempt to redress these gaps in the evidence base through the programme’s M&E framework. / Risk sharing products are a critical tool for expanding access to finance in markets where (1) banks are moving into new markets/conditions where the risks are not totally understood and (2) banks are sufficiently liquid and do not require credit lines. Not all banks require risk-sharing facilities, but for a certain segment risk-sharing can provide the critical catalyst to support a bank’s move into a new market. Experience from IFC’s programmes indicate that technical assistance/advisory services to banks without investment/risk sharing are much less likely to have the desired impact on the target market; the two pieces are highly complementary. / The evidence shows that combining finance with advisory services, including staff training, establishing good lending practices and loan portfolio risk management systems, with investment yields better results than stand-alone financing of financial intermediaries. The IFC’s Independent Evaluation Group (IEG) evaluated the operating results and performance of a subgroup of 36 SME financial institutions (FI) and concluded that the SME FIs that received advisory services from IFC had a development outcome success rate of 76%, compared with only 55% for SME FIs that did not receive any advisory services. Based on the IEG study, advisory services are considered one of six major factors driving the development outcome success rate of the IFC’s SME financing projects. DFIs are uniquely positioned to go beyond lending and add significant value by developing projects that combine investment and advisory components. / 3.2 Where an evaluation is planned what progress has been made? / Limited progress has been made on the planned evaluation of this programme with focus instead placed on early stage implementation. A procurement process has been initiated to hire an independent consultancy firm to develop and implement the programme’s M&E framework. The Initiative’s M&E activities are being designed to address knowledge gaps and answer questions essential to the programme’s objectives and learning agenda. / The strategy is to design M&E for a selected sample of projects with the highest degree of rigour, possible within the boundaries of commercial institutions operating in competitive markets and reasonable budgets. Dissemination activities will seek to share lessons learned from the M&E work, but will also investigate larger questions that may be relevant to the broader financial sector development community.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The Initiative continues to be assessed as medium-high risk but with potential for achieving high impact. At the operational level, three key risks have been identified: / (i) Potential conflict of interest between the IFC’s investment portfolio and specific deliverables under the Initiative. / (ii) Inability to secure other donor and DFI investment for the Initiative. / (iii) Lack of stakeholder commitment and buy-in particularly among PFIs. / The IFC’s Independent Blended Finance Committee has been effective in managing the potential conflict of interest. Significant contributions of up to 50% from PFIs in meeting cost of the AS projects has helped ensure strong commitment from the PFIs to achieving programme targets. After initial slow progress, the IFC mobilised nearly 75% of the total investment that that the Initiative expected to deliver from DFID’s concessional funding of £40 million.
Risk of funds not being used as intended / The risk is regarded as relatively low. DFID funding is subject to IFC’s strict policies and procedures for managing programmes and disbursements to third parties. IFC have robust due diligence procedures and anti-corruption policies. The IFC is required to inform us immediately to discuss relevant actions if it is identified that DFID funds are not being used appropriately or for intended purposes. / 4.4 Climate and Environment Risk / The review did not identify any new risk. SME financing and development is a core business line for the IFC. The IFC’s standard environmental guidance therefore applies to interventions under the Initiative. DFID’s Multilateral Aid Review (MAR) in 2011 scored IFC’s performance in meeting UK objectives on climate change and environmental sustainability as “satisfactory”. Climate change was not covered in the recent mini-MAR review of IFC, but will be covered in the 2015 review. One of the IFC’s seven development goals that IFC began to test in 2011 relates to working towards reducing greenhouse gas emissions. IFC will adopt this goal for full-fledged implementation from FY 2014. Once adopted for full implementation, the goal will be useful as a strategic management tool, and will cover a significant share of IFC’s business including interventions under the Initiative. / The review supports the original decision against setting climate-focussed targets which could place the programme in competition with other facilities that IFC is implementing to achieve climate change objectives. Setting climate change objectives for this Initiative within the broader context of DFID’s overall corporate strategy for its shareholding in the IFC is appropriate. The Initiative has set a target that at least 20% of the PFIs supported will be provided with technical support for strengthening capacity to identify, screen and support SMEs that either contribute to low carbon and climate resilient outcomes or have a neutral impact.

5. Value for Money
5.1 Performance on VfM measures / The Initiative is designed to support financial institutions through both advisory and investment services to achieve maximum impact. / As of March 2013, DFID’s funding of £7.6 million helped catalyse £178 million of investments from PFIs under the investment component, supporting a leverage ratio of 1:23 and demonstrating strong value for money. The Initiative is still in its early stages and IFC cannot yet assess the impact of Initiative funds at project level. However, analyses of IFC's outreach data for client PFIs from other projects shows that for every $1 million invested in each project with both an investment and advisory component, SME outreach is about 460 while PFI on-lending to SMEs averages $25 million. For every $1 million invested in projects with only an investment component SME outreach is lower at 200, while SME on-lending averages approximately $18 million[1]. / 5.2 Commercial Improvement and Value for Money / DFID funds are being leveraged significantly more than originally anticipated in the investment component as a result of the IFC’s focus on utilizing “minimal subsidy” in IFC projects. The original projection was that DFID funds would be leveraged 8.5 times over the full term of the programme. However, that leverage ratio is now forecast at 14 times, which means the IFC can do more projects per pound spent and achieve greater impact. Although IFI funds have been slower than expected, EIB has agreed to support the SME Initiative with US$100m. DFID has received a letter from EIB confirming this and the MOU with IFC will be formalised shortly. / 5.3 Role of project partners / The main partner is the IFC as implementer of the Initiative. IFC provides management oversight for all components through a coordinated approach across Investment and Advisory Services, to include: (i) recruiting for the required positions (ii) raising additional funding from IFIs and donors to leverage DFID funds; (iii) building a pipeline with regional IS and AS staff; (iv) communication and knowledge sharing, and (v) monitoring and evaluation. / The Global SME Finance Initiative is recognized as a signature program within IFC, with commensurate resources dedicated to achieving its objectives. At global level, AS and IS Co-Leads have been assigned to program oversight. Staff and consultants have been allocated to support the coordination, implementation, and M&E activities across the advisory and investment components of the program, including a full time Program Coordinator and M&E Specialist. / At regional AS level, the Global SME Finance Initiative has been operationalised as the principal initiative within the SME Banking Program. Regional managers, staff, and consultants have a deep understanding of the Initiative. Periodic visits will be undertaken by DFID advisors to the regions to ensure the Initiative continues to be prioritised. The process to assign two additional dedicated staff members for business development, administration and fundraising has been initiated in the Investment Facility to build capacity to manage the enlarged pipeline. / The Program Coordination Unit within IFC is responsible for coordination across the AS and IS components of the Initiative. Separate teams will manage the Advisory and the Investment programs. In both cases, overall program management will be managed by central teams in Washington, D.C., with project implementation generally led by staff in the field. On the Investment side, dedicated staff assigned to the Global Team will help build the pipeline in the initial years of the Initiative and will in some cases take the lead on projects in lieu of the Regional counterparts. / 5.4 Does the project still represent Value for Money : Y / The programme presents good value for money. DFID funding has leveraged almost double the amount of additional finance. Greater progress is expected in future years as project development and implementation gains traction. / 5.5 If not, what action will you take? / Not applicable.
[1] Based on analysis of IFC Outreach Data, a database of results achieved by IFC supported financial intermediaries with their MSME clients.

6. Conditionality
6.1 Update on specific conditions / The business case stated that if DFID judges the programme is seriously off-track or under threat, the programme (or component parts) may be suspended or terminated in line with DFID’s standard procedures. / DFID has set benchmarks to assess performance. If two or more outcome level indicators fall short of targets by more than 30% at the mid-term evaluation point, the programme will be deemed to be underperforming and not achieving VFM. DFID, in consultation with the Steering Committee, will reserve the right to modify the programme course, strategies and partnerships or cease funding if resolutions cannot be found. Standard IFC processes/conditions will also be applied for monitoring individual programme components. / Performance benchmarks have also been set for the investment component. At no point will IFC be able to draw down from DFID risk capital of more than 1/8.5th of the total investment funds they are able to mobilise providing strong incentives for IFC to mobilise additional investment from other investors. This benchmark was applied in May 2013, when DFID delayed the release of its second funding tranche for investment services after the IFC failed to meet the target for additional investments.

7. Conclusions and actions
The Initiative will aim to work with at least 35 PFIs. The 35 PFIs will be selected in the first 2-3 years of programme implementation, and are therefore not known at this stage. Baselines for target indicators will be developed incrementally as PFIs are identified and incorporated. / The recent expansion of the Initiative’s geographic footprint and the amendment of conditions regarding the point at which IFC funds are regarded as ‘committed’ are expected to support accelerated implementation and boost results. Revised results will be finalised with IFC in the next year or review. / The review has identified the following priorities for the IFC during next review period: / Determination of milestone targets for all output and impact indicators (by September 2013). / Further improvement in the data monitoring and reporting system for timely and better quality data on results the Initiative is expected to deliver, especially at the Output and Outcome level. / Detailed assessment of the potential risks to the delivery of the headline results by the time of the mid-term review in 2015. Options and contingencies for mitigating those risks will also be identified. / Better and more accurate financial forecasts, including risks to disbursement of initial DFID contribution of £75 million in full by the end of March 2015. / Development of a robust pipeline of projects with a specific focus in frontier markets. / Mobilisation of investments from DFIs to meet the overall target of £325 million by the time of the next review or before. / Strengthen the Initiative’s gender focus. / Better and more frequent coordination with DFID Offices in countries covered by the Initiative. / Early discussion on principles for deciding the future destination of returnable components of the DFID funds.

8. Review Process
This is a desk based review of various reports and material provided by IFC who manage this initiative. The 2nd donor Steering Group meeting held in Washington in February 2013 also contributed content for this review. We have shared this review with country offices, including DFID Mozambique and DFID Nigeria, which are contributing funding to the programme. DFID has also shared a draft of this review with IFC to confirm the accuracy of its content. / Review material included: / IFC-produced “SME Initiative Targets and Results Update” Report dated March 2013 (EDRM: 4012224) and update of May 2013 (EDRM: 3992152). / IFC-produced paper “SME Finance Initiative Information for DFID Annual Review – Advisory and Investment Services – January 2013” (EDRM: 4012224). / IFC-produced “Global SME Finance Initiative – Inception report – September 2012” (EDRM: 3664804). / Submission & exchanges with IFC regarding the geographical expansion of conflict countries and the timing of when activities are regarded as ‘committed’ (EDRM: 4012137). / IFC Presentation and minutes from the 2nd Donor Steering Committee Meeting – February 2013 (EDRM: 3928512). / PSD Business case (EDRM: 3349064) / Logical Framework (updated by IFC to reflect achievements) (EDRM: 3992152)

ANNEX 1