Annual Review – post April 2018

Title: Transforming Energy Access for Households and Improved Livelihoods (TEA)
Programme Value £ (full life): £69,650,000		Review Date: 22/03/2019
Programme Code: 204867	Start Date: 23/03/2016	End Date: 31/01/2022

Summary of Programme Performance
Year	2016/17	2017/18	2018/19	2019/20	2020/21	2021/22
Programme Score	A	A	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	LINK
DevTracker Link to Log frame:	LINK

A. Summary and Overview

Description of programme

DFID will provide up to £69.65[1] million between 2016 and 2022 via the TEA programme to support early stage testing and scale up of innovative technologies and business models that will accelerate access to affordable, clean energy services for poor households and enterprises, especially in Africa. This research and innovation programme will deliver new technologies and robust answers to the critical barriers hampering systemic change and scaling up clean energy access, working with Southern researchers and entrepreneurs to drive locally-relevant innovation and delivery. This is a critical response to the challenges of scaling up energy access to serve the poor and will play a key part in DFID’s contribution to supporting the innovation, partnerships and expertise needed to achieve Global Goal 7 - to ensure access to affordable, reliable, sustainable and modern energy for all. The six components of TEA are as follows:
[1] A £30m and time extension to 2024 for the TEA programme was approved on 5/3/19, however given the timing this annual review only considers the original programme value and scope.
1. £15m - Stimulating Technology Innovation, led by Innovate UK’s Energy Catalyst. Through annual open calls, this supports the development of low carbon technologies and business models which meet the energy trilemma of affordability, reliability and low carbon, and target developing country energy needs.
2. £30m - Accelerating Enterprise-led Innovation in Technology Business Models (TIME), led by the Shell Foundation. Through hands-on co-creation, incubation and grants and repayable grants, TIME supports energy innovations at household, business and off-grid utility scale via action research, market enabling actions, and creation of new financial mechanisms.
3. £10m - Clean Energy Partnerships (CEP) seek to address barriers across a sub-sector, beyond the abilities of a single entrepreneur or researcher. It is managed via the TEA Research Programme Delivery Consortium (RPDC) and involves 8 different sub-sector partnerships targeting a range of finance, industry voice, last-mile delivery, sector cost-base and other challenges.
4. £5m - Developing Local Skills and Expertise (SED), included a fast-start research project with the Low Carbon Energy for Development Network (LCEDN), and after the scoping phase the RPDC has developed an academic TEA Learning Partnership (TEA-LP) as well as a separate Off-Grid Talent Initiative (OGTI) focussing on bringing young African graduates into energy access businesses and supporting mid-management human development.
5. £4.5m - Bio-energy for Sustainable local energy services and Energy Access in Africa (BSEAA), led by the RPDC following on from an earlier scoping project (201878). BSEAA has been further developed into two separate project strands; an Academic Research Project looking to expand on previous studies and create industry relevant tools, and a further Technology Innovation Programme which has been delivered through the Energy Catalyst. These projects will support cost reduction and performance improvement of bioenergy technologies within Sub-Saharan Africa.
6. £5.15m - Research Programme Delivery Consortium - Co-ordination, Communication, Monitoring and Evaluation. Including the £2.7m contract with the RPDC to help manage DFID’s interests in TEA, to develop the allocation of the remainder of the Partnerships and Skills budgets, and play a linking role across the other TEA components and undertake overarching programme management, reporting and evaluation support. The remaining is as yet unallocated (although delivery support has been scoped out) but expected to cover independent review and contingency, including potential VAT).
Summary supporting narrative for the overall score in this review

Performance via the MOU-based partnerships with Innovate UK and the Shell Foundation has been strong. While the content of the work on the contract-based relationship with the RPDC has generally been strong, that portion of the work has seen substantial delays around updating the contract between the design and implementation phases (June to October 2018) and more recently lack of clarity around the VAT implications of the programme has stalled signature of the sub-agreements on the CEP and SED projects. However, overall momentum in the programme continues and of the £69.5m DFID has committed there are already co-funding commitments of at least £55m across the programme which reached 105,000 people in 2018-19, and is developing 141 new technologies and business models which, when scaled-up, have the potential to unlock energy access for many more. Constituent scoring leading to the overall score is summarised below:

1. Stimulating Technology Innovation (A+): 200 unique organisations receive part of the 92 DFID co-funded projects and have been working in 48 countries involving 44 international partners. Energy Catalyst Round 6 opened in August and closed in November 2018 attracting a strong response of 154 applications with a total value of £116m. With £40.2m worth of projects scoring 70% or above this allowed the remaining available TEA funding of £4.5m to be committed to 5 early, 6 mid and 1 late stage projects across sectors including cold chain, solar, hydro, and energy storage. Given the volume of projects scoring over 70% in the evaluation and recent agreement of GCRF to align £36m their funding with DFID via Energy Catalyst round 7 and 8, a scale-up of Energy Catalyst has been agreed.
2. TIME/Shell Foundation (A+): Over the past year TIME has continued to deliver substantially ahead of targets in most areas, including the launch of nine new applications and business models investigating a range of energy enabling services including financing facilities for specific high impact groups (smallholder farms, off-grid utilities and women) as well a blockchain based carbon offsetting mechanism, a clean cooking bond and an off-grid talent support and recruitment service. Cumulatively this has resulted in an improvement of over 1.7m lives and offset over 155k tonnes of CO2. Appointment of a jointly-funded liaison person between DFID and SF has enabled improved co-ordination between other DFID departments and country offices and the SF portfolio of innovators, as well as country accelerators and financing facilities.
3. Clean Energy Partnerships (CEP) (B): Following the 12-month scoping, consultation and design period, six new priority TEA partnerships were identified and selected in June 2018, adding to the two original Fast Start partnerships with Acumen and Energise Africa. The new partnership designs are of high quality and potential, however a series of contract-related delays, first with the RPDC contract uplift, then in the RPDC sub-contracts relating to new DFID Terms and Conditions, and then finally due to VAT uncertainty, has held back progress. Some of the partnerships have been able to make progress, and in particular the Powering Opportunities Partnership has already attracted in excess of 300 applications for £40m of support against a budget of less than £1m - and additional funds have been allocated in the scale-up, while the potential for scale-up of the other partnerships will be assessed later. The Fast Start Partnerships, Acumen PEII and Energise Africa, have continued to make strong progress under the respective Accountable Grants. Acumen have reached $19.2 of their $20m fundraising target, releasing a flagship report on Accelerating Energy Access: The Role of Patient Capital (accessible here: http://acumen.org/wp-content/uploads/Accelerating-Access-Role-of-Patient-Capital-Report.pdf), and investing in a further 4 businesses, while Energise Africa has now raised £7.5m from UK retail investors enabling 275,000 people to access energy in 10 African countries via 10 energy enterprise borrowers. Energise Africa was scaled-up by £1.47m under a separate business case as part of the Prime Minister’s visit to Africa in summer 2018, Minister of State Baldwin visited the organisation in Oxford in November, and it is contributing to the Secretary of State’s National Conversation on ethical investment and savings.
4. Developing Local Skills and Expertise (SED) (B): The scoping study was also successfully completed with delivery of the scoping report and two high quality business cases for the TEA Learning Partnership (TEA LP) and the Off-Grid Talent Initiative (OGTI) which were approved on time in June 2018. Design of the OGTI call has progressed and an RfP for delivery was launched in February with the LP requests due to be released by the end of financial year. The LCEDN Fast Start partnership has seen quite significant delays due to ill-health in the team at Loughbough University, and final deliverables have been received with a 9-month delay.
5. Bio-energy (BSEAA) (A): The BSEAA Academic Research Project tender process was launched in October 2018 with contracting expected to take place end of April 2019. Initial challenges gaining responses led to a 1-month extension of the expression of interest stage and resulted in a reasonable 4 applications. Two EOIs have now moved to full proposal preparation and the winner will be awarded by end of March 2019. The Technology Innovation competition was also launched as part of Energy Catalyst Round 6 and provisional awards agreed of £2.5m plus £95k of EPSRC co-funding and £1m of private investment giving a portfolio value of £3.6m. Awards have been made to six companies covering a range of technologies (AD, gasification, pyrolysis) with four projects in Kenya and one in Mozambique.
6. RPDC Co-ordination, Communication, Monitoring and Evaluation (A): The RPDC completed the TEA Scoping Report (August 2018 against a target of June) including the communications strategy, M&E framework, and Research-into-Use strategy. Full implementation of these was delayed until October due to contracting delays, but is now progressing with regular monthly reporting, a webpage set up for the programme and substantial action organising the ministerial Transforming Energy Access: Innovations towards SDG7 event on 7th March 2019. Significant work has gone into contracting and due diligence process for the ~29 sub-contracts to be delivered as well as engaging with potential co-funders for the TEA programme.
Recommendations for the year ahead

Specific recommendations for each of the 6 components are listed in the respective sub-sections below as well as in their Section B Detailed Output. Overarching actions for the TEA programme are as follows:
- Scale-up of Energy Catalyst contribution to fund high quality round 6 projects which could not be supported from the available budget, while also continuing to support rounds 7 and 8 at a lower level to maintain alignment with GCRF Funding. Ensure that round 6 grant contracts are concluded in a timely way, and that agreed levels of reporting to DFID and incubation support to the grantees are provided.
- Monitor the performance of the TIME portfolio and SF backloaded financial commitments, informing a possible scale-up decision on the partnership in 2020. Scale-up now would not be appropriate with 2 years of mainly SF match-funding still be to be invested, and with the DFID Agriculture Research Team recently also expanding the DFID-Shell Foundation partnership into energy and agriculture technologies with a £15m contribution.
- For both CEP and SED the priority must be finalisation of contracts for all new partnerships and acceleration into full implementation including successful launch of respective calls. While the high potential of the new selected partnerships is clear, any decision on which partnerhips to scale-up further in the future will have to wait until more evidence of traction and success can be demonstrated. For Energise Africa the priority will be to define the end terms and suitable governance of DFID’s revolving investment in the platform.
- Finalise and set up or drop Value-Added M&E Offers – VAT (and resulting budget) uncertainties have led to push-back in announcing potential supporting facilities for the projects. Recent agreement on a way forward involving paying VAT and reclaiming under VAT code 74 should be pursued so that delivery partners can benefit from the cross-cutting support planned on gender, research excellence and beneficiary feedback.
## B: DETAILED OUTPUT SCORING

Output Title	Stimulating technology innovation by UK enterprises through Innovate UK Energy Catalyst
Output number per TEA LF		1	Output Score	A+
Risk:		Minor	Impact weighting (%):	20%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicators	Milestone for this review	Progress
1.1) Number of awards made for promising innovative UK-led solutions that have international application and 1.1.2) number of projects with international partners, 1.1.3) total number of partners supported	1.1.1) 21 / 1.1.2) No target / 1.1.3) No target	Substantially Exceeded / - 92 (86 excluding BSEAA) / - 36 / - 200 / The original expected number of projects has been substantially exceeded due to early match funding from BEIS and Innovate in round 4 and 5. Projects have been working in 48 countries, with 36 of them involving 44 international partners. There are 200 unique organisations that receive part of the 92 DFID co-funded projects.
1.2) Total number of Patents: 1.2.1) Submitted, 1.2.2) Granted	1.2.1) No target / 1.2.2) No target	Additional Objective / 1.2.1 - 49 / 1.2.2 - 22 / 49 patent applications out of 76 projects within the DFID funded portfolio show a strong emphasis on generating IP.
1.3) Number of published academic peer-reviewed articles	1.3) No target	Additional objective / - 69 / This indicates that there is significant amount of new ideas being generated. Also demonstrates the active involvement by the academic community.

The original TEA funding unlocked the ability of Energy Catalyst to fund projects aimed at the needs in sub Saharan-Africa and South Asia, and for Innovate UK to fund international partners for the first time. Of the 92 projects funded up until Round 6 (announced in March 2019), 36 projects have involved international partners and survey respondents have reported that because of winning or undertaking their project they had been working with or in 48 different countries around the world. This result shows that projects are forging international partnerships and helping to address the energy access needs of overseas communities. It is encouraging that 49 patents have been submitted and 22 have been granted. In addition, 13 recipients received prizes or recognition for their projects from third parties. Fifty-three respondents achieved media coverage via a variety of channels such as presentations, blogs, publications, websites and news pieces to share their project delivery experiences. In total, 365 media pieces were generated. In total, 37 academic peer-reviewed journal articles have been published as a result of applying for, winning or undertaking a project. In all 200 unique organisations have been part of the 92 projects that have been funded by DFID.
With the conclusion of Innovate UK and BEIS funding to Energy Catalyst after Round 6, DFID and EPSRC have been the only funders of the Round 6 which was launched in August with a total funding available of £10m including £2m from EPSRC. This allowed the call to be dedicated to Sub-Saharan Africa and South Asia, and involved an enhanced engagement and facilitation effort in terms of webinars and outreach to support partnership creation. The RPDC played an active role working with Innovate UK on the setup and framing of the Round 6 call, as well as in the selection process applying the DFID criteria on development relevance, and gender and social inclusion. Round 6 can be considered a success attracting 154 applications, of which 117 were eligible requesting £63.5m, of which 58 scored above 70% representing £28.8m of funding request against the DFID and EPSRC budget of £10m. The supported projects from the TEA Energy Catalyst budget (the supported Bioenergy projects are reported under output 5 BSEAA) are illustrated below:

The total £15m TEA funding to Energy Catalyst is now fully committed with the £4.5m now committed in round 6, matching £750k in EPSRC R6 funding, and £1.5m in private investment. Of the total grant amount £778k will be spent via international partners. More than £20m worth of projects scoring over 70% in the assessment went unfunded due to the limitations on the amount of budget available for this call.
Further important progress this year was in terms of the agreement from the Global Challenges Research Fund to join DFID and EPSRC in funding via Energy Catalyst in round 7 and 8 over the next two years with a contribution of £36m in research ODA support.

Lessons identified this year, and recommendations for the year ahead linked to this output

- While there is good collaboration within the individual projects, there is less work to date on enabling sharing between projects and communicating externally. Innovate UK and the RPDC should co-operate to ensure that as much value and learnings from the projects are shared as possible.
- The large number of unfunded projects from Round 6 offers an immediate opportunity to scale-up DFID’s support and ambition on energy access and generate more value from the cost of running the Round 6 call. If a TEA scale-up is approved funding these unfunded “Blue Zone” projects should be considered.
- GCRF joining Energy Catalyst Rounds 7 and 8 offers an important opportunity for scale-up and co-ordination of HMG support to energy innovation targeting developing country markets. In order to maintain the DFID involvement and influence, it is recommended that DFID maintain a contribution in those rounds alongside GCRF with any available scale-up funding.
- The increasing volume of ODA being channelled through Innovate UK will also create challenges and Innovate UK should set out clearly their approach to ensuring the support is communicated and available to proponents from all countries, ensure strong outreach to African partners is increased still further in future rounds, and that an efficient and effective level of assurance and safeguarding is put in place regarding funding of international partners

Output Title	Shell Foundation partnership: Transforming Inclusive Energy markets (TIME)
Output number per TEA LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone for this Review	Progress
2.1 Cumulative number of new applications and business models tested and proven	10	Substantially Exceeded - 42 / With 9 new applications and business models added this year, the total now exceeds the end of programme target of 40 with 2 years to run.
2.2 Cumulative number of energy policies influenced	1	On track - 1 / SF supported the Rwandan government’s national off-grid energy strategy in 2016. The energy market accelerators in Rwanda, Ethiopia and Uganda as well as GOGLA are active on national and regional policy issues.
2.3 Cumulative number of financial innovations	3	Substantially Exceeded - 13 / With 5 new financial innovations in the reporting year, the end of programme target of 12 has been exceeded.
2.4 Cumulative number of new corporate partnerships	1	On track - 1 / TIME’s partnership with Vodafone continues and further opportunities are actively being pursued.
2.5 Cumulative Number of consolidated reports on aggregate findings from implementing partners published	25	Exceeded - 31 / 11 new reports have been published in the reporting year.

The TIME partnership between DFID and Shell Foundation (SF) has performed strongly in this period with all outputs having been met or exceeded and several end-of-project targets have already been met. Building on lesson learning from the previous two years, TIME’s focus for 2018 remained on deepening access to energy as well as finance in current markets, expanding into new markets through replication models, and co-creating value chain intermediaries to test and prove the assumption that efficiency gains are possible. Nine new applications and business models were funded by the TIME partnership this year:
Amiran	Amiran, an established agricultural distributor in Kenya, are piloting an asset finance unit for smallholder farmers to purchase productive use agricultural assets from various manufacturers. De-risking asset finance for Amiran will create a route to market for a variety of Energy for Business manufacturers.
BBOXX	BBOXX are trialling a new, potentially market-shaping mechanism for carbon offsetting via blockchain technology. Carbon financing represents a way to generate additional revenue for off-grid solar companies, allowing them to reduce costs and offer a more affordable service to low income consumers.
CrossBoundary Energy Access / (CBEA)	CBEA are working on a financing vehicle for Off Grid Utilities (OGU) that seeks to address the key market barriers of cost and access to capital. Establishing a holding company will enable savings from the aggregation of small projects, boosting the unit economics of Off-grid Utililitiess and improving their delivery and investability.
Energy Company of the Future (ECOF)	ECOF is a pilot utility company deploying first in Nigeria that seeks to build a larger scale business model that can integrate on and off-grid solutions, address key barriers in the energy sector, create a customer centric proposition and attract large scale commercial capital from corporates and strategic investors.
Energy Private Developers (EPD)	Supporting the ecosystem for achieving universal access to energy through market acceleration, EPD is a Rwandan not-for-profit trade association that addresses local market barriers for enterprises in the off-grid energy market. Th
Frontier Finance Solutions (FFS)	FFS are developing an innovative clean cooking Development Impact Bond. Seeking to measure and monetise the multiple impacts on SDGs related to health, gender equality, access to energy and climate change, the Impact bond will provide a results -based blended finance vehicle for cookstove companies and donors.
Green Light Planet (GLP)	GLP are exploring sustainable models for commercial financial institutions to provide financing for modern energy solutions for women, starting with a project in Nigeria. GLP seek to create innovative distribution partnerships and a direct sales network to reach low-income women and businesses.
Nayo Tropical Technology (NTT)	NTT are a Nigerian enterprise that is a mini-grid developer and operator/utility with a great pipeline of sites and the technical know-how to deploy and manage these at scale. TIME is supporting NTT to develop into a leading player in the Nigerian industry.
Shortlist Professionals	A key barrier holding back growth of the off-grid energy sector is the attraction and retention of talent to companies involved. Building on earlier work supported by TIME, Shortlist Professionals are developing new talent screening and training software, applying data science techniques to improve recruitment results.

Shell Foundation has acted on multiple recommendations highlighted in the last annual review including working on the portfolio balance, improving visibility and communication of lessons learned, and recruiting a partnership manager to strengthen coordination with DFID and the RPDC. They have also produced a final report for the earlier NEADM project allowing that to be closed. On the recommendation around exits, it is encouraging that Shell Foundation has earmarked 15 partners for graduation, while recognising the challenges in accelerating this given access to capital constraints and other commercialisation barriers. The Governance arrangements for the partnership have also been updated to reflect the £15m of funding which will be provided by the DFID Agriculture Research Team through a new Catalysing Agriculture by Scaling Energy Ecosystems (CASEE) partnership with Shell Foundation.

Lessons identified this year, and recommendations for the year ahead linked to this output
- Building communications and lessons sharing – good progress has been made on building awareness however opportunities exist for Shell Foundation and the RPDC to coordinate external communications more closely to help amplify relevant communications/outputs.
- Energy for Business strategy – with the addition of the CASEE funding, SF will update the TIME Energy for Business strategy to evolve away from Agricultural-processing technologies to focus on income generating appliances and circular economy. It will be important to co-ordinate via the Efficiency for Access Coalition.
- TEA programme links – a key area for the RPDC and Shell Foundation to review and track progress on over the coming year is making connections and forming collaborations where appropriate with work on other TEA components to ensure the programme adds up to more than the sum of its parts.
- Improved results tracking and reporting – Shell Foundation has been adding direct end-user consumer research and market insights to the KPIs already being collected but work remains to ensure that the impacts and results across the TIME portfolio are captured and available for quarterly and annual reporting. A strong results story will be essential to feed into any scale-up decision on the partnership in 2020, as the partnership enters its final year.

Output Title	Clean Energy Partnerships
Output number per LF		3	Output Score	B
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone for this review	Progress
3.21: Peer to Peer Solar (now Energise Africa)	3.2.1) £3.58m / 3.2.2) 2,341	On Track / 3.2.1) £2.23m / 3.2.2) 961 / Ahead on funds raised, but number of borrowers lagging
3.2.1) Volume of debt financing raised (including matched funding) to finance SHS businesses operating in Africa / 3.2.2) Number of UK retail investors engaged to support energy access in Africa by making small scale investments in SHS businesses
3.3: Acumen Pioneer Energy Investment Initiative (PEII)	3.3.1) 17 / 3.3.2) 14	On Track / 3.3.1) 15 / 3.3.2) 67 / Slightly behind on firms invested due to E Africa regulations, ahead on dissemination
3.3.1) Number of active companies in PEII portfolio. / 3.3.2) Number of public facing activities that Acumen or PEII companies participate in to discuss and disseminate learning from research and learning activities.

3.4: Powering Opportunities Partnership (POP)	3.4.1) 2 / 3.4.2) 7	Off Track / 3.4.1) 1 / 3.4.2) 0 / Call launch delayed by contracting, and long EoI period
3.4.1) Number of competition windows designed, developed and approved by RPDC/DfID, with competition documents produced / 3.4.2) Number of funded projects under the competition
3.5: Crowd Power Phase 2 (CP2)	3.5.1) 0 / 3.5.2) 0	Exceeded / 3.5.1) 2 / 3.5.2) 0 / First campaigns supported in Myanmar and on CrowdCube.
3.5.1) Equity campaigns supported in at least two jurisdictions which facilitate crowdfunded equity investment in energy access ventures / 3.5.2) At least two new credit guarantee mechanism established available to multiple platforms
3.6: Mini-grid coordination, research and cost reduction (MGCR)	3.6.1) 6 / 3.6.2) 3 / 3.6.3) 3	Off Track / 3.6.1) 0 / 3.6.2) 2 / 3.6.3) 3 / Contracting slow with Cross Boundary, limited traction on SoM Report to date.
3.6.1) Cost reduction prototypes delivered with mini-grid developers: # workshops with mini-grid developers / 3.6.2) State of Mini-Grids Market report: Number of meeting, calls etc. held with interested stakeholders to inform the scope and design of the report / 3.6.3) Number of MGF group meetings convened
3.7: Global Distributors Collective (GDC)	3.7.1) 0 / 3.7.2) 0	On Track / 3.7.1) 0 / 3.7.2) 0 / Contracting proceeding and GDC launched
3.7.1) # of Last Mile Distributors reporting time or cost-savings as a result of the GDC. / 3.7.2) LMDs benefit from improved margins as a result of centralised purchasing and standardised contracts: # of products purchased through centralised purchasing platform
3.8: Strengthening National Renewable Energy Associations (PowerUp)	3.8.1) 0 / 3.8.2) 0	Off Track / 3.7.1) 0 / 3.7.2) 0 / Contracting delayed
3.8.1) # of trainings delivered through network to NREA board and team members / 3.8.1) # of peer to peer learning opportunities created

Taking first the Fast Start initiatives which were launched in advance of the appointment of the RPDC:

Energise Africa (£2m) – On Track. has had a strong year continuing to raise crowdfunded working capital loans for energy access innovators. To date Energise Africa has raised £7.57m for 10 borrowers in the following countries: Senegal, Cameroon, Kenya, Tanzania, Uganda, Mali, Burkina Faso, Mozambique, Democratic Republic of Congo, and Rwanda. More challenging has been reaching the target number of retail investors and young people in the UK, although that work continues via a range of communications strategies and continual development of the platform, offer and risk/reward ratio. Energise Africa was scaled-up by £1.47m under a separate business case as part of the Prime Ministers visit to Africa in summer 2018, it has raised additional $100k of co-funding from the Danish-funded P4G partnership (in addition to Virgin Unite and Good Energies), Minister of State Baldwin visited Energise Africa in Oxford in November, and it is contributing learnings to the Secretary of State’s National Conversation on ethical investment.
The Acumen-led Pioneer Energy Investment Initiative (PEII) (£1m, increased to £2m in June 18) – On Track. is a multi-donor partnership working to explore the role of early stage patient equity in scaling energy access enterprises. PEII is currently on track to achieve milestones and has now secured funding totalling $19.2m of the target $20m. Closing transactions has taken longer than expected, due to new Fair Competition Commission (FCC) regulations in East Africa requiring investors to file with the FCC and receive approval. This approval process means additional transaction costs and delays of up to 4 months. PEII has overachieved the reporting and dissemination target with 34 activities and two published reports on energy impact and accessing capital in the energy sector including Accelerating Energy Access: the Role of Patient Capital launched in 2018 as a key output of the first phase of DFID support, and already informing considerations around the gap between grant provision and development capital instruments in DFID and beyond. TEA agreed to a second phase of support as part of the CEP implementation in Q2 2018 taking our investment up to £2m out of the total $20m.
Alongside the doubling of the PEII support under TEA, a further 6 partnerships were developed, assessed and refined after an extensive Scoping and competitive design phase concluding in June 2018. The brief rationale and progress on these partnerships since then is as follows:
Powering Opportunities Partnership (POP) (£1.35m) – Off-Track. POP will seek to demonstrate how the off-grid clean energy sector can stimulate local jobs and local value addition in Sub-Saharan Africa, via a challenge fund mechanism with two initial windows. The overall the rate of preparation and launching of calls has been slower than expected. POP launched its first call on Productive End-Uses in December, receiving more than 300 Expressions of Interest by the close in February with more than £40m in grant funding requests. The next call on Value Addition and Employment Creation competition materials are being produced for launch associated with the TEA Forum on 7th March. A partnership is also planned with USAID via CLASP on eWaste with the final call under the existing funding to be launched shortly.
Crowd Power 2 (CP2) (£1m) – Exceeded. CP2 will employ a range of interventions to encourage debt and equity crowd-financing of energy access ventures by testing new approaches including strategies to engage diaspora and young people, as well as addressing exchange issues and guarantees. CP2 activities began in September 2018 and it has already supported a £30k campaign on StartSomeGood by Myanmar-based start-up Mee Panyar to train rural electricians to work on solar mini-girds, and a second live campaign on CrowdCube, supporting Renovagen – a company developing, manufacturing and deploying portable solar power systems for disaster response operations. Both campaigns exceeded their initial fundraising goal.
Mini-grid coordination, research and cost reduction partnership (MGCR) (£1.5m) – Off-Track. The multicomponent MGCR Partnership is designed to address bottlenecks inhibiting mini-grid market expansion, by aligning relevant groupings into a collaborative partnership more effectively, addressing development costs, market intelligence and coordination needs. Contracting has taken longer than expected and it is behind on KPIs, however project pipeline development has been initiated and prototype testing is already planned for 4 projects in FY2019/20, with more to follow so component is expected to get back on track once contracts are signed. New prototypes with research objectives, planned for deployment in FY2019/20 period include: Wi-Fi bundled with mini-grid electricity (do they consume more and how much to help understand revenue model); metering (lowest cost options and behaviour change elements); grid densification; and reduced grid energy tariff subsidy. With regards to the Mini-Grid Partnership (MGP) component intended to provide overall sector coordination activity with the UN Foundation operating as secretariat, the State of the Mini-Grids Market Report consultation has been ongoing, however with the report funding decision milestone approaching (March 2019 no co-funders for the SotM report have committed, and the RPDC and the UN Foundation will mobilise and Plan B should no commitment be made by March 2019. The Mini-grid Funders Group component is currently on track to achieve set milestones, as next quarterly meeting is presently being planned for March 2019. The Carbon Trust has been working one-to-one with MGF members to improve their entries into the Funders Database; and new version of which was presented at the MGF face-face meeting on 12th March in Abidjan.
Global Distributors Collective (GDC) (£1.12m) – On track. The GDC is a collective of 130 last mile distributor (LMD) members, working in 28 countries in Sub-Saharan Africa and South Asia, and will test several ways of enhancing LMD business performance, building capacity, facilitating partnerships to unlock economies of scale for LMD companies to better serve bottom of pyramid consumers. Contracting has progressed well, the contract was signed and the GDC launched in late 2018. The GDC also successfully secured additional funding in August 2018 from P4G, as well as being awarded €131,000 by Inclusive Business Action Network (IBAN) to implement a complementary work stream on Training for Last Mile Distributors. During the reporting period the initial feasibility study and recommendations on next steps were presented to the RPDC and approved on the 4th of January 2019.
Strengthening Renewable Energy Associations (PowerUp) (£1m) – Off-Track. PowerUp seeks to promote off-grid solar markets, by strengthening the capabilities, networks and services of 12 national renewable energy associations (NREAs) (with the programme being open to more joiners), currently representing more than 150 sector players. Contracting has been slower than expected with GOGLA, however, preparation activities have started for all of the three project components. GOGLA have been identifying the national renewable energy associations (NREA) to work with; and have developed and undertaken a survey to identify the exact capacity and priorities needed. GOGLA are is also developing a handbook on how to run effective NREA, fundraising, governance etc. which will be used to inform training. GOGLA are presently working to finalise the review committee and developing the materials for the first call for projects targeted for early in FY2019/20. Finally, GOGLA has engaged with one NREA to ascertain their willingness and ability to participate as the first NREA who will undertake national data collection.

Lessons identified this year, and recommendations for the year ahead linked to this output

- The work to develop the Clean Energy Partnerships design and approvals was delivered in a timely way generating a high-quality portfolio, but contracting delays are putting momentum at risk. See further comments under output 5 relating to the RPDC as a delivery route.
- Crowd Power 2 (CP2): Energy 4 Impact should reconstitute the Advisory Committee for CP2 implementation, and revisit the CP1 campaign eligibility criteria to align with TEA objectives and provide clear criteria to inform campaign award decisions made by Energy 4 Impact.
- Mini-grid coordination, research and cost reduction partnership (MGCR): At the State of the Market report funding milestone (March 2019) a clear decision must be made regarding continued fund raising or the establishment of a plan B.
- The very strong interest in the Powering Opportunities Partnership calls implies that larger budgets could be deployed immediately into the Productive End-Use Call currently open, and for the upcoming Value Addition and Employment Creation Call. These should be included in scale-up work supported. Scale-up decisions on the other Clean Energy Partnerships, and consideration of any new partnerships, should be delayed until later in 2019 to allow for more evidence of success in the field to be generated from the existing cohort.

Output Title	Developing Local Skills and Expertise
Output number per LF		4	Output Score	B
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone for this review	Progress
4.1 TEA Learning Partnership / 4.1.1) Business plan developed for each course or degree / 4.1.2) workshops undertaken with participants from partner universities and external stakeholders (2.1)	4.1.1) 0 / 4.1.2) 0	Off-Track / 4.1.1) 0 / 4.1.2) 0 / Delayed by contracting issues, although preparation of the call documents is almost complete and the first annual capacity building workshop has been provisionally scheduled for July 2019
4.2 Off-Grid Talent Initiative (OGTI) / 4.2.1) Recruitment of mid-management level trainees for each intake (total target is 300 beneficiaries) / 4.2.2) Recruitment and placements of interns with host companies for each intake (total target is 300 beneficiaries)	4.2.1) 0 / 4.2.2) 0	Off-Track / 4.2.1) 0 / 4.2.2) 0 / Delayed by contracting issues, although preparation of the call documents is almost complete with the first draft approved with comments by DFID.
4.3 - Academic, skills and expertise relevant partnerships (LCEDN) / 4.3.1) Academic, skills and expertise partnerships contracted to support UK/South or South/South training initiatives / 4.3.2) Publish LCEDN Briefing Papers / 4.3.3) LCEDN Placements participants	4.3.1) 3 / 4.3.2) 5 / 4.3.3) 4	Achieved / 4.3.1) 3 / 4.3.2) 5 / 4.3.3) 4 / The work was delayed by around 9 months compared with expectations, however has now been completed – although the papers are still in various stages of publication.

The final Skills and Expertise Scoping report was delivered on time in June 2018 after an extensive consultation and analysis effort, and this included the designs which were approved for the TEA Learning Partnership and the Off-Grid Talent Initiative (OGTI) focussing on tertiary education and in-work young graduate and mid-management respectively.

The TEA Learning Partnership (£1.6m) aims to develop the longer-term pipeline of skills to meet the needs of the off-grid energy (OGE) industry in Africa. This involves a programme of support to universities with the design, implementation and promotion of appropriate curricula for application in the OGE sector. This will contribute to better equipped graduates that will become available to the OGE industry primarily, but also to the public sector, NGOs and other relevant stakeholders in the broader sector. Since approval of the project in June 2018, as part of the final SED Scoping Report, University of Cape Town have been developing the request for proposals aimed at identifying leading African universities to implement the initiative with. It was expected that the TEA LP call would have gone out by this point, however issues with both the RDPC and TEA LP contracts have held this up. The LP RfP are due to be released by the end of March 2019.

The Off-Grid Talent Initiative (OGTI) (£2.1m) aims to accelerate the market growth of the off-grid energy sector in sub-Saharan Africa by supporting the development of high quality local talent. It aims to competitively procure an existing service provider that has experience in training and talent development activities in Africa, to deliver a programme of support targeted at the off-grid energy sector. This expected to include a) a graduate work placement programme increasing the pool of young talent with professional skills available to the off-grid energy sector, and reduce the internal costs to companies of developing young people, b) a mid-management talent support programme – this aims to improve the quality of mid-management talent and thereby enable more productive workforces, and c) Provide inputs into the TEA Academic Support Programme – this aims to facilitate linkages and input from industry into universities’ curriculum redevelopment processes. It was expected that the RFP would have been distributed before the end of 2018 however this has not been feasible due to contracting delays and once the contract is in place delivery should pick up.
Low Carbon Energy for Development Network (LCEDN) (£1.3m). This Fast Start initiative which started in late 2016 involved the design and implementation of two international integrative conferences and webinar series; Comprehensive review of UK academic capacity for Energy Access research; nurturing of a new gender Community of Practice in India; Facilitation of Local Energy Governance initiative in East Africa; Widening the ICDRET initiative in South Africa; Establishment of new partnerships with Practical Action on Academic Research and Practice; Collaboration with EU initiative for capacity building in African Universities (the Pan African University and University of Lesotho); expansion of online networking and information work on newly relaunched website; Support to Energy Catalyst. The initial LCEDN fast track has now come to an end with the final report submitted in February 2019, 9 months later than expected.

Lessons identified this year, and recommendations for the year ahead linked to this output

- The overall priority for the coming period is conclusion of the relevant contracts, and issuing of the call for proposals under the Learning Partnership. It may be necessary to compress certain elements in order to ensure that windows relating to academic years or other dates are not missed.
- While the scoping activity was successfully completed and the two projects arising approved, the scoping report itself contained a large amount of high quality content and insights into the Skills and Expertise needs for clean energy access in Africa. The RPDC should consider ways to disseminate those findings more widely before they become out of date.
- Although gender was a consideration throughout the SED scoping and design work and there are some specific measures in both OGTI and the Learning Partnership to ensure the participation of women, it will be necessary for the RPDC to follow-up on the delivery of this as the projects move to implementation.
- To date there has been limited co-funding for the Learning Partnership with USAID the main interested party so far. However other academic and philanthropic funders should be engaged with as the partnership gets going within Africa and beyond, including UK academic funding streams (e.g. for scholarships for study between African countries).
- The LCEDN fast start programme should be closed out fully, ensuring that all deliverables have been completed to a high standard and research outputs have been communicated.

Output Title	Bio-energy for Sustainable local energy services and Energy Access in Africa (BSEAA)
Output number per LF		5	Output Score:	A
Risk:		Moderate	Impact weighting (%):	8%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone for this review	Progress
5.2[2] - Number of new technologies or technical modifications and adaptation of existing bio-energy technologies leading to the development of improved/tailored solutions to match various applications and geographical contexts.	At least 1-3 technologies under development by 2020	On target / The competition process undertaken by the Energy Catalyst is now in final approval. 6 applications with a value of £2.6m were selected for funding under BSEAA.
5.3 - Research testing the economic and commercial viability of a number of technically feasible bio-energy solutions to be deployed on the ground for various applications and in different geographical contexts / 5.3.1. Number of quantitative and evidence-based studies to test the economic and commercial viability / 5.3.2. Number of qualitative evidence-based studies to identify the project viability challenges	5.3.1) 5 project specific financial assessments covering at least five countries by 2020 / 5.3.2) 5 covering at least three countries by 2020	On target / The first milestones to be delivered under this indicator are due to be delivered during 2019/2020. The procurement process has commenced. Submitted EOIs have been evaluated and successful bidders have been invited to submit full proposals. Contracting is expected to take place end of April 2019.
[2] Output 5.1 related to scoping studies completed in an earlier phase of this project before it became part of TEA.

Phase II of the BSEAA programme which is being undertaken as part of TEA consists of a Technology Innovation Call (undertaken within the Energy Catalyst) and an Academic Research Project which will run in parallel and will be integrated with each other. Over 2018, the two sub-components were fully refined and scoped out for competitive tendering. Calls were then run for both under different vehicles outlined below.

The Technology Innovation Call has been undertaken through the provision of £3m of funding to the Energy Catalyst which ran an open call for tenders under Round 6 of its procurement process launching in August 2018 and concluding the selection of projects in February 2019 (this was a window in Round 6 as reported under Output1). The specific goal was to find for innovative solutions that will support market penetration of bio-energy technologies within SSA. The countries, scale and thematic focus (bio digestion and gasification) of the call mapped on to that of the Academic Research project. Energy Catalyst Round 6 received 28 applications related to BSEAA, of which 14 applications were shortlisted for the BSEAA component and 6 were selected to be funded under the BSEAA programme. The value of funding required for the 6 selected applications amounted to £2.6m as follows:

As can be seen there is a substantial focus of the successful applications in Kenya, although there is a reasonable mix across gasification and bio digestion project types. The funding was also not fully deployed and the RPDC will work with DFID over the coming quarter to identify optimal allocation of this. The successful applicants will also be invited to participate in the workshops to be held as part of the Research Call to i) allow collaboration and sharing of knowledge and insight, and ii) provide steering that enables a strong focus for next stages of research and insights into potential technology optimisation options.

With regards to the Academic Research project the Terms of Reference (ToR) were drafted based on the results of Phase 1 that identified challenges and opportunities and recommended selected themes for further research. The aim of the research call is to support commercialisation of bioenergy technology. The Scope of Work covers: quantitative economic viability testing and economical barriers of bio-energy technologies; Resource/Feedstock suitability and availability; Supply chain and local capacity/support; Policy, regulatory and market factors; Qualitative challenges in successfully deploying gasification technology; Assessment of the suitability of pre-determined bio-energy technologies to specific purposes and business models in various contexts. The targeted countries identified for further investigation in Phase II were: East Africa: Ethiopia, Kenya, Tanzania, Rwanda, Uganda, West Africa: Ghana, Nigeria, Southern Africa: Mozambique, South Africa, Zambia. The call for expressions of interest was opened after conclusion of the RPDC contract uplift in October 2018 and bidders were invited to submit an EoI. Following an extension for submission, four EoIs were received and evaluated by the RPDC, of which two were invited to submit full proposals. The submission deadline for the full proposal is 22/03/2019. Contracting is expected to take place end of April 2019. The academic research project is expected to take between 18-24 months from contracting to completion.

Lessons identified this year, and recommendations for the year ahead linked to this output

- The RPDC should ensure that there is close alignment between the technology development and research activities, as well as larger TEA bioenergy portfolio, to ensure the research is relevant to the bioenergy industry and that scale-up opportunities and synergies with other initiatives are realised.
- Based on the success of the Bioenergy projects and the findings of the research in the coming year, the potential for scale-up of the BSEAA component should be considered from 2020 onwards.
- Indicator 5.3 and related milestones should be revised to reflect more accurately the full scope and breadth of the academic research component (By end of April 2019)

Output Title	Research Programme Delivery Consortium (RPDC) - Co-ordination, Communication, Monitoring and Evaluation
Output number per LF		6	Output Rating	A
Risk:		Moderate	Impact weighting (%):	7%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone for this review	Progress
6.1 Successful delivery of TEA and overall management of all components	6	On Target / 6
6.2 Quarterly Programmatic Reporting over the TEA Portfolio	4	Off-Target / 3 / FY18/19 Q3 claim longer than expected
6.3 Internationally recognised conferences or high-level workshop/symposium attended and present at on TEA programme activity	3	Exceeded Target / 15 – This figure has been reached through efficiency savings found through either attending multi-value (i.e. representing more than TEA) or multi-component events (i.e. representing more than RPDC such as at MGF meetings)
6.4 Number of organisations engaged with through RPDC comprehensive in country engagement in SSA and SA and global energy access innovation community	250	Exceeded Target / 358 / A larger number of Phase 1 scoping interactions occurred than was initially planned which has resulted in achievement ahead of target.
6.5 Value Adding Coordinated Activity Between TEA Components: / 6.5.1 Coordination meetings undertaken with whole program component portfolio representation and DFID / 6.5.2 Collated international stakeholder engagement or programme reviewing exercises between components (CEP/SED)	6.5.1) 20 / 6.5.2) 15	On target / 6.5.1) 21 / 6.5.2) 16 / Meetings undertaken by 20/02/19 with monthly meeting planned for March.

The key RPDC deliverables for this reporting year were around successful completion and closure of the Scoping Phase as well as a programme transition to Delivery phase. The Phase 1 closure documentation was largely provided on time and largely to high quality – notably the Phase 1 Final Report which included the Communications Strategy, Research-Into-Use Strategy and M&E Strategy - although some of the documentation required a second and a final iteration into the summer.
However, the delays associated with the completion of the Phase 1 work were insignificant next to those linked with contracting. This began with the Cabinet Office recommendation after a review that DFID implement a contract uplift at the transition between the design and implementation phases, even though the original contract allowed for progress to the end of the programme. This coincided with a change in the DFID Terms and Conditions which had the effect of reopening the contract under different terms creating significant delay. The contract for implementation was not signed until the 26th October compared with a 20th July target. Although this allowed the Carbon Trust to proceed, there have then been further delays as they have sought to pass through the new contract terms to the other RPDC members and grantees/delivery partners (see CEP and SED outputs) where some partners (particularly smaller and southern partners) have struggled with the new terms. Uncertainty about the VAT liability relating to the programme has caused a further delay. This series of contract-related issues is on top of the original 10 month delay in procurement of the RPDC in the first place, which was reported in the last annual review.
In spite of these contract delays, which have affected the CEP and SED components most strongly, the RPDC team has provided a high generally level of core RPDC management, monitoring and reporting service since implementation started. This has included collating and streamlining the financial claims process for all directly contracted and non-contracted TEA partners to reflect actuals vs forecast as well as to undertake Earned Value Analysis (EVA) of the programme throughout. Guidance documentation was also produced for M&E, Quality Management (QMS) and Reporting to support project partners with their reporting activity. A two-day implementation kick-off meeting for all TEA partners was held in September 2018 and this was followed up with in January 2019 with a shorter quarterly telco-update. The RPDC has continued monitoring and support of the Energy Catalyst, Shell Foundation and Phase 1 Fast Track projects on implementing the 2018 AR recommendations, and providing review and evaluation of TIME and Catalyst projects for approval. Better online SharePoint monitoring and evaluation tools have been created along with a specific Phase
The Communications Strategy was approved in the summer, and has to date included representation and promotion of TEA at a wide variety of events and to a wide variety of stakeholders well ahead of logframe targets (6.3), and the design, development and launch of a live TEA micro-site with news updates (8 uploaded since launch) and open tenders. In addition, the “Transforming Energy Access: Innovations towards SDG7” event has become a significant expansion of the originally planned Delivery Review Workshop, and a major platform for communication, co-ordination and research-into-use. TEA is the main organiser, working with DFID’s Africa Regional Department and Low Energy Inclusive Appliances (LEIA) programme. The event will convene on behalf of DFID Minister of State Baldwin 9 African Energy Ministers, more than 220 delegates including city investors, and 55 speakers from partners and investees of most other UK aid-funded energy programming including Development Capital investors such as CDC, PIDG and the Green Investment Bank. The event will be launched by the Minister Baldwin, with an opening plenary including Rachel Kyte from SEforAll and Amadou Hott Vice-President, Power, Energy, Climate and Green Growth for the AfDB. This event preceded the TEA Delivery Review Workshop on 8th March.
In addition to the above, as part of the implementation design the RPDC also prepared a package of Value Added M&E to be available across the programme including Lean Data beneficiary feedback surveys, drawdown support on gender and social inclusion and research excellence, and further work on the Energy Portfolio Review Database to support co-ordination across DFID’s energy portfolio. Additionally, the RPDC will be contracting an independent expert reviewer for the programme within the next FY. These activities have been on hold pending the resolution of the VAT position.
Engaging potential co-funders for the TEA programme at the portfolio level and supporting implementation partners to raise co-funding has been another important area of activity for the RPDC. Currently, co-funders of TEA activities include IKEA Foundation (PEII), Virgin Unite and Good Energies Foundation (Energise Africa), P4G (GDC and Energise Africa), and Rockefeller Foundation (MGCR).
The final major area of activity has been around contracting for the CEP and SED programmes, including the enhanced legal support to the programme. The RPDC have been working with external legal support contractor Burges Salmon to get both the other primary RPDC sub-contracts contracts (3), the immediate start CEP sub-contracts (6) and the SED delivery sub-contract (1) into place and up to 29 sub-contracts (with associated Due Diligence, and annual follow-ups) are expected to be required for the delivery of the programme.

Lessons identified this year, and recommendations for the year ahead linked to this output

- The protracted delays and barriers around the procurement, contracting, contract update, subcontracting and VAT treatment of the RPDC contract highlights major challenges with the delivery of a DFID research and innovation programme via a fund management contract. As the programme is scaled-up, this will limit the scope for expansion of the element managed via the RPDC.
- Ensure outstanding VAT issue are resolved as soon as practicably possible and that RPDC supporting services are ready to contract subject to contract compliance
- KPIs should be added for the communications and research-into-use activities undertaken by the RPDC. As more results start to come out of the programme the emphasis on communications and research-into-use should increase, and Comms and RIU should be covered as discrete topics in the monthly meetings.
- It will remain important to commission the planned mid-term programme review from an external party in summer 2019 to inform any potential course correction in the programme at this point.
## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

The overall TEA Theory of Change from the Business Case is shown in the figure below:

Complementing the original Theory of Change, and providing more detail on the positioning of the new Clean Energy Partnerships and Skills and Expertise Development projects, the following graphic was produced as an output of the phase 1.

In addition, sub-Theories of Change have also been created and refined for the 6 new Clean Energy Partnerships.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

The past year has seen the collation of a standardised logframe (see Table 1 below) which has allowed comparability across the overall TEA delivery. Although many of the CEP and SED projects are yet to begin producing outputs, the programme is still ahead of key Outcome milestone targets for this year, with the current estimates to date as follows:
- People with improved energy access – 3.59m. This compares with a milestone target for this year of 2m, and an end of programme target of 6m.
- Investment Leveraged (collective private and public) – £359m (£348m private and £11m public). This compares with a target of £115m for this year (£100m private, and £15m public).
- CO2 reduced or avoided (t/CO2) – 2m compared with a target of 1.5m CO2 reductions to this milestone.
The main contributors to the Outcomes so far are the Shell Foundation, Energy Catalyst and Fast Track projects P2P Solar and Pioneer Energy Investment Initiative, however as additional partnerships come on line we expect these numbers to increase further. In addition the skills and expertise initiatives will start contribute outcomes in the area of graduates/trainees,

Explain major changes to the logframe in the past year

There has been significant modification to the Logframe since last year due to three key reasons:

1. The addition of new nested Logframes from the new CEP and SED projects
2. Some existing programmes have refined in their Logframes where either no strong Logframe existed before (Energy Catalyst) or where the learnings from delivery have predicated a requirement for Logframe update (BSEAA).
3. Standardisation of all sub-logframes into the new TEA master logframe format (discussed below) has resulted in all remaining Logframes (TIME, fast-track projects and RPDC) needing updating to better align common indicators.

TEA impact will now be measured from a ‘top-down’ perspective using trusted industry reports to measure the progress and development of the off-grid sector in three key sub-sectors:
- The size and growth of the SHS market using GOGLA data;
- The size and growth of the mini-grid market using Mini-Grid Partnership data; and
- The size and growth of the last mile distribution sector using GDC data.

A TEA attribution factor will then be assigned to measured impacts based on the independent mid-term and annual reviews which will focus on detecting the difference which TEA support has made to these wider sectoral trends.

This top down impact assessment methodology will also be compared with and complemented by a bottom up Outcomes assessment based around five standardised ‘Programme Outcomes’ which all of the separate projects are required to measure and contribute to as far as possible. The standard programme outcomes are not exclusive (i.e. further Outcomes are used for most projects) with the common indicators across components listed in Table 1 below. Outputs are maintained at a separate level and are reported individually for each project with key outputs collated at a (separated) TEA programme level.

Programme outcomes (P1-5)	Outcome Indicator P1: Lives Improved	Component reporting
Increasing use of affordable decentralised clean energy options for poor households and enterprises in SSA and SA	P1.1: People with improved energy access	TIME; PEII; P2PS
	P1.2: Graduates/trainees/placements	TIME, OGTI, TEA-LP GDC, PUP
	Outcome Indicator P2: Jobs Created	Component reporting
	P2.1: Sustainable long term jobs created - Energy Generation/Supply	TIME; PEII; OGTI; POP
	P2.2: Sustainable long term jobs created - Energy Demand/Use	TIME; PEII; OGTI; POP
	Outcome Indicator P3: Investment Leveraged	Component reporting
	P3.1: Private sector	All
	P3.2 Public sector	All
	Outcome Indicator P4: Clean Energy	Component reporting
	P4.1: Installed off-grid clean energy capacity (MW)	P2PS; PEII; TIME
	P4.2: CO2 avoided	P2PS; PEII; TIME
	Outcome Indicator P5: Innovation	Component reporting
	P5.1: Number of new energy access technologies prototyped and/or demonstrated in Africa	EC, MGCR, POP, BSEAA
	P5.2: Number of innovative businesses models tested in Africa	EC, TIME, PEII, CP2, GDC, MGCR, POP

Table 1: Standardised TEA Programme Outcomes

Describe any planned changes to the logframe as a result of this review

Additional KPIs for Output 6 relating to Communications and Research-Into-Use will be added.

BSEAA and POP KPIs will be updated as a result of additional contract awarding over the next review period.

## D: VALUE FOR MONEY

Assessment of VfM compared to the proposition in the Business Case, based on the past year

Key cost drivers and performance
The key cost drivers for the programme vary by component and include: researcher/staff costs, travel and logistics and exchange rates (although this risk is held by the delivery partners). Specific cost drivers relating to the programme portfolio numbers (i.e. businesses or projects supported) apply to the first two Outputs (Stimulating Technology Innovation and TIME). These are consistent with those identified in the Business Case.
The VAT status of the RPDC managed component of the programme has been an unresolved issue and recently DFID have stated that if Carbon Trust believe VAT is liable then they should charge it. DFID will then review whether that VAT can be reclaimed by DFID under VAT code 74 for research. If VAT is liable and not reclaimable, then an allowance from the TEA budget will have to be made for VAT and savings or additional funds found to cover it.

VfM Assessment against the 4Es of DFID’s VfM framework
Economy (Input)
Delivery costs for TEA in general have been compared internally and to external programmes at several levels - overall programme, component delivery and project delivery (see below) to ensure competitiveness of delivery. For competitively tendered multi-project components (e.g. Energy Catalyst, POP, BSEAA) and as with programme procurement in general, Value for Money is an assessment questions used to evaluate and score projects. Likewise, PMO/overhead is reviewed within the VfM appraisal where applicable. Any proposed changes to charges once contracted are assessed prior to approval by a monitoring/project officer to ensure VfM is maintained. For RPDC and delivery partner staff costs, pre-agreed profit rates or no profit margin is agreed and costs are split between funders where applicable. Travel and accommodation within the RPDC is undertaken via expenses (rather than per-diem) and controlled at ‘reasonable’ rates (e.g. standard class travel and modest appropriate accommodation).
Efficiency (Input to Output)
The overall programme delivery of TEA is undertaken using open book accounting and profit margins with DFID. Delivery against costs is monitored at the TEA level through the use of Earned Value Analysis and at the Component/Project level through (at least) quarterly monitoring/project officer evaluation of costs against delivery. RPDC sub-contracting includes clear deliverable measured against payment milestones to control efficiency. The RPDC also maintain a Quality Management Strategy document to support high value delivery internally against forecast. Most projects have just started to deliver however TEA/RPDC continue to evaluate overall projects delivery VfM and reserve the right to adjust scope or (in extreme cases) de-fund should projects be failing to deliver against business case.
Effectiveness (Output to Outcome)
Several measures are in place to monitor effectiveness throughout TEA depending upon component however these link back in all cases to assessment against the Logframe. Energy Catalyst undertakes annual questionnaires with completed projects to understand project outcomes (e.g. patents published etc.) TIME have similar processes in place where monitoring/project officers measure supported company outcomes (CO2 offset/lives improved). Standardisation of the RPDC logframe programme level outcomes has been employed (see Table 1 in section C) to allow comparability of outcomes between projects/components.
Equity
The newly standardised logframe’s first main outcomes now include disaggregation by gender. The RPDC has worked hard to ensure that gender and inclusion has been ingrained within the delivery of the new projects/components and all CEP and SED project business cases developed included ‘leave no one behind’ sections. The RPDC have also produced supportive gender and social inclusion (GESI) toolkit to assist delivery partners. The latest Energy Catalyst Round 6 had (for the first time) a gender and social inclusion gateway requirement within the application which was assessed by the RPDC. Energy Catalyst will circulate the RPDC GESI toolkit to R6 awardee projects and will work with RPDC support services where required to support their GESI status. Within TIME, Value for Women (V4W) provides support to its portfolio of enterprises to understand their customers and add commercial value to their business models through meeting the needs of women and girls. In 2018, the first phase of work with V4W was completed, with 6 enterprises undertaking a comprehensive analysis of core operational functions (HR, sales, product design, etc.) to determine potential added value from gender lens strategies. As well as the above, each of the separate CEP/SED and BSEAA projects have their own specific gender and social inclusion approach, supported in delivery by the RPDC, and clear in their respective business cases.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
Both Energy Catalyst and TIME continue to show exceptional value for money in delivery, InnovateUK charging a 5% margin on programme delivery (well below PMO average) and Shell Foundation securing 1:1 match funding for all staff time on TEA. Both have succeeded in leveraging large sums of additional funding to meet programme outputs and have delivered well above target ambition. We would have no concern about supporting continued funding of these components.
All CEP/SED and BSEAA programmes that are RPDC have led are in the very early stage of delivery and so it is still too early to make any definitive statement about their VfM performance however the business cases under which they were approved for funding are still valid and we therefore have no reason to believe these should not continue to be supported (i.e. no exogenous factors have changed that would affect the VfM for their delivery).
Fast Track projects within the CEP/SED are now coming to a close and (where not already closed) will be so by the end of the next year however have for the most part shown good VfM against forecasted Logframe outputs. LCEDN have had severe resourcing difficulties this year that have delayed delivery by several months however are also due to close out by the end of the financial year and with this exception have shown good value for money in all previous year’s reviews.
The RPDC continues to work to deliver efficiently and at good value for the tax payer since being competitively awarded delivery in 2016. Significant scope changes have been absorbed by flexible and risk-appropriate reallocation of RPDC costs (e.g. inclusion of EPR work, preliminary MGF activity). The RPDC also continue to proactively work towards more efficient strategic oversight and PMO of the TEA programme through scaling PMO activity such as automated online reporting processes, standardisation of supporting and reporting tools (e.g. GESI toolkit, Logframe, full reporting packs etc). Outstanding challenges with VAT remain a source of risk to programme delivery however these are not directly related to RPDC delivery.

E: RISK

Overview of programme risk:

The overall risk rating remains Moderate (no change since last Annual Review)

TEA takes an innovative approach and is large in size - to generate the desired transformation and impact, but balances these risks by including different types of complementary interventions and implementing partners, both tested and new, and adopting a phased approach, with a review after 18 months, and the scope to make adjustments. Bi-annual review meetings have been established to both support quality of delivery but also to allow ‘course-correction’ should delivery of individual projects be failing to meet business case objectives.
For existing components/projects (Energy Catalyst, TIME, Fast Track projects and BSEAA) the risk ratings have not changed. For all new projects (CEP, SED and BSEAA) new risk registers have been completed and the collective risks remain roughly commensurate to the rest of the programme portfolio, reflective of the similar profile of activity undertaken, (i.e. highly innovative technology and business innovation with overseas focus).
The risk management framework below continues to be updated by the RPDC for approval by DFID.
Overall TEA Risk Management Framework[3]
[3] Please note that each programme and project has its own live Risk Register. Only the main key risks are identified within this Risk Register.
Risks and Description	Rating[4]	Mitigating Actions
Research, Innovation and Uptake risks
Applications received and supported, and business models developed do not generate sufficient market demand to meet output and outcome indicator targets		Various delivery channels and implementing partners will test multiple innovations before deploying significant resources to formally launch them to the market. The nature of innovation is to test different options with some failures and some successes; these risks are intrinsic to this type of project and the channels and scale and spread of funding hedges these risks. The phased milestone approach to dispersing funds to implementing partners ensures performance is closely monitored, limiting the disbursement of funds to partners that do not show good potential for uptake.
Market uptake of the recommendations and ideas demonstrated by the research and innovation support is slower than anticipated		Leveraging SF, Energy Catalyst, other partnerships and DFID networks engages with a range of outreach activities and media channels. Uptake is a critical measure of the RPDC performance and the Carbon Trust led consortium has allocated significant budget to research uptake and has built an extensive global network within Phase 1 of delivery. Outcome indicators are already positive, which is a good indication of uptake.
Gender inclusion and diversity focus is de-prioritised due to project time delivery pressures		'Several tools for gender inclusion have been designed into reporting requirements and gender disaggregation has been included within the primary Logframe Outcome KPIs to ensure continual focus. Additionally, RPDC support will (budget allowing) be utilised to help with gender mainstreaming on projects that lack historical knowledge of gender issues (e.g. Energy Catalyst)
Capacity and Knowledge risks
Programme Impacts Un-credible: / Programme Impacts entered into logframe are based upon too optimistic assumptions which, when delivered are picked up and covered by media		1. Be pragmatic with assumptions to ensure they can stand up to scrutiny. / 2. Report on Outcomes rather than impacts (which still include for example ‘lives improved’ or ‘graduates’) where there’s a much stronger direct link to the delivery / 3. Rely on the External Evaluators to validate the attribution of impacts that can be claimed by the programme, therefore giving it external credibility. The challenge with this is that the evaluations will happen after we’ve already published numbers.
Governments are resistant to decentralised market based approaches and few enterprises are willing to pursue innovation opportunities identified.		Leveraging of DFID, SF and others networks and convening power will provide traction. SF country accelerators directly help to address the enabling environment, as will the wider TEA capacity building component, plus outreach available through the RPDC will address these barriers. One of the proposed Clean Energy Partnerships is explicitly aimed and encouraging government policy support by identifying opportunities for local value and employment creation in the manufacturing, assembly, service and recycling sectors. The major Transforming Energy Access Forum with the DFID Minister of State convening African Energy Ministers to consider the potential and results of TEA funded innovations is also intended to help address this risk.
Implementing partners are too engaged in managing their existing core businesses to devote sufficient time and effort to develop new innovations.		Shell Foundation evaluate resource availability ahead of any disbursements to ensure selected partners are ready and able to devote additional resources to develop new applications and models. Energy Catalyst projects are paid in arrears to reduce financial risk exposure for under-delivery. / RPDC let components will also be paid in arrears again, to reduce under-delivery and over the past year, delivery partners have already started to deliver project activity (sometimes at risk) validating their ambition for programme engamgent.
Insufficient capacity (technical, financial and management) in enterprises, universities and the market to support innovation, education and market update.		Implementing partners under the different components will provide specific support where relevant, and this will be complemented by the wider TEA skills and professional capacity building component to increase the sector pool of expertise. Catalyst have drafted a proposal to provide projects within R6 through business support
Governance and Programme Management risks
Large, ambitious programme lacks management capacity, technical expertise and focus on results to optimise research and innovation take-up.		The rationale for appointing an overall RPDC supplier is to address this risk and performance will be closely monitored. / RPDC led project procurements (SED, POP, BSEAA etc.) require potential providers to demonstrate both technical capacity and experience in undertaking similar work. Managerial and administrative capacity to undertake a projects is also evaluated.
Choice of implementing partners is not made transparently; downstream partners lack good governance and financial stability.		The EC and SF guidelines set out clear procedures and criteria for assessing proposals. Governance procedures must adhere an agreed risk control framework; All grants are assessed and approved will be in accordance with MoU stipulations, and DFID will continue to monitor transparency of all TEA activities (EC and SF specifically) through annual reviews and notably the Phase 1 review process. / The RPDC has also committed to good governance fiduciary risk management and due diligence in implementing CEP and SED delivery partners engaged with within implementation undertake and implement the Supplier Code of Conduct and are also subject to Due Diligence checks from the RPDC.
Complexity and volatility of programme scope causes schedule delay that affect outcomes		The RPDC and other sensitive delivery partners (InnovateUK for R6 awarding) manages the programme in a flexible and responsive fashion, accommodating for scope change requirements where needed and with a view to minimalizing delivery risk. / Provision of review periods and stage gates are utilised in projects where possible to redress scope variations. Additionally, projects are in some instances working outside of contract to ensure delivery timeframe is kept as well as concertinaing delivery where required.
[4] Categories of risk- Minor; Moderate; Major; Severe; (arrows up or down indicate a risk increase or decrease in the past year)

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues:
- Stimulating Technology Innovation: Energy Catalyst are currently on target with the round 6 selections recently made fully utilising the available budget. With payments being in arrears and depending on project performance there are some lags and uncertainties with communication not always being as far in advance as ideal, but on the whole in the reporting year has been adequate.
- Accelerating Enterprise-led Innovation in Technology Business Models (TIME): TIME is the largest spending element of the TEA Programme and has continued to deliver on expectations in terms of pipeline and expenditure.
- Clean Energy Partnerships (CEP): The transition from scoping to implementation phase has been longer than originally anticipated. However, this has been offset by: partners agreeing to begin work during the transition phase at risk; adjustment of delivery timeframes to expedite project delivery, in order to remain within the total project timelines. As such, at this early stage of the projects, there is no impact on total project budget or timeframe. Current CEP contract status is as shown below.

Partnership name	Contracting partner	RAG	Contractual status
PEII	Acumen Fund		Final review/amendment
GDC	Practical Action Consulting		Ready for final signing
CP2	Energy 4 Impact		Final review/amendment
POP	To Be Confirmed		N/A
PUP	Global Off-Grid Lighting Association (GOGLA)		Ready for final signing
MGCR	Cross Boundary		Mid-stage review amendment
MGCR	United Nations Foundation		Contract Issued to Supplier

For Fast-Tack projects (P2PS and Acumen), successful delivery to date against forecast has led to their scale-up within the Phase 2. As part of operational handover from DFID, partners are being subject to fresh Due Diligence and Supplier Code of Conduct as per the latest contract requirements.
Developing Local Skills and Expertise (SED): There have been contracting challenges in the delivery of the SED component against the planned timeframe. This will not delay delivery timeframes for the SED and components are still on track to be delivered within agreed budget. LCEDN programme has come to a close several months later than forecast due to severe staffing challenges. Final deliverables are yet to be evaluated. Current SED contract status is as shown below:
Initiative name	Contracting partner	RAG	Contractual status
TEA – LP	University of Cape Town, Energy Research Centre		Final review/amendment
OGTI	To Be Confirmed		Final review/amendment

Delivery compliance checks of both CEP and SED partners is ongoing concurrently with the contracting process. Latest status indicates there should be no problems however finalisation will be due start of Q2 FY19/20
- Bio-energy for Sustainable local energy services and Energy Access in Africa (BSEAA): BSEAA timeframe has been marginally re-scheduled due to (1 month) extension of the submission deadline for Expression of Interest for the Academic Research Project. The BSEAA programme can also still be completed within the overarching TEA programme timeframe.
- RPDC / partnership approach of TEA: Partnership engagement within the TEA portfolio has been one of the key value adding elements of the TEA approach. For example, RPDC’s (Carbon Trust, TERI and E4I) quality assurance and moderating role on Catalyst Round 6 was very important in ensuring strategic alignment between Round 6 grants and the rest of the TEA portfolio.

Asset monitoring and control

For the Energy Catalyst, each project is assigned a monitoring officer that visits the project at the project start, project end and after each quarter. Their role is to check that the project is on track and this included checking the claims are valid. As part of this they can ask to see receipts, invoices or transaction lists for any item. While there is not a specific spend limit in which they ask to see an invoice, in practice it tends to be on higher cost items (aka over £500), but if there is some questions over the costs they may ask to see them all.
No assets have been purchased or registered to the TIME, CEP, SED, BSEAA or RPDC components.

Date of last narrative financial report(s)	Sent to DFID 23/01/19
Date of last audited annual statement (s)	October 2018

G: MONITORING, EVIDENCE & LEARNING

Stimulating Technology Innovation:

Monitoring - Innovate UK undertake quarterly project checks for all projects through a dedicated monitoring officer who assesses the project activity. Projects are scored on metrics 1-5 as follows: Scope, Time, Cost, Exploitation, Project Management and Risk. Below is an average of scores across DFID funded projects for each of the metrics.
Scope	Cost	Time	Exploitation	PM	Risk
3.6	3.6	3.7	3.9	3.8	3.8

Evidence - Innovate UK will be reviewing the Energy Catalyst Programme with our evaluation team within the coming year, but thus far no Energy Catalyst specific work has been completed. Over the coming year(s), GESI indicators will be available as R6 projects kick-off (this has not been a prerequisite previously).

Learning - The primary learning for Energy Catalyst activity has been related to the modifications and changes that have occurred to the application and evaluation process as a result of Round 6 DFID funding amount. Specifically this has related to the inclusion on gender and social inclusion KPIs as well as the broader TEA requirements. Specific learnings are outlined in the Output section.

Accelerating Enterprise-led Innovation in Technology Business Models (TIME):
Monitoring - SF has frequent, at least monthly, contact with TIME supported enterprises. Some of this monitoring contact is by phone but the SF programme team meets partners in country at least once a quarter. When in the field with partners, SF’s staff make a point of meeting customers and staff across the partner company – to understand their business, monitor progress and provide support. Several TIME companies are receiving support to develop their own monitoring systems to improve business intelligence and management information, on the basis of KPI definition, recording and monitoring.

Evidence - The creation of evidence as a global public good is a core aspect of the TIME partnership, monitored by output indicator 1.5. TIME have produced 11 learning reports published by SF and partners in 2018 (see component level report)
Learning - Efforts to link TIME better with the TEA programme and both UK and African businesses should be continued, as will SF’s efforts to “exit” partners and create space in the portfolio for support to earlier stage innovation. SF are keen to develop and spin-out a dedicated Mini-grid programme or partnership, leveraging funds from other donors and capitalising on TIME’s work in this area.

Clean Energy Partnerships (CEP):
Monitoring - Even accounting for the immaturity of the delivery phase, a large amount of initial (and in many cases pre-contracting) monitoring progress in the reporting period has already occurred as briefly highlighted below:
- Pioneer Energy Investment Initiative (PEII): PEII measures and reports on impact via its Lean Data methodology. PEII also maintains a detailed logframe against which it reports annually.
- Global Distributors Collective (GDC): PAC worked with OPM to produce a robust M&E plan. Progress has been monitored via the monthly Global Distributors Collective management team meeting made up of the implementing partners and regular PM meetings with the RPDC.
- Crowd Power 2 (CP2): CP2 maintains a detailed logframe against which it reports annually. All deliverables currently on track to be achieved by set milestones.
- Powering Opportunities Partnership (POP): POP team report on progress to senior personnel in both Carbon Trust and E4I on project progress. Weekly team meetings direct efforts on an on-going basis and ensure time frames are met.
- PowerUp project: Formal M&E processes have been defined and will take effect once contracting complete and formal project implementation begins.
- Mini-grid coordination, research and cost reduction partnership (MGCR): Updated during TEA Quarterly update call in January. Formal M&E processes will take effect once contracting complete and formal project implementation begins.
Evidence - Project logframes and deliverables schedules are used to track delivery and performance. Key evidence and outputs in the reporting period for each project are provided within the separate component level review.
Learning - Specific learnings are highlighted within the Output section (Section C, Output 3)

Developing Local Skills and Expertise (SED):
Monitoring - Many stakeholders from the private sector and academia have provided feedback on the business cases and approach taken for SED TEA Phase II, and requested to be informed about the RFP and outreach activities. Monitoring and Evaluation for the TEA LP (implemented by the ERC) and OGTI (implemented by a service provider) has not commenced.
Evidence - SED evidence is as follows: Scoping study report, approved by DfID, Business case – Off Grid Talent Initiative, approved by DfID, Business case – TEA Learning Partnership, approved by DfID and a book chapter on the TEA scoping study – under review
Learning - Specific learnings are highlighted within the Output section (Section C, Output 4)

Bio-energy for Sustainable local energy services and Energy Access in Africa (BSEAA):
Monitoring - For the BSEAA programme, M&E will be split into the two sections related to the different delivery projects. For the Technology Innovation project , M&E will be performed through the RPDC and Energy Catalyst however as part of the RPDC BSEAA oversight, the bioenergy technology portfolio within R6 shall be monitored and evaluated separately as a sub-set throughout the BSEAA delivery. For the Academic Research project, Carbon Trust M&E shall be undertaken as with all RPDC held contracts (i.e. CEP/SED) and be undertaken as outlined within the RPDC section below.
Evidence - Given that the sub-components have not yet started, there is no evidence to date.
Learning - Specific learnings are highlighted within the Output section (Section C, Output 5)

Research Programme Delivery Consortium:
Monitoring - RPDC monitor all outputs from TEA with exception of formal reports from the external evaluation contractor (due to be installed late summer 2019) and less formal reporting from Shell Foundation and Energy Catalyst which will in some instances still go through the respective SRO at DFID.
Monitoring and evaluation is undertaken in accordance with the separate M&E Strategy document as well as the supporting reporting templates available to partners and DFID within the Phase 2 SharePoint site.
Evidence - Continual delivery engagement with DFID by the RPDC occurs through informal emails/calls/meetings, formal monthly meetings, quarterly programme wide meetings (last undertaken in January 2019) and bi-annual face-to-face programme meetings (including kick off meeting held in January.
Learning - The key lessons from the previous year in relation to RPDC activity is that facilitating and supporting intra-programme communications and interactions is an ongoing process that requires more than the provision of sharing tools, but also effort on all partners to keep regular dialogue occurring. Finally, contracting and due diligence can and does take longer than expected in many instances and adequate time should be allocated to ensure smooth delivery.