## TEA Project Logframe Blank (hidden)
Programme outcomes (P1-6) | Outcome Indicator P1: Lives Improved |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions | Component reporting | Comments / challenges | Gender split
Increasing use of affordable decentralised clean energy options for poor households and enterprises in SSA and SA | P1.1: People with improved energy access (unit) | Planned: F | [8 empty] | TIME; PEIi; EA | Weighting data to DFID / TEA; Consistency of methodology; How to use lean data pilot | Yes
Planned:M
Achieved: F
Achieved: M
Source
| P1.2: Graduates/trainees/placements (unit) | Planned: F | [8 empty] | TIME, OGTI, APEA, GDC, SREA |  | Yes
Planned:M
Achieved: F
Achieved: M
Source
| Outcome Indicator P2: Jobs Created |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions | Component reporting | Comments / challenges | Gender split
| P2.1: Sustainable long term jobs created - Energy Generation/Supply (unit) | Planned: F | [8 empty] | TIME; PEII; OGTI; POP | Numbers likely to be small; Methodology is a real challenge | Yes
Planned:M
Achieved: F
Achieved: M
Source
| P2.2: Sustainable long term jobs created - Energy Demand/Use (unit) | Planned: F | [8 empty] | TIME; PEII; OGTI; POP |  | Yes
Planned:M
Achieved: F
Achieved: M
Source
| Outcome Indicator P3: Investment Leveraged |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions | Component reporting | Comments / challenges | Gender split
| P3.1: Private sector (£m) | Planned | [8 empty] | All |  | No
Achieved
Source
| P3.2 Public sector (£m) | Planned | [8 empty] | All |  | No
Achieved
Source
| Outcome Indicator P4: Clean Energy |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions | Component reporting | Comments / challenges | Gender split
| P4.1: Installed off-grid clean energy capacity (MW) | Planned | [8 empty] | EA; PEII; TIME | Likely to be very small; not really suitable for an innovation programme | No
Achieved
Source
| P4.2: CO2 avoided (t/CO2) | Planned | [8 empty] | EA; PEII; TIME | Likely to be very small; methodology very difficult due to varying counterfactuals & lifetimes | No
Achieved
Source
| Outcome Indicator P5: Innovation |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions | Component reporting | Comments / challenges | Gender split
| P5.1: Number of new energy access technologies prototyped and/or demonstrated in Africa | Planned | [8 empty] | EC, MGCR, POP, BSEAA | Could split this between prototyped and demonstrated | No
Achieved
Source
| P6.1: Number of innovative businesses models tested in Africa | Planned | [8 empty] | EC, TIME, PEII, CP2, GDC, MGCR, POP |  | No
Achieved
Source
[11 empty] | Component reporting | Comments / challenges | Gender split
INPUTS (£) | DFID (£) | Govt (£) |  | Other (£) |  | Total (£) |  | DFID SHARE (%) |  |  | All |  | No
INPUTS (HR) | DFID (FTEs)
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions
(Project Specific Custom Outcome) | (Project Specific Custom Outcome Indicator) Outcome to be collated up to Programme Logframe | Planned | [7 empty] | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
Achieved
Source
| Outcome Indicator 2.2 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
| (Project Specific Custom Outcome Indicator) | Planned
Achieved
Source
| Outcome Indicator 2.3 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
| (Project Specific Custom Outcome Sub-Indicator) | Planned
Achieved
Source
| (Project Specific Custom Outcome Sub-Indicator) | Planned
Achieved
Source
| Outcome Indicator 2.4 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
| (Project Specific Custom Outcome Sub-Indicator) | Planned
Achieved
Source
| (Project Specific Custom Outcome Sub-Indicator) | Planned
Achieved
Source
OUTCOME 3 | Outcome Indicator 3.1 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions
(Project Specific Custom Outcome) | (Project Specific Custom Outcome Indicator) Outcome to be collated up to Programme Logframe | Planned | [7 empty] | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
Achieved
Source
| Outcome Indicator 3.2 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
| (Project Specific Custom Outcome Indicator) | Planned
Achieved
Source
| Outcome Indicator 3.3 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
| (Project Specific Custom Outcome Sub-Indicator) | Planned
Achieved
Source
| (Project Specific Custom Outcome Sub-Indicator) | Planned
Achieved
Source
| Outcome Indicator 3.4 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
| (Project Specific Custom Outcome Sub-Indicator) | Planned
Achieved
Source
| (Project Specific Custom Outcome Sub-Indicator) | Planned
Achieved
Source
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions
(Project Specific Custom Output) | (Project Specific Custom Output Indicator) Output to be collated up to Programme Logframe | Planned | [7 empty] | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
Achieved
Source
| Output Indicator 1.2 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
| (Project Specific Custom Output Indicator) | Planned
Achieved
Source
| Output Indicator 1.3 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
| (Project Specific Custom Output Sub-Indicator) | Planned
Achieved
Source
| (Project Specific Custom Output Sub-Indicator) | Planned
Achieved
Source
| Output Indicator 1.4 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
| (Project Specific Custom Output Sub-Indicator) | Planned
Achieved
Source
| (Project Specific Custom Output Sub-Indicator) | Planned
Achieved
IMPACT WEIGHTING |  | Source | [7 empty] | RISK RATING
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions
(Project Specific Custom Output) | (Project Specific Custom Output Indicator) Output to be collated up to Programme Logframe | Planned | [7 empty] | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
Achieved
Source
| Output Indicator 2.2 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
| (Project Specific Custom Output Indicator) | Planned
Achieved
Source
| Output Indicator 2.3 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
| (Project Specific Custom Output Sub-Indicator) | Planned
Achieved
Source
| (Project Specific Custom Output Sub-Indicator) | Planned
Achieved
Source
| Output Indicator 2.4 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
| (Project Specific Custom Output Sub-Indicator) | Planned
Achieved
Source
| (Project Specific Custom Output Sub-Indicator) | Planned
Achieved
IMPACT WEIGHTING |  | Source | [7 empty] | RISK RATING
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions
(Project Specific Custom Output) | (Project Specific Custom Output Indicator) Output to be collated up to Programme Logframe | Planned | [7 empty] | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
Achieved
Source
| Output Indicator 3.2 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
| (Project Specific Custom Output Indicator) | Planned
Achieved
Source
| Output Indicator 3.3 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
| (Project Specific Custom Output Sub-Indicator) | Planned
Achieved
Source
| (Project Specific Custom Output Sub-Indicator) | Planned
Achieved
Source
| Output Indicator 3.4 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
| (Project Specific Custom Output Sub-Indicator) | Planned
Achieved
Source
| (Project Specific Custom Output Sub-Indicator) | Planned
Achieved
IMPACT WEIGHTING |  | Source | [7 empty] | RISK RATING
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions
(Project Specific Custom Output) | (Project Specific Custom Output Indicator) | Planned | [7 empty] | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
Achieved
Source
| Output Indicator 4.2 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
| (Project Specific Custom Output Indicator) | Planned
Achieved
Source
| Output Indicator 4.3 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
| (Project Specific Custom Output Sub-Indicator) | Planned
Achieved
Source
| (Project Specific Custom Output Sub-Indicator) | Planned
Achieved
Source
| Output Indicator 4.4 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | If your project/programme has join investment, please provide a number that includes the impact weighting of DFID support
| (Project Specific Custom Output Sub-Indicator) | Planned
Achieved
Source
| (Project Specific Custom Output Sub-Indicator) | Planned
Achieved
IMPACT WEIGHTING |  | Source | [7 empty] | RISK RATING

## Final TEA Programme Logframe
TEA programme
IMPACT | Impact Indicator 4 |  | Baseline (Mar 2046) | Milestone 4 (Mar 2047) | Milestone 2 (Mar 2048) | Milestone 3 (Mar 2049) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2024) | Target (Mar 2022) | Assumptions | Component reporting | Comments / challenges | Gender split
Improved access to reliable energy services, leading to better well-being for poor people and livelihood opportunities. | MW mini-grid capacity in Africa | Planned | [7 empty] | Assumes that GMG MDP database can be used as a baseline & that the report / research will be repeated at least once more | N/A | Lacks programme independence? Attribution? | No
Achieved
Source:
Mini-grid state-of-the-market report - with estimate of TEA attribution from Independent Evaluation
| Impact Indicator 2 |  | Baseline (Mar 2046) | Milestone 4 (Mar 2047) | Milestone 2 (Mar 2048) | Milestone 3 (Mar 2049) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2024) | Target (Mar 2022) | Assumptions | Component reporting | Comments / challenges | Gender split
| SHS unit sales in Africa | Planned | [8 empty] | N/A | Lacks programme independence? Attribution? | No
Achieved
Source:
GOGLA Global Off-Grid Solar Market Report - with estimate of TEA attribution from Independent Evaluation
| Impact Indicator 3 |  | Baseline (Mar 2046) | Milestone 4 (Mar 2047) | Milestone 2 (Mar 2048) | Milestone 3 (Mar 2049) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2024) | Target (Mar 2022) | Assumptions | Component reporting | Comments / challenges | Gender split
| LMD sector total sales in Africa | Planned | [7 empty] | Assumes that there LMD state-of-the-market report can be used a baseline & that the report / research will be repeated at least once more | N/A | Lacks programme independence? Attribution? | No
Achieved
Source:
LMD state-of-the-market report - with estimate of TEA attribution from Independent Evaluation
| Impact Indicator 4 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions | Component reporting | Comments / challenges | Gender split
| Frontier Power Market Size in Africa | Planned | [7 empty] | BNEF keeps tracking this market | N/A | Cost of access to BNEF data. Attribution? | No
Achieved
Source:
Bloomberg New Energy Finance - with estimate of TEA attribution from Independent Evaluation
| Impact Indicator 5 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions | Component reporting | Comments / challenges | Gender split
| TEA transformational impact (0-4) | Planned | [7 empty] | Measuring level of transformational impact included in the TEA evaluation ToR | N/A |  | No
Achieved
Source:
Independent evaluation
Programme outcomes (P4-6) | Outcome Indicator P1: Lives Improved |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions | Component reporting | Comments / challenges | Gender split
Increasing use of affordable decentralised clean energy options for poor households and enterprises in SSA and SA | P1.1: People with improved energy access (unit) | Planned: F | 0 | 0 | 94532 | 190532 | 1000000 | 2000000 | 2000000 | Gender dissagregated figures are only introduced for 2020 reporting | TIME; PEIi; EA | Weighting data to DFID / TEA; Consistency of methodology; How to use lean data pilot | Yes
|  | Planned:M | 0 | 0 | 1000000 | 2000000 | 2000000 | 4000000 | 4000000
|  | Achieved: F | 0 | 0 | 148677 | 244441 | 0 | 0 | 0
|  | Achieved: M | 0 | 104501 | 1433237 | 3349700 | 0 | 0 | 97500
Source
Compiled Component Reporting
| P1.2: Graduates/trainees/placements (unit) | Planned: F | 0 | 0 | 0 | 0 | 6 | 126 | 246 |  | TIME, OGTI, APEA, GDC, SREA |  | Yes
|  | Planned:M | 0 | 0 | 0 | 0 | 10 | 190 | 370
|  | Achieved: F | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved: M | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
| Outcome Indicator P2: Jobs Created |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions | Component reporting | Comments / challenges | Gender split
| P2.1: Sustainable long term jobs created - Energy Generation/Supply (unit) | Planned: F | 0 | 0 | 0 | 0 | 133.32 | 133.32 | 166.6667 | Gender dissagregated figures are only introduced for 2020 reporting | TIME; PEII; OGTI; POP,EC | Numbers likely to be small; Methodology is a real challenge | Yes
|  | Planned:M | 0 | 0 | 100 | 200 | 266.64 | 266.64 | 333.3333
|  | Achieved: F | 0 | 0 | 0 | 53 | 0 | 0 | 0
|  | Achieved: M | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
| P2.2: Sustainable long term jobs created - Energy Demand/Use (unit) | Planned: F | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TIME; PEII; OGTI; POP,EC |  | Yes
|  | Planned:M | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved: F | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved: M | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
| Outcome Indicator P3: Investment Leveraged |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions | Component reporting | Comments / challenges | Gender split
| P3.1: Private sector (£m) | Planned | 0 | 0 | 50 | 100 | 150 | 150 | 180 |  | All |  | No
|  | Achieved | 0 | 15.3 | 146.9948 | 347.7206 | 0 | 0 | 2.3
Source
| P3.2 Public sector (£m) | Planned | 0 | 0 | 10 | 15 | 20 | 20 | 20 |  | All |  | No
|  | Achieved | 0 | 0 | 1.8844 | 11.196 | 0 | 0 | 0
Source
| Outcome Indicator P4: Clean Energy |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions | Component reporting | Comments / challenges | Gender split
| P4.1: Installed off-grid clean energy capacity (MW) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | EA; PEII; TIME | Likely to be very small; not really suitable for an innovation programme | No
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
| P4.2: CO2 avoided (t/CO2) | Planned | 0 | 0 | 780333.3333 | 1488333.3333 | 2170333.3333 | 2766666.6667 | 3193333.3333 |  | EA; PEII; TIME | Likely to be very small; methodology very difficult due to varying counterfactuals & lifetimes | No
|  | Achieved | 0 | 8516 | 990877.3333 | 2021749.1767 | 0 | 0 | 0
Source
| Outcome Indicator P5: Innovation |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions | Component reporting | Comments / challenges | Gender split
| P5.1: Number of new energy access technologies prototyped and/or demonstrated in Africa | Planned | 0 | 0 | 0 | 7 | 12 | 17 | 20 |  | EC, MGCR, POP, BSEAA | Could split this between prototyped and demonstrated | No
|  | Achieved | 0 | 0 | 0 | 53 | 0 | 0 | 0
Source
| P5.2: Number of innovative businesses models tested in Africa | Planned | 0 | 0 | 2 | 16 | 39 | 59 | 62 |  | EC, TIME, PEII, CP2, GDC, MGCR, POP |  | No
|  | Achieved | 0 | 19 | 33 | 130 | 0 | 0 | 0
Source
[11 empty] | Component reporting | Comments / challenges | Gender split
INPUTS (£) | DFID (£) | Other public sector (£) |  | Private (£) |  | Total (£) |  | DFID SHARE (%) |  |  | All |  | No
| 67946801 | 16205048.39 |  | 92932970.3 |  | 177084819.69 |  | 69.6%
INPUTS (HR) | DFID (FTEs)
0
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions
Stimulating Technology Innovation by UK Enterprises | 1.1.1 - Number of awards made for promising innovative UK led solutions that have international application. | Planned | 0 | 0 | 15 | 25 | 35 | 40 | 40
|  | Achieved | 0 | 0 | 75 | 86 | 0 | 0 | 0
Source
| 1.1.2 - Number of projects working with international partners | Planned | 0 | 0 | 0 | 0 | 25 | 25 | 25
|  | Achieved | 0 | 0 | 0 | 36 | 0 | 0 | 0
Source
| 1.1.3 - Total number of partners supported | Planned | 0 | 0 | 0 | 0 | 230 | 230 | 230
|  | Achieved | 0 | 0 | 0 | 200 | 0 | 0 | 0
Source
| Output Indicator 1.2 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022)
| 1.2.1 - Total Number of patents submitted | Planned | 0 | 0 | 0 | 0 | 75 | 80 | 80
|  | Achieved | 0 | 0 | 0 | 49 | 0 | 0 | 0
Source
| 1.2.2 - Total number of patents granted | Planned | 0 | 0 | 0 | 0 | 30 | 30 | 30
|  | Achieved | 0 | 0 | 0 | 22 | 0 | 0 | 0
Source
| Output Indicator 1.3 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022)
| 1.3 - Number of published academic peer-reviewed articles | Planned | 0 | 0 | 0 | 0 | 75 | 80 | 80
|  | Achieved | 0 | 0 | 0 | 69 | 0 | 0 | 0
IMPACT WEIGHTING |  | Source | [7 empty] | RISK RATING
INPUTS (£) | DFID (£) | Govt (£) |  | Other (£) |  | Total (£) |  | DFID SHARE (%)
| 15300000 | 16110286.7 |  | 12220428.3 |  | 43630715 |  | 35.07%
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions
Accelerating Enterprise-led Innovation in Technologies and Business Models | 2.1 - Cumulative number of new applications and business models tested and proven | Planned | 0 | 0 | 2 | 10 | 22 | 40 | 40
|  | Achieved | 0 | 19 | 33 | 42 | 0 | 0 | 0
Source
| Output Indicator 2.2 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022)
| 2.2 - Cumulative number of energy policies influenced | Planned | 0 | 0 | 0 | 1 | 2 | 3 | 3
|  | Achieved | 0 | 1 | 1 | 1 | 0 | 0 | 0
Source
| Output Indicator 2.3 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022)
| 2.3 - Cumulative number of financial innovations | Planned | 0 | 0 | 1 | 3 | 7 | 12 | 12
|  | Achieved | 0 | 2 | 8 | 13 | 0 | 0 | 0
|  | Source | [7 empty] | RISK RATING
| Output Indicator 2.4 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022)
| 2.4 - Cumulative number of new corporate partnerships | Planned | 0 | 0 | 0 | 1 | 2 | 3 | 3
|  | Achieved | 0 | 1 | 1 | 1 | 0 | 0 | 0
Source
| Output Indicator 2.5 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022)
| 2.5 - Cumulative Number of consolidated reports on aggregate findings from implementing partners published | Planned | 0 | 5 | 15 | 25 | 35 | 40 | 40
|  | Achieved | 0 | 3 | 20 | 31 | 0 | 0 | 0
IMPACT WEIGHTING |  | Source
INPUTS (£) | DFID (£) | Govt (£) |  | Other (£) |  | Total (£) |  | DFID SHARE (%)
| 30000000 | 0 |  | 60000000 |  | 90000000 |  | 33.33%
INPUTS (HR) | DFID (FTEs)
NOTE: OUTPUT 3.1 RELATES TO PIONEER ENERGY INVESTMENT INITIATIVE 1 WHICH IS COVERED IN OUTPUT 3.3
OUTPUT 3 | Output Indicator 3.2 - Fast Track: Peer to Peer Solar (P2PS) |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions
Clean Energy Partnerships | 3.2.1 - P2P Solar - Investments Made - Number of Investors | Planned | 0 | 0 | 0 | 2341 | 0 | 0 | 2341
|  | Achieved | 0 | 0 | 0 | 961 | 0 | 0 | 961
Source
Crowd Power // Energise Africa Quarterly Report - March 2019
| 3.2 - P2P Solar - Funding raised. - Funds raised | Planned | 0 | 0 | 0 | 3580000 | 0 | 0 | 3580000
|  | Achieved | 0 | 0 | 0 | 2234350 | 0 | 0 | 2234350
Source
Crowd Power // Energise Africa Quarterly Report - March 2019
| Output Indicator 3.3 - PEII 1 & 2 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | *note: these metrics reflect 2018 data for all companies except Orb (India and Kenya), Husk (Tanzania only), and Frontier Markets (cookstoves), where 2017 data has been used. These numbers are for the whole PEII portfolio which includes all active energy companies that Acumen are invested in, and not what can be attributed to the DFID grant. Timeframe: during the 42 month project period. "Active" portfolio companies are those in which Acumen has an existing investment and with whom Acumen actively engages with to support post-investment value and impact creation. Total PEII portfolio at baseline is 18, with 7 inactive companies.
| 3.3.1 - PEII 1&2 - Number of active companies in PEII portfolio. | Planned | 0 | 0 | 13 | 17 | 20 | 18 | 13
|  | Achieved | 11 | 11 | 14 | 15 | 0 | 0 | 0
Source
| 3.3.2 - PEII 1&2 - Number of public facing activities that Acumen or PEII companies participate in to discuss and disseminate learning from research and learning activities. | Planned | 0 | 0 | 1 | 14 | 29 | 44 | 49 | This could include podcasts, blog posts, panels, workshops, and published interviews.
|  | Achieved | 1 | 1 | 33 | 67 | 0 | 0 | 0
Source
| Output Indicator 3.4 - POP |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022)
| 3.4.1 - POP - Number of competition windows designed, developed and approved by RPDC/DfID, with competition documents produced | Planned | 0 | 0 | 0 | 2 | 2 | 2 | 3
|  | Achieved | 0 | 0 | 0 | 1 | 0 | 0 | 0
Source
| 3.4.2 - POP - Number of funded projects under the competition | Planned | 0 | 0 | 0 | 7 | 11 | 12 | 12
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
| Output Indicator 3.5 - CP2 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | -
| 3.5.1 - CP2 - Equity campaigns supported in at least two jurisdictions which facilitate crowdfunded equity investment in energy access ventures | Planned | 0 | 0 | 0 | 0 | 2 | 5 | 15
|  | Achieved | 0 | 0 | 0 | 2 | 0 | 0
Source
| 3.5.2 - CP2 - At least two new credit guarantee mechanism established available to multiple platforms | Planned | 0 | 0 | 0 | 0 | 0 | 1 | 3
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
0
| Output Indicator 3.6 - MGCR |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022)
| 3.6.1 - MGCR - Cost reduction prototypes delivered with mini-grid developers - # workshops with mini-grid developers | Planned | 0 | 0 | 0 | 6 | 21 | 21 | 21
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
| 3.6.2 - MGCR - State of Mini-Grids Market report - Number of meeting, calls etc. held with interested stakeholders (inc. the funders group members) to inform the scope and design of the report | Planned | 0 | 0 | 0 | 3 | 3 | 3 | 3
|  | Achieved | 0 | 0 | 0 | 2 | 0 | 0 | 0
Source
| 3.6.3 - MGCR - Mini-Grid Funders group coordinated by the Carbon Trust (As lead for the RPDC) - Number of MGF group meetings convened | Planned | 0 | 0 | 0 | 3 | 6 | 10 | 13
|  | Achieved | 0 | 0 | 0 | 3 | 0 | 0 | 0
Source
| Output Indicator 3.7 - GDC |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022)
| 3.7.1 - GDC - # of LMDs reporting time or cost-savings as a result of the GDC | Planned | 0 | 0 | 0 | 0 | 20 | 50 | 100
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
| 3.7.2 - GDC - Distributor Support Services - Centralised Purchasing Platform: LMDs benefit from improved margins as a result of centralised purchasing and standardised contracts) - # of LMDs participating in centralised purchasing platform | Planned | 0 | 0 | 0 | 0 | 2 | 5 | 10
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
| Output Indicator 3.8 - PowerUp |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022)
| 3.8.1 - PowerUp - # of trainings delivered through network to NREA board and team members | Planned | 0 | 0 | 0 | 0 | 2 | 6 | -
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | -
Source
| 3.8.2 - PowerUp - # of peer to peer learning opportunities created | Planned | 0 | 0 | 0 | 0 | 2 | 6 | -
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | -
IMPACT WEIGHTING |  | Source | [7 empty] | RISK RATING
INPUTS (£) | DFID (£) | Govt (£) |  | Other (£) |  | Total (£) |  | DFID SHARE (%)
| 10025632 | 0 |  | 18010000 |  | 28560632 |  | 35.1%
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 - LP |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions
Skills and Expertise Development | 4.1.1 - LP - Business plan developed for each course or degree | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 6
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
| 4.1.2 - LP - 3 workshops undertaken with participants from partner universities and external stakeholders | Planned | 0 | 0 | 0 | 0 | 1 | 2 | 3
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
| Output Indicator 4.2 - OGTI |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022)
| 4.2.1 - OGTI - Recruitment of mid-management level trainees for each intake (total target is 300 beneficiaries) | Planned | 0 | 0 | 0 | 0 | 0 | 1 | 2
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
| 4.2.1 - OGTI - Recruitment and placements of interns with host companies for each intake (total target is 300 beneficiaries) | Planned | 0 | 0 | 0 | 0 | 0 | 1 | 2
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Source | [7 empty] | RISK RATING
| Output Indicator 4.3 - LCEDN P1 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022)
| 4.3.1 - LCEDN - Succesful development of new collaborative partnerships | Planned | 0 | 0 | 0 | 3 | 3 | 3 | 3
|  | Achieved | 0 | 0 | 0 | 3 | 3 | 3 | 3
Source
| 4.3.2 - LCEDN - Briefing papers | Planned | 0 | 0 | 0 | 5 | 5 | 5 | 5
|  | Achieved | 0 | 0 | 0 | 5 | 5 | 5 | 5
Source
| 4.3.3 - LCEDN - Placements delivered | Planned | 0 | 0 | 0 | 4 | 4 | 4 | 4
|  | Achieved | 0 | 0 | 0 | 4 | 4 | 4 | 4
IMPACT WEIGHTING |  | Source | [7 empty] | RISK RATING
INPUTS (£) | DFID (£) | Govt (£) |  | Other (£) |  | Total (£) |  | DFID SHARE (%)
| 5000000 | 0 |  | 1157000 |  | 6157000 |  | 81.21%
INPUTS (HR) | DFID (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions
Bio-energy for Sustainable Local Energy Services and Energy Access in Africa | 5.1.1 - BSEAA - Technical reports including a detailed review of all current bioenergy technologies and their suitability to various geographical contexts (e.g. urban, rural, semi-rural) and applications (e.g. domestic, agriculture, industrial, commercial). | Planned | - | 1 | 1 | 0 | 0 | 0 | 0 | Phase 1 complete Inception report, which identifies: (i) confirmation of assumptions; (ii) proposed amendments to approach; (iii) logframe, deliverables and workplan; (iv) expanded methodology; (v) Investigation and analysis protocols Literature Review and Stakeholder Mapping Report showing analysis of academic publications and 'real-life' examples on the ground to identify all existing technologies, programmes and interventions currently deployed in SSA. Technology Value Chain (TVC) Prioritisation Report providing analysis of TVCs including feed stocks, technologies and end uses. 1. Existing level of diffusion, application and commercial potential for at least 1-3 viable bioenergy technologies, mapped against at least 5-10 shortlisted countries in SSA. 2. Research and technical expertise on bioenergy technologies identified, mapped and reported for 3-5 viable technologies and between 5-10 countries shortlisted.
|  | Achieved | - | 1 | 1 | 0 | 0 | 0 | 0
Source
| 5.1.2 - BSEAA - Number of existing bio-energy technologies identified as suitable for further testing in SSA geographical context. | Planned | - | 1 | 1 | 0 | 0 | 0 | 0
|  | Achieved | - | 1 | 1 | 0 | 0 | 0 | 0
Source
| Output Indicator 5.2 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | This output will be reviewed and refined using the initial findings from the academic study to be undertaken within the next reporting period
| 5.2.1 - BSEAA - (Number of case studies to test the technical feasibility and suitability of various bio-energy solutions for various applications (e.g. heating and electricity for domestic consumption, electric power gas or heating for commercial purposes). | Planned | 0 | 0 | 3 | 0 | 5 | 0 | 7-10
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
| 5.2.2 - BSEAA - Number of case studies to test the technical feasibility and suitability of various bio-energy solutions for various geographical contexts (e.g. urban, rural, semi-urban contexts). | Planned | 0 | 0 | 3 | 0 | 5 | 0 | 7-10
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
| Output Indicator 5.3 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | 5 project specific financial assessments covering at least five countries 8 covering at least three countries
| 5.3.1 - BSEAA - Number of quantitative and evidence based studies to test the economic and commercial viability of various bio-energy solutions for various applications against alternative baselines (e.g. heating and electricity for domestic consumption, electric power gas or heating for commercial purposes) and their potential to achieve economies of scale. | Planned | 0 | 0 | 0 | 0 | 1-3 | 5 | 5
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
| 5.3.2 - BSEAA - Number of high quality studies undertaken that identifies and quantify the feedstock availability and type suitability for at least three different bioenergy technologies or application types (e.g. AD, gasification and/or heat only applications) within a SSA country | Planned | 0 | 0 | 0 | 0 | 0 | 3 | 7
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0
IMPACT WEIGHTING |  | Source | [7 empty] | RISK RATING
INPUTS (£) | DFID (£) | Govt (£) |  | Other (£) |  | Total (£) |  | DFID SHARE (%)
| 4450000 | 94761.69 |  | 1020542 |  | 5565303.69 |  | 79.96%
INPUTS (HR) | DFID (FTEs)
OUTPUT 6 | Output Indicator 6.1 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022) | Assumptions
Research Programme Delivery Consortium | 6.1 - RPDC - Overall management of TEA: Successful management of All RPDC components | Planned | 0 | 6 | 6 | 6 | 6 | 6 | 6
|  | Achieved | 0 | 6 | 6 | 6 | 0 | 0 | 0
Source
| Output Indicator 6.2 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022)
| 6.2 - RPDC - Programmatic Reporting over the TEA Portfolio – Quarterly collated and synthesised reports for the whole TEA component portfolio inclusive of updated Logframes. | Planned | 0 | 0 | 1 | 4 | 8 | 12 | 12
|  | Achieved | 0 | 0 | 1 | 3 | 0 | 0 | 0
Source
| Output Indicator 6.3 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022)
| 6.3 - RPDC - Internationally recognised conferences or high level workshop/symposium attended and present at on TEA programme activity | Planned | 0 | 0 | 1 | 3 | 7 | 9 | 9
|  | Achieved | 0 | 0 | 3 | 15 | 0 | 0 | 0
Source
| Output Indicator 6.4 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022)
| 6.4 - RPDC - Number of organisations engaged with through RPDC comprehensive in country engagement in SSA and SA and global energy access innovation communilty | Planned | 0 | 0 | 200 | 250 | 300 | 400 | 400
|  | Achieved | 0 | 0 | 250 | 358 | 0 | 0 | 0
Source
| Output Indicator 6.5 |  | Baseline (Mar 2016) | Milestone 1 (Mar 2017) | Milestone 2 (Mar 2018) | Milestone 3 (Mar 2019) | Milestone 4 (Mar 2020) | Milestone 5 (Mar 2021) | Target (Mar 2022)
| 6.5.1 - RPDC - Coordination meetings undertaken with whole program component portfolio representation and DFID | Planned | 0 | 0 | 10 | 20 | 30 | 40 | 40
|  | Achieved | 0 | 0 | 11 | 21 | 0 | 0 | 0
Source
| 6.5.2 - RPDC - Collated international stakeholder engagement or programme reviewing exercises between components (CEP/SED) | Planned | 0 | 0 | 10 | 15 | 17 | 20 | 20
|  | Achieved | 0 | 0 | 14 | 16 | 0 | 0 | 0
IMPACT WEIGHTING |  | Source | [7 empty] | RISK RATING
INPUTS (£) | DFID (£) | Govt (£) |  | Other (£) |  | Total (£) |  | DFID SHARE (%)
| 3171169 | 0 |  | 0 |  | 3171169 |  | 100%
INPUTS (HR) | DFID (FTEs)