## DIB TA Programme
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | Education Development Impact Bond: Creating an innovative social finance tool
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1: March 19 | Milestone 2: March 20 | Milestone 3: March 21 | Target (March 2022) | Target (June 2022)
Impact Bonds are launched that demonstrate the potential to unlock new forms of social finance capital and shift focus from inputs to outcomes delivery | Number of Impact Bonds designed to achieve the SDGs in developing countries that are launched using learning and tools produced by this project | Planned | 0 | 1 Impact Bond launched (India Education DIB) | Social finance stakeholder map developed for the UK, US and South Asia region | 1 Live impact Bond (India education) 1 new Impact Bond in design phase | 2 Impact Bonds (1 education impact bond & 1 new DIB launched in the South Asia region) | 2 Impact Bonds (1 education impact bond & 1 new DIB launched in the South Asia region)
|  | Achieved |  | India Education IB launched Sept 2018
Source
Contractual agreements with BAT/partners; evidence of launch communications
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1: March 19 | Milestone 2: March 20 | Milestone 3: March 21 | Target (March 2022) | Target (March 2022) | Assumptions
Creation of a stable financing tool for learning, scaling and replication of Impact Bonds | A development impact bond for education outcomes is delivered effectively using financing tools that can be scaled and replicated and generating learning that informs future use of outcome tied funds / impact bonds. | Planned | 0 | Outcomes evaluation, performance management, and legal structure designed. | BAT Education DIB framework is operating effectively | BAT Education DIB framework is operating effectively. | Frameworks utilised throughout the programme period. | Frameworks utilised throughout the programme period | The DIB is implemented without substantial challenge Social, political, and environmental circumstances remain constant to enable implementation of the DIB and this Technical Assistance grant Service partners respond to and engage with the technical assistance provided
|  | Achieved |  | Achieved Milestone 1 and old MS2: IB launched in Sept 2019 with Outcomes Evaluation in place, baseline completed; Legal Structure finalised and performance management oversight operational.
Source
DIB internal reports and reports to DFID; contracts with providers; Steering Committee meeting minutes confirm Outcome verification reports and performance manager activities and reporting is to require quality and fit for purpose.
| Outcome Indicator 2 |  | Baseline | Milestone 1: March 19 | Milestone 2: March 20 | Milestone 3: March 21 | Target (March 2022) | Target (June 2022)
| Financial input (amount in US$) formally committed to development impact bonds that are either in design or launched in the South Asia Region, disaggregated by: (a) investors, (b) outcome funders | Planned | a) $1m committed b) $6m committed | a)$3m committed b)$10m committed | n/a | a) $4-6M (tbc) pledged by investors b) $11-13M (tbc) pledged by outcomes funders | a) $4-6M (tbc) committed by investors b) $11-13M (tbc) committed by outcomes funders | a) $4-6M (tbc) committed by investors b) $11-13M (tbc) committed by outcomes funders
|  | Achieved |  | a) $3m committed b) $11m committed
Source
Meeting minutes; teaming agreements; contracts with BAT
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  | DFID SHARE (%)
| 1500000 |  | 1500000 | 0 |  | 1500000 |  | 100%
INPUTS (HR) | DFID (FTEs)
1.7
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1: March 19 | Milestone 2: March 20 | Milestone 3: March 21 | Milestone 4: March 22 | Target (June 2022) | Assumptions
DIB evaluation and performance management tools designed and implemented | Suitable outcomes evaluation metrics to trigger payments are designed and implemented (outcomes metrics are considered suitable if they reflect the outcome to be achieved while mitigating for perverse incentives and risks of entrenching existing societal inequalities - gender, race, religion, disability) | Planned | 0 | 2 iterations of evaluation model tested November 18: Baseline for 3 service providers completed in November | Outcomes evaluation metrics finalised April 19: First year DIB Results report ready | Final set of outcomes evaluation metrics being utilised April 20: Second year DIB Results report ready | Final set of outcomes evaluation metrics utilised and no perverse incentives emerge. April 21: Third year DIB Results report ready | Final set of outcomes evaluation metrics utilised and no perverse incentives emerge. April 22: Final year DIB Results report ready | There is sufficient supplier capacity to enable the sub-contracts to be implemented to a high level of quality Partners respond effectively to the technical assistance provided All partners (including outcome funders) engage with and support the technical assistance provided Government and other external stakeholders remain supportive of the DIB and technical assistance provided
|  | Achieved |  | Achieved: Evaluation approach piloted in Summer 2018, and baselines completed by Nov 2018.
Source
DIB internal reports and reports to DFID; contracts with providers; Steering Committee meeting minutes; evidence of payments made
| Output Indicator 1.2 |  | Baseline | Milestone 1: March 19 | Milestone 2: March 20 | Milestone 3: March 21 | Milestone 4: March 22 | Target (June 2022)
| DIB Performance Management Framework designed and operationalised | Planned | 0 | Programme management framework designed quarterly management reports (September, December, March) | Programme management framework finalised 4 quartery management reports (June, September, December, March) | Programme management framework utilised 4 quartery management reports (June, September, December, March) | 1 PMF utilised throughout programme 4 quartery management reports (June, September, December, March) | 1 PMF utilised throughout programme
|  | Achieved |  | Achieved - relevant Quarterly Management Reports received for Sep 18, Dec 18 and Mar 19.
Source
DIB internal reports and reports to DFID; contracts with providers; Steering Committee meeting minutes; evidence of payments made
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1: March 19 | Milestone 2: March 20 | Milestone 3: March 21 | Milestone 4: March 22 | Target (June 2022)
50% | Legal structure for the DIB agreed and implemented | Planned | 0 | Legal structure agreed and implemented | Legal structure fit for purpose | Legal structure fit for purpose | Legal structure proves fit-for-purpose throughout programme implementation period | Legal structure proves fit-for-purpose throughout programme implementation period
|  | Achieved |  | Achieved: Legal structure agreed and implemented
|  | Source | [6 empty] | RISK RATING
|  | DIB internal reports and reports to DFID; contracts with providers; Steering Committee meeting minutes; evidence of payments made | [6 empty] | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  | DFID SHARE (%)
| 868007 |  | 868007 | 0 |  | 868007 |  | 100%
INPUTS (HR) | DFID (FTEs)
0.34
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1: March 19 | Milestone 2: March 20 | Milestone 3: March 21 | Milestone 4: March 22 | Target (June 2022) | Assumptions
Creation and dissemination of evidence-based learning and knowledge on the effectiveness of DIBs - in the South Asia region as well as globally | Number of resources created to enable the entry of new funders (public and private) in the impact bond market | Planned | 0 | Learning partner contracted | Learning agenda agreed Publication: India Education DIB Summary Publication: Using performance Management in Education Blog: Yearly Progress Update | Publication: Costings and pricing education outcomes Blog: Yearly Progress Update | Publication: A focus of efficiency Publication: Results of India Education DIB | Blog: Yearly Progress Update | Wider stakeholder community engages with the learning and dissemination events Potential funders (public and private) are responsive to network and engagement activities
|  | Achieved |  | Achieved
Source
Internal and external reports; documentation related to research and survey design; published documents.
| Output Indicator 2.2 |  | Baseline | Milestone 1: March 19 | Milestone 2: March 20 | Milestone 3: March 21 | Milestone 4: March 22 | Target (June 2022)
| Number of unique downloads of learning resources produced | Planned | 0 | Process for monitoring report downloads agreed/implemented | Plan for report production agreed | TBD | TBD | TBD
Achieved
Source
Number of unique document downloads through Brookings website (expect that they will increase overtime, so have as rolling increase across all knowledge products) can also disaggregate by location/organisation if useful
| Output Indicator 2.3 |  | Baseline | Milestone 1: March 19 | Milestone 2: March 20 | Milestone 3: March 21 | Milestone 4: March 22 | Target (June 2022)
| Number of effective learning dissemination events (online and in-person) held to share learning and evidence with relevant audience | Planned | 0 | Learning partner contracted In person event: Presentation of the DIB- UNGA 18 | Programme of learning events agreed Webinar: Impact Bonds for Education- Lessons from India | In-Person Event: Dissemination of Brief- Costing and Pricing Education Outcomes Webinar: Topic TBD | In-person Event: Dissemination of Brief- Results of India Education DIB | 5 learning dissemination events held
|  | Achieved |  | Achieved
Source
Guest list of attendance at events; organisations reached out to/engaged as part of stakeholder mapping. Reporting will include feedback from event evaluation surveys to assess event quality and effectiveness
IMPACT WEIGHTING (%) | Output Indicator 2.4 |  | Baseline | Milestone 1: March 19 | Milestone 2: March 20 | Milestone 3: March 21 | Milestone 4: March 22 | Target (June 2022)
30% | Number of new relationships developed to take forward replication models | Planned | 0 | Initial list of potential partners developed | Social finance stakeholder map developed for the UK, US and South Asia region | Clear partner engagement plan developed to identify potential funders | 2 new outcomes funders brought into the DIB space | 2 new outcomes funders brought into the DIB space
Achieved
|  | Source | [6 empty] | RISK RATING
|  | Internal reports and reports to DFID; evidence of partner commitment and engagement (meeting minutes; teaming agreements);external/press communications on funding | [6 empty] | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  | DFID SHARE (%)
| 269740 |  | 269740 | 0 |  | 269740 |  | 100%
INPUTS (HR) | DFID (FTEs)
0.34
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1: March 19 | Milestone 2: March 20 | Milestone 3: March 21 | Milestone 4: March 22 | Target (June 2022) | Assumptions
Tools developed to enable replication and scaling of DIBs across the South Asia region | Number of feasibility studies completed to assess potential for establishing DIBs in other SDG sectors (such as health, livelihoods, micro-finance, WASH) in DFID priority countries. | Planned | 0 | Selection of countries/sectors for feasibility studies completed Feasability studies in process | Feasibility study report framework agreed 2 feasability studies completed | 1 feasability study completed | NA | 3 feasability studies completed | The wider South Asian region remains stable enough to foster and engage with DIBs Stakeholders and other potential partners engage with DIBs The wider debate and discourse around DIBs remains positive
Achieved
Source
Reports detailing selection of countries/sectors and rationales; evidence (including invoices) of feasibility studies; finalised feasibility reports.
| Output Indicator 3.2 |  | Baseline | Milestone 1: March 19 | Milestone 2: March 20 | Milestone 3: March 21 | Milestone 4: March 22 | Target (June 2022)
| Number of Design documents completed based on the feasibility studies (see outline content in Grant proposal) | Planned | 0 | NA | NA | 1 Design document completed | 1 Design Document completed | 2 Design Documents completed
Achieved
Source
Evidence (including invoices) of proof of concept research; finalised proof of concept reports
| Output Indicator 3.3 |  | Baseline | Milestone 1: March 19 | Milestone 2: March 20 | Milestone 3: March 21 | Target (March 2022) | Target (March 2022)
| Financial input (amount in US$) formally committed to development impact bonds that are either in design or launched in the South Asia Region, disaggregated by: (a) investors, (b) outcome funders | Planned | a) $1m committed b) $6m committed | a)$3m committed b)$10m committed | n/a | a) $4-6M (tbc) pledged by investors b) $11-13M (tbc) pledged by outcomes funders | a) $4-6M (tbc) committed by investors b) $11-13M (tbc) committed by outcomes funders | a) $4-6M (tbc) committed by investors b) $11-13M (tbc) committed by outcomes funders
|  | Achieved |  | a) $3m committed b) $11m committed
Source
Meeting minutes; teaming agreements; contracts with BAT
IMPACT WEIGHTING (%) | Output Indicator 3.4
20% | Deleted as this duplicates the outcome indicator.
RISK RATING
Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  | DFID SHARE (%)
| 362253 |  | 362253 | 0 |  | 362253 |  | 100%
INPUTS (HR) | DFID (FTEs)
1.02

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.

## Change Record
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1 | Outcome Indicator 1 Milestone 2 | Milestone 2 "BAT Education DIB launched with operational Outcomes evaluation, performance management, and legal structure operationalised" was achieved by date of Milestone 1 as the DIB was operational, legally set up with the performance manameent and outcomes evaluation framework in place. Therefore, Milestone 2 has been updated "BAT Education DIB framework is operating effectively (Steering Committee meetings confirm Outcome verification reports and performance manager activities and reporting is to require quality and fit for purpose)." | Jessica Cartwright | 2019-05-16
2 | Outcome Indicator 2 Milestones | Added a more specificity to milestone. | Jessica Cartwright | 2019-05-16
3 | Output Indicator 1.1 | Added more specifity about the timeframe for when the annual endline evaluations outputs are due (April each year). | Jessica Cartwright | 2019-05-16
4 | Output Indicator 1.2 | Added more specificity about programme management framework designed | Jessica Cartwright | 2019-05-16
5 | Output Indicator 2.1 | More specificity added to milestone definitions now that we know what the expected learning outputs are, and their timeframes. | Jessica Cartwright | 2019-05-16
6 | Output indicator 2.2 | No updates to targets but have confirmed that Learning Partner can report on this data, and can also disaggregate by organisation user geography and type. Will base later product targets based on outreach for first product and use as metric to monitor effectiveness of dissemination in key geographies. | Jessica Cartwright | 2019-05-16
7 | Output indicator 2.3 | Indicator milestones made more specific based on Learning Partner contracted outputs and planned briefings, events and webinars. | Jessica Cartwright | 2019-05-16
8 | Output 3.1 | Updated the milestones as were too late and progress is much faster. So milestones now include 2 feasibility studies by MS2 (March 2020) and a third feasibility study in (March 2021). | Jessica Cartwright | 2019-05-16
9 | Output 3.2 | Updated timing of first Detailed IB design documents so that the first is by March 2021, and second by March 2022. This is earlier than the old logframe had planned. The name of the document is changed from "Proof of Concept" to "Design Document". The content expected in the design document are set out in the Grant Proposal Document - but will continue to need to be refined in programming discussions. | Jessica Cartwright | 2019-05-16
10 | Output 3.4 | This was deleted as it duplicated Impact Indicator 1 | Jessica Cartwright | 2019-05-16