Global SME Finance Initiative: Annual Review 2019

Date Programme started: February 2012
Dates review undertaken: 03 December 2018 – 12 February 2019

Annual Review - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Global SME Finance Initiative
Programme Value: £75 million		Review Date: May 2019
Programme Code: 202935	Start Date:28/02/2012	End Date: 31/03/2021

Summary of Programme Performance
Year	2013	2014	2015	2016	2017	2018	2019	2020
Programme Score	B	A	A	A	A	A	A+
Risk Rating	Medium	Medium	Medium	Medium	Moderate	Moderate	Moderate

Summary of progress, lessons learnt and headline actions

Description of the Initiative

The DFID-IFC Global SME Finance Initiative (the ‘Initiative’ or the ‘programme’) aims to bridge the gap in financing to small and medium-sized enterprises (SMEs), especially in more challenging environments and market segments, including fragile and conflict-affected states (FCAS) and women-owned or headed businesses. The Initiative does this by providing direct funding lines, risk-sharing facilities (RSFs) and performance-based incentives and rebates (together, investment services or ‘IS’) with a view to changing behaviour of bank and non-bank financial institutions (together, partner financial institutions, or ‘PFIs’) in lending to SMEs in the target geographies and segments. The Initiative also provides advisory services (AS) – expert knowledge in building capacity of PFIs to better understand and price the risks of lending to SMEs, including supporting specific focus on SME sub-sectors where there is a need (e.g. women-owned SMEs).

In addition, the Initiative supports innovation, and the establishment and strengthening of financial market infrastructure (credit reporting bureaux and development of secured transactions and collateral registries) to address more systemic constraints on SME financing in the target countries. The Initiative also incorporated a third component: a technical assistance pool to fund three of 14 G-20 SME Finance Challenge Winners for scaling up technology-based solutions. This component of the Initiative was completed in 2016.

In light of the completion of this third component, since the annual review in June 2017, DFID provided funding to World Bank Group’s SME launchpad, a collaborative programme of the World Bank and IFC that aims to identify innovative approaches to support early stage and high growth enterprises. DFID currently supports four pilot projects that are directly focused on SME Finance or that have a link to SME Finance. This platform allows the World Bank and IFC to identify and test new ideas with the goal to enhance the productivity of SMEs, support enterprises in fostering growth and achieving scale, as well as to catalyse private sector financing needed for these firms to grow.

At this juncture in the life of the Initiative, DFID is looking for additionality in the following areas: (1) catalysing development finance institutions (DFIs) and private sector lending in support of SMEs, especially in FCAS, (2) women-headed businesses, to drive job creation and women economic empowerment, (3) potential expansion of the geographies supported by DFID funding and (4) systemic impact and sustainability.
The Initiative is a programme implemented by the International Finance Corporation (IFC), part of the World Bank group. DFID is an anchor investor in the Initiative. The Initiative does not involve any new legal entity and is managed through a trust funds structure. The Initiative forms part of IFC’s ‘blended finance’ initiatives. Since the date of the last annual review, the Initiative was transferred from the IFC’s Financial Institutions Group to its Blended Finance Department, which is responsible for overseeing the use of donor funds for blended finance in a consistent, standard manner, quality control, and relationship management. The project under the Initiative will continue to be implemented by staff of the Financial Institutions Group.

Concessional funding from DFID and the Netherlands Ministry of Foreign Affairs has helped mobilise investment from IFC and the European Investment Bank (EIB).

Process of Review

The most recent annual review was completed in February 2018. This annual review is based on the final results data received from IFC in December 2018 which includes results covering portfolio updates from November 2017 (the end date of the portfolio updates for the last annual review) to November 2018 and impact results as of December 2017.

This Annual Review includes findings from four field visits conducted by DFID private sector advisors in Bangladesh, Ghana, Mozambique and Nigeria, the most recent operational report from IFC (delivered to us in December 2018), and interviews with the IFC staff in Washington, DC and its regional staff, the head of the Private Sector Department (PSD), the head of the investment team in PSD, and the adviser in the International Financial Institutions Department responsible for DFID’s institutional relationship with IFC and the World Bank Group.

Current Status of the Initiative

All of DFID’s funding to the Initiative has been committed and disbursed since 2015. Since then, the Initiative has been using reflows from completed projects to support new projects. IFC’s ability to recycle reflows to new investment services projects is constrained by the requirement that reflows from investment services projects be collected prior to the end date of the Initiative (currently March 2021). The average tenor of investment projects exceeds five years and the remaining life of the Initiative is approximately three years. DFID will work with IFC to determine the best use of expected reflows to reflect evolving DFID priorities and other potential changes maximise the impact of the Initiative, See ‘Headline future actions’, below.

Site Visits

As part of this annual review, DFID private sector development advisers in Bangladesh, Ghana and Nigeria conducted site visits in January and February 2019 to together with representatives of IFC. Moreover, one private sector development advisor based in London visited a project in Mozambique with the local IFC representative in December 2018 during a visit to that country on other business.

In Bangladesh, we visited City Bank in connection with an advisory services project funded by the programme. City Bank has traditionally been focused on corporate and retail banking and IFC have been working with the bank across the its retail and SME banking divisions to support the bank’s Vision 2020 focusing on SME finance, retail banking, including women in banking and digital finance. With the support provided through this project:

- The bank has set up a new SME small business division dedicated for sourcing and serving small business clients which was not part of the bank’s strategy or future planning even in 4 years ago. The bank has also constituted a dedicated banking on women team and launched the first ever supply chain finance programme in Bangladesh.
- From December 2018, City Bank has started offering both collateral free and secured loans, in 31 districts. The bank has already disbursed 3,500 million Bangladesh taka (BDT) – approximately £32m – to 3,500 customers through its the new SME network.
- The bank has set up a strong sales governance team to monitor mis-selling and improving service and have focused on sales training and process re-engineering.

The project has focused on the continuing automation of its loan origination process tracking bottlenecks and delays, automation of its collections process to, among other things, facilitate better management of overdue accounts and to support staff skill and capacity building.

In Ghana, we visited Bank of Africa Ghana. The programme has entered into a regional risk-sharing facility with the Bank of Africa Group to support de-risking and scaling its SME lending activities in fragile markets. The programme has supported this project with a first loss guarantee for up to 25% of portfolio risk pooled across ten subsidiaries of the Group (six of which are supported by DFID, including Ghana). Bank of Africa Ghana is a relatively new player in the Ghana banking and SME landscape. Bank of Africa Ghana risk sharing facility from IFC to support overdraft loans to SMEs. Prior to this support, the bank provided limited overdraft loans. Most of the SMEs reached have been women-owned small trading ventures in the retail sector. The risk sharing facility has increased the bank’s appetite to expand their overdraft facilities. The bank has been able to increase SME loans with a limited increase in defaults. As the project continues it will be important to see expansion into other economic sectors

In Mozambique, we visited Vodacom Mozambique and spoke to its managing director to assess progress on an advisory project to develop and implement merchant payments via mobile technology (M-Pesa). Different components of the project are funded by different programme. This project is more difficult in Mozambique than in other countries where mobile payments have been successful (e.g. Kenya). The project is still working on identifying a sustainable business model, particularly in the rural areas of the country and because people ARE frequently changing their mobile telephone provider. Moreover, some people stop using the M-Pesa service primarily because of financial illiteracy issues that prevent them from using the service, such as not having sufficient money in the account to be able to transact. In response, M-Pesa are trying several initiatives. These include using open ‘APIs’ (application programming interfaces) to attract more companies, identifying the right partner in South Africa, the largest source of remittances to the country, partnering with ABC Bank in Mozambique to design savings and ‘microloans’ and merchant payments to build the ecosystem to retain users. Vodacom and IFC have a very good working relationship and Vodacom appreciated the support that IFC has provided through this programme. At the moment, there is a new governor for the Central Bank with whom the project will need to engage. The managing director indicated that additional financial support would be needed in the future.

In Nigeria, we visited the National Collateral Registry (NCR) within the Central Bank of Nigeria (CBN), one of the advisory projects supported by the Initiative, and one of the three licensed credit bureaux, CRC Ltd. Credit Bureau. We visited this project as part of the annual review in 2018.

Officials of the CBN and the NCR stated that all of the target outcomes for the projects were accomplished, including enactment of substantive legislation on credit reporting and secured transactions in movable assets. Over 50,000 transactions secured with moveable assets valued at over N1.5 trillion were registered in the NCR against 154,827 borrowers. In addition, three credit bureaux are now fully functional with coverage increasing from a baseline of 2m at the time the credit bureaux projects were initiated to approximately 15m uniquely identified borrowers, including over 1.5m firms.

The CBN mentioned that the requirement for lenders to perform checks with at least two credit bureaux would be reviewed in line with the provisions of the National Credit Reporting Act. Although in the short-term there might be an impact on the cost of credit because of this requirement, the CBN explained that the requirement was meant in part to support the evolution of a competitive credit reporting industry.

Support provided by the programme has help to integrate over 600 of the entities supervised by the Other Financial Institutions Supervision Department (OFISD) of the CBN, including microfinance banks, into the credit reporting system and enabled the OFSID to get a better view of the sector and its contribution to financial inclusion. In the year to September 2018, credit in the microfinance sector grew from N600bn to N900bn and over 3m borrowers were added to the credit reporting system.

Summary of progress

Overall targets have been met: Although the programme will operate through its expiry date of March 2021, as of December 2017, the programme had achieved all its overall targets. The table below sets out the targets and the results achieved by the programme:

Summary DFID Results / (as of December 2017)
Indicator	Result	Target	Result as % of Target
Number of SME loans	669,298	200,000	335%
Volume of SME loans	US$47.20bn	US$8.00bn	590%
Number of women SME loans	52,297	50,000	105%
Volume of women SME loans	US$2.73bn	US$0.83bn	330%
Number of SME loans in FCAS	174,903	50,000	350%
Volume of SME loans in FCAS	US$13.97bn	US$2.00bn	698%

These results were achieved despite reflecting reports from only 46% of clients (55 clients out of a total of 120 clients). The actual results including those achieved by the clients who had not reported as of the date of the operational report provided to DFID by IFC would increase the performance reported.

The 54 reporting clients are comprised of 46 of 100 (46%) PFIs and 8 of 24 (33%) financial infrastructure projects. The bulk of the results achieved by the programme to date represents the impact achieved by financial infrastructure projects. These projects accounted for 89% and 90% of the reported loan volumes for all SMEs and for women SMEs, respectively, and 92% and 91% of the number of loans to SMEs and to women SMEs, respectively. As more financial infrastructure projects report results and are completed, we expect the reported impacts to increase. We also expect greater impact from the investment projects as risk sharing facilities, which are a more efficient use of donor funds, are emphasised over direct funding lines and as more PFIs report results. Of these results, the credit bureau project in Nigeria and the collateral registry project in India report the largest share. Due to the size of these countries, the overall impact of these projects on results is substantial.

The following table summarises the project data through November 2018 and November 2017:

Project Data
	November 2018	November 2017
1. Total projects	155	118
of which: Investment	55 of 155 (35%)	46 of 118 (39%)
Advisory	100 of 155 (65%)	72 of 118 (61%)
2. Number of DFID funded projects	120	102
of which: Investment	39 of 120 (32.5%)	38 of 102 (37%)
Advisory	81 of 120 (67.5%)	64 of 102 (63%)
3. DFID funded projects in FCAS*	53 (44% of 120 DFID funded projects)	47 (46% of 102 DFID funded projects)
of which: Investment	11 of 53 (21%)	11 of 47 (23%)
Advisory	42 of 53 (79%)	36 of 47 (77%)
4. Total number of PFIs	100	71
5. Number of PFIs - DFID	73	61
6. Total number of countries	34	31
7. Number of countries - DFID	27	26

* According to DFID’s definition of FCAS countries which includes Afghanistan, Bangladesh, Democratic Republic of Congo (DRC), Liberia, Malawi, Mozambique, Nepal, Nigeria, Pakistan, Rwanda, Sierra Leone and South Sudan.

The programme has continued to perform well despite constraints that have been identified in earlier annual reviews: there is no agreement on the use of expected reflows from investment projects and the ability to enter longer-term investment projects is limited by the expiry date of March 2021. IFC and DFID will work to address these constraints as described in ‘Headline future actions’, below.

The programme uses the IFC definition of an ‘SME’, which uses the loan size as a proxy for the size of the enterprise. IFC defines SMEs as firms taking loans between US$10,000 and US$1,000,000; the programme therefore does not track results of loans in the range of US$5,000 to US$10,000. The reported average loan size would be lower if those results had been captured. It is worth noting that the average loan size to SMEs (as so defined) was US$87k and average loan size to women SMEs was US$56k. Therefore, the impact on firms with a smaller size is underestimated and the average loans sizes are likely overstated.

Performing extremely well in reaching SMEs in IDA and FCAS countries: The Initiative has supported a total of 155 projects in 34 countries, of which 120 projects in 27 countries worth over US$1.18bn are funded by DFID. The 120 projects funded by DFID include 39 investment projects and 81 advisory projects (which includes 47 advisory projects to PFIs and 17 financial infrastructure projects). Of the 39 investment projects, 18 are loans to PFIs and 21 are risk sharing facilities, reflecting the increased focus on risk-sharing facilities. Of the 81 advisory projects, 26 projects have been completed, 45 are in implementation phase with the rest in pre-implementation phase or dropped.

Since the last annual review, 8 projects have been completed (all funded by DFID), and 26 new projects have been committed (9 investment services, one of which is funded by DFID and 28 advisory projects, 17 of which are funded by DFID). Because of the issues relating to the short remaining tenor of DFID’s funding, IFC have not been able to devote efforts to develop a project pipeline that could not be funded. However, if these issues were resolved, IFC estimate that approximately US$10-15m could be used to support rebates, risk sharing facilities and loans in DFID priority countries and an additional US$2m could be used for rebates.

All projects funded by DFID are either in ‘IDA-only’ countries – the world’s poorest developing countries eligible for funding from the International Development Association (IDA) – or in ‘IDA-blend’ countries. The IDA blend countries where DFID funding supports projects comprise Nigeria, Pakistan, Kenya and The Republic of Congo. Of the 120 projects funded by DFID, 53 (or 44%) are in FCAS versus a logframe target of 25% (42 advisory projects representing 52% of AS projects and 79% of total projects in FCAS and 11 investment projects, representing 28% of IS projects and 21% of total projects in FCAS). Projects funded in FCAS by DFID under the Initiative total US$29.7m. The total number of SMEs reached in fragile countries and frontier markets was 174,903 representing 350% of the target of 50,000 and approximately 26% of total SMEs reached.

Good performance in mobilising investments in the PFIs in FCAS: Out of the total of 100 partner financial institutions (PFIs) supported by the Initiative, DFID-funded projects under the Initiative supported 73 PFIs of which 24 are in FCAS countries, representing some of the hardest-to-reach markets like Afghanistan, Bangladesh, Democratic Republic of Congo (DRC), Liberia, Malawi, and Sierra Leone. In total, the Initiative is working with PFIs in 9 FCAS countries and is working on building financial infrastructure in 12 markets, including in 7 FCAS countries. The Initiative’s investment and technical assistance supported PFIs in providing £13.97 billion of loans to 174,903 SMEs in FCAS.

Overall targets for volume of loans and number of loans have been exceeded, including the overall targets relating to women SMEs. The Initiative has exceeded the overall targets for volume of loans and the number of loans. DFID funding has facilitated 669,298 SME loans (335% of the target) totalling US$47.20bn (590% of the target). The Initiative also exceeded its overall target for the number of loans to women-owned SMEs (52,297 representing 105% of the overall target of 50,000). The Initiative has significantly surpassed its overall target for the volume of loans to women-owned SMEs (US$2.73bn representing 330% of the overall target volume of US$0.83bn). This indicates that the average loan size for women-owned SMEs is higher than anticipated when targets were set. An increased average loan size for women-owned SMEs is a positive change that indicates a diminishing gender gap in loan sizes among the Initiative clients. More analysis is needed to evaluate the growth in the average loan size for women-owned SMEs. It should be noted that while the Initiative’s work on financial infrastructure (such as collateral registries) does not have specific gender components, it disproportionately helps women borrowers who have fewer fixed assets available to provide as collateral for loans. The financial infrastructure projects take a longer to start reporting results due to the necessary legal and regulatory work that precedes the establishment of credit bureaux and collateral registries, and the time needed for PFIs to develop the appropriate products using these registries. Currently only 8 out of 24 financial infrastructure projects (33%) and 46 PFIs out of a total of 100 (46%) report results, and as more projects become mature enough to report results, it is expected that these projects will show a solid impact, in addition to the results already achieved that have exceeded the overall targets for women SMEs, on access to finance to women-owned SMEs.

The number of SMEs reached: The PFIs supported by the Initiative are estimated to have reached 669,298 SMEs versus a target of 200,000, primarily as more projects are in advanced implementation stage and are able to report results.

Jobs target: Loans to SMEs facilitated under the Initiative are estimated to have sustained and created an estimated 770,692 to 1,075,509 additional permanent direct jobs compared to the milestone target of 700,000. See ‘Main issues or challenges’ for a discussion of job data estimation. Additionally, 1,038,228 to 1,245,155 permanent jobs are estimated to be supported by the Initiative.

Efficiency in use of DFID funding: The total number of PFIs and financial market infrastructure projects supported under the Initiative has well exceeded the logframe targets. This is largely attributable to minimisation in use of DFID-funded subsidy and to the relatively smaller size of projects in FCAS (and IDA countries) than was anticipated in the programme design.

Strong mobilisation of funding from DFIs and the Initiative’s PFIs: Every £1 of DFID concessional funds has helped mobilised over £15 of commercial funding from IFC and other investors. DFID’s concessional funding for the investment component of the Initiative has mobilised approximately £604m (US$967m) of DFI investment.

Funding Mobilised*
	Millions
	US$	£
IFC	749	468
Other commercial funds managed by IFC	90	56
European Investment Bank	100	63
The Netherlands	28	17
Japan	0.3	0.2
TOTAL	967	604

* Based on an exchange rate of US$1.60 = £1.00 (the exchange rate used at start of the Initiative).

Priorities, Innovation and Consolidation: Going forward, the Initiative is focusing on consolidating the progress it has made in reaching SMEs, including in FCAS and women-owned SMEs. Specifically, IFC have developed new approaches to the RSFs provided under the programme, structuring RSFs in a pooled structure where possible to enable the support provided by the RSF to have the maximum impact in additional generating SME loans, particularly those deemed of higher risk whether because of the sector or because borrowers are operating in more difficult environments.

The Initiative is also exploring trade and value chain finance for SMEs, mezzanine finance for high-growth SMEs that would require equity or quasi-equity financing support (currently being piloted in India together with the World Bank and the government of India). The Initiative is working on digital finance innovations for SMEs and is partnering with fintech companies and banks to develop digital finance solutions for SME merchants, such as M-Pesa in Mozambique. For example, it has supported ASEAN Financial Innovation Network, an open network industry platform for banks and financial technology companies with sold governance aiming to onboard at least 6 pilot banks and over 25 fintech companies to test and integrate services via APIs. The programme is also scaling up a fintech ‘sandbox’ pilot in East Asia and looking to potentially replicate this in Africa and MENA regions. IFC is also working to create better data through alternative sources. In Bangladesh, IFC are working to increase the data available against which clients can be scored.

Main issues or challenges faced

Use of DFID resources going forward: Since inception of the Initiative, significant additional resources have supported an increase in financing for SMEs. Several programmes relating to SME financing have been initiated and funded by DFID country offices. Additionally, there is additional support available via the IDA-18 private sector window (PSW) to support IDA-only countries, including its US$600m blended finance and US$400m local currency facilities. Already as risk sharing facilities, rebates, performance incentives and technical assistance have proved to be a more efficient use of donor funds and to have a greater sustainable impact on SME lending by financial institutions than just merely credit lines, particularly in FCAS, the programme has been focusing increasingly on these to ensure they are focused on the most challenging segments. In light of these developments, as discussed below, IFC and DFID have worked on the use of the expected reflows to increase the impact of the programme.

In October 2018, DFID agreed that IFC can use US$10m of reflows from investment projects to support advisory services, including to support the Applied Research and Learning Initiative under the programme. See ‘Headline future actions – Agree use of expected DFID resources’, below.

Achieving scaled impact on gender: As outlined in the summary of the progress of the Initiative, The Initiative continues its focus on scaled impact on gender, which includes a focus not only on women SMEs in the Initiative’s investment projects, but also on financial infrastructure projects that can have a disproportionate positive impact on women SMEs (e.g. collateral registries and credit bureaux) and capturing and providing better quality gender disaggregated data. The gender action plan, improvement on tracking women SME data by PFIs and the expected results seen from the activities under the Initiative in prior years have shown and expected to continue to show a marked improvement in gender results.

Job-creation measurement methodology: IFC have worked extensively to improve the econometric models used to estimate the number of jobs created and supported by the Initiative. IFC has developed two models to extrapolate jobs growth results which it believes give a more reliable indication of jobs created under the Initiative. IFC has updated the models to include more data and to measure jobs supported in addition to jobs created. The current estimates are based on a database of more than 50,000 observations, which is the largest possible database for such indicators. Furthermore, the extrapolation model will be refined throughout the life of the Initiative as more data become available. IFC are working to improve the estimations and have prepared methodology note for jobs extrapolation which is currently being peer reviewed. IFC expect to publish the note in an industry journal in 2019.

Lessons learnt from the Initiative

Concessional support can be catalytic in mobilising DFI investment in challenging environments: DFID’s funding to the investment services component of the programme (US$61.25m in DFID funding, consisting of US$59.48m in original funding and US$1.77m in reflows) have been used alongside funding from IFC to support investment projects totalling US$1,183.5m. DFID funding is supporting 39 investment projects (of which 21 are risk sharing facilities and 18 are loans) in 16 countries.

Financial institutions generally need risk-sharing and technical assistance more than credit lines in lending to SMEs in FCAS: Although in some markets, the lack of funding is a constraint to SME lending, lending to SMEs in FCAS is generally constrained more by high perceived risks and transaction costs and low technical know-how than lack of funds. Risk-sharing helps stimulate the initial appetite of financial institutions to start their SME lending and, over time, develop a better understanding of the risks involved and price their products to reflect the actual risks involved. The technical ability of the financial institutions in FCAS is generally very weak and they need technical assistance in developing systems, processes and products for lending to SMEs. The agreement to allow the use of US$10m of reflows for advisory services will further support financial institutions in their SME business expansion efforts. See ‘Headline future actions’, below.
Women entrepreneurs need more than capital to start and grow business: Women headed businesses are generally smaller than male-headed business and have less access to professional support in running the business. Therefore, they need non-financial services like training and mentoring support in different areas of business, including accountancy, business development, and product design. Non-financial services are presently outside the remit and constrain the Initiative’s ability to support women-headed businesses in a more meaningful way.

IFC representation on governing bodies of banks has a big positive impact: PFIs have expressed the value of IFC’s participation on the governing body. It increases international actor’s trust of the banks and helps facilitate connections with international financers. IFC are also valuable in contributing towards discussions on experiences and difficulties, such as issues with tax which can be communicated via the IFC to governments and central banks.

Loans to under-served SMEs have greater impact on job creation than loans to SMEs that are relatively better served by formal financial institutions: Early indications suggest that loans to first- time borrowers and under-served SMEs are more effective. For example, it is estimated that loans to SMEs in FCAS and low-income countries that were relatively more credit-constrained (e.g. first-time borrowers) created twice as many jobs as loans to SMEs that previously had access to formal commercial loans. The largest amount of growth in jobs within SMEs has been within the smallest firms of between 5 and 15 employees. The larger firms are more likely to have acquired loans in the past and are therefore not reflected in the data being collected.

IFC role is more effective when accompanied by strong engagement through the tenor of the loan than just at the point of disbursement of the loan: Providing lending capital is not enough and the PFIs need continuous technical support in adjusting their risk models to realities of the market. Continued careful attention is required to ensure that capital support is effective in bringing about sustainable behavioural changes. A key aspect of ensuring additionality of IFC support is to promote strong engagement from the IFC contact point designated for partner banks.

Headline future actions

Agree future use of DFID resources: As of November 2017, IFC estimated that from 2017 to the end of the Initiative, reflows from DFID-funded investment projects under the Initiative could be in the range of US$45.9m to US$64.8m with a mid-point estimate of US$57.4m, assuming no change in the end date of the Initiative and no other changes to the structure of the Initiative. To date, IFC have been recycling funds into new investments to the extent possible under the terms of the existing administration agreements governing the operations of the programme.

In October 2018, IFC and DFID agreed amendments to the administration agreements underlying the investment and advisory services components of the programme to allow up to US$10m in reflows (generated by the investment component of the programme) to be used for the following purposes:

- advisory services of the same type as provided have been provided under the Initiative to date;
- research and market building activities (for example, diagnostics and market studies) related to SMEs’ access to finance, women SMEs or related matters;
- activities to promote sharing of learning across PFIs in different countries, whether on a country or regional basis, particularly in the more difficult environments or market segments (such as FCAS and women SMEs);
- financial infrastructure projects (i.e. work on establishing collateral registries and credit bureaux), including additional funding to existing projects and of new credit bureau projects/collateral registries.
- new pilot projects under the SME Launchpad and other initiatives to explore potential technology solutions to increase access to finance by SME and/or improve delivery of finance to SMEs.
- replenishment of the M&E budget for the amounts from this budget used to fund pilot projects under the SME Launchpad.
- additional investment projects – if expected reflows from such projects are expected within the remaining life of the Initiative.

In May 2019, DFID and IFC agreed on the use of the expected reflows. This agreement incorporates updated DFID priorities since the establishment of the programme in 2012, in both regional focus to include the Sahel region and North Africa/Middle East and new areas such as disability and climate. The agreement ensures continued value for money, impact and sustainability. The agreement provides for, among other things, the following:

1. the elimination of DFID caps in respect of one or more countries currently subject to a cap to allow supporting projects in West Africa,
2. the expansion of the geographies in which DFID funding may be used to support activities in South East Asia and MENA, particularly in the Levant,
3. an extension of the end date of the programme from March 2021 to March 2024, to allow the programme time to build the pipeline of projects in the new geographies,
4. the use of reflows from investment projects made prior to the end date of the programme to be collected after such date,
5. the use of reflows after the new end date to be used to support new risk sharing facilities and advisory services.
6. logframe, including milestone and overall targets for the period to the new expiry date of March 2024 and a commitment to work towards tracking impact on disability and inclusion in addition to the existing focus on FCAS, gender and climate. Increased targets are outlined below:

Summary Targets	Original Targets (set in 2012)	2017 Results	Final GSMEF targets (increased since Version1)
			Cumulative GSMEF Targets (Original Contribution + Reflows)	FI & Fin Infra targets consolidated (for reference only)
Total PFIs reached	15	54	125	125
Number of SME Loans (PFIs)	200,000	103,181	300,000	1.70M
Number of SME Loans ( Fin Infra)		566,117	$1.4M
Volume of SME Loans (PFIs)	$8.00B	$9.57B	$25.0B	$120.0B
Volume of SME Loans ( Fin Infra)		$37.64B	$95.0B
Number of Women SME Loans (PFIs)	50,000	9,585	30,000	120,000
Number of Women SME Loans (Fin.Infra.)		42,712	90,000
Volume of Women SME Loans (PFIs)	$825.0M	$587.0M	$1.0B	$5.0B
Volume of Women SME Loans (Fin.Infra.)		$2.14B	$4.0B
Jobs *	$1.0M	923,101	$2.0M	2.0M
* 2017 jobs results represent the average of the low-high end extrapolations

Continue focus on gender: IFC continues to build a strong awareness of working with women SMEs with their PFIs and is seeing results of earlier work with PFIs including work on risk scoring, credit assessment and underwriting. As noted in the mid-year report, the results under the Initiative should not be expected to be linear and we have seen results based upon the earlier groundwork with respect to reaching women SMEs, particularly following the Gender Action Plan adopted by IFC. Although DFID’s initial funding commitments to the Initiative have been fully disbursed, DFID will continue to support IFC’s efforts with PFIs on gender and to strengthen the gender focus under the Initiative. Moreover, women entrepreneurs are constrained by a myriad of factors including but not limited to access to finance. IFC have raised concerns that the Initiative’s inability to provide more direct advisory support to SMEs is a significant limiting factor in IFC’s ability to provide well-rounded (financial as well as non-financial) support that women entrepreneurs need. As an ongoing effort, DFID will encourage IFC to consider partnerships with programmes that work with smaller or informal women SMEs that are working to scale them up. DFID has enabled the use of some resources to advisory services including to women SMEs and will work with IFC to strengthen the performance of the Initiative in this segment and in FCAS. See ‘Headline future actions – Agree use of expected DFID resources’, above.

Promote linkages and share lessons learnt with others: As an ongoing effort, DFID will work to increase the linkages between the Initiative and its other programming, particularly in terms of gender, job impact, financial inclusion and mobilisation of funding, including for example, CDC, Financial Sector Deepening Africa (FSDA), the HiFi programme (an IFC programme addressing financial inclusion in which DFID is active), the ‘billions-to-trillions’ agenda and the Financial Sector Reform and Strengthening (FIRST) programme. The programme team will work on sharing learnings from the Initiative more widely. The M-Pesa programme in Mozambique is an example of collaboration and linkages between this programme and HiFi, where the two programmes are supported different aspects of the project. These two programmes are also supporting the ASEAN Financial Innovation Network (AFIN) launched in 2018 to help accelerate digital transformation of financial services and adoption of innovative technologies by financial institutions across the Asia-Pacific region, with an initial focus in ASEAN countries and Bangladesh. Promotion of linkages and learnings can include, for example, the learnings from the G20 Challenge Winners component of the Initiative and the pilot projects under SME Launchpad, working with other organisations such as the Global Banking Alliance for Women to organise roundtables, disseminating results of research financed by the Initiative on SME finance and other events.

Explore lending and support options in local currencies: Most developing countries face volatility in the exchange rates. Given the lack of appropriate hedging mechanisms in those countries or the high cost of hedging even if available, this volatility poses significant risks to PFIs and SMEs in borrowing in foreign currency. IFC has reported that often the banking sector is not able to provide local currency loans in the target countries. IFC has explored and continues to explore local currency loans and currency risk management support to PFIs in the markets where currency risk is a critical binding factor on SME financing. Challenges in providing local currency options include the pricing gap between local currency and hard currency funding, the availability of currency swaps to enable hedging of currency exposure. The IDA-18 private sector window can enable greater lending and support options for SMEs in local currency going forward. The programme has enabled local currency loans – although not with funds provided by DFID – in the Caribbean and Southeast Asia, both of which lie outside the areas eligible for DFID funding. DFID will continue to work with IFC to seek opportunities to increase local currency activities in Africa and south Asia.

Agree on use of funding provided by DFID Mozambique. DFID Mozambique contributed £2.5m to the Initiative and this funding has been disbursed to IFC. However, due to developments in Mozambique, IFC have not been able to commit the full amount of the funding to projects under the Initiative. As of November 2018, the total committed amounts in Mozambique were to three projects: ABC SME advisory– now completed – M-Pesa Mozambique advisory and BCI SME advisory pre-implementation. IFC have a pipeline for advisory projects which it expects to commit over the course of the next year dependent upon the conditions in the country. There is also a possibility that the existing M-Pesa advisory project will require additional funding for the next stage of the project.

A. Introduction and Context (1 page)
DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3716779.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5351599.xlsx

Summary of Programme

How it works – what it does
The Initiative was created in February 2012 with the objective of increasing access to finance for SMEs, and as a result creating and supporting new jobs. The Initiative supports scaling up of lending to SMEs through partnership with mainstream commercial banks, leasing companies and other non-banking finance companies in developing countries. The Initiative provides banks with risk sharing mechanisms, credit enhancement and technical assistance as well as improved credit history information and referencing in support of scaling up their financing to SMEs.

The Initiative is made up of three components:

1. Risk sharing and investment component (£40m): Combining returnable grants and investments to help scale up lending to SMEs. This is done through (a) the risk sharing, which guarantees to cover up to 50% of the loss suffered by the PFIs in the SME lending portfolio, (b) performance-based incentives to achieve targets, e.g. women headed SMEs and (c) direct funding lines.
2. Advisory Services (£32m): IFC provides capacity building support to the PFIs and support for changes in the broader financial support infrastructure such as collateral registries or credit bureaux.
3. Financing for G20 SME Finance Challenge Winners (£3m) DFID provided funding to three of the 14 G-20 SME Finance Challenge Winners for scaling up technologies which may help SME finance. Part of DFID’s funding contributed to the establishment of the SME Finance Forum. This component is completed. All grants made under this component of the Initiative have been utilised. The final results were shown in the annual review in June 2017 and are also shown in Section C of this annual review, below for ease of reference.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
Results data relating to loans provided, SMEs reached and volume of investments mobilised from DFIs reported in this Annual Review relate to the year ending December 2017. The Initiative has measured these results based on outstanding loans as opposed to disbursed loans starting in 2015. IFC results measurement system also switched to using the Annual Reach Survey to collect data from the PFIs which is based on year-end information.

The performance of the Initiative against the milestone outcome indicators is listed below:

Outcome Indicator 1: Number of SMEs reached with loans, of which (a) 25% to women headed or owned businesses, and (b) 25% in the fragile countries and frontier markets

Results exceeded overall targets: As of December 2017, 669,298 SMEs were reached compared to the logframe target of 200,000. It is notable that as of December 2017, only 8 of 24 financial infrastructure projects were at an advanced enough implementation stage to report results. As these projects mature, more projects will report results and IFC expect the reported SME reach to increase significantly. The programme has already experienced a significant increase in the reported SME reach due to reporting from two large financial infrastructure projects in Nigeria and India. The Initiative has reached 52,297 women owned SMEs versus a target of 50,000 (105% of the target). The total number of SMEs reached in fragile countries and frontier markets was 174,903, in excess of the logframe target of 47,363, representing approximately 26% of total SMEs reached vs a target of 25%.

Outcome Indicator 2: Monetary value of additional principal amount of SME loans made by PFIs through the investment and advisory components of the Initiative and through the development of financial infrastructure, of which (a) volume of loans outstanding to women headed or owned businesses, and (b) 25% in the fragile countries and frontier markets

The Initiative has exceeded its overall targets for the volume of loans facilitated to SMEs, including for women and in FCAS: The Initiative has already met and exceeded its overall target for the volume of SME lending (590%: US$47.20bn versus an overall target of US$8.0bn) including the overall target for FCAS (698%: US$13.97bn versus an overall target of US$2.0bn). The results for women SMEs and for SMEs in FCAS significantly surpassed the overall targets. The Initiative has met its overall target for volume of lending to women-owned SMEs (330%: US$2.73bn versus an overall target of US$825.0m). The monetary value of additional loans to SMEs headed by women at US$2.73bn was more than eight times the set target of US$330.0m. The monetary value of additional loans to SMEs in FCAS (US$13.97bn) exceeded seven times the set target of US$1.8bn. Overall, approximately 30% of the Initiative’s results for the monetary value of loans made have been in FCAS markets, exceeding the targeted 25%.

Outcome Indicator 3: Number of new jobs created and supported by SMEs benefiting from the Initiative

On track to meet the overall target by 2019 of 1 million jobs created: There are limited data on jobs created since PFIs typically do not collect such data from SMEs, and even those that track such data do not use a consistent methodology. To address this issue, IFC developed a jobs extrapolation econometric model to estimate the number of jobs created and supported as a result of the Initiative’s activities. IFC extrapolations indicate that 770,692 to 1,075,509 jobs have been created as a result of the Initiative’s activities versus a milestone target of 923,101. In addition, an estimated 1,245,155 jobs were supported by the SME loan portfolio of the Initiative (compared to a total of 1,038,228 jobs supported in 2016). These results are based on a dataset comprising of more than 50,000 observations, and the multipliers from the econometric model are robust to various regression methodologies and specifications (e.g. Heckman selection model, fixed effects). As a result, the model now is better able to estimate the actual number of jobs which have been created as well as the jobs supported. Furthermore, modelling for jobs growth to predict the number of jobs created shows that the Initiative should be able to comfortably meet its 2019 target of creating one million jobs.

Aggregate Output Score and Description:
The overall composite score across the three programme outputs is estimated at A.

Lessons: Provided in the Summary Sheet
Actions: Provided in the Summary Sheet

Has the logframe been updated since the last review? No. Following the MTR in 2015, the Initiative has redefined its gender targets for the volume of loans and has extended the timeline for meeting its overall targets from 2019 to 2020.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Risk sharing mechanism (s) to catalyse investments from DFIs in the selected PFIs for scaling up SME financing on commercially sustainable basis in the 15 target countries, including in the high-risk environments of fragile/conflict-affected countries.
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	50
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Year 7 / (2018) / Target	Progress (December 2017)	Score
1.1: Cumulative number of Partner Financial Institutions (PFIs) supported with risk sharing and funding mechanisms.	15 PFIs	73 PFIs	A++
1.2a: Volume of additional funding mobilized for SMEs through PFIs under the investment facility component (concessional funding).	£1,516m	£3,185m	A+
1.2b: Investment leveraged from DFIs and PFIs as a multiple of the size of the risk sharing funding from DFID.	£323m	£604m (16x)	A+
1.2c: Share of fragile countries and frontier markets in (a) –see note below	£379m	£845m	A+

Note: The indicator in 1.2(c) includes investment services only. The share of fragile countries and frontier markets supported by advisory services and financial infrastructure projects is much higher – 79% (42/53) of advisory projects are in FCAS vs 21% (11/53) of investment projects.

Key Points
- Almost 5x the number of PFIs/banks and non-banks financial institutions supported. The initiative has exceeded not only the set milestone for indicator 1.1 but also the overall target of the programme. These investments were supported by DFID’s concessional funding of US$61.25m (US$59.48m in original funding and US$1.77m in reflows recycled into new projects) with 18 loans and 21 RSFs.
- The Initiative has met its target for overall volume of SME loans generated. The volume of additional funding mobilised for SMEs £3.185bn exceeded the 2017 milestone target of £1.516bn by 110% and the final target of £1.784bn by 78%.
- The Initiative has considerably exceeded its target to mobilise investment from DFIs. The Initiative has mobilised US$967m (£604m) of DFI investment, exceeding the target of £323m by £281m. Of amount mobilised, US$749m (£468m) came from the IFC, representing a 275% increase from the original commitment of US$200m), US$28m (£17m) from the government of the Netherlands, and an additional US$90m (£56m) of other commercial funds managed by IFC. The European Investment Bank (EIB) made a US$100m (£63m) envelope commitment, primarily for RSFs in Africa.
- The Initiative is working in the most difficult geographies where investment is most needed. The Initiative has significantly exceeded the targets for work in fragile countries and frontier markets, more than trebling the targeted PFIs in FCAS.

Output Title	Capacity of partner banks and Non-Banking Financial Institutions (NBFIs) strengthened through well-targeted technical assistance to partner financial institutions in risk management, product development, and improvement in of business processes, and support for development of financial market infrastructure such as credit bureau and collateral registry in the identified.
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	45%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Year 6 / (2018) / Target	Progress (December 2017)	Score
2.1a: Cumulative number of PFIs and financial infrastructure projects covered with advisory services and activities.	34	71	A++
2.1b: Cumulative number of PFIs and financial infrastructure projects supported with advisory services in the fragile countries and frontier markets	9	47	A++
2.2: Volume of SME loans generated by PFIs / financial infrastructure covered by advisory services plus IFC's non-concessional financing.	£3.2bn	£26.3bn	A++
2.3a Percentage of PFIs reporting that the growth of their SME loan portfolio is greater than the growth of the bank's commercial loan portfolio. / 2.3b Percentage of PFIs with the NPL rates over 10% at baseline that report a lowered NPL ratio (at the SME portfolio level).	(a) 65%-75% / (b) 65%-75%	(a) 73% / (b) 86%	A
2.4a: Number of Credit Bureaux (CBs) and Collateral Registries (CRs) created or significantly strengthened. / 2.4b: Credit Bureaux: / (b1) Total number of firm inquiries / (b2) Total number of loans to firms / (b3) Total value of loans granted to firms / 2.4c: Collateral Registries: / (c1) Number of SME loans by CRs / (c2) Value of SME loans by CRs	(a) 14 / (b1) 65,000 / (b2) 13,000 / (b3) £122.1m / (c1) 45,000 / (c2) £4,896m	a) 16 / (b1) 895,247 / (b2) 95,097 / (b3) £4,856.58m / c1) 471,020 / c2) £18,666.83m	A++
2.5: Number of PFIs provided with technical support for strengthening capacity to identify, screen and support SMEs that either contribute to low carbon and climate resilient outcomes or have neutral impact.	7	15	A+

Key Points

- The Initiative has exceeded the milestone target for the number of PFIs and financial infrastructure projects supported. The initiative has significantly exceeded the target for number of PFIs supported with advisory services.
- During the reporting period, only 8 of 24 financial infrastructure projects reported results. As many projects are in early stages of implementation, we expect results reflected in Output Indicator 2.4 to increase substantially as projects mature over the next several years.
- Advisory services are needed to increase lending to women SMEs. Of the overall volume of loans to women SMEs, 88% come from projects supported by advisory services, which includes financial infrastructure projects: US$2.39bn versus total women SME loans of US$2.73bn.
- Risk sharing activities need the support of advisory services. IFC have stressed that it is very important to provide advisory services to go along with their risk sharing activities. IFC have worked to improve their on-boarding and the PFI’s understanding of the programme to maximise take up and the benefits to the clients.
- Pricing incentives have proved effective at increasing uptake of advisory services. IFC offer performance step-downs where clients get pricing incentives contingent upon their meeting certain targets. This has been effective in driving partners in thinking about their use of funds and the expansion of their programmes. This has also assisted in the creation of very clear commitments which pave the way for the requirement of advisory services.

Output Title	Development of technology-based approaches and solutions to drive SME financing and development in the identified developing countries.
Output number per LF		3	Output Score	A+
Risk:		Minor	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

G-20 Finance Challenge Winners
This component of the Initiative has finished as all challenge winners have completed their projects. The results of this component were set forth in the annual review conducted in 2017 (EDRM 5488068).

Key Points
- Although, this was a relatively small component of the Initiative in terms of share in funds allocated, it is very strategic given the focus on harnessing of innovation and technology in SME lending.
- Good take up of the psychometric tool. One of the challenge winners developed a psychometric tool for use in the credit assessment process. The tool has been adopted by over five times the targeted number of banks and non-bank financial institutions, and over twice the milestone number of SME loan applications have been processed and approved using the tool. This is encouraging given the promise of the psychometric tool, especially in poor countries with weak credit history information sharing mechanism (e.g. credit bureaux).
- Many SMEs in fragile countries have successfully won large procurement contracts.
- Many SMEs have been reached through credit counselling and/or facilitation. The Initiative was able to reach over 15 the targeted number of SMEs through credit counselling and/or facilitation.

## D: VALUE FOR MONEY AND FINANCIAL PERFORMANCE (1 page)

Performance of key cost drivers:

The key cost drivers for both investment and advisory services relate to:

1. Overall program management,
2. Implementation of individual projects and transactions, and
3. Monitoring and evaluation activities.

The Initiative’s delivery model emphasizes partnerships between global and regional teams of the IFC. This model ensures the global team leverages and work closely with the regional managers and staff to select, approve projects, as well as deploy DFID funding. Assigned regional staff are responsible for driving the programme at the regional and country levels, while the global team leads the overall coordination supporting regional teams as needed to ensure sufficient delivery capacity and cost effectiveness.

The Initiative reduces the cost for DFID by utilising IFC’s existing investment apparatus. All investment projects are managed by IFC Investment and Portfolio Officers, with the support from the SME Initiative global team for portfolio-level supervision, oversight and reporting to DFID. The vast majority of the investment costs are funded by IFC or by project fees thus reducing the cost of deal origination and execution for DFID.

The operating expenses for the Initiative’s investment and advisory services components are leveraged by contributions from PFIs, and in the case of investments, other IFIs and investors. These are expected to be further leveraged as the Initiative scales up and the average administrative costs decline relative to the volumes invested.

Overall management fee paid to IFC has remained unchanged and competitive at 4.6% of the overall programme cost, including a 3% centrally mandated Trust Fund Management Fee paid to the World Bank for providing back-stop and trust fund account management support.

Performance against Value for Money (VfM) metrics

The Business Case considered value for money under the specified components listed in the table below. The volume of investment leveraged from DFIs for every pound sterling of funding from DFID substantially exceeded the set target (15.1 vs a target of 8.5). The volume of additional lending to SMEs by DFIs for every pound sterling of concessional funding from DFID also exceeded the set target of £20, at £80. IFC management fees are fixed and have remained unchanged relative to the size of the Trust Fund. Costs are on target even as the number of projects supported by the Initiative exceeds the anticipated number when it was designed.

VfM Indicator	Milestone target (2018)	Results (December 2017)
1) Volume of investment leveraged (£) from DFIs for every £ of funding from DFID.	8.5	15.1
2) Volume of lending to SMEs by PFIs (£) for every £ of concessional funding from DFID.	£20	£80
3) Management costs.	Below 6.4% (£4.8m) of the overall programme size (£75m)	On target

Note: The results in the above table reflect only the investment component of the programme, consistent with Indicator 1.2(a). The programme does not have an indicator for all PFI results, i.e. including advisor services. The management costs are for all components of the programme.
Does the project continue to represent value for money?
The Initiative has used less DFID funding per project than was originally anticipated, reaching the PFIs with 39 investment projects and 81 advisory assistance projects. The number of PFIs supported with investment projects and advisory projects have exceeded the respective targets of 15 and 34 with 39 PFIs supported with investment projects and 81 supported with advisory projects. In terms of jobs, as has been previously explained, the time lag between loans to SMEs to jobs is much longer than was originally anticipated in the Initiative Cost Benefit Analysis. However, the job impact results for this year have exceeded the milestone targets and the Initiative is well on track to meet further milestone and overall targets. As of December 2017, the upper end of the estimated range of jobs created exceeds the overall target of 1,000,000 jobs created.

The Initiative continues to represent good value for money based on the criteria set in the Business Case. The Initiative has met its overall targets in 2017.

E: RISK

Overall risk rating: Moderate
The SME Finance Initiative has a Risk Matrix with a mitigation strategy in place. DFID conducts a detailed risk review with IFC as a part of the annual review process which in 2016 identified three additional risks related to programme delivery. The risk review included a categorisation of risks by category (fiduciary, external context, delivery, safeguarding, reputational) and a rating of the likelihood (rare to probable) and impact (minor to severe) of gross risk and the net risk after accounting for mitigating factors in the Initiative. The risks embedded in the programme are reviewed and updated as necessary between annual reviews to ensure that DFID and IFC discuss and agree any changes, potential new risks or risks which are no longer relevant.

The risks under the Initiative remain stable, with some risks declining with the increasing years of operation of the Initiative. There are three broad primary risks associated with the programme:

Delivery risk: A Central Assurance Assessment (CAA) was carried by DFID’s International Financial Institutions Department over November-December 2015 and IFC has shown to be a low risk delivery partner. IFC is focusing on applying its performance standards more consistently and evenly across its portfolio.

Gender take-up: As a result of previous recommendations, IFC has introduced the Gender Action Plan (outlined in Section F: Gender Considerations, below), following which there was been a marked improvement in gender results.

Results measurement: Throughout the life of the Initiative, results measurement has proved to be challenging due to data availability and data collection issues. This is compounded by the very long lag times for projects to feed through to job creation and has meant many results are extrapolated estimates. A key recommendation from the MTR relating to data collection has been implemented with significant progress being made. There have been improvements in PFIs tracking results by gender, and IFC has offered instruments to improve tracking, including an extrapolations model to help estimate numbers of loans to women-headed businesses. IFC have recruited more staff to ramp up work on M&E and are focused on it, as a key recommendation from the mid-term review.

F: GENDER CONSIDERATIONS

Context
This Initiative is a flagship economic development programme of the Private Sector Department with strong focus on gender. The partnership with IFC has strategic significance and is part of other female economic empowerment initiatives of IFC, for example the Goldman Sachs Foundation-IFC Women Entrepreneurs Opportunity Facility (WEOF) supporting women entrepreneurs in emerging markets.

IFC adopted a gender action plan in October 2015 to improve the gender focus and performance of the Initiative. This has improved the gender performance of the programme. In total, 36 projects out of a total of 120 DFID-funded projects have a dedicated gender component. This represents 30% of the total number of projects and approximately 40% of total DFID funding (US$41.7m out of total DFID funding of US$104.25m (US$61.25m committed to investment projects, consisting of the original US$59.48m contribution plus US$1.77m in reflows and US$43m allocated to advisory projects). The current focus of the Initiative is on building a strong business case for financial institutions to focus on women-owned SMEs and developing a pipeline of projects with a gender component. IFC are committed to working with PFIs to improve tracking, data collection and reporting to enable the Initiative to capture, among other things, the gender-specific performance of the Initiative.

The main actions under the gender action plan include the following:

Stronger Pipeline: The Initiative has worked with IFC’s regional teams to implement its gender business development strategies. IFC have appointed three Gender Champions in Africa and have engaged a Senior Gender Specialist to raise the profile. Of the funding provided to new projects since November 2015, approximately 70% has been to support projects with a dedicated gender component.

New financial products: IFC has successfully worked with supply chain-based financing to target small women SMEs in the distribution chain in Nigeria. IFC are exploring how this approach might be replicated in reaching small women entrepreneurs involved in agribusinesses and other manufacturing activities such as ready-made garments in countries like Bangladesh, Pakistan, Nigeria, DRC and Sierra Leone. IFC’s advisory services also focus on developing and providing non-financial services (NFS) to SMEs through its partner banks. NFS is particularly beneficial to PFIs targeting women SMEs as financial services coupled with NFS is a proven approach to increase the ability of PFIs to acquire and retain women customers. In addition, IFC are looking at how technology may be harnessed to better target women entrepreneurs. For example, IFC are exploring ways that banks can help women to carry out transactions more easily using mobile technology and how payments and cash flow data can be used to design lending products for women entrepreneurs who often lack collateral. IFC are also seeing how PFIs can address other financial services needs of women entrepreneurs better, e.g. with savings and insurance products.

More diversified workforce and management: IFC are also working with the PFIs to help them and their SME clients become better employers of women with a more diversified workforce and management board.

Increased efforts to collect gender data: Starting with the 2015 results, the Initiative has made targeted efforts at collecting gender disaggregated results for all projects. Data on gender is integrated into IFC’s Annual Reach Survey process and all projects are asked to report on number of loans and value of loans to women headed or owned businesses. When clients are not able to report gender disaggregated data, IFC applies extrapolation techniques tailored to the type of project or client to enable estimation of the number and volume of loans to women-owned SMEs.

Research and making the business case for lending to women entrepreneurs: There is ongoing wider research that examines the performance of portfolios of women SME projects compared with those of men which should benefit the Initiative. In order to advance the know-how in financing of women entrepreneurs and women’s economic empowerment in general, the Initiative will have to continue intensive engagements with wider efforts within the World Bank Group and other DFIs to progress knowledge and actions in this area.

Sponsorship of gender-focused activities: IFC has an active partnership with the Global Banking Alliance for Women (GBA) through which it supports knowledge and business development activities to promote increasing access to finance for women. GBA is organising learning events, including the GBA All-Star Academy, a 3½-day skill-building immersion programme for banks that are interested in targeting women, including women owned SMEs. Enrolment is open to senior bank executives with responsibility for new business development, marketing or new customer segments. The All-Star academy focuses on developing holistic value propositions for women, outlining market strategies and best practices for implementation.

IFC have organised roundtable meetings with selected groups of bank CEOs to discuss strategies for targeting the women SME segment in a profitable and sustainable manner. The roundtables include discussions on market opportunities presented by women-owned SMEs, approaches for efficient implementation of a women-focused customer value proposition, as well as examples of successful and bank offerings targeting women-owned SMEs.

Update on projects with a gender component
During the Annual Review period, IFC committed DFID funds to 7 new investment projects and 17 new advisory services projects. On the investment side, all projects (RSFs with six Bank of Africa affiliates and a rebate on an IFC loan to Calbank) have a gender focus. These investments include performance incentives to motivate a higher rate of growth in on-lending to women-owned SMEs, as well as SMEs operating in the climate space. Of the 17 new advisory services projects, all the projects were capacity building advisory services engagements with financial institutions, except for one project which was an upstream/market creation project focusing on women in Tanzania. All advisory services projects are required to report gender disaggregated data which is a considerable shift from our original conditions and require multiple engagements with the client banks to commit to tracking and reporting women SMEs. Four of the projects have explicit gender components in addition to tracking and reporting women SMEs.

IFC’s SME banking advisory has also evolved over time and SME advisory projects in many cases include women’s markets as a segment to target where it makes market sense, without necessarily having an explicit gender component embedded in the project. This is certainly true for projects that include non-financial services as well as those that serve the small and very small enterprise segment.

In addition, client banks tend to focus resources on the women SME segment once they have built out the internal SME capacity – hence for banks that are new to IFC’s advisory services portfolio, a distinct gender component may not materialize in the first engagement. A bank’s focus on women SMEs would generally be after it has built internal capacity in serving SMEs generally and has a growing SME portfolio. However, for these banks to commit to tracking and reporting on gender disaggregated data is a strong first step in the right direction, enabling them to understand what percentage of the current portfolio includes women and, with some help, the potential opportunities in this space.

G: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
DFID’s contribution of £75m has been fully disbursed to IFC in December 2015 and fully committed to activities identified. DFID agreed with IFC in May 2015 to provide a no-cost extension to the Initiative from March 2019 to March 2021 to allow IFC to deploy remaining allocations on deals with tenors of five years or more. As discussed above, the programme has achieved its overall targets in the logframe ahead of schedule and DFID and IFC have worked on the use of the expected reflows to increase the impact of the programme.

Performance of partnership(s)
DFID relies upon IFC’s investment apparatus and operational systems and procedures in implementation of the Initiative. Strategic direction and management oversight is provided by a Donor Steering Committee composed of the donors to the Initiative that meets annually. Additionally, IFC meets with each donor semi-annual in bilateral meetings. There is more frequent engagement between the relevant PSD and IFC staff at the operational level. Overall, the relationship between DFID and IFC is positive. Although in-country coordination between IFC and DFID country offices can be improved, IFC have acted to address this – for example, they have made it routine procedure to meet DFID advisers when on mission to countries with DFID offices and IFC local staff and DFID advisers in country offices interact during visits to projects as part of DFID’s annual review. From the viewpoint of DFID’s project teams, we now share progress reports with DFID country offices and involve them in AR and field visits.

Asset monitoring and control
DFID receives semi-annual operational/progress reports. It also receives quarterly financial statements and high-level information about pipeline of activities along with IFC’s call of funds which provide assurance over the use of programme assets and the implementation of projects.

H: CONDITIONALITY

Not applicable – as the Initiative is delivered through IFC. DFID does not provide any funding directly to financial institutions or the governments of the countries in which the Initiative operates.

I: MONITORING AND EVALUATION (½ page)

Monitoring progress throughout the review period
All projects under the Initiative are subject to IFC’s governance and monitoring and evaluation (M&E) standards. Projects under the Initiative are subject to the same SME results framework and reporting requirements as applicable to all other IFC advisory and investments services projects. Results data for projects funded through this Initiative are collected and reported through the IFC’s Results Measurement Network (RMN). Data for this Initiative go through three stages of IFC’s internal data control and assurance by:

1. IFC’s in-country staff leading on the project who provides quality assurance for the data collected and reported by a PFI;
2. RMN staff for the relevant region, and
3. A senior staff of IFC’s Development Impact Department based in IFC’s head office in Washington, DC.

The data are finally reviewed by IFC’s external quality assurer of impacts and results, Ernst & Young.

IFC undertakes supervision missions to projects and continues to do so over the life of the Initiative so that IFC’s M&E team can verify their results and can engage their clients to get a better understanding of how PFIs’ clients have been impacted by this Initiative. Going forward, IFC has agreed to the following actions:
- including M&E/data reporting clauses in the legal agreements with PFIs, as it is essential for IFC staff to have a legal basis for requesting data
- integrating M&E into project cycles so that questions are being asked at appropriate times in the project cycle, not too early or too late
- maintaining an M&E specialist for the programme to work with regional staff and clients on ongoing M&E, which will also support an ongoing learning agenda
- continuing to communicate with staff and management about the critical nature of the M&E programme and specific demands on staff and clients going forward.

SME Finance Applied Research and Learning
This project builds on the model established by the IFC-Mastercard Foundation Partnership for Financial Inclusion Applied Research and Learning programme. Innovative research and its application to clients led to publication in top-tier academic journals; presentations at international industry and scientific conferences; support to clients to scale operations to new markets and underserved clients; and to understand qualitatively and quantitatively substantiate impact to 13.6 million individuals.

The SME Finance Applied Research and Learning (ARL) programme has three research pillars: (1) scaling within and across markets, (2) improving FSP business models and strategies and (3) understanding beneficiaries and impacts. Each of these will have a cross-cutting research area that incorporates innovation and advanced data analytics. The research team has experience in data science, machine learning and big data methodologies that are needed in these research areas, will work with clients to develop products, segment markets and customers and deliver algorithms that support operations. Traditional research methods will be incorporated into study designs, including randomized control trials, surveys and sentiment analysis and econometric modelling. Qualitative research will be woven into study designs to facilitate understanding behaviour, motivations and socio-cultural factors that influence SME lending in distribution channels. A robust programme to publish, discuss and demonstrate thought-leadership is a core objective. The initial research and knowledge pipeline of the SME Finance ARL programme will focus around two areas of strategic enquiry:

Merchants and supply chains
- Big data SME segmentation and engagement: predictive data product algorithms to support clients to identify businesses on digital channels to target, upsell and engage for business/merchant services. Who are SMEs, how can they be engaged, formal/informal market size. Enhancing and scaling an existing research product. Continuing existing research enquiries to map transaction networks and identify formal/informal supply chains. Client implementation in Tanzania and Mozambique.
- Handbook on Merchants, Payments and Digital Channels: a guidance resource for industry practitioners and clients implementing merchant payment and distribution systems. Building off existing delivery expertise.

Markets and demand
- Understanding SME finance supply and demand in markets (SME market sizing) and developing a consistent methodology to do so with the aim to facilitate SME lending through superior market insights and tools. Tanzania. (1 study – overall research expects multiple studies for multiple countries over program timeline)
- Leveraging financial operational data collected through IFC’s supervision of investment services projects and risk sharing facilities in collating and organising anonymised data to develop an insights dashboard tool to enable investment and advisory programs to visualize and compare bank performance and analyse market performance, risks and lending characteristics.

During 2018, the Initiative, in addition to developing the framework for the ALR, supported the following research studies:

In 2018, IFC produced a report analysing the lessons learned from 20 years of IFC SME Finance work in Sub-Saharan Africa. The report discusses the lessons learned, the successes and the challenges, to inform future SME engagements and make recommendations for practitioners seeking to build their SME banking capabilities. The report additionally describes 15 sector-wide lessons and key take-away messages with insights into specific product and country learnings. The formal report will be launched during the Spring Meetings of the World Bank and IMF in 2019.

Additionally, a new report “The Credit Crunch” was produced to provide an overview of the how the use of movable collateral and credit reporting can help finance inclusive economic growth in Nigeria. The study identified collateral as the missing link between the small-scale business sector and the financial institutions that could provide the necessary capital for them to grow. Smaller firms often lack the assets/collateral required to access formal loans, such as land or fixed property, making them risky clients in the eyes of the financial sector. To improve access to finance and promote inclusive economic growth, the Central Bank of Nigeria, in partnership with IFC, and support from DFID through the Initiative, has established the National Collateral Registry and is supporting the development of a modern credit reporting system in Nigeria. This new financial infrastructure will allow for increased use of moveable and reputational collateral to make it possible for more SMEs to access financing through the formal sector.

SME Financing Gap
In May 2016, IFC and the World Bank launched an update of their original study of the financing gap for micro and small and medium-sized enterprises. The results were presented at the meeting of the IFC Finance Forum in November 2017 and identified a larger gap (US$5.2 trillion) of which incorporates an SME finance gap of approximately US$4.5 trillion and found that 44% of SMEs are financially constrained. Sub-Saharan Africa and South Asia (the geographies of focus for DFID under the Initiative) had an SME finance gap of approximately US$340bn. IFC are working to update these results to estimate the overall size of SMEs and the SME financing gap.

Review Process
- DFID staff engages regularly with IFC with progress reports submitted every six months to monitor the effectiveness of the Initiative. There are more frequent engagements at the operational level, almost on a weekly basis between IFC and DFID.
- Meetings of the Donor Steering Committee, composed of IFC, DFID, the Netherlands Ministry of Foreign Affairs and the EIB are held annually. The last meeting was held in December 2018 at which the donors were updated on the performance of the programme and the donors and IFC discussed priorities and expectations for the coming year.
- Formal bilateral meetings between DFID and IFC are held semi-annually in June and December of each year.

List of Documents
1. Business Case approved by the Secretary of State for International Development in January 2012. EDRM 3716779
2. Audited results at December 2017 reported by IFC against revised logframe indicators. Vault No. 45699805
3. DFID Annual Review Report February 2018 Vault No. 45697032
4. Final Mid-Term Performance Review 08 June 2015 EDRM 5178032
5. Delivery Plan EDRM 5382472
6. Risk Register EDRM 5474826
7. Quarterly financial statement of receipts, disbursements and fund balance as of 30 September 2018 Investment and Services Vault No. 45697589
8. Gender Action Plan EDRM 5172563
9. M&E Plan EDRM 5172580
10. IFC Note on Blended Finance in the Initiative EDRM 5477339
11. IFC Note on Attribution of Results EDRM 5477502 and 5477491
12. Country visit reports (Vault No. 45742647)
13. Evaluation of G20 SME Finance Challenge, Report by Enclude, September 2015 EDRM: 5283334
14. IFC Operational Report, December 2018 (Vault No. 45634935).
15. DRC Advans Case Study, Vault No. 45697590
16. The Credit Crunch – Nigeria Collateral Registry and Credit Bureau project Vault No. 45697177
17. SME Finance – Lessons Learned from IFC Engagement on sub-Saharan Africa Vault No. 45697591