Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: China UK Global Health Support Programme (GHSP)
Programme Value: GBP 12 million		Review Date:12-20 March 2015
Programme Code: 202708	Start Date:Jan. 2013	End Date:September 2017

Summary of Programme Performance
Year	2013/14	2014/15
Programme Score	A	A
Risk Rating	Low	Low

Summary of progress and lessons learnt since last review

Programme activities:

The China-UK Global Health Support Programme (GHSP) is a partnership based on China’s progress in improving health outcomes and its potential to make a greater contribution to global health. The business case is based on the assumption that China has experiences to share with other countries, and that a UK-China partnership will both enhance China’s effectiveness in the provision of development cooperation for health and increase China’s role in global health policy and governance. It takes place at a time of increasing attention to global health by the Chinese Government and the desire of both partners to increase their cooperation on global issues, including cooperation in health and development.

The present review takes place following one year of substantive GHSP activities. The Annual Work Plan includes 34 programme activities with a budget of GBP 2.9343 million.Most components of the work plan are on track: Programme Implementation Agencies (PIAs) have completed their scheduled tasks, and thematic activities such as the Global Health Diplomacy Executive Training Course organized by Public Health School, Peking University have taken place. Some activities have been delayed as a result of the Ebola outbreak in West Africa - notably the Fifth China-Africa Health Roundtable, which will now take place in Beijing (rather than Addis Ababa) in late March 2015. A highlight of the GHSP this year was the Second China-UK Global High-level Dialogue held in Shanghai in November 2014.

Compared with the initiation period in 2013, programme management and operation has been enhanced. The PMO has improved a number of its regulations, rules and procedures, including the revision of Programme Management Manual in line with new regulations issued by the Chinese government. The PMO has organized training for PIA staff to enhance understanding of and compliance with new financial regulations.

A website for the dissemination and exchange of programme activities and results has been established. This seeks to enhance information sharing among PIAs and will help to increase awareness of GHSP more broadly in China.

The Technical Advisory Group has been expanded from 3 to 7 members with expertise covering health aid, public health, international development, social research and other global health related fields. PMO has invited 2 additional national experts to enhance its technical management capacity.

Lessons learned

- It is increasingly clear that GHSP is not a project with a traditional linear structure as implied by the logframe, in which a synthesis of Chinese experience and capacity building leads to increased awareness for policy change, and pilot projects in LICs lead to better health outcomes. Rather, GHSP is better understood in terms of many lines of activity, involving very different institutions, working at different speeds, with several complex linkages between institutions and between outputs and outcomes.
- There exists a very broad spectrum of capacity and awareness among PIAs. At one end are those just beginning to discover the world of health and development outside China and the existence of different types of global organization. These institutions have some way to go to catch up and provide policy relevant inputs. At the other end of the spectrum are those with greater pre-existing global experience and which have a deeper understanding of global health debates.
- The China Global Health Strategy(see Output 3)will be one of the most significant outputs of the project. While the PMO reports that technical inputs are progressing well, it is important that they are more closely geared to what is required by policy makers.
- On capacity building the most obvious need for Chinese officials is to get more exposure to an international working environment. In this way training, research and other activities in country will become more relevant and meaningful. The purpose of proposed pilot projects (output 4) needs also to be seen in terms of exposure and lesson learning in addition to the achievement of better health outcomes. Most pilots likely to be small-scale.
- Lessons on setting up structures for financial accountability in pilots will have broader relevance for the China Global Health Strategy.

Summary of recommendations for the next year

All recommendations and actions are summarised in Section B and set out in more detail under each Output.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme

The China-UK Global Health Support Programme (GHSP)is a partnership based on China’s progress in improving health outcomes and its potential to make a greater contribution to global health. The business case is based on the assumption that China has experiences to share with other countries, and that a UK-China partnership will both enhance China’s effectiveness in the provision of development cooperation for health and increase China’s role in global health policy and governance. It takes place at a time of increasing attention to global health by the Chinese Government and the desire of both partners to increase their cooperation on global issues, including cooperation in health and development. foreign aid.
The GHSP seeks to strengthen China-UK collaboration and build capacity for China to increase engagement in global health. It aims to increase learning from China’s experience of improving health outcomes and reforming its health system and to increase China’s engagement in overseas health aid and in global health governance. It builds on a long history of DFID partnership with Chinese government and is a new phase in China-UK collaboration in health. Similar to a number of contemporaneous programmes, the GHSP gives support to China as a means to increase China role in global health and to increase south-south learning, as well as build a foundation for long-term China-UK partnership.
The project was initiated in September 2012 through a Memorandum of Understanding between the UK Department for International Development (DfID) and the Ministry of Commerce (MOFCOM). A project launch workshop took place in January 2013. Thereafter, over the course of 2013 and early 2014, the newly established Project Management Office (PMO), under the guidance of the Strategic Oversight Committee (SOC), co-chaired by the National Health and Family Planning Commission (NHFPC), MOFCOM and DfID, defined technical requirements, established management systems and conducted a bidding processes for consortia of Project Implementation Agencies (PIAs) that will carry out activities for the three main outputs of the project. A Technical Advisory Group (TAG) made up of experts from China and the UK supports the work of the PMO and SOC.

Impact:China-UK partnership that contributes to improved global health policy and outcomes.

Outcome:UK partnership helps China improve its contribution to global health and achieve the potential of its health cooperation.

Outputs:
1. Increased capacity to distill, disseminate and apply Chinese experience in improving health outcomes and strengthening health systems.
2. Improved understanding amongst Chinese officials and researchers of best practice in international health development cooperation (including bilateral and multilateral).
3. Enhanced capacity of Chinese officials/researchers to contribute to global health policy & governance.
4. Pilot partnerships apply China experience and international best practice in development cooperation in five developing countries that are preferably DFID priority countries and including cross border.

Policy Context

Global Health is increasingly high on the policy agenda in China. In part this is a function of the growing importance attached to involvement in global affairs more broadly on the part of the Chinese leadership, as evidenced by recent developments, including the establishment of the BRICS Bank, the Asia Infrastructure Investment Bank (AIIB) and the One Road One Belt Initiative. Health is seen as an important aspect of this global engagement. In this regard Chinese involvement in the outbreak of Ebola Virus Disease (EVD) has been a game changer[1].
[1] To date China has provided over $120 million in Ebola support and over 800 personnel, with over 1000 to follow in coming months.
The Ebola response provides important lessons for China and GHSP partners in terms of a) the need for a more comprehensive response beyond the provision of doctors, that includes public health and laboratory facilities and liaison with other sectors, including military assets; b) a recognition that China has a valuable role to play in global health security beyond its own borders; and c) an awareness of the complexity of the policy, institutional and cultural dimensions involved in international support.

The rapid evolution of the policy context has important implications for GHSP. First and foremost, it is no longer necessary for PIAs to build awareness of the need for a Global Health Strategy; it is needed as soon as possible and the demands for its completion comes from the highest levels of Government.

Secondly, the growing political importance of global health will generate increasing demands for new research and policy support and GHSP needs to have the flexibility to respond. Emerging research and support needs include: rapid work on lessons learnt from China’s involvement in Ebola, as well as follow-up on issues discussed at the China-UK dialogue (e.g. AMR, positions on global health organizations, neonatal mortality, and the post-2015 agenda).

Acronyms

AIIB	Asia Infrastructure Investment Bank
AMR	Anti-Microbial Resistance
CCUGH	Chinese Consortium of Universities in Global Health
CGHS	China Global Health Strategy
CNHDRC	China National Health and Development Research Centre
DFID	Department for International Development
EVD	Ebola Virus Disease
GHSP	Global Health Support Programme
GoC	Government of China
IET	Independent Evaluation Team
MCH	Maternal and Child Health
MFA	Chinese Ministry of Foreign Affairs
MOFCOM	Chinese Ministry of Commerce
NHFPC	National Health and Family Planning Commission
NIPD	National Institute of Parasitic Disease
PIA	Programme Implementing Agencies
PKU	Peking University
PMO	Programme Management Office
SOC	Strategic Oversight Committee
VFM	Value for Money
WHO	World Health Organisation

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

There has been encouraging progress towards the project outcome over the course of the last year. We therefore record an overall assessment of positive achievements. In particular, we note the enthusiasm of all nine groups of PIAs that we met; a growing awareness and interest in global health issues; and a large volume of substantive work carried out by the various partners.

The PMO has a good understanding of the complex projects they are managing and are producing high-quality documentation, albeit by imposing a somewhat heavy reporting load on PIAs.

We also note that interest in and activities related to global health are not confined to GHSP partners. There are a growing number of institutions in China that are active in this area.

At the outcome level, there is real appreciation in China of GHSP and for DFID’s role - not least in establishing the China-UK High Level Dialogue. Overall, the project is providing valuable learning for both sides and the high-level objective of UK-China cooperation is important for both parties.

Overall output score and description

It is reasonable to expect that the outcome of the project will be achieved. As noted in the Baseline report of the IET some of the outcome indicators are hard to use to show change, given that China is already active in many of the institutions specified. The challenge will be to find ways that clearly demonstrate “China’s development cooperation for health improved to show greater results” (Outcome indicator 3). In many respects the key outcome will be the enduring nature of the partnership itself, beyond the life of the specific activities funded by GHSP.

Key actions/recommendations

- China Global Health Strategy (CGHS):PIAs working on the Global Health Strategy should increase the involvement of other major stakeholders in government including MOFCOM, MOFA and MOF. An agreed outline and agenda of the content and policy decisions should form the basis of ongoing work on the GHS (see Output 3 for more detail). The proposed Flagship course in the UK offers an opportunity to form a cross-ministerial group that will continue to work on strategy development on return to China.
- Research to policy:a) The PMO, working with practitioners and policy makers, should organize a workshop on the preparation of policy briefs. b) In the light of emerging research needs the NHFPC should commission policy briefs from PIAs - clearly specifying the format and content that they require.
- Global Health Network:a) The network should take steps to build awareness of and create links with other partners in China (both universities and others) that have an interest in Global Health; b) it should also take steps to make links with other similar networks in the region - for example the Asia-Pacific Observatory on Global Health Policy and Systems.
- Innovation Fund:The Innovation fund should be used to increase the effectiveness of the Global Health Network rather than be the subject of a new bidding exercise. Its purpose will still be linked to bringing in new partners in China with an interest in global health.
- Capacity Building:Increase the number and range of opportunities to expose Chinese officials to working environment in development cooperation for health and global policy. More detailed proposals are found under output 3 in the Section C.
- Reporting:Until new reporting software in place, SOC should review whether 3-montly reports on activities are necessary and genuinely add value to project management.
- Strategic management:SOC to consider the appointment of support to the Director-General Department of International Cooperation in the National Health and Family Planning Commission to help articulate and ensure the implementation of demands from SOC and to provide day-to-day strategic guidance to project partners.

Has the logframe been updated since the last review?

The logframe has been refined with inputs from the Independent Evaluation Team (IET) and the Technical Advisory Group. Its basic structure, however, remains the same.

## C: DETAILED OUTPUT SCORING(1 page per output)

Output Title	Increased ability to distil and disseminate Chinese experience in improving health outcomes and strengthening health systems that is relevant to Low Income Countries (LIC).
Output number per LF		Output 1	Output Score	A
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Output indicator 1.1	10 individuals + 4 institutes	10 + 4
Output indicator 1.2	27 publications/papers	31
Output indicator 1.3	4 partnerships	12
Output indicator 1.4	4 research dissemination events	7
Output indicator 1.5	1	4
Output indicator 1.6	1	4

Key Points
The budget for Output 1 approved by SOC for 2014/15 and implemented by PIA is shown in the table (RMB 10 000), the implementation data were calculated to March 5th, 2015:

Output 1	PIA	Plan／Implementation
GHSP-CS-OP1-01 / Disease Prevention and Control	National Institute of / Parasitic Disease, China CDC	259.37	105.27
GHSP-CS-OP1-02 / Reproductive Health / Maternal and Child Healthcare	Global Health Institute, / Fudan University	206.82	109.49
GHSP-CS-OP1-03 / Health Systems Strengthening	School of Public Health, / Peking University	271.09	158.56
GHSP-CS-OP1-04 / The Practice and Experience Dissemination of China Integrated Care Pathway and Payment Reform	National Health Development Research Centre	151.64	85.56

Summary of responses to issues raised in previous annual reviews (where relevant)
No specific recommendations were made in first annual review

Findings
A key assumption among several PIAs is that peer-reviewed publications represent the main route for disseminating their findings. While this may hold true for an academic audience, decision makers in government require more concise policy-oriented briefs.

Second, with only limited exceptions most of the research focuses on health alone. PKU is the exception in this regard bringing in components on food safety, environment, trade and international relations as part of their input into the CGHS. There remains a need however to better engage with the other partners (eg. MOFCOM, MOFA and MOF) that will have a stake in the strategy.

Third, most of the international partners that are part of the PIA consortia are also universities and many of the early dissemination strategies feature meetings that remain university-to-university. Broadening the range of partners to others in government, as well as to think-tanks and other institutions working directly on policy in other countries would be of benefit.

Last, we note the advantages in those Chinese institutions where those in leadership positions have come to academia from positions in government. Their impact in bringing direct practical experience of policy to their colleagues is very evident.

Recommendations

The key issue as noted above is to ensure that research findings are presented ways that are more useful for policy makers. We note the great interest in research that focuses on current reforms in China as opposed to purely historical synthesis.

Following the annual meeting, there is a growing awareness on the part of PIAs concerning the needs of the NHFPC. There is a growing awareness that concise policy briefs are needed but there is limited experience in some PIAs (but not all) in how to produce them.

- We would recommend that the PMO, working with practitioners and policy makers, organize a workshop on the preparation of policy briefs.
- We would further recommend, in the light of emerging research needs (see Section 2 above) that NHFPC commission policy briefs from PIAs - clearly specifying the format and content that they require.

Looking to the future, it is important to recognize that many governments - not least the UK - have faced similar problems in securing effective policy and consultancy support from universities. It is also important to recognize that there is a structural problem to be overcome in that incentives in most universities are linked more to the production of peer-reviewed research papers rather than to policy advice.

In the 1990s, the UK faced with similar issues, decided to invest in the establishment of a number of so-called “resource centres”. With modest amounts of core funding, their mandate was to develop policy and consultancy services relevant to the needs of government. Health was a leader in the field. The resource centres that were establish were engaged through competitive tender, but provided professionals with a degree of security, encouraged them to collaborate with universities and others non-university partners and, in effect, provided incentives to ensure that their work met the needs of development officials in government agencies. The challenge in China, where a similar approach has been tried in the context of health sector reform, is to sustain institutions once project funding has finished.

Output Title	Improved understanding amongst Chinese officials and researchers of best practice in international health development cooperation (including bilateral and multilateral).
Output number per LF		Output 2	Output Score	A
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Output indicator 2.1	3 policy papers	4
Output indicator 2.2	5 relevant research projects	7
Output indicator 2.4	10 consultants	8

Key Points
The budget for Output 2 approved by SOC for 2014/15 and implemented by PIA is shown in the table (RMB 10 000), the implementation data were calculated to March 5th 2015:

OUTPUT 2 / Centre of Excellence in HDA	PIA	Plan / Implementation
GHSP-CS-OP2-01	School of Public Health, Peking University	184.94	164.30
GHSP-CS-OP2-02	China National Health and Development Research Centre	132.59	66.34
GHSP-CS-OP2-03	National Institute of Parasitic Disease, China CDC	137.53	86.62

Summary of responses to issues raised in previous annual reviews (where relevant)

The Global Health Network has yet to be officially established but we note progress in this regard below. Coordination between the PIAs involved in OP3 has increased, but could improve further and a functioning network provides an important means to this end. Recommendations with regard to country case studies (in Uganda and Tanzania) have been acted upon. As has the recommendation for the involvement of Chinese officials in events held under the International Health Partnership (two officials, 1 from NHFPC and one from PKU attended the IHP+ Country Team Meeting in Cambodia in December 2014.

Findings
The log frame sees establishment of a Global Health Network as being key to enhancing the ability of Chinese officials and researchers to contribute to global health policy and governance.

Setting up the network was the subject of a meeting that took place during the mission, led by staff from Peking University Department of Global Health. Decisions were made that GHSP PIAs would be the founding members; that an election would take place to decide which institution would initially host the network; that the network would be formally launched later this year; and that membership would expand progressively to include non-health partners from different parts of government and other research organizations with an interest in global health. In particular, the network would also incorporate the Chinese Consortium of Universities in Global Health (CCUGH).

We understand that the meeting discussed the role of the network: focussing particularly on acting as a platform for exchange of information between its members. Its role in coordination would seem more ambiguous, given the fact that university members are likely to be concerned to protect their autonomy. Funding from GHSP is available to finance meetings of the network, whether this extends to support for some kind of secretariat function is less clear.

Recommendations

As the Global Health Network develops we would make two recommendations.

- Firstly, the network should take steps to build awareness of and create links with other partners in China (both universities and others) that have an interest in Global Health[2].
  [2] While a complete mapping of all involved institutions may be too challenging, it will nevertheless be an important resource for NHFPC to have an overview of key institutions and their particular areas of interest.
- Secondly, it should take steps to make links with other similar networks in the region - for example the Asia-Pacific Observatory for Health Policy and Systems Reearch[3].
  [3] The Asia-Pacific Observatory links research institutions with policy makers in several countries. It has hubs in Australia, Japan and China and is supported by the Western Pacific Regional Office of WHO.

Innovation Fund

We see the proposed Innovation Fund as a potential means to increase the effectiveness of the Global Health Network. The initial idea was that a small innovation fund be used to contract other institutions not currently involved as PIAs to conduct additional research. This would involve a further bidding and contractual process and, in our view, risks generating further proposals that have little added policy value.

The alternative, which we support, would be to use the fund as an incentive mechanism to enhance the effectiveness of the Global Health Network once a hosting institution has been agreed. The Fund should not, however, be used by existing PIA members for their own research. Rather, its use would allow the network to carry out a range of secretariat activities beyond the conduct of network meetings: bringing in new partners; commissioning work from new partners that complements or expands existing efforts; making links and holding meetings with other groups within and outside China; and mapping resource institutions in China. If additional resources are available (see also section 10 below) the Innovation Fund could also be used as a channel for commissioning specific pieces of work from network members.

If this approach is approved by SOC, we recommend that the network host, when selected, should be asked to prepare a more detailed proposal along these lines.

Recommendations on capacity building which are equally relevant to this output are found under Output 3

Output Title	Enhanced ability of Chinese officials and researchers to contribute to global health policy and governance.
Output number per LF		Output 3	Output Score	A
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Output indicator 3.1	Network established	Started and ongoing
Output indicator 3.2	5 policy relevant research	8
Output indicator 3.3	Information sharing and mutual understanding	ongoing

Key Points

The budget for Output 3 approved by SOC and implemented by PIA is shown in the table (RMB 10 000), the implementation data are calculated to March 5th 2015:

OUTPUT 3	PIA	Plan / Implementation
GHSP-CS-OP3-01	School of Public Health, Peking University	206.78	179.49
GHSP-CS-OP3-02	School of Public Health, Fudan University	128.52	62.69

Summary of responses to issues raised in previous annual reviews (where relevant)

The China Global Health Strategy, as noted above, is now the key element in this output and activities are now more closely geared to its development.

Findings

China Global Health Strategy: As suggested in the last review the CGHS will be a key outcome of the project. However, while the PMO reports that technical inputs are progressing well, it is important that they are more closely geared to what is required by policy makers. We see two key challenges:

1. To be clearer as to content and format of the CGHS. Beyond a more general review of global health challenges, decisions will be needed as to: where China’s priorities should lie; what objectives it should be aiming to achieve; what level of resources will be required to achieve these objectives; to what extent multilateral versus bilateral channels will be used; how and to what end China seeks to influence global health institutions; the role of non-state actors in health and development; China’s positions in regard to on-going global negotiations[4]; what mechanisms are needed to support new ways of working in countries - particularly those that involve passing resources to non-Chinese institutions. A clear agenda outlining these kinds of decision points for the CGHS is needed. It is a task that GHSP should support.
  [4] The work on preparing for the negotiations related to WHO Report of the Consultative Expert Working Group on R&D: Financing and Coordination in 2016, being carried out by PKU Global Health Department is a good example.
2. The Global Health Strategy needs to be embedded in a broader debate on Chinese global development policy. Even for health, the NHFPC needs to work closely with and seek support from other major players across government, including MOFCOM, the Ministry of Foreign Affairs and the Ministry of Finance. Linkages across the many institutions that are concerned with international development in general and health in particular are a feature of GHS in all countries that have produced such strategies and securing their buy-in often represents the biggest challenge. Cross-sectoral meetings have begun, but there is a need to support this process through good documentation and drafting text for comment. Establishing links with the State Council Development Research Centre (DRC) could be an option to consider. We return to the issue of GHSP support in the discussion of the proposed Flagship Course below.

Recommendations

PIAs working on the Global Health Strategy should increase the involvement of other major stakeholders in government including MOFA and MOF. An agreed outline and agenda of the content and policy decisions (as above) should form the basis of ongoing work on the GHS. The proposed Flagship course in the UK offers an opportunity to form a cross-ministerial group that will continue to work on strategy development on return to China (see also capacity building below).

Capacity Building

Findings
Many of the Chinese institutions in GHSP see capacity building as a key element of this project. In practical terms, however, capacity building is too often seen in terms of training courses.

We particularly noted the work of NIPD in Shanghai and commend their efforts to bring in young trainees from different Provinces. As the Director noted, if this institution is to retain its relevance in a field where many of the communicable diseases with which it has been concerned are rapidly being controlled in China, up to half of his staff in future will need to be working outside China. Preparing them so that they begin to understand the global environment in which they will operate is therefore vital.

We also noted that the Global Health Institute in Fudan Universityis working with University of Manchester on ways of measuring capacity building. This collaboration is also feeding in to the work of the IET.

As a general point on capacity building, however, we would wish to make the point that the most obvious need for all Chinese officials is to get more exposure to an international working environment. Only in this way will training, research and other activities become more relevant. We note with concern in this regard the small number of secondments that have been proposed and the slow progress that has been made on selecting individuals to be seconded under GHSP (only one person has gone to the OECD as far as we are aware).

Recommendations

1. The Flagship Course in the UK. This course offers an opportunity to select participants from those institutions that are key governmental stakeholders in the development of China’s Global Health Strategy. The design and terms of reference for the course should provide a balance between orientation on global development and aid management for health specialists with orientation on health issues for those with a more general development and aid background. The course should be geared as far as possible towards issues relevant to the development of the Global health Strategy. Specifically, we recommend that participants be carefully selected and be given a prior mandate to continue to work together on the strategy when they return.
2. As part of GHSP several groups are preparing to visit low-income countries. We support the proposal that DfID China as a member of the SOC will liaise with relevant DfID country offices well in advance of such visits. The aim being to help introduce visitors to others in the development partner community, ideally inviting them to meetings and providing opportunities to present and discuss their work with a wider audience.
3. The participation of Chinese officials in the County Team Meeting of the International Health Partnership (IHP+) held recently in Cambodia was appreciated by both sides. Work on IHP+, which focuses on aid effectiveness in health, offers many opportunities for Chinese officials to be included in Joint Health Sector Reviews and other similar activities. We would propose that a formal request be made to the IHP Secretariat in Geneva to find opportunities to further involve Chinese officials in these activities, informing the PMO, with adequate notice, when they arise.
4. It is already proposed within DfID that the next health advisors retreat take place in China - this should involve to the extent possible advisers from Africa as well as Asia. We strongly support this idea (also noting that greater awareness of China’s experience is one of the project outcomes).
5. Lastly, we met several individuals in the course of our meetings who would potentially be eligible to apply for positions in international organizations. We propose that the idea of holding a workshop on how to apply for work in global health organizations be considered by GHSP.

Output Title	Pilot partnerships apply China experience and international best practice in development cooperation in Low Income Countries and cross border (probably to include in the first instance Malaria, Universal Health Coverage, Maternal and Child Health, Polio and Human Resources for Health).
Output number per LF		Output 4	Output Score	A
Risk:		Low	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Output indicator 4.1	1 pilot partnership implemented	Contract to be signed soon
Output indicator 4.2	1	Contract to be signed soon

Key Points
Contracts for the two projects under Output 4 are still under negotiation.

Summary of responses to issues raised in previous annual reviews (where relevant)

Agreed, as suggested in last review, that the PKU work on health systems should not be the subject of a specific pilot project. Rather Chinese official should seek opportunities to engage with a wider range of partners in specific countries (notably Tanzania) on the relevance of Chinese experience in areas such as health financing and human resources for health.

Findings
Output four of GHSP focuses on the development of pilot projects that are based on Chinese experience. Proposals are currently being negotiated by PMO with the relevant PIAs (NIPD and Global Health Institute in Fudan University on malaria control and MCH respectively).

In both cases the interventions proposed are small in scale. It is our view that the objectives, while needing to be of value to receiving countries, need to be seen primarily in terms of exposure and learning for the Chinese officials involved.

We note that at a managerial level two key obstacles have to be overcome. One is concerned with tax or overhead payments levied on the total value of the project that cannot be met by DfID. The second concerns accountability for funds that are to be transmitted to and handled by non-Chinese partners. This would appear to be an important issue, not just in relation to these projects, but more broadly, for Chinese aid in the future.

Recommendations

Aid management: While it is not within our competence to suggest how the issues noted above be resolved, we would suggest that this is an aspect of institutional learning of relevance to the Chinese Global Health Strategy to which the experience of GHSP can make a significant contribution.

Dissemination of experience: In addition to the pilot projects, we have noted several other routes through which Chinese experience has been successfully disseminated. These should be taken into account in evaluating GHSP. They include international meetings (for example participation at the recent Health Systems Research event in South Africa), the global schistosomiasis network of which NIPD is a key member, links between individual countries and Chinese provinces (such as Sichuan and Angola), the work on clinical pathways and payment systems in India and South Africa. We also note that several individuals from PIAs are active as consultants aklthough a formal network has yet to be formed.

One further event that links Chinese experience with other low-income countries is the China-Africa roundtable, supported in part by GHSP funds, to be held this month in Beijing (having been postponed and moved from the earlier venue in Addis Ababa as a result of Ebola). This year’s event focuses on access to medicines in the context of Universal Health Coverage. As with previous roundtables the main value will be in ensuring that health gets proper recognition at subsequent ministerial and heads of government events, rather than in term of specific follow-up activities. From the perspective of GHSP, we note with some concern that PIAs are not adequately included as participants and are thus unable to use this platform for the dissemination of Chinese experience.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Budget for 2104/15 approved by SOC is higher than identified in the Busines Case in order to reflect the actual need, the implementation data are calculated to March 5th 2015. See table below:
        (GBP 10 000)
Budget	Output 1	Output 2	Output 3	Output 4	Management	Governance	Evaluation	TOTAL
Plan	89.71	66.29	54.90	44	22.30	13.40	2.8	293.4
Done	67.28	43.90	27.50	0.86	19.83	6.81	8.69	174.89

The low rate of funds implementation are mainly caused by two reasons: funds payment lagged behind of activities implementation (expenses not being settled/calculated in terms of financial accounting even activity had been initiated); activities delayed due to long process of negotiating and signing of contract with collaborators abroad (especially for output 4).

VfM performance compared to the original VfM proposition in the business case
The project has the potential to achieve value for money in terms of its outputs and eventual outcome. A better understanding of current practice in development, reviews of past experience in Africa and exposure to the practices of other development partners are likely to increase the focus of Chinese aid on the achievement of value for money in future. Some projects, in addition, are likely to have an impact on value for money. A good example is the work on using standardised treatment practices and linking these to the performance of providers.

Assessment of whether the programme continues to represent value for money
Yes. The assumption detailed in the Business Case about the potential value for money gains through more effective and efficient Chinese aid remain valid and the risk of Chinese experience not being relevant to LMICs has reduced. Project governance and management continues to focus on value for money and efficiency.
Overall, for a relative modest level of investment DfID can expect significant value from the partnership with China in the area of global health and more broadly in the field of global development. The approach adopted by GHSP is valued and has been adopted in other sectors.

Quality of financial management

Semi-annual and Annual reports for 2014/15 were issued on October 2014 and March 2015 respectively, which stated that “fund expenditure strictly followed relevant regulations in the Programme Management Manual and procedure of disbursement (followed) strictly expenditures and standards control”.

DFID conducted one internal audit visit last year and the China National Audit Office conducted an audit over the expenditures in 2013 during the period from April to June 2014. CNAO issued a disclaimer opinion that states “the financial report was prepared in line with China’s accounting standards and accounting system as well as relevant requirements in the programme grant agreement in terms of all major aspects, which fairly reflects financial condition, financial revenue, programme implementation as well as revenue of the Special Account of DFID’s GHSP grant between 1 January 2013 and 31 December 2013.” This indicates that the financial management meets the requirements. However, auditors pointed out that n order to reduce potential financial risks, PMO reserve the original invoices/receipts when activities are entrusted to other institutions.

In the presentation made by the PMO we noted that many activities are on track and have been completed, but, by contrast, implementation rates for fund disbursements are significantly below what is expected - possibly due to over-budgeting for some activities. The implication, however, is that there remain unspent funds - thereby giving GHSP a degree of flexibility. This may be useful in terms of commissioning new work to address emerging policy and research needs or augmenting the proposed Innovation Fund.
Date of last narrative financial report	15th March 2014
Date of last audited annual statement	30th June 2014

E: RISK (½ page)
Overall risk rating: Low

Overview of programme risk

Continuing work is needed to ensure that the activities of PIAs become more relevant to the need of policy makers. If this does not take place there is a risk that the development of the China Global Health Strategy will take place without significant GHSP inputs.

Outstanding actions from risk assessment

Programmatic risk: See recommendations in Section C, Output 1 on linking research to policy
Financial risk: As noted above following comments from Chinese audit report.

F: COMMERCIAL CONSIDERATIONS (½ page)
Delivery against planned timeframe
Implementation is broadly on track in terms of originally specified products. Capacity building, to bring new partners up to speed such that they can make a significant input into policy will nevertheless take time.

Performance of partnership (s)
The partnerships established are working well.

The PMO imposes a heavy reporting load on PIAs. In some respects this is understandable and it is right to put pressure on PIAs to be accountable for what they are doing.

The proposal to use new software tools to increase real time entry of activity and financial data as proposed to SOC would help lighten the load considerably and introduce a greater degree of transparency.

In the meantime, however, we would recommend that the SOC review whether 3-montly reports on activities are necessary and genuinely add value to project management. It is our impression that semi-annual reports that cover both activity and expenditure should be sufficient.

Asset monitoring and control as of the date of Annual Review

The programme does not involve purchase of significant assets but some computers, printer etc for the programme management office. Procedure for purchase, management and disposals of assets is set out in the programme management mannual. The most updated inventory list is attached in Annex 2.

G: CONDITIONALITY (½ page)
Update on partnership principles (if relevant)
Not applicable

H: MONITORING &EVALUATION (½ page)
Evidence and evaluation
Formal evaluation of GHSP is the responsibility of the Independent Evaluation Team (IET). They have issued a detailed Inception report that sets out the conceptual approach to evaluation. A more recent Baseline study provides an excellent overview of the whole project and the Annual Review Team concurs with their main conclusions concerning the complexity of the project structure and the relationship between outputs and outcomes.

Monitoring progress throughout the review period
The annual review was conducted between 12-20 March and included visits to all nine PIA teams. Feedback from all project stakeholders was very positive and it is clear that GHSP is valued. All major findings were presented to the Strategic Oversight Committee at the end of the mission and initial feedback from the Committee was positive.

Annex 1

Agenda for the 2nd GHSP Annual Review
12-20 March 2015

Date and Time		Topic	Location	Contact Person
Mar. 12th / Thursday	10:00-12:00	Interview with DFID	DFID Beijing Office	Ms. Qiao Jianrong and Ms. Ma Xiaochun
	14:00-17:00	Interview with PIA for OP203	CNHDRC, China National Health Development Research Center	Ms. Wang Yunping, Ms. Fan Xiaodan and Mr Tian Muye
Mar. 13th / Friday	9:30-11:35	Travel to Shanghai	CA1519
	14:00-16:00	Interview with PIA for OP102, OP302 and OP4V01	Global Health Institute, and / School of Public Health, / Fudan University	Ms. Qian Xu, Mr. Chen Wen, Mr. Chen Yingyao, Ms. Huang Jiayan.
	20:00	Interview with TAG Member	Hope Hotel	Mr. Stewart Tyson
Mar.14th / Saturday	9:00-15:00	Interview with PIA for OP101, OP202 and OP4D02	National Institute of Parasitic Diseases,NIPD, China CDC	Mr. Zhou Xiaonong, Mr. Xiao Ning, Ms. Yao Jiawen with 14 other participants
	20:00	Interview with TAG Member	Hope Hotel	Ms. Charlotte Laurence
Mar 15th / Sunday	11:50-14:10	Travel to Beijing	CA1502
Mar 16th / Monday	9:00-12:00	Interview with TAG Member	Weishi Hotel	Mr. Tang Shenglan
	16:00-18:00	Interview with Independent Evaluation Team	Jian Guo Hotel	Mr. Lewis Husain / Mr. Sam McPherson
	20:00	Interview with TAG Member		Ms. Charlotte Laurence
Mar. 17th / Tuesday	10:00-12:00	Interview with PIA-Beijing University for OP103	School of Public Health / Beijing University	Mr. Meng Qingyue and / Ms. Yuan Beibei
	13:00-16:00	Interview with PIA for OP1D04	National Health Development Research Center, Gaode Building	Ms. Zhao Kun Ms. Shi Liwei，Ms. Rita Hou
Mar. 18th / Wednesday	9:00-15:00	Interview with PIA for OP201 and OP301	School of Public Health / Beijing University	Mr. Liu Peilong，Ms. Zhang Tuohong, Ms. Ding Chaochao, Ms.Yin Hui and Mr. Wang Yu
Mar. 19th / Thursday	09:00-12:00	Interview with PMO	Center for Project Supervision and Management, NHFPC	Mr. Zhang Chaoyang and Ms. Yu Yang with 8 PMO staff
	15:30-16:30	Interview with SOC Member	Department of International Cooperation, DIC, NHFPC	Mr. Ren Minghui and / Ms. Li Juan
	17:15-18:45	Debriefing at DFID	DFID Beijing Office	Ms. Qiao Jianrong and / Ms. Ma Xiaochun
Mar. 20th / Thursday	09:00-12:00	Drafting Report & Template	Jian Guo Hotel
	1:30-14:30	Debriefing at SOC meeting	Gehua New Century Hotel	Mr. Ren Minghui, Ms. Qiao Jianrong, Ms Liang Hong, Mr. Zhang Chaoyang

No	Procurement	Item	Specification	Unit
1	GHSP-GS-01 Electronic office equipment	Desk-top computer	ThinkCentre M6400t	8
2		Lap-top computer	ThinkPad T440p 20AN002JCD	16
3		Mobile hard-drive	WDBY8L0020BBK-PESN	16
4		Color printer	Epson R3000	1
5		Portable printer and copy machine	HP 1213nf	1
6		Digital camera	Canon 60D	1
7		Web service	IBM X3300 M4（7382I01）	1
8	GHSP-GS-02 management software	Finance management software	GRP-U8	1
9	GHSP-GS-03 interpretation equipment	Portable transmitter	WT-080T	2
10		Portable receiver	WT-080T	20

Annex 2

Asset Inventory