Annual Review – Summary Sheet

Title: / Infrastructure and Cities for Economic Development (ICED)
Programme Value £ (full life): £33,500,000 (of which £8M ICF)		Review Date: 26 April 2019
Programme Code: 204250	Start Date: March 2015 / (with varying dates for implementing partners)	End Date: July 2020 / (implementation period 5 years, / with shorter periods for individual components and partners, including ICED Facility)

Summary of Programme Performance
Year	2015/16	2016/17	2017/18	2018/19	2019/2020
Programme Score	A	A	A	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate

[1]
DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204250
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204250

A. Summary and Overview

Description of programme

DFID is providing £33.5 million to the Infrastructure and Cities for Economic Development (ICED) programme over five years, from March 2015 to July 2020.

This project supports DFID and our development partners through:
- Improving the enabling environment for sustainable, inclusive growth-enhancing infrastructure service delivery in DFID focus countries; and,
- Harnessing the benefits of cities for sustainable economic growth and poverty reduction in DFID focus countries.

Some of this work is delivered by assisting DFID Country Offices to scale up bilateral programming; other work is focused on international influencing and delivery of global public goods, in addition to cross Whitehall working to strengthen the UK offer on infrastructure.

The expected impact is: An improved enabling environment for infrastructure service delivery and better managed and governed cities as drivers of inclusive economic growth in DFID focus countries.

The expected outcome is: DFID scales up, enhances coordination and improves the quality of its country/regional/central-level support for an improved enabling environment for infrastructure and planning for cities (including in our most fragile and conflict-affected states). This will be achieved through the following outputs and partners:

At the country level, and to support DFID’s policy globally:
Outputs 1, 2 & 3 - The ICED Facility includes PWC, Adam Smith International, Engineers Against Poverty, the International Institute for Environment & Development, Social Development Direct, MDY Legal and ARUP. To deliver the Economic Development Strategy (EDS), DFID needs more high-quality infrastructure and cities programmes at country level. This Facility provides support to DFID Country Offices and central/regional departments to develop new, and improve existing, infrastructure enabling environment and city economic development programming.

At the global level:
- Output 4 - Scale up and enhance the impact of CoST activities to reduce corruption and increase value for money in public sector funded construction projects;
- Output 5 – Supported the World Bank’s Enhancing Economic Performance of African Cities programme - to support economic growth in 4 cities in Africa – this component is now closed.
- Output 6 - Shape the strategic priorities of the Cities Alliance and develop and implement its Economic Growth programming.
- Output 7 - Strategic Opportunities Fund (SOF) – to enable additional high priority activities that support this programme’s objectives. The use of the SOF is agreed with the ICED SRO and approved by the Head of DFID’s Growth and Resilience Department.
- Output 8 - support the Coalition for Urban Transitions – which seeks to build the case for national level support to urban development in developing countries. This component was established in April 2017.

The programme components are designed to be complementary, building on each other’s outputs where applicable.

Summary supporting narrative for the overall score in this review

The overall programme score is A+.

The ICED Facility continues to achieve its log frame targets. The successful implementation of the ‘Strategic Pivot’ – which was designed to enable greater prioritisation and strategic engagement with priority countries and teams – has delivered increased demand for the Facility’s services from across DFID and UK Government with output indicators increased accordingly. It has developed key Knowledge and Learning products for DFID-wide utilisation in the form of the Whole Systems Approach tool for the energy sector, supported DFID’s Country Development Diagnostics, and delivered 17 studies to support DFID and other government departments to strengthen existing programmes or inform new ones. As the Facility comes to an end, attention will be focused on developing an appropriate exit strategy which ensures sustained impact of the Facility beyond the lifetime of the contract.

Cities Alliance, and the Coalition for Urban Transition (CUT) are all moving towards their expected outcome indicators. Resources produced by the Cities Alliance received extensive attention at global forums and importantly, also at the local level. The Infrastructure Sector Transparency Initiative (CoST) has made excellent progress in surpassing a cumulative total of 24,000 projects where data has been disclosed in the Infrastructure Data Standard (IDS) format.

Overall output score and description:
Output 1: ICED Facility (1)	A+	(impact weighting 30%)
Output 2: ICED Facility (2)	A+	(impact weighting 10%)
Output 3: ICED Facility (3)	A+	(impact weighting 20%)
Output 4: CoST	A	(impact weighting 20%)
Output 5: World Bank	A	(2018, awarded at completion of component)
        (impact weighting 5%)
Output 6: Cities Alliance	A+	(impact weighting 5%)
Output 7: Strategic Opportunities Fund	A	(impact weighting 5%)
Output 8: Coalition for Urban Transitions	A	(impact weighting 5%)

Annual outcome assessment

As the ICED programme moves towards completion in the coming 18 months, emphasis will shift from assessing outputs to the outcomes listed in the Theory of Change for the programme. The ICED Facility is on track to meet its outcomes, and has met or exceeded all this year. CoST is off-track in terms of new members, despite achieving an “A” at output level, and the ToC and targets will be reviewed. Both Cities Alliance and the Coalition for Urban Transitions are reporting to be on-track against outcomes, and will be undertaking reviews next year to more broadly assess how they have achieved their outcomes.

Recommendations for the year ahead

Overarching Programme
ICED Facility and DFID team to hold a workshop reviewing the Facility’s ways-of-working and development over the past four years, with key points to be captured in an internal learning document, as part of the close-down activities and to feed into the design of a successor programme.

ICED Facility
- Strategy and DFID engagement:
  - Use remaining months to support DFID central teams, Country Offices as they scope new programmes and support the UK Overseas Development Assistance (ODA) `offer’ related to infrastructure and urban development;
  - Focus remaining core budget on strategic Call Down Facility (CDF) engagements and continue to attract co-financing from the Facility’s clients in order to maximise outreach;
  - Develop a programme exit strategy by end April 2019;
  - Recognising the pipeline of Facility support to potential business cases in Year 5, maximise the opportunity for including climate and environment in the work of the ICED Facility.

- Knowledge and Learning:
  - Continue to deliver relevant and high-quality knowledge events;
  - Develop an accessible compendium of Facility deliverables from Years 1 -5;
  - Consider legacy arrangements for Facility deliverables from Years 1-5, and the Facility’s website;
  - Share the Facility’s ICF attribution methodology with DFID as an example of clear guidance and methodology for assessing ICF eligibility.

Other Components

Strategic Opportunities Fund (SOF): the DFID programme team should review options for appropriate use of remaining funding by the end of July 2019 and decide whether the funding should be allocated to specific opportunities or returned to the central DFID budget.

## B: DETAILED OUTPUT SCORING

Output Title	ICED Facility - High quality technical assistance (TA) provided by ICED Facility to DFID teams (country office, regional and central) to facilitate the delivery of new and improved existing programmes, initiatives and partnerships
Output number per LF		1	Output Score	A+
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1a Number of active TA substantive interventions (SI) supporting DFID or OGD teams to scope or strengthen new or redesign existing, programmes, initiatives, partnerships, approved by the DFID or OGD client.	Year 4: 14	Exceeded: 16
1.1b Number of Business Cases (BC) supported and/or strengthened by ICED, approved by the DFID or OGD client.	Year 4: 1	Met: 1
1.2 Number of DFID or OGD programmes that have adopted ICED developed tools and/or programme approaches.	Year 4: 14	Exceeded: 17
1.3 Number of successfully delivered short term engagements and advice, for example through call-down requests (not including large scoping studies).	Year 4: 11	Exceeded: 12

N.B: New indicators and stretch targets as agreed with DFID following the contract replenishment.

Key Points

In Year 4 the Facility’s mandate has remained prioritised in its support of DFID central departments and Country Offices. However, there has been an increased focus on: (i) working across UK Government, and (ii) seeking funding from other DFID teams and Other Government Departments (OGDs) who commission work packages. The Facility has seen an increase in demand in Year 4, successfully meeting new stretch targets for this year.

Due to the high demand seen from DFID departments, and an increasing desire from OGDs to access the Facility’s services, the DFID team decided to increase the funding available to the Facility, and Facility was allocated an additional £700,000 of core funding in December 2018. Alongside this, the contract was amended to enable OGDs to commission services from the Facility on a paid-for basis, with a maximum total value of £1.5m additional “headroom” available for external-funded commissions.

This increased funding and widened range of cross-Government clients has led to a range of new topics and work beyond those areas initially anticipated, and the ability of the ICED Facility to increase their work in emerging priority areas such as safeguarding and disability.

Key highlights included:

- Supporting new or improved programming through 16 work packages, which scoped new programmes, as well as strengthening or redesigning existing programmes
- Reaching new clients across DFID and in other government departments. This included the Private Infrastructure Development Group (PIDG), advisors in DFID’s Private Sector Department; support on Foreign and Commonwealth Office (FCO) China Prosperity Fund Business Case; and working across UK Government to map Overseas Development Assistance (ODA) infrastructure programming
- Completing scoping studies in four countries (Ghana, Nepal, Rwanda and Sierra Leone) to inform design of the next phase of the Cities and Infrastructure for Growth (CIG) programme
- Working with advisers in Growth and Resilience Department (GRD) and Country Offices in Uganda and Rwanda on Safeguarding. With DFID Pakistan on the Pakistan Economic Corridors Programme mobilised in Y4-Q4, with the first phase of work on providing Safeguarding support;
- Undertaking a number of Call Down Facility (CDF) engagements, providing rapid-response support on disability and at various international multi-donor events, including hosting a roundtable on disability with PIDG and CDC Group which subsequently led to mobilisation of further Work Package on Disability Inclusion with GRD;
- The Facility delivered a Business Case for a future Water, Sanitation, and Hygiene (WASH) programme with DFID Ethiopia.

Summary of responses to issues raised in previous Annual Reviews

The recommended implementation of the ‘Strategic Pivot’ resulted in a raised demand and an increase in work packages delivered. The DFID Senior Responsible Owner (SRO) decided against establishing a Strategic Advisory Panel at this stage in the programme, but has played a significant role in providing direction, support with demand raising, and disseminating outputs across DFID and other government departments.

Roundtables on disability were held with PIDG and the CDC Group, and the Facility subsequently worked with PIDG on the development of a Gender and Inclusion Ambition Framework and the development of a tool for the Infracredit. There are ongoing conversations with CDC and their investment team to consider how the Facility could provide further support.

Fortnightly management meetings have been restructured to promote a greater focus on strategy and management. This has enabled a wider range of participants to join relevant meetings including Head of Profession (HOP), and for advisors leading on particular themes to join on a needs basis.

The Facility has also responded positively to a number of practical recommendations:
- The Terms of Reference (ToR) development process has been refined to produce a tiered approach reflecting the appropriate level of effort for different types of request.
- 5 out of 6 of the Facility’s portfolio managers have not changed throughout Year 4. The Facility has continued to deliver using a good balance of expertise by using staff with established knowledge of the Facility’s ways of working versus those with a niche technical expertise.
- The Facility continues to deliver a high quality level of engagement through the entire cycle of Work Package delivery. This is reflected in Year 4 feedback surveys, by clients, providing an average Key Performance Indicator (KPI) scores for quality of 7.5/10.

Recommendations

- Build on the Facility’s ongoing work to support UK Government/ broader UK `offer’ on ODA spend related to infrastructure and urban development, both centrally and in specific countries, across FCO, Department for International Trade (DIT), PIDG, Department for Business, Energy, Innovation and Skills (BEIS) and CDC.
- Focus remaining core budget on the CDF type of Facility engagement to prioritise opportunities with high likelihood of achieving strategic outcomes, and aligned with DFID’s priorities.
- Continue to attract co-financing from the Facility’s clients in order to maximise delivery.
- The Facility should develop a programme exit strategy by the end of April 2019, to ensure that the impact of its outputs and knowledge products is maximised.

Output Title	ICED Facility - High quality TA provided by ICED to DFID teams (country/regional/central) to facilitate increased access to ICF funding
Output number per LF		2	Output Score	A+
Impact weighting (%):		10%	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
2.1 % of ICED-supported business cases that are ICF compliant	Year 4: 100%	Met: 100%
2.2 % of ICED-supported programmes that are ICF compliant having ICF KPIs	Year 4: 100%	TBC due to ongoing programme development
2.3 % of £ value of DFID or OGD approved Business Cases in infrastructure/urban development supported by ICED classed as ICF eligible	Year 4: 25%	Exceeded: 50%

Key points

The Facility ensures all Business Cases it prepares are fully International Climate Finance (ICF) compliant and are reviewed to ensure climate and environment are accounted for, including a ‘do no harm’ risk assessment. ICF-relevant indicators and themes are promoted where appropriate, particularly where these provide programming opportunities and enhance the socio-economic narrative.

The Facility supported DFID Ethiopia to develop a C&E relevant WASH Business Case: Strengthening Climate Resilient Systems for Water, Sanitation and Hygiene Services, Ethiopia. This Business Case focused directly on addressing the challenges of climate impacts on the water sector in the country, and was assessed to be 50% ICF relevant.

It should be noted that the Facility delivered a further 9 Work Packages to support country level programme design (both early scoping and post-business case implementation). All of these Work Packages were ICF compliant. However, there was variability in the extent to which climate and environment aspects were captured.

Summary of responses to issues raised in previous Annual Reviews

The Facility met with the ICF Secretariat in Year 4 to discuss its ICF methodology to ensure it adequately strengthens the assessment of ICF attribution. This was confirmed by the Secretariat.

The Facility engaged more systematically with the Climate and Environment Cadre to ensure the Facility’s offer to DFID in this area was sufficiently robust. The Climate and Environment Department (CED) commissioned work to understand the effect of ocean plastics for the Commonwealth Heads of Government Meeting (CHOGM). CED was also a key stakeholder within Middle East and North Africa Department’s (MENAD) climate assessment of its portfolio that the Facility undertook in Year 4.

Recommendations
- Continue to prospectively and retrospectively assess ICF contribution within the Facility’s Work Packages;
- Continue to share the Facility’s ICF attribution methodology with DFID as an example of clear guidance and methodology for assessing ICF eligibility.

Output Title	ICED Facility: Knowledge management, research and policy influencing mechanisms in place to improve the basis for international dialogue and action on the infrastructure enabling environment and cities that drive sustainable, inclusive growth
Output number per LF		3	Output Score	A+
Impact weighting (%):		20%	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
3.1 Number of peer reviewed knowledge products (KPs) delivered by ICED	Year 4: 20	Exceeded: 36
3.2 Number of active learning sessions led by ICED (i.e. Events, Roundtables etc.)	Year 4: 12	Exceeded: 17

Key Points

There has been a strong focus on learning events throughout Year 4. The Facility delivered 17 active learning sessions. Highlighted included a presentation on the “UK ODA infrastructure offer” to the UK Government Infrastructure Working Group, and a Belt and Road Initiative roundtable, well-attended by representatives from DFID, PIDG and CDC.

A significant contributor in exceeding these targets was the development of infrastructure factsheets to support the Country Development Diagnostics for 16 priority countries. Another key knowledge product developed was the Whole Systems Approach tool and guide, to aid advisers in understanding sector complexities in designing energy programmes.

Summary of responses to issues raised in previous Annual Reviews

The Facility is currently categorising and packaging all existing deliverables as part of its Knowledge & Learning to ensure they focus on addressing issues raised by core Country Offices. It has continued to disseminate learning material to ensure full access to DFID and broader stakeholders through the website and is also making plans to continue the hosting of the website into Year 5, and after the contract with the Facility ends, through hosting through another ICED programme partner (CoST).

In order to support prioritisation while still reaching a wide audience, the Facility now uses an Audience Matrix to split knowledge products into five distinct types, with a specific target audience for each. An events calendar is used to track events by their purpose/audience, and different online platforms are used to most effectively reach different audiences. Finally, the Facility provides international influencing support on a case by case basis where expert technical inputs are required.

Recommendations
- Continue to deliver relevant and high-quality knowledge events in order to share Facility lessons learnt within DFID and OGDs, so that development advisers receive as much in-person knowledge transfer as possible before the Facility’s closure.
- Develop an accessible compendium of Facility deliverables in the form of a Facility legacy document which collates all of the Facility’s deliverables from Years 1-5.
- Work with appropriate channels for housing the Facility’s legacy documents within DFID and OGDs.
- Set up mechanism to maintain the Facility website beyond the Facility’s lifetime to ensure ongoing access.

Output Title	CoST: CoST creates a more transparent enabling environment for publicly procured infrastructure by establishing effective government systems to publish project information through the implementation of a scaled-up business plan
Output number per LF		4	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
Outputs
4.1 CoST develops and publishes: / a) The ITI methodology that measure transparency within public infrastructure and that will be implemented at a national level by stakeholders is developed and published / b) A new joint data standard (OC4IDS) for infrastructure is developed and launched in collaboration with the Open Contracting Partnership	Year 4 (a) ITI and (b) ODS published	Not met: (a); Whilst this output has not been met progress has been made - a new version of the indices and methodology is being tested in Honduras, Guatemala and Ukraine in Q2 of 2019. A final version is expected to be published later this year. / Met: (b); The OC4IDS (Open Contracting for Infrastructure Data Standard) beta version has been completed and will be launched in April 2019, to coincide with the OECD Infrastructure Governance Forum.
4.2 Training on implementing CoST is delivered in member countries: / a) Number of Government staff trained; / b) Number of civil society or media representatives trained; / c) Number of private sector representatives trained.	Year 4 (a) 5,200 / (b) 1100 / (c ) 180	Not Met: (a) 3,883; Met: (b) 1110; Exceeded (c) 301
4.3 (a) Number of international and regional organisations recommend or incorporate CoST tools and standards as part of their approach to improving infrastructure governance; (b) Number of invitations to participate at international and regional events to promote CoST tools and standards	Year 4: (a) 5 (b) 10	Exceeded: (a) 6; Exceeded: (b) 12; / (a) Over the last twelve months three additional organisations: IADB, the World Roads Congress (PIARC), and the G20 Infrastructure Working group; / (b) Including: an OECD session at the International Anti-Corruption Conference and a panel at a UNDP event, titled ‘Promoting a Fair Business Environment in ASEAN’.
4.4 Number of knowledge products (KP) that capture activities/results/lessons from implementing CoST that are disseminated.	Year 4: 12	Exceeded: 15; 8 knowledge products were developed in the last twelve months. In addition, CoST has published 4 newsletters and 8 blogs, double the number in the previous year.
4.5 £2.5m in additional funding is secured to fully fund the new Business Plan.	Year 4: £2.5m	Not met: £1.723m; It is unlikely that CoST will meet target. However, fundraising remains a priority. Agreements with Dutch Ministry of Foreign Affairs (MFA), October 2018 for €1m over 4 years and with UNDP (see below). CoST Members have been encouraged to raise additional funding for their national programmes through a match funding scheme designed by the CoST international secretariat.

Key Points

CoST addresses the challenges of mismanagement, corruption and inefficiency in public infrastructure by working with government, industry and civil society to promote greater transparency and accountability. DFID supports CoST to address these challenges not least to ensure that public investment in infrastructure delivers value for money and provides services to communities.

CoST currently works with 14 member countries including six DFID partner countries and several fragile states (Afghanistan, Ethiopia, Ghana, Malawi, Tanzania, Uganda, Honduras and Ukraine). It is currently exploring the potential for programmes in Myanmar and Nepal as well as working with the FCO in Colombia and South Africa.

Particular highlights include:
- CoST’s Executive Director, Peter Matthews, was invited to Chair the C20 Infrastructure Working Group. Provides CoST with platform to directly engage and influence G20 Infrastructure Working Group and OECD/G20 Long-term Investment group;
- Data from 9895 projects was disclosed in line with the CoST Infrastructure Data Standard (IDS) from April 2018 to Dec 2018, a 33% increase to date on the last financial year. The cumulative total, from July 2015, is now 24,831. Web-based disclosure platforms launched in Afghanistan have facilitated the disclosure of over 1800 road sector projects.
- Nine projects where government actions will improve outcomes from specific infrastructure projects, including: road repairs in Ukraine; health and safety improvements in Thailand; and, a new financial model for a toll road in Honduras. There have also been five sector reforms including establishing a new design unit in the Afghanistan Ministry of Public Works and a new process for identifying environmental risks in the Honduras ports sector.
- Regional Workshops held in Africa and Latin America, and a lesson learning visit between CoST Afghanistan and CoST Ukraine in 2018.

Working across UK Government

CoST’s relationship with the Prosperity Fund has deepened over this year. CoST signed a funding agreement with United Nations Development Programme (UNDP), financially supported by the Prosperity Fund, for £300k over three years to support CoST programmes in Thailand and Indonesia. In addition, the UK Embassies in Panama and El Salvador have provided small grants to the respective CoST programmes.

CoST continues to work with British High Commission India and UK Embassy Colombia to explore how far CoST can safeguard private sector investment in infrastructure. A follow-up visit to Colombia planned for the first quarter of 2019 with support of the UK Embassy. Final draft of the India study is currently under review.

CoST is exploring the potential for programmes in Burma and Nepal as part of the CIG programme. A scoping study in Burma has been commissioned with support from DFID Burma and Burma Ministry of Construction, and should be completed in April 2019. CoST’s work in Ghana and Liberia has led to the Minister of Public Works in Liberia formerly writing to CoST expressing his interest in the programme.

Summary of responses to issues raised in previous Annual Reviews

In the last Annual Review, CoST was encouraged to continue to expand its membership base. This has led the Board to agree to a competitive process in 2019 for interested organisations to join as CoST members. To this end, CoST is seeking to encourage two or three DFID partner countries to apply to join CoST over the next year. We have also found that primary demand for CoST has come from emerging economies which are investing larger sums of expenditure in infrastructure but without the systems to manage the investment. To this end CoST provides governments with tools and standards that helps to strengthen their systems.

Recommendations

- Strengthen approach to fundraising by recruiting a fundraising manager dedicated to engaging and retaining high value funding relationships including donors, private sector firms and foundations
- Develop and implement a fundraising strategy alongside its advocacy strategy.
- Review the approach to development of the Infrastructure Transparency Initiative (ITI) methodology and review the option of prioritising the promotion of the Open Contracting for Infrastructure Data Standard (OC4IDS) as a stand-alone tool to prospective members and as part of the wider UK offer on infrastructure, as this is may be a more effective way forward. If so, resources allocated to the development of the ITI methodology should be redeployed to focus on promoting the OC4IDS.

Output Title	World Bank: Improved analytics and diagnostics, planning of economic reforms and institutional and skills development in cities.
Output number per LF		5	Output Score	n/a (previously A in 2018)
Impact weighting (%):		5%	Impact weighting % revised since last AR?	Y

This component closed last year and therefore there is no reporting against this project for the final two years of the ICED Programme. The WB may undertake a summary report which identifies learnings from this project and links to new work they are developing with other cities.

Output Title	Cities Alliance: Knowledge management, research and policy influencing mechanisms to improve the basis for international dialogue and action on the infrastructure enabling environment and cities
Output number per LF		6	Output Score	A+
Impact weighting (%):		5%	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
6.1 Number of global advocacy events on Equitable Economic Growth in cities has raised awareness on the relationship between public goods and equitable economic growth.	Year 4: 1	Exceeded: 3. The Joint Work Programme (JWP) organised its main annual policy dialogue at the Africities Summit in Marrakesh, in a session dedicated to identifying strategies for local governments to improve management of public land and space to support increased productivity in cities.
6.2 Number of peer reviewed global knowledge products are being produced per year addressing the relationship between urbanisation, inequality and growth in cities	Year 4: 3	Exceeded: 6. The year marked the highest output of global knowledge products to date, including a toolkit for local authorities on how to support informal livelihoods in public space and a manual for street vendors on how to organize and initiate dialogue with local authorities to improve access to public space.
6.3 Number of completed, peer reviewed Institutional Enabling Environment Reports (IEER) for JWP Countries-Cities (Bangladesh, Uganda, Ghana and Kenya)	Year 4: 2	Met: 2. Two IEERs were produced for Nyandarua and Kajiado Counties in Kenya. Both validated at kick-off workshops with 50+ participants constituting multi-stakeholder forums.
6.4 Number of peer reviewed city level assessment reports and policy briefs on how to foster equitable economic growth in JWP cities delivered	Year 4: 4	Exceeded: 6. Two policy briefs and action plans were produced in Bangladesh. The evidence base and action plan produced in Sylhet in particular received strong buy-in and resulted in a commitment by the local government to support and co-finance further work related to waste management. Four Policy Briefs were produced in Uganda. / The work on public space and land management received much attention in Uganda, endorsed by the Ministry of Local Government, the Ministry of Lands, Housing and Urban Development, and the Urban Authorities Association of Uganda (UAAU).
6.5 Cities Alliance membership increases by 2 members per year (annual)	Year 4: 2	Met: 2; C40 Cities Climate Leadership Group and the Swiss Agency for Development and Cooperation (SDC) joined in 2018.

Key Points

The Cities Campaign has continued to yield positive results, both in terms of engagement methodology and outcomes, and is emerging as the trademark product of the Joint Work Programme (JWP). The two earliest campaigns, Uganda and Bangladesh, recorded significant achievements in 2018.

In addition, through the establishment of national sounding boards and by leveraging Cities Alliance members and partners, the cities campaign methodology has proved capable of mitigating its inherent limitation in scope by triggering follow-up and spin-off initiatives.

Several global knowledge products received strong uptake and much attention, particularly those on the relationship between public space, informal workers and economic development in cities.

The quality assurance and feedback mechanisms of the JWP shows that the outputs are perceived by beneficiaries as useful and of high quality. Importantly, the outputs were also rated high on the likelihood of follow-up action by the local government to implement the key findings and recommendations: 84% of responses among city focal points characterized follow-up action as likely or very likely (rating of 4 and 5 respectively).

Key Challenges

Two overarching challenges have been recorded during the reporting period, both of which are well known from previous years. Several measures have been taken to mitigate and overcome both:

The JWP city campaign has an inherent limitation in scope, in that it ends at the point of formulation of policy recommendations and action plans for the improvement of specific service areas. Expectations have been thoroughly managed throughout the campaigns, and links to other initiatives (within the JWP and through alignment to member and partner engagements in-country) have been secured, however there remains a strong case for specific follow-up action to take the work in the campaign cities to the next stage.

As identified in previous Annual Reviews, the JWP has experienced challenges in establishing and maintaining strong links to DFID Country Offices. The challenge has been in part overcome through active use of the sounding boards, particularly in Uganda and Bangladesh, with local DFID representatives taking part.

Recommendations

n/a

Output Title	Strategic Opportunities Fund (SOF) : Support the utilisation of the SOF
Output number per LF		7	Output Score	A
Impact weighting (%):		5%	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
7.1 £ value and number of sub-sector projects approved by SOF	Year 3: 0	As per the 2018 Annual Review it was agreed not to initiate any new projects for funding under the SOF in Year 4, but to focus on successful completion of existing projects
7.2 £ value and number of projects approved by SOF that have achieved their intended outcome as defined by DFID (on a case by case basis)	Year 3: 0	As above.

Key Points

The Strategic Opportunities Fund was set up to support emerging opportunities across the urban, energy and infrastructure sectors. However, it was agreed in the 2018 Annual Review given the number of components and projects funded as part of the ICED programme that no new funding would be allocated to new projects under the Strategic Opportunities Fund for that year, and instead the DFID team would focus on successful completion of the existing projects funded under this component. The score of A for this output is therefore based on successful completion of those projects.

This year, the Strategic Opportunities Fund has:

Provided support to Chatham House research on Extractives in Development: Implications for Power and Infrastructure Planning in a carbon-constrained world. Whilst this research output took longer to complete than planned, a detailed final report was received and approved by the cross-government steering group in June 2018.

Continued support to the senior DFID infrastructure advisor seconded to the Global Infrastructure Hub. The advisor was requested to extend their secondment on promotion (as a director to the Hub), which is a positive endorsement of their contribution. We have agreed with the Hub that we will not provide continued funding to the extended post (due to our budget constraints). We have allocated budget to support their move back to the UK at end of posting (December 2019), as originally agreed.

Summary of responses to issues raised in previous annual reviews

The DFID team worked with Chatham House to effectively deliver the research report on Extractives in Development, which was published and disseminated across government departments.

Recommendations

At this point, there is approximately £300k remaining in the Strategic Opportunities Fund, with the ICED programme having 15 months more to run. Therefore, the team should review options for appropriate use of this funding in the next three months and decide whether the funding should be allocated to specific opportunities or returned to the central DFID budget.

Output Title	Coalition for Urban Transitions (CUT)
Output number per LF		8	Output Score	A
Impact weighting (%):		5%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
8.1 - Number of flagship country urban roadmaps developed in low income countries (Tanzania and one additional country in Africa - TBC).	1	Met (1) / • Tanzania: Coalition finalised the first draft of the National Urban Transition Assessment (NUTA), which will be launched in partnership with the Tanzanian government in Q1 2019. / • Ghana: Development underway. Coalition established a similar TU Lab model in Ghana with the creation of the Ghana Urbanisation Think Tank.
8.2 - Number of major high impact, high quality, peer reviewed working papers - supported by relevant regional and country case studies - capturing the wider net economic, social, and environmental benefits and the range of relevant national policy levers and financial instruments published to encourage compact, connected, coordinated, and efficient urban development.	5	Exceeded (6)
8.3 - Number of draft flagship global synthesis reports capturing the findings of various projects within the workstreams and communicated by the Coalitions leadership council and steering group.	1	Met (1) / • First draft of the report has been completed on schedule. Release date of the report will be in September 2019.
8.4 - Number of National Media Assessments completed to lay foundation for successful release of national urban roadmaps drawing on both local partner communications expertise as well as organisations known for conducting media capacity building.	1	Met (1) / • The Tanzania National Media Assessment has been completed and a second one has been commissioned for Ghana.
8.5 - Number of publications in global outlets, national newspapers or leading sector media (including digital platforms) by senior Coalition spokespeople and champions (op-eds, blogs, long reads or interviews).	2	Met (2) / • 2 op-eds published by Naina Lal Kidwai and Seth Schultz / • 67 media mentions (April 2018 to January 2019)
8.6 - Number of "meeting proceedings" (to inform bespoke briefing notes and presentations) from successfully completed bilateral meetings with Heads of State / Ministerial / CEO / IFI Head / Senior decision-maker/official level at which Coalition findings and analysis is discussed.	8	Exceeded: 12 / • 6 bilateral meetings held with CEOs / Executive Directors briefing them on the Coalition work programme and emerging findings. / • 2 Urban Leadership Council meetings held. / • 4 Steering Group meetings held to discuss Coalition strategy and ULC outcomes.
8.7 - National groups of relevant key policy makers and other important champions facilitated by the Coalition are set up and operational in each focus country.	1	Met: 1 / • Tanzania Urbanisation Lab (TU Lab) established with 50+ key stakeholders to give national ministries, local government, donors and academia a forum to exchange policy ideas.

Key Points

The Coalition for Urban Transitions (CUT) is currently on track to meet its 3-year outcomes and met the conditions for continuation of funding set out in the contract’s 18-month break clause (September 2018), approved by DFID on 10 October 2018. CUT has completed the first draft of a global flagship report targeted at Heads of State, scheduled to be published in September 2019 at the United Nations Secretary General’s (UNSG) Climate Summit. The report will explore the unique roles of national governments in creating sustainable, prosperous and equitable cities, analyse the economic benefits that countries will enjoy if they foster a zero-carbon urban transition, and offer detailed priorities for action to catalyse that transformation.

CUT has established a coalition of urban stakeholders within the Tanzania programme, who have collectively commissioned and finalised a range of research to address key knowledge gaps. CUT has set-up a major new country programme in Ghana to help the Government review and reform national urban policy to harness the economic potential of urbanization while reducing the risks of climate change. CUT received requests from the Governments of Ethiopia and Indonesia to support development of national urban agendas, in addition to enquiries from multilateral institutions such as the UNSGs office.

Issues and Lessons Learned

Sustainability of the Tanzania Urban Laboratory (TUL) - a programme aimed at building capacity of stakeholders to identify and address issues related to Urbanisation in Tanzania - after the end of the ICED programme has been a focus. Plans are underway to reflect on lessons learned and scope how the TUL continues to be active after ICED ends to ensure that the process for embedding the recommendations of the Tanzania national urbanization roadmap into national development and urban planning efforts can continue post launch.

Recommendations

- Upgrade website: CUT works with member organizations to create communication products to host on its website. However, due to increased outputs, and therefore demand, coupled with limited website capacity the website has not been fit for purpose so CUT has commissioned an upgrade to meet requirements.
- CUT has recognised the need to develop deeper institutional relationships over individual relationships and focused on developing related strategies to achieve this during the period.

Summary of responses to issues raised in previous Annual Reviews:

n/a
## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

The ICED Programme Theory of Change (detailed in full in the diagram below) outlines the two levels the programme works at: the national and the global. It also highlights linkages between the two levels, both at interventions to outputs, and at outputs to outcomes. The delivery partners for the ICED Facility have been encouraged to take advantages of these linkages where possible. For example, the city economic diagnostics produced by the World Bank at a global level could be integrated into the scoping of new programming at the national level.

Changes made to the Theory of Change since the last annual review have been highlighted in yellow. These specifically reference the increased support to other government departments through the Strategic Operations Fund and the ICED Facility.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

The ICED Facility continues to achieve its log frame targets. The successful implementation of the ‘Strategic Pivot’ – which was designed to enable greater prioritisation and strategic engagement with priority countries and teams – has delivered increased demand for the Facility’s services from across DFID and UK Government with output indicators increased accordingly. It has developed key Knowledge and Learning products for DFID-wide utilisation in the form of the Whole Systems Approach tool for the energy sector, supported DFID’s Country Development Diagnostics, and delivered 17 studies to support DFID and other government departments to strengthen existing programmes or inform new ones. As the Facility comes to an end, attention will be focused on developing an appropriate exit strategy which ensures sustained impact of the Facility beyond the lifetime of the contract.

Cities Alliance, and the Coalition for Urban Transition (CUT) are all moving towards their expected outcome indicators. Resources produced by the Cities Alliance received extensive attention at global forums and importantly, also at the local level. The Infrastructure Sector Transparency Initiative (CoST) has made excellent progress in surpassing a revised cumulative indicator total of 23,000 projects where data has been disclosed in the Infrastructure Data Standard (IDS) format.

In the coming year, the ICED programme will close. In light of this, the emphasis in the 2020 Annual Review will shift away from outputs, to take a closer look at the outcomes and long-term impact that the programme has had.

Explain major changes to the logframe in the past year

ICED Facility: In light of the contract amendment of December 2018 and the increase in programme funds (by £700,000, along with an additional window of £1.5m for externally funded work), the logframe targets for the ICED Facility have been proportionately increased to reflect the additional funding.

CoST: Following the completion of the CoST Business Plan, CoST re-developed its logframe and agreed a new set of targets as part of the ICED programme logframe. CoST Member countries complete a report every three months, which captures the logframe data and identifies success and impact stories in a more systematic manner.

Describe any planned changes to the logframe as a result of this review

In addition to the overarching ICED programme logframe, all delivery partners work to individual logframes, in order to ensure indicators and milestones are suitably detailed.

There are proposed changes for CoST, as set out below.

Outcomes

CoST has not met the target for outcome 1.7. This is partly due to attracting fewer new members than had been predicted. The team will review the causes and consider revising down the year 5 target.
CoST has exceeded the target for outcome 1.8:
1.8(a) was substantially exceeded from its revised year 5 target of 23,000. We propose revising the target from 31,000 to 34,000 for year 5.

Outputs

Target for output:
- 3.2(c) was revised up to 170 in year 4 and 300 in year 5. The year 5 target has been exceeded in year 4 and it is suggested that the target for year 5 be increased to 500.
- 3.3: CoST changed output indicator 3.3 as ‘recommending the use of CoST Tools and Standards’ was open to interpretation. The indicator was split into two as follows:
(a)	# international and regional organisations incorporating CoST tools and standards as part of their approach to improving infrastructure governance. The year 5 target remains at 8.
(b)	# invitations to participate at international and regional events to promote CoST tools and standards. The year 5 target has now been set at 22.
The year 4 target for output 3.4 has been exceeded and an increase in the year 5 target from 17 to 20 knowledge products is suggested.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

The programme operates based on the VFM proposition in the BC. In particular, the ICED Facility reports against quarterly KPIs.

Key cost drivers and performance

The Facility provides specialised technical assistance to DFID, primarily DFID Country Offices. The Facility works by developing specific Work Packages with Country Office to deliver a piece of scoping or design work. These are reviewed first by the commissioning advisor, and then the budget and number of days are signed off by the DFID SRO. This provides two levels of check, both on the content of the work to be undertaken and the costings.

Consulting time remains 96% of the Facility’s total spend. The remainder is allocated to travel and expenses. The two key cost drivers are consultant daily rates (fees) and number of consulting days (input unit).

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

The programme partners have taken a number of actions to maximise VfM, and the team are confident that it has a strong VfM case:

Economy

ICED Facility
- Seeks synergies at work package and Facility level: e.g. clustering groups of thematically similar requests into single work packages.
- Leverages PWC infrastructure: additional costs associated with implementing the Facility which PwC does not charge and not included within fee rates i.e. hosting team meetings, roundtables, etc.

CoST
- Outsourcing the International Secretariat function to Engineers Against Poverty: lowers overheads, grants access to high-quality consultants.
- Regional managers: part-time consultancy basis, provide support to members at lower rate.

Cities Alliance
- Applies ‘three modes of delivery’ to reduce costs i.e. human resources, grants and procurement: grant modality in particular is effective, requiring at least 20% additional co-financing by grantee.
- Adopts United Nations Office for Project Service systems and procedures for competitive and sustainable procurement: financial negotiations with the lowest cost, technically compliant bidder.

CUT
Negotiates fee rate discounts or co-investments and benchmarks salaries against similar Non-Government Organisations (NGO) in the field.

Efficiency

ICED Facility:
- Leverages thematic, institutional and country knowledge: among others, the Nepal Cities & Infrastructure for Growth (CIG) scoping and the Nepal Local Infrastructure Services Programming Scoping Phase 1 Work Packages used the same consultant (John Cox) as Team Leader for both Work Packages.
- Drew on lessons learned: used tools and approaches developed during CIG Phase 1 to deliver four Scoping Studies for CIG Phase 2 countries within ambitious time frame of 3 months.
- Leveraged increased efficiencies through implementation of portfolio approach[2].
  [2] The Infrastructure & Energy (I&E) team: linked its work on Whole System Approach to energy with discussions around energy in CIG Phase 2 scoping; The Fragile & Conflict Affected States (FCAS) team: combined engagements in Somalia with work on case studies for infrastructure programming in FCAS; The Gender, Disability & Inclusion (GD&I) team: applied tools and approaches particularly around disability inclusion and safeguards; The Economic Development, Investment & Jobs (EcDev): building out a portfolio of work around the construction sector.

CoST
- Selects and monitors partners according to efficiency of delivery: works in strategic partnerships (Open Contracting Partnership, Hivos) to develop joint standards, build capacity and organise joint events or knowledge sharing platforms. Allows CoST to benefit from economies of scale in its work.
- Uses training of trainers’ approach: with annual managers’ and regional workshops and regional managers to provide direct support to the CoST countries in the region and are responsible for the growth of CoST in their geographical area.

Cities Alliance
‘Three-modes of delivery’ model facilitates efficiencies: use of local consultants in Uganda from Makerere University then able to organise course based on the research at the University, targeting local government officials.

CUT
Continues to leverage significant resources: for example, has a number of private sector in-kind core staff secondments. Members of the Steering Group and Urban Leadership Council participate on a pro-bono basis. Many of the paper reviewers also participate on a pro-bono basis.

Effectiveness

ICED Facility
- Impact on programmes: supported development of seven business cases amounting to £337 million[3] in new DFID programming, three programmes supported by the Facility design, in process of being implemented in four countries[4];
  [3] Calculation based on the following: (ICED spend: BC value): CIG (£459,759: £165m), Sierra Leone off-grid (£70,528: £34.5m), Sierra Leone grid rehabilitation (£62,720: £32.4m), SPEED (£201,756: £30m); Pakistan SUP (£250,545: £20m); SCIG (£28,184: £35m). Ethiopia WASH BC will be added which is (£49,180: £50m). SPEED is excluded from this total as it did not result in a new programme.
  [4] 1) Rural Electrification in Sierra Leone Project; 2) Increasing Access to Electricity in Sierra Leone; and 3) CIG (Phase 1 countries: Burma, Zambia and Uganda).
- Streamlined delivery model and strengthened operating model: appointment of Portfolio Director across three of the six portfolios; a Director of Monitoring, Evaluation & Learning (MEL); and, a single Programme Manager, responsible for functions previously delivered by two individuals;
- Responded to extensive demand for ‘Call Down Facility’ in areas of disability inclusion and safeguarding;
- Facility work inspiring further investigation: following delivery of the CIG work in Nepal, a DFID energy advisor intended to commission downstream work to expand elements related to the Whole Systems Approach, through existing DFID Nepal programme.

CoST
- Institutionalising approach to transparency and accountability within government systems: can deliver clear effectiveness where the ultimate aim of CoST is delivered through assimilating objectives of transparency into existing government systems no longer requiring CoST support;
- Uses a result-based approach: through funding of CoST national programmes where applicants must meet certain criteria to be eligible for original and continued funding.

Cities Alliance
The partnership orientation of the JWP (and Cities Alliance) ensures effectiveness, locally and globally, by allowing for flexibility and space to adapt to emerging opportunities, for example, PMT worked with United Nations Capital Development Fund (UNCDF) in Uganda to disseminate outputs and recommendations of the City Campaign, with policy recommendations endorsed by the Ministry of Local Government among others.

Equity

ICED Facility
Extended its mainstreaming “offer”: explicitly addresses disability inclusion (through the use of disability focused entry points) within Facility Work Packages through ToR approval process. Relevant Work Packages included developing a Disability and Inclusion Action Plan for DFID Uganda, providing support for the Global Disability Summit and a Disability Roundtable with PIDG and CDC.

Cities Alliance
The JWP contributes to the implementation of the Cities Alliance Gender Equality Strategy (GES) with a clear commitment to equality enshrined in the Cities Alliance Charter. The JWP aims to contribute to an acknowledgment of the interrelationship between access to public goods and services by women and men and equitable economic growth strategies in cities by applying gender mainstreaming efforts throughout the JWP activities.

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

Overall risk rating: Moderate
The overall implementation of ICED continues to be moderate.

Overview of programme risk given the progress so far:

ICED Facility
- The Facility monitors risks through quarterly reports to DFID. Key risks managed and mitigated during the period:
  - Delay in contract amendment results in funding gap resulting in inability to deliver: DFID and the Facility managed the risk through regular budget profiling and scenario planning, including to managing demand. The contract amendment effected a change of the Terms and Conditions under which the ICED alliance worked. The ICED Facility lead contract holder, PwC, actively managed the potential delivery risk of non-compliance of the delivery chain. This was done through early and sustained engagement with the suppliers to ensure awareness of the need for compliance.
  - Expected demand from other Government Departments does not materialise, jeopardising co-financing model: Facility worked with DFID to prepare communications for potential clients in advance and manage expectations, resulting in high subscription to the available headroom.
  - Conflicts of Interest undermine credibility of the Facility: the Facility has set out clear conflict of interest procedures to manage this and where they anticipate these are quick to alert DFID and work with DFID to resolve them.
  - Risk of delivery to OGDs: the Facility has developed clear financial and technical guidelines, however the DFID SRO and programme manager should closely monitor progress of these work packages.

CUT
- Regular risk monitoring and reporting including regular progress reviews of the core initiative management team and quarterly progress calls between the Coalition and DFID.
- Key risk:
  - Analysis and recommendations for each country and global research pillar (policy, economics, finance) are ignored by governments and do not translate into policy changes. The critical way this is mitigated is by ensuring a strong process of partner engagement and building buy-in in each country and at the international level.

CoST
A new risk register based on the current business plan was finalised for the Board meeting in late March. It provides a more comprehensive approach to defining risk appetite and how each risk will be managed by an International Secretariat staff member and owned by a CoST Board sub-group. There are four key risks:
- Government interest in CoST does not materialise into joining the programme as a member or affiliate. Mitigated by introducing competitive process with limited number of places to join the programme. Anticipated that this creates value in joining CoST and ensure applications are robust and of a good quality. It also helps to manage programme resources.
- Inability to attract additional funding. This still remains a significant risk despite the new agreement with the Dutch MFA. CoST is now looking to engage foundations who are interested in open contracting, open data and civil society capacity building programmes as well as bilateral and multi-lateral donors.
- Misuse of funds by CoST member programmes (the host organisations that host CoST national programmes in country). Grant agreements between the CoST Secretariat, Host Organisation and Multi-Stakeholder Group (MSG) establish how grant funding should be used. It also includes their Anti-Corruption and Bribery Policy. CoST also requires MSGs to provide a financial report on a quarterly basis as part of the grant agreement and undertake due diligence checks on each host organisation including an annual audit of previous grant funding.
- The lack of a safeguarding policy and procedure for potential beneficiaries principally those who receive training. CoST has finalised a Safeguarding Policy which is included in all grant agreements. It has also provided training on the policy at regular intervals and will be expected to adopt the policy as part of their next grant agreement which will commence in July 2018.

Cities Alliance
The JWP is reporting against a Risk Management Framework to the Cities Alliance Director on a bimonthly basis.

Outstanding actions from risk assessment
n/a. The programme risk matrix is now managed live on AMP and reviewed at monthly programme meetings.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

The ICED programme is currently on track for all deliverables against agreed work plan and log frame.

As the Facility is now undertaking work which can be paid for outside of the core programme budget, the DFID programme manager and SRO are reviewing the ICED Facility’s system for oversight of OGDs engagement with the ICED Facility, as this is a new way of working.

Performance of partnerships

The partnerships with all suppliers are working well.

ICED Facility: The team engage through on a regular fortnightly meeting, along with more regular communication as required. The Facility provides detailed information on work-packages through the development tracker which highlights risk on poor delivery and provides mitigating actions/solutions providing assurance. Forecasting on a monthly basis provides greater accuracy and control over spend and remains within tolerance.

The Facility has performed well under their complex KPI/PbR structure which is scored and achieved on a quarterly and annual basis, and overall feedback from DFID clients is positive. All suppliers have now signed the revised DFID Terms and Conditions as well as the Supply Partner Code of Conduct.

CoST, WRI and CA partnerships are all positive quarterly or six-monthly reports and regular feedback provided to the DFID team. Financial performance according to agreements are consistent and accurate, allowing for slight flexibility especially relating to foreign exchange variances.

Asset monitoring and control

The ICED programme does not acquire any assets. Any IT software or platforms developed are open access, open source and will constitute a global public good.

G: MONITORING, EVIDENCE & LEARNING

Monitoring

Meetings have taken place with all DFID partners under ICED on a regular basis to clarify questions and agree on forward work plans. All partners work to individual logframes, which contain more detailed indicators and milestones.

In the case of the ICED Facility, the team and DFID meet on a fortnightly basis to discuss progress in DFID and engagement, and to clarify any outstanding issues, along with ad-hoc engagement as required. The Facility also provide quarterly reports to DFID.

CUT: Monitoring of the Coalition is primarily conducted through quarterly progress reports (narrative and financial) and conference calls. Quarterly progress is measured and reported against quantitative and qualitative interim indicators in several log frames (ICED Log Frame Output 8, 18-month Break Clause Log Frame, and Coalition ‘nested’ Log Frame), established at the outset of the Coalition. Communication between DFID and the Coalition is regular and occurs throughout each quarter. The next evaluation will be the 2019/20 Annual Review.

CoST: Following the completion of the CoST Business Plan and the development of a new ToC, CoST re-developed its log frame and agreed a new set of log frame targets as part of the ICED programme log frame. CoST Member countries complete a report every three months, which captures the log frame data and identifies success and impact stories in a more systematic manner.

Cities Alliance: Based on the Results Framework of Cities Alliance JWP, the ICED log frame as well as annual workplans, a distinct reporting system has been established to allow for product-oriented monitoring. All implementation entities of the JWP are obliged to provide a bi-monthly update.

Evidence

DFID commissioned an independent review of the ICED Facility, which was undertaken in between February – April 2019. The outputs are under finalisation, however on the whole it is positive around the ICED programme model and its deliverables and provides useful evidence on policy areas and programmatic approach undertaken by ICED. This will be used to inform the programme’s next annual review, and design of future programmes.

Given the nature of the ICED Facility interventions, providing support to Cos and OGDs, and support to strategic priorities and international influencing, the approach to continual evaluation and monitoring of expected results has continued to place a strong emphasis on learning, which needs to inform programme direction and feedback into programme design. This approach requires the ICED team to regularly engage in reflections on what they have learned so far and review the delivery of individual Work Packages. This continues to be done through learning sessions and events which are opened up to relevant DFID advisers, as well as sessions at wider events, such as the Advisor Professional Development Conferences.

Learning

Learning forms a cornerstone of the recommendations outlined in the ICED 2019 Annual Review, for both the programme as a whole and the ICED Facility.

ICED Facility and DFID team plan to hold a workshop reviewing the Facility’s ways-of-working and development over the past four years, with key points to be captured in an internal learning document, as part of the close-down activities and to feed into the design of a successor programme.

The ICED Facility specifically will:

- Continue to deliver relevant and high-quality knowledge events;
- Develop an accessible compendium of Facility deliverables from Years 1 -5;
- Consider legacy arrangements for Facility deliverables from Years 1-5, and the Facility’s website;
- Share the Facility’s ICF attribution methodology with DFID as an example of clear guidance and methodology for assessing ICF eligibility.

Progress on recommendations from previous reviews

Actions against recommendations from previous reviews are summarised here:

ICED Facility:

- Implementation of the ‘Strategic Pivot’, which was designed to enable greater prioritisation and strategic engagement with priority countries and teams.
- Restructuring of the management meetings to provide a greater focus on strategy and management.
- The Terms of Reference (ToR) development process has been refined to produce a tiered approach reflecting the appropriate level of effort for different types of request.
- 5 out of 6 of the Facility’s portfolio managers have not changed throughout Year 4. The Facility has continued to deliver using a good balance of expertise by using staff with established knowledge of the Facility’s ways of working versus those with a niche technical expertise.
- The Facility continues to deliver a high-quality level of engagement through the entire cycle of Work Package delivery. This is reflected in Year 4 feedback surveys, by clients, providing an average Key Performance Indicator (KPI) scores for quality of 7.5/10.The Facility met with the ICF Secretariat in Year 4 to discuss its ICF methodology to ensure it adequately strengthens the assessment of ICF attribution. This was confirmed by the Secretariat.
- The Facility engaged more systematically with the climate and environment Cadre to ensure the Facility’s offer to DFID in this area was sufficiently robust.
- The Facility is currently categorising and packaging all existing deliverables as part of its Knowledge & Learning to ensure they focus on addressing issues raised by core Country Offices.
- In order to support prioritisation while still reaching a wide audience, the Facility now uses an Audience Matrix to split knowledge products into five distinct types, with a specific target audience for each.

CoST:
CoST was encouraged to continue to expand its membership base. This has led the Board to agree to a competitive process in 2019 for select, interested organisations with a limited number of places to join as a CoST member.

Cities Alliance:
- The JWP city campaign has an inherent limitation in scope, in that it ends at the point of formulation of policy recommendations and action plans for the improvement of specific service areas. Expectations have been thoroughly managed throughout the campaigns, and links to other initiatives have been secured.
- The JWP has experienced challenges in establishing and maintaining strong links to DFID Country Offices. The challenge has been in part overcome through active use of the sounding boards, particularly in Uganda and Bangladesh, with local DFID representatives taking part.

Strategic Opportunities Fund:
The DFID team worked with Chatham House to effectively deliver the research report on Extractives in Development, which was published and disseminated across government departments.