Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Ideas to Impact – innovation challenges for climate & environment technologies for the poor
Programme Value: £10,909,350		Review Date: April 2015
Programme Code: 201879	Start Date: April 2014	End Date: April 2019

Summary of Programme Performance
Year	2015	2016	2017	2018	2019
Programme Score	A
Risk Rating	High

Summary of progress and lessons learnt since last review
Ideas to Impact is a new, innovative payment-by-results programme led by a dynamic consortium[1]. Over the next five years, the programme will test the value in using innovation or incentive prizes as a way to bring new solvers and new solutions to persistent development problems. Launched in March 2014, this is the first annual review for the programme. At this early stage, Ideas to Impact is performing well and is assessed as being on track to meet its logframe targets. Five well-defined problem statements have been researched, leading to the design of five individual prize concepts in the areas of energy access, water and sanitation and climate adaptation. The table below provides a description and update on each prize as of March 2015.
[1] The team consists of IMC Worldwide as the programme manager, Tremolet Consulting as thematic leads on water and sanitation, the Global Village Energy Partnership as thematic leads on energy, the Institute for Development Studies (IDS) as thematic leads on climate adaptation and leading the learning and research agenda, ITAD as the monitoring and evaluation specialists and InnoCentive as the prize design experts.

Table 1: Update on individual prize concepts

Prize name	Description	Country	Est. Launch Date
#Clean City	Foster innovative approaches to integrated sanitation in small cities that are currently not receiving adequate investment	Ghana / (to be confirmed)	Hope to announce at AfricanSan in May 2015
#Dream Pipe	Stimulate the design and implementation of an innovative financing and contractual arrangement for reducing non-revenue water	Global	Late May 2015
#Clean Cooking	Enhance the LPG market for clean cooking solutions, addressing challenges in both the supply and demand of LPG cooking solutions (3 prizes)	Ghana	First prize May 2015, 2nd prize July 2015, and 3rd prize in 2016
#Adaptation at Scale	Support the replication and growth of successful local adaptation innovations	Nepal	Sept 2015
#Climate Information	Demand-driven actionable climate information for low-income households	Kenya	Sept 2015

The programme, at this early stage, has already learnt a broad range of lessons applicable to prize programmes, as well as complex innovation programmes more generally. These include:
- Early scoping revealed that the priority problems in energy access, WASH and climate adaptation are often related to challenges within the broader innovation systems[2] (e.g. lack of collaboration between actors, inefficient policies, lack of end-user demand), rather than simply a need for new ideas or technologies;
  [2] The concept of an “innovation system” is well recognised in the innovation literature, used to describe the arrangement and interactions of actors (firms, NGOs, universities, etc.), policies, social influences, and markets, in which innovation may or may not occur. It provides a more holistic view of the how innovation arises and where challenges or barriers exist, beyond just looking at individual technological solutions.
- Prize design takes a long time (around 8 months) and requires considerable stakeholder engagement to effectively understand the problem landscape, especially in relation to innovations systems rather than technology invention;
- This has knock-on impacts for the duration taken to launch prizes – from a starting point of problem identification, it is likely to be 12-18 months to launch;
- A diverse team adds value both to design and implementation, and from a learning perspective, but can slow initial progress;
- A high level of management input is required to support programme establishment and delivery;
- Establishing M&E frameworks is a challenging, iterative process during prize design; and
- As the programme will gather evidence on the impact of prizes which does not currently exist, the programme has received significant interest from other international organisations. As such, a new outcome indicator will be added to the logframe to monitor research outreach and uptake.

Given the longer than anticipated time required for prize design (8 months instead of 6), there have been some delays in finalising the M&E framework for the individual prizes, as well as the programme as a whole, however this has not affected meeting logframe targets.

Overall, the diverse consortium partners work together well, forming a strong and adaptable delivery partner for DFID. The diversity of skillsets on the team has undoubtedly strengthened the outputs and their links to expected outcomes and impact as there is a good level of internal challenge and debate. Team interaction is great for solving problems; boosting morale; getting focus back onto what needs to be done; and generating ideas for strengthening the programme across all output areas. Quarterly review meetings (which DFID participate in) have been an important management tool in keeping the programme on track.

Finally, the programme has received a significant amount of interest from external organisations, notably other donors and funders, who may have used prizes in the past or are exploring using them in the future. There has been particular interest around the M&E framework, as there is a severe lack of understanding around what makes an effective, successful prize. Ideas to Impact has a growing following, with the first newsletter going out to over 550 people across 10 countries. We will measure and monitor the outreach activities as part of the logframe going forward.

Summary of recommendations for the next year
The programme overall is on track to meet the outputs and outcomes specified in the logframe, and achieve its aim to build the evidence base on innovation prizes for development. Since the focus of the past 12 months has been detailed design in the build-up to launching five innovation prize topics, there are few substantial recommendations at this early stage.

Overall, IMC (the lead consortium partner) needs to maintain its role in coordination and support across the various prizes areas; ensuring effective communication and debate between the diverse team; and ensuring that maximum value is derived from the team arrangements. Quarterly consortium meetings should continue, with DFID participating where possible. Recommendations are grouped below as per the programme outputs:

Prize launch and management
Momentum must be maintained throughout 2015, not just for prize launch but for engaging with partners and potential funders, and to ensure maximum value is derived from the implementation of all prizes. Sufficient time and resources need to be given to the theme leaders to continue effective stakeholder engagement and oversight into prize design and implementation. Realistic work plans that take account of resource constraints and resolve them where possible must be in place and followed by all team members. DFID and IMC Worldwide hold quarterly meetings to discuss project progress. At these quarterly meetings, DFID and IMC will will monitor and assess the momentum of the project to ensure that it is on track for prize launch and for engaging with partners and potential funders, and to ensure maximum value is derived from the implementation of all prizes.

Publication of research papers
The launch and dissemination of four research papers is a high priority in the first month of next year, along with programme-level communications to engage with interested stakeholders, and share the potential for innovation prizes as learnt so far by the programme. The fifth paper in the first series is due around September 2015.

Research and M&E frameworks
Monitoring and evaluation methodologies will need to continue adapting as the prizes are designed, with early baseline capture a priority pre-launch. As such, three M&E frameworks will need to be finalised for May 2015 (Clean Cooking, Clean City and Dream Pipe), the remaining two M&E frameworks will need to be finalised for September 2015.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3954668.docx
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4456243.xls

Outline of the programme
Ideas to Impact[3] is a new £10.9m programme to support research and development (R&D) in energy, water and climate adaptation solutions for developing countries over the next five years.
[3] More details are available on the programme website: http://ideastoimpact.net/. Previously known as Innovation Prizes for Environment and Development (IP4ED).

The programme will design and launch a variety of “innovation prizes” to stimulate and incentivise the development and deployment of solutions for low income consumers, focusing on improving poor people’s access to affordable clean energy, safe drinking water and improved sanitation, and resilience to climate change. The programme was launched in April 2014 and runs until March 2019 to test the application of innovation prizes as a funding mechanism to achieve development outcomes. IMC Worldwide leads the programme and manages a consortium with specialist expertise. The programme is structured around thematic leads on water, sanitation and hygiene (Trémolet Consulting); low carbon energy (Global Village Energy Partnership); and climate adaptation (Institute for Development Studies). The consortium also includes experienced prize designers from InnoCentive, with research, evaluation and learning led by ITAD, with support from IDS.

An innovation prize is defined as “a financial incentive that induces change through competition”. More specifically, to win the prize, solvers need to compete against one another to meet a set of specified criteria, which if met, entitles them to some form of financial reward. Innovation prizes aim to stimulate or induce innovation rather than reward good performance ex-post, as a more standard recognition prize (also referred to as “award”) would do.

Rather than looking for purely technical solutions, prizes under Ideas to Impact are likely to include solutions requiring combinations of systemic, social and technological change. Following the design phase, the programme will launch innovation prizes to address five well-defined problem statements in the area of energy access, water and sanitation and climate adaptation:
1. Clean City to foster innovative approaches to integrated sanitation in small cities that are currently not receiving adequate investment (country in Sub-Saharan Africa to be confirmed, likely to be Ghana).
2. Dream Pipe to stimulate the design and implementation of an innovative financing and contractual arrangement for reducing non-revenue water (water lost through leaky, unmaintained pipes) in DFID target countries (global).
3. Clean Cooking to enhance the LPG market for clean cooking solutions, addressing challenges in both the supply and demand of LPG cooking solutions (Ghana).
4. Adaptation at Scale to support the replication and growth of successful local adaptation innovations (Nepal).
5. Climate Information to make sophisticated climate information more useable for the poorest (Kenya).

As an innovative, new programme for DFID, Ideas to Impact has a strong emphasis on evaluation and lesson learning. The programme will launch a series of research papers, including papers on each thematic area, providing evidence of the problem analysis of opportunities; evaluation papers on completion of each prize process; and an analytical guide providing a framework for using innovation prizes in a developing country context.

Ideas to Impact aims to improve the lives of around 12 million people (directly and indirectly). It will achieve this by supporting:
1. At least 7 new, affordable and accessible technologies, solutions or processes developed for poor people
2. At least 5 affordable and accessible technologies, solutions or processes deployed to poor people
3. At least £35m of new private investment in technologies and business models attracted in
4. At least 50% of entrants applying for prizes are new teams/organisations to DFID’s existing portfolio of grantees in this area

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
At this early stage of the programme, no outcomes and impact can be reported. The original business case and logframe targets included very indiciative impact and outcome numbers, since it drew on indiciative prize concepts only. During the design phase, the thematic experts were tasked with researching and identifying the most pressing challenges within their sector in which the prize approach could be used to stimulate innovation. Unsurprisingly, the concepts that have been worked up are different to the indicative prizes in the original business case. This may have some consequence for the original impact and outcome milestones and targets, though at this stage it is difficult to know for sure – the achieveable impacts may be greater than 12 million people, or they could be less. At this early stage the programme has estimated a target of improved livelihoods for around 10 million people (2.2m directly and 7.8m indirectly).

On outcome milestones and targets, the programme is on track and may in fact exceed expectations, as described below.
At least 7 new, affordable and accessible technologies, solutions or processes developed for poor people
Many of the five prize areas will reward more than one winner, for example, the top three ideas that meet the specified criteria will win the prize. This process will result in many more innovative technologies, solutions and processes being developed than simply one winning idea for each of the five prize areas. At this early stage, it is difficult to predict how many new solutions might be developed as a result of the prizes, but it is likely that the programme will exceed this target.
At least 5 affordable and accessible technologies, solutions or processes deployed to poor people
Many of the prizes are ‘multi-staged’ – this means there will be a number of winners awarded at the design/development stage who will be eligible to proceed for the second stage, at which point they will have had to demonstrate that they have implemented their newly developed solution, process or technology. As such, it is likely this target will also be exceeded, however, it is difficult to predict the results at this early stage.
At least £35m of new private investment in technologies and business models attracted in
Through the design phase, the team calculated the sum across all innovation prizes to provide an overall new investment potential of £318 million. This may be reduced by moving Clean City to an African country (rather than its original location of India). Further work on assessing this indicator is required once the Clean City in-country consultation process has concluded.
At least 50% of entrants applying for prizes are new teams/organisations to DFID’s existing portfolio of grantees in this area
This indicator is also on track to achieve this target – particularly in the areas where DFID does not have a currently programme either in that thematic area (non-revenue water, LPG cooking) or in the chosen country (urban sanitation in Ghana). Further work on assessing this indicator is required once local prize implementation partners are chosen and communication strategies are developed.

Overall output score and description
A – met expections
The programme has met its current milestones. At this early stage, the programme is on track to meet the agreed output targets, even though prize design has taken longer than originally anticipated. At the end of March 2015, the programme has developed five prize areas across the three themes (energy access, WASH and climate adaptation) that trial different prize approaches in different contexts. Of these, four have nearly completed detailed design and are on a path to launch in 2015, with the fifth concept also aiming to launch in 2015, following the completion of the in-country consultation. The programme is also on target to meet its research publication objectives, with four papers to be published in April 2015 (at time of writing these were with the publishers), and M&E frameworks being finalised alongside the prize design.
Key lessons
Key lessons that have emerged over the past 12 months provide valuable insights for other prize programmes, as well as innovation programmes more broadly. These include:
- Priority problems in each sector are often related to challenges in the broader innovation systems (lack of collaboration between actors, inefficient policies, lack of end-user demand) rather than a need for specific new ideas or technologies. Techologies and solutions exist, but individual actors do not appear to be incentivised to collaborate with other actors to implement solutions;
- Prize design takes a long time (around 8 months) and requires considerable stakeholder engagement to effectively understand the problem landscape in relation to innovations systems rather than technology invention;
- A diverse programme team adds value both to design and implementation, and from a learning perspective, but can slow progress;
- A high level of management input is required to support programme delivery; and
- Establishing M&E frameworks is a challenging, iterative process during prize design, but can support design by ensuring outputs can be effectively measured.
In addition, the learning agenda of the programme has been found to have greater relevance than first expected. Several institutions have expressed interest in joining the conversation on the potential role of innovation prizes and awards to support development. This interest provides a rationale to keep the documentation and dissemination of lesson learning a high priority.

Key actions
Given the importance of learning and research uptake in the programme, and the high degree of interest across multiple stakeholders, it is recommended that an additional outcome indicator should be added: “Discussions among key stakeholders around innovation prizes in development or for social outcomes that refer to the programme”. The communications lead from IMC will work with DFID’s Evidence into Action team to identify appropriate measures for this outcome indicator. In addition, a number of the output indicators will be reworded to reflect the emphasis on learning – this is described under each output summary below.

Key actions over the next 12 months:
- In April, the programme will be launching four research papers – one on each thematic area and a framework to guide others through the option of using innovation prizes for development.
- In May, three prizes will be launched (Clean City, Dream Pipe and one Clean Cooking prize).
- The remaining prizes will be launched between June and September 2015.
- M&E frameworks for each individual prize must be completed before they are launched. The M&E framework for the programme as a whole will also need to be completed before the next annual review.
- Finally, stakeholder engagement will need to ramp up, both as part of the individual prizes to stimulate participation, but also with other potential donors and funders to increase the impact of the programme.

Has the logframe been updated since the last review?
The logframe has not been updated in this first 12 months. Following this annual review, a number of the output indicators will be reworded to reflect the importance of learning in the programme and to include indicators on research uptake activities. In addition, a new outcome indicator will be added to monitor research outreach and uptake performance, as noted above.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Five innovation prizes launched and three successfully awarded
Output number per LF		1	Output Score	A
Risk:		High	Impact weighting (%):	71
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicators		Milestones	Progress
1.1	Prize implementation plans, resources and tools in place	Innovation prize design teams in place and operational in 2014/15 / Prize implementation and steering committees in place in 2015/16	Achieved / On track
1.2	Prizes launched	Five prizes launched in 2015/16	On track
1.3	Prizes awarded	Two prizes concluded and at least one awarded in 2015/16	On track

Key Points
At the end of March 2015, the programme has developed five prize areas across the three themes (energy access, WASH and climate adaptation) that trial different prize approaches in different contexts. Of these, four have nearly completed detailed design and are on a path to launch in 2015:
1. Dream Pipe: global prize for a new financing mechanism for non-revenue water
2. Clean Cooking: 3 prizes in support of new policy legislation for LPG and clean cooking in Ghana
3. Adaptation at Scale: award community adaptation activities that are replicated and scaled in Nepal
4. Climate Information: demand-driven, actionable climate information for low-income households in Kenya
The exception is Clean City (prize for urban sanitation solutions implemented in small towns) which was originally planned to launch in India. However, uncertainty relating to new DFID funding in India brought progress to a halt. As such, alternative locations were explored and, following consultation with various contacts (including donors, consultants, or government representatives), Ghana was selected as a suitable alternative. This would also allow us to test running multiple prizes in a single country. In-country consultation will take place in May, with the aim of launching the prize at AfricanSan in end May.

A number of the prizes being developed will be staged, such that at least two stage one prizes will be awarded by the end of 2015/16.

Summary of responses to issues raised in previous annual reviews (where relevant)
Not relevant – this is the first annual review.

Recommendations
The programme is on track to meet this output. Momentum must be maintained throughout 2015, not just for prize launch but for engaging with partners and potential funders, and to ensure maximum value is derived from the implementation of all prizes. Sufficient time and resources need to be given to the theme leaders to continue effective stakeholder engagement and oversight into prize design and implementation. Realistic work plans that take account of resource constraints and resolve them where possible must be in place and followed by all team members.

Output Title	At least 10 papers produced, five on the design process and five evaluating each prize, and disseminated to key stakeholders
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	19
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicators		Milestones	Progress
2.1	Number of high quality papers published documenting the research into prize design process, for each topic, to coincide with the launch of a prize	Four papers disseminated in 2015/16 / One paper disseminated in 2016/17	On track / On track
2.2	Number of high quality evaluative research paper an analysis published following final evaluation of individual prizes- must include details of “failed” projects	One disseminated by 2017/18 / Four disseminated by 2018/19	On track / On track

Key Points
Five papers on the design process have been developed as follows:
1. A framework for using innovation prizes in a developing country context
2. Addressing problems in energy access through the use of innovation prizes
3. A role for innovation prizes to support adaptation to climate change? An analysis of challenges, opportunities and conditions
4. Can innovation prizes help address water and sanitation challenges?
5. Designing monitoring and evaluation frameworks for innovation prizes
At the end of March 2015, the first four top-publishers were with editors and publishers and are expected to be published in April 2015. The team are aiming to launch the papers at an upcoming Nesta prize event at the end of April 2015. The fifth paper on M&E of innovation prizes will be written toward the latter part of 2015 once all M&E frameworks for all prizes are in place.

Five evaluation papers will have their outlines developed upon conclusion of the M&E framework for each prize. This is expected to be in place by December 2015.

Summary of responses to issues raised in previous annual reviews (where relevant)
Not relevant – this is the first annual review.

Recommendations
In order to capture the importance of learning and research uptake, it is suggested that this output be reworded to: “Learning on effective prize design and implementation of innovation prizes aiming to support low income households is accessed” and include the two indicators above, as well as an indicator to measure the number of key stakeholders (such as other donors, funders and implementers) engaging with the research publications (via social media, participation at events, etc.). We will work with DFID’s Evidence into Action team to design appropriate measures for this indicator and update the logframe will accordingly.

The launch and dissemination of the four research papers is a high priority for the next few months, particularly as the first prizes aim to be launched in May 2015. Programme-level communications is also crucial to engage with interested stakeholders, and share the potential for innovation prizes as learnt so far by the programme. The communications and outreach strategy will need to ramp up to engage both potential prize participants as well as donors and funders who may be interested in investing in prize participants or replicating the prize.

Output Title	At least three papers on the value and use of different innovation prizes tested by the programme disseminated to key stakeholders
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	11
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator		Milestones	Progress
3.1	Number of high quality papers published on the value and use of prizes for development and environment	Three papers disseminated in 2017/18	On track
3.2	Number prize types (e.g. staged, proportional, large, etc.) tested	At least three prize types contributing to evidence base	On track

Key Points
Over the past 12 months it has become apparent that there is very little evidence on the impact of prizes for development. While a number of organisations and instutions are deploying prizes to address development challenges, there exists no best practice or standard for evaluating the impact of these. This output ensures Ideas to Impact addresses that evidence gap by publishing high quality papers on the impact of prizes for development, drawing on findings across the different themes and prize types.

A research framework has been developed and, on completion of the M&E frameworks for each prize over the coming months, the framework will be turned into a research plan. The papers are likely to be finalised towards the end of the programme in 2018/19 when the lessons have been learnt across the various prize types tested.

There is no definitive catogorisation of prizes, a vast range of groupings exist in the literature. Defined by intended prize outcomes, the programme is on track to test the following prize types:
- Public education (Clean Cooking)
- Market stimulation (Clean Cooking)
- Public sector / public-private partnership (Clean City and Dream Pipe)
- User-led innovation (Climate Information)
- Solution replication (Adaptation to Scale)

Summary of responses to issues raised in previous annual reviews (where relevant)
Not relevant – this is the first annual review.

Recommendations
To capture the importance of learning and research uptake, it is suggested that this output be reworded to: “Learning about cross cutting issues on the value and use of different innovation prizes tested by the programme is made available to key stakeholders”.

In addition, the M&E frameworks will need to continue adapting as the prizes are designed, with early baseline capture a priority pre-launch. As such, three M&E frameworks will need to be finalised for May 2015 (Clean Cooking, Clean City and Dream Pipe), the remaining two M&E frameworks will need to be finalised for September 2015. The programme team are on track, but will need to be sure this doesn’t slip given the high amount of external interest in the M&E process.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
Up to March 2015, programme activities have been concentrated on design work for the programme. This phase has been successful with no financial anomalies to contend with. There have been no unexpected costs and so far the programme is on track. The main cost drivers throughout the past 12 months have been programme management in the form of core project team, advisors and support team. Very little delegation of tasks was possible during this first year due to the complex and untested nature of the programme, and the need for experienced thematic leads and prize designers with specialist skills. Over 75% of the design work done has been undertaken by the team proposed in the original programme proposal aligning with agreed benchmarked fees. We expect the key cost drivers to change once the prizes are launched, and the full implementation of the project starts later in 2015.

This project uses a funding mechanism that is new to the DFID Climate research Team in the form of milestone payments underwritten by actual expenditure and agreed sign-off by DFID for each invoice submitted by IMC. IMC have provided a detailed and comprehensive financial plan which builds on the milestone payments proposal contained in the original contract. IMC have also provided payment forecasts on demand from DFID and have been very accurate, reliable and timely when submitting invoices.

VfM performance compared to the original VfM proposition in the business case
The Ideas to Impact team have illustrated stringent application of a methodology to ensure that VfM for the project is monitored and reported on. Drawing on ITAD’s expertise in M&E, the team have identifed key costs driving an assessment of Economy, Efficiency and Effectiveness of the programme. Indications of these key costs will allow DFID and others to assess the VfM across the whole programme, as well as of the individual prizes. As some indicators will vary considerably by prize type and location, they are there to build evidence rather than make a judgement call between the different prizes.

Under Economy indicators for fee rates and budget allocations (programme versus admin spend) will be monitored and measured. Under Efficiency indicators for budget allocations and management systems (e.g. achievements against work plans, etc.) will be monitored and measured. The value for money indicators for effectiveness will be developed along with the M&E frameworks for each prize due by end of September 2015. The figure below illustrates the indicator dignostic being worked-up to categorise the various VfM metrics that will be used in this programme going forward (the numbers represented the indicators being designed which are not listed here, but can be found in the Ideas to Impact Annual Report 2015 Annex 6[4]).
[4] DFID Quest document: 4942707

Table 2: Indicator Diagnostic for Economy and Efficiency

Given the stage of the programme, it is too early to assess the VfM for this project, apart from the accuracy of the financial information provided by IMC.

Assessment of whether the programme continues to represent value for money
At this early stage, it is deemed that the programme continues to represent value for money, however, this assessment will be much more meaningful in 12 months time as the prizes are launched.

Quality of financial management
IMC have provided clear, detailed and precise financial information that is very easy to read and analyse. After brief discussion and guidance from DFID, they have produced the forecast financial plan in the form that is required and will prove easy to follow.

Date of last narrative financial report	05 February 2015
Date of last audited annual statement	30 September 2014

E: RISK (½ page)

Overall risk rating
Under the RED risk framework the programme is considered high risk with the following breakdown:
Management:	Medium: given IMC is a new partner to the Climate team, and the consortium is a large mix of diverse organisations.
Technical/intellectural:	High: since innovation is inherently risky – as the programme is attempting to incentivise innovation, there is no gaurentee that the prizes will result in high-impact solutions.
Output:	High: as a new programme for DFID, there is no best practice that exists across the organisation (and very little outside DFID) on whether the programme might reach it’s intended outputs. If one prize does not work, it risks the programme as a whole not achieving its outputs.
Context:	Medium: while the programme does not intend to operate in highly challenging contexts (e.g. fragile states), it is focusing on complex problems in DFID priority countries – problems that to this day remain unaddressed.

Overview of programme risk
The programme is naturally high risk, trialling innovation prizes in new ways and new contexts. The programme takes a proactive and rigorous approach to risk management. Highly detailed risk assessments for each potential prize were undertaken and included in the Design Report submitted to DFID in October 2014[5] - a summary of the risks across the individual prizes areas are illustrated below.
[5] DFID Quest document: 4732670

Table 3: Summary risk profile of all five prize concepts

During the design phase, each risk matrix is revisited at key points (review points and quarterly meetings). The Annual Report compiled by the Ideas to Impact consortium as part of this annual review process provides an annex with an update on all risks considered to be high across the programme (including for individual prizes). In summary, all risks continue to be monitored, and many are mitigated for (where these are within the capabilities and influence of the Ideas to Impact team). All variations (from Design Report to Annual Report) relate to reduction in risk scores as a result of mitigation actions.

Outstanding actions from risk assessment
As the prize designs are finalised over the coming months prior to launch, risk assessments for both the prizes and the programme as a whole will be monitored and adjusted regularly.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The overall assessment of each output for the project is that it is on track and at this early stage is running according to plan. Robust work plans, including risks registers, are available for each prize, updated frequently as circumstances change or risks are mitigated. All financial milestones have been met in order for payments to be processed. The design phase, originally intended to run for six months, has proven to require more time (around 8 months for detailed design), illustrating that it takes around 12-18 months from initial concept to prize launch (this is similar to the experiences of USAID). This resulted in a variance to be carried forward to 2015/16. Clear action plans are in place and it is expected that this will be resolved by September 2015. DFID will monitor this.

Performance of partnership(s)
The partnership between DFID and the entire Ideas to Impact consortium is very strong and effective one – very encouraging at this point given the complexity and novelty of the programme, both to DFID and the consortium members (not to mention anywhere in the world). As the programme lead, IMC provide regular updates on project progress, including meeting minutes and action points from both quarterly meetings as well as adhoc meetings. IMC Worldwide is a strong delivery partner, illustrated by their recent success at the 2015 British Expertise International Awards, winning the Outstanding International Business (SME) Award. Communication lines are open and accessible and requests for adhoc information by DFID are met within given deadlines and answered accordingly.

The consortium appears to work very well together, interacting with each other independently as well as when organised by the IMC team leader. The team interaction is assessed as great for solving problems; boosting morale; getting focus back onto what needs to be done; and generating ideas for strengthening the programme across all output areas. Participation by DFID in these team meetings is seen positively and helpful at providing guidance to the team and confidence that they are meeting the desired objectives of DFID.

Asset monitoring and control
No assests have been procured to date. In the next phase Ideas to Impact will procure the services of national agencies for implementation, monitoring and verification, data collection, communications and outreach. All these services will be procured in line with OJEU rules. Procurement of assets is likely to be low. For all items over £1000 three quotes will be obtained and the asset recorded on the programme’s Asset Register.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
Not relevant – this programme does not support a bilateral programme in a partner country.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
Evidence and evaluation is a crucial part of the programme and exists on multiple levels: evidence and evaluation of innovation prizes in general as a new way of achieving development outcomes, as well as evidence and evaluation for each of the five problem areas across the three themes. As the design phase for each prize has taken longer than originally anticipated, there have been delays to finalising the M&E framework, both for the individual prizes and the programme as a whole. Final M&E frameworks will be in place once prize design is concluded. ITAD are leading the M&E framework. This area is receiving a lot of external interest, particularly from donors or other funders who have used or are considering using innovation prizes to achieve development outcomes. There currently is no best practice on how prizes in development are evaluated. Anecdotal evidence suggests that the current typical measure of success of a prize is if the prize money has been deployed. This programme will therefore be setting a new standard for evaluation of prizes for development – which has generated a lot of interest from a diverse range of teams from organisations such as the Rockefeller Foundation, the Gates Foundation, USAID and the World Bank.

All the five problem areas have undergone a rigiours eight month evidence gathering and prize design process, including in-country consultation with key stakeholders such as local government, NGOs and private sector. At the conclusion of the prize design process, when the individual thematic research papers have been drafted, each concept has been independently reviewed by two respective sector experts who have critiqued but also validated the evidence base behind the areas chosen. These will be published prior to the prizes being launched to stimulate the potential solver market.

Monitoring progress throughout the review period
Over the course of the first 12 months of the programme DFID have received a number of large reports documenting progress: (1) an inception report in April 2014, within the first few weeks of the contract beign finalised; (2) mid-design report in June 2014; (3) design report in September 2014; and (4) Annual Review report in April 2015 (on which this annual review draws on). In addition, we have received emails of agendas and papers for each review point meeting (4 in total so far) as well as meeting minutes and action points. DFID attends these quarterly meetings when possible. Finally, there have been countless emails and phone calls between DFID and the consortium members across the 12 months to discuss immediate needs or issues.

As mentioned above, IMC also provide regular financial information in line with DFID’s requirements for forecasting.

This annual review was written by the lead Climate and Environment Adviser (Leanne Jones) and the Programme Manager (Andrew Leslie) for the Ideas to Impact programme in the Climate team in RED, drawing from the comprehensive, 80 page Annual Report by the Ideas to Impact consortium[6] and a series of follow-up queries via telephone and email.
[6] DFID Quest document: 4942707

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process