Annual Review – post April 2018

Title: Africa Division funding to the African Agriculture Development Company (AgDevCo)
Programme Value £ (full life): £154.4m		Review Date: 15th May 2019
Programme Code: 204270	Start Date: 24th September 2013	End Date: 31st December 2023

Summary of Programme Performance
Year	2014	2015	2016	2017	2018	2019
Programme Score	A+	A	A	A+	A	A
Risk Rating	Severe	Severe	Major	Major	Major	Major

DevTracker Link to Business Case:	44827985
DevTracker Link to Log frame:	47011038

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

Over three quarters of people living in extreme poverty in Africa are located in rural areas. Two-thirds of these, mostly women, earn a living from agriculture. Investing in agribusiness (food production, processing and related services) and working with private companies to improve agriculture productivity is one of the most efficient ways to foster inclusive growth. It can also be effective in developing new manufacturing opportunities by processing of crops in rural areas and introducing new products, for example improved seeds, and financial services.
AgDevCo is a United Kingdom (UK) based agribusiness investor and project developer operating in Sub Saharan Africa. Established in 2009, it is active in nine countries, with country offices in seven. AgDevCo’s investment objective is to build profitable businesses that contribute to food security, drive economic growth and create jobs. AgDevCo fulfils a unique niche, providing capital and ongoing management and technical support to agriculture companies, accepting high risks and moderate returns. Its work is fully aligned with DFID’s Economic Development Strategy, which set out DFID’s intent to take an increasingly commercial approach to agriculture including through boosting agri-business.
A range of barriers prevent investment in the agricultural sector in Africa, even within countries with stronger enabling environments, including access to affordable finance, poor infrastructure, and low technical and management capacity. These increase investment risks and costs, and thus limit investment in the sector, particularly in greenfield and early-stage businesses. AgDevCo caters to this gap by providing early stage agriculture companies with patient capital (debt, equity and hybrid), ongoing management and tailored technical support, to overcome the various financial and technical constraints which restrict them from growing and developing agriculture markets.
The UK had committed £99.5 million to the AgDevCo programme under the central Business Case funded by the Africa Regional Department (ARD), Private Sector Department and the following Country Offices: Ghana; Malawi; Sierra Leone; Tanzania; and Zambia.[1] Additional funding of £55 million was approved in 2018 under a cost extension, bringing the total cost to £154.4 million and extending the programme until December 2023, with the objective of providing AgDevCo with the continuity of funding required to continue progress towards financial sustainability, and to transition towards attracting funding from Development Finance institutions (DFIs) and other capital providers. £1.7m has been earmarked for monitoring, evaluation, and gender focused activities.
[1] Separate business cases in Rwanda and Uganda underpin funding to AgDevCo from the respective Country Offices. A single funding agreement and monitoring and oversight system ensures coordination across DFID, with ARD leading the corporate relationship with AgDevCo. This Annual Review covers progress for DFID Africa Division funding to AgDevCo (i.e. all countries of AgDevCo operations, although a separate dedicated Annual Review process continue to be implemented in except Uganda. and Rwanda) except where explicitly stated.

Summary supporting narrative for the overall score in this review (1/2 page)

The project has scored an [A] overall, and is currently meeting expectations, in terms of delivery and achievements. It continues to operate in varied and challenging environments, resulting in a range in commercial and development impact performance across the portfolio. Both aspects should improve as the portfolio, and AgDevCo’s learnings, continue to develop and mature.

Stakeholder interviews and a field visit confirmed the unique offering and additionality that AgDevCo investment provides. The majority of DFID country teams were highly positive about the role AgDevCo is playing in country, its core competence as an investor and the impact on investees. Concerns expressed were largely limited to the risk of diminishing development impact with the shift in emphasis towards AgDevCo’s financial sustainability. The field visit provided examples of the catalytic impact that AgDevCo investments can deliver for employees, smallholders and wider market participants, subject to their ability to remain commercially viable in these challenging environments.

	Output	Assessment	Score
1	Develop or expand agribusiness enterprises that are financed, owned or operated on a commercial basis by AgDevCo	Moderately did not meet expectation. Targets on investment committed were missed for 2018 annual commitments, however $30.3m has already been committed in early 2019, well ahead of expectations, meaning this is not an area of concern. The proportion of businesses reporting improvements in earnings increased but remained below target.	B
2	Increase integration of smallholders into commercial agribusiness through access to irrigation, processing infrastructure, modern inputs, finance, markets and services	Moderately exceeded expectations. Smallholder farmers (SHFs) engaged were well above target (for both genders), however a one-off programme (Demeter) was (unintentionally) responsible for the majority. Overall targets are met when excluding Demeter, although engagement of female SHFs is slightly down.	A+
3	Increase in employment through the development of agribusiness	Met expectations. The overall target for jobs created and sustained was exceeded with sustained growth in this indicator compared to previous years. Did not meet the equality target for women employment, with only a marginal increase.	A
4	Investments meet AgDevCo’s criteria for additionality and transformational change	Met expectations. Over 70% of investments score highly for transformation or additionality. This is a fall on the previous year but remains marginally above the milestone.	A

Recommendations for the year ahead (1/2 page)

Recommendation 1: AgDevCo will continue to explore both Ventures and Growth deals across its portfolio, whilst targeting a significant majority of larger Growth deals in the short-term. In light of this, DFID should work with AgDevCo to a) monitor and explore ways in which the pipeline for future Ventures deals in these markets can be maintained and developed over the short-term, such that they can quickly be mobilised as progress with the current strategy is made; and b) explore the options for future DFID support that may be required to maintain a strong development impact approach, alongside attracting wider DFI investment.

Recommendation 2: The development impact targets and results for the indicators that are used for the contributions from DFID Rwanda (programme ID 204940) and DFID Uganda (programme ID 204012) should be integrated into the central business case logframe, to provide a full picture of AgDevCo’s performance for subsequent Annual Reviews.

Recommendation 3 – analysis of performance across the portfolio:
1. AgDevCo should provide more narrative and analysis on the significant variance seen in output performance across the portfolio in next year’s annual review, including comparison to previous years. Consistent levels of impact and outputs (for SHFs & jobs) are not expected across investments and countries (given the varied operating environment, type and maturity of investments), but a better understanding of the variation is important to AgDevCo’s and DFID’s continuous learning. Also, the one-off 2018 Demeter impact figures should be excluded from future output scoring against future logframe milestones.
2. It would be useful for AgDevCo and DFID to agree and monitor a revised approach in the parts of the portfolio where it has been particularly challenging to generate impact and/or there have been high failure rates (specifically the Ghana portfolio).
3. (From the VfM section D) It is recommended that AgDevCo provides both the development impact and financial performance for individual investments in its next annual report.

Recommendation 4 - benchmarking performance: It is recommended that DFID further builds available benchmarking evidence from comparator organisations (for both commercial, VfM and impact benchmarks), whilst noting the inherent challenges in this. DFID should therefore ensure AgDevCo is included within relevant benchmarking exercises, specifically a portfolio review of DFID funded commercial agriculture interventions and a review of risk/return profiles and hurdle rates across DFID funded investment facilities. AgDevCo should support this where possible through further collation and dissemination of industry benchmarking.

Recommendation 5: Once the transformational change assessment has been finalised (July 2019), both DFID and AgDevCo should discuss and agree suggested changes to the transformational change and additionality framework, and the extent to which it will be used in investment decisions and results reporting. This should include the scope to move beyond just an ex-ante assessment.

Recommendation 6
1. DFID should continue to build on the developments made in the country-centre relationship with AgDevCo, including the more efficient centralising of funding. As this develops, it is important that DFID country teams remain fully engaged with AgDevCo in country, including through regular discussions of the investment pipeline, even where they do not retain a direct funding line.
2. DFID country programming should further build on, and respond to, the opportunities AgDevCo investments are identifying for achieving transformational change in specific value chains. This should include DFID seeking greater alignment of supportive country programming and wider policy activity, particularly in value chains in which AgDevCo has invested.

Recommendation 7: both DFID and AgDevCo should review how AgDevCo’s theory of change fits alongside the strategic goals of International Climate Finance (ICF) funding and re-assess which ICF KPIs should be monitored and how AgDevCo captures its progress in responding to the challenges of climate change. This could include baselining AgDevCo's climate impact across operations and investments and developing plans to achieve climate related outcomes (including on carbon neutrality and climate resilience). DFID and AgDevCo will need to agree the resourcing implications of this.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Develop or expand agribusiness enterprises that are financed, owned or operated on a commercial basis by AgDevCo
Output number per LF		1	Output Score	B
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 Value of investment committed ($) (annual)	$32.00 million	$18.55 million / (substantially did not meet)
1.2 Value of investment committed ($) (cumulative)	$151.2 million	$134.3 million / (moderately did not meet)
1.3 Businesses reporting an increase in Earnings Before Interest, Taxes, Depreciation, and Amortisation (EBITDA) (%)	50%	44% / (moderately did not meet)

Provide supporting narrative for the score

1.1 and 1.2 Output 1 provides a core measure of how AgDevCo is putting DFIDs funding to work and improving the profitability of its investees. For the scope of activities assessed in this logframe, AgDevCo committed $18.6 million to 14 investments in 2018 (eight existing and six new investments), which was significantly less than the logframe milestone (at 58% of the $32 million global target). Accordingly, the total investment milestone was also missed, with 43 impact generating investments and total value of $132 million committed across the portfolio by end 2018, 89% of the log frame milestone. This follows an over-performance against the milestone in 2017. Mitigating factors highlighted included that 2018 was a year of transition for the company with the strategy shift to invest in more Growth deals and less Ventures deals[2], as well as the impacts of cost reduction measures.
[2] Growth investments are typically $5-10 million in size and can be ‘Working Capital’ or ‘Expansion’ deals for profitable businesses. Ventures investments are typically $1-5 million and can be ‘Early’ (pre-revenue), ‘Late’ (EBITDA positive) or ‘PD’ (AgDevCo as principal developer). AgDevCo management are aiming that around 80% of deals over the next 2 years should be Growth deals.

However, across the totality of AgDevCo investment (i.e. including $11 million of Uganda and Rwanda investments reported separately), commitments of $30m were made (which is on target for the business as a whole). Going forward it would make sense to bring all AgDevCo results together against a single investment. AgDevCo management noted that it has also committed a significant amount ($30.3m) of investment in early 2019 for Africa Division funding which suggests commitment rates are ahead of expectations this year and that this is not an area of concern. AgDevCo does not expect that cost reductions will further impact the commitment of expected investment. However, the number of commitments in 2018 remained bunched towards the end of the year. Delays from Board investment approval to actual disbursement of finance have continued, which pose challenges for both AgDevCo’s performance (from delays to revenue generation) and DFID’s financial management. This remains a key challenge and is discussed further in the delivery section.

Of note were the investment commitments made in Rwanda, Uganda, Sierra Leone and Kenya. These were seen by DFID country offices to have largely turned around prior concerns over investment deals not being successfully closed. Commitments were made across all active countries. The investment commitments contributed to a shifting of the portfolio in line with AgDevCo’s strategy, with the largest share of new investments being into Growth deals (particularly working capital – 47%). This is part of the drive to achieve financial sustainability (given the higher investment return to cost ratio of Growth deals). The average value of commitments to investees across the whole active portfolio has risen to just over $3 million this year (from $2.2 million last year).

1.3 The proportion of applicable companies improving their EBITDA increased from 37% in 2017 to 44% in 2018 for the ARD portfolio. Overall, declines in the indicator were seen in the Zambia and Uganda portfolios, increases in the Ghana, Malawi, Mozambique portfolios, whilst both Rwandan businesses included in the indicator improved EBITDA again this year. Zambia and Mozambique were the only portfolios reporting this indicator as below 50%. The indicator was introduced in 2016 to measure progress against the key objective of making investee businesses more profitable, also noting that AgDevCo invests in pre-profitable companies. As noted previously there are limitations with this indicator (including that absolute levels of profitability are not reflected, whilst the revenues and returns of most AgDevCo investees are volatile and subject to exogenous risks). It is important to complement assessment of this measure with progress for other measures of investment and commercial performance including return on investment in aggregate and at investor level, as well as the costs to assets ratio recorded under VfM. AgDevCo’s primary concern remains in developing and demonstrating commercially viable agri-business investments. The metric should therefore be kept under review, along with greater granularity in AgDevCo’s annual report on investee EBITDA performance to better aid assessment of this indicator.

The overall output rating for this output is a B. Whilst a number of wider points and mitigating factors are noted, it remains the case that applicable investment was below the target, with the profitability measure also remaining below target.

Lessons identified this year, and recommendations for the year ahead linked to this output

Logframe targets have been reviewed and updated during 2018 based on learning from historical performance, as per last year’s recommendation.

The shift in strategy in Sierra Leone, towards project development investments, slightly smaller investments and blending AgDevCo finance with the Smallholder Development Unit (SDU) grants was noted in last year’s report. DFID Sierra Leone’s view was that this has made a difference with a first investment completed during the year, a stronger pipeline and overall positive performance by the AgDevCo team.

AgDevCo continues to operate and invest in a very challenging environment. Interviews provided a consistent and, in most cases, strong view that AgDevCo is performing well in this context, making agribusiness investments with good potential to be both viable and developmentally catalytic. There are challenges within this, including the West Africa portfolio, which is noted further below. In its investments in 2018, AgDevCo also demonstrated that it can source and deliver a range of Growth deals, which is a core aspect of its revised strategy and a direct consequence of the drive to achieve financial sustainability. However, concerns were raised by a number of DFID teams (Malawi, Mozambique, Rwanda, Sierra Leone and Tanzania) that it will be difficult to find multiple further Growth deals in future in these markets, with the few available likely to already be receiving development finance support. These teams also felt that the additionality and strength of continued development impact relied on continued investment at the smaller end of the Ventures deal size. And that AgDevCo’s continued investment in Ventures deals will be key for retaining a developmentally impactful pipeline in these markets.

This is a challenging issue. Related aspects are noted further in the review. Following a sustained period of grant financing, and affordability questions of whether this will continue, it seems right to have shifted the focus much more onto financial sustainability. Achieving and evidencing strong commercial discipline is central to being able to attract wider financing and investment including from DFIs (as well as demonstrating confidence over the value for money of DFID development capital grants). It also supports AgDevCo’s long-term viability, which has wider benefits for building and retaining long-term, UK-based, expertise. Relatedly, the decision to exit seed investments was largely supported through interviews. However, AgDevCo are transparent that the impact of this shift is to pursue less Ventures deals, particularly over the next 2 years. This risks forgoing investment opportunities in a number of AgDevCo countries where smaller Ventures investments are likely to remain the most impactful approach, noting also the long lead-in times associated with developing the pipeline through to completed deals. It is a difficult challenge to balance long-term sustainability with catalytic development impact in the agriculture sector. However, DFID should remain actively focussed on exploring the options to maintain this balance through AgDevCo.

Recommendation 1: AgDevCo will continue to explore both Ventures and Growth deals across its portfolio, whilst targeting a significant majority of larger Growth deals in the short-term. In light of this, DFID should work with AgDevCo to a) monitor and explore ways in which the pipeline for future Ventures deals in these markets can be maintained and developed over the short-term, such that they can quickly be mobilised as progress with the current strategy is made; and b) explore the options for future DFID support that may be required to maintain a strong development impact approach, alongside attracting wider DFI investment.

Recommendation 2: The development impact targets and results for the indicators that are used for the contributions from DFID Rwanda (programme ID 204940) and DFID Uganda (programme ID 204012) should be integrated into the central business case logframe, to provide a full picture of AgDevCo’s performance for subsequent Annual Reviews.

Output Title	Increase integration of smallholders into commercial agribusinesses through access to irrigation, processing infrastructure, modern inputs, finance, markets and services
Output number per LF		2	Output Score	A+
Impact weighting (%):		35%	Impact weighting % revised since last AR?	Y (↑)

Indicator(s)	Milestone(s) for this review	Progress
2.1 Total number of smallholders engaged in agribusiness with and without formal contracts (annual): / (a) total number of farmers / (b) male farmers; / (c) female farmers; / (d) total individuals benefiting.	a) 171,781 / b) 85,890.5 / c) 85,890.5 / d) 790,192	a) 452,899 (167,520) / b) 306,120 (92,086) / c) 146,778 (75,434) / d) 2,083,335 (770,592) / Figures in brackets exclude Demeter

Provide supporting narrative for the score

2.1 The headline reported figures have significantly outperformed both the logframe milestones and last year’s performance. However, most of the increase is due to a single one-off facility with Demeter – a seed company in Malawi. AgDevCo’s one-year working capital loan facilitated Demeter’s role as a seed provider to a Malawian Government supported farmers input subsidy programme. The program is long running and would likely have gone ahead without AgDevCo investment. The long-run impact of such large-scale input-subsidy programmes for subsistence crops - and the Farm Input Subsidy Programme (FISP) in particular - is also questionable. Further, the rationale for the AgDevCo investment was not related to its expected impact but was to support scoping of a more transformational pipeline investment opportunity; similar impact cannot be expected in future. For these reasons we have also shown results excluding the Demeter impact in the figures above. Further, whilst the scoring reflects the total reported number, we advise that these figures are excluded when considering the scoring going forward and in future milestones. The reported 2018 figure also includes final numbers for investments exited during the year, which is a change in methodology from last year. This change was reflected in the revised logframe milestone (on a like-for like basis there is a slight decrease in engagement commensurate with the loss of impact from the exited investment). When excluding the Demeter project, 2018 figures are in line with milestone performance.

Significant variance is seen across the remainder of the portfolio: remaining investments in Malawi and Mozambique account for 80% of the indicator (but only a quarter of total investment value). Average Small Holder Farmer (SHF) engagement across the remainder of AgDevCo investments is much lower. This reflects the difficulty of the operating environment and the different types of impact that can be expected – as noted below. Further the impact-generating portfolio remains young (only 15% of investees are four years or older), although AgDevCo note that maturity of investments does not seem to correlate with increased SHF engagement. Results for SHF engagement in Ghana investments remained disappointing (as with jobs).

Good progress seems to have been made across the portfolio in engaging women SHFs, particularly when excluding Demeter. Over one-third of the total (an estimated 27,282 out of 75,434) is linked to a single Malawian investment, Afri-Oils a purchaser of groundnuts from smallholders which it cleans, grades and sorts for onward sale. The field visit confirmed the potential for catalytic impact from this investment – and therefore for female groundnut growers – if it can demonstrate the viability of a high-grade groundnut exporting industry. The company is pursuing an improved procurement strategy through local traders to aid this, although the potential impact of this on groundnut growers could not be assessed. Further thought should be given to increasing the engagement of female smallholders across the remaining portfolio. Across the active-only portfolio, AgDevCo report that more than half (54%) of SHFs reached are women. Jacoma’s engagement of smallholders was also explored during the field visit, which is reaching over 3,000 smallholders as an off-taker and input provider for its macadamia, paprika and chilli operations. This is further explored under output 4. The investee is also expanding its irrigation scheme (with DFID funding) to service new paprika outgrowers, which has involved significant community engagement. To support the success of this, Jacoma will also work with the outgrowers to retain and increase yields on a portion of subsistence maize crop. Side-selling remained an underlying challenge.

More generally, discussion with AgDevCo’s Smallholder Development Unit identified a range of value adding work being undertaken with smallholders across several projects. This service is provided as a separate activity with separate Mastercard Foundation funding, and whilst not tied exclusively to AgDevCo investments, is further supporting the quality and sustainability of investees smallholder engagement.

The overall output rating is A+ (moderately exceeded expectations).

Lessons identified this year, and recommendations for the year ahead linked to this output

AgDevCo has considered last year’s recommendation to better capture indirect benefits of investments for local farmers and communities, including where these are being strengthened through the Smallholder Development Unit support. These are being further explored through the separate impact assessments.

Learnings have shown that the extent and nature of smallholder engagement depends on the intervention and/or investment being pursued. For example, businesses involved in input provision will likely have a very wide SHF reach (but have a shallower impact on incomes), whereas tree crop investments tend to reach much smaller numbers of SHFs. A wide variation in this output is seen across the portfolio (and is also noted for other output and outcome indicators elsewhere). AgDevCo does not have the ability to choose between types of investment to respond to such insights, given the limited number of viable investment propositions. However, discussion between DFID and AgDevCo should continue to be proactive around the types of investment being made across the portfolio and how this is expected to feed through to impact indicators – both for outputs and outcomes. This includes whether there is a case for any flexibility in how they are applied/interpreted. The key will remain to tie this into longer-term measures and understanding of transformational impact, including that which is driven through smallholder engagement.

This output continues to provide an important snapshot of annual (and over time trend) investment reach to smallholders. Field visits (particularly to Tropha in Malawi) confirmed the efforts being made by investees to find sustainable ways of engaging and incentivising smallholders, including through outgrower schemes, notwithstanding the common challenges including side-selling that need to be overcome. The core driver for businesses remains the economic benefit of smallholder engagement. As noted above AgDevCo’s Smallholder Development Unit continues to provide a range of value adding work to complement and develop successful approaches. DFID should be proactive in learning lessons from this activity and applying them elsewhere.

Recommendation 3 – analysis of output performance across the portfolio
AgDevCo should provide more narrative and analysis on the significant variance seen in output performance across the portfolio in next year’s annual review, including comparison to previous years. Consistent levels of impact and outputs (for SHFs & jobs) are not expected across investments and countries (given the varied operating environment, type and maturity of investments), but a better understanding of the variation is important to AgDevCo’s and DFID’s continuous learning. Also, the one-off 2018 Demeter impact figures should be excluded from future output scoring against future logframe milestones.

Output Title	Increase employment through the development of agribusinesses
Output number per LF		3	Output Score	A
Impact weighting (%):		15%	Impact weighting % revised since last AR?	Y (↑)

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of jobs created and sustained (FTE) to date through exited and active investments (cumulative) / a) total / b) men / c) women	a) 9,145 / b) 4,572.5 / c) 4,572.5	a) 11,117 (122% of target) / b) 8,464 (185% of target) / c) 2,653 (58% of target)

Provide supporting narrative for the score

The overall aggregate performance against this output indicator has been strong, including under like-for-like comparison to last year (total FTE increased by 30%). As with smallholder engagement there is significant variation across the portfolio. A single investment in Tanzania (Equity for Tanzania Limited) is responsible for half (51%) of the entire aggregate and the majority of the increase from 2017. A further 5-6 investments are relatively high employment generators (with Malawi, Zambia and Mozambique portfolios covering 45% of the total) and the remaining investments generating much lower direct employment. Relatedly, half of all FTE for women are concentrated in just four investments. Taken with smallholder engagement, the Ghana portfolio remains a very low generator of FTE and therefore overall impact outputs.

EFTA’s business model is to provide equipment leasing - providing agriculture and non-agriculture machinery to small businesses on credit, with normal repayment terms of 3 years. Colleagues set out that EFTA, as a receiver of other development funds, collects a large amount of data from its businesses on the jobs and income uplift that has been created.

The overall growth and number of jobs for women remains below target. Some limited progress has been made when compared to last year (a 4 percentage point increase in the share of jobs for women in active investments) and our interviews consistently highlighted that AgDevCo has made genuine efforts to strengthen and mainstream a gender focussed approach into its operations and the work of investees. The 2018 Impact Report also highlighted an increase in women in formal employment. Alongside this, both the number and proportion of women in full-time jobs compared to part-time and seasonal jobs has increased, as well as a small increase in the number and proportion of women in senior management roles. The ongoing target of 50% remains challenging but appropriate. There is further to go including consideration of how gender impact can feature in investment decisions. This is an area of agreed focus and activity for the coming year with an associated workplan, including to address recommendations from an Environmental, Social, Governance, and Gender Audit and for example further building capacity within specialist teams.

The overall output rating for this output is A.

Lessons identified this year, and recommendations for the year ahead linked to this output

AgDevCo identified several relevant lessons over 2018. These included that the proportion of women employed into formal employment increases as commercial farms mature and add more value-adding/processing operations, as part of a wider direct correlation between an investment’s maturity and the number of jobs it sustains or creates. With the portfolio remaining relatively young, further growth and time is needed before conclusions over the scope for large-scale job generation across investment type can be drawn or used to drive investment decisions. However, job creation remains a key objective of AgDevCo investment and it is key to continue learning from impact evaluations and applying findings across the portfolio. As the impact generating portfolio matures, job creation is expected to grow more widely across the portfolio, particularly for investments in Rwanda, Uganda and Ghana. AgDevCo has not yet been able to draw conclusions on the $-efficiency of job creation from the relatively limited sample of Growth investments compared to Ventures or Seed, however the limited data suggests the cost of creating a job is higher for Growth deals.

AgDevCo remain optimistic that the performance and resulting impact of the Ghana portfolio can be turned around. In 2018 it provided 2% of FTE generation across the ARD-funded AgDevCo portfolio despite representing 20% of the investment (by value). DFID Ghana colleagues confirmed the difficult operating environment that continues to constrain investment, including wider economic conditions. However, given the disappointing results generated so far, it would be useful for AgDevCo to set out the plan and actions being taken to improve performance on this part of the portfolio.

Interviews confirmed that a challenge in assessing AgDevCo performance - both financial and impact - remains the lack of comparator organisations against which it can be readily assessed. For example, it was noted that other DFIs and impact investors investing in agriculture are typically investing in less risky businesses and investing at the top end of the scale of Growth investments. AgDevCo’s combination of patient capital together with business development and agronomy TA, invested into early stage agri-business remains relatively unique. However, it is important to try to build understanding of comparator metrics as far as possible. AgDevCo is engaged with the Council on Smallholder Agricultural Financing (CSAF) which has collated a certain amount of benchmarking analysis for the sector, including on impairment rates. Further analysis and benchmarking will be important for DFID’s next Annual Review and for further building the case around the nature of future DFID support. Some comparator organisations highlighted include: Root Capital, Opportunity, SliverStreet, Norfund, Injaro, Acumen, Phatisa.

Recommendation 3 – analysis of performance across portfolio (continued)
It would be useful for AgDevCo and DFID to agree and monitor a revised approach in the parts of the portfolio where it has been particularly challenging to generate impact and/or there have been high failure rates (for example the Ghana portfolio).

Recommendation 4 - benchmarking performance:
It is recommended that DIFD further builds available benchmarking evidence from comparator organisations (for both commercial, VfM and impact benchmarks), whilst noting the inherent challenges in this. DFID should therefore ensure AgDevCo is included within relevant benchmarking exercises, specifically a portfolio review of DFID funded commercial agriculture interventions and a review of risk/return profiles and hurdle rates across DFID supported investment facilities. AgDevCo should support this where possible through further collation and dissemination of industry benchmarking.

Output Title	Investments meet AgDevCo’s criteria for additionality and transformational change
Output number per LF		4	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1 Percentage of investments achieving a score of 3 or higher on Level of Transformational Score (measured by number of investments)	66%	71% (108% of target)
4.2 Percentage of investments achieving a score of 3 or higher on Level of Additionality Score (measured by number of investments)	66%	74% (112% of target)

	Additionality Score			Transformational Score
1	Profitable business, attractive to all commercial investors		1	Investment will lead to operational improvements to existing business models and/or incremental improvements to livelihoods
2	EBIT-positive business, attractive to DFIs and higher-risk private equity firms		2	Investment in a new business entering an existing market and/or moderate improvement of livelihoods from existing activities
3	Negative EBITDA business, difficult to attract commercial capital as there is still no proof that the business model is viable		3	Investment in a new business model or route to market for existing products and/or new sources of income for beneficiaries alongside existing economic activities
4	Greenfield/start-ups, almost no appetite from any type of investor		4	Investment in new markets/products and/or significant improvement in livelihoods due to new economic opportunities and improved income

Provide supporting narrative for the score

Reported performance has remained positive against this indicator. However, it has consistently fallen each year for the past three years (the Transformation score was 80% 2017 and 86% 2016; the Additionality score 88% 2017 and 89% 2016). This trend is expected to further continue with the shift towards more Growth deals.

There was a consistent view across all DFID country teams that AgDevCo financing and support remains highly additional in country with few alternative or comparable financing sources available to the early stage agribusinesses receiving AgDevCo investment. It was seen that AgDevCo continues to bridge a gap between early stage grant/challenge fund type funding and large-scale commercial bank or DFI investment. The combination of this financing - particularly the ability to provide equity capital - with significant TA expertise continues to provide a unique and catalytic offer. Discussion with investees during the field visit further confirmed this, along with showcasing the unique support that AgDevCo provides where it has a strong on the ground presence and local market knowledge. The critical role that such local expertise plays in sourcing potentially transformational deals was also clear.

Following last year’s annual review, the transformational change scoring methodology has been reviewed as part of a portfolio assessment on transformational change, in which a new model has been proposed. This will identify the main pillars through which transformation is created and how this can be captured. The field visit provided evidence of transformational change potential. For example, Jacoma farms in northern Malawi is developing significant operations across macadamia nuts, paprika and chillies, including for export, with some local processing and value addition. This is helping to demonstrate the viability of these crops, in addition to creating direct employment (1,000 full time and seasonal workers) and a market for local smallholders and outgrowers (around 3,000) whom it is supporting to move into these cash crops. This includes through off-taking, input and seedling provision and development of outgrower schemes. The success of the farm has increased the case for a separate processing and cracking factory in central Malawi, which could further support growth of the macadamia value chain. A further (unintended) impact seen was the effect the business is having on improving access to financial services for employees: the business now effectively operates a savings scheme for its employees who also all now have bank accounts and increased access to ATMs.

The overall progress for this indicator has remained slightly above target and is around the boundary for A and A+ in terms of scoring. Considering the decline compared to last year (which received A+), driven by the scores for new investments, the overall output rating for this output is A (met expectations).

Lessons identified this year, and recommendations for the year ahead linked to this output

Interviews and the field visit further highlighted the importance of AgDevCo’s staff on the ground and the role they play in delivering both sourcing and delivering deals that are genuinely additional. In discussion AgDevCo management confirmed the retention and recruitment of effective resource in-country will be prioritised against cost reductions. We agree this is critical.

As AgDevCo moves up the investment scale the additionality of its investment is likely to further reduce, with potential for some competition with other capital providers, and a more limited pool of potential Growth deals in certain countries. AgDevCo management were cognisant of the risks of a potential loss of the uniqueness and development impact of their approach. They confirmed that Ventures deals will remain the main medium-term focus in a number of markets. However, given the high failure rates of Ventures-scale investments seen across the industry (around 20%), these will need to be cross-subsidised by greater Growth deals elsewhere. This was discussed under output 1 and recommendation 1.

Alongside capturing outputs on job creation and direct smallholder farmer impacts, it is the sustained success of investments that are transformational - through their catalysing of new markets and value chains - that will deliver sustained outcomes and development impact. As noted previously this indicator is ex-ante and it is important to find a method of tracking whether investments remain transformational over time. The transformational impact studies provide useful data and examples which should be disseminated across AgDevCo and DFID teams.

The extent to which investments can deliver transformational change will also depend on other actors (the crowding in of other investors, removal of regulatory/government bottlenecks and supportive community engagement). Related to this, last year’s annual review (under output 1) noted the importance of exploring further linkages between AgDevCo and DFID country portfolios. This year’s interviews highlighted the strong alignment country offices felt between AgDevCo investment activity and DFID objectives for private sector and agriculture development. In many cases AgDevCo experience is helping shape future DFID programming priorities. However, this should be further explored and built upon, to make sure DFID programming is actively addressing bottlenecks that might otherwise constrain the scope for transformational change and market development in the areas where AgDevCo is investing. For example, in Malawi DFID programming is looking to support the macadamia value chain, whilst AgDevCo’s investment activity in Rwanda and Uganda is well integrated with wider market development programming.

A key factor in this is ensuring country offices retain strong links and a sense of responsibility towards AgDevCo activity in country, as funding has been centralised. It is important to maintain a model of working between DFID centre and country operations that enables continued (and increasingly) close collaboration with AgDevCo teams, in particular for those countries whose bilateral funding has reduced.

Recommendation 5: once the transformational change assessment has been finalised (July 2019), both DFID and AgDevCo should discuss and agree suggested changes to the transformational change and additionality framework, and the extent to which it will be used in investment decisions and results reporting. This should include scope to move beyond just an ex-ante assessment.

Recommendation 6
1. DFID should continue to build on the developments made in the country-centre relationship with AgDevCo, including the more efficient centralising of funding. As this develops, it is important that DFID country teams remain fully engaged with AgDevCo in country, including through regular discussions of the investment pipeline, even where they do not retain a direct funding line.
2. DFID country programming should further build on, and respond to, the opportunities AgDevCo investments are identifying for achieving transformational change in specific value chains. This should include DFID seeking greater alignment of supportive country programming and wider policy activity, particularly in value chains in which AgDevCo has invested.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

AgDevCo’s updated Theory of Change remains as set out in the diagram below. This illustrates how AgDevCo’s capital investment and expertise delivers impact through the direct results of investees’ improved business and through enabling wider transformational change through demonstrating and creating new markets, enabling the growth of viable value chains and supporting community transformation.

The global logframe has seen major changes to outcome indicators which are set out further below.
The theory of change and related assumptions have remained as set out above. The scope and nature of transformational change is undergoing a review which includes detailed case studies of two specific investments (Tropha and Saise) and should further inform any revisions to the theory of change. However, through 2018 AgDevCo has continued to both clarify and enact its new strategy to shift the balance of its investments towards larger Growth deals, reducing new Ventures deals and exiting Seed investments. Further assessment will be needed to assess the extent to which this requires a revised set of assumptions of how outputs and outcomes are delivered and feed through into impact.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

Indicator(s)		Milestone(s) for 2018	Progress	Met?
1	Capital leveraged ($) (annual)	$30.00 million	$22.18 million	No
	Capital leveraged ($) (cumulative)	$193.35 million	$185.04 million	No
2	Direct increases in annual household income ($ million) (annual)	$39.46 million	$50.99 million	Yes
2.1	Incremental outgrower income ($) (annual)	$28.30 million	$35.82 million	Yes
2.2	Incremental employee income ($) (annual)	$11.16 million	$15.17 million	Yes
3	Value of exports ($) (annual)	$5.30 million	$4.92 million	No
4	% costs covered by income from investments	18%	23%	Yes

AgDevCo is on track against three of the four outcome indicators. For outcome 3, despite missing the target the level of achievement is within 10% of the target and judged to be broadly on track having increased by a third compared to 2017.

Capital leveraged by applicable AgDevCo investments was below the 2018 milestone, and the milestone for cumulative capital leveraged was therefore also missed. $22 million was leveraged from other sources. Whilst this was below target it was in line with the target leverage ratio when compared to capital invested ($18.5 million). Further capital leveraged for Rwanda and Uganda investments was only around $1 million in 2018, much less than the new investment in those countries. As with the output for investment committed, it is understood that 2019 activity is expected to rebound in line with milestones. The majority of capital leveraged was from private institutions (76% - mainly from other shareholders) with a minority from DFIs (24% - notably Root Capital and Acumen). AgDevCo remain keen to co-invest with other DFIs and there should be more scope for this across the increased number of larger Growth deals. During the field visit, an investee highlighted that AgDevCo’s investment had been important for giving CDC confidence to also come in. Interestingly, the investee noted that the involvement of AgDevCo (and CDC) had also given potential MNC buyers the comfort to fast track discussions given the importance they attach to supply chain visibility and impact.

Direct increases in household income significantly exceeded the 2018 milestone, for both employees and outgrowers. As with SHF reach, the one-off Demeter investment was an outlier, responsible for $12.7 million (35%) of total SHF income uplift. Excluding Demeter’s impact still sees the total increase in overall household income ($38 million) meet the 2018 milestone. Beyond this there is still significant variation across the portfolio. The Westfalia project’s success has resulted in a huge income uplift per SHF ($17k annual). Stakeholders noted the major success of Westfalia’s aggregation model for high quality avocado exports, albeit that this hasn’t yet been able to be replicated by other market entrants. Input providing businesses are delivering very low-income uplift for SHFs, despite their wide reach, whereas the highest levels are seen for primary production and production with value addition businesses. The challenge of delivering longer-term impact will be to grow the portfolio of smallholder engagement across businesses having a deeper impact on income.

Two thirds of employee income generated is attributable to the Tanzanian portfolio and primarily the EFTA business, as with job creation output. However, there have been increases in income uplift across all regions except Ghana and Lafco. Higher income uplift rates per job are being seen across businesses engaged in production with value addition as well as processing, which tend to hire skilled workers. Going forward AgDevCo should also provide baselines against which income uplifts are being reported to better enable an assessment of where impact is lifting beneficiaries out of poverty.

Overall, the 2018 Impact Report found that the number and proportion of women contributing to outcomes has increased across the portfolio, except for women in jobs.

The value of exports was marginally below the outcome milestone but is within 10% of the target and is judged to be broadly on track, having increased by a third compared to 2017. This remains an important measure to track. Whilst not key to all AgDevCo businesses, it is an important measure, given the need to build businesses that demonstrate the competitiveness of specific crops/value chains, crowd-in other actors and more widely support economic transformation. Further, AgDevCo’s work assessing transformational change has identified that investments working in cash crops for export markets showed more signs of transformational change than those working in food crops for domestic market. Increasing exports, or otherwise import substitution, should remain an aim for AgDevCo’s investments. Exporting businesses are also likely to be generating hard currency revenues which should reduce risk against the typical US$ lending provided – an issue highlighted in a few interviews.

Costs covered by investment revenue were also above the milestone target. This is a core focus for AgDevCo management in the drive to achieve financial sustainability and was achieved despite greater than expected impairments across the portfolio. Further efficiencies will likely be necessary, alongside the shift to greater Growth investments, to deliver AgDevCo management’s ambitious strategy. Clearly this contains a risk that such progress will negatively impact the unique offering that AgDevCo has built up; the approach taken to this should continue to be a core focus of DFID’s ongoing engagement.

Climate The previous output indicator regarding installed clean energy was removed last year. However, it remains important to better capture and mainstream climate change resilience and mitigation activities within AgDevCo investments, as part of tracking and delivering progress against International Climate Finance funding objectives. The field visit confirmed that investees are engaging in a number of activities consistent with the environmental best practices that AgDevCo requires. Economic considerations seem to be a primary driver for this, but interviews did not suggest that AgDevCo is driving an additional climate smart agenda with investees beyond the ESG focus.

Explain major changes to the logframe in the past year (1/2 page)

Major changes to the logframe were approved in February 2019 following iterative discussions between AgDevCo and DFID in 2018. The following changes were made to the logframe:

Removed Output Indicator 4.1 “level of installed capacity of clean energy” as recommended in the previous Annual Review but to keep tracking it as part of the International Climate Finance reporting. The output focused on Green Mini Grid projects linked to farms and refers to a specific investment type unlike other outputs that refer to the wider portfolio. Setting a target was deemed problematic since it depended on whether AgDevCo makes specific investments that are not part of their core mandate. As suggested below, AgDevCo should strengthen the monitoring on International Climate Finance indicators to ensure that progress is sufficiently captured. Following the removal of the output, the 10% impact weighting was redistributed equally between the “increase integration of smallholders into commercial agribusinesses” and “increase employment through the development of agribusiness”. The reason for this was to place equal weighting on beneficiary outputs as the commercial outputs required for sustainable and inclusive economic growth.

Amended Outcome Indicator 4 from “value of capital repaid to AgDevCo” to “percentage of AgDevCo costs covered by income from investments” since this is a more accurate measure of AgDevCo’s progress towards financial sustainability.

Amended the majority of milestones so that they reflect:
- The methodological improvements as AgDevCo have refined their target assumptions based on actual results in 2011-2017 rather than initial assumptions based on a smaller sample of investments at an early stage of the programme.
- The likely future mix of investments under AgDevCo’s new investments strategy, with fewer seed investments and a rebalance between growth and venture investments
- The results to be achieved with the additional funding approved in 2018 are included in the projections.

The historical data has allowed AgDevCo to refine their understanding of the impact of different types of investment and for different stages of the value chain, enabling more accurate forecasting. For example, previous estimates used assumptions about income uplift largely based on smallholder maize farmers, without differentiating for higher value produce or different stages of the value chain. AgDevCo’s 2011-2017 data suggests that investments in businesses engaged in seed production, primary production and processing generate comparatively smaller income uplift than investments in storage, distribution, and trading.

Although historical data was used to revise and refine many of the milestones, it was not used for the female beneficiary targets. AgDevCo has not yet achieved the 50% target for female beneficiaries and the aspirational target has been sustained to ensure continued focus on women’s economic empowerment.

There are still assumptions in the new model which have less of an evidence based. For example, after six years of each investment the model assumes ‘steady state’ development impact. More time series data would allow this assumption to be refined.

Describe any planned changes to the logframe as a result of this review (1/2 page)
The logframe was revised extensively as described above. Moving forward into the coming year:

DFID and AgDevCo should reflect suggested changes to the transformational change and additionality framework as per Recommendation 4.

Recommendation 7: both DFID and AgDevCo should review how AgDevCo’s theory of change fits alongside the strategic goals of the International Climate Finance (ICF) and re-assess which ICF KPIs should be monitored and how AgDevCo captures its progress in responding to the challenges of climate change. This could include baselining AgDevCo's climate impact to date across operations and investments and developing plans to achieve climate related outcomes (including on carbon neutrality and climate resilience). DFID and AgDevCo will need to agree the resourcing implications of this.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

Key cost drivers
The key cost drivers of the programme remain Fund Management and Overheads (FM&O), which were $10.6m in 2018. These costs include specialist investee support by the deal, ESG, agriculture, and enterprise development teams.
Economy, efficiency, effectiveness, and equity
The 2017 annual review recommended that the VfM framework be updated to define more clearly some of the indicators being reported and bring it in line with DFID’s latest thinking on VfM. These recommendations are reflected in the figures presented below which have also been revised retrospectively to allow year-on-year comparison. The figures for the period 2015-2017 therefore differ to those presented in previous annual reviews and are not directly comparable although the trends and conclusions drawn in previous reviews remain unchanged for all revised indicators (indicators 1-5 below). Where new indicators have been introduced (indicators 6-9), these have also been calculated respectively for previous years which allows an assessment of trend.

#	Metric	VfM Dimension	Description	2015	2016	2017	2018*
1	Fund Management cost ratio	Economy	Annual fund management (FM) costs divided by total investment funds (FUM)	2.8%	3.1%	3.3%	2.8% (2.8%)
2	Administrative cost ratio	Economy	Annual fund management (FM) and overhead (OH) costs divided by total investment funds (FUM)	6.7%	5.3%	6.1%	4.3% (4.3%)
3	Leverage ratio	Efficiency	Cumulative capital leveraged per dollar of capital invested by AgDevCo	$1.01	$1.54	$1.37	$1.38 ($1.38)
4	Investment committed per smallholder engaged	Effectiveness	Dollar of capital disbursed per SHF reached	$772	$440	$613	$209 ($556)
5	Investment committed per Full Time Equivalent (FTE) job created	Effectiveness	Dollar of capital disbursed per FTE created and sustained	$11,337	$9,042	$12,737	$8,532 ($8,480)
6	Write-offs	Effectiveness	Value of cumulative write-offs as a percentage of cumulative capital disbursements	5.8%	4.0%	4.3%	10.3% (10.3%)
7	Impairments	Effectiveness	Value of cumulative impairments as a percentage of cumulative capital disbursements (excludes KPL)	20.2%	14.8%	18.0%	24.5% (24.5%)
8	Proportion of smallholder farmers engaged which are women	Equity	Taken from logframe indicator output 2.1	35.4%	39.2%	42.0%	32.4% (45.0%)
9	Proportion of FTE jobs which are filled by women	Equity	Taken from logframe indicator output 3.1	25.5%	28.2%	26.0%	23.9% (23.8%)

Source: AgDevCo Annual Report to DFID 2018
*Figures in brackets exclude the impact of Demeter for output and outcome figures

Based on the analysis below, the programme continues to deliver good value for money.
- Economy. Both measures of economy improved between 2017 and 2018 with the admin cost ratio of 4.3% now below the 5.7% target set out in the business case.
- Efficiency. The capital leverage ratio remained almost identical to last year at 1.38 although this is above the 2018 logframe target of 1.28. The difference however is driven by lower cumulative investment by AgDevCo (actual of US$134m against a target of US$151m) against target rather than higher cumulative leveraged capital which was also below target (actual of US$185mn against target of US$193mn).
- Effectiveness. Investment per smallholder engaged and per FTE job created or sustained both improved in 2018. Estimates of the cost of creating a new job range between US$2,000-20,000 in the literature[3] suggesting the figure of US$8,480 per job created is comparable with experience elsewhere. However, to be able to measure whether this is truly cost-effective or not, information on average salary levels is needed.
  [3] Private Enterprise Programme Ethiopia (2012-20)
The write-off and impairment rates do not appear to be unduly high given AgDevCo’s relatively small portfolio of investments and the segment of the market it is servicing which make it vulnerable to changes in performance of a small number of loans. That said, the expectation should be for these metrics to improve as AgDevCo shifts its strategy towards lower risk, more bankable investments. This is recognised in its 2018 consolidated financial statement which states that 2018 performance ‘reflects the ongoing process of managing out legacy investments which were higher risk and lower return than investments made under our current strategy. Although there are some legacy assets remaining in our portfolio, 2018 is the last year in which we expect to see such large negative movements.’
Equity. AgDevCo started reporting on equity indicators for the first time in 2018. There has been a steady improvement in the proportion of smallholders engaged that are women, which is now close to being gender neutral. A similar trend has not been observed with the FTE jobs created, although AgDevCo remains committed to creating decent jobs for women through its gender policy and action plan.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

The programme continues to deliver good value for money in a difficult operating environment.
The majority of targets for VfM and development impact (smallholder farmers reached, jobs created or maintained, income uplift) are being met, although it should be noted that the greatest single factor in determining income uplift for smallholder farmers remains commodity prices which are exogenous to the programme.
That said, AgDevCo remains some way from being financially self-sustaining and will need to see a marked improvement in cost recovery in the coming years. Further, AgDevCo and DFID should keep monitoring how the change in strategic direction will affect the development impact of the programme.

Recommendation 2 (c): In this regard, it is recommended that AgDevCo provides both development impact and financial performance reporting at the individual investment level in its next annual report. This year’s report included information aggregated at the country-level, with some investment level data available through quarterly reports. The recommendation is to provide the impact and financial performance data per investment as part of the annual report. This will better enable assessment of how far positive financial performance - and hence company sustainability - is correlated with impact.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation
The overall risk continues to be major, but with an upward trajectory. This is due to AgDevCo shifting strategy towards financial sustainability for which the organisation is adjusting its investment approach. The documents reviewed and interviews indicated that AgDevCo has a good plan in place and is likely too early to determine if the proposed approach will be successful in achieving both the commercial and developmental outcomes, thus the risk is not considered severe. The major risk rating is within DFID’s appetite and reflects AgDevCo’s business model of investing in agribusinesses in Africa that cannot access finance from other institutions.

Key Risk Identified	Mitigation Strategies	Risk Assessment
AgDevCo being owned by a sole shareholder, which could discourage potential DFIs from investing in AgDevCo and foster a negative UK public perception of DFID’s continued support for AgDevCo.	The refreshed Accountable Grant Arrangement outlined the timeline for the transfer of shares between AgDevCo Ltd to the holding company AgDevCo CLG, which will be governed by both DFID, AgDevCo, and independent experts. The DFID lead advisor has regularly communicated with both DFID and AgDevCo lawyers to ensure sufficient oversight of the process.	The net risk rating has reduced to minor, and the risk should be removed from the risk register. Since 2018, all the paper work and Board members of AgDevCo CLG are now in place, and approvals have been granted by the relevant government authorities to recognise the transfer of shares.
AgDevCo not receiving funding from CDC and other DFIs when the financial position is low so DFID either loses its investment or must invest more in AgDevCo. Potential causes include perceived high risk of investing in AgDevCo or the limited profitability of agri-business investments.	AgDevCo continues to discuss with potential investors the feasibility of investing in AgDevCo. DFID continues to have discussions with CDC colleagues on their risk appetite.	The net risk rating continues to be major. DFI appetite for investing is partly dependent on the progress towards financial sustainability. Since this is the first year of the new strategy it is too early to fully assess the trajectory and so should be revisited at the end of 2019.
Ongoing trade-off between development impact and financial sustainability resulting in AgDevCo not simultaneously promoting poverty reduction and economic growth. Potential causes include limited staff capacity in learner structure, and management choices to promote financial sustainability over poverty reduction.	DFID monitors AgDevCo’s portfolio for additionality and impact, including feedback from country offices. AgDevCo commissions development impact studies, with oversight from DFID to ensure robust methodology.	The net risk rating continues to be major. As above, since it is the first year of the new strategy it is too early to fully assess whether the risk is materialising. In 2018, AgDevCo sustained positive progress towards achieving the developmental objectives but has not fully met the commercial targets. As more of AgDevCo’s investment mature this will need to be monitored closely.
At the country level, standards for environmental, social, and governance safeguards are lower than international best practice. Social risks include disputes over land, child labour, poor employment practices, and disputes over access to resources and services that result in harm to individuals. Environmental risks can lead to problems over water resourcing, land use, contamination of land/water systems and public environmental health issues.	AgDevCo implements DFID’s due diligence recommendations and refreshed Accountable Grant Arrangement to further strengthen its ESG processes. AgDevCo undertakes an ESG and gender audit. Both AgDevco and DFID monitor potential risks quarterly through the Steering Committee meetings.	The net risk rating continues to be moderate but with a downward trajectory as AgDevCo’s ESG management system has been strengthened to include an additional team member, communication with downstream partners, and further rollout of ESG assessments.
AgDevCo accumulates large cash balances up to 2021 resulting in AgDevCo holding DFID funds in advance of need and loss of DFID funding if there is a financial crash.	AgDevCo uses short to medium term cash deposit and uses any gain to offset costs paid for by DFID. Also, if investments fall through the amount is netted from amounts requested from DFID.	The net risk rating has increased from moderate to major. AgDevCo has accumulated higher than anticipated cash balances, partly due to slower than expected disbursement rates. As suggested in the financial performance section, both DFID and AgDevCo should revisit the mitigation strategies to ensure they are effective.

AgDevCo and DFID also monitor the contextual risks of extreme weather conditions and fluctuations in the forex market every quarter through the Steering Committee. Since AgDevCo makes investments in USD and is specialised in agri-businesses, the programme is highly sensitive to these contextual risks. Fluctuations in the forex market were a particular concern for DFID’s disbursements to AgDevCo due to fluctuations between USD and GBP, and also for AgDevCo’s investments in Uganda, Zambia, and Ghana, Mozambique. Extreme weather has also impacted the majority of countries, with particular concerns highlighted for Mozambique, Malawi, and Zambia.

Risks are monitored quarterly through a Steering Committee chaired by the DFID SRO and attended by AgDevCo HQ, DFID Africa Regional Department, and DFID country offices. Both DFID and AgDevCo have separate risks registers that are updated, shared, and discussed at the Steering Committee meetings. A delivery chain risk map is now also updated quarterly following each disbursement. DFID country offices also escalate risks on an ad-hoc basis to the Africa Regional Department as needed. For example, DFID Mozambique, Malawi, and Sierra Leone expressed concern regarding the potential trade-off between financial sustainability and development impact, which was discussed with follow up actions agreed.

In 2018, AgDevCo made significant progress in strengthening risk management and the ESG management process. Improvements included:
- Recruiting an additional person to the ESG team to increase collaboration with other specialist teams within AgDevCo, with a particular focus on investments for which they are a Controlled Entity for AgDevCo
- Completing ESG visits to 30 companies, including both existing and potential investees
- Undertaking environmental and social due diligence assessments of the two expansion countries of Cote D’Ivoire and Kenya.
- Environmental and Social Management System reviews and action plans have now been developed for approximately half the active investment portfolio.
- Introducing a revised serious incident reporting mechanism, which has been communicated to AgDevCo staff and investees to enable timely escalation of these risks.
- AgDevCo sent their Code of Conduct and Crop Protection Policy to all active investees and asked them to read and note alignment with AgDevCo’s standards

In 2018, there were several DFID and AgDevCo risk assessments. DFID conducted a due diligence assessment as part of reviewing implementing partners’ systems and processes every three years, and an enhanced due diligence assessment to focus on sexual abuse, exploitation and harassment as part of DFID’s renewed focus on these risks. The recommendations for the major risks were included in the refreshed Accountable Grant Arrangement, and AgDevCo has implemented all of these. AgDevCo has also made good progress on the recommendations related to the moderate risks, however high cash balances continue to be a risk and has increased to a major risk rating.

Following DFID’s Internal Audit Department 2017 assessment of DFID’s Africa Regional Department’s oversight of the AgDevCo programme, all project recommendations have been implemented. Despite this, there are three Africa Regional portfolio recommendations which are expected to be implemented by the end of June 2019. These are:
- Escalation of key risks to DFID Africa Regional Department’s portfolio board, such as the high cash balances
- Providing more granular detail on potential fraud risks within the programme risk matrix
- Consider disaggregation of value for money indicators by country, which has been explored as part of this Annual Review. The Economic Advisor made an alternative suggestion to annually report the impact alongside the financial performance data per investment to better enable assessment of how far positive financial performance – and hence company sustainability – is correlated with impact.

In 2018, AgDevCo also commissioned a Gender and ESG Audit, which found AgDevCo had made good progress in these areas but that the gender policies and action plan could be better integrated into other business areas. The assessment also highlighted the need to recalibrate internal resources to ensure maximise effectiveness with the limited staff capacity. The draft report has been discussed with DFID and AgDevCo intends to provide updates through quarterly meetings on the feasibility of the recommendations and progress made for both integrating gender within the portfolio and mitigating safeguarding risks.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

Delivery Performance:
Overall, DFID teams have found AgDevCo to be a responsive partner that regularly communicates with one country office stating it was a “healthy, open, and transparent” relationship. Both DFID HQ and country offices valued the combined expertise of AgDevCo staff citing the mix of investment, agriculture, and smallholder engagement as a key comparative advantage. DFID country offices also valued AgDevCo staff country presence and considered this as important for being able to proactively identify good investments, ensure quality engagement in country, and to mitigate risks.

As noted in section A, stakeholder interviews and a field visit confirmed the relatively unique offering and additionality that AgDevCo investment provides. The majority of DFID country teams were highly positive about the role AgDevCo is playing in country, its core competence as an investor and the impact on investees. Interviews revealed that current coordination with other DFID programmes varied between countries, and concerns were raised by some DFID country offices regarding AgDevCo’s continued additionality with the shift in strategy. The quality of investments in terms of both commercial and development impact criteria also varied between countries. Some countries, such as Malawi, have made good progress for achieving both commercial and developmental success, whereas others, such as Ghana, appear to be lagging. The interviews and documents reviewed indicated that the variability is partly due to the diversity of the agribusiness market context between countries and within AgDevCo’s investment portfolio. However, moving forward both DFID and AgDevCo should ensure that consistently underperforming country portfolios are more closely monitored to help reduce the variability in performance.

In terms of areas for improvement, a few DFID country offices suggested that AgDevCo country teams could more proactively communicate potential risks which would undermine investment performance. Both DFID HQ and country offices also suggested that the timing of DFID’s disbursements could be better synced to reduce AgDevCo’s high cash balances.

Within DFID, delivery of the African Division funding to AgDevCo is coordinated by DFID HQ and country offices through quarterly Steering Committee meetings that are complemented by ad-hoc discussions. The Africa Regional Department manages the corporate strategic relationship, which has included undertaking the due diligence assessment, negotiating the refreshed Accountable Grant Agreement, and managing the disbursement process. DFID country offices maintain the strategic relationships with AgDevCo and monitor the portfolio performance in country. This model has introduced staff efficiencies in reducing duplication of assessments and corporate processes. However, interviews revealed the novel set up can create confusion in terms of roles and responsibilities, and that coordination could be strengthened. Several interviewees also noted that as DFID moves towards using a flexible centralised funding pot rather than separated earmarked funds that the existing arrangements for DFID country engagement and management may not be sustainable due to reduced DFID staff capacity at the country level.

Commercial Performance:
DFID provides funding to AgDevCo through an Accountable Grant Arrangement, which was refreshed in December 2018 following approval of an additional funding for AgDevCo. The additional funding included: £55m from Africa Division (programme 204270); £6m from DFID Uganda (programme 204012); and £4.9m from DFID Malawi (programme 203824). The refreshed Accountable Grant Arrangement includes DFID’s new standard provisions that further clarify DFID’s expectations for safeguarding, gender equality reporting, and delivery chain risk mapping. The Arrangement also includes special provisions that incorporate the key recommendations from DFID’s updated due diligence assessment.

For the original Accountable Grant Arrangement AgDevCo has fulfilled the key provisions, which included:
 Reinvesting all profits into the organisation and not shared by the members
 Providing annual evaluation of investments
 Providing a management response to the external audit within six months of the end of the financial year
 Sharing the AgDevCo Board agenda and minutes when requested

AgDevCo also shares an updated asset register annually. A spot check on asset management of the AgDevCo Malawi office confirmed good asset management practices were being implemented.

To streamline reporting and to accommodate seasonal variances AgDevCo now produces six-monthly rather than quarterly reports. AgDevCo’s reporting continues to be timely, well-structured, and provides sufficient detail on progress and key challenges.

Financial Performance:
AgDevCo strives to set ambitious annual targets and outlines the investment pipeline to DFID at the start of each calendar year, alongside the stage of investment, probability of AgDevCo Board approval, and which financial quarter AgDevCo will likely need DFID disbursements. The investment forecast is adjusted quarterly to reflect any changes, and the information is used to update the delivery chain risk map. In 2018, AgDevCo provided timely quarterly forecasts, however the quarterly investment forecasts were not consistently accurate with at least one investment change each time that created highly volatile forecasts and significant variances. Consequently, there is a need to review the forecasting strategies to ensure that the figures are more realistic.

Core costs:
These include overhead costs, fund management and specialist teams such as the agriculture investee support team. In 2018, the net core costs overall were $10,607,000, which was $1,385,311 (15%) higher than initially budgeted. This was primarily due to lower than anticipated investment income to cover the core costs, higher than expected restructuring costs related to redundancies, and a reallocation of staff resources to fund management from project development.

Investments:
Despite the shift in strategy AgDevCo were able to commit $18.5m of additional Africa Division funding in 2018 against a global target of $27.5m[4]. Alongside these commitments, AgDevCo committed an additional $11.1m through funding provided by DFID Rwanda and DFID Uganda, resulting in AgDevCo surpassing the overall target at $29.6m. At least one new investment was approved in each country except for Tanzania. Zambia had the highest number of investments but also the smallest average deal size. In terms of the value of each investment commitment, eight out of fifteen new commitments in 2018 were above $1m.
[4] The global target includes contributions from DFID Rwanda and DFID Uganda that are reported under projects 204290 and 204012

Country	Total amount of new commitments in 2018 (USD)*	Average amount of new commitments in 2018 (USD)*	No. of new commitments in 2018
Ghana	$ 4,400,129.00	$ 1,466,709.67	3
Kenya	$ 2,500,000.00	$ 2,500,000.00	1
Malawi	$ 2,070,000.00	$ 690,000.00	3
Mozambique	$ 4,075,000.00	$ 2,037,500.00	2
Sierra Leone	$ 3,000,000.00	$ 3,000,000.00	1
Zambia	$ 2,500,025.60	$ 625,006.40	4
Grand Total	$ 18,545,154.60	$ 1,324,653.90	15

*Some commitments are to additional amounts to existing investees

AgDevCo’s ability to disburse has been less successful with only $16.5m being disbursed in 2018 for the Africa Division. Delays in disbursements were primarily due to the time taken to confirm all legal, financial, and ESG requirements are met by the investees before AgDevCo finalises the legal agreement and disburses. This indicates that AgDevCo continues to appropriately screen potential investees, however this has likely impacted the rate at which the organisation can achieve financial sustainability and has resulted in higher cash balances of $79.8m.
Reflows:
AgDevCo has developed a portfolio of investments that have started generating reflows that can cover part of their ongoing management costs. In 2018, AgDevCo’s overall portfolio generated $3.313m which indicates good progress, however this is $1,213,000 lower than expected due to delays in disbursing some investments. In addition, AgDevCo received an additional $575,000 through interest rates on cash held than originally budgeted, which will need to be effectively managed to reduce the cash balance.

Overall, AgDevCo’s 2018 financial statement indicate that the AgDevCo has high cash balances and lower than anticipated reflows and, therefore, needs to progress more rapidly towards the commercial targets to achieve financial sustainability by 2023. Despite this, the documents reviewed and interviews revealed the pace of this should be carefully balanced with the need to appropriately select transformative investments that will achieve the desired development impact and retain the mix of staff expertise that have contributed to AgDevCo’s success.

Date of last narrative financial report(s)	March 2019
Date of last audited annual statement (s)	Calendar Year 2018

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)
Programme monitoring encompasses a broad set of programme information, including risks, finances, perceived value for money and activity updates as well as results. Specific details on these aspects (risk, VfM, and finance) are covered in other sections of this review so this section will focus on results monitoring and DFIDs approach to overall programmatic monitoring. The overall governance of AgDevCo through quarterly Steering Committee meetings, bi-annual narrative reports, and ad-hoc discussions ensures that issues are raised early, and DFID is adequately sighted. DFID’s oversight of AgDevCo happens at two levels:
1. Corporate level – the Africa Regional Department manages the corporate strategic relationships with AgDevCo on behalf of the Africa Division. In 2018, this included the monthly calls between the DFID Senior Advisor and AgDevCo CEO, alongside quarterly communication between the DFID programme manager and AgDevCo finance controller on the expected investment commitments.
2. Country level – DFID country offices maintain the strategic relationships with AgDevCo in country, which focuses on the results and potential blockages within the country. In 2018, this also included escalating concerns on the impact on the new strategy on AgDevCo’s ability to achieve the desired beneficiary impact.

Governance of the monitoring and evaluation component of AgDevCo has been strengthened since the previous DFID Annual Review in response to Recommendation 7. Joint quarterly meetings between DFID and AgDevCo are now held regularly, which serve as a forum to understand progress on monitoring and evaluation activities, sign off any changes in approach and increase DFID oversight of the evaluation portfolio. In addition, DFID ensures all products have been independently quality assured by technical leads in the field of impact evaluation.

AgDevCo uses a holistic ‘impact management system’ which encompasses a global log frame for results monitoring agreed with DFID (updates of which are discussed in section C), the production of an Annual Impact Report and an evaluative component focusing both at individual investment level and at portfolio level. The below diagram gives an overview of the impact management system used by AgDevCo[5]:
[5] Source: ASI/Good Economy Inception Report

The overall monitoring and evaluation approach undertaken by AgDevCo is subject to an Independent Review every 3 years, which is jointly managed by AgDevCo and DFID. The last review was undertaken in 2016 and the current independent review is underway and aims to assess the extent to which AgDevCo’s ‘impact management system’ (which encompasses results monitoring and evaluation) produces high quality data which provides credible evidence of AgDevCo’s impact and can be used to improve impact. The review methodology has primary data collection planned at 10% of the investments to verify programme results data and this field work will also be an additional chance to understand direct beneficiary feedback. The detailed data mapping work will not only provide information on the accuracy of reported data but will also test the boundaries or barriers for the data disaggregation agenda. The ability to disaggregate key beneficiary indicators will also be explored through the evaluation work. For example, through exploring the use of the Washington Group questions at the next data collection round for the longitudinal studies.

While the results of the current Independent Review will not be available for this Annual Review the inception phase has already indicated interesting findings when comparing stakeholder expectations and views of the results management system. A potential concern was highlighted that there may be a “pressure to adopt a less ‘conservative’ approach to counting impact, in the context of the ‘over-claiming’ which often happens in the impact investing industry”. This will be explored more fully in the review (including the implication that AgDevCo currently employs a ‘conservative’ approach) via a benchmarking exercise which will compare results methodologies against good practice in the impact investing sector, to better understand the extent to which impact can be counted through primary data collection versus estimation models. This aspect will be particularly pertinent for DFID to understand in the context of ongoing developments in the approach to measuring ‘job creation’ within DFID and should feed into wider work within the organisation.

Evidence and Learning (1/2 page)
AgDevCo evaluation portfolio aims to collect insightful evidence about ‘what works’ to build successful agribusinesses, improve livelihoods and create lasting economic benefits. The approach uses a mix of longitudinal studies, qualitative case studies and a multi-investment study focusing on economic transformation, summarised in Table 1 below. Methodologically, the evaluative approach experimented with traditional designs to quantify impact which were difficult in the impact investing context. For example, it’s difficult to collect any ‘pre-treatment’ data on treatment sites until the investment has been selected and with many development evaluations, control site selection is difficult. The teams have experimented with difference in difference analysis using propensity score matching to account for these issues for some studies where this feasible, in doing so methodological lessons have been learnt about the types of approaches that can be carried out in impact investing.

Table 1: Summary of evaluation products
Type	Investments	Audience	Utility
Longitudinal	GADC	AgDevCo and investee; DFID and wider impact investing sector	Measure the progress of the investment / Provide AgDevCo’s investment teams with details on the status of the investment, smallholders, and the market, which can be used to help manage the investment / Evidence base on ‘what works’
	Babator
	Uzima
Case studies	2 per year; Phata, GADC, Saise Farm, Jacoma,	AgDevCo and investee; DFID and wider impact investing sector; potential future funders of AgDevCo	Provide lessons which can be used in investment decision-making processes and show case success / Provide AgDevCo’s investment teams with details on the status of the investment, smallholders, and the market, which can be used to help manage the investment / Evidence base on ‘what works’
Multi investment study	Multiple, focus on Economic Transformational Change in current study	AgDevCo and investee; DFID and wider impact investing sector; potential future funders of AgDevCo	Feed into reviews of the transformation scoring system (as recommended in the 2017 Annual Review) / Provide lessons which can be used in investment decision-making processes / Understand the impact of AgDevCo’s work / To capture lessons on creating economic transformational change which can be shared across DFID programmes

Due to the mix of study designs, some findings will only be applicable to that investment rather than generalisable across the portfolio. While many studies are still at the baseline stage, findings have already emerged from some studies, such as Uzima, that provide useful insights for AgDevCo, DFID, and the investee. Uzima Chicken Limited is a poultry company holding exclusivity on the production, distribution and sale of a breed of chicken known to be more productive than local breeds. The below conclusions are based on small samples and there is a limitation to the study related to the time point of data collection, however indicative findings anecdotally show mixed signs of success for this investment:

- The majority of Sasso day-old chicks sold to sales agents across the whole country end up contributing to the income and nutrition of smallholder farmers.
- Whilst the average number of day-old chicks purchased by agents is lower than Uzima’s target, most agents are interested to increase their order sizes in future.
- The profitability of the Sasso birds for smallholders is reduced by the feeding advice given to them by agents as many are providing commercial feed and not relying as much on scavenging.
- AgDevCo’s gender equality targets are not yet met, but this is not surprising given the investment has only been operational for one year.
- The investment’s contribution to poverty reduction and gender equality is also limited by the profile of the smallholder customers – there may be opportunities to target poorer farmers but caution should be taken since NGOs providing chickens for free are already undermining willingness to pay.

The purpose for these case studies includes insight to ways of working and lessons to the investment team. In this case, lessons have already been acted upon due to this evaluative piece, as Uzima is currently piloting a re-designed distributional model based on these findings. The approach to learning from these studies includes AgDevCo hosting a ‘learning session’ after each study with the researchers, investment team, and investee involved to discuss what action could be taken given the findings. Whilst this is positive, it would be good to capture what changes AgDevCo has committed to given findings and for this to be discussed with DFID – particularly where findings are not being acted on.

In terms of further dissemination, once agreed with DFID the studies are all shared on the AgDevCo website and AgDevCo social media. They are printed and shared with potential investees and investors and AgDevCo is exploring sharing the studies on impact investor knowledge sharing platforms, such as BEAM Exchange, SEEP, GIIN, and Market links. AgDevCo have also established connections with TAF, CDC, and PIDG and are exploring options to participate in learning sessions for DFID.

Further routes should be used to ensure findings are used by both AgDevCo and DFID, and programme adaptation is tracked and challenged where appropriate, potentially making use of the quarterly meetings on M+E as a forum for this.

Progress on recommendations from previous reviews (1/2 page)

Overall, there has been good progress in addressing the recommendations from the previous DFID Annual Review, with those still in progress reflecting areas that need continued engagement between DFID and AgDevCo. The progress made for other assessments are included in the ‘Delivery, Commercial, and Financial Performance’ and ‘Monitoring, Evidence, and Learning’ sections.

#	Recommendation	Response
1	AgDevCo will work with DFID to review and propose updates to logframe targets, after comparing actual performance in 2013-2017 against the original development impact assumptions. This should include reviewing the methodology to score progress on EBITDA.	Complete. AgDevCo and DFID have updated the logframe to reflect the previous performance, improved understanding of the assumptions, and to include the additional results expected with the additional £55m of funding. Reviewing the EBITDA methodology score was not included in this update. The changes were approved by the Head of DFID’s Africa Regional Department following quality assurance from an Evaluation Advisor and an Economist.
2	AgDevCo, with DFID guidance, should explore how to better capture indirect relationships between AgDevCo investees and local farmers and traders, including the gender impact. They should reflect on understanding and maximising positive impact in these relationships.	In progress. AgDevCo, with oversight from DFID and EQUALS, has begun exploring the indirect relationships through the monitoring and evaluation activities. For example, in the Uzima baseline study and the transformational change assessment.
3	We recommend that Output 4 is removed from the logframe before the next Annual Review but tracking continues as part of International Climate Fund reporting. Green Mini Grids (GMG) projects are high risk, with significant regulatory uncertainty. To attach a logframe target to a specific typology of investment rather than to outputs that all investments by AgDevCo contribute to seems to be out of sync with the overall logframe approach. Moreover, GMG investments are a specific investment type, and do not form part of AgDevCo’s core investment strategy (historically and in the near future). As the previous Annual Review noted, AgDevCo would only invest in new clean energy projects where it was aligned with its core agribusiness mandate and Theory of Change. This is consistent with the fact that AgDevCo only has one completed and one ongoing clean energy deal, and has no standalone clean-energy projects in its investment pipeline.	Complete. The updated logframe has removed this indicator with an agreement to monitor progress through the annual narrative reports.
4	ARD and DFID Tanzania should work with AgDevCo to address the policy and regulatory difficulties faced by their investees. DFID could connect specific investments in off grid power generation with key national and international stakeholders including relevant DFID funded initiatives. There should be a strategy in place to assess risks, with a clear timeline to assess whether the off grid power generation investment remains viable.	In progress. AgDevCo and its partner (RVE) have communicated the policy and regulatory difficulties faced by Suma Hydro to Tanesco and the Ministry of Electricity, particularly the tariff structure. AgDevCo intends to continue monitoring the tariff policy whilst assessing the risks and measures to mitigate. Currently, AgDevCo expects that the Sumo Hydro will remain commercially viable if it is expanded from 1MW to 4MW.
5	The methodology for scoring additionality and transformational impact should be kept under review. In particular, AgDevCo and DFID should: / - Explore whether there is scope to revise and report investment transformation scores annually based on the current status of investment; / - Work together to update transformational score to reflect this new strategy [?], and consider whether there is scope to produce separate transformational scores from both business and smallholder’s perspective to capture the updated Theory of Change; / - Work together to update the additionality score to better reflect the non-capital services that AgDevCo provides investees, and the true investment risks/costs it faces - which many DFIs and commercial investors are unwilling to make; and / - Explore further defining gender considerations in transformational scores, to enable AgDevCo to assess the extent to which investments contribute to improving the life chances of women, and identify investments with strong gender dimensions that can contribute to achieving the gender targets.	In progress. AgDevCo intends to update the additionality scoring methodology following the 2019 review of AgDevCo’s M&E system, which is expected to be completed by July 2019. The transformational change scoring methodology has been reviewed as part of the portfolio assessment on transformational change, in which a new model has been proposed. A workshop was attended by both DFID and AgDevCo in April to discuss the findings and potential application within AgDevCo. Once the report is finalised, both DFID and AgDevCo will discuss and agree the framework and the extent to which it will be used in investment decisions and results reporting
6	AgDevCo and DFID should continue to work together to ensure AgDevCo’s policies and procedures on use of chemicals fully comply with DFID Smart Rules within three months of the Annual Review.	Complete. In July 2018, AgDevCo developed a new Crop Protection Policy to better comply with DFID Smart Rules. This is now part of their investment agreement for new investments and existing investees were sent the policy and have been asked to confirm that they are aware of this and will operate in line with it. The vast majority of the portfolio engaged have now done so. The policy allows for a derogation process for situations where it cannot be applied for practical operational reasons. In 2018, derogation requests were submitted from five businesses, a few which have subsequently lapsed and not required renewal.
7	DFID should increase oversight of Monitoring & Evaluation (M&E) activities during next year. In particular, DFID should work with AgDevCo to set the terms for an independent gender-sensitive review and quality assurance of its M&E processes within three months of the Annual Review. This is in line with existing agreements between AgDevCo and DFID (2016) to support AgDevCo’s own M&E function rather than running a separate evaluation.	Complete, but to continue into 2019. Throughout 2018, DFID has increased the oversight of the Monitoring and Evaluation activities through quarterly meetings, reviewing the TORs and impact reports, and soliciting feedback from EQUALS to ensure the outputs achieve the desired standard. Also in 2018, AgDevCo’s internal auditor conducted an audit of AgDevCo’s gender and ESG systems, which has been discussed with DFID. For the 2019 external review of AgDevCo’s M&E system a steering committee has been established, which includes members from AgDevCo, DFID, and EQUALS.

ANNEX: ANNUAL REVIEW PROCESS

The core review team comprised of a Senior Private Sector Development Advisor, an Economic Advisor and a Programme Manager. The team initially reviewed both DFID and AgDevCo documents and received support in the analysis from an Evaluation Advisor, Finance Analyst, and Social Development Advisor. Following this, the team interviewed each DFID country office, key AgDevCo stakeholders, and conducted a field visit to Malawi to verify and triangulate the findings.

Stakeholder group	Stakeholder engaged
DFID Head Office	Group Head/SRO – East and Central and Prosperity / Lead Advisor – Livelihoods/Private Sector / Evaluation Advisor / Finance Analyst / Social Development Advisor – gender and safeguarding / Commercial Advisor / Economic Advisor / Risk Manager / Senior Evaluation Advisor
DFID Country Offices	Ghana, Malawi, Sierra Leone, Tanzania, Zambia, Kenya, Zimbabwe, Uganda, Rwanda, and Mozambique
AgDevCo Head Office	CEO / Finance Controller / Impact Manager / Investment Manager in the Smallholder Development Unit / Head of ESG / Managing Director
Malawi Field Visit	AgDevCo Malawi Country Director / AgDevCo Malawi Receptionist / AgDevCo Malawi Finance Manager / Tropha CEO / General Manager of Thulwe Farm / Tropha Project Manager / Afri-oils Consultant

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g. on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.
The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (e.g. first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the appropriate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g. costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g. Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible e.g. categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management e.g. accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided