­­Commercial Case – ensures that the delivery route for the preferred option is commercially viable and delivers value for money:

Commercial case: Is there a clear demonstration of how value for money will be achieved through the procurement process?
Has the BC considered ways to increase local value added?

Direct procurement: Is there an assessment of the marketplace and how DFID can best use competition to drive commercial advantage?
Is the intended procurement process to support contract award set out?
Is it explained how contract and supplier performance will be managed through the life of the intervention?

Indirect procurement: Does the BC justify the funding mechanism proposed?
BC should draw on evidence in the MAR, FRAs, independent evaluations, procurement audits etc., and consider the strengths and weaknesses of partners including at local level, and including senior management (e.g. is there strong senior management cover if key people change). For multilateral partners common issues include whether management/admin fees are appropriate and disbursement rates. Different funding mechanisms include accountable grants, MoUs and formal contracts

Funding to UNOPS for Livelihoods and Food Security Trust Fund is the preferred delivery option of this business case. A detailed analysis of commercial viability of LIFT and the delivery of value for money were set out in the appraisal case.

This type of funding is regarded as an indirect procurement. UNOPS, the Fund Manager, is responsible for effective, transparent and efficient management of the Fund on behalf of the Fund Board and the Donors, and has delegated authority for the management of the Fund under the Rules and Regulations of UNOPS, and in accordance with the strategy approved by the Fund Board.

In addition to the economic appraisal in the above section, the following facts and evidences can be drawn to support the fact that it is commercially viable and has a reliable procurement system in place to retain UNOPS as the Fund Manager of LIFT.

The LIFT framework agreements with UN, and EC rules provide several safeguards to ensure value for money. With the EU as a donor partner to LIFT, financial and administrative arrangements between UNOPS and the European Community are also agreed under the EU-UN Financial and Administrative Framework Agreement (FAFA). In addition to agreement to and monitoring of international standards of audit, control and procurement, the FAFA agreement sets out a limit of 7% indirect (overhead) costs as a percentage of direct management costs. This agreement is also in operation for LIFT. Indirect costs for LIFT are fixed at 7%. In line with UN Development Group guidance on multi-donor trust funds, UNOPS receives 7% indirect costs on its direct in-county costs. On funds which are passed through to implementing partners, UNOPS receives 1% as indirect costs and implementing partners can claim up to 6% for indirect costs. The total indirect costs to LIFT do not exceed 7%.

UNOPS (LIFT) follows the LIFT Operational Guidelines (OG) for grant selection and approval, grant management, procurement etc,. The evolution of the LIFT Fund and feedback from the IPs and the Fund Board were taken into account in the development of the OG. The objective of the use of th OG is to ensure IPs are selected through a transparent and competitive process.

The Fund Manager comply with UNOPS procurement regulations based on the procurement principles of public procurement. The IPs also need to ensure to follow public procurement principles which are best value for money, fairness, integrity and transparency, effective competition, and in the best interest of organizational objectives.

In 2014, UNOPS in Myanmar underwent a due diligence assessment called the 6-Pillar Assessment with EC assessors (Ernst & Young). The design and operating effectiveness of relevant systems, controls, procedures and rules which are relevant for the procurement process at UNOPS were assessed. The EC’s Pillar Assessment reported there were no concerned areas related to the UNOPS’ management of grants and procurements.

In Burma, UNOPS is the only agency with multi-donor trust fund management capacity to manage such a diverse project activities and geographically widely spread interventions. Over the last four years, UNOPS as the fund manager of LIFT awarded a total of 93 grants to 50 Implementing Partners. The total funds spent and committed up to the end of 2014 has come to a total of USD 142 million. Operating in 170 (out of 330) townships. The International Financial Institutions (IFIs: World Bank, ADB, IFAD) have only recently established in Burma. The IFIs in Burma have limited capacity for now to take over and manage LIFT trust fund and its projects in a short time-frame, without destruction of the current project activities.

UNOPS has been managing LIFT and there have been a number of good evidence of success over the last four years. UNOPS has also built up a strong relationship with all key stakeholders - beneficiaries, IPs, DPs and the Government of Myanmar. This strong relationship is powerful and helping the interventions at all levels.

LIFT is also in the last phase of the programme since it will be phasing out in 2018-19. Given that, the replacement of fund manager may not be feasible due to a huge amount of time is required for selection of a new fund manager. Funding through NGOs and the Government are also considered but they are not the recommendable options. (the details mentioned in the appraisal case pg:xx). Therefore, it is recommended to retain UNOPS as the fund manager of LIFT.

It is however to be recorded as a less probable risk of underperforming Fund Manager but, with a high impact on the whole programme. The Donor Consortium and the Fund Board regularly monitor the performance of the Fund Manager and also LIFT projects portfolio.

## Financial Case
## Is a clear and credible disbursement schedule set out, broken down between administrative and programme costs if appropriate?
## Are there any innovative financing or tranching methods?
## Is fiduciary and corruption risk addressed robustly?
Overview of costs

According to the fund flow statement and the budget plan of LIFT as in April 2015, UNOPS has planned to programme for a total of USD 284.25 m for over four years (2015/16 -2018/19). The total commitment and soft commitment made by EC, Switzerland, and USA plus the balance budget at the end of Mar 2015 is about USD 132.46 m. The funding gap is therefore about USD 151.79 m. By this business case, the UK is proposing to contribute additional GBP100m which is equivalent to USD152 m (at an exchange rate of £1=$1.52).

The LIFT budget consists of 89% for project grants, 11% for Fund Management Cost which is consist of the cost for annual reviews, audit reviews, mid-term and project end evaluations, fund management office costs and other direct costs for consultancies, studies, etc,. Indirect costs for UNOPS are fixed at 7% as mentioned details in the Commercial Case.

Flow of funds

The recipient of payments is the UNOPS. According to the disbursement schedule which will be agreed in the bilateral MoU with UNOPS, UNOPS (LIFT) will receive contributions from DFID. The UK’s contributions to UNOPS (LIFT) are comingled with those of other Donors as a pool fund and it is spent for the project grants, FMO operation and fund management.
The LIFT funding cycle proposal for each year’s spend has been sensible and will maintain a strong and constant cash flow to meet their expenditure targets while maintaining an appropriate cash balance against contracted obligations with IPs.
DFID has practiced of making disbursement according to the budget requirement of the fund, which is determined according to the recent cash flow statement of the LIFT. The SRO makes final-decisions to disburse each and every payment.
Disbursement Schedule for GBP 100 m (~ USD 160 m) to UNOPS
Components of LIFT	2015/2016	2016/2017	2017/2018	2018/19	Total
Livelihoods and food security	GBP 15 m	GBP 20 m	GBP 15 m	GBP 10 m	GBP 60 m
Climate Adaptation and Resilience (RDEL)	GBP 6 m	GBP 10 m	GBP 10 m	GBP 6 m	GBP 32 m
Climate Adaptation and Resilience (CDEL)	GBP 6 m	GBP 2 m	-	-	GBP 8 m
Total	GBP 27 m	GBP 32 m	GBP 25 m	GBP 16 m	GBP100 m / (~USD152m)

The above allocations are made according to the current funds flow statement, and should be considered flexible within the overall budget framework and also the changes in contributions of other donors.
Affordability
DFID Burma will fund UNOPS an additional GBP100 m of which GBP 60m is from Burma’s programme resource allocation as budgeted in the refresh Operational Plan 2015/16 -2018/19 and GBP 40 m of which is from the International Climate Fund (ICF). The ICF funding has been approved at concept level.

Financial Risk and Fraud Assessment

Financial risk and fraud is considered low. All programme funds will be channelled through UNOPS which has a strong financial management and internal controls. No funds will be channelled through the government of Myanmar.

UNOPS (LIFT) underwent the 6-pillar-assessment with EC assessors (Ernst & Young) in September 2014. According to the EC’s Pillars Assessment, there were no areas of concern related to the internal control system of UNOPS.

DFID Burma has also conducted a due diligence assessment on UNOPS (LIFT) to assure the intervention through LIFT delivers intended outputs and outcomes and potential risks being identified and ensure a mitigation plan in place. The findings from the due diligence assessment confirm that the UNOPS (LIFT) and its implementing partners have in place controls to deal with financial risk and fraud. The following table highlights the risks to be monitored and actions which should be progressed to mitigate risks.

Rating / critical/high/ medium/ low	Finding	UNOPS Response/Follow up
Low	A risk matrix for LIFT is in place and is reviewed by the FM and FB quarterly but there is no local risk register for the UNOPS to monitor risk at the entity level.	UNOPS MMOH to develop a local risk register to monitor risk at the entity level.
Medium	A high turnover of M&E specialists may lead to the inconsistent management in M&E of the whole programme portfolio of LIFT.	UNOPS continues strengthening the M&E unit of LIFT in liaison with the LIFT fund board.
Low	It is not a requirement for UNOPS to carry out due diligence assessment on sub-grantees.	UNOPS to explore with the FB executive members whether it should be a requirement to conduct assessments on the sub-grantees of the IPs.

For the assurance of the financial management of the downstream partners, UNOPS follows the Operational Guidelines of LIFT, the UNOPS internal rules and regulations on grants and an internal assessment template for selecting implementing partners. Implementing partners also undergo a financial capacity assessment based on the commonly agreed World Bank questionnaire for financial capability, however it is noted that the sub-grantees (mainly local implementing partners) do not undergo financial capacity assessment, and DFID will explore with other donors how LIFT Fund Manager secure assurance on the financial capacity of the sub-grantees.

UNOPS has a policy and a process in place to respond to fraud, bribery and corruption effectively, which is known as ‘LIFT Financial Risk and Fraud Policy’. LIFT undertakes trainings with IPs to inform them about the policy and to inform them about their responsibilities in reporting about such incidences. The fraud policy states a clear reporting procedure at various levels where fraud cases could occur. Over the four years of LIFT programme, there was a fraud case uncovered and it was an evidence of how a fraud case was reported / communicated and taken action by the fund manager.

UNOPS has conducted audits and managed well financial risks and fraud. LIFT-funded projects are audited annually. After an audit each IP prepares an audit action plan to address the audit findings. IPs report on the implementation of the plan in their annual and semi-annual reports. This is the main process by which UNOPS (LIFT) ensure that IPs have adequate internal financial controls in place.

UNOPS Audit Arrangements

All non-UN implementing partners are audited annually by an independent audit firm. The areas of focus include: a) Effective, efficient and economical use of resources; b) Reliability of reporting; c) Safeguarding of assets; and d) Compliance with applicable legislation. UNOPS monitors and takes actions on the audit findings and also presents them at Fund Board meetings for awareness, transparency and requests steers from FB if necessary.

UNOPS (LIFT) is audited annually by a team of auditors appointed by the UNOPS Internal Audit and Investigations Group (IAIG). The objective of the audit is to ascertain the effectiveness and efficiency of operations, including the economical use of resources in addition to verification of compliance activities of the office with the relevant UN and UNOPS rules and regulations.

Management Case
(Management arrangements: Is it clear how ongoing management will happen throughout the delivery process?
Risks: Is a comprehensive set of risks and mitigation measures identified, focusing on the risks that threaten successful delivery of VFM?
Evaluation plan: Does the BC set out a clear evaluation plan following the guidance?
A good plan suggests a clear set of intentions including evaluation questions, timeframe, partners, methods, and justification of the M&E budget. It is closely linked to the theory of change and gaps in existing evidence.
Logframe: Is the logframe based on a clear results chain? Narrative should discuss whether this has strong links to the theory of change for the chosen option in the Appraisal Case.
How well does the logframe set out indicators, baselines and milestones, and data sources?
Indicators should be well defined (SMART), disaggregated (e.g. by sex) where appropriate, and should allow an assessment of VFM. It may be difficult to judge the realism of milestones and targets, however assessment should at least consider whether milestones and targets have been set and appear broadly acceptable given baseline. Data sources should be explicit and easily referenced.
How will the intervention be operationalised? Are there clear lines of accountability and clarity on who is responsible for delivery performance? If things go wrong, who will be responsible for remedial action? What role does DFID have in assessing performance or proposing solutions? What rights do we have to exit the intervention in extreme events?)

Governance structure of LIFT

The above diagram is the governance structure of LIFT that illustrates the fundamental roles and responsibilities of the IPs, Fund Manager, Fund Board, Senior Consultation Group and the Donor Consortium. Their detail roles and responsibilities are clearly set out in their respective ToRs.

The Fund Manager (UNOPS) is primarily responsible to manage LIFT in a transparent, efficient and effective manner. According to the direction of the LIFT new strategy, based on the lessons learned and in consultation with key stakeholders (the donors, the potential implementing partners, the Government department, the beneficiaries), the Fund Manager formulates programme designs, and with the final approval of the Fund Board, select implementing partners through competitive and transparent process. The FM is also responsible to manage the performance of each grant and report and publish the annual progress of the whole LIFT portfolio.

The head of DFID Burma is the Chair of the Donors Consortium (until July 2015) has a role to review and advise the governance structure of LIFT and the main priorities of LIFT based on the programme performance and the changing operational context.

The Livelihood Adviser of DFID Burma (the SRO for LIFT) is also representing the UK at the LIFT Fund Board which is convened every four months. The Livelihood Adviser takes the lead in providing strategic leadership to the LIFT FB and FM to ensure the new strategy is being implemented on track.

With a pending consensus of other FB members and the UNOPS (LIFT) on the DFID’s proposal for thematic sector working groups within LIFT FB, DFID Burma will provide UNOPS and its programme team with the expertise of DFID Economic, Private Sector Development and Climate Change & Environment Advisers.

The Programme Manager of DFID Burma who is assigned to manage LIFT programme is responsible to monitor the timely submission of the UNOPS reports on the LIFT’s performance and the financial statements. The Programme Manager is also responsible to manage the programme according to the MoU with UNOPS, to lead the Annual Reviews and ensure the DFID’s recommendations on LIFT’s performance are being addressed, and the lessons learnt from the LIFT programme are disseminated to both internal and external audience.

DFID Burma Staff	Their role in LIFT	Brief description of tasks
Head of Office DFID Burma / (Chair and member of the DC)	Donor Consortium / Once a year	Conduct a joint annual review of LIFT, including its governance structure and its main priorities for the coming year.
Livelihood Adviser / DFID Burma / (the Fund Board Executive Member and the SRO)	Fund Board Meetings / Every 4 months	Provides strategic leadership for LIFT with a focus on strategy, policy decisions, donor coordinaton, & building relations with the GoM / Does performance management of the FM / Selects grantees
	Fund Board Field Visits / Every 4 months	To observe the project activities, have conversation with beneficiaries to understand their views on the project and their needs.
	Programme Management	Programme Management in line with DFID’s Smart Rules and Smart Guides
Entry Scheme Livelihood Advisor / DFID Burma	Advisory Role	Contribute to the development of the BC, the ToC, the result framework of LIFT, and M&E plan with technical inputs for the Climate adaptation and resilience component of LIFT.
	Programme Management	As assigned, attend Fund Board meetings, join LIFT FMO’s monitoring field visits. / Provide technical inputs for Annual Reviews
Programme Manager	Programme management in line with Smart Rules and Smart Guides	Lead the development of the commercial, financial and management cases of the BC. / Take lead in due diligence assessment of the Fund Manager. / Take lead in doing Annual Reviews and Project Completion Report according to the smart guides and meeting the deadlines. / Monitor, review, feedback and put on record the programme performance and financial reports. / Make disbursements according to the agreed schedule and the cash flow of LIFT fund. / Project data/ information are fed onto DFID system in timely manner.

Risk Management

Burma remains a high risk environment. The general election will be held in November 2015 and there are potential significant changes in the GoM. The LIFT Fund Manager, Fund Borad and the Donor Consortium will discuss to design the LIFT new projects which are flexible to address any issues / demands coming out in the post election.

LIFT represents a high return programme, sustainably supporting Burmese people, increasing growth in the rural economy.
The Operational Risk Assessment Framework was developed by LIFT Fund Board covering all aspects of risk to the programme. Risk mitigation activities are included in the framework, which is formally reviewed every 4 months by UNOPS (LIFT) and the FB executive members.
In terms of programme risk, the key risks are associated with 1. Design of LIFT programmes, 2.Ineffective knowledge management, 3. Social & Environmental consequences and 4. Delivery Quality. The risk description and possible impact on LIFT programme is stated in the following table. The key risks stated in the table have been managed and monitored by LIFT Fund Board members and Fund Management Office according to the agreed time lines. The Fund Manager monitors and updates the risk matrix and brings it into discussion in the Fund Board meetings. (See Annex 1 for the detailed Risk Matrix.)

Risk Type	Risk description and possible impact on LIFT
Design of LIFT programmes	Design of programme(s) fails to bring coherence and synergies across IP interventions (for each agro-ecological zone)

	Nutrition is insufficiently addressed in Food security / livelihoods, limiting the impact of such programmes on rural economic growth

	Design of major programmes fails to balance growth and direct poverty reduction goals.
	Failure to adequately design role for local government services (Department of Agriculture, DAR, Livestock breeding and veterinary department) reduces multiplier effect of LIFT’s investment.
	Design of new programmes does not align with new Strategic Framework for Rural Development leading to disengagement by government with LIFT.
	The lack of a strategy and sufficiently detailed implementation document means that there is no transparent guide for effective LIFT decision making.
	The consultation process for the uplands programme will be inherently tricky given the number and complexity of the stakeholders involved (e.g., ethnic armed groups, potential IPs, government).

Social & Environmental consequences	Severe adverse weather events destroy livelihood assets and undermine LIFT’s impact on food security. / Project activities are not adequately targeted. Ethnic minorities are not sufficiently included under (targeted by) LIFT activities. Some vulnerable households/beneficiaries cannot access the benefits of the project. Some elite capture of benefits. Political and socio-economic factors at community and township level not adequately recognized (e.g. religious, ethnic, marginalized).
Delivery Quality	Lack of adequate M&E information to assess the quality of outputs and outcomes delivered. Learning from implementation limited leading to less than expected outcomes. / LIFT lacks systems and processes to effectively use the increasing amount of information and knowledge that is generated by IPs, the FMO and the FB.

The programme delivery team of DFID Burma also keeps a project level risk register and monitor risks as part of the project delivery plan of LIFT programme.

Monitoring and Evaluation and Reporting Plan

UNOPS as the fund manager of LIFT is responsible to design, develop and implement the overall M&E strategy for LIFT that is capable of monitoring and reporting progress of the Fund, monitoring the performance of implementing partners, and ensuring that fund resources are used effectively. A high level of consultation and participation on M&E is expected with implementing partners and with national authorities.

UNOPS (LIFT) has established mechanisms to use LIFT’s knowledge and experience, including feeding into a) LIFT’s own programming, b) programming by other donors in the sector, and c) policy dialogue with the Government and the private sector.

It has ensured that IPs of LIFT fulfil their M&E obligations, including enabling the participation of beneficiaries, and that recording and reporting systems are harmonised both among implementing partners and with national systems where possible.

The fund management office staff visits each LIFT-funded project at least three times a year. Projects are visited four or more times per year if the Fund Manager has noted serious issues that need to be addressed. During these trips, the Fund Manager assesses the progress of projects, identifies issues with implementation, and capture lessons through comparative analysis of the approaches used. Debriefings with partners are conducted after each visit to discuss findings and agree actions for follow up. Fund Board members also make regular visits to projects.

Monitoring results are reported to the Fund Board. A monitoring and evaluation system specific to the Fund is designed and developed to monitor the performance of IPs and ensure that fund resources are used effectively. This includes but not being limited to an agreed LIFT logframe. The Fund M&E mechanism will measure progress through the use of output and outcome indicators. In addition to the financial and administrative aspects of the Fund, the indicators have been developed to measure programmatic progress including aspects such as sustainable increase in agricultural productivity, off farm opportunities, social protection, scaling up of coverage, geographic distribution, focus on vulnerable households, direct community/household participation, and equity.

The LIFT Monitoring, Evaluation And Learning (MEAL) Framework
The MEAL Framework elaborates a multi-level framework for evaluation and learning in LIFT based on Evaluation and Learning Plans (ELPs) for (1) the FMO as a whole; (2) each regional programme/funding window; and (3) each individual project. ELPs define the core set of evaluation and learning questions that will need to be answered for both accountability, learning and policy influence purposes at each level.
At the level of LIFT as a whole, five questions have been defined for evaluation purposes. They will be answered through a combination of evaluation activities at the LIFT FMO-level and through the programme- and project-level ELPs, as detailed in the table below.
Questions	Approach
To what extent has LIFT appropriately followed and implemented its the strategy? Have LIFT-supported interventions been relevant to the needs of the people it intends to reach?	This question will be answered through a combination of evaluation activities. It will include a detailed assessment of the LIFT strategy, and other relevant project and programme documents. It will draw on project and progamme level evaluations and will also entail an organisational assessment. Specific questions on relevance will be included in the evaluations of individual projects.
Is the strategy working? To what extent has LIFT been effective in achieving its intended purpose and higher level outcomes, including in helping people to step up, step out and hang in?	This question will be answered through a combination of LIFT-level surveys, in particular the LIFT Household Survey (to be administered with a representative sample across all regions where LIFT is working and including both project and comparison villages) and regional and individual project evaluations. The LIFT Household Survey will provide data on the overall changes (including but not limited to those defined in the LIFT logframe) that LIFT has contributed to in its focus areas, using appropriate mechanisms to draw statistically sound inferences about LIFT's contribution to these changes. Regional and project level evaluations will be more narrowly focussed and provide evidence about the effectiveness and sustainability of LIFT-supported models and interventions. These studies will use a combination of robust evaluation methods that are suited to the specific questions related to effectiveness that they seek to answer. They will feed into and support the evidence generated through the LIFT HH Survey in answering this question.
What have been the positive and negative unintended and unexpected consequences of LIFT's operations?	Specific questions will be included in evaluations conducted at each level to capture and document unintended and unexpected consequences arising from LIFT's work and supported interventions. In addition to this LIFT staff will be tracking unexpected and unintended consequences related to their intervention as part of routine monitoring of implementation. Answering this question will entail conducting a systematic review of unintended and unexpected consequences identified as resulting from LIFT's interventions.
To what extent has LIFT delivered value-for-money against the results framework where material / tangible benefits are measureable?	LIFT is implementing a value for money framework that focuses on four domains: / Intervention design to ensure that value for money has been adequately considered in the design/formulation of projects; / Outreach to track the cost per individual reached overall and for specific interventions (this will require systematic tracking of budgets and outreach by IPs); / Selected outcomes overall and for specific interventions to track the overall cost per individual for changes in higher level outcomes and where appropriate for specific project components by building relevant questions and evaluation design into ELPs; and / Use of VfM results to ensure that value for money is feeding into ongoing decision-making within programmes and projects.
To what extent has LIFT positioned itself as an influential knowledge platform on sustainable agriculture, food security and rural development policy and practice in Myanmar?	This question will assess the extent to which LIFT has been successful in achieving its vision of either becoming or establishing a knowledge platform that effectively sources, vets and synthesises robust evidence and channels it into improved pro-poor policy and practice in Myanmar. This question will be anwered in two parts. First, a comprehensive evaluation of all LIFT's policy work to date and up to the end of 2018 (e.g. evidence generated, disseminated, policy influencing activities carried out, contribution analysis of changes made to policies and programming through LIFT activities, etc.). Second, an assessment of LIFT's achievements in establishing a demand-driven, long-term knowledge platform that is able to continue gathering and channelling evidence for improved policy and practice after 2018.

Exit and closure scenarios

Within the four-years (2015/16 – 2018/19), UNOPS (LIFT) will design programmes that have explicit ‘exit’ strategies and that contribute positively to its legacy and long-term sustainability. The three main avenues to achieving a smooth exit and positive legacy are civil society organisations (CSO), the private sector and government.

The capacity- and institution-buildings of the CSOs will be one of the key elements of the LIFT programme to promote their potential to continue deliver services sustainably even after LIFT phases out from Burma. DFID Burma is proposing the FB members to establish a direct funding window to CSOs in order to enhance the capacity building of CSO themselves in addition to delivering project activities.

The LIFT programmes will be managed to demonstrate the partnerships between targeted beneficiaries of LIFT and the private sector is successful. The LIFT programme aims to leave a practice of positive partnership with the private sector and the farmers that could contribute to the rural growth in the longer run.

LIFT FB and UNOPS (LIFT) will ensure that the core systems and approaches of LIFT are adopted by government after 2018. The government could utilise the knowledge generation and learning from the LIFT evaluation reports, surveys and studies in the development of the government’s policy, planning and programming at scale.

Annex 1: LIFT Risk Management Matrix

Annex 2: Logical Framework …