ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Commercial Agriculture for Smallholders and Agribusiness Programme (CASA)
Country or region targeted	Africa and Asia (inc. Malawi, Uganda, Nepal)
Type of cost extension (if applicable)	No Cost Extension
Original project budget	£29.9 million
Original project start and end dates	Start Date: / 01 July 2017 End Date: / 31 June 2023
Cost extension value (if applicable)	n/a
New project end date (if applicable)	31 March 2024
Business Case Quest Document No.	15481289; 15481477

INFORMATION
What is the project’s purpose?
Project Summary: / CASA will increase economic opportunities for smallholder farmers by demonstrating the commercial viability of businesses with significant smallholder supply chains and by attracting more investment into the sector. / The programme will intervene in a small number of countries to support early-stage agribusinesses to prepare for and secure investment and to bring more, poorer smallholders into agribusiness supply chains. At a global level, the programme will work with larger agribusinesses to deepen their smallholder supply chains and engage more constructively with local communities. / The programme will also undertake learning activities which bring together the experience from across DFID's commercial agriculture programmes and research in order to shape the debate on smallholder agriculture and influence the approaches of investors, donors and governments. / Together these activities will support a shift in agriculture, away from subsistence farming towards a more productive, commercially vibrant agriculture sector in Africa and South Asia. The programme supports the UK’s national interest by increasing economic prosperity and stability in the developing world, reducing incentives to migrate and increasing the global supply of food.
What is the objective of the cost extension or other changes?
The business case was approved on July 20, 2017. Following significant interest during two early market engagement events, a decision was made to run a restricted two-stage tender process. This process took longer than expected due to / New Cabinet Office requirements requiring the inclusion of a Sourcing Strategy and a number new approval stages associated with it; / The decision to adopt a two-stage procurement process in response to the higher-than-expected interest from the market during the September 2017 Early Market Engagement Event; / The decision to extend the bidding deadline over the summer holiday period and a subsequent decision to further extend the bidding period in order to enable smaller, SME bidders to submit proposals / Given these unexpected delays we now require a no-cost Business Case Amendment to extend the Business Case end date from 31 June 2023 to 31 March 2024 to bring it in line with current timelines. / Smart Rule 2.8.5 authorises the Head of Department to approve a no cost business case extension: / “2.8.5 Business Case Time extensions / Extensions to project timescales (or no-cost extensions) which do not affect the value for money of the project should be made by a submission to the Head of Department or individual with appropriate delegated authority. The Head of Department will want assurance that closure has been genuinely considered and SROs will want to be mindful of optimism bias. “
What is the additional and total support the UK will provide?
No additional support is required, therefore total support will remain at £29.9m.
What are the expected results?
The expected results remain the same.
What is the approach to implementation?
The approach to implementation remains the same as there have been no new relevant circumstances that would affect it.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
There are no key changes to the original approved business case