ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Sanitation and Hygiene Programme
Country or region targeted	Zambia
Type of cost extension (if applicable)	Bridge funding
Original project budget	£19,000,000
Original project start and end dates	Start:01/04/2011(Aries), 23/11/2011(MOU) / End: 31/12/2014 (original), extended to 31/03/2016 (Annual Review March 2014)
Cost extension value (if applicable)	£4,100,000
New project end date (if applicable)	31/03/2018
Business Case Quest Document No.	3717522

INFORMATION
What is the project’s purpose?
The impact of the programme will be reduced diarrhoea morbidity amongst rural children under 5 from 15% (Demographic and Health Survey (DHS) 2007) to 12% (DHS 2015). This amounts to 14,300 fewer cases of diarrhoea in children each year. / The outcome will be 3 million additional people consistently using an improved sanitation facility with handwashing device measured by the following indicators taken from the National Rural Water Supply and Sanitation Programme (NRWSSP): / the proportion of people in rural areas with sustainable access to improved sanitation increased from 43% (WHO/UNICEF Joint Monitoring Programme (JMP) 2008) to 73% (JMP, 2015). DFID’s support would enable 3 million people in rural areas, including 300,000 school children to get access to improved sanitation. / the proportion of households with a designated place to wash hands, in or near the sanitation facility, with a hand cleansing agent (soap or ash) and water available at the time of inspection increased from baseline (from DHS 2012) to 60% (DHS 2015).
What is the objective of the cost extension or other changes?
The extension’s overall objective is to ensure the sustainability of the project’s outputs and outcomes, and to maximise project impact and to support the Government of Zambia to assume full responsibility for the project; to budget for the project’s continuity, its geographical extension to include all rural districts in Zambia not covered under this project; and to monitor performance to inform sector policy.
What is the additional and total support the UK will provide?
This will require additional funding of £5.0m; £4.1m of this will come from DFID, with UNICEF, which manages project implementation with its Government Counterparts, providing the balance of £0.9m. The time extension amounts to two full years.
What are the expected results?
The expected results in phase II will be; / Strengthened system capacity of rural communities and Government at all levels to plan, implement, monitor and sustain sanitation and hygiene programmes. / Scaled up and developed mobile-to-web monitoring system to cover all 67 rural districts where the project is being implemented to link this to the ongoing development of a National WASH MIS. / Evidence generated on the time and resource inputs needed to ensure sustainability of sanitation and hand washing practices. / Government owned and budgeted for standard interventions to scale-up and sustain sanitation and hygiene activities on a national scale.
What is the approach to implementation?
The approach to implementation of the Phase II will include; / Consolidation of School WASH, Sanitation Marketing & Hand Washing: This component relates to the original elements of Phase I which require consolidation in order to meet current programme targets with no additional funding. It includes the finalisation of school toilets and mass hand washing facilities construction. / Post ODF Monitoring in 67 districts: The mobile-to-web monitoring system being introduced in 46 districts will be scaled up to include all 67 districts in the project area. The system has been adopted by MLGH to become the core of a future National WASH-MIS, with UNICEF adding a water supply module to the software. / Strengthening capacity and accountability for Hygiene and Sanitation: With decreasing emphasis on service delivery at the grassroots level, there will be an increasing focus during Phase II for support at upstream level and focus on institutional strengthening. / Improved Learning and Knowledge Management: In Phase II the project will draw from the experience of Phase I implementation and the introduction of mobile to web reporting, and conduct further assessments to examine and address knowledge gaps in terms of sustainability of rural sanitation programmes, and the relationship between a behaviour change intervention and the establishment of related social norms. / The project will consistently advocate that the standard interventions to scale-up and sustain Hygiene and Sanitation are budgeted for by the Government.
Describe any key changes to the original business case?
Shift of programme focus from basic sanitation and hygiene activity implementation based on the current log frame in phase-I, to project sustainability, advocacy and knowledge management in phase-II to maximise impact.