Annual Review

Title: Programme to pilot Development Impact Bonds
Programme Value £ (full life): £6,300,000		Review Date: 30 September 2019
Programme Code: 204722	Start Date: 30 June 2017	End Date: 31 March 2023

Summary of Programme Performance
Year	2018/19	2017/18
Programme Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	Business Case / 2017 BC Addendum
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/48902575.xlsx

A. Summary and Overview

The purpose of this programme is to pilot the Development Impact Bond (DIB) model, to generate evidence on the suitability and cost-effectiveness of DIBs in improving development outcomes. The programme launched in June 2017.

The first annual review of the programme was conducted in June 2018. DFID identified, assessed and structured financial support to three projects where there is a strong rationale for using a Payment by Results (PbR)/DIBs approach to achieve DFID results priorities. These projects provide a rich set of case studies from which we can generate learning on the suitability of the DIB model. DFID is an outcome funder in two projects – this means that DFID will only pay the providers and their investors if pre-agreed outcome level results are achieved.

The second annual review has been delayed from June to September 2019. This was to enable staff to be deployed in support of delivering priorities related to the UK exiting the European Union.

The first project with the International Committee of the Red Cross will provide new more efficient physical rehabilitation services, that help people living with physical disabilities in conflict affected areas, to regain mobility. The Humanitarian Impact Bond (HIB) is a 5 year programme. It will be set up (2017-20) and will run (2020-22) three new physical rehabilitation centres in Mali, Nigeria and Democratic Republic of Congo, providing people living with physical disabilities with access to rehabilitation services that enable them to re-gain mobility – helping them to live better lives, work and go to school. The goal of the impact bond is to increase the efficiency of new centres and generate learning that can be applied across the ICRC Physical Rehabilitation programme. ICRC will use the HIB to invest in innovating and piloting new ways of delivering services that increase efficiency while protecting quality. DFID has committed £2m to this project (of ~£20m total size). DFID’s payment is strictly tied to the level of efficiency the new centres achieve after 2 years of operations, with the ICRC and its investors only being repaid in full if the centres are more efficient than benchmark centres. It’s expected that during the HIB the new centres will support more than 2,700 individuals to regain mobility. When fully operational, each centre is designed to serve up to 2,000 people with disabilities each year.

The second project with the Global Development Incubator and Village Enterprise aims to sustainably increase the incomes of at least 12,660 very poor households[1] in Kenya and Uganda, by helping them set up income-generating microenterprises. Under the DIB, the NGO (Village Enterprise) and its investors are only paid for the outcomes they achieve: $1 for every $1 of increased income[2] gained by participating households measured 6-18 months after the end of the intervention. Under the DIB, Village Enterprise will significantly increase the scale of their operation, while also testing larger asset transfers with the aim of increasing their impact. DFID has committed $2.02m to this project (of $5.3 total size). A portion of DFID’s funding will support the costs of the independent results evaluation ($0.48m), as well as learning activities managed by Instiglio.
[1] Those living on less than $1.90/day
[2] This is measured using an RCT approach that will measure households consumption, assets and savings

In addition, following a £1.5m project addendum in November 2017, DFID is also providing technical assistance to a third project managed by the British Asian Trust, the Quality Education India (QEI) DIB, where UK funding helps leverage in $10m of new philanthropic outcome funding to improve education outcomes for 200,000 marginalised children in India. DFID’ is supporting the structuring, results measurement and wider learning activities in the DIB. The DIB aims to demonstrate that Impact Bonds can be used efficiently at scale, by using one DIB contract structure to work with multiple NGOs.

Summary supporting narrative for the overall score in this review

The two pilot DIBs where DFID acts as an outcomes funder are now close to completing 2 years in operation, delivering according to expected timelines, with regular reporting to DFID as well as to investors. The Quality Education India impact bond launched in schools in India in September 2018 and has now produced first-year results as well as additional learning outputs. The first output of the programmes’ evaluation has been published through the Government Outcomes Lab website. The DFID Impact Bonds team is already using the evidence produced on the suitability and VfM impact of the impact bond tool in designing a new programme and advising teams across DFID in commissioning own projects.

There have been minor delays in delivering a number of additional learning products both internal (e.g. impact bonds Smart Guide) and externally-facing (report on first-year lessons learned in the QEI DIB). These have been caused by the team allocating resources to support the Government’s EU exit priorities and delays in contracting, respectively. Delays to products have not had a significant impact on the programme’s likelihood of delivering expected outcomes and impact within the set timeline, and we expect to catch up on these outputs within the next year.

Recommendations for the year ahead

For the Impact Bond Field
- Continue work with other outcome funders (donors as well as domestic governments) to build understanding of outcomes-tied funding, capacity to use this type of contract and access to impact investment. We will do this through convening key actors, sharing learning outputs, as well as direct technical advice on projects at critical design stages (e.g. defining outcomes and metrics, drafting contracts).
- Continue to advocate for partners to contribute to the evidence base the programme is building on the effectiveness and value for money of the impact bond tool, and on ways to reduce the costs of future transactions through adapting design, as well as replication and scaling.

For the Programme
- Ensure that findings from the evaluation are fed into the design of the new impact bonds programme in a robust and timely manner as outputs are produced (all future delivery partners in the new programme should be using evaluation findings in driving effective commissioning of future outcomes-based projects).
- Continue to monitor closely the implementation of enhanced safeguarding standards across the DIBs supported in the pilot, flag any emerging issues rapidly to DFID’s safeguarding teams and seek advice as appropriate.

## B: DETAILED OUTPUT SCORING

Output Title	DIB programmes deliver improved results for poor people
Output number per LF		1	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of direct beneficiaries with improved outcomes as a result of DFID funded DIB projects.[3] / ICRC HIB: Number of patients regaining mobility thanks to orthoses, prostheses, and wheelchairs provided in new ICRC physical rehabilitation centres. / VE DIB: Number of VE households with average (i) USD per capita increase in consumption compared to control group (USD PPP 2016 units); AND (ii) USD per capita increase in asset stock compared to control group (in USD PPP 2016 units).	(i) ICRC – 0 people (but project on track against project level output milestones). / (ii) VE – 0 households (but project on track against project level output milestones).	(i) ICRC project is on-track against build phase project milestones. Facing some delays – but these were anticipated and built into the timeline. / (ii) VE – Effect on household asset and consumption outcomes will be measured in 2020 and 2022. In interim, VE is on track against project level output milestones.
1.2 Number of DFID supported DIB projects that complete programme cycle as planned.	3 projects active	3 projects active
1.3 Number of DFID supported DIB projects with improved cost-effectiveness ratio compared with service providers' own past performance.	0 (as too early to assess)	0 (but data being generated to answer this question)
[3] These indicators are for purposes of the DFID Programme Logframe which aims to look at the impact of the DIB approach. These differ slightly from the outcome payment metric used in each DIB. The outcome payment metric and method of calculation for each DIB has been published on the Government Outcomes Lab’s Impact Bond knowledge repository

Provide supporting narrative for the score

DFID continues to be an outcome funder in two projects – the ICRC HIB and the Village Enterprise DIB. The ICRC HIB launched in July 2017 and the Village Enterprise DIB in November 2017, following detailed project appraisal, negotiation of outcome payment metrics and finalising of the independent verification approaches and agents for each project.

There are minor delays to the projected timeline for the delivery of ICRC’s physical rehabilitation centres. The construction work in Mali and DRC is progressing well (with some delays, though these have been budgeted for in the project plan) however there was a six-month delay on construction starting in Nigeria due to issues faced sourcing a technical consultant. The centre is expected to be operational concurrent with the staff returning from training so the delay will not have had a major impact overall, which was factored into project level output milestones.

Implementation of the VE DIB is on track against project milestones. To date cash transfers have been disbursed to 1,535 businesses benefitting 4,549 people, of which 1,414 were male and 3,135 female. The business types funded were 354 crop businesses, 177 livestock, 911 retail, 91 service and 37 skilled (note that multiple sectors apply to some businesses). Mobile money transfers are being piloted by Village Enterprise in Kenya. More detail on these results and evidence, can be found in Section G.

An evaluation on whether Village Enterprise households are better off as a result of the programme is scheduled to start in 2020 and complete in 2022 for the final cohort. In the interim we are monitoring VE’s progress in engaging households in the programme and launching businesses. The Village Enterprise team in Kenya is reporting climate challenges such as a recent drought affecting produce which has resulted in business transitions as an adaptation to the weather – for example changing from crops to retail-based businesses. The Village Enterprise team continues to adapt their intervention to ensure businesses are resilient to climate.

It is also too early to report against Indicator 1.3, as the projects have not yet delivered results. However, we are collecting cost and benefit data against which performance under the DIB can be compared to past cost-benefit data. The DFID evaluation will help to answer this question in future years, collecting data on transaction costs, as well as delivery costs.

Lessons identified this year, and recommendations for the year ahead linked to this output
ICRC HIB – while delays in the construction of new centres are still within the ‘buffer’ that ICRC projected, the team will continue to monitor the project’s progress closely, and ensure that we are aware of any further delays and any responses or recommendations from investors

Output Title	Independent robust qualitative evidence available on whether Development Impact Bonds enable efficient and effective delivery in DFID priority results areas and the conditions for DIBs to be an appropriate commissioning tool, and the costs and benefits of using them.
Output number per LF		2	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Quality independent evidence of programme effectiveness is generated by DIB Project level Verification Providers.	Independent Results Verification Process is operating effectively for all 3 DIBs	All three Results Verification Processes are operating as planned.
Quality Independent Process Evaluation Reports produced by contracted Evaluation Provider that have been published.	Quality Assured Evaluation Reports published on design phase of development impact bonds - costs, challenges, barriers and opportunities to designing and agreeing DIBs, and recommendations for future use of DIB instrument.	Evaluation report was later than planned: approved by Quality Assurance in April 2019, with final versions published in August 2019. However, lessons have been being disseminated to key stakeholders and target audiences since April 2019.

Briefly describe the output and provide supporting narrative for the score

Indicator 2.1: Robust independent results verification procedures are in place and operating for all three Impact Bonds. While the ICRC programme is not yet at the stage of delivering results for verification, the verification approaches for Village Enterprise DIB and the Quality Education DIB have determined the first sets of results payments.

In the Village Enterprise DIB, independent verifiers complete multi-stage checks to confirm cash transfers made to targeted households, including enumerators attending disbursement events, financial audit, and spot check calls with households to confirm the transfers as reported. The verified transfers are reported to donors, enabling donors to pay $1 for every $1 transferred to participating households. Verification protocols have been updated following a decision to adopt mobile money transfers in Kenya after successful piloting. Mobile money isn’t yet possible in Uganda due to limited mobile money coverage. The randomised controlled trial methodology for assessing programme impacts has been agreed and in April 2020 will measure how much participating households’ incomes (assets and consumption) have increased as a result of the microenterprise approach. If the programme has improved households’ incomes, this will trigger further results payments for Village Enterprise. Any second stage results payments will reimburse Village Enterprise and their investors for the broader costs they have already incurred in identifying, training and mentoring very poor households for several months to help them launch income-generating microenterprises.

DFID’s technical grant to the Quality Education DIB supports the robust evaluation of children’s maths and literacy skills, to monitor whether DIB providers are enabling girls and boys to achieve grade appropriate learning levels. Impact is independently measured by Grey Matters India, a specialist educational assessment and analytics firm. GMI measured baseline and endline learning levels of students in schools where providers implemented services and in similar control schools using various safeguards to prevent any gaming of results. The evaluation met the expectations of DFID as well as the QE DIB outcome funders, investors and providers in enabling a first round of outcomes payments to be made for the learning gains achieved. Results are disaggregated by provider, gender, grade and school classes, helping providers and stakeholders monitor that all children are on a positive learning journey.

Indicator 2.2: The first Independent Evaluation Report of the DIBs pilot programme has been quality assured and is published on the Government Outcomes Lab’s Impact Bond knowledge repository. The report comprehensively met expectations but took longer to produce as the evaluator identified an opportunity to incorporate an additional project - the Cameroon Cataract Impact Bond led by the Fred Hollows Foundation – which would enable further evidence to be collected from a new outcomes area at no additional cost to DFID. This was coupled with challenges collecting and validating project cost data which had to be obtained from multiple sources. The evaluation assesses the conditions, costs and benefits of using impact bonds. The first report provides lessons on, and recommendations for, designing and launching impact bonds. This includes the necessary conditions for impact bonds to be suitable; how the DIB model affects design and financing of projects and early implementation including through risk transfer and in allowing incremental innovation in service delivery. Key findings are summarised in section G below. The next report (due 2020) will assess how the Impact Bond model affected provider performance in terms of SDG impact delivered. The evaluator, Ecorys, has produced shorter summary reports, short briefs and run three webinars with various groups of impact bond users and potential users to share learnings. Lessons from our evaluation are summarised in the updated Theory of Change section below – and this is informing DFID future use of impact bonds.

Lessons identified this year, and recommendations for the year ahead linked to this output
- Village Enterprise Endline Results Verification: DFID evaluation advisors should review the piloting of endline survey instruments ahead of full endline assessment in April 2020.
- Next Independent Evaluation Report: While the report was completed in April 2019, additional work by the evaluator was needed to make the report more accessible. It also took longer than planned for stakeholders to review and validate cost data. The DFID team will support Ecorys in speeding up the validation process and agree a format for the next report that ensures accessibility of lessons and suitability of wider dissemination activities relevant to target audiences.

Output Title	Evidence generated on the process of agreeing and managing a project on a Development Impact Bond basis, including implications for DFID's funding arrangements, assurance and management
Output number per LF		3	Output Score	B
Impact weighting (%):		20	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Internal policy guidance generated on process of agreeing and managing a project on a DIB basis.	Internal paper / Smart Guide and signed off by Better Delivery Department on using, designing, agreeing, and managing a DIB project.	No smart guide developed. However, TeamSite includes internal guidance on using, designing and agreeing DIBs and advisors are providing direct advisory support to DFID teams.

Provide supporting narrative for the score

The milestone for this review was not completed in the form prescribed. A key factor was that reprioritisation of team members to support wider government planning for the UK’s exit from the European Union reduced the team’s capacity to develop a smart guide. A new Smart Guide was a lower priority given that the team had already established a comprehensive TeamSite that provides colleagues with information on all three of the DIBs we support, and the lessons and considerations essential to designing these DIBs. The DFID DIBs advisor and programme manager also provide direct advisory support to all DFID teams considering or planning to use an impact bond approach ensuring design and evaluation lessons transfer directly into each area of work.

Additionally, DFID through its engagement in the Donor Impact Bond Working Group has been working with the UK Government Outcomes Lab (GO Lab) at Oxford University to develop a public database of Impact Bonds globally that includes technical guidance for commissioners on when and how to use impact bond modalities, and situates information and lessons from the first DIBs alongside lessons from the UK’s Governments wider use of Impact Bonds in the UK. This is available on GO Lab’s website, though work will continue through Sep/Oct 2019 to further expand the guidance. An internal Smart Guide that captures this advice will still be a useful product, and if priorities allow, will be developed by June 2020 making use of the next independent evaluation output.

Lessons identified this year, and recommendations for the year ahead linked to this output

- Technical advice on designing payment by results structures and considering the financing needs of providers continues to be very important. The team will prioritise producing a Smart Guide next year - and work with commercial advisors to explore how impact bonds can be considered as a commercial option under any future Payment-by-Results programmes.
- Direct advice and technical support to teams designing impact bonds also continues to be in high demand – the team has advised DFID Kenya on scoping a project in Sexual and Reproductive Health, for example, and DFID India in early-stage exploration of investing in future impact bonds. The team will continue to ensure availability to work with teams directly to match growing demand.
Lessons from the pilot stage have also shown that PSD should prioritise assisting domestic governments in appraising where impact bonds could be useful in domestic commissioning (see ‘Theory of Change’ section).

Output Title	Resources are produced that support other outcome funders to use development impact bonds to achieve sustainable development goals in DFID priority countries in South Asia.
Output number per LF		4	Output Score	A
Impact weighting (%):		20	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Number of resources created to enable the entry of new funders into the impact bond market in other DFID priority countries in South Asia (not cumulative)	Research provider is contracted, learning agenda agreed and activities are underway.	Achieved. Research provider contracted, though with a delay. As a result of this, agreed activities need to be refined/amended to endure additionality to other learning work (e.g. programme evaluation)
Number of proof of concept studies completed to assess potential for establishing DIBs in other SDG sectors (such as health, livelihoods, micro-finance, WASH) in DFID priority countries in South Asia.	Selection of countries/sectors for feasibility studies completed	Achieved. A longlist of countries and sectors has been identified.

Provide supporting narrative for the score

The British Asian Trust (BAT) contracted the Centre for Universal Education (CUE) at the Brookings Institution as the learning partner for the Quality Education India DIB. The aim of the partnership is to create learning products from the DIB, feed the learnings back to the project and, critically, showcase this across global and South Asian platforms to enable other players to enter the market. The contracting process took longer than expected – with a contract signed in January 2018. BAT and CUE agreed the research agenda in Q1 2019, with research activities launching in Q2. The first draft publication was submitted to BAT in June, though BAT and DFID have requested significant changes to improve the quality of the output and ensure it reflects the stated aims of the research. Overall, given contracting delays and reflections on the quality of the first draft output, BAT have agreed to review with CUE the most efficient allocation of research activities in order to ensure that all deliverables add value to the programme and the sector.

BAT has also identified a long list of counties and sectors for feasibility studies on future impact bonds. BAT is pursuing consultations with governments, donors, as well as service providers in India, Pakistan and Bangladesh within the remit of a concept for an Outcomes Fund for Women and Girls in South Asia. Thematic areas under consideration include education, health, livelihoods, mental health and anti-trafficking. Provisionally, the above areas align well with DFID’s thematic preferences in planned future impact bonds programming, though the next stage in the feasibility work will be critical in narrowing down the list to products that can generate high SDG impact and represent good value for money, whilst attracting interest from outcome funders (governments and donors), service providers and investors.

Lessons identified this year, and recommendations for the year ahead linked to this output
- DFID and BAT to work together closely (and involve QEI DIB Steering Committee) in refining the learning agenda and suitable products to be created through the learning partnership with CUE. Ensure that the final products agreed are aligned well with Ecorys evaluation, and provide additional insights and value, emphasising focus on learning specific for South Asia.
- DFID and BAT to finalise details of feasibility/scoping studies to be produced during the following year, focusing on areas that align with domestic government interest and planned DFID impact bonds programmes. DFID DIBs team to ensure relevant DFID country advisors are involved in conversations as appropriate

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

A diagram summarising the Theory of Change for this programme is included as Annex 1 – this has not changed over the past year. Impact Bonds are a potentially valuable tool for achieving SDG outcomes. However, there experience and evidence on their suitability in a development context is still limited. The DIBs pilot programme works to overcome this barrier by i) establishing a portfolio of DIB projects, which will act as case studies from which ii) to gather initial evidence and learning on the model’s suitability and effectiveness in achieving development outcomes, and their value as a commissioning tool used by DFID, and iii) share this learning within DFID and the wider international development community to enable replication of effective approaches.

The first phase of the programme’s evaluation has contributed valuable evidence on effective design and launch of impact bonds. It highlighted:
- The need to adapt impact bond structures to contexts in which they are delivered – the ‘problem’ impact bonds seek to address, and local conditions and priorities.
- The potential to leverage investment made in developing first products into lower transactions costs as the market develops – through replication and scaling future instruments.
- The need to focus resources on components of DIBs that are most likely to generate impact (‘DIB effects’, e.g. in encouraging innovation, or enabling more providers to enter the PbR market).

In the past year, DFID has started building emerging lessons from the DIBs Pilot into follow-on programming. The early concept of the ‘Pioneer Outcomes Funds’ programme incorporates features to drive government-led commissioning of services (to ensure adaptation to local context and policy challenges), is built around ‘outcomes funds’ commissioning multiple projects competitively rather than single impact bonds (delivering at scale, and with potential to replicate from existing Pilot DIBs), and includes a technical assistance element to build capability in service providers as well as governments and donors. In this, the work under DIBs Pilot Programme is important in providing evidence, but also in building an early pipeline of potential projects – with design work underway to assess the potential of using the VE DIB concept at scale with a range of providers, and BAT consulting governments in South Asia on outcomes fund opportunities.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

The outcome targeted by the programme is improving DFID’s ability to make informed choices on how to use DIBs and compare the instrument to other PbR and non-PbR tools in commissioning and management, and emerging evidence on impact and value. On outcome indicator 1 we achieved the target of 8 DFID programmes interacting with DIBs guidance, evaluation findings and reports. We have continued supporting two DFID country offices (India, Kenya) and one centrally managed programme team (WASH) in thinking through the initial stages of impact bond design – sharing evidence and insights generated during the first year of programme implementation. In the last year, we have expanded support in Kenya from the social protection programme, to a new programme in sexual and reproductive health. In addition, we have provided support to DFID Zambia in assessing an early design for an impact bond in clean cooking. Importantly, linked to designing the new Pioneer Outcomes Funds programme, we have provided advice to DFID Ghana (education) and DFID Rwanda (social protection). Note that whilst a delay in publishing internal guidance, the first evaluation findings have meant that fewer finalised documents have been available. The team have filled in this gap with other resources and direct consultations with projects.

Milestone 3 is 15 new programmes interacting with guidance – this is likely to be a challenging target as it depends on both the number of new programmes coming through the pipeline, as well as availability of guidance/reports. The project pipeline is likely to be boosted by the Pioneer Outcomes Funds programme, which is targeted to go live in 2019/20. The first evaluation reports are now available online through the Government Outcomes Lab website and the team will share this proactively in Sep/Oct 2019.

Outcome indicator 2 is the proportion of new DFID DIBs commissioned, that are informed by recommendations of DFID DIBs evaluation reports. So far, the only concrete impact bond where work has been commissioned is the Kenya sexual and reproductive health project in partnership with the Children’s Investment Fund Foundation – here, the design work is closely following lessons from the DIBs pilot. We are confident that the 100% target specified for Milestone 3 can be achieved.

In terms of impact, the programme aims to deliver value for money, better results for more poor people, and ensure that money is spent where it makes the most difference. On the impact indicator value of DFID spend delivered through PbR programme financing structures that target increased efficiency and/or cost-effectiveness, the team is still working on understanding baseline data better, before finalising milestones. Early challenges include ensuring the sustainability of impact generated through pilot DIBs – e.g. through planning to use DIB evidence in attracting follow-on funding from donors or national governments.

Explain major changes to the logframe in the past year (1/2 page)

In June 2018 a number of minor changes were made to clarify indicators and milestones in the logframe, these are explained in full in the logframe change frame and were approved by the Team Leader
- Output 4.1: Milestones were updated to reflect the timing and outputs of the finalised learning agenda agreed with the learning partner.
- Output 4.2: Milestones have been updated to reflect final grant agreement with the British Asian Trust, and a more realistic timeline for completing the scoping and feasibility studies for impact bonds in other sectors in South Asia.

Describe any planned changes to the logframe as a result of this review (1/2 page)

Output 4.1: Milestones will need to be revised as we work with BAT and CUE (the learning provider) to consider what types and timings of outputs will be most impactful and complementary to Ecorys’s outputs. The misalignment over the past year has happened due to delays in contracting CUE, as well as draft outputs not meeting quality expectations – further work is needed with BAT, CUE and other partners on the impact bond to agree an optimal set of products that continues to demonstrate good VfM.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

The purpose of this pilot is to test and generate lessons about how impact bonds work – specifically on conditions that make impact bonds appropriate, and the costs and benefits of using them in terms of achieving development results. The business case proposed to achieve value for money by:
- Driving value for money (to drive cost-effectiveness, efficiency, economy and equity) through the payment-by-results agreements between providers and DFID as an outcome funder;
- Minimising additional transaction costs; and
- Efficiently generating evidence on using impact bonds through case-based evaluation of pilots.

Driving value for money through Pay for Results agreements and incentives
The previous annual review set out how DFID’s Payment by Results Agreements with ICRC and Village Enterprise are designed to drive value for money: particularly cost-effectiveness, efficiency and equity. While the first sets of final outcomes won’t be measured until next year, the evaluation found several indications that the DIB model is working to protect value for money as anticipated.

Under both the ICRC and VE projects, if service providers do not meet the outcome targets outlined in DIB agreements outcome payments will not be made by donors and investors stand to lose money. This transfer of risk to investors helps ensure available public and philanthropic funds are used to ensure vital social benefits get delivered. The evaluation confirmed that risk has been transferred to investors in both the VE and ICRC agreements. The evaluation also found that the available investment returns, which compensate investors for the risk transfer and for lending capital, are tied to results being delivered and sit within benchmarked ranges for investor returns.

At the same time, the results payments in each DIB are structured so that payments increase with increasing effectiveness (subject to a budget cap). The evaluator has identified that both ICRC and VE are investing in new systems and procedures that support more adaptive management that help them to deliver more results with the resources available.

VFM in the Village Enterprise Bond – VE is delivering at larger scale in new communities and with new staff. VE is also testing larger size cash transfers with the aim of increasing impact on household incomes and managing the impact of varying weather patterns on agriculture-based micro-enterprises. Under the PbR Agreement, equity is protected because VE must work with the poorest households in each village, and this is independently verified. The payment from donors is contingent on VE achieving growth in income of targeted households, with donors paying $1 per $1 additional income generated, as measured by a randomised controlled trial. This is an incentive for VE to deliver outcomes whilst also managing delivery costs (to ensure investment spent on delivery will be covered from results payments). VE’s investors understand that repayment depends on VE helping households achieve higher income gains than in the past.

In support of this stretching goal, VE report changes made to performance management software, data collection and procedures that are enabling more adaptive management to drive results. Examples include: changes to VE's microenterprise training curriculum, providing front line staff with more real time data on how the enterprises they are supporting are performing, and VE is now risk-rating enterprises based on household participation, income and benefits businesses produce to identify which types of enterprise are most impactful. At present VE is on track in terms of reaching the number of households expected, though it is too early to tell if the above changes are driving better results – but we will be able to assess this in April 2020 when the first outcomes are delivered.

ICRC Humanitarian Impact Bond – Efficiency in operating physical rehabilitation centres is at the heart of the ICRC impact bond agreement. ICRC must deliver at least a 10% increase in efficiency in operating physical rehabilitation centres built under the DIB (as compared to current centres) to recover costs. The outcome payment grows with additional efficiency increases (capped at 80% increase in operational efficiency). Efficiency targets were benchmarked to ensure investor returns are attached to stretching targets. While ICRC is an experienced provider, the project faces several risks related to the fragility of the operating environments and in formalising operational agreements with local health ministries. Under the impact bond ICRC is also investing in a new Digital Centre Performance Management System that should enable better patient case management and centre supply chain management. This workstream is expensive and requires bottom-up software development. The IB model enables ICRC to make these longer-term strategic investments, but also ensures that donors only repay these additional investments if they enable ICRC to help more people with the same resources. Equity considerations have been designed into the performance metric and will be evaluated once services start to be delivered.

Quality Education Impact Bond – While DFID is not an outcome funder in the QE DIB, DFID’s technical assistance grant provides for the independent measurement of numeracy and literacy gains being achieved for children and enables the bond’s funders and providers to make impact-focused delivery decisions. At the end of the first year of services, the results showed that 40% of the participating schools had met or exceeded their targets for literacy and numeracy skills. However, 60% of schools had failed to outperform non-participating schools. These results meant the Bond funders only repaid investors for the learning gains that were achieved. The Bond partners then worked together with providers to assess how causes of underperformance could be overcome. While three services will continue into the next academic year, the review ultimately decided to discontinue an underperforming teacher training programme because operational challenges could not be overcome.

This decision reduces the total number of children who were expected to benefit under the project. Therefore, BAT is discussing with its co-funders and with DFID whether the outcomes funding and evaluation budget that was allocated to the discontinued services should be reallocated to enable one of the higher performing services to be delivered in additional schools in order to reach more children. We are supportive of this in principle but are waiting for more information on target schools before approving.

More broadly, the QE DIB results evaluation that is funded by DFID is generating data on the cost per outcome of the different education services being tested. The evaluation provides disaggregated data by geography, provider, school, grade and gender, that is useful to QE DIB funders and providers in ensuring equity of results, and this data is being used to inform on-going service development. (See section G below for emerging learnings).

Keeping Transaction Costs Low

While the process of negotiating payment metrics was time-intensive and a steep learning curve for DFID, engagement in each DIB project since they launched has been comparatively less intensive than other DFID programmes. This is because target cohorts and value for money are protected through the financing arrangement, and decisions on whether to reallocate inputs and expenditure occur between service providers and their investors. This allows DFID advisors more time to engage with providers on operational lesson learning, monitoring safeguards, and interpreting results verification reports and emerging evidence.

A key transaction cost in each of the impact bonds is results verification. In all three DIBs, DFID and partners worked with evaluators to select the most relevant evaluation approach and to keep the cost of verification as low as possible. In the ICRC DIB it is appropriate to use a simple audit of administrative data to verify results. Comparatively, for the VE and QE DIBs there is huge value in using experimental methods to measure the impact of the programme and its adaptations on beneficiaries that go beyond simple results verification. This is because results are uncertain. As the first year of QE DIB results shows, even services that performed well in the past evaluations can face operational challenges that prevent impact. We also want to learn which service adaptations to take forward.

Efficiently generating robust evidence on impact bonds that is demanded by the sector
At programme level the three DFID funded impact bonds provide a diverse group of case studies through which the process evaluation can consider the conditions where DIBs are appropriate and assess the presence of anticipated DIB effects in driving programme performance and results. The evaluation has identified relevant comparison project sites that provide a counterfactual argument through which process tracing can be used to disentangle the contribution of the DIB in achieving results compared to other factors. In co-funding outcomes alongside other donors and investing in evaluation, DFID is generating vital evidence of IBs under different conditions at a lower cost than had we initiated several pilots alone.

In addition, a fourth DIB was added to the evaluation in the past year. The Cameroon Impact Bond is not funded by DFID and has quite a different structure. Donors to the Cataract IB have engaged DFID’s evaluation methodology and supplier, enabling an additional case study to be added at no additional cost to DFID, but with significant benefits to sector learning about different DIB conditions and effects.

The first evaluation report was very well received, with evaluators invited to present at various donor and stakeholder gatherings including the Impact Bond Working Group that was attended by more than 100 representatives of donors, multilaterals, investors and providers. Stakeholders confirm the evaluation is starting to help answer the most important questions and informing their use of Impact Bonds.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

From a VfM perspective, the programme should continue as it has been set up with a focus on both driving and monitoring VfM throughout. The evidence generated is vital for effective decision-making by DFID, other donors and local governments in using Impact Bonds. So far, Impact Bonds look to be a promising tool, and the evaluation has highlighted that several of the DIB effects anticipated were present in the design and early implementation of DIBs to a lesser of greater extent, and that emerging findings mirror findings in evaluations of impact bonds used in UK social services.

Importantly, at this stage of the programme it is only possible to talk about the costs incurred in setting up the DIBs and emerging indications of potential benefits. Actual benefits can be assessed from next year onwards when the intended outcomes will be measured and when the evaluation can assess how the impact bond has affected how providers deliver, and if there has been any impact on the volume of results achieved. It is therefore important to continue our engagement in these DIBs and maintain the evaluation in order to assess how the expected benefits materialise in terms of results delivery, to enable a full discussion of the costs and benefits of the impact bond approach. The next evaluation product (due Summer 2020) is timed to promptly generate this evidence.

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

The programme is still moderate risk given that the programme outcomes are focused on generating lessons around how impact bonds perform. However, certain risks are escalating in that they have the potential to impact on the scale of SDG outcomes achieved by each DIB project or on value for money:

Safeguarding risk assessments – have been completed by DFID on all partners and in the past year all tier 1 partners. All tiers of partners in this pilot programme recognise the importance of safeguarding and all are taking action to continuously look at and ensure safeguarding procedures in their delivery chains are being continuously strengthened. The DFID programme team is monitoring these actions closely. As the QE DIB brings in new delivery organisations, DFID is closely monitoring that BAT verifies that providers have suitable child protection safeguards.

Climate Change – This is the second year in a row of extremely delayed rains in Uganda. Village Enterprise is seeing businesses begin to struggle with this risk where their businesses are agriculture or livestock related. VE is mitigating the risk by giving more targeted support to struggling businesses and encouraging business groups to diversify their business activities. Cohorts 1 and 4 were impacted, and Cohort 7 may face similar challenges due to seasonal timing

Changing Currency Risk – the British Pound has been losing value against the US dollar, this means that the results we pay for are slightly more expensive. The impact is still relatively small and can be managed within the programme’s budget.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

An up to date Delivery Chain Map is included as a tab in the Delivery Plan. Overall all partners are performing well on commercial and financial matters. Actions to improve performance noted below are transferred into the delivery plan

Independent Evaluation Contract: In the past year the supplier, Ecorys, has delivered the evaluation design and first evaluation report. Both outputs were delivered to a high standard covering the required scope of work and scoring good or excellent with DFID’s independent evaluation quality assurance service. Ecorys has since developed a stand-alone evaluation summary, a number of shorter briefing notes and run 3 webinars/panel events to disseminate key findings and recommendations. The pilot project partners are positive about the evaluation team and their engagements to date. Payments are tied to outputs and this has worked well in ensuring content and quality. Savings were agreed as part of adjustments to the team composition and reduced team inputs. Action: Going forward Evaluation Reports need to be shorter and more digestible. DFID will issue a survey of report users to gather further suggestions for improvement. In addition, while Ecorys’s core team remains the same and brings wider experience of evaluating Social Impact Bonds in the UK, Ecorys needs to appoint new in-country thematic experts to supplement the core team.

GDI is performing their trustee role effectively and has completed outstanding due diligence recommendations. GDI’s sub-contractors (the NGO delivering the outcomes – Village Enterprise, the outcome verifier and the process learning partner are all delivering their activities effectively and proving to be strong collaborators; each providing quality reports as agreed at design stage and being transparent in the management of their programme activities). The delivery chain is reasonably complex, and we have worked to establish an oversight structure that brings together all outcome funders and delivery partners on a quarterly basis – for direct interactions, which gives DFID direct oversight of all delivery partners.

ICRC is producing quality reporting as agreed in the programme documentation and manages well-attended and thorough oversight meetings every six months. The project is still in the first phase of ‘constructing treatment centres’. ICRC is currently working closely with the local Ministries of health responsible for staffing and overseeing the centres day to day to agree the specific operational protocols and safeguarding procedures that will be in place. DFID is monitoring this process closely to ensure suitable protocols are in place by the time centres start receiving patients from April 2020. ICRC will update DFID on this process in October 2019.

British Asian Trust (BAT) is providing good quality narrative reporting and access to wider documentation and lessons learned in the delivery of the DIB. BAT’s forecasting has also improved significantly now that relationships with their downstream contractors (evaluator, learning partner) have been finalised. However, there are several areas where DFID is monitoring BAT’s performance closely. Staff changes in recent months have impacted on continuity and meant some DFID expectations have not been fully met, and DFID is monitoring that the next stage of impact bond scoping is adequately resourced. BAT is working intensively with all partners in the DIB to drive ever higher safeguarding standards across the project. DFID is monitoring this very closely. Finally, following initial delays in contracting, BAT is working with the learning partner, CUE, to propose changes to planned outputs of the learning workstream (in both timing and product types) to ensure that the stream better complements the pilot evaluation carried out by Ecorys.

	GDI/VE DIB	ICRC	BAT	Ecorys
Date of last narrative and financial reports[4]	11 July 2019 / 31 July 2019	15 May 2019	30 July 2019 / 30 July 2019	May 2019
Date of last audited annual statement (s)	31 Dec 2018	31 Dec 2018	31 Mar 2017[5]	N/A
[4] Reports saved to vault folders on Financial Management and ICRC, BAT, GDI/VE reporting folders
[5] BAT 2018 audit was due on 30 Sept 2019. BAT report that BAT’s Board is due to approve it in October 2019 and will immediately send to DFID. DFID Management Actions have been taken pending receipt of audit).

G: MONITORING, EVIDENCE & LEARNING

Monitoring

A key benefit of the DIB model is the focus on monitoring, evaluation and learning (MEL). The last annual review sets out the monitoring and result verification approaches in use across the pilot projects. This section updates on how those activities are performing and key lessons coming through.

Village Enterprise DIB
The VE DIB includes a randomised controlled trial design to measure the impact of the programme on a sample of households’ incomes, assets and consumption, 6-18months post-intervention. It is also designed to generate learning on the impact of higher value cash transfers ($150 per 3-person business versus $450 per 3-person business). It will also produce learning on how programme impacts persist post intervention. Data will be disaggregated by gender, location and disability. The first endline evaluation for the first 4 cohorts (out of 7) of participating households will report results in April 2020.

In the interim, Village Enterprise relies on its internal enumerators to monitor performance against intervening milestones and have drawn out the following internal indicative lessons:
- Encouraging internal end line data: Only the first cohort of households have fully completed VE’s programme of support, and VE’s internal end-of-cycle data looks encouraging. Monthly per capital consumption appears to have increased by 40% and asset stocks have doubled among households who completed the programme compared to baseline.
- Increased Grant Size: VE report improvements in the quantity and quality of businesses that received the larger grant size of $450 per business group, evidenced by businesses’ inventories and record books. On average, businesses receiving the larger grant size earn roughly twice the monthly revenue of businesses receiving VE’s regular grant size of $150 and are starting new types of businesses such as motorcycle parts shops and maize shelling. VE have also learned to mitigate price increases when suppliers learn about disbursements by helping business owners to enter into agreements and commitments with selected suppliers to lock in prices prior to disbursement day.
- Business Savings Groups: Despite a previous evaluation indicating the Business Savings Groups were not increasing outcomes for households, VE has persisted with this part of their intervention and their internal data suggests households are saving progressively more money, with savings averaging between $86-$107 per BSG per month.
- RCT constraints: To have sufficient power to measure results the RCT needs the programme to operate in a large number of villages. Because the funds for the outcomes funds available were limited to £4.2m, this meant VE can only work with the poorest 70 households in each village, though in some villages a larger number of households would be eligible for the programme. This also increases VE’s transport costs. Such constraints demonstrate again why an impact bond model benefits from a minimum level of scale, and why it would be preferable to work with all eligible households at the same time.

ICRC HIB
The HIB is still in the construction phase, so reporting is limited to quarterly project construction reports. Every 6months ICRC colleagues leading delivery in each country present detailed updates on progress in each country to donors and investors, together with emerging risk and mitigation.

Quality Education India DIB
The QE DIB consists of two layers of independent monitoring: a performance manager working with the three providers day to day and reporting on risks and issues on a quarterly basis, and an independent results evaluator. Both activities are funded or part-funded by DFID. The performance managers and evaluation provider have established strong relationships with service providers, which is enabling lessons to be learned and adopted.

Emerging lessons from this monitoring and evaluation that are informing conversations between investor-providers are that girls are performing slightly better than boys, there is variation in performance by geography, and schools with higher baselines are generally seeing lower learning gains. Investors and providers are considering greater customisation of interventions by geography and children’s starting levels, as well work to improve boys’ attendance particularly during harvest season. Other factors that the performance manager indicates are positively impacting on performance include the use data to customise interventions to specific contexts, while changes to the capabilities of staff executing programmes can dramatically impact an organisations ability to deliver.

Evidence
The programme level evaluation has been published on the GO Lab website. This evaluation report focused on assessing how the DIB model affects the design, delivery, performance and effectiveness of development interventions. A summary of the key DIB effect categories considered under the evaluation are summarised below. The RAG rating indicates the extent to which these effects emerged, with Green signalling Yes, Amber signalling To some degree, and Red signalling No.

Transfer / of Risk from outcome funder to investor	ICRC	QE DIB – 100%	VE – 100%	Cataract
	The level of risk transfer varied by project and design. However, in all cases a level of risk transfer was achieved. Whilst the DIB reduces some financial risks for outcome funders and service providers, it increased other risks. Outcome funders and service providers voiced concerns around the uncertainties of using a new funding mechanism, alongside the heightened attention the DIB brings to projects increasing unwanted exposure should the results not materialise.
More providers entering PbR market	ICRC	QE	VE	Cataract
	Service providers also noted it was unlikely they would have participated in projects if they had been required to pre-finance services themselves. However, evaluators found that other barriers to providers entering PbR contracts remain: Investors work repeatedly with trusted organisations with strong and credible management teams, and entering into a DIB requires a degree of capability and capacity that a large number of service providers may not have.
Greater collabor-ation due to aligned interests	ICRC	QE	VE	Cataract
	The DIB fostered new working relationships between stakeholders and led to greater levels of collaboration than is normally seen, primarily because the DIB aligns all stakeholders’ interests but also because the intensive design stage necessitates closer working. The extent to which collaboration occurred differed between the DIBs. Collaboration was noted as stronger in cases where there were more multilateral discussions, though this also made negotiations less efficient.
Projects wouldn’t have been funded otherwise	ICRC	QE	VE	Cataract
	The DIB made it possible to implement PbR contracts in contexts where, previously, this would not have been possible because the projects were too risky or too large, hence funding projects which would not have been funded otherwise, or in the same guise. While PbR has been used in these countries, a number of outcome funders across all four DIBs said it was unlikely they would have funded the intervention on an input-based model.
Additional finance for SDG sector	ICRC	QE	VE	Cataract
	These DIBs also demonstrate that private investors are willing to take on sizeable risk in impact bonds, and that it is possible to launch impact bonds at a larger scale (i.e. the QEI DIB, which builds on the Educate Girls DIB). There is evidence of impact bonds drawing in additional financing to the development sector, as well as longer term funding.
Enables innovation	ICRC	QE	VE	Cataract
	Reputational risk of involvement in the pilot DIBs created a level of risk aversion, which Evaluators believe limited the level of innovation in the interventions – all four DIBs involve service providers with some track record and interventions with some evidence base, with innovation being incremental, rather than radical.
More careful intervention design	ICRC	QE	VE	Cataract
	A lot of work has been done in all four DIBs to build a stronger performance management infrastructure, including investing in new monitoring systems and working closely with service providers to embed adaptive management systems. There is less evidence that the DIB supported more careful and rigorous design of the interventions themselves.
Complex to set up	ICRC	QE	VE	Cataract
	All four DIBs were complex to design and launch, which resulted in large development costs. It is too early to conclude whether the benefits outweigh these costs. Stakeholders were confident that lessons could be learned from the DIBs that would reduce the complexity and cost of future DIBs,

Learning
These ‘first of their kind impact bonds’ were complex and expensive to launch compared to their size, particularly where funders are understanding DIBs for the first time. Many of the transaction costs were incurred before DFID became involved in these first DIBs – so the priority of the evaluation was to understand cost drivers and explore where costs may be reduced. The evaluation finds scope to reduce some of these costs through more transparency that would enable models to be replicated, grow knowledge and support template contracts to be developed. However, some costs such as those associated with measuring results can only be reduced so far, and therefore will only make sense at larger scale. This underlines why DIBs should be used judiciously in areas where there is value in measuring if services are working and in giving providers more space to innovate and adapt services to meet the needs of individuals and contexts, notably to improve underperforming services or to bring services to underserved populations.

Progress on recommendations from previous reviews

For the Impact Bond Field

- Work with donors: The 2018 AR recommended continuing to work with funders to share learning, build capacity and alignment – we have held two further meetings of the donor Impact Bonds Working Group to share lessons learned from the pilot so far and enable partners to hear about new projects in development. In addition, the team has partnered with the UBS Optimus Foundation who appointed (through a competitive call for proposals) a consortium led by GO Lab to expand their website and start building a globally-facing knowledge-sharing platform for impact bonds. We plan to continue this work in the year ahead, and identify a sustainable, long-term way of running (and funding) the knowledge-sharing platform alongside other partners.
- Opportunities for scaling and replicating – given investments made in exploring the IB model, the last AR also recommended looking for opportunities to scale and replicate pilot impact bond models with partners. The team has now developed a follow-on Business Case to create a number of ‘outcomes funds’ in areas similar to pilot DIBs (graduation, education, health) as well as emerging fields (clean energy, sanitation) – this will seek to engage domestic governments in commissioning using outcomes-based instruments (including impact bonds) to provide high-quality public services. The next 12 months will be critical in securing approvals and launching the new programme.
- Encouraging partners to share programme learning during implementation – we have emphasised the need to share programme learning through meetings of the Impact Bonds Working Group, and a number of partners have been proactive in disseminating own insights (most notably at the GO Lab’s annual Social Outcomes Conference, held on 5-6 September 2019). In addition, the Fred Hollows Foundation have agreed to include the Cameroon Cataract Impact Bond in the Ecorys evaluation.

For the Project

Continue to monitor that verification approaches for each project are operating effectively on the ground and generating robust evidence on outcomes – the team has monitored the first stages of verification development, notably for the Village Enterprise impact bond. The first results of the verification are due in April 2020 and the team will continue to ensure that Village Enterprise and partners receive an appropriate level of support.

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.
The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided

## Annex 1: DFID Theory of Change for Development Impact Bonds Pilot Programme