Business Case

## Summary Sheet

Title: Africa Division funding to Africa Agricultural Development Company (AgDevCo)
Project Purpose: To support poverty reduction and increased food security through catalysing additional private sector investment in agribusiness and agricultural infrastructure and increasing agricultural cross border trade in targeted countries, generating jobs and income for smallholders
Programme Value: £36.5m		Country/ Region: Africa Regional, Ghana, Malawi, Mozambique,Tanzania, Uganda, Zambia
Project Code: 204270	Start Date: 1 April 2015	End Date: 31 December 2020
Overall programme risk rating:	MEDIUM-HIGH
Quest Number:	4864496

Intervention Summary (2 Pages)

What support will the UK provide?
£34.8 million of re-deployable capital in 2015-2018 to catalyse private sector investment in agriculture and agribusiness infrastructure through the Africa Agricultural Development Company Limited (AgDevCo), whose mission is to reduce poverty and improve food security through a non-for-profit investment approach.
£1.7m for an independent evaluation (2014-2020) of the impact of DFID funded AgDevCo’s investments across 5 Countries.
In 2013, DFID Private Sector Department committed £11 million and DFID Africa Division committed £65 million to AgDevCo to be disbursed through the Private Infrastructure Development Group (PIDG) framework, of which AgDevCo was an affiliated facility. In November 2013 the PIDG Governing Council rejected the establishment of a dedicated PIDG facility for agriculture, which means that a continuation of current management arrangement is not possible. £31 million of the approved funding has already been disbursed through PIDG.
This BC sets out a new mechanism for DFID funding to AgDevCo outside of the PIDG framework. This is a direct contractual relationship. It covers £34.8m yet to be disbursed plus £1.7m for the independent evaluation component.
What are the main programme activities?
AgDevCo will continue operating 3 SMEs Catalytic Funds in Malawi, Zambia and Ghana and a portfolio of co-investments with private companies in Tanzania funded by DFID Country Offices, as well as a Regional Innovation Investment Fund funded by Africa Regional Department.
AgDevCo combines debt and equity investment with technical assistance to address both the financial and technical constraints to SME participation in agricultural value chains, performing a “business incubator” function.
The Regional Innovative Investments (RIIs) fund provides project development and patient capital for innovative agribusiness ventures with the potential to substantially stimulate production in multiple countries. Such investments consolidate the integration of SMEs and smallholders into higher-value more modern regional supply chains, shaping regional market development.
Access to regional markets will increase profitability and sustainability of SMEs funded through national SME catalytic funding. Conversely, tapping into more reliable and higher quality agricultural production flows through linkages to SMEs will increase the viability of regional agro-processing and marketing investments.
Through the provision of debt and equity AgDevCo will recoup a proportion of the funds it invests. It is proposed that for the funding in this BC we retain the existing funding modality where AgDevCo will redeploy funds into future projects rather than return funds to DFID. We will investigate whether future AgDevCo funding can be transformed into Development Capital Investment funding through a proposed Africa agribusiness investment platform.
Why is UK support required?
Africa is recognized as the region with the most unexploited potential for agriculture production. Development of agribusiness and transformation of agriculture in Africa could create jobs, income and opportunities for African smallholder base of which 60% of economically active women is part.
Yet there is relatively little investment in commercial agriculture, even in countries where the policy environment is more supportive. This is because investors face very high costs and risks associated with early-stage development, poor access to and high cost of finance, lack of experienced workforce and lack of a supporting network of service companies.
AgDevCo SME Catalytic Funds will address the specific needs of existing agriculture SMEs for additional finance, better linkages to markets and commercial demand, and managerial and technical capacity strengthening. The Regional Innovative Investments (RIIs) fund will target investments with a regional scope to offer expanded markets for SMEs and smallholders while strengthening regional value chain coordination. Funding for co-investment in Tanzania and across the portfolio will continue mitigating high front end costs and risks for potential investors.
What are the expected results?
The funding covered by this BC combined with the funding already disbursed through PIDG since mid-2013 will result in an investment portfolio for 2013-18 which will directly benefit over 900,000 people (50% women) and is expected to positively impact many more through additional spill over investments and improvements in agriculture infrastructure. Expected Outputs by 2018[1] are:
[1] For the full portfolio of investments 2013-18 including DFID funding from PSD (£11m, already disbursed) and Africa Division (£65.58m of which £30.82m have been disbursed and £34.76 are outstanding and covered by this BC)
- 57 agribusiness enterprises developed or expanded with an additional turnover of over £120 million
- Over 900,000 individuals directly benefiting from the new investments, including: over 77,000 smallholders’ households (over 420,000 individuals) and 7,000 additional FTE jobs (over 34,000 individuals)
- Improved availability of agriculture supporting infrastructure – 34,000 additional hectares under irrigation (Ha) and 125,000 additional metric tonnes in processing throughput
- Over $22million of additional regional trade directly generated by AgDevCo’s investments

How does the project fit with the country programme or department’s strategic objectives set out in the Operational Plan?
The intervention contributes to ARD’s headline result of 3 million people benefiting from improved participation in national and regional value chains by 2015, to DFID Ghana’s headline result of 30,000 producers accessing business services and to the delivery of the UK Tanzania High Level Partnership for Prosperity. It aligns with DFID Zambia priorities of leveraging private sector capital and increasing households’ income, and DFID Malawi priorities of supporting jobs and income generation, food security and growth in order to sustainably help people out of poverty.
What are the key risks to the success of the programme?
The programme is considered medium to high risk. AgDevCo maintains a full risk register and significant changes are promptly shared with DFID. The main identified risks for this intervention are:
1. Poor policy and regulatory environment, including barriers to cross border trade, deter private investment and hinder regional investments. This is mitigated by analysis before starting up operations and linkages to relevant policy initiatives, including through national level steering committees;
2. Displacing private finance or unnecessarily subsidising private companies. This is mitigated by including additionality in AgDevCo’s investment criteria and where feasible including private sector investment experts in the national steering committee;
3. Inability of investees to deliver expected development results, mitigated by rigorous pre-investment due diligence and technical assistance;
4. Environmental social and corporate governance not complied with. This is mitigated by adherence to IFC social impact standards and compliance with World Bank principles on community engagement relating to land issues. AgDevCo undertakes an environmental, social and governance (ESG) review of each investee, with additional requirements for larger investments and a rigorous Know Your Client policy requiring all investees to adopt ESG best practice, and to act in compliance with applicable local and international laws.

Strategic Case

Rationale for DFID Intervention - Investment in agriculture in Africa: potential and constraints
Africa is recognized as the region with the most unexploited potential for agriculture production[2]. Africa’s food markets, currently valued at US$313 billion a year from agriculture, could triple to US$1 trillion by 2030 if Africa’s farmers and agribusinesses expand their access to more capital, electricity, better technology and irrigated land, according to the World Bank[3].
[2] Africa holds almost 50 percent of the world’s uncultivated land which is suited for growing food crops, comprising as many as 450 million hectares that are not forested, protected, or densely populated. Africa uses less than 2 percent of its renewable water sources, compared to a world average of five percent. Its harvests routinely yield far less than their potential and, for mainstay food crops such as maize the yield gap is as wide as 60 to 80 percent. Post-harvest losses run to 15 to 20 percent for cereals and are higher for perishable products due to poor storage and poor farm infrastructure. World Bank (2013), Growing Africa: Unlocking the Potential of Agribusiness report
[3] World Bank (2013), Growing Africa: Unlocking the Potential of Agribusiness report

Few, if any, DFID focus countries in Africa will be able to make significant and sustained progress on broad-based poverty reduction and inclusive economic growth without attention to the agriculture sector. The AgRefresh identifies commercial agriculture as an area DFID should improve its offer on.[4]
[4] The AgRefresh is DFID’s latest thinking on the agriculture sector, drawing on the latest evidence, future trends, and a light touch portfolio review of DFID’s agriculture spend spanning over 2007-2012.

There are two main reasons for this. First, commercial agriculture creates both farm and non-farm income generating opportunities for the rural poor. Supporting smallholder access to markets and productivity enhancing inputs drives up incomes, creates better paying jobs and contributes to a dynamic rural economy. Second, agriculture is a productive sector and has much to offer to the economic development agenda. This extends beyond the farm to agribusinesses involved in light manufacturing such as food processing, textiles, and services. If untapped, this potential could help support a long-term pathway out of poverty for many of DFID’s focus countries.

As countries transition towards upper middle income status, the relative importance of manufacturing (including agribusiness), and services rises, replacing primary agriculture. DFID supports this transition by focusing on factors which will ensure agriculture is a positive force for economic development and poverty reduction. At the farm level, we support smallholders to be more productive and have greater market access - national, regional and international. For agribusinesses, we prioritise support for investments which will better connect them to smallholder farmers, providing sustainable demand for higher value added products and thus higher incomes. Both pathways have smallholders at their heart.

Investing in the transformation of African agriculture is important to poverty reduction for the following reasons:
1. Poverty is predominantly a rural phenomenon and will remain so for at least the next two decades. More than three quarters of those living in extreme poverty are in rural areas, with two thirds of those earning a living from agriculture;
2. The agriculture sector has played a critical role in the economic transformation of many middle income and developed countries, so needs to be sufficiently factored in when supporting future inclusive growth pathways for the world’s poorest countries;
3. Regional ILO data shows more than 60 per cent of employed women in Sub-Saharan Africa work in agriculture. Investment in women working in agriculture can contribute significantly to inclusive economic growth;
4. Without sufficient attention to the sector, wider development outcomes on increased nutrition and food security will not be achieved;
5. Africa’s food import bill currently stands at $50 billion annually[5] and growing, although opportunities exist to develop competitive production and regional supply chains.
  [5] World Bank, 2014

Despite Africa’s high agricultural potential there has been relatively little investment in commercial agriculture, even in countries where the policy environment is more supportive. This is because investors face very high costs and risks associated with early-stage development – including high land clearing costs, lack of essential infrastructure (e.g. bulk water supply, electricity connections, feeder roads), lack of experienced workforce and poor access to and high cost of finance, especially for emergent and smallholder farmers. More generally there is a lack of a supporting network of service companies (e.g. inputs suppliers, logistics companies, rural finance providers), which further increases operating costs for pioneering agricultural investors.

1. Smallholder farmers achieve low productivity because of poor access to modern inputs and credit, and what limited services smallholders can access are very expensive. They also have very limited access to post-harvest facilities (e.g. storage) and consequently suffer high post-harvest waste and weak bargaining power with buyers, resulting in low farm-gate prices. Moreover, typically they have limited knowledge of modern farming practices, including of conservation farming methods, soil fertility management and use of improved seeds.
2. The development of regional agriculture markets is constrained by an uncertain policy environment, lack of infrastructure and low investment. Quality and reliability of production supply are a big constraint for agri-business processing and marketing operations.

1. Four specific transmission mechanisms between investment in agriculture and poverty reduction are generally considered: direct impact of improved agricultural productivity on rural incomes; impact of cheaper food for the urban and rural poor; multiplier effects from increased agricultural productivity on increased economic opportunities in the non-farm sector; and agriculture’s role in stimulating and sustaining economic transition away from agriculture towards manufacturing and services.[6]
  [6] DFID, 2014. Agriculture and Poverty: Agriculture and growth evidence paper series
2. The extent to which increased agricultural growth impacts on poverty reduction also depends on contextual factors like:
- distribution of and access to land by poor and vulnerable groups, including women and youth;
- farm size, quality and potential of land;
- distribution of labour and the likelihood that wage gains from increased productivity can benefit a large number of women, men and youth;
- crop mix impact on domestic and imported food prices and the extent to which poor households might benefit from cheaper food;
- economic linkages and the capacity of non-agricultural economy to realise transmission effects[7];
  [7] DFID, 2014. Agriculture and Poverty: Agriculture and growth evidence paper series, p24.
- Agricultural policy, including subsidies and trade issues and the barriers/opportunities these present with regard to the productivity of the agricultural sector and on food prices.
AgDevCo
The Africa Agricultural Development Company Limited (AgDevCo) is a not-profit-distributing (i.e. they choose to reinvest any profit generated) limited company registered in the UK. It is an agricultural project developer and social impact investor operating in sub-Saharan Africa since 2009.

AgDevCo invests ‘patient capital’[8] in early stage or new commercially viable agriculture and agribusiness ventures with high developmental benefits, bringing them to the point where they can attract private investment from domestic and overseas investors.
[8] AgDevCo defines “patient capital” as long-term capital that seeks a social as well as a financial return and one that has a high tolerance for risk and is willing to accept positive but less than fully commercial returns in exchange for greater development impact
Figure 1. Project activities, financing and the project development cycle

AgDevCo’s distinctive business model combines the ability to invest debt and equity in promising agricultural businesses and provide hands-on management support both pre- and post-investment.

For SME investments this means that AgDevCo takes an active role on company boards and in many cases performs a “business incubation” function (e.g. by offering support in developing financial systems, brokering sales agreements, devising a marketing strategy etc.)[9]. For medium-size and large irrigation and agro-processing developments AgDevCo enters into joint venture partnerships with commercial sponsors or in some cases acts as the principal sponsor itself to develop a project and see it through to the point where it attracts commercial investment.
[9] AgDevCo’s experience in Mozambique is that the business incubation function with SMEs is critical to long-term success. It can however involve significant costs, which may not be entirely recoverable from the investee, at least not in the early years when there is limited project cash flow available.
Current and planned DFID funding to AgDevCo and rationale for a new Business Case
The current business case has been prepared principally to outline the management arrangement to continue funding AgDevCo through a coordinated Africa Division framework outside of PIDG as continuation of current management arrangement is not possible. This also means that having funding approved through the PIDG business case is no longer appropriate.

Prior to 2013, DFID committed £8.97m to AgDevCo through accountable grant agreements between AgDevCo and DFID Mozambique (2011, £6.5m) and DFID Ghana (2012, £2.47m).

In 2013, Private Sector Department committed £11 million to AgDevCo under the PIDG business case.

In June 2013, the SofS approved £50m additional funding to AgDevCo through an Africa Division framework for 2013-18, which allowed AgDevCo to set up 3 new SME Catalytic Funds in Malawi, Zambia and Ghana at £10m each, funded by DFID Country Offices, and a new Regional Innovation Investment Fund at £20m, funded by Africa Regional Department. The Africa Division framework created the coordination mechanisms and monitoring structures that would allow other DFID Country Offices to join and included up to a further £2.5m approved for an independent evaluation.

In October 2013, the SofS approved a further £15.58m additional funding to AgDevCo through the same framework as part of the launch of the High Level Prosperity Partnership between UK and Tanzania.

The preferred channel to disburse the additional funding to AgDevCo was the PIDG, taking advantage of AgDevCo’s status as a PIDG affiliated facility. In November 2013, the PIDG Governing Council rejected the establishment of a dedicated PIDG facility for agriculture, as some donors believed this would take the PIDG beyond its mandate of infrastructure into on-farm investment. However the Governing Council approved AgDevCo continuing as an affiliated facility whilst action is taken to transfer it outside the PIDG. The Governing Council also approved DFID and Dutch funding to continue to be channelled to AgDevCo through the PIDG Trust in the short term.
Specific needs addressed by the continuation of funding to AgDevCo and complementarity between ARD and Country Offices’ funding
The advantages of a joined up approach to Africa Division funding to AgDevCo have been evident since the approval of additional funding and allowed AgDevCo to scale up its operations in 5 countries consistently achieving the proposed results as evidence by the 2014 AR of the AgDevCo scale up which scored A+. Investments in the first 6 months since the 2013 scale up approval directly benefited 3000 farmers (49% women) and over 13,500 individuals. Advantages of continuing the Africa division funding framework include:
- Strategic coordination between various DFID investments
- Improved country level oversight of various funding streams to AgDevCo
- Strategic management of AgDevCo operational scale up;
- Improved institutional learning;
- More efficient and effective monitoring and evaluation;
- Lower transaction costs for DFID and for AgDevCo
The continuation of the coordinated framework for DFID investment into AgDevCo will maximise strategic synergies within Africa Division between national level SME catalytic funds and the Regional Innovation Investment fund as well as between these two instruments and other DFID investments.
In-country SME catalytic funds
Country level funding for the set up of in-country SME Catalytic Funds will continue to address the specific needs of existing agriculture SMEs for:
- additional finance (equity, debt/loan)
- better linkages to markets and commercial demand
- managerial and technical capacity strengthening.

AgDevCo will combine patient capital with technical assistance to address both the financial and technical constraints to SME participation in agricultural value chains. In this sense AgDevCo’s SME Catalytic Fund investments will perform a “business incubator” function. As part of this, the Catalytic Fund in Ghana will expand its geographical focus from Northern Ghana only, to a national basis. This is to take advantage of the increased opportunities in other areas to drive economic growth and development of the agricultural sector through more strategic investments. Northern Ghana will remain a particular focus area of the Fund.
Regional Innovative Investments Fund
Africa Regional Department will continue funding a Regional Innovative Investments (RIIs) fund for innovative agribusinesses ventures with the potential to substantially stimulate production in multiple countries.

The development of modern regional food value chains in Africa is an opportunity to contribute to spreading economic growth, while increasing the competiveness of the regional agriculture sector and diversification of jobs and income opportunities in rural areas. Investment into innovative medium to large scale agribusiness is constrained by[10]:
[10] World Bank (2013), Growing Africa: Unlocking the Potential of Agribusiness report; Tayler G and Dixie G. (2012); Investments in Agribusiness: A Retrospective View of a Development Bank’s Investments in Agribusiness in Africa and East Asia, The Committee for Food Security, 39th Session
- the need to ensure a reliable throughput flow in a highly fragmented and thin market which increases risks and costs for investors investment
- high front end costs and risks, both for larger production and for processing operations
- lack of coordination and quality services along the value chain

Unless these needs are addressed, the current trends of increased imports to meet the emerging and evolving local demand will continue, negatively impacting countries’ balance of payments position, while the possibilities for neighbouring countries to trade with each other remain largely untapped.

AgDevCo will provide social venture capital (capital invested ‘at front end’ to structure viable investments) and patient capital in RIIs that provide the opportunity to consolidate the integration of SMEs and smallholders into higher-value more modern regional supply chains, stimulating both national and cross border trade and generating jobs and income. Access to regional markets will increase profitability and sustainability of SMEs funded through national SME catalytic funding, ensuring that they share in the growing regional food and agribusiness sector linking in larger numbers of smallholders. Conversely, tapping into more reliable and higher quality agricultural production flows through linkages to SMEs and SMEs clusters will increase the viability of regional agro-processing investments.
Complementarity with existing DFID funding to AgDevCo outside this BC and framework to consider for future funding increases under this BC
Funding to AgDevCo for investment in Uganda, approved by the SofS in September 2014 as part of the NU-TEC[11] Business Case, although not covered by this BC, will benefit from the coordination mechanisms set up through this BC. A single contract with AgDevCo will cover funding from this and Uganda NU-TEC business cases.
[11] ‘Northern Uganda; Transforming the Economy Through Climate-smart agribusiness’

Funding under this BC will continue to complement DFID’s Private Sector Department £11m funding to AgDevCo through PIDG (already disbursed and invested by AgDevCo), DFID Mozambique funding to AgDevCo to manage Beira Agriculture Growth Corridor Catalytic Fund (£7m accountable grant) and DFID Ghana funding to develop large scale irrigated outgrowers farm hubs in Northern Ghana (£2.47m accountable grant).

Africa Division coordinated funding is allowing AgDevCo to consolidate its business model at scale. DFID Ghana and DFID Tanzania among others have already indicated the intention to scale up existing funding to AgDevCo, building on the coordination and management structures already set up through this BC. The intention is to review progress and determine funding needs as part of the 2015 and subsequent years Annual Review process. If required, a submission for a cost extension to this Business Case will then be made, in order to allow further investment to be made through this framework.

Africa Division coordinated funding will continue to address the need for coherent learning through a joint independent evaluation which has been competitively contracted in 2014.

Finally the coordinated funding framework will continue to allow more strategic coordination between DFID support to investments in agriculture through AgDevCo and wider DFID support to developing agriculture markets, improving business environments and encouraging trade both at country and regional level. Although policy and regulatory issues are not directly targeted through this intervention, the Africa Division funding framework enables DFID Country Offices and ARD to take an active role in linking investment made by AgDevCo to relevant sector wide country support programmes through national level Steering Committees and an Africa wide Steering Committee.
Gender Equality

Regional ILO data shows that over 60% of women working in Africa do so in the agriculture sector yet research shows that the gender gap in African agriculture significantly undermines efforts to reduce poverty through agricultural growth. A World Bank report[12] on improving opportunities for women farmers notes that closing the gender gap through investing in women farmers and instituting policies that address gender inequality in African agriculture could help increase food security and improve livelihoods for Africa’s growing population. Drawing on the FAO (2011) State of Food and Agriculture Report, the World Bank suggests that if women worldwide had the same access to productive resources as men, they could increase yields on their farms by 20-30% and raise total agricultural output by 2.5-4%.
[12] World Bank, (2014). Levelling the Field: Improving Opportunities for Women Farmers in Africa. The World Bank and One Campaign.

Gender sensitive investment in agriculture is therefore expected to contribute to women’s economic empowerment. AgDevCo recognises that increasing the income of the primary woman in the household can have a significant impact on poverty reduction and food security and therefore seeks to design and invest in businesses that incorporate opportunities to maximise improvements in household welfare by supporting women farmers and women entrepreneurs.

Clearly, other factors influence the extent to which agricultural investment leads to women’s economic empowerment in various contexts, such as access to resources (e.g. land, water, credit, capital), accessible technology, availability of market and technical advice, skills, customary gender roles (especially child rearing and inheritance norms) and government policy on gender equality. The recent World Bank report[13] notes that productivity gaps between men and women in sub-Saharan Africa range from 13% in Uganda to 25% in Malawi. This was correlated with lower levels of agricultural inputs by women (e.g. fertiliser, new seeds, extension services) and market failures or institutional constraints that hinder the effectiveness of inputs for women.
[13] . ibid

Gender equality challenges therefore need to be fully understood and addressed as far as possible to enhance agricultural investment potential for women entrepreneurs and labourers and to guide responsible investment. Examining women farmers’ constraints should be integrated into planning interventions. In 2015, AgDevCo will develop a dedicated strategy to increase its investments’ benefits to women with DFID providing technical support and guidance. The 2012 PIDG study Impact on Women and Girls of PIDG-Support Projects will inform the development of the gender strategy for AgDevCo.

AgDevCo’s work has the potential to make a significant difference to women’s economic empowerment opportunities in project countries and to provide evidence of success and learning in this area. It will be important to demonstrate impact on poorer members of society, including women and girls. This will be addressed through monitoring and evaluation arrangements. In support of this AgDevCo disaggregates all beneficiaries’ results by sex and has agreed an aspirational target of 50% of development benefits accruing to women. This is above current trends which show that 25-30% of beneficiaries are women and will be facilitated by having a gender strategy to guide good practice in due course.

Expected Outputs and Outcomes

Expected Impact: Inclusive agriculture sector growth which benefits smallholders in the African countries in which AgDevCo operates, contributing to wider poverty reduction and food security in the region.

The programme’s Outcome is to leverage additional private sector investment in agribusiness and agricultural infrastructure and increase agricultural cross border trade in targeted countries, generating jobs and income for smallholders.

The expected Outputs generated by 2018 by the funding covered by the BC and the funding already disbursed by DFID to AgDevCo through PIDG since 2013 will be[14]:
[14] A coordinated logframe including results directly attributable to DFID funding committed for 2013-28 (from DFID PSD, ARD, Malawi, Ghana, Zambia, Tanzania) has been approved in May 2014 with nested logframes for specific results in each country.
    1. Development or expansion of 57 agribusiness enterprises that are financed, owned or operated on a commercial basis by AgDevCo which will result in an additional turnover for these enterprises of over £120m Over 900,000 individuals to directly benefit by 2017 (50% women), including: over 77,000 smallholders’ households (over 420,000 individuals) directly benefiting from additional income by 2018 through linkages with companies in which AgDevCo invests. Over 34,000 individuals benefiting from around 7,000 additional jobs created (FTE) through/in enterprises supported by AgDevCo.
    2. Improved availability of agriculture supporting infrastructure – 34,000 additional hectares under irrigation (Ha) and 125,000 additional metric tonnes in processing throughput.
    3. Over $22million of additional regional trade directly generated by AgDevCo’s investments
As the UK will provide re-deployable capital, we expect that part of the DFID funding invested by AgDevCo will be returned to AgDevCo by 2021 to be used for reinvestment. In this way UK aid money will be redeployed several times over, multiplying the developmental impact estimated above.
Rationale for approving funds beyond the current Spending Review (SR) period

There is a compelling VfM case for approving funds beyond the current SR period, although strictly speaking this is a re-approval of funds already approved. Firstly, AgDevCo is highly complementary to the rest of ARD’s regional portfolio in agribusiness, thereby increasing the potential impact and value for money of related DFID interventions. Secondly, the value for money of continuing with AgDevCo is determined to be significantly greater than delaying or terminating the programme. The original programme started in 2013, and given the nature of the investments it was not possible or intended to complete the programme before the end of the current SR because it is important that investments are carefully considered, reviewed, contracted and monitored to ensure value for money and maximum results.

## Appraisal Case

Option 1 - Withdraw funding

There is no option of DFID continuing to fund AgDevCo under the PIDG umbrella. If DFID does not move to direct funding of AgDevCo, then it would no longer be able to provide funding to the organisation.

All outstanding commitments to funding for AgDevCo, along with associated results and development impact, would be suspended. AgDevCo would, however, be able to see investments already approved through to completion, as necessary funds have already been disbursed, although their staff complements will have to be significantly scaled back due to the reduced size of the portfolio.

The decision to withdraw funding would not be based on any underperformance on the part of AgDevCo, but rather on a decision taken by PIDG entirely out of AgDevCo’s control. Given that DFID had committed these funds, and AgDevCo has planned investments in good faith, a decision to withdraw would entail a reputational risk for DFID.

Option 2 – Continue coordinated DFID Africa Division (Country Office funds and ARD funds) funding through direct funding with AgDevCo.

Under this option, DFID would continue to provide previously agreed funding, and AgDevCo would retain commitments to deliver agreed results. The funding would come from the following sources:

DFID Funding Source	Approved (£)	Outstanding (£)
Africa Regional Department	20,000,000	10,008,311
Ghana Country Office	10,000,000	7,627,294
Malawi Country Office	10,000,000	6,904,029
Zambia Country Office	10,000,000	5,037,445
Tanzania BP	15,580,000	5,186,572
Total DFID Funding through AgDevCo	65,580,000	34,763,651
Additional funding for Independent Evaluation Research and Dissemination (through separate contract) – ARD Funding	Up to 2,500,000	Revised to 1,700,000

Justification for Option 2

AgDevCo tackles the key binding constraints to private sector investment in agriculture highlighted in the strategic case, namely high start-up costs, high risk and broken value chains which in turn prevent smallholders and SMEs from benefiting from developing regional markets. As illustrated in the table below, AgDevCo enters the market at an earlier stage of development than other facilities and provides the capital and hands-on management support needed to allow SMEs to start-up and expand.

Figure 2: Differences between AgDevCo and comparators
This option allows DFID to continue to invest in the development of agriculture value chains in a way that strategically coordinates different funding streams, focuses on the private sector and its commercial viability, and uses innovative private sector oriented funding mechanisms.

DFID funds are used by AgDevCo to invest debt and equity in agribusinesses. AgDevCo recoups a proportion of these funds, which can then be redeployed into future projects generating even greater development outcomes.

Furthermore, by developing businesses until they become commercially attractive investment opportunities, AgDevCo helps develop previously missing links in agriculture value chains. After AgDevCo exits, it is expected that these businesses will continue functioning, helping agriculture markets thicken and expand.

An independent multi country evaluation, research and dissemination component is running alongside the intervention and under this option it will draw on the experience of the full portfolio of investment for which DFID funding had been committed.

Theory of Change

The diagram below outlines the main change processes and assumptions in this intervention’s Theory of Change (Annex 1 contains the supporting evidence). The initial Theory of Change has been further refined and reviewed in coordination between DFID, AgDevCo and the appointed independent evaluators.

Cost-Benefit Analysis

As outlined in sections 2.1 and 2.2, the decision open to DFID is either to maintain existing funding commitments to AgDevCo under a new arrangement, or to stop funding when AgDevCo moves out of the PIDG umbrella (the counterfactual). The cost-benefit analysis (CBA) below considers the impact of outstanding DFID Africa Division funding approved in the 2013 submission (£34,763,651). The methodology of the CBA has been refined from past calculations to reflect more directly the benefits to smallholders and employees, which underpin the logic for DFID intervention. Assumptions have been updated to reflect the latest available information. Proposed changes in the management structure (move to a direct relationship with AgDevCo) do not change expected results.

The £11 million committed by PSD under the PIDG BC have already been disbursed in 2013 and therefore are not included in the calculation for the cost-benefit analsysis as there is no change between Option 1 (terminating funding) and Option 2 (continuing funding).

Annex 2 contains the full Cost-Benefit Analysis. The table below shows the balance of costs and benefits from the outstanding amount of approved Africa Division funding to AgDevCo (£34.8m excluding evaluation funding) through to 2024.

BALANCE OF COSTS & BENEFITS (2015 - 2024) UNDISBURSED FUNDS FROM AFRICA DIVISION
Costs (GBP)
Total Costs to DFID	34,763,652
Benefits (GBP)
Direct Increase in Employee Income	16,862,745
Direct Increase in Smallholders’ Income	101,259,630
Total Benefits	118,122,375

Nominal Net Benefits	83,358,723
NPV	37,312,740

The total financial benefits are defined as the direct increases in the income of employees and smallholders reached by the program. Total financial benefits generated through the additional £34.8m from ARD, DFID Ghana, DFID Malawi, DFID Zambia, and Tanzania Blended Partnerships in terms of direct increases in income amount to approximately £118m by 2024[15]. Accounting for the direct costs to DFID, this has a net present value (NPV) of £37m when discounted over the period using a 10% discount rate[16]. The internal rate of return (IRR) is 33% and the benefit/cost ratio is 2.17. In addition to this there are likely to be further unquantifiable benefits which will arise from the programme, including poverty reduction and increased food security. It is noted that these NPV calculations take into account only the first round of investments, i.e. they do not take account of future reinvestment of recycled funds by AgDevCo.
[15] Indirect increases in income have not been included in this total.
[16] A 10% discount rate is a rough estimate of the economic opportunity cost of capital for the 5 countries included in the analysis and is in-line with DFID policy

These benefits are attributable to both the investment made by AgDevCo (using Africa Division funding) and additional capital invested by DFIs and private investors in the firms supported by AgDevCo. However, the monetary value of the (returnable capital) DFI and private sector investments has not been included in the CBA on the grounds that they should be profitable and so not a net cost.  That is, we assume that the expected returns to DFI and private sector investments are greater than the costs (otherwise the investments would not be profitable and so would be made); therefore including both the present value of the investments in the costs and the present value of financial returns to this additional investment in the benefits would increase the calculated NPV. To simplify the calculation and to make it more conservative, these returnable capital investments are not included in the above table.

This implies that investment in AgDevCo does make economic sense, even without accounting for the significant unquantifiable benefits. Assuming that many of the quantifiable benefits are incremental and that AgDevCo operating procedures ensure that investments are additional (i.e. do not crowd out other private sector investment) and have a strong developmental impact, the project is likely to also show significant positive socio-economic net benefits.

Value for Money

7 VfM indicators are identified in annex 3 to enable ongoing monitoring of the VfM achieved by AgDevCo throughout programme implementation. Not all of these will be reported from the outset. Initially, reporting should focus on economy, reflecting the fact that efficiency and effectiveness relate to outcomes and impact and so will take longer to materialise. Indicators will be agreed with AgDevCo, which will undertake to ensure that data is available for DFID Annual Reviews.

In addition to specifying indicators to be reported by AgDevCo, relevant comparators and milestones are also identified. This will allow for assessment of:

1. AgDevCo’s VfM performance as compared to similar organisations, providing context; and
2. Performance against business case assumptions, providing information on the extent to which expected results will be achieved at the expected cost.
## Commercial Case

Preferred route and AgDevCo’s unique advantage

As explained in the Appriasal Case the recommendation is to continue with the previously approved and committed funding to AgDevCo. To do so DFID need to move to a direct relationship with AgDevCo because they will no longer be an affiliated facility PIDG facility from 2015.

The options considered to formalise the relationship were: (i) an Accountable Grant; (ii) a Memorandum of Understanding (MoU); or (iii) a contract. A MoU is not considered appropriate for our relationship with AgDevCo which is a company rather than a Government or DFI. The Accountable Grant route also poses issues regarding legal enforceability.

A legally binding contract is considered to be the best option for the following reasons:

- it will allow us to include clauses to provide DFID with an enhanced oversight and compliance assurance as detailed in the Management Case;
- it should allow reduction of the cash balances AgDevCo hold prior to the execution of their funds. AgDevCo currently require cleared funds in their account for the total value of an investment before it is approved by their Board. Providing contractual assurances will allow AgDevCo to progressively move to request funds after Board approval which will reduce cash balances.

A single source waiver will be sought for a direct contract with AgDevCo. The main justification for a waiver is that this is a continuation of previously approved funding and an ongoing programme which is delivering results. A contract provides oversight and operational benefits as noted above over alternative forms of agreement.

Additionally AgDevCo still occupies a unique space in agribusiness investment in Africa. There are no other comparable companies that: (i) specialise completely in agribusiness investment in Africa; (ii) have a clear mandate to support poverty reduction and food security through a non-for-profit investment approach in agriculture; (iii) target an otherwise unsupported category of firms that needs both significant technical assistance and finance (debt and equity); and are able to develop and structure larger deals with competent sponsors at the same time; (iv) are already set up to continue to deliver the results DFID are aiming to achieve in this set of countries.

1. A new Agribusiness investment platform is now being considered that could potentially attract more project developers and investors in the same space and allocate funding competitively to AgDevCo and others but its design is still at early stages and it will not come to fruition in the next 2 years. We intend to increase competition in this area through such a platform.
2. We do not believe it appropriate to hold a competitive tender for this already approved funding at this point. If a single source waiver is not agreed this will harm the previous investment made by DFID in strengthening AgDevCo so that it could deliver at scale. A withdrawal of DFID committed funds would cause AgDevCo to exit current negotiations of investments planned in 2015/16, which are expected to directly benefit over 80,000 people. In addition to forfeiting these developmental benefits, a cessation or suspending of programme activity will cause severe reputational damage to AgDevCo and DFID and it is likely to cause AgDevCo loosing key staff while funding is on hold.

Value for Money in investment decisions

AgDevCo operates under a fully developed Investment Policy and Procedures, including procedures for the rigorous appraisal of risks and returns for each investment. Investment decisions are competence of the Executive Committee, Investment Committee or Board according to their delegated authorities. AgDevCo’s governance structure consists of a main board with five reputable, qualified and experienced Directors.

Value for Money through procurement

AgDevCo’s own Procurement and Competitive Tendering Policy and Procedures are fully compliant with PIDG procurement policies (AgDevCo is an affiliate of the PIDG until March 2015).

The procurement policies of the PIDG facilities were fully evaluated in the Multilateral Aid Review in 2010 (MAR) and in the approved PIDG Business Case. PIDG was one of the top three performers in the MAR, offering very good Value for Money. It scored 4 (out of 4) on Effectiveness in terms of Delivery, Strategic and Performance Management and Financial Resources Management.

Management of contract and supplier performance

As detailed in the Management Case, ARD will lead engagement with AgDevCo at the corporate level while country offices maintain oversight of AgDevCo country offices as well as of the full portfolio of investments in country. The independently contracted Evaluation Management Unit will also have a critical role in providing evidence of AgDevCo’s performance. A direct contract between DFID and AgDevCo will include compliance assurance mechanisms as well as specific clauses related to DFID’s oversight (see 5. Management case below).

ARD and PSD completed a comprehensive Due Dilligence Assessment (DDA) of AgDevCo in 2014. The DDA found that AgDevCo does not pose unacceptable fiduciary and/or reputational risks to DFID. AgDevCo has a well-established approach to remuneration, recognising the need to recruit and retain suitability qualified people who are able to command market levels of remuneration in the commercial sector AgDevCo’s actual remuneration structure is lower than recently agreed CDC remuneration levels. DFID does not have a role in setting bonuses for AgDevCo staff but its bonus policy is considered to be reasonable and similar to DFID’s. The DDA recommendations continue to be followed up in the monthly meetings between ARD and AgDevCo’s CEO.

The contract for the Evaluation Management Unit (EMU) was awarded in July 2014 following a competitive tender process through the Global Evaluation Framework Agreement (GEFA). The contract was awarded on an output based agreement and contains a number of break points.

## Financial Case

Overview of funding by Africa Division through the proposed framework

The table below shows the total AgDevCo funding for 6 years (2013 – 2018). Total disbursed and planned contributions to AgDevCo by Africa Division amount to £65.6m. This business case covers the funding that remains to be disbursed from the July 2013 submission - £34.8m for AgDevCo as detailed below, plus £1.7mfor the independent evaluation contract. This funding is already available within each office’s budget and had already been approved by the SofS in July and October 2013:

Funding Profile (GBP)	2013	2014	2015	2016	2017	2018	Total BC	Total

DfID ARD (RII)	1,566,667	8,425,022	4,303,720	2,849,633	2,854,959	-	10,008,311	20,000,000
DfID Ghana (SME CF)	680,673	1,692,033	1,366,223	2,302,544	2,297,544	1,660,982	7,627,294	10,000,000
DfID Malawi (SME CF)	572,533	2,523,438	4,452,890	1,197,475	835,777	417,888	6,904,029	10,000,000
DfID Tanzania (BP)	-	10,393,428	3,473,862	570,903	570,903	570,903	5,186,572	15,580,000
DFID Zambia (SME CF)	180,127	4,782,429	2,265,607	1,539,110	821,818	410,909	5,037,445	10,000,000
Total Additional Funding	2,999,999	27,816,349	15,862,301	8,459,665	7,381,002	3,060,683	34,763,651	65,580,000

Additional Contributions

DFID spending Departments could in future decide to make additional contributions through this framework, upon AgDevCo satisfactory performance. DFID Ghana and DFID Tanzania have already indicated that they are actively considering this option. Spending Departments may request, within the next 6-18 months, for additional funds to be added to the new DFID AgDevCo Business Case and contract through a submission and BC addendum that increases AgDevCo existing budget and more especially its investment portfolio.

DFID Uganda has recently started a new programme which includes work with AgDevCo. Their £12 million of additional funding is covered under the NU-TEC business case. In order to reduce transaction costs and increase coordination, their funding will form part of the new contract.

Funding sector codes

AgDevCo components
Benefiting Country: Africa Regional, Ghana, Malawi, Tanzania, Zambia
	Input Sector	Input Sector Code	Percentage Allocation
1	Agricultural Development	31120	70
2	Agriculture Policy and Administrative Management	31110	30
Evaluation components
Benefiting Country: Africa Regional, Ghana, Malawi, Mozambique, Tanzania, Zambia
	Input Sector	Input Sector Code	Percentage Allocation
1	Agricultural Development	31120	70
2	Agriculture Policy and Administrative Management	31110	30

Disbursement of funding

A contract will be agreed and signed with AgDevCo to cover the funding in this business case and funding already approved for DFID Uganda. The contract will support the enhanced oversight arrangements we will be putting in place as detailed in the Management Case.

It is anticipated that ARD and Country Offices’ funds will be disbursed to AgDevCo in four (quarterly) payments per year with separate payment requests for Fund Management and Overheads and actual investments. Additional requests for DFID disbursements to cover investments will be considered on an ad hoc basis.

Disbursements to AgDevCo will be made on the basis of need, following receipt of disbursement requests/needs letter from AgDevCo and any supporting documents required under the contract. Disbursement requests will detail the funding needs, cash balance and liquidity position of AgDevCo to avoid payments being made in advance of need. Promisory notes were considered and discussed with FCPD as an option to reduce AgDevCo’s cash balances but it was agreed that the transactions are not large enough to proceed with that option.

AgDevCo requests will itemise funding needs from ARD and each Country Office. The requests will be centrally received by ARD who will share them with the Country Offices for agreement. AgDevCo need funds in their account to be able to make a commitment to an investment at their Board, so investment approval is defined as their point of commercial need. All needs requests will therefore include any investments expected to go to the Board for approval in the next three months. Any cash balances due to funds disbursed to AgDevCo that have not been committed or exchange rate gains will be offset against the next needs letter.

Disbursements under the previous arrangements were every six months; moving to quarterly disbursements reduces the risk of investments not proceeding to Board approval and cash being held in the AgDevCo account for a long time before commitment. AgDevCo’s policy is for investments to move from Board approval to execution (a legally binding contract) within 8-12 weeks.

In the framework of the contractual certainty of funding, AgDevCo will progressively move to commercial need for funds being after Board approval so closer to when contracts will be signed, further reducing the length of time that AgDevCo holds funds before investment contract execution.

ARD and Country Offices’ support to AgDevCo will remain in their respective budgets. A separate component within the AgDevCo programme will appear for ARD and each contributing Country Office.

The tentative disbursement schedule for the remaining funds covered in this business case will be as follows:
Funding Profile (£)	2015	2016	2017	2018	Total
DfID ARD (RII)	4,303,720	2,849,633	2,854,960		10,008,311
DfID Ghana (SME CF)	1,366,223	2,302,544	2,297,544	1,660,982	7,627,294
DfID Malawi (SME CF)	4,452,890	1,197,475	835,777	417,888	6,904,029
DfID Zambia (SME CF)	2,265,607	1,539,110	821,818	410,909	5,037,445
Tanzania BP	3,473,862	570,903	570,903	570,903	5,186,572
Total Funding	15,862,302	8,457,665	7,381,002	3,060,683	34,763,651

*AgDevCo accounting practices use calendar year not fiscal year.

Use of funding by AgDevCo and AgDevCo costs

Funding to AgDevCo is made up of the following:

1. Fund Management & Overhead (FM&O) costs and Investment management (IM) staff costs which are fixed at 5% per annum (pa) of the portfolio under management (total value of funds), disbursed in GBP quarterly. These costs cover: office costs, administration, professional fees (including corporate legal fees), fund management staff and activities, investment management staff and activities.
2. Project Development Costs which are intended to be capitalised into a project vehicle and recovered at financial close (i.e. when commercial finance becomes available for the business). For this reason, they will be funded from the investment element of funding
3. Investment funds which are the funds actually invested by AgdevCo in companies.
4. Technical Assistance which will be 12.5% pa of catalytic fund elements to be used to support the SMEs in the development and running of their businesses after investments have been made. The TA will be typically a combination of technical agronomic and business management support, financial reporting support, and technical social impact and gender support. It will be provided by both AgDevCo staff and third parties.

Funding for (i), (ii) and (iii) is classed as CDEL and (iv) is RDEL. All the funds from ARD and DFID Tanzania will be classed as CDEL and the SME CF programmes will be a mix of RDEL and CDEL. The evaluation is also classed as RDEL. Of the total funding (£36,500,000) for this programme: £31,400,000 will be CDEL and £5,100,000 will be RDEL.

The above analysis does not take account of the expected interest and investment income from the investments or defaults. Based on a relatively conservative disbursement profile over 5 years[17] and 5% per annum assumed return on all investments the expected accrued interest income (excluding any capitalisation) could eventually be around £1m for SME and £2.3m for the medium and large scale investments. This interest income could be used to partially offset defaults or write downs in the investment portfolio and/or to fund future FM&O and IM costs to continue managing investments with a longer horizon of this BC and re-invested funds after DFID funding finishes. The detailed arrangements will be included in the new contract.
[17] 10%/30%/30%/30%/0%

Assessment of possible financial risk and fraud

A comprehensive due diligence assessment of AgDevCo was conducted in March 2014. The assessment found that AgDevCo does not pose unacceptable negative fiduciary and/or reputational risks to DFID. However it did highlight two areas of medium risk: AgDevCo’s growing reliance on DFID financing; and that its operating policies and procedures (OPPs) have not been fully tested at scale. On the first, AgDevCo have been taking steps to increase financing from other sources. And, on the second the lead adviser in ARD initiated monthly meetings with AgDevCo’s CEO to monitor progress on the scale up. 2015 and future ARs will further scrutinize the application of AgDevCo’s OPPs at larger scale.

Monitoring of Financial spend

ARD undertakes regular monitoring of AgDevCo spend against annual forecasts and conducts Annual Reviews of project performance. AgDevCo will submit quarterly unaudited financial statements (highlighting drawdown on the ARD and Country Offices’ funds) with its quarterly narrative reports on progress, for discussion in the Steering Committee.

AgDevCo, are subject to annual external audits which will be shared with ARD annually including their management response.

Treatment of assets

Through the provision of debt and equity AgDevCo will recoup a substantial proportion of the funds it invests. As a non-profit-sharing investment company, AgDevCo statutes confirm they will redeploy funds into future projects generating even greater employment, income and development outcomes. ARD will monitor their balance sheet and request valuation annually. Through the enhanced oversight arrangements that will be included in the contract (detailed in the management case) DFID will have the right to scrutinize any change in AgDevCo’s main policies including how reflows are managed. We will investigate whether future AgDevCo funding can be transformed into Development Capital Investment funding through a proposed Africa Agribusiness platform.

## Management Case

AgDevCo governance

AgDevCo is currently an affiliated PIDG facility but its affiliation is expected to cease in 2015. As outlined in the original submission if AgDevCo did not become a fully-fledged PIDG member by the end of FY 2013-14 we would explore alternative arrangements to channel funding to AgDevCo. DFID will now put in place a direct contract with AgDevCo, which will include break clauses if we find the programme no longer demonstrates value for money or delivers results.

1. DFID will establish enhanced oversight and compliance mechanisms as it currently provides about 80% of AgDevCo’s funding (although new donors have been attracted with a reduction of DFID burden share expected from 2016-17). AgDevCo is currently registered as a company limited by shares which chooses not to share profits.
2. In order to strengthen DFID oversight ARD will include clauses in the contract with AgDevCo that will give DFID the right to terminate funding if any of the following happens without DFID prior consent: (i) appointment of AgDevCo Directors or removal of directors under special circumstances; (ii) changes in AgDevCo’s Main Policies, including those related to social and environmental policies and procedures; and (iii) distributions of returns from investments to the shareholder (should a request arise in rare circumstances).

In the medium term, DFID will seek an enhanced role in AgDevCo’s governance to further strengthen DFID’s oversight, while preserving AgDevCo’s operational freedom.

ARD sought legal advice on how DFID could enhance oversight of AgDevCo’s governance under the current arrangements. The option of DFID being issued with a ‘golden share’, a special share class in order to give DFID specific powers was considered. Legal advice considered that this would be possible but there is a risk it could be successfully challenged as contravening EU law as a restriction on the free movement of capital under Article 63 of the Treaty on the Functioning of the European Union. It was considered probable that DFID would be able to defend any action, with the arrangement regarded as a justifiable and proportionate restriction to serve a legitimate overriding interest. On balance however, the legal risks around the option make it not feasible. The alternative of including strong compliance clauses in the contract with AgDevCo was considered the best option in the short term. Initial discussions with Procurement Division and AgDevCo have confirmed this would be possible and positive legal advice was received, so ARD will proceed in this way if the Business Case is approved.

AgDevCo are currently considering two options on their governance: (i) to transfer its shares to a UK registered charity Enterprise for Development (EFD); or (ii) to become a company limited by guarantee (by transferring all assets to a new company limited by guarantee registered in the UK. Both options would address the perceived anomaly of public money being used to fund a company owned by an individual. If AgDevCo became a company limited by guarantee then DFID could potentially become a member of the company as we have done in other programmes, with a role in AgDevCo’s governance commensurate to the level of funding provided. If AgDevCo’s shares were transferred to EFD, we will continue enforcing our oversight through contractual compliance mechanisms.

AgDevCo’s Operating Policies and Procedures guide the way it does business through both SME catalytic and regional innovative investment funding. This includes a commitment to responsible investing and adherence to the International Finance Corporation (IFC) Performance Standards on social and environmental sustainability. It conducts commercial and legal due diligence for all new inestments and requires all investees to adopt environmental, social and governance best practice, and to carry on their businesses in compliance with all applicable loal and international laws. Ensuring that local communities and smallholder farmers are significant beneficiaries of AgDevCo’s investments is a specific goal. The development of a new gender strategy will underpin these standards, providing more opportunity to take a gender sensitive look at who benefits, who doesn’t and why, and consider lessons around the wider social and political opportunities and risks to inform future design and decision making. The application of ESG standards will be monitored through annual reviews and through the independent evaluation.
Management and oversight

DFID oversight happens at 2 levels.

Corporate Level - ARD manages the corporate strategic relationship with AgDevCo on behalf of Africa Division. The SRO is the Wealth Creation Team Leader in ARD. The lead advisor in ARD meets regularly with AgDevCo CEO to ensure close supervision of the company scale up. ARD can also attend AgDevCo Board meetings and AGMs as observer.

ARD convenes a programme steering group which meets quarterly made up of representatives from all DFID contributing departments. The steering group:
- provides oversight on the overall programme
- discusses AgDevCo funding requests and reports
- builds a coordinated and more strategic picture of investments implemented through different funding streams
- discusses input from independent evaluators
- discusses any other matter of strategic importance.

Country Level - Country Offices maintain regular contacts with AgDevCo country teams as part of programme oversight and to provide strategic guidance to portfolio development incountry. Each Country Office has an SRO, the lead adviser, for their specific part of the programme.

A national level Steering Committtee meets regularly in all countries in which AgDevCo operates to:
- provide oversight for all AgDevCo’s investments (irrespective of the funding stream)
- ensure coordination between AgDevCo investments and relevant sector wide initiatives in-country.

Management of Re-deployable Capital

As explained previously, it is expected that over the years AgDevCo will recover part of the invested capital as investments reach financial close and commercial investment is brought in. As a non-profit-sharing organisation AgDevCo will re-deploy the capital recovered for similar investments and management costs during the course of the programme. It is not foreseen that funds covered by this BC will be returned to DFID but redeployed by AgDevCo. This reflects the fact that funding approved in 2013 and in this business scale supports AgDevCo to expand and prove its business model at scale. As DFID thinking on Development Capital Investment (DCI) evolves and AgDevCo structures consolidate, investing DCI in AgDevCo either directly or through another vehicle will be considered.

Monitoring

AgDevCo and DFID have developed a Logical Framework incorporating all streams of DFID investment (PSD, ARD and Country Offices) with nested logframes for each Country.

The LogFrame will form the basis for internal monitoring and evaluation. AgDevCo will provide quarterly narrative reports by Country, and a yearly summary of progress made against DFID logframe indicators with related narrative. At a minimum all appropriate indicators will be disaggregated by sex, with further variables considered (age, ethnicity etc) in the development of the M&E design. A coordinated annual review will take place every year in May with all DFID offices. The EMU will undertake two annual reviews, the first in 2016, and every year they will provide a quality assurance role on AgDevCo’s annual reports. Beneficiary feedback will be sought as part of the annual review process.

Independent Evaluation Research and Dissemination component

Abt Associates have been appointed as the independent Evaluation Management Unit (EMU) to work alongside AgDevCo and DFID. They were appointed through DFID’s Global Evaluation Framework Agreement (GEFA), with SofS approval in June 2014. ARD will contribute up to £1.7 milion (equal to 3.4% of 2013 scale up funding) from its RDEL budget for the Independent Evaluation, which is delivered through a separate contract.

An evaluability assessment has been conducted to examine the feasibility of the evaluation, potential evaluation questions and potential approaches, and the EMU has recently submitted their final design report designed in consultation with AgDevCo. An internal reference group has been convened including the lead advisers and evaluation advisers in each country office (including Mozambique) and led by ARD. Two independent peer reviewers are being contracted to support this process.

The evaluation design developed by Abt is currently being reviewed by SEQAS, the internal evaluation reference group and the independent peer reviewers.

The scope of the evaluation includes all investments made under this funding proposal, and may be extended to include large-scale infrastructure investments. There will be nine in-depth studies, of which four will be quantitive and qualitative assessments, and five will be case studies.

The purpose of the evaluation is to:
- Generate solid evidence and learning on stimulating private sector investment in agriculture and its poverty reduction and developmental benefits, including understanding how change happens, in what circumstances, who experiences changes and how.
- Test untested assumptions and change processes, mainly relating to the interaction between various investment typologies and the regional innovation investments
- Ensure accountability, demonstrating how funds have been spent and ensuring value for money.

AgDevCo’s theory of change underpins the evaluation questions, which are grouped into the following four areas:
  - Catalytic fund model: how sustainable and effective is the catalytic fund model? Does it generate additional investment that would otherwise not have been made?
  - Regional investments: what are the links between SME catalytic funds and regional investment funds in particular, what are the additional benefits generated by regional innovation investments for SMEs and their complementarity. The interaction between national and regional investments will also be examined.
  - Impact: what are the impacts of the investments (positive and negative) on the various stakeholders involved (farmers, investors, employees, smallholders, with specific attention to disaggregation and analysis of data by sex)? Are there discernible poverty impacts?
  - Conditions for success: what are the conditions for success when making agricultural investments in Africa? Why are some investments more successful than others? These questions will address issues such as land tenure, risk bearing, support provided, investment terms, and sectors/locations/products, job creation and poverty reduction potential, gender differences especially with regard to productivity and gender based constraints, barriers to women’s participation, management of social and environmental impact risks.

Evaluation approach
A single overall evaluation matrix has been developed for the project defining the evaluation questions and methodological approach. However, the EMU is working with DFID and other country partners to tailor its approach to each national context.

The impact of the catalytic fund investments will be measured using a longitudinal case study approach. This approach uses a mixture of qualititative and quantitative data periodically gathered from AgDevCo investments and tracks their additionality and development impact over the course of the programme. Comparisons would then be made between investments and also between these and commercial investments to understand the impact of the programme on individual investees and the broader sector, and the necessary conditions for success.

The effectiveness and sustainability of both the the catalytic fund model and of regional innovation investments will be evaluated through analysis of financial investment and enterprise performance.

The evaluation will run concurrently to the programme to ensure lesson learning can immediately inform implementation. This will also ensure that baselines are established in order enable pre and post-intervention comparison.

A strategic communications matrix has been developed as part of the evaluation, design, and will evolve throughout the evaluation to ensure that ground-breaking evidence are key evaluation products are disseminated to stakeholdrs using a variety of channels.

ARD ensured VfM by using a competitive process for procure the EMU.

Risk Assessment
AgDevCo mantains a comprehensive risk register which is mornitor reguraly by ARD. This investment is considered a medium-high risk as follows:

	Risk	Probability	Impact	Mitigation Strategy
1.	Regional macro-economic stability is not sustained	M	H	Support to overall macro economic stability through DFID and other donor programmes
2.	Poor policy and regulatory environment deters investment in agriculture infrastructure and agribusiness	M	H	Criteria for selection of AgDevCo investments include countries where business climate is sufficiently well developed to attract private sector investment in agriculture.
3.	Fluctuating political support and strong vested interests hinders commercial investments	L	M	AgDevCo continues to establish and maintain good relations with local counterparts testing their support and locking it in where it exists. Ongoing policy influence by DFID country offices and other donors in-country.
4	Non Tariff Barriers obstruct cross border trade flows, affecting levels and reliability of throughput for regional agro-processing investment	M	M	Criteria for selection of AgDevCo regional investment include an analysis of relevant costs of tariff and non-tariff barriers. Coordination with other DFID programs specifically targeting NTBs.
5.	Fees charged for use of improved infrastructure are unaffordable by the poor	L	H	AgDevCo projects are structured to be financially viable, which necessitates the price of services to be pitched at an affordable level to its customer base which are smallholder farmers.
6.	DFID money is used for projects which would be developed by private sector without any public sector involvement	L	L	AgDevCo’s investment framework requires additionality.
7.	Investee failure to achieve development impact results	M	H	AgDevCo’s investment policies and processes will apply impact, eligibility and evaluation criteria robustly and will ensure investees have the competences to implement proposals; and AgDevCo will monitor, manage and report quarterly on investee risk.
8	Inability to track poverty impact within the life of the program.	M	H	The EMU design report has made AgDevCo’s theory of change and ultimate goal of poverty reduction an integral part of the whole evaluation.
9	Environment Risks	L	H	AgDevCo adheres to IFC environmental impact standards and requires all investees to adopt environmental best practice and act in compliance with all applicable local and international laws.
10	Social impact risk	L	H	AgDevCo adheres to IFC social impact standards and complies with World bank principles where community engagement relating to land issues is concerned. Agdevco requires all investees to adopt best practice in social impact assessment. AgDevCo will analyse potential winners and losers and develop appropriate risk mitigation options.
11	Inability to discern winners and losers by sex and incorporate gender analysis in project development.	L	H	AgDevCo disaggregates all beneficiaries’ results by sex and has agereed an aspirational target of 50% of development benefits accruing to women. Analysis of women’s economic empowerment will be further facilitated by having a gender strategy to guide good practice in due course.
12	Corporate governance risks	L	H	AgDevCo is committed to responsible investment through private sector development, conducting commercial and legal due diligence for all new investments and requiring all investees to adopt environmental, social and governance best practice, and to act in compliance with all applicable local and international laws.
13	Private sector and DFI investment in AgDevCo projects does not materialise.	M	H	AgDevCo’s business model identifies investments that will become commercially viable and attractive. AgDevCo’s retains expertise in identifying and developing bankable projects.
14	Climate change undermines investments in production	M	H	AgDevCo considers climate risks as part of their investment assessment process, explores and adopts best practice in efficienct natural resource use and climate smart agricultural techniques.

Risk Matrix Summary

		Impact
Probability		High	Medium	Low
	H
	M	[1] [2] [7] [8] [13] [14]	[4]
	L	[5] [9] [10] [11] [12]	[3]	[6]

#### Annex 1 – Evidence underpinning the intervention

SMEs Catalytic Funding - Inputs to Outputs
Catalytic funding targeting agriculture SMEs through a combination of debt and equity and hands on technical assistance is an innovative model and systematic evidence about its impact is not yet available. For the first time, the independent evaluation and research component will systematically test the effectiveness of this model in multiple countries including Ghana, Malawi, Zambia, Tanzania and Mozambique.

AgDevCo’s own experience to date provides anecdotal support. Of Africa Division resources for AgDevCo approved in 2013, $8.6m had been disbursed by the time of the 2014 Annual Review. By December 2013, just six months after approval, investments made with these funds had delivered 143 jobs (35% women), engaged 2,900 smallholder farmers (49% women), and benefitted 13,600 people.

The independently conducted Annual Review 2014 of AgDevCo scale up showed that in the first 6 months AgDevCo had exceeded its targets achieving an A+ score and benefiting over 13,600 smallholder farmers’ households and directly engaging 2,959 smallholders, 49% of whom were women. The Review noted that the agronomic expertise and technical assesstance provided by AgDevCo’s business model was an important part of its additionality.

SMEs Catalytic Funding - Outputs to Outcomes
There is consensus that increasing SMEs’ and smallholders’ access to markets, finance and support services which increase their managerial and technical capacity will increase their sustainability and commercial viability (World Bank 2013 Agribusiness Report, World Bank World Development Report 2008, Pinstrup-Andersen and Shimokaya, 2006, Birkhaeuser et al., 1991; Feder et al., 2004).

There is anecdotal evidence from specific AgDevCo investments in Mozambique that smallholders do increase production and income when linked to SMEs providing a package of credit, technical assistance and guaranteed markets. For example AgDevCo monitoring data show that after investment in ECA (Empresa de Commarcilaizazao Agricola), ECA established an outgrower scheme engaging 1,000 smallholders in its first year. They received a package of input on credit and ECA achieved a 100% repayment rate at the end of the season with farmers typically doubling their production and obtaining a 100% cash income increase. ECA doubled its outgrowers base to 2,000 in its second season, as it secured further commercial contracts through AgDevCo brokering of demand partnerships.

There is some evidence to suggest that boosting the productivity of women, which lags behind that of men in African agriculture, through increasing their capabilities and opportunities, could have a positive impact on agricultural growth, poverty reduction and women’s empowerment (World Bank, 2014). This needs to be further researched.

This programme and its proposed independent evaluation will test the validity of this model and its assumptions on a much larger scale, in conjuction with AgDevCos operational delivery processes. Furthermore, there is no systematic evidence of how which type of investments and investment modalities maximize benefits for smallholders and women in particular, and limited evidence as to the long term sustainability of these benefits. A systematic evaluation of multiple typologies of SMEs investments in various countries will generate ground-breaking evidence in this respect.

Regional Innovation Investments - Inputs to Outputs
There is evidence - although non sector-specific - that Development Finance Institutions (DFIs) create financial additionality, particularly in low-income countries and in less commercially attractive sectors by supplying finance, mitigating risk, and leveraging additional finance (ODI, 2013 Review of DFIs including PIDG). There is also consensus that to increase developmental impact, DFIs could do more to increase supply chain linkages with SMEs (Ib.).

A recent retrospective study of CDC investments in agri-business (Tyler and Dixie, 2012) assessed 179 investments in 32 countries between 1948 and 2000 (122 investments in Sub Saharan Africa and 57 in South East Asia and Pacific) against the two main criteria of development impact (jobs and income) and equity return.

The study states that “while only one fifth of projects were rated complete failures, one third of equity investments generated at least moderately attractive internal rates of return, and overall about 55 percent resulted in financially viable projects (i.e. financially self-sustaining)”.

The same study highlights the importance of rigorous investment project development and patient capital to ensure the long term viability of investments.

An IFC meta-evaluation[18] (33 evaluations over a period from 2000-2011) of DFI interventions’ impact on job creation and poverty found that activities aimed at improving access to finance, infrastructure, investment climate and employment skills had the most positive effect on job creation, with training apparently particularly beneficial for women and disadvantaged youth.
[18] Michelitsch, R., Paniagua, G., and A. Denisova (2013), Meta-evaluation on job creation effects of private sector interventions: Summary of preliminary findings. Assessing Private Sector Contributions to Job Creation: IFC Open Source Study. Washington DC: International Finance Corporation IN Massa, I, 2013. A brief review of the role of development finance institutions in promoting jobs and productivity change. ODI.

Such evidence will be tested in the specific context of developing regional supply chains to feed an emergent urban market through the independent evaluation and research component.

Regional Innovation Investments - Outputs to Outcomes
The evidence outlined above (Tyler and Dixie, 2012) suggests that well-structured commercially sound investments in agri-business can attract private sector financing, achieve positive returns and generate developmental benefits in Africa. The study finds that “the majority of projects in both Asia and Africa ended up being sustainable businesses that delivered broadly the number of jobs and level of turnover that had initially been anticipated.”

There is however no systematic evidence of the impact of medium to large agri-business investments on regional production in multiple countries, or of what are the best ways to ensure that such investments allow SMEs and smallholders, especially women, to participate in higher-value commercial value chains. The independent evaluation and research component will focus on those two aspects generating and disseminating ground-breaking new evidence.

Synergies between in Country SMEs Catalytic Funds and Regional Innovation Investment Fund
There is consensus that lack of market access for agriculture SMEs prevents their sustainability (WB WDR 2008 and 2013; Pinstrup-Andersen and Shimokaya 2006) and that volatile and fragmented markets which prevent a guaranteed throughput of agriculture production are a binding constraint to agri-business investment (WB Africa Agribusiness Report 2013).

Simultaneous and coordinated investment in regional agro-processing facilities and in country SMEs which connect smallholder farmers is however an innovative approach. The independent evaluation and research component will rigorously develop and test assumptions about the effectiveness of this approach in multiple countries and it will generate and disseminate learning for future interventions.

Outcome to Impact
There is consistent evidence of the link between investment in agriculture and economic growth. The DFID Agriculture and Growth Evidence Paper indicates that evidence from growth accounting studies suggests that productivity growth in agriculture has been a source of growth in developing countries. Studies on agriculture’s economic multipliers show that farming has significant growth linkages with other sectors. Studies analysing determinants of economic growth using cross-sectional and panel data suggest that growth in agriculture will be associated with growth in the rest of the economy in low-income countries. Where direction of influence is examined in this relationship, the evidence suggests it is from agriculture to the rest of the economy. (DFID Agriculture and Growth Evidence Paper, 2014)

There is also significant evidence suggesting that the poorest stand to benefit significantly more from agricultural growth than from growth in other sectors of the economy (World Bank, WDR 2008; DFID Agriculture and Growth Evidence Paper, 2014)

The independent evaluation and research component of this programme will therefore not focus on these aspects, although it will help to increase our understanding of how – and under what circumstances – private sector investment in agriculture can maximise impact on economic growth and poverty reduction.

#### Annex 2 – Cost-Benefit Analysis

Costs of Additional Funding Approved in 2013

This cost benefit analysis (CBA) is based on the latest expectations of the project pipeline. Analysis is conducted using a portfolio of investments of varying size (SME, medium and large) across 5 African countries (Ghana, Malawi, Zambia, Mozambique, and Tanzania).

The methodology of the CBA has been refined from past calculations to reflect more directly the benefits to smallholders and employees, which underpin the logic for DFID intervention.

In light of revisions to the expected project pipeline since the submission seeking approval for additional funding to AgDevCo in 2013, some changes have been made to the underlying assumptions informing expected results. The assumptions behind the model are based largely on AgDevCo’s existing experience from projects, including AgDevCo’s early stage Public Private Partnerships (PPP) projects in Ghana, the existing Sao Hill and Sasumua businesses in Tanzania, and existing Phoenix Seeds business in Mozambique. AgDevCo has carried out in-depth scoping studies to identify potential investments for the Catalytic Funds in Northern Ghana and Malawi.

Total Africa Division resource costs approved in the 2013 submission and approved Tanzania Blended Partnerships funding, along with amounts outstanding, are as follows:

DFID Funding Source	Funds (£)	Outstanding (£)
Africa Regional Department	20,000,000	10,008,311
Ghana Country Office	10,000,000	7,627,294
Malawi Country Office	10,000,000	6,904,029
Zambia Country Office	10,000,000	5,037,445
Tanzania BP	15,580,000	5,186,572
Total Funding through AgDevCo	65,580,000	34,763,651
Additional funding for Independent Evaluation (through separate contract) – ARD Funding	Up to 2,500,000	1,700,000

All DFID funds are expected to be disbursed to AgDevCo by 2018. The tentative disbursement timetable for the outstanding amount is as follows:

Funding Profile (£)	2015	2016	2017	2018	Total
Africa Regional Dep’t	4,303,720	2,849,633	2,854,960		10,008,311
Ghana Country Office	1,366,223	2,302,544	2,297,544	1,660,982	7,627,294
Malawi Country Office	4,452,890	1,197,475	835,777	417,888	6,904,029
Zambia Country Office	2,265,607	1,539,110	821,818	410,909	5,037,445
Tanzania BP	3,473,862	570,903	570,903	570,903	5,186,572
Total Funding	15,862,302	8,457,665	7,381,002	3,060,683	34,763,651

Including funds from Africa division that have already been disbursed, this will represent 84.7% of the total AgDevCo funding from all donors of £77.4m already committed with impact targets over the 5-year time period 2013 - 2018[19]. The outstanding £34.8m represents 44.8%.
[19] Small foundation funding £352,564, PIDG Funding Tranche 1 (PSD & ADA) £11m, DFID BP Tanzania £15.58m, DFID Mozambique £500,000.

From investments made in 2015 and 2016, AgDevCo is expected to attract an additional £46.9m of DFI investment and £15.7m of private investment by 2024 to the agribusinesses supported. This additional investment will support the scale-up of businesses and the generation of jobs, forming part of the anticipated benefits. This gives a total of over £62.6m of additional private capital invested[20].

These funds will be used to fund a portfolio of large, medium and SME projects. Estimates of impact are based on the assumption that AgDevCo will invest in 21 projects, all of which would have been initiated by 2016, based on latest expectations of the project pipeline as follows:

Project Portfolio	2015	2016	Total
Large Projects	1	-	1
Medium Projects	4	1	5
SME Projects	10	5	15
Total	15	6	21

The model used to derive estimated results involves a number of assumptions. The following table shows the key estimations by size of investment. These are based on AgDevCo experience from projects in 3 major programme countries: Ghana, Mozambique and Tanzania.

	Large Projects	Medium Projects	SME Projects[21]
Total AgDevCo Investment per Project($)	4,000,000	2,000,000	500,000
Total Capital Cost per Project ($)	30,000,000	15,000,000	793,103
Private Capital Leverage Ratio	7.5	7.5	1.6

New Direct jobs created per project	600	300	48
Smallholders reached per project	6,000	3,000	7,752
Increase in number of hectares - Ha	3,000	1,500	117
Increase in Processing Throughput/Capacity - MT	10,000	5,000	776
[21] This is based on a weighted average of the five different SME investment type as per pipeline at time of submission, and is therefore subject to revision based on any change in the pipeline/actual investments made.

The following general estimations are made across the portfolio:

General Development Impact
Baseline Income for employees (Annual $)	472
Increase in income for employees	300%
Base income for smallholders	472
Increase in income for smallholders	95%

Baseline income for employees is based on the average GNI across Mozambique, Malawi, and Tanzania[22]. Employee increase in income is calculated assuming that employees are paid minimum wage from the time the investment is made and employment begins. Smallholder increase in income is calculated assuming an increase in yield through the application of inputs, technical assistance, access to irrigation and improved seeds. This income increase again occurs at the time of project investment.
[22] Source: www.UN.org

A key assumption and uncertainty is the number of investments that will reach successful completion. The model estimates that 25% of projects will fail and not reach exit stage. The model assumes however that these projects still deliver 20% of the total development benefits. These assumptions are based on AgDevCo judgement. Tyler and Dixie’s paper on CDC found that 20% of CDC investments failed. AgDevCo’s estimation of 25% is therefore conservative in comparison to this. A sensitivity analysis was conducted below to estimate the impact of relaxing this assumption.

An implicit assumption of this analysis is that markets in target countries are reasonably competitive and consequently that the market prices of goods and factors of production such as labour are not under- or over-valued.

Despite assumptions being based on the best data available, the context-specific evidence underlying many of them is not extensive. As already outlined, the AgDevCo business model has been proven over the past three years mainly in the context of Mozambique and to a lesser extent Ghana and Tanzania. It proved able to deliver increases in agriculture business revenues, better market linkages, jobs and income uplift for smallholders. As AgDevCo is a relatively young organisation and given the length of its intervention cycle however, it has not yet fulfilled its business model to the point where commercial finance can fully replace patient capital investment. Robust monitoring and evaluation of the AgDevCo programme including an independent evaluation will build up the evidence base and test the assumptions linking input to outcome and outcome to impact.

Expected Benefits

In comparison to the counterfactual (withdraw funding) the expected outcome of maintaining funding is to increase the incomes of both direct firm employees and smallholder farmers reached by the program through investments developed by AgDevCo and co-invested with DFIs and the private sector. This will increase investment in agribusinesses and agricultural infrastructure, and increase cross-border trade in targeted countries. An integral part of the AgDevCo model however is that AgDevCo investments help create missing markets and develop missing market linkages that previously did not exist. By making agriculture an attractive investment for private capital the benefits are expected to be sustainable and continue long after AgDevCo has exited. Therefore, this CBA considers costs and benefits for 10 years through to 2024.

At output level the following benefits are expected by 2024:

OUTPUT RESULTS BY 2024	Attributable to Total AgDevCo Funds (£77.4m)	Attributable to Outstanding Africa Division Funding (£34.8m) [23]
Increase in agribusiness turnover (GBP)	91,448,718	33,128,205
Increase in hectares of irrigated land (Ha)	38,480	8,940
Increase in processing capacity (MT)	147,500	42,500
Direct jobs created (50% men, 50% women)	8,423	2,396
Smallholders reached (50% men, 50% women)	1,375,952	231,760
Total direct beneficiaries	1,414,699	1,077,116
[23] Note that estimates are based on the expected future project pipeline, which does not have identical characteristics to the existing project portfolio. Therefore results attributable to the outstanding £34.8m are not a constant proportion of the results attributable to the full £77.4m.

At outcome level the following quantifiable benefits are expected by 2024:

OUTCOME RESULTS BY 2024	Total AgDevCo Funds (£77.4m)	Attributable to Outstanding Africa Division Funding (£34.8m)
Increase in employee income (GBP)	7,645,674	16,862,745
Increase in smallholders income (GBP)	24,934,562	101,259,630
Total increase in direct beneficiary incomes (GBP)	32,580,236	118,122,375

AgDevCo have strict operating procedures in place[24], which stipulate investments to not only produce financial returns but are additional and result in positive developmental impacts. AgDevCo Investment Policy and Procedures state that project teams must assess and, where appropriate enhance, the development impact of proposals. A full assessment and estimation of the development impact of each investment must also be carried out. Social, environmental and governance risks must be identified and mitigated and performance indicators and milestone targets set.
[24] AgDevCo conducts commercial and legal due diligence for all new investments and requires all investees to adopt environmental, social and governance best practice as well as to comply with all applicable local and international laws. DFID expects that the gender strategy to be developed in 2015 will include an analysis of specific opportunities for women economic empowerment as part of the investment appraisal process.

Unquantifiable Benefits

There will also be an indirect increase in income for households not directly connected to AgDevCo businesses, generated through spill over investments along the same value chains in which AgDevCo will invest. Indirect increase in income is expected to arise through improved market linkages and is calculated as a multiple (x3) of the increase in AgDevCo-supported business turnover[25]. Total indirect increase in income is estimated to be over £274m by 2024, of which £99m is attributable to the additional £34.8m. Whist this benefit has been estimated, because there is a greater degree of uncertainty around it, it was not included in the quantified cost-benefit analysis.
[25] This indirect multiple is referred to in various papers including DFID (2005) Role of Agriculture in Growth and Poverty Reduction and IFPRI (2010) Agricultural Growth in Rwanda

An important additional benefit to those listed above comes from the form of finance that AgDevCo provides. Through the provision of debt and equity, AgDevCo recoups a proportion of the funds it invests. This provides a valuable demonstration effect, showing other potential investors that attractive rates of return are achievable through investment in agricultural firms with strong links to smallholders. It is anticipated that there will be many copy-cat investments following AgDevCo-type models if the approach is shown to be positive, yielding similar benefits.

The return on capital achieved by AgDevCo will be reinvested in future projects and used to cover corporate costs. It is expected that by 2021, total redeployed investment funds from returns on all AgDevCo investments will be £46.7m. This is 61% of the total investment funds received by AgDevCo. Additional income from re-invested returns by 2021 will be £11.5m, a further 15% of the initial funds provided to AgDevCo.

Other important positive impacts not quantified include the contribution AgDevCo will make to local and national poverty reduction, improved nutrition and food security in sub-Saharan Africa. An indication of this can be seen by tracking increases in agricultural growth rates in countries in which AgDevCo operates and changes in the national population living on less than $1.25 per day. By concentrating on SMEs and smallholders the programme is also likely to have positive benefits in terms of income distribution and equitable growth. The evaluation will consider how some of these indicators might be captured and disaggregated appropriaptely (e.g. by sex) for further analysis[26].
[26] The independent evaluation will generate learning and knowledge about the impact of similar interventions. As these benefits are broadly outside the project and they are not quantified in this CBA we have excluded the independent evaluation’s costs from the CBA costs too.

As a result of the investment made by AgDevCo, and expected additional investments made by DFIs and the private sector, investees are expected to experience significant increases in turnover and profits. These increases will contribute to increased spending in the local economy, boosting demand for other goods and services. The benefits from increased turnover is not included in the formal cost-benefit analysis as it does not necessarily accrue to the target population to the same extent as the direct increases in incomes do.

Economies of scale[27] will be achieved within each new fund set up (in Country SMEs and RII Fund for any future investment by DFID or others). Benefits also accrue for other DFID Country Offices who will in future be able to access this framework for investment in agriculture in their country of operation. Reduction in transaction costs and improved coordination will be achieved through a single oversight mechanism for all DFID investment in AgDevCo. Coordinated regional and national investment provides benefits in terms of linking SMEs and smallholders to infrastructure corridors and agro-processing plants, enabling them to access higher-value chain. This will be achieved either through investments along same national and regional value chains or through complementary investments in different operations of the same business.
[27] For example for SME Catalytic Funds, fund management costs are set to 6% per annum of the first $10m, 4% per annum for the next $10m and then 2% per annum for any amount over $20m.

Finally, the strong independent evaluation, research and dissemination component offers substantial benefits in terms of institutional learning and advancing the development community’s knowledge on how to maximise the developmental benefits of private sector investment in agriculture, especially for smallholders and women.

Balance of Costs and Benefits

The table below shows the balance of costs and benefits from the outstanding amount of approved Africa Division funding to AgDevCo (£34.8m) through to 2024.

BALANCE OF COSTS & BENEFITS (2015 - 2024) UNDISBURSED FUNDING from AFRICA DIVISION
Costs (GBP)
Total Costs to DFID	34,763,652
Benefits (GBP)
Direct Increase in Employee Income	16,862,745
Direct Increase in Smallholders Income	101,259,630
Total Benefits	118,122,375

Nominal Net Benefits	83,358,723
NPV	37,312,740

The total financial benefits are defined as the increases in employees’ and smallholders’ income. Total financial benefits generated through the additional £34.8m from ARD, DFID Ghana, DFID Malawi, DFID Zambia, and Tanzania Blended Partnerships in terms of direct increases in income amount to approximately £118m by 2024[28]. Accounting for the direct costs to DFID[29], this has a net present value (NPV) of £37m when discounted over the period using a 10% discount rate[30]. The internal rate of return (IRR) is 33% and the benefit/cost ratio is 2.17. In addition to this there are likely to be further unquantifiable benefits which will arise from the programme including poverty reduction and increased food security.
[28] Indirect increases in income have not been included in this total.
[29] It is assumed that agribusinesses invested in do not need to make additional capital investments themselves in order to attract AgDevCo investment.
[30] A 10% discount rate is a rough estimate of the economic opportunity cost of capital for the 5 countries included in the analysis and is in-line with DFID policy

These benefits are attributable to both the investment made by AgDevCo (using Africa Division funding) and additional capital invested by DFIs and private investors in the firms supported by AgDevCo. However, the monetary value of the (returnable capital) DFI and private sector investments has not been included in the CBA on the grounds that they should be profitable and so not a net cost.  That is, we assume that the expected returns to DFI and private sector investments are greater than the costs (otherwise the investments would not be profitable and so would not be made); therefore including both the present value of the investments in the costs and the present value of the expected financial returns to this additional investment in the benefits would increase the calculated NPV. To simplify the calculation, these returnable capital investments are not included in the above table.

This implies that investment in AgDevCo does make economic sense, even without accounting for the significant unquantifiable benefits. Assuming that many of the quantifiable benefits are incremental and that AgDevCo operating procedures ensure that investments are additional (i.e. do not crowd out other private sector investment) and have a strong developmental impact, the project is likely to also show significant positive socio-economic net benefits.

Assuming that many of the quantifiable benefits are incremental and that AgDevCo operating procedures ensure that investments are additional (i.e. do not crowd out other private sector investment) and have a strong developmental impact, the project is likely to also show significant positive socio-economic net benefits.

Sensitivity analysis

Slight changes in the estimations used can often have large impacts on the expected benefits. Whilst the model has been designed to be conservative and represent the true costs and risks faced by AgDevCo, there is a lack of strong, context-specific evidence to back up some of the assumptions. Furthermore, there will always be uncertainty regarding future events and agriculture is susceptible to exogenous shocks such as droughts or changes in government policy. Key assumptions that underpin the above analysis must therefore be modified to test the robustness of the results obtained.

The following parameters were adjusted simultaneously to represent a substantially less positive outcome:

- Percentage of projects reaching exit and developmental impact of these - Increase failure rate of investments to 50% with these having 0% developmental benefits.
- Percentage increase in income for direct beneficiaries - Reduce income gain for employees and smallholders by a quarter to 113% and 225% respectively.
- Number of direct jobs created and smallholders reached - Reduce increase in number of direct jobs created and smallholders reached by 25% for all investment sizes.

Adjusting these 3 parameters affected outcomes by 2024 in the following way:

SENSITIVITY ANALYSIS	OUTCOMES
	Financial Benefits (Total Increase in Income, £)[31]	Total Direct Beneficiaries
Baseline Outcome	36,739,629	1,077,116
Outcome after changing assumptions	69,265,185	795,779
Percentage Change	47%	26%
[31] In present value terms, discounted at a 10% discount rate.

These changes in assumptions represent a substantial degradation in expected benefits. Nominal net benefits would fall to £28m, with a NPV of £4.8m.

Taking the substantial unquantified benefits identified above into account (including increases in business turnover, the demonstration effect of investments, contributions to improved nutrition and food security, improvements in the evidence base on the effectiveness of agribusiness interventions, and the benefits from subsequent rounds of investments using recouped capital), would show a greater net positive developmental benefit even under this scenario.

Despite the limits identified -primarily that the nature of the intervention means that the analysis is based on a typical hypothetical portfolio of investments rather than on the actual investments that will be made- the analysis above nevertheless gives a good indication of the financial and developmental benefits that investing in AgDevCo will bring and their robustness to potential changes in assumptions.

#### Annex 3 – Value for Money

Economy
Both indicators of economy would be reported from the first Annual Review and throughout programme implementation.

1. Fund management cost ratio (the ratio of fund management costs to total investment funds).
2. Administrative cost ratio (the ratio of fund management and overheads to total investment funds).

Both of these should be compared to cost ratios for the AECF and CDC, which are expected to have the most similar cost structures to AgDevCo. Interpretation of this indicator should be cognisant of the fact that AgDevCo’s fund management costs include a significant amount of business development support provided by the fund managers in order to develop viable and impactful businesses. Newly started investments should be expected to incur extra early-stage costs, making them more expensive than more mature companies.

Efficiency
The following VfM indicator of efficiency will be used:

Leverage ratio (The ratio of private and DFI finance committed to AgDevCo investment)

Under AgDevCo’s business model, private sector and DFI investment is not expected to be leveraged during the first years of new investments. This indicator could be meaningfully interpreted for investments over 5 years old. Including projects in the existing portfolio (funded under previously approved Africa Division funding), information would be available from 2017.

Effectiveness
Effectiveness indicators would be reported from the 2016 Annual Review.

Smallholder engagement rate, disaggregated by sex (Ratio of total committed investment to number of smallholders engaged)

Expected results are based on an indicative portfolio if hypothetical large, medium and small investments. In practice, at the portfolio level the ratio of smallholders reached to funds committed will depend on the sequencing and types of investments made, and how mature they are. By 2016, all investments are expected to have been committed. By 2018, the model predicts that 140,428 smallholders (50% women/50% men) will have been engaged from outstanding £34.8m funding.

    1. Job creation rate, disaggregated by sex (Ratio of total committed investment to number of jobs created)

As with the smallholder engagement rate, direct jobs created will be contingent on the accuracy of the expected project pipeline. By 2018, it is expected that 8,490 (50% Women/ 50%Men) jobs will have been created from outstanding £34.8m funding.

Business failure rate (Number of investees ceased trading as a proportion of enterprises financed)

Expected results are based on the assumption that 25% of projects will fail and not reach exit stage, which is deemed to be conservative. A failure rate in excess of 25% at any point should trigger a reassessment of the extent to which this assumption remains valid.