Annual Review - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Reducing Maternal and Neonatal Deaths in Kenya
Programme Value: £79.8m		Review Date: November 2015
Programme Code: 202549	Start Date: 14/11/2013	End Date: 30/06/2019

Summary of Programme Performance
Year	2013/2014	2014/2015
Programme Score	B	A
Risk Rating	Medium	Medium

Summary of progress and lessons learnt

There has been good progress since the 2014 Annual Review; implementation has accelerated and the programme is broadly now on track to meet key output milestones.

- Liverpool School of Tropical Medicine (LSTM) has scaled up training in Emergency Obstetric and Newborn Care (EmONC) and is back on track after 18 months of implementation.
- Options, which was contracted in January 2015 to provide health systems strengthening support in Bungoma County and to manage the County Innovation Challenge Fund (CICF), has made impressive progress. A health systems strengthening (HSS) needs assessment has been completed and Options is providing HSS support in Bungoma. The CICF has launched two rounds of calls for proposals, receiving around 500 applications; seven projects are being funded through Round 1 and an estimated 10 will be funded through Round 2.
- UNICEF is implementing and testing some interesting and innovative interventions, including Kangaroo Mother Care for pre-term babies, new approaches to support more culturally acceptable delivery positions such as a birthing cushion that allows mothers to squat during delivery, and the uterine balloon tamponade, a low-cost but effective way to prevent women dying from post-partum haemorrhage. UNOPS, which has been contracted by UNICEF to manage facility renovation and climate change upgrading in the five UNICEF-supported counties, has moved quickly to establish a team, conduct assessments, and develop detailed plans and budgets.

However key issues include:

- Slow progress in implementation of some planned activities managed by UNICEF. UNICEF has experienced considerable delays in taking forward some activities, e.g. support to counties for human resources for health, redesign of the demand-side financing component and implementation of nomadic clinics. Some of this is due to internal systems, some to delays in recruiting staff and sub-contracting partners, and some due to lack of capacity.
- Revised programme scope. The scope has expanded to include additional funding of £4.5m to support climate change interventions at health facilities providing maternal health care across all six programme counties. Since this programme was designed, Save the Children has started implementing a maternal and newborn health (MNH) programme in three sub-counties in Bungoma; to avoid duplication, Options is focusing some areas of support on the other six sub-counties.
- Achievement of results. At current rates of progress, the programme is unlikely to achieve the target for additional attributable skilled birth attendance of 95,000 by 2018; a target of around 60,000 may be more feasible and UNICEF is currently discussing revised numbers.
- UNICEF has provided important inputs to enhance service delivery, but limited support for health systems strengthening. UNICEF inputs, specifically procurement of equipment and supplies, have been critical to ensure that health facilities can deliver quality MNH care. UNICEF has sub-contracted UNOPS to implement renovations of health facilities, to ensure that facilities have the capacity to deliver quality care. However, UNICEF support for other areas of health systems strengthening is less strategic. There is no clear plan for providing tailored systems strengthening support to each of the five counties or at national level; UNICEF reports that completing these plans by end of January 2016 will be a priority.
- Capacity of county health services to meet increased demand for maternal health care remains a concern. Programme demand creation activities, including support for community units, demand-side financing and incentives, are expected to increase demand for services. However, demand has already increased as a result of the Government of Kenya’s policy on free maternity care, and many health facilities are already experiencing difficulties in meeting existing demand. County budgets are stretched and unlikely to be able to fully address shortages of health workers, equipments and supplies in the short term.
- Better information is required about the effectiveness and cost-effectiveness of community units. The community unit functionality scorecard measures process issues, e.g. meetings held, reports submitted, but there is little rigorous evidence about the effectiveness of community units (UNICEF is planning to conduct a study of effectiveness and cost effectiveness). Despite this, the programme is investing significant funding in training and equipping large numbers of community health volunteers; in addition, the attrition rate of volunteers is reported to be high in areas where they are not well supported or supervised.
- The security situation has deteriorated further. The risk of terrorist attacks remains high and there are increasing incidents of violence in Turkana and West Pokot. This may have an adverse impact on programme activities and costs.
- Integration of DFID’s maternal and newborn health and nutrition programmes. The programme’s results and logframe will need to be modified to reflect the integration of elements of DFID Kenya’s nutrition programme. Key changes proposed are: delivery of high-impact nutrition interventions through health facilities and community health services; and expansion of MNH interventions to two additional arid and semi-arid lands (ASAL) counties currently covered by the nutrition programme (Mandera and Wajir).

Key lessons include:

1. UNICEF has technically competent, committed staff, but lacks in-house capacity for some areas of programme activity, particularly health systems strengthening, and therefore has to recruit external expertise for these. Slow systems and procedures for identifying and sub-contracting expertise have contributed to substantial delays. These delays could have been anticipated and UNICEF should have taken steps to manage them.
2. Counties and health facilities have limited absorptive capacity; county health teams are still adjusting to managing devolution of funds and functions. Health systems support needs to be sequenced carefully to avoid overloading staff and sufficiently flexible to respond to specific county needs.
3. Working in partnership with the private sector, i.e. KPMG, to manage the innovation fund has been an efficient and effective approach.
A. Introduction and Context

Dev Tracker Link to Business Case:	QUEST: 4264533
DevTracker Link to Log frame:	QUEST: 4264580

Outline of the programme

Kenya has one of the highest rates of maternal deaths in the world, at 360 per 100,000 live births (WHO, 2013), and there has been little progress in the last decade. Although deaths in young children have declined, newborn deaths have not (22 per 1,000 live births). High death rates are due to poor access to quality delivery care and EmONC and low use of available services. Health system challenges include shortages of health workers, equipment and supplies, and weak referral systems. Financial, cultural and geographical barriers limit uptake of maternal health services. Devolution of funds and functions to 47 new counties after the 2013 election has presented opportunities to improve maternal health services but also challenges, particularly in counties with limited capacity, poor infrastructure and shortages of staff.

Under the Reducing Maternal and Neonatal Deaths in Kenya programme, the UK is providing support through: LSTM to scale up EmONC training for all maternity care providers (doctors, nurses, midwives and clinical officers) in 32 counties to achieve national coverage; UNICEF in five counties (Homa Bay, Garissa, Kakamega, Nairobi [in two peri-urban sub-counties] and Turkana) and Options in one county (Bungoma) to build local government capacity to plan, manage and deliver quality MNH services, strengthen referral and accountability and increase community demand for and uptake of maternal health care; UNICEF to provide technical assistance for health systems strengthening to the national Ministry of Health (MOH); and Options to manage a County Innovation Challenge Fund (CICF) to support testing and scale up of innovative approaches in all six programme counties. There is also an evaluation component with three retrospective studies planned to assess the impact of the programme.

DFID is providing £75.3m over 5 years: £9.3m for scale up of training; £32.2m for health systems strengthening and demand-side activities in five counties, national health systems strengthening support and overall programme oversight; and £29.3m for health systems strengthening and demand-side activities in Bungoma and the CICF. The remaining £4.1m is allocated to operational research, monitoring, independent review, evaluation and contingency. In 2015, DFID allocated an additional £4.5m to integrate climate change interventions. DFID is also funding separate family planning and nutrition programmes; it is anticipated that the latter will be integrated into the MNH programme in 2016.

The programme is expected to contribute to the achievement of DFID Kenya’s 2011-2015 Operational Plan results, specifically its commitment to provide skilled birth attendance to an additional 15,000 women by 2015, and an additional 95,000 by 2018, and to DFID’s overall Business Plan commitment to support at least 2 million safe deliveries, save the lives of 50,000 women in pregnancy and childbirth, and stop 250,000 newborns from dying. The programme impact is: Reduced maternal and neonatal deaths in Kenya. It is expected to contribute to preventing 1,092 maternal deaths and 3,838 neonatal deaths by 2018. Overall, the programme and the Theory of Change remain relevant.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

There are five outcome indicators. Progress against milestones for 2015 is as follows:

Milestones 2015	Achieved	Comment
Skilled birth attendant rate: / National 65% / Homa Bay 65% / Turkana 35% / Kakamega 60% / Garissa 45% / Bungoma 43% / Nairobi Embakasi See comment / Nairobi Kamunkunji See comment	62% / 61% / 52% / 60% / 38% / 53% / - / -	Data source for progress data Kenya District Health Information System (KDHIS) August 2015. / Milestones achieved in three programme counties (milestones and data reported for Nairobi sub-counties unclear i.e. >100%). Overall trends going in the right direction; nationally, proportion of births attended by a skilled provider increased from 44% in 2008/9 to 62% in 2014 (KDHS).
Milestones 2015	Achieved	Comment
Additional births delivered by a skilled birth attendant: / Additional national: (No milestone) / Additional attributable: / 36,360 programme total (1,365 Bungoma)	See comment / See comment (Bungoma 233)	In 2014, nationally, additional SBA 278,371, of which 13,919 attributed to the programme (of a target of 17,700). / Total national births as of August 2015 627,712; UNICEF notes that additional births delivered by SBA and number attributable to the programme will be reported in December 2015, as annual figures are used. / Milestone unlikely to be achieved.
Milestones 2015	Achieved	Comment
Functioning BEmONC and CEmONC facilities (population coverage and number of facilities):
Nationally BemONC 30%; CEmONC 40% / In each of the 5 UNICEF counties 10 BEmONC; 3 CEmONC / Bungoma 2 BEmONC; 1.5 CEmONC	(i)National data not available / (ii) BEmONC Homa Bay 16; Turkana 18; Garissa 16; Kakamega 23; Nairobi 9; and CEmONC Homa Bay 4; Turkana 2; Garissa 3; Kakamega 4; Nairobi 3 / (iii) Bungoma BEmONC 2; CEmONC 1.5	UNICEF notes national data will not be available until an EmONC survey is done. / Milestones achieved except for BEmONC in Nairobi and CEmONC in Turkana. / Milestones achieved.
Milestones 2015	Achieved	Comment
Caesarean section rate: / National 13% / Homa Bay 5% / Turkana 8% / Kakamega 6% / Garissa 11% / Bungoma 5% / Nairobi Embakasi 12% / Nairobi Kamunkunji 25%	12.9% / 2.8% / 7.1% / 5.7% / 11% / 8% / 13.6% / 19.7%	Data for month of June 2015. / Milestones achieved in three of six programme counties. Higher rates in Nairobi sub-counties explained by presence of referral hospitals.
Milestones 2015	Achieved	Comment
Stillbirth rate: / National 2% / Homa Bay 2% / Turkana 2% / Kakamega 3% / Garissa 2.5% / Bungoma 2.4% / Nairobi Embakasi 2% / Nairobi Kamunkunji 2%	2.9% / 2.7% / 3.7% / 2.1% / 3.3% / 2.64% / 0.65% / 2.3%	Data for month of June 2015. / Milestones achieved in Kakamega and Nairobi (Embakasi sub-county).

The programme will contribute to most expected outcomes, as planned activities will increase demand for and the availability and quality of MNH services, although success is also contingent on county health services being able to ensure that adequate staff and supplies are available. However, the programme is unlikely to achieve the target for additional attributable skilled birth attendance of 95,000 by 2018.

Overall output score and description

The overall programme has been scored A, reflecting considerable progress with some programme components since the last annual review, however this is a weak A reflecting continued slow progress with others.

Table 1: Summary of output performance:
Output	Output Description	Impact Weight (%)	Output Performance
1	Health workers in five provinces (32 counties) have the knowledge and skills to provide quality delivery care	30%	Output moderately did not meet expectation (B)
2	Health systems strengthened to manage and deliver maternal and newborn health services in Homa Bay, Turkana, Kakamega, Garissa, Nairobi and Bungoma counties	50%	Output met expectation (A)
3	Increased demand for maternal health services in Homa Bay, Turkana, Kakamega, Garissa, Nairobi and Bungoma counties	20%	Output moderately did not meet expectation (B)

Key lessons
1. UNICEF has technically competent, committed staff, but lacks in-house capacity for some areas of programme activity, in particular for elements of health systems strengthening. Slow systems and procedures for identifying and sub-contracting expertise have contributed to substantial delays.
2. Counties and health facilities have limited absorptive capacity; health systems support therefore needs to be sequenced carefully to avoid overloading staff.
3. A strategic and systematic approach, based on sound analysis, is important to guide health systems strengthening interventions. Health systems strengthening support also needs to be sufficiently flexible to respond to specific county needs.
4. Using the private sector to manage the innovation fund has been an efficient and effective approach.

The assumption that county health budgets would be able to fully address staff and supplies needs to be monitored. Although most counties are receiving more funding for health, allocation of funding is an issue in some counties, ability to spend in others, and all counties have resource limitations.

Summary of key recommendations for the next year

Action	Timeline	Responsible
Accelerate programme implementation	All contracts in place by December 2015	UNICEF
Review the target for additional attributable deliveries with SBA and, if appropriate, agree a revised target	By end December 2015	UNICEF/DFID
Track systematically whether supply can meet demand for services and plan demand creation activities carefully, using clear criteria for prioritisation	Ongoing	UNICEF/Options
Develop county-specific health system strengthening plans based on systematic analyses	By end January 2016	UNICEF
Identify an additional partner to provide national health systems strengthening support	By end March 2016	DFID
Prioritise support to counties to establish effective HRH information systems including (i) training plans, (ii) plans to ensure newly recruited health workers receive EmONC training, and (iii) plans to ensure effective follow up and mentoring for health workers trained in EmONC	By end March 2016	UNICEF/Options/ / LSTM
Monitor the effectiveness of participant selection and verification procedures for trainings	Ongoing	LSTM
Determine how to measure the combined contribution of each partner to indicator 1.3 (MPDSR)	By end December 2015	UNICEF/Options/ / LSTM/DFID
Redesign the UNICEF demand-side financing component	By end February 2016	UNICEF
Review targets for community units and identify measures of effectiveness	By end February 2016	UNICEF/Options/ / DFID
Develop plans to strengthen accountability at county level	By end January 2016	UNICEF/Options

Fund procurement of essential EmONC equipment for Bungoma	By end December 2015	DFID
Extend the CICF to allow for a third funding round	By end December 2015	DFID
Develop and maintain an overview of programme operations research	By end December 2015	UNICEF
Integrate key nutrition interventions, delivered through the health system, into the MNH programme	By end March 2016	DFID/UNICEF/ / Options
VfM measures for economy, cost efficiency and cost effectiveness to be agreed and reported on	By end December 2015 and ongoing	DFID/UNICEF/ Options/LSTM

Has the logframe been updated since the last review? Yes, specifically:

- A new outcome indicator has been added (stillbirth rate). Two outcome indicators have been removed (obstetric case fatality rate and cost per additional birth attended by a SBA). This may be worth reconsidering as obstetric CFR is a useful measure of the programme goals, specifically quality of care, and cost per additional SBA is a useful measure of programme cost-utility.
- The wording of outputs 2 and 3 has been revised, as recommended, to reflect the additional three counties. The wording of output indicator 1.2 has been changed from Average number of hours of mentoring follow up supervision received in last 12 months to The proportion of health facilities followed up quarterly, in line with recommendation made by the 2014 annual review.
- The wording of output indicators 3.1 (DSF) and 3.3 (ANC visits) has been changed to remove references to wealth quintiles; this data is not available from the DHIS for ANC visits. However, it would be useful to identify and track alternative measures of equity.
- Where appropriate, outcome and output indicators are now disaggregated by county.

Partners need to address gaps in milestones for 2016 and 2017 for some indicators. In addition, the three implementing partners, and DFID, need to agree consistent milestones and data sources; currently some milestones in partner logframes are not consistent with those in the overall logframe used by UNICEF to monitor and report on programme progress.

C: DETAILED OUTPUT SCORING

Output Title	Health workers in 32 counties have the knowledge and skills to provide quality delivery care and EmONC
Output number per LF		1	Output Score	B
Risk:		Low	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones 2015	Progress
1.1 Number of additional health workers trained in EmONC (disaggregated by sex)	4,000 (cumulative target)	4,397 health workers trained (direct and indirect trainings). Direct trainings Q1-Q3 2015: 65% female, 35% male. Score: A+
1.2 Proportion of health facilities followed up quarterly	70%	57%. LSTM reports that of 67 facilities eligible for follow up by 30 September 2015, 38 had commenced quarterly M&E. Score: B
1.3 % of facilities (that have been trained) conducting MPDSR that (i) are submitting complete monthly reports (ii) have made adjustments to service provision and/or management practices based on MPDSR	Overall: (i) 20% / (ii) 10% / Options (Bungoma): (i) 30%; (ii) 15%	UNICEF: (i) 27%; (ii) 0%. UNICEF notes that these are national figures. All CoE in Kakamega, Turkana and Homa Bay are conducting maternal audits; actions have been taken on recommendations in 8 facilities in Turkana and 15 documented cases in Homa Bay and Turkana. The referral hospital in Garissa and 2 facilities in Nairobi have recorded actions on recommendations. / Options: County and sub-county health teams sensitised, 42 facilities identified for training; on track to achieve milestones by end 2015. Score: B

Key Points

Output indicator 1.1:
There has been good progress with health worker training. LSTM has scaled up training and is on track to meet the target of training 9,000 health workers by end March 2019. LSTM counts direct trainings, conducted by its own trainers, and indirect trainings, conducted by those it has trained as trainers. LSTM has also trained 169 master trainers, 93% of the end of programme target.
LSTM is generating wider benefits. LSTM maintains and updates a database of the more than 25 other partners conducting EmONC training, provides support to these partners for training, and organises 6-monthly meetings to encourage coordination of training.

Output indicator 1.2:
- LSTM conducts follow up in facilities only after a minimum of 80% of all maternity staff have been trained in EmONC. For larger facilities this can take up to 3 months given the number of staff to be trained; facilities are then followed up at 3-monthly intervals for a year. Consequently, in facilities where a lower proportion of staff have been trained, there has been no follow up. LSTM notes that the target of 70% in year 2 may be over-optimistic.
- Follow up and mentoring needs to be strengthened. LSTM conducts end of training evaluation of changes in knowledge and skills but subsequent follow up is largely a data collection exercise and does not include mentoring support for health workers who have received EmONC training or assessment of sustained changes in competencies. Stakeholders highlighted concerns about whether those trained are putting newly-acquired knowledge and skills into practice. There is no national mentorship package – LSTM is currently discussing this with the MOH – and standard supervision does not include EmONC.

Output indicator 1.3:
There has been much MPDSR activity, but it is difficult to assess the combined impact of programme partners activities in this area. Each partner has different milestones for the percentage of facilities trained that submit reports and make adjustments to services. LSTM reports on actions in the past 3 months (in the overall logframe it is 12 months).

Summary of responses to issues raised in previous annual reviews

UNICEF and the Bungoma service provider should ensure that counties have accurate information about human resources for health, and provide support for effective county coordination of training. UNICEF has experienced delays in identifying TA to support counties to strengthen HRH management but expects to start by the end of 2015. Options is implementing plans to strengthen HRH in Bungoma, assisting the county to develop an HRH database and a training plan.
- UNICEF, LSTM and the Bungoma service provider should jointly review training plans to ensure that EmONC training covers health workers in facilities identified as centres of excellence in the focal counties and ensure that they jointly provide follow up support to these facilities. Partners have collaborated to ensure LSTM training prioritises key facilities in programme counties. More needs to be done to improve joint follow up.
- LSTM needs to monitor the costs of training, in particular increased costs due to security concerns, and keep DFID informed about budget implications. LSTM is monitoring the cost of training and reporting this to DFID.
- DFID should consider allocation of programme funding to cover the costs of training for tutors in pre-service training institutions. LSTM has submitted a proposal which has been approved by DFID, but this is on hold pending action by LSTM to address financial management issues.

Recommendations

- UNICEF and Options to prioritise support to counties for establishing effective HRH information systems and development of training databases and plans, starting with a focus on MNH.
- UNICEF, Options and LSTM, together with counties and other training partners, to ensure that newly recruited staff who require it receive EmONC training.
- LSTM to monitor the effectiveness of the more rigorous participant selection and verification procedures for trainings that it has put in place.
- UNICEF, Options and LSTM to develop and implement, in partnership with county health teams, a strategy to assess the competencies of staff trained and ensure that they receive effective mentoring and supportive supervision after training; the potential role of master trainers should be considered.
- UNICEF, Options and LSTM to identify requirements for replacement of EmONC training equipment and agree on how this will be procured and funded.
- UNICEF, Options and LSTM to determine how to measure the combined contribution of each partner to indicator 1.3 and to ensure that the milestones for this indicator are harmonised and have clear baselines i.e. the number of facilities trained.

## C: DETAILED OUTPUT SCORING
Output Title	Health systems strengthened to manage and deliver MNH services in Homa Bay, Turkana, Kakamega, Garissa, Nairobi and Bungoma counties
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones 2015	Progress
2.1 Innovation Fund projects demonstrate successful new approaches to improving delivery of quality MNH services	Six projects selected and contracted for Round 1	Seven projects contracted for Round 1; a further 2 have been shortlisted. Round 2 also completed and 10 projects provisionally selected for contracting. Score: A+
2.2 Counties have consolidated operational plans and budgets that include MNH services	County health plans include budgets for MNH	All six programme-supported counties have health plans that include MNH budgets. Score: A
2.3 Number of management systems supported and strengthened to objective standards and implemented at county level	Three per county	UNICEF has supported evidence-based planning, facility assessments, financial management training, routine monitoring, stakeholder coordination, but has not provided support to strengthen systems. / Options has conducted a health systems assessment in Bungoma and to date has provided support for governance, coordination and accountability systems (e.g. to restructure county and sub-county health teams, establish health sector coordination systems, train health management boards and health facility management committees). / Score: B

Key Points

Output Indicator 2.1:
- The County Challenge Innovation Fund (CICF) is ahead of schedule. It has completed contracting for Round 1 and provisionally selected projects for contracting for Round 2; the milestone was six projects selected and contracted for Round 1.
- The Fund is well managed and efficient. The CICF was established quickly by Options, and its sub-contractor, KPMG. Effective systems have been put in place to market the CICF, assess eligibility, screen and select proposals. 212 applications were received for Round 1 and 277 for Round 2. Projects approved will assess approaches to increase uptake of services and improve the efficiency and quality of maternal and newborn care. However, the range of innovations and the challenges proposals aim to address is less varied than anticipated. Many of the proposals focus on use of new technology and none address some key challenges e.g. night-time deliveries, health worker attitudes, cultural barriers. This is one consequence of the open nature of the competition; proposal were not solicited to target specific challenges or gaps.
- Achieving an equal number of projects from all programme counties may be difficult. In Round 1, few applications were received from Turkana and Garissa; no proposal from Garissa has been contracted. Regional distribution of funding will need to be considered carefully in Round 2..
- Funds could be available for a third round of applications. After Round 2, there will be a balance of around £3.5m from the current allocation. Consideration could be given to extending the contract timeframe, to allow for a further round that focuses on soliciting creative solutions to specific barriers and gaps. Extending the timeframe would also enable the results to be written up and disseminated more widely, in order to maximise their potential impact.

Output indicator 2.3
Options has made rapid progress in establishing the foundations for health systems strengthening in Bungoma. The use of an organisational capacity self-assessment tool has been well received by county and sub-county health management teams; it has provided a systematic assessment of priority needs and the basis for Options’ health systems strengthening plan as well as for future monitoring of progress. Implementation of support has started and Options is well on track. Options is also planning to introduce performance-based financing (PBF) in selected facilities to incentivise better quality of care and build the capacity of health facilities to manage funds; PBF will be awarded to health facilities based on selected ANC, delivery care and PNC indicators.
UNICEF has provided important inputs to enhance service delivery, but its support for health systems strengthening has been poor. UNICEF inputs, specifically procurement of equipment and supplies, have been critical to ensure that health facilities can deliver quality MNH care. UNICEF has sub-contracted UNOPS to implement renovations of health facilities and is in the process of contracting EGPAF to provide support to counties to improve the quality and completeness of DHIS reporting. However, there is no clear plan for providing tailored support to each of the five counties or for monitoring progress. UNICEF’s plans to support counties on human resources for health and governance, leadership and management have been delayed while UNICEF has sought to identify TA and to sub-contract UNOPS to manage funds; there has been no action to date on strengthening health financing or procurement systems.
- UNICEF has provided technical support to the national Ministry of Health to develop and revise a range of MNCH policies, strategies, guidelines and training materials. However, there is no clear plan as yet for health systems strengthening or evidence of collaboration with WHO on national health systems support through this programme.
- Options support does not include provision of essential equipment. Some health facilities in Bungoma lack equipment required to provide signal functions for BEmONC and CEmONC. The county health budget is unlikely to cover this in the short term. Lack of key equipment could undermine achievement of some programme outcomes in Bungoma. Options will need to assess what equipment is required, but also to check what equipment WHO has procured with DFID funding.
- The cost of renovations may have been under-estimated. UNICEF has contracted UNOPS to renovate facilities across the five UNICEF-supported counties. UNOPS’ initial assessment has identified some additional essential works e.g. removal of asbestos.
- Climate change interventions should target high-volume BEmONC and CEmONC facilities to maximise their contribution to programme results. Climate change/green energy interventions will encompass health facility improvements in power supply, water and sanitation. UNOPS will manage this on behalf of UNICEF and has budgeted for upgrading 150 facilities across five counties. Some facilities, such as hospitals, may require a more substantial power supply, which will increase the cost. If facilities need to be prioritised, it would make sense to focus on these providing CEmONC and high-volume BEmONC facilities. Options has a target of auditing 75 and upgrading 60 facilities in Bungoma, twice as many as in the other five programme counties. It may not make sense to audit facilities that will not be upgraded as this raises expectations and audit costs could be invested in upgrading other facilities. Again, it may be better to prioritise around 30 facilities, to cover the 6 county and sub-county hospitals and the 24 additional facilities that manage more than 100 deliveries per year. UNOPS is planning to recruit a green technology specialist for short-term inputs; it may be more cost-effective for Options to use the same person.

Summary of responses to issues raised in previous annual reviews

- UNICEF should share the findings of facility assessments with LSTM and Ministry of Health. Done.
- UNICEF and the service provider in Bungoma will need to monitor the balance of programme support for supply and demand-side interventions and adjust this as required. This is being monitored by UNICEF and Options and it is clear that facilities are struggling to meet existing demand.
- Specific systems strengthening plans, including planned technical assistance, need to be developed, implemented and monitored for each programme county, by UNICEF and the service provider for Bungoma. UNICEF should also build on good efforts to date to promote dialogue between county health teams and national Ministry of Health. Options has a system strengthening plan for Bungoma and a monitoring process in place. UNICEF’s plans are less clear; the need for a more systematic approach was discussed during this annual review. UNICEF should develop a specific plan, based on needs assessment, for systems strengthening support for MNH to the national MOH; this should build on the experience of the Kenya Health Programme. There is no specific plan.
- UNICEF should revise the title of Output 2 and indicators 2.1, 2.2 and 2.3, and related milestones and targets, to reflect the additional programme counties for DFID approval. Done.
- UNICEF should review the criteria for a centre of excellence for BEmONC and CEmONC and review findings of the evaluation of the centre of excellence and continuum of care approach before scale up across all programme counties. The concept of a centre of excellence has been documented, although some partners are still uncertain about what it means in practice. There has been no evaluation as yet.

Recommendations

- UNICEF senior management needs to urgently address areas of weakness, including delays in implementation and strategic support for health systems strengthening. UNICEF needs to consider using a similar approach to Options to identify county health systems strengthening priorities, provide a baseline for monitoring progress, and inform planning; and accelerate support for health systems strengthening to counties. Related to this, DFID and UNICEF should consider changing output indicator 2.3 and its milestones to be consistent with the approach taken by Options (i.e. Number of health system domains strengthened to meet objective standards with milestones setting targets for the number that should be red, amber or green by 2016 and 2017) as this is a better way of measuring systems strengthening progress.
- DFID to consider funding procurement of key equipment for CEmONC and BEmONC for Bungoma.
- UNICEF and Options to ensure that operation and maintenance costs for equipment are factored into county budgets to maximise sustainability of equipment and value for money from DFID investment.
- UNICEF and UNOPS to review county requests for infrastructure renovation carefully in view of existing county health budget allocations for infrastructure.
- UNOPS and Options to prioritise health facilities to receive climate change upgrading and, again, to factor in budgetary implications for maintenance.
- UNOPS and Options to consider cost-sharing of green energy technical inputs.
- DFID to discuss with programme partners how best to document the costs and cost savings of climate change interventions so that this knowledge and lessons learned can be shared more widely.
- DFID to consider extending the timeframe for the CICF, to allow for a third round that focuses on soliciting creative solutions to specific barriers and gaps and provision of TA to smaller organisations.

C: DETAILED OUTPUT SCORING
Output Title	Increased demand for maternal health services in Homa Bay, Turkana, Kakamega, Garissa, Nairobi and Bungoma counties
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones 2015	Progress
3.1 Number of poor women covered by demand-side financing	40,000 (Bungoma: 1,200; Turkana, Garissa, Homa Bay, Kakamega, Nairobi: 38,800)	Options will start DSF through provision of transport vouchers in Bungoma 1 October 2015, and expects to cover 600 women by end of 2015. UNICEF component not yet commenced. Score: C
3.2 Number of community units (i) established and (ii) that are functional	Homa Bay: 243 (100% coverage at baseline); Turkana: 120; Kakamega: 120; Garissa: 150; Nairobi (Embakasi): 110; Nairobi (Kamukunji): 120; Bungoma: 40	Homa Bay: 243; Turkana: 73; Kakamega: 120; Garissa: 60; Nairobi (Embakasi): 0; Nairobi (Kamukunji): 0; Bungoma: 50 CUs trained; functionality to be assessed in Q4. / Score: B
3.3 % of women receiving at least 4 ANC contacts during pregnancy (national and by programme county)	National 54% / Homa Bay 48%; Turkana 60%; Kakamega 50%; Garissa 50%; Nairobi (Embakasi) 55%; Nairobi (Kamukunji) 55%; Bungoma 45%	National 64.8% / Homa Bay 61.4%; Turkana 54.5%; Kakamega 84.4%; Garissa 51%; / Bungoma 44%; Nairobi (Embakasi: 114%; Nairobi (Kamukunji) 84.4% / Note: Figures based on DHIS for August 2015; some seem rather high and it is not clear how 114% has been achieved in Embakasi. / Score: A

Key Points

Output Indicator 3.1:
- Government of Kenya commitment to free maternal health care in public facilities has increased demand for services, but there are other demand-side barriers in addition to payment at point of use. In some counties, support to address the costs of transport, cultural and other barriers is still required to encourage women to come to facilities for ANC and delivery care.
- UNICEF has made little progress in taking forward demand-side financing. UNICEF has had difficulties in identifying a consultant, but expects design work to start by the end of 2015.
- UNICEF is planning to implement other interventions to address cultural and other barriers. These include: providing incentives for women who come to a facility to deliver, such as Mama kits, spoons, bowls and baby shawls; establishing waiting mothers’ shelters in Turkana so that women can come to a facility prior to delivery; and piloting the use of a birthing cushion in Turkana to enable women to deliver in a squatting position, which is more culturally acceptable.
- Options is focusing on transport vouchers. This reflects the findings of the qualitative assessment it conducted in Bungoma during the inception phase earlier this year, which identified the cost of transport as a key barrier. A key issue that needs to be considered is whether transport vouchers can be used by birth companions, as many women may be reluctant to come to a facility to deliver alone. This would mean, however, that fewer women would benefit from the subsidy.

Output Indicator 3.2:
- Targets for the number of community units supported should be reviewed. The 2014 annual review recommended focusing on functionality rather than numbers. UNICEF reports that it is now doing this, although UNOPS’ training plans and budget imply that UNICEF is still proposing to cover a large number of units. Options has a target of 173 units.
- Better information is required about the effectiveness and cost-effectiveness of community units. The community unit functionality scorecard measures process issues, e.g. meetings held, reports submitted, but there is little rigorous evidence about the effectiveness of community units (UNICEF reports that it is planning a study of effectiveness and cost effectiveness). Despite this, the programme is investing significant funding in training and equipping large numbers of community health volunteers; in addition, the attrition rate of volunteers is reported to be high in places where they are not well supported or supervised.

Output Indicator 3.3:
- The proportion of women attending for 4 ANC visits has increased but more needs to be done. It is difficult to ascertain how much of the increase is attributable to the programme and how much to the Government’s free maternity care policy. Significant drop off between the first and fourth visits remains a challenge, and many women present for their first ANC visit late in pregnancy.
- Demand-creation activities have not fully commenced in some programme areas. Options’ qualitative formative research during the inception phase identified barriers and facilitators; this has been used to inform the development of a Social and Behaviour Change Communication strategy for Bungoma. The strategy is sound and based on evidence. UNICEF has been supporting demand-creation activities; additional work is due to commence in 2015 once UNICEF has identified and sub-contracted organisations to implement this in Kakamega, Homa Bay and Turkana.

Summary of responses to issues raised in previous annual reviews

- UNICEF, in consultation with DFID, needs to redesign the demand-side financing component and identify options to be tested. This should involve review of upcoming evidence and dialogue with other key partners including the Ministry of Health, WHO and the World Bank. UNICEF has reviewed evidence, but the DSF component has not yet been redesigned.
- UNICEF and the service provider for Bungoma should focus on strengthening the functionality of community units linked to centre of excellence facilities, rather than achieving an increase in the absolute number of units, collect baseline information about the functionality of these units, develop a plan to improve the functionality of referral systems and monitor progress. Not clear how UNICEF is prioritising which units to support. UNICEF is recruiting TA for the design of referral systems.
- UNICEF and the service provider for Bungoma should provide support to county health teams and community units to establish and use effective accountability mechanisms and ensure that community demand creation activities include promoting awareness of these mechanisms and how to use them to register complaints and seek redress. Leadership, management and governance capacity development for county health teams should include accountability. UNICEF and Options have provided support to establish health management boards and health facility committees; both are also introducing use of the RMNCH scorecard.

Recommendations

- UNICEF to accelerate design of demand-side interventions including DSF.
- UNICEF and Options to consider how to measure the effectiveness of community units, in particular community health volunteers, and revise indicator 3.2 milestones to include effectiveness measures.
- UNICEF and Options to prioritise support for community units that are linked to UNICEF-identified centres of excellence in the five counties and facilities with high volume of deliveries in Bungoma.
- UNICEF and Options to monitor the balance between supply and demand and sequence demand-creation activities to ensure that health facilities can meet additional demand.
- UNICEF and Options to assess the underlying reasons for drop out between first and fourth ANC visits and identify demand-side interventions to address these factors.
- UNICEF and Options to give higher priority to ensuring that counties and facilities have effective accountability mechanisms in place.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The original investment in the programme is £75.3m through 2019; an additional £4.5m has been added for climate change interventions. Key costs[1] and performance are an important component of understanding expenditure flow within the VfM assessment. Among the three implementers, key costs are reported as follows:
[1] Key costs are resource areas that consume the greatest amount of programme expenditure.
Implementing Partner	Cost Driver 1 and per cent of total expenditure	Cost Driver 2 and per cent of total expenditure	Cost Driver 3 and per cent of total expenditure
Liverpool School of Tropical Medicine (LSTM)	EmONC direct training costs (49%)	Staff and office costs (23%)	Overheads (8%)
UNICEF	Transfer of cash to partners (40.7%)	Procurement MNH equipment and supplies (34.3%)
Options/Marie Stopes International (MSI)	Fees (26%)	Activities (67%)	Office rent and running costs (2%)

Key drivers affecting these costs that have been cited by implementing partners are: inflation, security, global market prices, the devolution process (in causing delays) and political instability (see Annex for details). Implementing partner top actions to maximise VfM (economy, efficiency and effectiveness) include the following (see Annex for details):

- UNICEF is adhering to rigorous supply and procurement regulations (global supplies division platform), which involves bulk procurement and negotiated purchase and freight costs and ensures high-quality products.
- LSTM is maximising use of Kenyan trainers rather than paid staff/consultants or volunteers from the UK, to reduce international travel-related costs.
- Options/MSI has processes in place to support procurement of items at the lowest price with consideration to quality.

Potential weaknesses all implementers have experienced to maximise VfM at present include the limited amount of benchmarks available, uncertainty in market forces and political instability.

VfM performance compared to VfM proposition in the Business Case

This is the second annual review of the programme. Under the Business Case[2], the current programme was selected as the preferred option because it represented very good, high level value for money compared to international benchmarks. In summary, the Business Case estimated that by 2022 the programme is expected to save about 650,000 DALYs at a unit cost of just over £100[3] per DALY. As the programme is in the second of five years of operation it is premature to compare unit costs per DALY (with the original estimation), because of two factors: 1) more robust cost data should be available in the later years of the programme, and 2) possible delayed impacts related to both training and health systems strengthening components. At present, the implementing partners are not providing quantitative VfM data. A practical VfM framework is therefore being developed by a health economist and will be discussed with partners in November 2015.
[2] Business Case: Reducing Maternal and Newborn Deaths in Kenya, October 2013
[3] This is well below GDP per capita of £500, a reference point for determining whether or not health interventions are cost effective.

Assessment of whether the programme continues to represent VfM

The programme is likely to remain good VfM. Although the cost per DALY is likely to be higher than the target of £100 due to the lower performance against the skilled birth attendance target, it is very unlikely to go higher than the WHO threshold for high cost effectiveness (Kenya’s GDP of US$1,290 in 2014). However, greater reporting and analysis of VfM measures is needed to be sure of this.

Results: although the Output score is A, the majority of Outcomes are on track except skilled birth attendance.
Costs: are on track (see Financial Management below).
Theory of Change: remains valid (see Section H below).
Risks: remain stable at Medium (see Section E above).
VfM practices: are adequate (see above).
VfM measures: need to be agreed and reported on (see above).

Quality of financial management

UNICEF, LSTM and Options have met narrative and financial reporting requirements. Two issues have arisen during the past year. First, in response to DFID rules concerning direct funding of government in Kenya, UNICEF has had to sub-contract UNOPS to manage funding for national and county-level activities. Second, A DFID spot check and subsequent forensic audit of LSTM financial management systems highlighted concerns and weaknesses; based on this LSTM will develop and agree an action plan with DFID Kenya and report on actions taken on a quarterly basis.

Financial forecasts are on track and in line with the programme budget. The following table shows funds disbursed to date.

Implementing partner	Total budget £	Year 1 and 2 budget £	Funds disbursed by DFID as of September 2015 £	Balance £
LSTM	9,318,000	2,771,605 (Year 1) / 2,313,851 (Year 2)	2,605,056	6,712,944
UNICEF	25,793,796 / (These includes Evaluation and ICF funds)	6,532,616 (2,000,000 – inception phase and 4,532,616 – Year 1) / 8,353,067 (Year 2)	11,957,696	13,836,100
Options	20,146,294	733,620 – inception phase and 2,444,125 – Year 1	1,949,216.00	18,197,078

Date of last narrative financial report	16 July 2015
Date of last audited annual statement	31 December 2014

E: RISK

Overall risk rating: Medium

The overall risk rating is unchanged.

Overview of programme risks

As required, UNICEF, Options and LSTM have separate risk matrices and systems for monitoring risk in place; risk matrices are updated on a quarterly basis. While there are no new risks in addition to those identified in the Business Case and partner risk matrices, some risks have increased, in particular those associated with insecurity and county health budgets and capacity.

- Changes in the risk context: The risks associated with insecurity and conflict have increased, following the terrorist attack on Garissa University and other incidents, and due to sporadic violence in Turkana and West Pokot; the probability should be revised from Medium to High. Health worker strikes were also not anticipated.
- Key risks affecting successful delivery of results: A key risk affecting county capacity to deliver quality MNH services is the increase in demand resulting from the GOK’s free maternity care policy in settings that continue to experience shortages of health workers. Counties are currently recruiting health workers, but attracting and retaining staff is likely to remain a challenge, particularly in Turkana and Garissa. A related risk is shortfalls in county health budgets. If health worker strikes result in pay increases, county budgets will be even more stretched. There are also competing demands on County Health Management Team time; MNH is one of many priority issues.
- New mitigating actions needed: Support for county planning and budgeting and advocacy with county governments will be critical, to ensure health budgets are adequate to needs; support to counties for efficient management of human resources for health and procurement will also be critical. Continued monitoring of the security situation and the impact of this will be required.
- Additional checks and controls needed: UNICEF, UNOPS and Options will need to monitor renovations and green energy inputs carefully, to assure the quality of the work and effective management of assets. LSTM will need to develop a comprehensive action plan following the assurance audit conducted by DFID.

Outstanding actions from risk assessment
None.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

Delivery against the programme timeframe was off track at the time of the 2014 annual review; delivery by LSTM and Options is now broadly on track. LSTM has scaled up training and has made up for the delay in start up. Options had made rapid progress since its contract began in January 2015, making up for delays in start-up of activities due to the procurement process; health systems strengthening and demand-side support in Bungoma is on track, and the CICF was mobilised quickly and will deliver against approved timescales.

However, UNICEF delivery is off track in some areas. This reflects UNICEF systems, the time it has taken for UNICEF to fill staff positions, and the need to sub-contract UNOPS to manage some areas of programme activity, including funding for county level activities. UNICEF has experienced difficulties in identifying technical assistance to take forward some areas of programme activity and, as a result, there have been delays in taking these forward. UNICEF has also issued calls for expressions of interest to implement various components of the programme (DSF; Respectful Maternity Care; demand creation; social accountability; and M&E) in the five UNICEF-supported counties. It will be critical for UNICEF to get programme activities on track as quickly as possible.

Performance of partnership(s)

UNICEF, LSTM and Options have a good working relationship and meet regularly. UNICEF and LSTM also have a good relationship with the national Ministry of Health. Programme steering and technical committees, with representation of government, implementing partners and DFID, have met.

UNICEF and Options have established effective partnerships with county health teams in their respective counties. Options is working closely with other partners in Bungoma, in particular with the Boresha MNH Project, which is being implemented by Save the Children in three sub-counties. Following initial delays, UNICEF has contracts in place with its existing sub-contractors; the contract with UNOPS was effected very quickly. Options also has contracts in place, and a good working relationship with, KPMG and Population Council for management of the County Innovation Challenge Fund, and the other four programme sub-contractors.

Partnerships could be strengthened though more thematic meetings between programme implementing partners to share approaches, experience and lessons learned and discus issues of common concern, such as health systems strengthening, DSF and community units, and more systematic sharing of programme reports, assessments and other documents. The recent appointment of the UNICEF Partnerships Specialist should help to improve this. Examples of areas where it may be useful for partners to share experience or collaborate include: UNICEF to share experience of Kangaroo Mother Care, use of the uterine balloon tamponade and of maternity tours with Options as these approaches could also be of value in Bungoma; LSTM, UNICEF and Options to share and agree on a common list of key equipment required by health facilities to be able to provide signal functions for BEmONC and CEmONC; UNOPS and Options to explore the potential to use the same international expert to conduct health facility green energy assessment and follow up in all six counties; and UNICEF to consider using the OCAT approach used by Options for health systems self-assessment and monitoring in Bungoma in the UNICEF-supported five counties.

Overall, DFID is seen as an effective and supportive partner by key stakeholders. However, DFID’s responsiveness could be improved and UNICEF identified the need to manage ad hoc requests for information.

Asset monitoring and control

Assets financed by this programme include equipment for health facilities procured by UNICEF, and training equipment procured centrally by LSTM. UNICEF, LSTM and Options have systems in place to record and monitor assets. UNICEF maintains a computerised record of all items procured and conducts regular spot checks; LSTM and Options also maintain asset registers. Since the previous annual review, partners have ensured that equipment has UKAID branding. The systems in place suggest that DFID can be confident that programme assets are well managed. With the addition of funding to integrate climate change interventions, implementing partners will need to ensure that solar panels and other equipment procured with climate change funds is included in asset registers.

G: CONDITIONALITY

Update on partnership principles

Since DFID is not providing financial aid using Government of Kenya systems in the delivery of the programme, partnership principles do not apply in management and monitoring of the programme.

H: MONITORING & EVALUATION

Evidence and evaluation

The overall programme design and theory of change remain relevant. New evidence has emerged on DSF; this evidence, and the findings of UNICEF qualitative assessments of factors influencing uptake of MNCH services, will be used to inform UNICEF’s approach to DSF. Options has used evidence from a qualitative assessment of social, cultural and economic barriers to accessing MNH services in Bungoma to inform the design of its approach to DSF, which will focus on transport subsidies.

UNICEF is implementing studies on the impact of community MNH services in increasing uptake of antenatal and delivery care, use of the uterine balloon tamponade to manage post-partum haemorrhage in low-resource settings, and use of birthing cushions that allow women to deliver in a squatting position. Studies on use of nomadic clinics and maternity waiting homes to improve access in nomadic communities have yet to start. LSTM studies include the effectiveness of EmONC training with and without Quality Improvement (QI), retention of knowledge and skills by health workers after EmONC training (data collection completed), the effects of QI and data management training, the social return on investment of EmONC training (data collection completed), and the causes of and factors associated with stillbirth (to be completed end October 2015). A study of the role and performance of community health workers in MNH will commence in November 2015. Options has identified a range of operations research questions to be addressed during programme implementation. The CICF will also generate evidence about innovative and effective approaches to address supply and demand challenges. As recommended by the 2014 annual review, UNICEF needs to maintain an overview of programme operations research by all partners, including projects funded through the CICF, to ensure coherence and coordination and allow DFID to track the progress of different studies. Partners and the CICF also need to consider the resource (financial and staff) costs as well as the technical aspects of interventions and innovations piloted; for the latter this will be important to assess the costs of scale up and longer-term financial viability.

The Business Case proposed that beneficiary perspectives be sought through a range of approaches. Implementing partners are capturing beneficiary feedback and human interest stories to some extent. However, it would be useful to establish a system for systematically documenting beneficiary feedback and human interest stories and to agree on a common approach or format for this.

An independent evaluation is planned for this programme, to generate evidence on the effectiveness of strengthening health systems in contributing towards reduction of maternal and newborn mortality and, specifically, to explore the impact of training only vs. training and health systems interventions on maternal health outcomes and to compare programme delivery by different partners. There have been delays in recruiting an independent evaluation contractor; a consortium of organisations led by HERA Consulting Services is currently being contracted by UNICEF. Evaluation activities will start in January 2016 following a 3-month inception phase. UNICEF has established an Independent Expert Group (IEG) to provide oversight; it will be critical that the IEG group includes adequate evaluation expertise to ensure that the evaluation design will generate the data DFID requires.

Monitoring progress throughout the review period

UNICEF submits consolidated six-monthly reports to DFID. Partners noted that UNICEF requires a long lead time to prepare consolidated reports; UNICEF should take steps to reduce this so that progress reports include data that is as up-to-date as possible. Options has a comprehensive M&E plan and has conducted baseline household and facility surveys. However, Options has not budgeted for endline surveys; this needs to be addressed either through re-allocation of available funds or through the independent evaluation.

Feedback from county health teams and health workers during field visits for this annual review on the LSTM EmONC training was very positive. Feedback from county and sub-county health teams and facilities in Turkana and Nairobi on UNICEF support was also very positive, as was feedback from county and sub-county staff in Bungoma on Options support. In Bungoma, the county reproductive health coordinator was extremely enthusiastic about support for provided for health systems strengthening, and the Kabuchai sub-county team noted that, prior to the programme, ‘they were working in the dark’ as they had no annual work plan or budget.

The annual review was conducted by an external consultant with inputs from DFID staff. Meetings were held in Nairobi with UNICEF, LSTM, UNOPS, Options, KPMG, Population Council, DFID staff and the Ministry of Health. Field visits to Turkana and Bungoma counties and Embakasi sub-county in Nairobi included meetings with county and sub-county health teams, UNICEF and Options staff, local implementing partners, hospital and health centre staff, community units and community health volunteers. The annual review results will be shared with implementing partners.