Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Multi-Year Humanitarian Programme
Programme Value: £100m		Review Date: 10-12-2015
Programme Code: 204603	Start Date: 10-12-2014	End Date: 30-09-2019

Summary of Programme Performance
Year	2015
Programme Score	B
Risk Rating	Low

Summary of progress and lessons learnt since last review

This is the first annual review of DFID’s Multi Year Humanitarian Programme (MYHP). The programme commenced in December 2014, with partnerships officially rolled out in July 2015. Over the first year the Team has invested significant time in defining harmonized approaches for all delivery pillars, selection of partnerships and in streamlining governance structures. This will support more effective delivery throughout the full programme cycle. During this mobilisation year, DFID has also been able to respond to three separate humanitarian emergencies through MYHP, reaching around 20,000 people. It must be noted that the current logframe indicators did not allow for a means of monitoring progress achieved during the mobilization period (discussed under ‘Summary of Recommendations’ below), which has been the focus of the first year of programming.

A summary of progress under each pillar is below:

Under Pillar I (response to natural disasters), DFID has focused on establishing strong partnerships through a consortium approach, helping to set up strong governance structures. The International Organization for Migration (IOM) was selected as the consortium lead, in partnership with Food and Agriculture Organization (FAO), Health and Nutritional Development Society (HANDS), Agency for Technical Cooperation and Development (ACTED), and UNICEF. Delivery of the programme is underway, and the consortium has already responded to the summer monsoon floods, and an earthquake in October.

Under Pillar II (protracted displacement), The International Rescue Committee (IRC) was selected to lead a consortia comprising of ACTED and HelpAge to respond to livelihoods and protection activities for those in displacement. So far, focus during the inception phase has been on standardization of the programme across the members, and defining triggers for intervention. Specific interventions will be rolled out during the coming months.

Joint UN Support to the Federally Administered Tribal Areas Returns and Rehabilitation Strategy (FATA R&R) was signed on 11 November. This will allow roll out of support to Internally Displaced People (IDPs) in returns areas through the four consortium members (UNDP, WFP, UNICEF and FAO) with a focus on immediate needs for returning families.

WFP Standby Arrangement was signed in September, and was activated almost immediately, due to the need to respond to, first, the flash flood in Chitral, followed shortly thereafter by an earthquake in the same area. As the MOU was already signed, it allowed for a reactive, response to be mounted within two months, rather than starting the contracting stage following a new emergency.

DFID disbursed the full annual £2 million to OCHA for the Pakistan Humanitarian Pooled Fund (PHPF) in September 2015. This formed the basis of a standard allocation for activities in returns areas, with all funding set to be distributed through the existing Cluster system within the coming months. There are positive signs that the newly-revamped PHPF will allow more strategic and rapid funding during emergencies, and DFID will continue to be an active member of the Advisory Board.

On the research and evidence strand, an Early Market Engagement was held for the Pakistan Evidence and Learning Programme (PELP), with procurement expected to start in December, 2015.

Summary of recommendations for the next year

Logframe indicators. Following this annual review, an amendment of the existing logframe indicators will take place, to ensure project- and programme-level progress are being captured accurately. Several of the indicators (as indicated under the relevant Detailed Output Scoring) were set to measure activities outside of the programme’s control – e.g. reporting on incidence of violence against women and girls – or do not specifically capture the current set-up of the individual projects – e.g. no means of measuring scale of relief activities other than through speed of delivery. In addition, the logframe did not allow for measuring progress made during the mobilization of the overall programme, or the inception periods of the individual projects. Both of these time periods are crucial for the overall success of the programme. The proposed amendment will not impact the overall Outputs, but allow better monitoring of progress towards achieving them through improved indicators.

Preparedness and early recovery. Once the emergency phase for response to the floods and the earthquake are completed, the Natural Disasters consortium will be able to shift their focus to preparedness and early recovery activities. So far, the Natural Disasters consortium successfully adapted its strategy immediately after signing, to focus exclusively on three almost-concurrent disasters (monsoon floods, flash flooding and an earthquake). During the coming year, with all the partners now operational, there will be sufficient breathing space for the consortium to place more focus on early recovery, as well as on being better prepared for both predictable and unpredictable emergencies. This will require more emphasis on innovative and sustainable approaches, and continued DFID engagement.

Improved forecasting by partners. During the reporting period, several partners were over-ambitious in their forecasts, with one partner not spending any of the first quarter tranche. This was due to delays in signing agreements with consortium members, rather than other operational issues. DFID will continue to work with partners to ensure they are realistic in their forecasting, while still being able to scale up as the needs dictate.

Increased ownership by consortia leads. Some initial teething problems with both consortia were expected over the mobilisation period, but this also included lack of cohesive reporting, with consortia leads not taking sufficient accountability for the overall output of the consortia. A focus for the next year, will be to make sure that the consortia are truly integrating their responses and their reporting, rather than acting as individual organizations.

1. Continued revision of the thresholds for response. There is a need for harmonization of the trigger mechanisms for response among the various partnerships, as part of the regular contingency planning process. This will allow for more rapid and strategic decision-making within DFID as to which emergencies call for intervention, and the scale of our response. This will also create clearer lines, such that even where there is no UN coordination Cluster System (i.e. for all natural disasters), response through both the WFP Standby Arrangement and the Pillar I Natural Disasters consortium can be closer linked to pre-defined triggers and the same qualitative assessments. The trigger mechanisms will also be discussed with the relevant Provincial Disaster Management Authorities (PDMAs) during emergencies, as a means of communicating the basis of DFID’s engagement.
2. Integrating lessons learned from previous programming. The Predictable Emergencies Programme (PEP) completed recently with a number of technical and programmatic recommendations made for future humanitarian programming. PEP implementing partners are delivering a number of MYHP interventions. Recommendations relevant to MYHP included:
  1. Reducing the overall number of implementing partners. This will result in more efficient and cost-effective programme implementation, and has driven the delivery methodology for the MYHP, in particular the use of consortia and standby agreements rather than individual partnership arrangements with each organisation.
  2. Beneficiary selection. Beneficiary selection remains a challenge. The MYHP will invest more effort and resources in documenting the beneficiary selection process and maintaining data on beneficiaries to ensure the most vulnerable are reached.
  3. Community approaches to promote cohesion. Better promotion of social relations within communities that are hosting IDPs is required overall, due to local services becoming overwhelmed, and the need to reduce potential conflict over limited resources. This will be addressed through our protection programming, but requires monitoring.
  4. Standardised beneficiary feedback. Beneficiary feedback mechanisms can be complicated when considering multiple interventions, and will need to be harmonized with all MYHP partners. This will form part of the upcoming dialogue with all partners
  5. Cash-disbursement mechanisms. A more thorough market assessment of the local cash-disbursement system for all cash transfer programmes needs to be commissioned. This will result in a more efficient disbursement mechanism to individual beneficiaries in rural parts of the target areas.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4811609.odt
DevTracker Link to Logframe:	http://iati.dfid.gov.uk/iati_documents/4849825.xls

Pakistan has been affected by at least two humanitarian emergencies per year in the last five years and is likely to continue to face a variety of serious disasters and the potential for conflict-induced displacement over the next four years and beyond. The country sits in an active seismic zone and earthquakes have caused huge damage, particularly in the northern region, with an average of 19,000 deaths per earthquake over the past 50 years. The monsoon season is a growing but predictable risk. The impacts since 2010 have been particularly harsh, due to pressures of both climatic change and an increasing population. In 2010, 20 million people were affected across the country by monsoon floods, leading to an average of 8.9 million people severely affected per year in the four years since then. Although less frequent than floods, localised droughts have been a regular occurrence in Pakistan. They particularly affect pastoralists living in the marginal lands of FATA and Baluchistan. All of these require DFID programming to focus on both humanitarian relief, as well as preparedness and early recovery activities to mitigate risks to natural disasters.

Since the approval of the MYHP, Pakistan has suffered three major natural disasters, and up to one million people are still displaced due to conflict. The summer monsoon of 2015 resulted in up to 1.2 million people displaced, with 12,000 houses destroyed. At the same time, flash floods occurred in Chitral in Khyber Pakhtunkhwa (KP), exacerbated by glacial melt. This resulted in around 210,000 people affected across an area with difficult access, and the loss of over half the crops. Both of these required a rapid response at the time when both the Natural Disasters consortium and the WFP Standby Arrangement were being finalized.

Two months after the flash floods in Chitral, the same area was hit by a 7.5 magnitude earthquake, which has resulted in the damage or destruction of over 100,000 houses across northern Pakistan. This double devastation has resulted in actors trying to respond to the flash floods no longer having access to the most affected areas, and a huge increase in the number of people in need. DFID has already scaled up existing funding mechanisms to reach an additional 10,000 families, and much of the focus for early recovery activities and earthquake-resilient housing will begin in spring 2016.

Additionally, there are around 1.6 million registered IDPs in north-west Pakistan as a result of military operations and armed violence in the Federally Administered Tribal Areas (FATA). The military operations in North Waziristan in June and July 2014 resulted in the further displacement of around 700,000 people. During 2015 and 2016, the new governmental strategy for returns will require continued humanitarian support regardless of any new conflict-induced displacements. On current plans, all IDPs are expected to return home by December 2016, at the latest.

DFID has provided significant humanitarian aid for those affected by natural disasters and conflict over the last ten years. On average, the UK has contributed around £25m per year from 2011 to 2014 to humanitarian response efforts following earthquakes, flooding and displacements, not including 2010 flood response. DFID is the third largest humanitarian donor in Pakistan. Previously, DFID Pakistan has delivered various programmes of support but always through an ad-hoc or annual funding cycle. The MYHP as a four-year continuous programme gives DFID the time to work on long-term disaster preparedness activities, and to build in resilient approaches to future disasters where possible.

This will help to reduce the impact and financial cost of post-event emergency responses over time. A four-year programme also allows DFID to develop closer partnerships with funded agencies, and to explore prospects for performance gains in their programmes.

Over the four-year period, the programme will support between two and three million people in humanitarian need, depending on the size and location of unpredictable emergencies, and assuming the programme’s full financial allocation is spent.

The MYHP is divided into four pillars, the first two of which are for ongoing humanitarian response. Pillar I focuses on preparedness, response, and early recovery in natural disasters; Pillar II is related to complex emergency and conflict-induced displacement. Pillar III is a contingency fund able to top up the responses when large-scale emergencies occur, with Pillar IV focusing on evidence, learning and monitoring and evaluation.

Pillar I
Delivered through an IOM-led consortium, with partnerships with FAO, UNICEF, ACTED and HANDS, for £31 million over 4 years. The MOU was signed in July 2015. Initial response activities have been mounted to address 2015 monsoon floods in Sindh, and flash flooding and earthquake in Chitral, Khyber Pakhtunkhwa, with early recovery work planned.

Pillar II
An IRC-led consortium, in partnership with HelpAge and ACTED, for £8 million over 4 years. Accountable Grants were signed at the beginning of August, but the project is still in the inception phase due to issues signing with consortium members.

IDP Vulnerability Assessment Profiling (IVAP), managed by IRC, for £1.6 million over 4 years. Initial roll-out of the new strategy is underway, with a database of 170,000 vulnerable families available to the humanitarian community for their assistance. A new IDP profiling exercise will begin in February.

Joint UN response in support of the FATA Returns and Rehabilitation (R&R) Strategy, with up to £10 million over 2 years. Delays have resulted in the consortium partner lead (UNDP) only having signed the MOU as this report is being compiled.

Bridging Strategy – Under Pillar II
Following the Secretary of State’s approval of the Business Case, and while calls for concepts were being elaborated, there was a deterioration of the situation of recently-displaced people. The planned returns to their places of origin were significantly delayed, and with the onset of winter, humanitarian assistance was urgently required. As such, DFID designed a short-term intervention with two existing partners to cover the emergency phase, for a total of £2.5m (IOM: £500,000 & Acted £2m)

Pillar III
- WFP Standby Arrangement: up to £20 million over 4 years, based on pre-defined thresholds and DFID analysis of need for WFP response. So far, this mechanism has been activated for £1m for immediate response to joint flood and earthquake needs in Chitral.
- OCHA Pooled Fund (‘Pakistan Humanitarian Pooled Fund’ – “PHPF”). £2m a year with potential to top up. Disbursement in September 2015, with the first standard allocation in October for needs in returns areas.

Pillar IV
The Pakistan Evidence and Learning Project (PELP) earmarked at £11m is the research and evidence pillar. This will overlap with the Resilience programme. An Early Market Engagement (EME) event was held in October 2015. The EME helped to warm up the market for the project but also to determine the appropriate route for procurement, which is expected to commence in the first quarter of 2016.

PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The overall outcome for MYHP is summarized as follows:

Outcome Statement: “People affected by disasters have access to timely, appropriate and good value humanitarian assistance to recover, which leads to reduced vulnerabilities to future shocks”

The aim is an overall decrease in needs among populations affected by both natural disaster and by conflict; for individuals to be in a position to recover sufficiently from each shock, such that they are better able to sustain any future disasters; to build back better in an environment of protracted disasters; and to ensure that all lessons learnt are disseminated to the wider humanitarian community.

The partnerships under MYHP have only been operational for six months or less. In that short space of time, however, DFID has already been able to deliver effective humanitarian responses to three separate emergencies including two large-scale floods and an earthquake. The logframe milestones are based on a one-year timescale, however, proportionally these are on-track, based on six months of partner operations.

The programme is working towards the overall outcome, with the focus shifting towards the second element of the outcome statement, namely reducing vulnerabilities to future shocks. Plans for sustainable rebuilding of earthquake- and flood-damaged and destroyed housing is already underway, with integrated programming to include water and sanitation activities. In FATA, the Joint UN Support to the Returns and Rehabilitation Strategy will also be focusing all efforts on supporting the viability of returns of up to a million people affected by conflict, through livelihoods, and the reestablishment of basic services.

Overall outcome score and description

The annual review scored a B overall, due to the time that was taken to set up the programme partnerships. The logframe, unfortunately, does not recognize progress made during the first year on either the mobilization phase, or the inception period required for the partners. This is reflected in the final score, and three of the four output scores. In addition, the logframe does not allow us to adequately capture specific responses that we have mounted so far, related to the floods and the earthquake. As noted above under ‘Summary of Progress’, the logframe is being revised for the next annual review.

Annual Outcome Score	B
Annual output performance	Outputs moderately did not meet expectations
Outcome risk rating	Low

Output Description	Impact Weight	Output Performance	Risk
Output 1: Timely delivery of appropriate relief in immediate aftermath of disaster	30%	Outputs exceed expectations (A+)	Medium
Output 2: Integrated post-disaster recovery support that restores living conditions and reduces vulnerability to future shocks	30%	Outputs substantially did not meet expectations (C)	Low
Output3: Improved access to humanitarian assistance and protection services	25%	Outputs moderately did not meet expectations (B)	Medium
Output 4: Improved coordination and technical design of humanitarian projects	15%	Outputs moderately did not meet expectations (B)	Low

Key lessons
This is the first time that DFID’s humanitarian programme in Pakistan has set up consortia that involve a mix of local and international NGOs along with UN agencies. Delays encountered in signing agreements with the consortium partners for the Natural Disaster component has affected programme delivery. The main lesson is that consortia leads need to ensure that the HQs of all UN agencies and organizations are made aware of the discussions, in order to streamline the procedures around contracting.

The time spent in elaborating the Terms of Reference (ToRs) and the call for concept, has proven to be critical, so that all roles and responsibilities are in line with the overall programme, and the expectations from partners are clear, and included in contracting arrangements. However, as referenced above, progress during the mobilization phase cannot be captured by the logframe in its current state, and the logframe will undergo a review to make it fit for purpose.

  1. The need to have the Natural Disasters consortium operational prior to the annual floods, resulted in the lead organization (IOM) signing with DFID prior to signing with their consortium members. From the perspective of some of the partners, this meant they were unable to have sufficient influence over the contents of the main contract (i.e. between DFID and IOM). However, this is an issue that has now been resolved among the partners.

Flexibility is vital in the humanitarian context, and during the initial set -up phase of the MYHP, a deteriorating situation among IDPs came to light. With returns to their places of origin delayed until the Spring, many thousands of displaced families from North Waziristan were in need of emergency assistance over the winter months. The programme flexibility allowed DFID to immediately elaborate a ‘bridging strategy’, such that assistance would not be unduly delayed by the need to devise a longer-term strategy. This allowed 18,000 households to be reached with winterization kits and cash assistance, in line with the humanitarian imperative to respond.

Partner Financial Profiling: The original activity-based budget submitted by consortia partners and associated financial profiles have been over-ambitious. For example, during the first quarter a key Natural Disasters consortium partner, UNICEF, did not spend any money disbursed to them by the consortium lead, IOM. This was due to delays in their signing internal consortium contractual agreements with IOM. Thus, UNICEF were unable to proceed with activities as originally set out in the Natural Disasters proposal. Similarly, the RELIEF consortium led by IRC has been unable to start activities in line with the original plan, due to their own contractual issue with partners. DFID will work with both consortia to help them devise more realistic forecasts in future, and during the first year continuously review these forecasts.

Some partners have experienced delays in obtaining ‘No Objection Certificates’ (NOCs), which allow access to areas such as KP/FATA. Consequently, there have been delays in partners’ implementation schedules. Partner access remains a risk that will have to be monitored regularly by the programme team.

By having four Cluster/Working Group leads and co-leads in the two main consortia, DFID has ensured that lessons can be carried beyond just the scope of DFID-funded response, to the wider humanitarian community. The work of the Clusters feeds directly into DFID projects, ensuring that our response remains in step with sectoral developments.

Has the logframe been updated since the last review?

No – this is the first review of the programme.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Timely delivery of appropriate relief in the immediate aftermath of disasters
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 % programmes based on coordinated needs and/or vulnerability assessments	0.70 (70%)	100% All responses so far have been based on coordinated needs assessments / (A+)
1.2 Time taken for DFID partners to deliver assistance	2 months	Floods in Sindh – 2 months / Earthquake – 2 month / Flash floods – 4 months / (A)

Key achievements :

Indicator 1.1: FAO and WFP are co-cluster leads for the Food Security Cluster (FSC), and though both are in different partnership arrangements with DFID – FAO through the Natural Disasters consortium, and WFP through a standby arrangement. However, during both the flash flooding in KP, and the subsequent earthquake in the same area two months later, they conducted a number of joint assessments, which led to better evidence for both DFID projects, and will allow synergies between the responses.

Indicator 1.2: Within a few weeks of bringing on board programme partners, Pakistan was hit by monsoon floods both in Sindh and with flash flooding in areas of KP. Immediate response was initially slow due to contracting/MOU issues, but all partners were able to carry out coordinated needs assessments within the first two weeks, despite some access restrictions to earthquake-affected areas. This was due to most of the DFID consortia partners also being active members of the Cluster system, and to pre-existing partnership arrangements with other humanitarian actors.

Delivery of assistance for flash floods in Chitral was initially constrained, with a limited pool of local organizations with the access, local knowledge and the requisite experience to take the response to scale. Nearly all response in the area by donors/actors was heavily dependent on two local NGOs (Focus, and the Aga Khan Development Network). In addition, the flood was followed closely by an earthquake, resulting in the response being both critical and complex. Areas where clearing of flooding debris had already taken place, immediately became inaccessible once more as a result of multiple landslides.

Despite this, DFID was able to scale up the ongoing flash flood response in the north, to include life-saving activities related to the subsequent earthquake, given that the same populations were affected twice. With the WFP Standby Arrangement already in place, DFID funding was able to reach those affected faster, while also complementing the Natural Disasters consortium’s response. This also allowed for a more joined-up approach and will assist in early recovery activities.

For the floods in Sindh and Punjab, DFID has reached 12,550 families with a combination of shelter/NFI kits and standard roofing kits, as part of the emergency response phase. In addition, the Natural Disasters consortium is finalizing distribution of modified roofing kits and winterized NFI kits for 1,500 families for those affected by the flash floods in Chitral. Earthquake response is ongoing, with relief interventions planned for 18,000 families. All of these response were mounted within a two to three month period.

Recommendations
Ensuring flexibility in humanitarian programming. The three recent emergencies have demonstrated the need for flexibility both in programming and in the way that milestones are captured. The Natural Disasters consortium was specifically set up to be able to flex during emergencies, to allow a scaled-up response. However, this will naturally lead to some difficulty in reaching certain milestones (especially those related to early recovery) while an emergency is ongoing. To address this, DFID will be continually reviewing the indicators with partners to ensure equal focus on early recovery and emergency activities.

More attention will be needed to ensure that the good practice that DFID partners are rolling out can reach a wider humanitarian audience. With DFID’s Natural Disasters consortium consisting of three global- and Pakistan-level Cluster/Working Group leads, it is important to capitalize on this for both sharing of good practice, and a clearer understanding of the prioritisation of needs from within the Clusters. So far, IOM has started to demonstrate good initiatives with the updating of the Shelter Working Group guidelines for earthquake-resilient shelters and how to prioritize winterization needs.

Closer links between WFP and the Natural Disasters consortium are envisaged such that DFID’s responses are better harmonized through the different partnerships, including on cash transfers specifically. With FAO being both a member of the Natural Disasters consortium and a co-cluster lead on food security with WFP, a natural link between the two components already exists. During the next year, this link will need to be strengthened, as well as ensuring that all partners are in the Cash Working Group, with parameters for standardized responses agreed upon.

Advocacy on access and humanitarian principles. The ability to respond rapidly will always be contingent on access permission and the provision of NOCs from the authorities. Through using local partners with experience in the area and of the communities, DFID can mitigate some of these delays, but we need to continue to ensure that the main partners in the consortium can also have access in order to monitor projects. This will require continued advocacy by the consortium themselves with the authorities on access, as well as for DFID to be continually aware of any challenges and raise them through the appropriate fora.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Integrated post-disaster recovery supported that restores living conditions and reduces vulnerability to future shocks
Output number per LF		2	Output Score	C
Risk:		Low/Medium/High	Impact weighting (%):	30%
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
2.1 Number of people living in rebuilt houses that are more resilient to disasters	148,879	0 – in progress / (13,750 families (85,000 people) across Pakistan have received shelter/NFI kits [B]
2.2 No. people accessing durable safe drinking water systems	482,212	None to date [C]
2.3 No. people with access to sanitation services	482,212	None to date [C]
2.4 No. people receiving appropriate livelihoods support that assists their recovery	46,869	4,000 families (24,000 people) / (+60,000 people supported with emergency cash assistance during returns) [A]

Key Points
Indicator 2.1: Although no houses have been rebuilt with DFID funds yet, 13,750 families have received modified shelter and NFI kits in response to the flash floods and earthquake in Khyber Pakhtunkhwa. As the earthquake happened shortly before the arrival of winter, these emergency winterization kits were deemed the most feasible in the short window of time available. Elements of the kits will be integrated in the resilient shelters that are planned for spring 2016, and have thus been included in this early recovery output.

Indicator 2.2: Due to floods and earthquake, all planned early recovery activities for those affected by previous emergencies were postponed. These activities will now take place in the first quarter of 2016.

Indicator 2.3: Nothing to report at this stage. As above

Indicator 2.4: As of the reporting date, 4,000 families (around 24,000 people) have received wheat seed packages, which consists of one bag of wheat seeds and fertilizer, along with a half-day training on planting methods. This will be supplemented in the spring, as the roads to the affected areas are no longer passable due to the winter weather. For livelihoods, there have been limited chances for early recovery programming, due to the short timescale since the signing of MOUs. The focus of the indicator will come through Pillar I (FAO within the Natural Disasters consortium), Pillar II (IRC through the protracted displacement consortium, and UNDP and FAO through the Joint UN support to the FATA R&R Strategy).

In addition, through the Bridging Strategy funding to ACTED over the winter of 2014/15, DFID was able to reach 10,030 displaced families with cash assistance, to provide for immediate needs. The project reached all intended beneficiaries, but identified specific challenges. These included the need to balance transparency with the local officials with the requirement for confidentiality of the beneficiaries selected at the local level[1], logistic issues around disbursements of cash including limits on total monetary assistance that the State Bank of Pakistan allowed for each household.
[1] Several instances were reported of community leaders demanding payments from the beneficiaries, and were collecting identity cards from beneficiaries. This resulted in further outreach by ACTED to ensure that only those selected were able to pick up their payments.

Under the IOM-led consortium of Pillar I, integrated recovery is planned to start in early 2016, to provide technical support for the rebuilding of 10,000 homes damaged or destroyed by the flash floods and earthquake in northern areas of Khyber Pakhtunkhwa. As of the reporting time, consultations are underway with the Heritage Foundation (a Pakistan-based organization focusing on sustainable architecture) to develop realistic models for earthquake-prone areas, which will enable resilient homes to be built with local materials. A pilot will be rolled out, with an initial phase of 500 houses, and should become the model for the remainder of the early recovery work in KP during Spring 2016.

Summary of responses to issues raised in previous annual reviews (where relevant)

n/a

Recommendations

More innovation is required from the partners to ensure integrated emergency and recovery response – e.g. emergency shelter kits that will later form part of the long-term shelter. With three humanitarian disasters (monsoon floods, flash floods and earthquakes) having occurred shortly before the reporting period, planning is still ongoing for the roll-out of most of the early response components of the project. Part of this can be met with ensuring funding for pilot projects, and making sure DFID continues to have relevant expertise on board to assess the feasibility of new models of shelter (this is already underway with the Heritage Foundation pilot for Chitral earthquake-resilient shelters).

The lessons learnt by ACTED during the difficult cash transfer programme for 10,030 families is important going forward for both the Natural Disasters consortium and the Protracted Displacement consortium. The challenges presented during this project will be similar in future programming, and DFID is encouraging both consortia to take on board the lessons, and consider practical means of overcoming them for future response. With a global lean towards increased cash transfers in emergencies[2], it is vital that the programme overall understands the complex environment for disbursements, and also the opportunities that cash represents for families. DFID Pakistan is encouraging all partners to consider cash as the default mechanism during emergencies following clear analysis of its feasibility, due to research findings that cash (as compared to in-kind aid) is emerging as more efficient to deliver, and resulting in better value for money[3]. In addition, cash allows for flexibility, dignity among beneficiaries, and recognizes the right of individuals to decide their priority needs. There are several limitations on the use of cash, however, which will be built into the programming, and based on conclusions and good practice from the Cash Working Group. This includes the need for strong understanding of markets, and mitigating vulnerabilities (e.g. following natural disasters in Pakistan, there has been some evidence of landlords insisting that cash transfers be used to repay existing debt, thereby not allowing families to address their immediate needs).
[2] In preparation for the World Humanitarian Summit to take place in March 2016, DFID has funded report of the High-Level Panel on Humanitarian Cash Transfers. The Panel has concluded that more unconditional cash transfers need to be considered, and for cash to be the benchmark against which in-kind aid is measured.
[3] In preparation for the above research, studies from humanitarian programming in three countries concluded that, “the flexibility of cash to provide access to a range of goods and services means that it is uniquely placed to enable VfM gains in the humanitarian system.” See footnote 7, below

With livelihoods and food security, DFID will encourage partners to include disaster risk management elements, including the (re)introduction of new resistant seed varieties and more work with Farmer Field Schools that provide outreach.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved access to humanitarian assistance and protection services
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 No. people supported with preventative and responsive protection activities	12,000	No activities to date / (C)
3.2 No. of VAWG (Violence against women and girls) incidents reported where services exist	No baseline/milestone	No data as of reporting time / n/a
3.3 Time taken for the Pakistan Humanitarian Pooled Fund action from submission to delivery of high quality projects	4 months	On-track (see below) / (A)

Key Points
Indicator 3.1 - During the inception phase, the IRC-led consortium on response to protracted displacement, has focused on defining priority areas for protection interventions. This has included a review of existing protection programming, key gaps and geographical needs. To this end, two new staff have been hired by IRC (starting in December 2015) who will elaborate and roll out new guidelines for psychosocial spaces for people in displacement, and be shared as good practice through the Protection Cluster. The IRC has faced delays due to access restrictions. These are both expected to be resolved within a month.

Indicator 3.2 – The IRC-managed IDP Vulnerability Assessment Profiling (IVAP) is still in its inception phase, with a new profiling exercise set to take place in February 2016. This will be able to track some of the progress on this milestone. In addition, through the protection activities of the Pillar II Protracted Displacement consortium (also led by IRC), data on VAWG will be tracked in its areas of operations.

Indicator 3.3 - The new UN Pooled Fund mechanism (PHPF) has already shown itself to be more strategic and timely than under its previous form. In mid-2015, the Pooled Fund mechanism underwent a major change (from the ERF – Emergency Relief Fund) to the PHPF, based on a global review within OCHA. This resulted in two standard allocations throughout the year, and a clearer link to the priorities defined in the annual Strategic Plan. The first new standard allocation was in October 2015, with the call for proposals underway in November, through the Clusters and disbursements expected within the four month milestone timeframe. Previously, DFID had raised concerns over the overall functioning of the pooled fund (then called the Emergency Relief Fund - ERF), due to the time taken between the decision for a distribution and the disbursement of funds, along with lack of clarity on the overall strategic objectives of the ERF. The new mechanism – the PHPF –represents a positive change in that it is clearly linked to the broader strategic response plans, and with the pre-defined partnership in place, will allow for a more rapid disbursement of funds. While this has yet to be tested, progress demonstrates that the logframe target is on-track to be delivered.

Summary of responses to issues raised in previous annual reviews (where relevant)
None

Recommendations
Work closely with all partners to ensure that protection concerns are mainstreamed throughout all projects, with specific focus on ‘do no harm’ approaches to aid delivery, and that all data is age- and gender-disaggregated.

Continued active participation in the PHPF Advisory Board, and representation at UN-led donor meetings to ensure PHPF meets its targets overall, and that the new Country Operations Guidelines form the basis of all PHPF implementation. DFID will also pay specific attention to the monitoring capacity of OCHA over PHPF projects, with an eye on ensuring that all projects are funded in a timely manner. DFID Pakistan will also increase its engagement at the global level, through CHASE advisers working with OCHA in New York, to raise any specific issues on overall country-level pooled funding

Continued chairing of the Good Humanitarian Donorship (GHD) forum, which brings together a dozen donors, This will allow for better scope on issues related to the overall functioning of the in-country UN system, and which relate to the PHPF.

As previously referenced, the logframe targets require revision, and apply to Indicator 3.2 above. While the programme has an overarching protection objective, including on mitigating violence against women and girls, this indicator does not adequately address what can be measured from within the specific projects. As such, this indicator will be adjusted in line with DFID’s commitments on gender equality, and based on targets for which the programme can be accountable, with advice from DFID gender experts.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved coordination and technical design of humanitarian projects
Output number per LF		4	Output Score	B
Risk:		Low	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
4.1. % of DFID partners innovating and testing new designs and approaches that are better VfM	20%	20% [B]
4.2 No. of technical trainings and capacity-building workshops attended by local NGOs and other civil society actors	0	0 [C]
4.3 No, of research and innovation projects undertaken by DFID Pakistan	3	0 [C]
4.4 % of partners attending coordination meetings which involve all local stakeholders	60	100 [A+]
4.5 % of DFID partners with well-designed beneficiary feedback mechanisms in operation	100	20% [B] (one of our five partners are integrating innovation into current projects)

Key Points
- Indicator 4.1: Through the Natural Disasters consortium, a pilot is planned to test earthquake-resilient shelters in Chitral. This will be carried out by the Heritage Foundation, and will have a roll-out of 500 shelters. At present, the funding arrangement for this are in the final stages, and already volunteer architects are visiting the affected areas, to start looking at design options. DFID Pakistan can also rely on our expert Shelter Consultant (through CHASE OT), to help assess the feasibility of the options. Based on the design and the DFID analysis, the pilot could be scaled up to cover all 10,000 households who are already targeted for emergency winterization and shelter kits. Though it is too early to establish VfM metrics, by its nature, the pilot will result in better VfM, due to the shelter designs being based on rebuilding with existing materials from damaged houses, and being built by the beneficiaries themselves based on DFID-funded resilient designs to break the cycle of rebuilding vulnerable shelters.
- As referenced under Indicator 2.4 above, DFID is in communication with FAO for including more innovation in their early recovery activities for the spring. This is already in the pipeline, but due to season-dependent planting, cannot yet be distributed.

Indicator 4.2: None was planned to date. With the partnerships in place for only six of the twelve months of the programme cycle to date, no trainings were anticipated, but are instead one of the planned activities for the first quarter of 2016 (that is, one year three months after approval of the Business Case). The indicators overall have not been able to reflect the necessary time for either setting up the partnerships, nor the inception phase of each project. These will be rectified by the next annual review.

Indicator 4.3: As above.

Indicator 4.4: All partners within the natural disaster and the protracted displacement consortia are active members of the Cluster systems. Furthermore, these include four Cluster/Working Group leads, who have a global- and Pakistan-level mandate to coordinate with all stakeholders. This includes UNICEF (Cluster lead for Education, Nutrition, WASH), WFP & FAO (co-cluster leads for Food Security), IOM (Shelter Working Group lead), and IRC (Protection Cluster co-lead).

- Indicator 4.5: Both consortia (IOM and IRC) are in the final stages of defining their beneficiary feedback mechanisms, to be rolled out in early 2016. However, for all ongoing and completed responses to floods and earthquakes, mechanisms have been built into the projects.
  - For the ACTED support to displaced populations (under the Bridging Strategy), an independent ACTED Appraisal, Monitoring and Evaluation Unit (AMEU) monitored the project throughout its implementation. A dedicated accountability mechanism was established, through which beneficiaries, stakeholders, and the local population could register comments and complaints to ACTED, independent of the project staff.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendations

1. Continue to use the technical expertise of the CHASE OT consultants, to ensure the best innovative approaches to programming, on WASH, shelter and livelihoods during the roll out of all programmes. Given their strong working knowledge of both the context in Pakistan, and the capacities of the individual partners, this will remain a valuable asset within the programme for the first year of implementation, and ensure that all options are feasible and in line with our programming.
2. Conduct regular reviews of different models of beneficiary feedback mechanisms with partners, to ensure that good practice is shared among the different partners, and that all information feeds into better programme design overall.
## D. VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The main cost drivers in humanitarian programmes will be the assistance distributed (both in-kind and cash transfers). During the reporting period, the key costs have related to the assistance, however, due to the partners mostly being in the inception phase, this cost has not yet been quantified, but will be monitoring during the programme cycle.

The Business Case identified three other keys cost, which were anticipated to affect overall price in the programme:
- Security: Given that the security situation in Pakistan remains volatile, insecurity increases the ratio of administrative to implementation costs. However, this has not been a major contributor to the overall costs charged by all partners in the programme this year as the security situation has been relatively stable in most parts of the country.
- Transport: Some areas of humanitarian need are hard to reach / difficult terrain, particularly in FATA and Baluchistan. This year, the flooding in Chitral has resulted in distribution costs going up for partners under the Pillar I Natural Disasters consortium. However, the transport of staff and supplies is not categorized as a major cost element of the programme this year.
- Insurance and fraud prevention: whilst this has not been explicitly calculated, it is assumed that the cost of insurance for goods and staff will be high in Pakistan. No instances of fraud or corruption under this programme have been reported this year however it is recognised as a risk that needs to be actively managed.

VfM performance compared to the original VfM proposition in the business case

Since July 2010, DFID Pakistan has worked in most of the currently planned programming areas and continued to collect VfM data in the main sectors. Some VfM gains have been made, mostly related to minimising unit costs of inputs (improving economy) and outputs (improving efficiency). As in all humanitarian aid, outcomes and impact were difficult to measure, and so were the related VfM metrics. However, in some sectors such as WASH and livelihoods, it was possible to go further and calculate cost benefit ratios based on outcomes achieved. Within the four components of MYHP, multiple interventions were planned and for the most relevant ones, six separate sector appraisals were carried out at the Business Case stage using cost benefit analysis, cost effectiveness analysis or unit cost analysis (depending on data availability), as well as more qualitative assessments of expected benefits while mainly relying on information available from previous support.

The methodology used for appraising sector interventions individually did not take into account the benefits and cost-savings of cross-sector working. Instead, to illustrate VfM in cross-sector working at business case stage, its costs were set against implementing the three typical early recovery interventions separately and against the cost of cash transfers.[4]
[4] “Recovery cash transfers” is included because it was the largest single recovery investment following 2010 floods, costing around $1bn, including both Government of Pakistan (GoP) and donors investments. The GoP has stated its intention to use cash transfers as a recovery mechanism in the event of future disasters, which already has the tacit support of World Bank and other donors.

Recovery options: unit costs per family
Cost per family in £ GBP

The economic appraisals of the different sectors indicated that an integrated relief-recovery approach contributing to resilience can be more cost-effective than repeated humanitarian relief interventions[5]. Now that some of the programme components have just started delivering (while some are in inception), the significant additional benefits identified in some sectors need to be closely monitored and quantified at the earliest to enable greater prioritisation of sector interventions in the outer years. The investment in research for the next four years will need to do this and build up the evidence on the VfM of integrated approaches and the best returns on investment.
[5] For example, under the Predictable Humanitarian Emergencies Programme (PEP), closed in November 2015, one of the implementing partner (HANDS) was able to provide both emergency shelter (relief) and flood-resistant shelter (recovery) to the same group at a unit cost of £150, as the main elements of the emergency shelter were reused in building flood-resistant shelter. This was 100% cheaper compared to the unit cost of £300 incurred by other partners in providing flood-resistant shelters. The approach used by HANDS suggests that an integrated relief-recovery approach can lead to achieving certain cost efficiencies.

Some of the metrics, unit costs of inputs and benefits streams identified in the sector appraisals can be used as baselines, but with a word of caution that these unit costs were estimated on a retrospective basis and may not have fully captured the costs (particularly the administrative costs associated with delivering each input by different partners). Please see Annex A[6] for details on how this information can potentially be used to monitor and achieve VfM.
[6] Annex A provides a sample VFM template that needs to be incorporated in the regular M&E framework agreed with implementing partners to allow systematic collection of data, regular reporting and allow any course correction if needed. This information needs to be captured and linked up with the evidence sharing and learning platform planned under this programme.

Assessment of whether the programme continues to represent value for money

Within Pillar I, the partners have been able to deliver a livelihoods-focused response during the emergency phase for the flash floods and earthquake in Chitral. So far, 4,000 families (around 24,000 people) have received wheat seed packages, which consist of one bag of wheat seeds and fertilizer, along with half-day training on planting methods. There has been no data made available on costs to allow for simple unit cost analysis, as the procurement and distributions occurred two weeks prior to the annual review completion.

Additionally, through the Bridging Strategy, 18,000 internally displaced families (or 108,000 IDPs) received winterization kits and cash assistance. The total amount disbursed to the two implementing partners (IOM £500,00 and ACTED £2m) stood at £2.5m. Based on the information received from ACTED, over 10,000 people participated in sensitization sessions on WASH, nutrition and DRR, and benefitted from conditional cash grants at a unit cost of £123[[2]]. The amount of the cash assistance was based on general market assessments, taking into account the costs of a core food basket[7] and average rents for IDPs. The three disbursements aimed to cover up to six months of need among the targeted population.
[[2]] Actual take home cash provided was £73 per family, while the remaining cost was associated with organising and delivering trainings.
[7] Humanitarian good practices call for food baskets to be based on 2,100 calories per day.

The potential for Value for Money gains of cash are particularly evident when cash is considered as a multi-sector tool with a wide range of benefits. The goods and services that households access as a result of cash transfers vary between households and span different aid sectors – results that would be difficult or impossible to replicate via in-kind assistance. The specific outcomes of the intervention depend not solely on the transfer but also on the context, programme design and implementation, including targeting and programme quality.

As cash enables receiving households to use assistance according to their own capacities, risks and opportunities, a case can be made that cash has the potential to support the resilience of households to manage shocks. The link between cash transfers and resilience, however, is a hypothesis that needs to be tested, and will be one of the unique pieces of research commissioned through the Pakistan Evidence and Learning Platform (PELP) of this programme, once it is operationalized.

The flexibility of cash to provide access to a range of goods and services means that it is well-placed to provide VfM gains in the humanitarian system. This is not to suggest that cash is always a preferable and more appropriate transfer, but rather highlights the significant opportunity for expanding the use of cash, and investigating the political and institutional frameworks required to allow increased use of cash.

Overall, since some of the partners have been selected or are being procured, it is critical to set up a single VfM (preferably embedded in the M&E framework) tracking template. As mentioned earlier and sampled in Annex A, the team needs to use some of the business case proposals as baselines and anecdotal evidence used to allow meaningful monitoring of the unit costs and identification, quantification and monetisation of benefit streams to allow assessment based on benefit cost ratios.

Recommendations:
A single VfM tracking template, which is linked up with the CHASE database, needs to be agreed with all implementing partners. It will be more efficient and effective if this template is embedded in the regular M&E framework to allow systematic collection of data, regular reporting and allow any course correction if needed. This information needs to be captured and linked up with the evidence-sharing and learning platform (PELP) planned under this programme[8].
[8] The PELP is still in procurement stages, and is the link between the humanitarian and resilience programmes for sharing evidence and lessons in both programmes

Ensure that the research components of the PELP are able to focus on improving the measurement of outcomes and cost effectiveness of cash transfers

Quality of financial management

DFID has engaged with six partners to date to implement the project:
1. ACTED- Accountable Grant for Complex Emergencies Bridging support;
2. IOM- (i) MOU for Complex Emergencies Bridging support, and (ii) Natural Disasters consortium;
3. IRC- (i) Accountable Grant for RELIEF consortium and, (ii) IVAP;
4. UN OCHA- MOU for Pakistan Humanitarian Pooled Fund
5. UNDP- (i) Standard Administrative Arrangement for Joint UN community Resilience and, (ii) recovery support to FATA IDPs
6. WFP- (i) Contribution Agreement for Joint UN community Resilience and, (ii) Standby Arrangements for Disaster Preparedness, Response and Recovery support to FATA IDPs.
Component	Component name	Total Budget for Lifetime of Programme – 4 years [£]	Total spend to date [£]
204603-101	CHASE OT & Surge Staff	£300,000	£17,145
204603-102	ACTED- Complex Emergencies Bridging support	£2,000,000	£2,000,000
204603-103	IOM- Complex Emergencies Bridging support	£500,000	£500,000
204603-104	IOM- Natural Disasters Consortium	£29,000,000	£3,662,795
204603-105	IRC-RELIEF Complex Emergencies Consortia	£8,000,000	£534,168
204603-106	IRC IVAP	£1,657,937	£110,228
204603-108	WFP joint UN community Resilience and recovery support to FATA IDPs	£2,000,000	£1,000,000
204603-109	UNOCHA- Pakistan Humanitarian Pooled Fund	£9,700,000	£2,000,000
204603-110	Pakistan Evidence and Learning Platform + Third party monitor costs	£4,000,000	Under procurement
204603-111	Contingency/unpredictable emergencies funds	£14,842,063	Contingency
204603-112	WFP- Standby Arrangement for Disaster Preparedness, Response and Recovery	£20,000,000	£1,000,000
204603-113	UNDP [FAO, UNICEF]- Joint UN community Resilience and recovery support to FATA IDPs	£8,000,000	£4,000,000
	Total	£ 100,000,000.00	£ 14,824,336.00

Despite initial delays in setting up these partnerships, the programme recovered momentum and spending picked up once the agreements were finalized. A breakdown of spend to date by partners is as follows:

Most of the projects are still in inception phase and most partnerships are less than 6 months old therefore detailed financial reports or audits are not yet due from all partners. However, DFID will continue to monitor the financial reports received in the coming months and closely scrutinize these to ensure spending variances are managed.

Bridging Support funds [ACTED and IOM
ACTED [£2m] and IOM [£500,000] have been able to meet their budget commitments for activities under the short-term bridging support grants to meet immediate needs of IDPs. Financial reports show full utilization of DFID’s funds with around 70% of the spend under both programmes committed to direct  project related costs, as outlined below

		ACTED	IOM
Project costs		1,430,086.99	384,650.74
Support costs		439,072	82,639.25
Indirect support costs [7%]		130,841	32,710.30
Total budget		2,000,000.00	500,000.00

Natural Disasters consortium [IOM, ACTED, HANDS, FAO, UNICEF]
For the Natural Disasters consortium, DFID signed the MOU with IOM as the lead administrative agent in July 2015 and the first tranche was released in September 2015. The first quarterly financial report  received by DFID in November 2015 shows slow spending by all partners in the consortium during the first quarter [July-September 2015], with the spend totalling 46% of the initial tranche amount of £2.02m to date.  We expect spend to increase in line with the profiled amount over the next quarter as the projects mobilise following the inception period .

With the floods and earthquake hitting Pakistan in the opening months of the programme, the preparatory activities planned for this time (prepositioning of stocks; capacity mapping of local implementing partners; development of joint assessment tools etc.) have not taken place as planned by the consortium during the proposal stage and the focus has been primarily on flood response. It is worth noting that 31% of the total spend in the first quarter by the consortium is on shelter related activities. There has been no spend in the WASH or livelihoods sector mainly due to the consortium experiencing delays in mobilization due to contractual issues faced by IOM in bringing FAO and UNICEF on board during the first quarter.

To date, the consortium’s total expenditure remains at £2,474,696, which includes commitments amounting to £1,544,985. To note, the majority of the commitment value relates to procurements currently being delivered to project partners.

Spending by all consortia partners is expected to pick up in the second quarter of the programme as multiple activities are planned under Shelter, WASH and Food Security/Livelihoods (FSL) in response to the earthquake in KP.

RELIEF consortium [IRC, ACTED, HelpAge] and IVAP [IRC]
IRC and DFID signed their agreements for the RELIEF and IVAP projects in August 2015 and DFID paid the first quarterly tranche to IRC in September 2015. Spend under the RELIEF project has been slow in the first quarter with only 20% of £534,168 disbursed being spent during the first quarter [August to October 2015]. This is due to the lengthy process for IRC to sign its contracts with ACTED and HelpAge under the RELIEF project, which has delayed start-up of inception phase and on ground activities. The Government of Pakistan’s new policy for INGOs has also affected the ability of consortia partners to get ‘No Objection Certificates’ (NOCs) allowing them to travel to affected areas. As the result, the budget forecast for the second quarter on the RELIEF project has been revised down by 85%.

Pakistan Humanitarian Pooled Fund (PHPF) [UNOCHA]
DFID released its first tranche of £2m to UN OCHA in September 2015, immediately after signing the MOU. In the Advisory Board meeting held in October 2015, UN OCHA announced the fund allocation for 2015 of $5m from DFID and Swedish International Development Agency (SIDA) allocations. This has been divided between a standard allocation of $4,750,000 to support the IDP return process in FATA, along with a ‘reserve’ allocation of $250,000 for unforeseen events.[9] Funds for the standard allocation are expected to take place in December 2015.
[9] Whereas the standard allocation is directly linked to the prioritization as defined in the HCT annual Strategic Plan, the ‘reserve’ sits directly under the Humanitarian Coordinator and is to be used in emergencies, with advice from the Humanitarian Country Team.

Joint UN community Resilience and recovery support to FATA IDPs [UNDP, UNICEF, FAO, WFP]
DFID released the first tranche of £4m to UNDP on 11 November, 2015 and £1m to WFP in September. On the ground implementation is yet to begin, hence it is too early to comment on funds utilization by partners.

Standby Arrangement for Disaster Preparedness, Response and Recovery [WFP]
DFID has released the first tranche of £1 in November related to a joint flash flood and earthquake response in Chitral by WFP. On the ground implementation is yet to begin, hence it is too early to comment on funds utilization.

Date of last narrative financial report	12 Nov 2015 [IOM], 18 Sept 2015 [ACTED]
Date of last audited annual statement	Not yet due – partnerships less than 6 months old

E: RISK (½ page)

Overall risk rating: Medium

The MYHP programme has recently started, implementing partners are mobilising resources and there have been delays in implementation, in part due to consortia administrative and contractual issues, as outlined earlier within this review. Access issues remain a Medium/High risk. Other key risks at this stage include:

Volatile security environment - insecurity varies considerably across the region. Partners have protocols which allow them to operate much of the time based on negotiated access, staff localisation and low visibility operations. This leads to challenges when technical skills or monitors are not available locally. All implementing partners have experience, however, of working in a variety of hazard-prone areas, including the parts of Baluchistan and KP/FATA that are affected by complex emergencies. Furthermore, we will ensure that the budget exists for using third party monitors in order to capture information relating to interventions where access is an issue.

Humanitarian space becomes further constrained and access becomes more difficult for partner agencies. From experience with the recently-completed Predictable Emergencies Programme, registration of non-governmental organization, along with project and travel NOCs remains the biggest constraints on partners in KP/FATA. All non-governmental organizations are reapplying for registration through the Ministry of Interior in line with the new Government of Pakistan requirements. Some having made the decision not to work in more sensitive areas of the country (such as KP, FATA and Baluchistan). There is a risk that this could lead to a smaller pool of operational partners in these key areas. Our implementing partners have a strong track record of acquiring project NOCs when required. Partners have also confirmed that in cases where direct implementation is not feasible or ‘in-house’ access difficulties exist, they can draw on existing partner networks to implement accordingly.

Lack of humanitarian leadership and capacity - despite sustained DFID engagement with the UN leadership to improve its delivery, including through a faster ERF, significant improvement to in-country UN leadership is still evolving. OCHA has now developed a new pooled funding mechanism known as the Pakistan Humanitarian Pooled Fund (PHPF), which we hope will improve country-level operations, knowledge-sharing and coordination of activities with the Cluster System. In addition, DFID is a vocal advocate in relevant UN forums for improved leadership, and a more strategic response to crises across Pakistan.

Risk of corruption/ diversion of resources - there are two remaining live allegations of fraud relating to the predecessor humanitarian programme, PEP. We have worked closely with CFU/IAD, and internally as a programme team, to investigate these cases, and are in the process of concluding actions to take. The lessons learned will feed into a series of mitigating action we will take during project inception and programming, and allow better tracking of potential diversion of resources during the entire project cycle.

Government leadership - for Pakistan, the military and the civilian counterparts are the clear first responders in all disasters, and as a sovereign nation they meet the needs of their citizens themselves. Challenges, however, remain in terms of coordination both within the government response and between the authorities and the UN system. Whereas the UN has a clear mandate for coordinating the response to conflict-induced displacement in KP/FATA, the Cluster system has not been mandated by the authorities to coordinate activities in natural disasters (since the 2010 floods). To this end, DFID is an active participant in the relevant coordination fora (the UN donor meetings, the Pakistan Humanitarian Forum, government-led conferences and workshops) to have the clearest view of the needs and challenges.

Pakistan requests for humanitarian assistance - Many of UN agencies have not been able to launch a significant response this year due to the Government of Pakistan not requesting formal assistance following the natural disasters. This has constrained potential funds from several donors whose internal mechanisms – unlike DFID – only allow for a response following a Federal-level request. For the earthquake, the National Disaster Management Authority (NDMA) has stated that the current government-led response has sufficiently addressed the immediate needs of the affected population. The relationship between the NDMA and the PDMAs, however, remains a challenge for DFID, in that while the NDMA has not requested assistance, the PDMA for Khyber Pakhtunkhwa has called a donor conference[10] to help address the needs for people affected by the earthquake, which has been the impetus for DFID response. DFID maintains strong relationships with both the national- and provincial level disaster management authorities, to have a clearer picture of the overall needs, and to ensure transparency of its programming objectives with all the authorities of Pakistan.
[10] The donor conference is called for 10 December, 2015 (after publication of this annual review), and will be chaired by the Chief Minister of Khyber Pakhtunkhwa

Further details on our current risk and risk mitigations strategies are set out in the MYHP delivery plan which is updated regularly.

MYHP Delivery Plan – Programme and Project-level risk registers

Our programmatic tools for capturing and recording risk are sound. We have risk/issues logs that individual partners maintain and send to us on a monthly basis. Templates have been standardised and we feed these issues/risk logs in to our delivery plan. The project-level risks are assessed and then our overarching MYHP risk register is updated accordingly.

We have started a new regime of assessing programmatic risk and pinch points in quarterly meetings including with partners, promoting discussions on risk as a whole programme team, and resulting in risk evaluations. These evaluation are ranked by level of risk, for ease of reference and to promote discussion around the priority areas. The results of the discussion are disseminated with actions to the wider team, and recorded within the delivery plan.

 The link to the latest quarterly risk evaluation is included.

Risk of Funds not being used as intended

Due to the nature of some of the areas targeted as part of this programme and the associated security constraints (e.g. FATA/KP and Baluchistan) remote management and monitoring and evaluation will be required.

In those areas that are more accessible, we will conduct our own field monitoring visits, the reports from which will feed in to the programme lifecycle and reporting e.g. lessons learned, flagging risks, assessment of outputs and an opportunity to feedback directly to implementing partners in the field.

Delivery partners provide the first line of protection for DFID funds, and we have communicated expectations of DFID’s zero tolerance of fraud and corruption to partners. Furthermore, we have conducted thorough due diligence assessments and clarified DFID requirements and expectations into contractual obligations. Field monitoring visits and third party monitoring reports will provide additional assurance that funds are being used as intended.

Through PELP, third party verification  in the form of spot checks and beneficiary feedback are to be commissioned. The spot checks would enable the programme team to acquire timely information on field-level activities while the beneficiary feedback survey will prove to be a useful source of information on project performance, empowerment and accountability to beneficiaries. Collectively these tools will help provide an objective assessment of programme performance and allow for improving effectiveness of interventions.

Fraud Risk Mitigation
There have been allegations of fraud relating to a previous humanitarian programme (PEP). Based on this experience, we have developed rigid tools in line with DFID best practice and guidance, and in conjunction with DFID Counter-Fraud Unit (CFU) and Internal Audit Department (IAD) to assess cases of fraud in order to take the most appropriate actions.

Using our experience of these allegations and corresponding investigations, we will be able to improve our mitigation against fraud in the MYHP, employing systems that help us process allegations more efficiently and utilise the right level of support from IAD/CFU colleagues. An internal report that considers these factors will be produced following the completion of final PEP fraud investigations.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Formal approval for the MYHP programme came in December 2014. Immediately after the approval, DFID established short-term partnerships with ACTED and IOM to meet immediate needs of IDPs in KP/FATA under Pillar II while the longer-term partnerships were being established. An Accountable Grant was signed with ACTED in January 2015 to deliver a cash-based response to IDPs in KP/FATA and a short-term MOU was signed with IOM in March 2015 for provision of non-food items to vulnerable IDPs of KP/FATA. No-cost extensions had to be granted to both partners due to the delays in completion of activities resulting from delayed NOC approvals with the government. The projects were completed in July 2015 and October 2015 respectively and have met their targets..

The selection of a consortium under Pillar I started in March 2015. Negotiations and due diligence assessments were conducted in a rapid timeframe to allow an MOU to be signed with the IOM-led Natural Disasters consortium in July 2015 and they were the first major partners to come on board under this programme. The timing of when DFID signed this partnership ensured that the team had key partners engaged prior to the monsoon flooding to allow for a rapid humanitarian response from DFID if needed. In addition, the team engaged with WFP to sign a Standby Arrangement on preparedness, response and recovery to natural disasters and UNOCHA on DFID’s contribution to the Pakistan Humanitarian Pooled Fund. Agreements with both were signed in September 2015 during the critical time period of major flooding in Chitral and Sindh. The speed with which these partnerships have been mobilised has been a significant success for the programme.

Although DFID met the timescales of bringing these partnerships on board during a crucial time, the pace of response activities expected from these partners has been slow. This is mainly due to administrative delays faced by IOM in bringing all partners under the consortium on board, particularly FAO and UNICEF. This significantly delayed the WASH and livelihoods response in flood-affected areas this year. Nonetheless, DFID has continued to engage with all partners and going forward the team would be conducting a lessons learned exercise to review how response from partners can be improved in future humanitarian emergencies.

Under Pillar II, DFID began the process for selection of a consortium in April 2015. The grant was signed with the IRC-led consortium in August 2015 following negotiations and a due diligence exercise. Again, there have been delays for the consortium to become fully functional and to start on the ground implementation. The major focus for the consortium in the first quarter [August – October 2015] has remained on developing guidelines and tools (specifically for community mobilization, beneficiary identification and preparation of field plans) while the interventions in the field will be initiated in the second quarter.

The agreement for the UNDP-led ‘Joint UN Community Resilience and Recovery support to FATA IDPs’ took longer than anticipated to sign with DFID. The delays had primarily to do with internal UNDP negotiations in signing their agreements with FAO and UNICEF, as both agencies had to revert to their respective headquarters around DFID’s reporting requirements for the project. These delays are anticipated as a one-off and DFID will continue to engage with all UN agencies on a regular basis to ensure effective coordination takes place with all partners and their headquarters throughout the project lifecycle. Although WFP is a partner under this joint UN consortium, a separate contribution agreement has been signed with the agency due to their existing PC1[11] with the Government under this programme and a direct partnership with DFID was found to be more suitable. The administrative issues within the UN agencies which the Team encountered have been fed back to DFID Whitehall, with the aim of resolving such delays by UN Headquarters in future joint programming for other country offices.
[11] This is a Government project proposal designation, which ultimately gives organizations lessened access restrictions.

The research and evidence pillar of this programme has experienced the greatest delays in mobilisation. This has been mainly due to staffing constraints within the DFID team. The team was able to secure time from an Evaluation Adviser to develop the ToRs for the programme by April 2015. However, the team then carried a gap of three months, during which, the additional time of a Social Development Adviser was secured to take a lead on this component. A decision has now been taken on the procurement route for the programme and the component is expected to start implementation by second half of next year.

Despite some initial delays in procurement, and setting up relationships, the team acknowledges the valuable time that has been invested in ensuring good governance structures have been established. Given that the consortia-approach is new for DFID Pakistan’s humanitarian programming, it is vital that these systems are correctly considered at the start of the programme, and the rewards will be felt throughout the life of the programme.

Performance of partnership(s)

One of the innovations in programme delivery under MYHP has been to set up consortia instead of having individual partners deliver individual projects. As part of this annual review, the team conducted a light touch exercise to review the performance of the consortia and below are some key lessons learned for DFID and some recommendations:

1. This is the first time that DFID Pakistan’s humanitarian programming has set up consortia that involve a mix of UN agencies and NGOs. A key lesson learnt is that the consortium leads need to ensure the HQs of all UN agencies are made aware of the discussions ongoing around DFID projects by the UN country team from the very beginning (i.e. during the call for concepts stage). This will streamline the procedures around legal matters and signing of these agreements once the project is approved.
2. During the inception period, DFID has seen less of an integrated multi-sector response from any consortium partly due to the delays in starting on the ground activities. The consortia therefore need to be advised accordingly on realigning their work plan and activities to ensure that all activities remain integrated as was DFID's expectation regarding programme delivery through these consortia during the call for concepts stage.
3. The consortia will need to be represented as cohesive units rather than individual projects. Often the budgets presented for various activities from consortium partners have not been uniform. Consortia leads need to ensure they are taking full accountability for downstream partner delivery.
4. Although the RELIEF and Natural Disasters consortia are both working on different project activities and areas of intervention, going forward more coordination can take place between these two consortia around learning and sharing lessons on applying an integrated multi-sector response. Using PELP to assess some of the synergies among Pillar I and Pillar II of the programme will be vital.
5. The original forecasts submitted by both consortia were over-ambitious. For example, UNICEF under the Natural Disasters consortium did not spend any money out of the first quarterly tranche disbursed to them. This was mainly due to the delays in signing the agreement with IOM and hence being unable to start any activities during the first quarter. Similarly, IRC also experienced delays in getting the contracts signed with the other partners resulting in almost no on-the-ground implementation. Continuous engagement with the consortia is required in ensuring the forecasts are robust and in line with the current pace of mobilization and emergencies. This is also important to ensure forecasts are robust to manage the spending pressures in DFID.
6. One of the strengths of the Natural Disasters consortium is that it comprises three Cluster/Sectoral lead agencies: Shelter, WASH and Food Security. In addition, IRC is able to capitalize its position as the Protection Cluster co-lead, to coordinate at the provincial levels. All partners are active members of the relevant coordination forums, including the IASC Clusters, the Pakistan Humanitarian Forum (PHF) and National Humanitarian Network (NHN), and Cash Working Group. This will allow for good practice from DFID projects having a natural outlet to the wider humanitarian community and lessons learnt to be integrated into our programming. In addition, through the Cluster leads, DFID will be able to capitalize on the advocacy opportunities that these fora represent, and encourage more coordinated responses overall. During the inception period, this has already been positively noted through the IOM-led Shelter Working Group, and their elaboration of new shelter guidelines for winterization, a key component of our response. Elements of the guidelines will now become standard practice by other shelter actors, leading to more cohesive and less disparity among beneficiaries.

Asset monitoring and control

DFID has ensured that all partners under the MYHP programme adopt DFID’s asset policy as covered under the Smart Rules. None of the partners have any assets to report as of now as most of the partnerships are in the inception period and key procurements are still underway. IOM and ACTED have not procured any asset above £1,000 and hence have no assets to report to DFID for their bridging support grants.

For the future, the DFID team will inform all partners to record all assets purchased using DFID funds in their asset registers and report these to DFID on a quarterly basis. Similarly, a schedule of asset spot checks on all partners will be developed along with a review of the procurement guidelines being followed by all partners to ensure VFM considerations are being followed by all partners.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Currently, the team is using the programme delivery plan as the primary monitoring tool to review programme performance. The consortia structure is a relatively new model for programme delivery, which the team continues to monitor through progress review meetings. A consortia performance review was conducted as part of this annual review to provide feedback on performance.

The PELP will further add to the existing evidence base for humanitarian programmes. As the PELP component is being commissioned jointly with the Resilience programme, one of its values will be to act as a bridge between both programmes, and therefore helping to overcome the false divide over the relief/recovery continuum. It will support research, monitoring and evaluation, capacity building, and will commission evaluations. PELP will create an evidence-based understanding of humanitarian and resilience issues in Pakistan and globally within the development/ humanitarian sector in general. This will also be useful for further testing the assumptions in the Theory of Change, and help identify priorities to aid better programming. This will help contribute to an effective dialogue with government partners, namely to elaborate disaster response strategies based on evidence, and be more accountable to its citizens.

Valid International have been contracted by RED and CHASE to run a multi-country evaluation of multi-year humanitarian and resilience programmes. They are expected to visit Pakistan in early 2016 and conduct an evaluability assessment of both the MYHP and Resilience Programmes. This will predominantly focus on VfM for multi-year humanitarian as compared to single-year financing through:
- operational cost saving (staff, procurement, proposal writing and currency risk)
- early action (speed of responses) predictability (pre-positioning of stocks, pooling orders, leveraging of additional funds, cost savings from long-term investments).

Monitoring progress throughout the review period

The team has continued to use the MYHP delivery plan as a key tool for monitoring the timelines for setting up of various partnerships and other key milestones, quarterly reporting issues and timelines, programme/partner risks and financial performance. Monthly review meetings with the partners have been held for stocktake, discussing challenges and solutions as well as identifying priorities. Due diligence assessments conducted prior to awarding grants/ MOUs, now serve as risk monitoring tools.

Weekly meetings have been held with partners during the 2015 flood and earthquake emergencies to get the most up to date information from partners, identifying needs of affected population and agreeing on activities for response.

All programme partners are in the process of developing individual project logframes. These are being quality assured by the DFID team as they will feed into the overarching MYHP logframe.

Other key monitoring systems that will be set up include :

- More formal third-party monitoring expected to begin next year through the supplier contracted under PELP.
- More evidence gathering through PELP allowing for better interactions across the various components of the MYHP programme, as well as the Building Disaster Resilience Programme.
- Independent evaluation of the MYHP conducted by VALID which will begin next year.

The MYHP overarching logframe should be regularly assessed throughout the programme lifecycle. Individual project logframes must also be relevant and must translate through into the overarching logframe. Thereafter, we will ensure a regularly periodic (quarterly) assessment of the MYHP logframe, especially when new projects and interventions start, and revisions to the logframe may be required. Ensuring the appropriate maintenance of the logframe across the programme lifecycle will lead to more verifiable and consistency in the final programme scoring assessment, and annual reviews.